## Sheet1
KENTUCKY TRANSPORTATION CABINET
DEPARTMENT OF HIGHWAYS
DIVISION OF CONSTRUCTION
FINAL ESTIMATE CHECKLIST
DATE:
CID: |  |  | DISTRICT: |  | CREW:
COUNTY: |  |  | PROJ.NO.
CONTRACTOR:
CONTRACT TYPE:
RUN TAPES AND VERIFY TOTALS ON LAST LOAD TICKETS FOR ALL ITEMS PAID BY WEIGHT.
RUN "INSTALLED WORK" REPORT IN SITEMANAGER TO VERIFY ALL DWRS HAVE
BEEN APPROVED FOR PAYMENT.
RUN "DWRALL" REPORT AND USE EXCEL TO CREATE A PAY BOOK THAT SHOWS
ITEMS RECORDED ON DWRS. COMPARE LAST LOAD WEIGH TICKETS OR OTHER
DOCUMENTATION TO TOTAL PAID.
FOR FUEL AND ASPHALT ADJUSTMENTS, RUN THE FAA REPORT (SEE CONSTRUCTION
WEBSITE) AND VERIFY ALL TONNAGE AMOUNTS IN CORRECT MONTH OF PLACEMENT ON
PROJECT. FINAL PAYMENT OF ADJUSTMENTS SHOULD EQUAL WORKBOOK CALCULATIONS.
IF APPLICABLE, CHECK ALL LOT PAY ADJUSTMENT WORKSHEETS AND VERIFY ANY
PAYMENTS OR DEDUCTIONS HAVE BEEN PAID.
IF APPLICABLE, CHECK ALL RIDEABILITY CALCULATIONS AND VERIFY ANY PAYMENTS
OR DEDUCTIONS HAVE BEEN PAID.
IF APPLICABLE, CHECK ALL CALCULATIONS FOR DEDUCTIONS OF NON-SPEC MATERIALS.
VERIFY STOCKPILE BALANCES ARE ZERO
IF APPLICABLE, INCLUDE DISPUTE/CLAIM SUMMARY
IF APPLICABLE, SUBMIT LIQUIDATED DAMAGE REVIEW WITH FINAL ESTIMATE.
IF APPLICABLE, REVIEW PAVEMENT THICKNESS CALCULATION REPORT FOR ANY DEDUCTIONS
TO FINAL PAYMENT.
COMPLETE AND SUBMIT CONTRACTOR EVALUATION(S). RECORD IN CHECKLIST
SCHEDULED EVENTS FOLDER
| MATERIALS CERTIFICATION APPROVED |  |  | (Approval date:)
ALL CHANGE ORDERS IN APPROVED OR DENIED STATUS
CHECK CRITICAL DATES IN SITE MANAGER FOR FORMAL ACCEPTANCE
MARK ALL KEY DATES APPLICABLE TO PROJECT INCLUDING:
CORRECTIVE WORK COMPLETION
OPEN TO TRAFFIC
WORK BEGIN DATE
WORK COMPLETE DATE
COMPREHENSIVE CORRECTIVE WORK NOTIFICATION
RESIDENT FINAL CHECK
READY FOR MATERIALS CHECK RE
FINAL CHECKED BY RE
IF APPLICABLE TO PROJECT, FINAL INSPECTION DATES SHOULD BE ENTERED INTO KEY DATES:
STRUCTURE FINAL INSPECTION
ELECTRICAL FINAL INSPECTION
FHWA FINAL INSPECTION
ROADWAY INSPECTION
SIGNING FINAL INSPECTION
PAINTING FINAL INSPECTION
STRIPING/REFLECTIVITY FINAL INSPECTION
LANDSCAPING FINAL INSPECTION
RESURFACING FINAL INSPECTION
OTHER FINAL INSPECTION
KPDES NOI
KPDES NOT
| PLAN SHEETS: |  | (SUBMIT ALL TO CENTRAL OFFICE)
CHECK ALL FINAL PAY QUANTITIES AGAINST FINAL ESTIMATE ON GENERAL
SUMMARY SHEETS, PIPE SHEETS, BITUMINOUS SHEETS, STRUCTURE SHEETS.
SHOW ALL SUBGRADE DRAINAGE, INCLUDING PERFORATED PIPE, BY INDICATING
STATION NUMBER, LENGTHS, SIZE, TYPE, SKEW, ETC. OR CHECK MARK THOSE
UNCHANGED ON THE PIPE SHEETS OF THE PLAN SHEETS.
AS-BUILT STRUCTURE PLANS SUBMITTED TO CENTRAL OFFICE:
FOUNDATION SHEETS
CONSTRUCTION ELEVATIONS
ANY ADJUSTMENT OR CHANGES TO ORIGINAL PLANS
At the time of submitting the final estimate, all payments should be made for Demobilization. Check to see that all
discrepancies are resolved while preparing the final estimate.
To the District Office:
Send email stating CID, Amount of Final Estimate Pay, Balance on Project, and Materials Certification date (if applicable).
Attach a copy of the final estimate, and any documentation for adjustments.