## Slide 1: Ohio River Bridges Project Downtown Crossing Construction Update
Jeremiah Littleton, PE – KYTC
Kenny Pietz, PE – HDR
September 9, 2015

## Slide 2: Brief History
1969
  Project placed in long range plan
Fall 2012
  KYTC & IFA/INDOT Announce Results
    Downtown Crossing – D/B Contract
      KYTC selects Walsh Construction DBT Bid = $860 Million and Dec. 9, 2016 Substantial Completion
Dec. 28, 2012
  Notice to Proceed

## Slide 3: Downtown Crossing
Three components:
  New cable-stayed bridge
  Improved Kennedy Bridge
  New interstate connections
Ground breaking in June 2013
Construction started in earnest in July 2013
Over 750 workers, including subcontractors

## Slide 4: KYTC Enlists Help with Construction Oversight
Oversight Assistance Consultants

## Slide 5: Positives of Consultants on the Project
Technical Expertise and Cable Stayed Bridge Experience
Staffing Flexibility and Adjust to Changes in Work Load
Ability to Quickly Establish an Onsite Material Testing Lab
Understood Role as Support to KYTC, who’s Managing the Project

## Slide 6: Oversight Assistance Consultants
– Prime Consultant
Subconsultants:
Greenman-Pedersen, Inc.
FIGG Bridge Inspection, Inc.
Parsons, Cunningham & Shartle Engineers, Inc. (DBE)
Redwing Ecological Services, Inc. (DBE)
S&ME, Inc.
American Engineers, Inc.
Thelen Associates, Inc.
KHAFRA (DBE)

## Slide 7: Fast Pace, High Volume of Work
    Simple math really.
    $860 million of work in 42 months = >$20 Million of work per month
    Peak months have exceeded $30 million!

## Slide 9: Oversight Assistance Consultant Team

## Slide 10: Downtown Crossing By The Numbers
More than 60 overpasses and bridges
More than 60 retaining walls
More than 440,000 tons of asphalt
1.3 million cubic yards of soil being moved
New bridge is 2,100 feet long

## Slide 11: Section 1: KY Approach
Kennedy Interchange is being reconfigured eliminating the weaves of “Spaghetti Junction”
More than 40 new ramps and overpasses are being built on the Kentucky side
Several new ramps have already opened to traffic

## Slide 12: Section 1 Numbers
21.5 million lbs. of structural steel
Over 100,000 cu.yds. of concrete
25.0 million lbs of re-steel
Nearly 32,000 L.ft. of precast girders
154 setups for deck finishing machine
Driven over 385,000’ of the 481,000’ (91 miles) of piling

## Slide 13: Maintaining Traffic = Phased Construction

## Slide 14: Maintaining Traffic = Night Work

## Slide 15: Pace Meant Working through the Winter

## Slide 16: Technical Challenges - Straddle Bent

## Slide 17: Straddle Bent Post-Tensioning (PT)

## Slide 18: Straddle Bent PT Capping and Grouting

## Slide 19: Completed Straddle Bent

## Slide 20: Section 2: New I-65 Bridge
All three towers reached their finished heights in June
  Tower 3: 230 feet
  Tower 4: 280 feet
  Tower 5: 230 feet
Currently erecting structural steel, setting precast deck panels, and installing and stressing stay cables
Deck will be completed this fall
New bridge to open to two-way traffic by January

## Slide 21: Cable Stayed Bridge Construction (after towers)

## Slide 22: Erecting Pre-assembled Segments

## Slide 23: Welding HDPE Stay Pipe Together

## Slide 24: Installing Cable Stay Pipe and Master Strand

## Slide 25: Master Strand and Stay Pipe Installed

## Slide 26: Installing the Rest of the Cable Strands

## Slide 27: Removing HDPE Sheathing Off Strand Ends

## Slide 28: View of Cables and Anchors in Tube

## Slide 29: Stressing Cable Strand with Mono-strand Jack (Stage1A)

## Slide 30: Strands Range from 36 & 103 per Cable

## Slide 31: Installing Precast Deck Panels

## Slide 32: Stressing to Stage 1B

## Slide 33: Adding Shear Studs and Rebar; then do Infill Pour

## Slide 34: Final Stressing to Length

## Slide 35: Balanced Cantilevered Construction

## Slide 36: Survey and Geometry Control

## Slide 37: Anchor Pier 6 Floor Beam Installed

## Slide 38: Landed on Anchor Pier and Doing Final Bolting

## Slide 39: Installing Precast Panels at Anchor Pier

## Slide 40: Preparations for Finger Joint

## Slide 41: Future Inspection and Maintenance Access

## Slide 42: Challenges – High Water

## Slide 43: Section 3: IN Approach
I-65 North traffic shifted to new completed lanes of I-65 North
I-65 South traffic to shift over later this month
Indiana approach now connects to Tower 5
Flyover ramp from US 31 North to I-65 North to open late this year

## Slide 44: What to Expect
New cable-stayed bridge opens to two-way traffic in less than 4 months
Attention shifts to the Kennedy Bridge for $22 million in improvements
Substantial Completion in December 2016
  New bridge = Six lanes NB traffic
  Kennedy = Six lanes of SB traffic

## Slide 45: Summary
On budget and on schedule
Design is essentially complete
Construction is 75% complete
Substantial completion in December 2016
Final completion in April 2017

## Slide 46: Staying Informed
www.kyinbridges.com
E-blasts and text alerts
Twice-weekly traffic updates
Louisville Downtown Bridge
@LouDntwn Bridge
1-888-ORB-1993
Regular media updates

## Slide 47: Tower Foundations

## Slide 48: 12’ Diameter Drilled Shafts (Hain Drilling Machine)

## Slide 49: Shaft Repair
Core-drilled a 90” dia. shaft inside 12’ dia. shaft.
Added beam for section loss and overall stiffness.
Over 5,000 shear studs and 170,000 lbs. of plate steel.

## Slide 50: Picking and Setting the Beam

## Slide 51: World’s Largest Plumb Bob

## Slide 52: Tower Anchor Boxes

## Slide 53: Wind Fairing

## Slide 54: Cable Stayed Bridge Layout
750 ft
750 ft
2106 ft