## Production Hour Worksheet
Highway Design Production Hour Worksheet
V2.8 - Rev 1/24/24
County |  | Project
Route |  | Consultant
Desc |  | Reviewed By
Prepared By
Item No |  | Date
No. | Item | Crew | Unit | Amount | Hr / Unit | Hours
Survey
Reconnaissance
1 | Control - (existing) | 1 | Mile |  |  | 0
2 | Utilities - (data gathering, identification & contact) | 1 | No. |  |  | 0
3 | Drainage - (sink holes, streams, pipes, etc.) | 1 | Mile |  |  | 0
Control
4 | Horizontal | 2 | Mile |  |  | 0
5 | Vertical | 2 | Mile |  |  | 0
6 | Additional LiDAR Control | 2 | Mile |  |  | 0
7 | Process Survey Control data | 1 | Mile |  |  | 0
Utility Survey
8 | Subsurface Utility Engineering, Quality Levels C & D | 1 | Mile |  |  | 0
9 | Subsurface Utility Engineering, Quality Level B | 1 | Mile |  |  | 0
10 | Subsurface Utility Engineering, Quality Level A (Pot Hole) | 2 | No. |  |  | 0
11 | Process Utility Survey data | 1 | Mile |  |  | 0
Terrain Survey
12 | Prepare Statewide LiDAR | 1 | Tile |  |  | 0
13 | Static LiDAR | 2 | Acre |  |  | 0
14 | Determine roadway elevations (Crown and EP) | 2 | Mile |  |  | 0
15 | Planimetric Pickup | 2 | Acre |  |  | 0
16 | Verify terrain model accuracy | 1 | Mile |  |  | 0
17 | Tie-ins | 2 | No. |  |  | 0
18 | Drainage situations survey (Bridge) | 2 | No. |  |  | 0
19 | Drainage situations survey (Culvert) | 2 | No. |  |  | 0
20 | Drainage pipe section (non-situation size) | 2 | No. |  |  | 0
21 | Flood plain data | 2 | Acre |  |  | 0
22 | Railroad Survey | 2 | No. |  |  | 0
23 | Additional necessary Terrain data | 2 | Acre |  |  | 0
24 | Process Terrain Survey data | 1 | Mile |  |  | 0
25 | Process LiDAR data | 1 | Mile |  |  | 0
26 | Prepare Existing Manuscript | 1 | Mile |  |  | 0
Establish Property Lines & Ownership
27 | Develop Contact Letter | 1 | LS |  |  | 0
28 | Contact & Interview Property Owners | 1 | Parcel |  |  | 0
29 | Field tie property lines/corners | 2 | Parcel |  |  | 0
Staking
30 | Stake centerlines, approaches, detours | 2 | Mile |  |  | 0
31 | Stake core holes - structures | 2 | No. |  |  | 0
32 | Stake core holes - roadway | 2 | No. |  |  | 0
Survey Miscellaneous
33 | Septic Tanks | 2 | No. |  |  | 0
34 | Cemeteries | 2 | No. |  |  | 0
35 | Environmental areas | 2 | No. |  |  | 0
36 | [5 empty] | 0
37 | [5 empty] | 0
38 | [5 empty] | 0
39 | [5 empty] | 0
40 | [5 empty] | 0
Survey TOTAL | [5 empty] | 0
Preliminary Line & Grade
Preliminary Line And Grade
41 | Computer setup | 1 | LS |  |  | 0
42 | Establish approximate property lines and ownership | 1 | LS |  |  | 0
43 | Develop preliminary pavement design | 1 | No. |  |  | 0
44 | Study and develop typical sections | 1 | No. |  |  | 0
45 | Study and develop horizontal alignments | 1 | Mile |  |  | 0
46 | Study and develop vertical alignments | 1 | Mile |  |  | 0
47 | Develop entrance alignments | 1 | No. |  |  | 0
48 | Preliminary Mainline Backbone | 1 | Mile |  |  | 0
49 | Preliminary Approach Backbone | 1 | Mile |  |  | 0
50 | Preliminary Mainline Grading | 1 | Mile |  |  | 0
51 | Preliminary Approach Grading | 1 | Mile |  |  | 0
52 | Preliminary Roundabouts - single / multi lane | 1 | No. |  |  | 0
53 | Pre-size pipes | 1 | No. |  |  | 0
54 | Pre-size culverts | 1 | No. |  |  | 0
55 | Pre-size bridges | 1 | No. |  |  | 0
56 | Conduct Traffic Engineering Analysis (Basic Hwy Capacity Manual Procedures) | 1 | Intersection |  |  | 0
57 | Conduct Traffic Engineering Analysis (Advanced: Micro-Sim) | 1 | Intersection |  |  | 0
58 | Study and development of interchange | 1 | No. |  |  | 0
59 | Study and develop Maintenance of Traffic plan | 1 | LS |  |  | 0
60 | Plot/print copies of project | 1 | LS |  |  | 0
61 | Calculate preliminary quantities and develop cost | 1 | Alt. |  |  | 0
62 | Revise Design and Estimates | 1 | LS |  |  | 0
63 | Preliminary Right of Way with taking areas | 1 | Parcel |  |  | 0
64 | Prepare Design Executive Summary | 1 | LS |  |  | 0
65 | Develop/document "Avoidance Alternatives to Water Related Impacts" | 1 | Alt. |  |  | 0
Preliminary Line And Grade Miscellaneous
66 | Project Scheduling | 1 | LS |  |  | 0
67 | Highway Safety Analysis | 1 | LS |  |  | 0
68 | Prepare Intersection Design Forms | 1 | No. |  |  | 0
69 | Prepare KMZ files | 1 | Alt. |  |  | 0
70 | [5 empty] | 0
71 | [5 empty] | 0
72 | [5 empty] | 0
73 | [5 empty] | 0
74 | [5 empty] | 0
75 | [5 empty] | 0
Preliminary Line & Grade TOTAL | [5 empty] | 0
Utility Coordination
Utility Coordination
76 | Utility Coordination Meeting | 2 | No. |  |  | 0
77 | Develop Utility Relocation Layout Sheets | 1 | Mile |  |  | 0
78 | Develop Utility Relocation Plans | 1 | Mile |  |  | 0
Utility Coordination Miscellaneous
79 | [5 empty] | 0
80 | [5 empty] | 0
Utility Coordination TOTAL | [5 empty] | 0
Right Of Way Plans
Right Of Way Plans | [5 empty] | 0
81 | Deed research | 1 | Parcel |  |  | 0
82 | Establish property and ownership | 1 | Parcel |  |  | 0
83 | Calculate Right of Way | 1 | Parcel |  |  | 0
84 | Prepare legal descriptions | 1 | Parcel |  |  | 0
85 | Complete Right of Way summary sheet | 1 | Parcel |  |  | 0
86 | Generate Additional Right of Way Plan Sheets (only when needed) | 1 | Sheet |  |  | 0
87 | Generate Right of Way Strip Map | 1 | Sheet |  |  | 0
88 | Prepare Right of Way Plans Submittal | 1 | LS |  |  | 0
89 | Right of Way revisions after Right of Way submittal | 1 | LS |  |  | 0
90 | Prepare Legal Descriptions for Right-of-Way Transfer | 1 | Parcel |  |  | 0
Right Of Way Miscellaneous
91 | [5 empty] | 0
92 | [5 empty] | 0
93 | [5 empty] | 0
94 | [5 empty] | 0
95 | [5 empty] | 0
Right Of Way Plans TOTAL | [5 empty] | 0
Final Plans
Final Plan Preparation
96 | Computer setup | 1 | LS |  |  | 0
97 | Develop pavement design | 1 | No. |  |  | 0
98 | Prepare interchange geometric approval sheet | 1 | No. |  |  | 0
99 | Refine alignments (horizontal & vertical) | 1 | Mile |  |  | 0
100 | Revise roadway plans from soils report | 1 | Mile |  |  | 0
Final Roadway Modeling
101 | Mainline Backbone | 1 | Mile |  |  | 0
102 | Approach Backbone | 1 | Mile / Each |  |  | 0
103 | Mainline Grading | 1 | Mile |  |  | 0
104 | Approach Grading | 1 | Mile / Each |  |  | 0
105 | Radius Modeling | 1 | No. |  |  | 0
106 | Roundabouts - Single Lane | 1 | No. |  |  | 0
107 | Roundabouts - Multi Lane | 1 | No. |  |  | 0
108 | Entrances - Low complexity | 1 | No. |  |  | 0
109 | Entrances - Medium complexity | 1 | No. |  |  | 0
110 | Entrances - High complexity | 1 | No. |  |  | 0
111 | Solid Rock / RDZ Lines | 1 | Mile |  |  | 0
Drainage
112 | Develop culvert pipe sections | 1 | No. |  |  | 0
113 | Develop drainage system map | 1 | Mile |  |  | 0
114 | Develop blueline stream channel changes (=> 200') | 1 | Mile |  |  | 0
115 | Drainage analysis (Entrance pipes) | 1 | No. |  |  | 0
116 | Drainage analysis (A <= 200 acres) | 1 | No. |  |  | 0
117 | Drainage analysis (200<A<1.0 sq. mile) | 1 | No. |  |  | 0
118 | Bridge Risk Assessment analysis - Level 1 Analysis | 1 | No. |  |  | 0
119 | Bridge Risk Assessment analysis - Level 2 Analysis | 1 | No. |  |  | 0
120 | Bridge Risk Assessment analysis - Level 3 Analysis | 1 | No. |  |  | 0
121 | Special Drainage Studies | 1 | No. |  |  | 0
122 | Roadway ditches and channels | 1 | Mile |  |  | 0
123 | Inlet Design | 1 | No. |  |  | 0
124 | Storm Sewer Layout | 1 | No. |  |  | 0
125 | Develop storm sewer profile | 1 | No. |  |  | 0
126 | Perform scour analysis | 1 | No. |  |  | 0
127 | Assemble preliminary and final drainage submittals | 1 | LS |  |  | 0
128 | Prepare advanced situation submittal - bridge | 1 | No. |  |  | 0
129 | Prepare advanced situation submittal - culvert | 1 | No. |  |  | 0
Drainage Miscellaneous
130 | [5 empty] | 0
131 | [5 empty] | 0
132 | [5 empty] | 0
133 | [5 empty] | 0
134 | [5 empty] | 0
135 | [5 empty] | 0
Final Plan Set
136 | Prepare layout sheet | 1 | LS |  |  | 0
137 | Prepare typical sections | 1 | No. |  |  | 0
138 | Generate plan sheets | 1 | Sheet |  |  | 0
139 | Generate profile sheets | 1 | Sheet |  |  | 0
140 | Detail cross sections | 1 | No. |  |  | 0
141 | Prepare coordinate control sheet | 1 | Sheet |  |  | 0
142 | Prepare elevation development sheets | 1 | No. |  |  | 0
143 | Prepare striping plans | 1 | Sheet |  |  | 0
144 | Develop erosion control plan | 1 | Sheet |  |  | 0
145 | Calculate final quantities | 1 | Mile |  |  | 0
146 | Complete general summary | 1 | LS |  |  | 0
147 | Complete paving summary | 1 | LS |  |  | 0
148 | Complete drainage summary | 1 | LS |  |  | 0
149 | Complete pavement under-drain summary | 1 | LS |  |  | 0
150 | Prepare cost estimate | 1 | LS |  |  | 0
151 | Prepare KMZ files | 1 | No. |  |  | 0
Maintenance Of Traffic
152 | Write maintenance of traffic notes (TCP) | 1 | LS |  |  | 0
153 | Prepare construction phasing plans | 1 | Mile |  |  | 0
154 | Show construction phasing on cross sections / pipe sheets | 1 | Mile |  |  | 0
155 | Develop diversion plan sheets | 1 | Sheet |  |  | 0
156 | Develop diversion profile sheets | 1 | Sheet |  |  | 0
157 | Develop diversion cross sections | 1 | No. |  |  | 0
158 | Develop temporary drainage | 1 | No. |  |  | 0
Final Plan Preparation Miscellaneous
159 | Plot/Print copies of plans | 1 | LS |  |  | 0
160 | Plan revisions | 1 | Mile |  |  | 0
161 | Prepare final construction plans submittal | 1 | LS |  |  | 0
162 | [5 empty] | 0
163 | [5 empty] | 0
164 | [5 empty] | 0
165 | [5 empty] | 0
166 | [5 empty] | 0
167 | [5 empty] | 0
Final Plans TOTAL | [5 empty] | 0
Meetings
168 | Early Alignment Review | 2 | No. |  |  | 0
169 | Preliminary Line and Grade inspection | 2 | No. |  |  | 0
170 | Geometric Review meeting | 2 | No. |  |  | 0
171 | Drainage inspection | 2 | No. |  |  | 0
172 | Final inspection | 2 | No. |  |  | 0
173 | Virtual Project Team meeting | 2 | No. |  |  | 0
174 | Project team meetings | 2 | No. |  |  | 0
175 | Prepare for Meeting | 1 | No. |  |  | 0
Meetings Miscellaneous
176 | Value Engineering Study | 2 | No. |  |  | 0
177 | [5 empty] | 0
178 | [5 empty] | 0
179 | [5 empty] | 0
Meetings TOTAL | [5 empty] | 0
Public Involvement
Public Involvement
180 | Develop and maintain mailing list | 1 | LS |  |  | 0
181 | Prepare for advisory committee/officials meetings | 1 | No. |  |  | 0
182 | Attend advisory committee/officials meetings | 3 | No. |  |  | 0
183 | Prepare for public meetings/hearings | 1 | No. |  |  | 0
184 | Attend public meetings/hearings | 3 | No. |  |  | 0
185 | Prepare and distribute newsletters | 1 | LS |  |  | 0
186 | Property owner coordination | 1 | No. |  |  | 0
Public Involvement Miscellaneous
187 | [5 empty] | 0
188 | [5 empty] | 0
189 | [5 empty] | 0
Public Involvement TOTAL | [5 empty] | 0
QA/QC
QA/QC - Only when Recommended by KYTC
190 | Plan review | 1 | LS |  |  | 0
191 | Structure review | 1 | LS |  |  | 0
QA/QC TOTAL | [5 empty] | 0
Survey | [5 empty] | 0
Preliminary Line & Grade | [5 empty] | 0
Utility Coordination | [5 empty] | 0
Right of Way Plans | [5 empty] | 0
Final Plans | [5 empty] | 0
Meetings | [5 empty] | 0
Public Involvement | [5 empty] | 0
QA / QC | [5 empty] | 0