## 2018 STIP PROJECT PHASES
TIP / STIP | REQUIRED MPO TIP AS OF SEPTEMBER '18 | CURRENTLY REQUIRES MPO TIP ACTION | MPO Comments | MODIFICATION OR AMENDMENT | STIP ADMINISTRATIVE MODIFICATION OR AMENDMENT NUMBER | APPROVAL DATE | COMMENTS | FUND PREFIX | FEDERAL PROJECT NUMBER | COUNTY | Item No. | ROUTE NO. | LENGTH | BMP | EMP | PRIORITY | TYPE OF WORK | DESCRIPTION | PHASE | FAST ACT FUND | TYPE OF FUND | FISCAL YEAR SCHEDULE | TOTAL PHASE COST | FEDERAL PORTION | FEDERAL STP | FEDERAL NH | STATE MATCH | LOCAL MATCH | ILLUSTRATIVE PROJECT | STATUS OF FEDERAL FUNDS | CURRENT AMOUNT OF FEDERAL FUNDS OBLIGATED | CURRENT ADVANCE CONSTRUCT (AC) AMOUNT OF FEDERAL FUNDS | TOTAL PHASE COST CURRENT FEDERAL FUNDS PLUS CURRENT AC | FISCAL YEAR OF INITIAL PROGRAMMING OF FEDERAL FUNDS | FISCAL YEAR QUARTER OF INITIAL PROGRAMMING OF FEDERAL FUNDS | NAME OF LOCAL PUBLIC AGENCY
STIP | [9 empty] | ADAIR | 885 | KY 704 |  | 11.905 | 11.913 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON KY 704 (11.909) OVER PETTY'S FORK. (001B00078N)(SD) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [9 empty] | ADAIR | 8-1068 | KY 704 |  | 11.905 | 11.913 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON KY 704 (11.909) OVER PETTY'S FORK. (001B00078N)(SD) | C |  | BR/STP | 2020 | 490000 | 303800 |  |  | 186200 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.015 | 2019-01-25 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 9010354 | ADAIR, MCCREARY, PULASKI | 8-9013 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | PRELIMINARY DESIGN AND STUDY TO DETERMINE LOW COST IMPROVEMENTS AT VARIOUS INTERSECTIONS WITHIN DISTRICT 8. (2018BOP) | D |  | SAF | 2019 | 200000 | 200000 | [5 empty] | OBLIGATED | 200000 |  | 200000 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.306 | 2021-06-16 | ADD D PHASE TO STIP; NEW |  |  | ALLEN | 3-8902 | KY 98 |  | 9.85 | 10.25 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT 1.0 MILE EAST OF BRIDGE OVER BARREN RIVER LAKE TO CORRECT VERTICAL AND HORIZONTAL DEFICIENCIES. (2020CCN) | D |  | SPP | 2021 | 400100 | 100 |  |  | 400000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.029 | 2019-02-21 | ADD PROJECT TO STIP; PARENT NO. 3-9013.00; NEW | HSIP | 9010375 | ALLEN | 3-9013.5 | US 31E & KY 100 |  | 7.15 12.5 | 7.68 12.8 | SAFETY | SAFETY-HAZARD ELIM(P) | MILL AND RESURFACE THE APPROACHES, UPDATE THE SIGNING AND STRIPING, AND UPDATE THE SIGNAL TO INCLUDE REFLECTIVE BACKPLATES AT THE INTERSECTION OF US 31E & KY 100. (2018BOP) | C |  | SAF | 2019 | 220000 | 220000 | [5 empty] | OBLIGATED |  | 200200 | 200200 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.218 | 2020-08-28 | ADD C PHASE TO STIP; PARENT NO. 99-911.06; NEW |  |  | ALLEN | 3-9014 | KY 100 |  | 0 | 8.83 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ALONG KY 100 BETWEEN MP 0.000 TO MP 8.830 (2016BOP). | C |  | SAF | 2020 | 2080000 | 2080000 | [8 empty] | 0
STIP | [9 empty] | ALLEN | 3-10000 | KY 3499 |  | 1.412 | 1.422 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-3499 BRIDGE OVER BAYS FORK. (002B00004N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030017 | ALLEN | 3-10000 | KY 3499 |  | 1.412 | 1.422 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-3499 BRIDGE OVER BAYS FORK. (002B00004N) | C |  | BR/STP | 2020 | 525000 | 325500 |  |  | 199500 |  |  | OBLIGATED |  | 341985 | 341985 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.291 | 2021-04-23 | ADD C PHASE TO STIP; NEW |  |  | ALLEN | 3-10002 | CR 1125 |  | 0.027 | 0.035 |  | BRIDGE (P) | Address Deficiencies on Max Roark Rd over Puncheon Creek | C |  | STP | 2021 | 448500 | 448500 | [8 empty] | 0
STIP | [9 empty] | ALLEN | 3-10011 | KY 585 |  | 0 | 0.002 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 585 BRIDGE OVER MIDDLE FORK DRAKES CREEK. (002B00021N) | D |  | BR/STP | 2019 | 245000 | 151900 |  |  | 93100 | [5 empty] | 0
STIP | [9 empty] | ALLEN | 3-10011 | KY 585 |  | 0 | 0.002 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 585 BRIDGE OVER MIDDLE FORK DRAKES CREEK. (002B00021N) | C |  | BR/STP | 2020 | 822500 | 509950 |  |  | 312550 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.021 | 2019-02-04 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030016 | ALLEN | 3-10011 | KY 585 |  | 0 | 0.002 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 585 BRIDGE OVER MIDDLE FORK DRAKES CREEK. (002B00021N) | C |  | STP | 2019 | 850000 | 850000 |  |  | 0 |  |  | OBLIGATED |  | 710195 | 710195 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.139 | 2019-10-25 | ADD PROJECT TO STIP; NEW | STPBRZ | 9030196 | ALLEN | 3-10019 | CR 1611 |  | 0.616 |  | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES ON OLD WALNUT TRAIL (CR 1611) OVER WEST BAYS FORK CREEK. (002C00060N) | C |  | STP | 2020 | 800000 | 800000 |  |  | 0 |  |  | OBLIGATED |  | 718905 | 718905 | 2020 | 1ST QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.197 | 2020-07-01 | ADD C PHASE TO STIP; NEW |  |  | ANDERSON | 7-10020 | KY 44 |  |  |  | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 44 BRIDGE OVER CROOKED CREEK. 003B00029N | C |  | STP | 2020 | 2386250 | 2386250 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.229 | 2020-09-14 | ADD C PHASE TO STIP; PARENT NO. 99-224.14; NEW |  |  | ANDERSON | 7-20038 | KY 53 US 127B |  | 1.175 3.272 | 5.95 6.656 | RELIABILITY | AM-PAVEMENT(PRI)(P) | Resurfacing of KY 53 (MP 1.175-5.95) and US 127B (MP 3.272-6.656) in Anderson County, KY. | C |  | STP | 2020 | 2050000 | 2050000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.274 | 2021-02-04 | ADD D PHASE TO STIP; NEW |  |  | ANDERSON | 7-80001 | US 62 |  | 20.493 | 22.78 | SAFETY | SPOT IMPROVEMENTS(O) | IMPROVE US-62 (VERSAILLES RD.) FROM HILLTOP DR. TO WEST END OF BRIDGE OVER KENTUCKY RIVER AT TYRONE(18CCN) (2020CCR) | D |  | STP | 2021 | 1250000 | 1250000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | BALLARD | 1-115 | US 60 | 3.7 | 13.62 | 16.937 | RELIABILITY | MAJOR WIDENING(O) | PADUCAH-WICKLIFFE RD: IMPROVE US-60 FROM STAFFORD ROAD TO BETHEL CHURCH ROAD (INCLUDES KEVIL BYPASS)(TO BE LET WITH 1-115.10) (06CCR)(12CCR)(14CCR)(18CCR). | R |  | NH | 2020 | 2500000 | 2500000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.311 | 2021-07-21 | INCREASE FUNDS BASED ON NEW ESTIMATE; MOD |  |  | BALLARD | 1-115 | US 60 | 3.7 | 13.62 | 16.937 | RELIABILITY | MAJOR WIDENING(O) | PADUCAH-WICKLIFFE RD: IMPROVE US-60 FROM STAFFORD ROAD TO BETHEL CHURCH ROAD (INCLUDES KEVIL BYPASS)(TO BE LET WITH 1-115.10) (06CCR)(12CCR)(14CCR)(18CCR). | R |  | NH | 2020 | 5900000 | 5900000 | [8 empty] | 0
STIP | [9 empty] | BALLARD | 1-115 | US 60 | 3.7 | 13.62 | 16.937 | RELIABILITY | MAJOR WIDENING(O) | PADUCAH-WICKLIFFE RD: IMPROVE US-60 FROM STAFFORD ROAD TO BETHEL CHURCH ROAD (INCLUDES KEVIL BYPASS)(TO BE LET WITH 1-115.10) (06CCR)(12CCR)(14CCR)(18CCR). | U |  | NH | 2021 | 3500000 | 2800000 |  |  | 700000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.229 | 2020-09-14 | ADD C PHASE TO STIP; PARENT NO. 99-911.08; NEW |  |  | BALLARD GRAVES MCCRACKEN | 1-981 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | REPLACEMENT OF TARGETED GUARDRAIL END TREATMENTS IN DISTRICT ONE. (2018BOP) | C |  | SAF | 2020 | 490000 | 490000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | BALLARD | 1-1140.01 | US 51 | 0.97 | 7.327 | 8.297 | ASSET MANAGEMENT | AM-BRIDGE (P) | PE AND ENVIRONMENTAL FOR REPLACEMENT OF CAIRO BRIDGE AT OR BESIDE EXISTING LOCATION. (004B00021N)(SD)(18CCR) | D |  | BR/NH | 2020 | 2500000 | 1550000 |  |  | 950000 | [5 empty] | 0
STIP | [9 empty] | BALLARD | 1-1140.02 | US 51 | 0.97 | 7.327 | 8.297 | ASSET MANAGEMENT | AM-BRIDGE (P) | PE AND ENVIRONMENTAL FOR REPLACEMENT OF CAIRO BRIDGE AT OR BESIDE EXISTING LOCATION.(SD)(18CCR) | D |  | BR/NH | 2022 | 6500000 | 4030000 |  |  | 2470000 | [5 empty] | 0
STIP | [9 empty] | BALLARD | 1-1140.03 | US 51 |  | 7.327 | 8.297 | ASSET MANAGEMENT | AM-BRIDGE (P) | PE AND ENVIRONMENTAL FOR REPLACEMENT OF CAIRO BRIDGE AT OR BESIDE EXISTING LOCATION. | D |  | BR/NH | 2021 | 20000000 | 12400000 |  |  | 7600000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.039 | 2019-03-19 | ADDING PROJECT TO STIP; PARENT NO. 99-911.06; NEW | HSIP | 9010318 | BALLARD | 1-9007 | KY 473 |  | 1.7 | 2.3 | SAFETY | SAFETY-HAZARD ELIM(P) | RECONSTRUCT THE INTERSECTION OF KY 473 AT MOSSTOWN RD FROM 'Y' TO 'T' INTERSECTION IN BALLARD COUNTY. (2016BOP) | C |  | SAF | 2019 | 448560 | 448560 |  |  | 0 |  |  | OBLIGATED | 821144 |  | 821144 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.197 | 2020-07-01 | ADD C PHASE TO STIP; PARENT NO. 99-911.05; NEW |  |  | BALLARD MCCRACKEN | 1-9010 | US 62 |  | 1.373 0 | 1.754 8.808 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON US 62 FROM KY 1837 IN BALLARD COUNTY EXTENDING EASTWARD TO KY 998 IN MCCRACKEN COUNTY. (2018BOP) | C |  | SAF | 2020 | 2120000 | 2120000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.075 | 2019-05-28 | ADD PROJECT TO STIP; NEW | STPBRZ | 9030133 | BALLARD | 1-10014 | CR 1203 |  | 0.399 |  | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES ON JOHNSON ROAD (CR 1203) OVER SHAWNEE CREEK. | C |  | STP | 2020 | 649975 | 649975 |  |  | 0 |  |  | OBLIGATED |  | 597570 | 597570 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.075 | 2019-05-28 | ADD PROJECT TO STIP; NEW | STPBRZ | 9030132 | BALLARD | 1-10019 | CR 1309 |  | 1.733 |  | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES ON PALMORE ROAD (CR 1309) OVER BR OF CLANTON CREEK. (004C00047N) | C |  | STP | 2020 | 366249 | 366249 |  |  | 0 |  |  | OBLIGATED |  | 390880 | 390880 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.123 | 2019-09-06 | ADD PROJECT TO STIP; PARENT NO. 99-65.16 AND 99-65.17; NEW |  |  | BALLARD | 1-10020 | KY 1290 |  | 4.084 |  | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES ON KY-1290 OVER CANE CREEK. (004B00055N) | C |  | BR | 2020 | 1375000 | 1375000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | BALLARD | 1-20000 | US 51 |  | 4.873 | 7.3 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) |  | D |  | PM/NH | 2020 | 275000 | 220000 |  |  | 55000 | [5 empty] | 0
STIP | [8 empty] | 0511050 | BALLARD | 1-20000 | US 51 |  | 4.873 | 7.3 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT | C |  | PM/NH | 2020 | 2750000 | 2200000 |  |  | 550000 |  |  | OBLIGATED | 551100 | 1873740 | 2424840 | 2020 | 2ND QUARTER
STIP | [9 empty] | BARREN | 3-108.5 | KY 90 | 4.217 | 17.758 | 21.975 | RELIABILITY | RECONSTRUCTION(O) | PRIORITY SECTION 3: IMPROVE KY-90 EAST OF GLASGOW FROM BRIDGE OVER FALLEN TIMBER CREEK TO THE METCALFE COUNTY LINE. (2002BOPC)(08CCR)(10CCR)(12CCR) | C |  | STP | 2022 | 3950000 | 3160000 |  |  | 790000 | [5 empty] | 0
STIP | [7 empty] | NHPP | 0802009 | BARREN | 3-195 | LN 9008 | 0.1 | 0 | 0.1 | ASSET MANAGEMENT | AM-BRG PAINTING(P) | LOUIE B NUNN PKWY (LN-9008) BRIDGE PAINTING, CLEANING, AND MINOR REPAIRS ON BRIDGE OVER I-65 IN BARREN CO. KY. 005B00067R, 005B00067L (2016BOP) | C |  | NH | 2019 | 500000 | 500000 |  |  | 0 |  |  | OBLIGATED | 522510 |  | 522510 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.269 | 2021-01-22 | ADD R PHASE TO STIP; PARENT NO. 3-8819.00; NEW |  |  | BARREN | 3-8819.1 | KY 90 |  | 0.16 | 1.4 | RELIABILITY | MAJOR WIDENING(O) | MAJOR WIDENING ON KY 90 (5 LANES WITH CURB, GUTTER, AND SIDEWALK) FROM SANDERS STREET TO ESTES ROAD IN CAVE CITY. (SECTION 1)(2016BOP) | R |  | STP | 2021 | 50000 | 50000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.269 | 2021-01-22 | ADD U PHASE TO STIP; PARENT NO. 3-8819.00; NEW |  |  | BARREN | 3-8819.1 | KY 90 |  | 0.16 | 1.4 | RELIABILITY | MAJOR WIDENING(O) | MAJOR WIDENING ON KY 90 (5 LANES WITH CURB, GUTTER, AND SIDEWALK) FROM SANDERS STREET TO ESTES ROAD IN CAVE CITY. (SECTION 1)(2016BOP) | U |  | STP | 2021 | 50000 | 50000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.269 | 2021-01-22 | ADD C PHASE TO STIP; PARENT NO. 3-8819.00; NEW |  |  | BARREN | 3-8819.1 | KY 90 |  | 0.16 | 1.4 | RELIABILITY | MAJOR WIDENING(O) | MAJOR WIDENING ON KY 90 (5 LANES WITH CURB, GUTTER, AND SIDEWALK) FROM SANDERS STREET TO ESTES ROAD IN CAVE CITY. (SECTION 1)(2016BOP) | C |  | STP | 2021 | 1500000 | 1500000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.269 | 2021-01-22 | ADD R PHASE TO STIP; PARENT NO. 3-8819.00; NEW |  |  | BARREN | 3-8819.2 | KY 90 |  | 1.4 | 8.754 | RELIABILITY | MAJOR WIDENING(O) | WIDEN KY 90 TO 2 + 1 ROADWAY FROM ESTES ROAD IN CAVE CITY TO THE GLASGOW OUTER LOOP (US68). (SECTION 2)(2016BOP) | R |  | STP | 2021 | 400000 | 400000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.269 | 2021-01-22 | ADD U PHASE TO STIP; PARENT NO. 3-8819.00; NEW |  |  | BARREN | 3-8819.2 | KY 90 |  | 1.4 | 8.754 | RELIABILITY | MAJOR WIDENING(O) | WIDEN KY 90 TO 2 + 1 ROADWAY FROM ESTES ROAD IN CAVE CITY TO THE GLASGOW OUTER LOOP (US68). (SECTION 2)(2016BOP) | U |  | STP | 2021 | 1450000 | 1450000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.269 | 2021-01-22 | ADD C PHASE TO STIP; PARENT NO. 3-8819.00; NEW |  |  | BARREN | 3-8819.2 | KY 90 |  | 1.4 | 8.754 | RELIABILITY | MAJOR WIDENING(O) | WIDEN KY 90 TO 2 + 1 ROADWAY FROM ESTES ROAD IN CAVE CITY TO THE GLASGOW OUTER LOOP (US68). (SECTION 2)(2016BOP) | C |  | STP | 2021 | 7000000 | 7000000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | BARREN | 3-8821 | KY 1297 | 1.721 | 11.085 | 12.806 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE KY-1297 FROM CR-1366 (DONNELLY DRIVE) TO US-31E (ROGER WELLS), AND IMPROVE CR-1366 (DONNELLY DRIVE) FROM KY-1297 TO US-68 IN GLASGOW. (14CCN) (16CCN) | R |  | STP | 2022 | 2250000 | 1800000 |  |  | 450000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.229 | 2020-09-14 | INCREASE FUND AMOUNT AND UPDATE FISCAL YEAR FROM 2022 TO 2020; MOD |  |  | BARREN | 3-8821 | KY 1297 | 1.721 | 11.085 | 12.806 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE KY-1297 FROM CR-1366 (DONNELLY DRIVE) TO US-31E (ROGER WELLS), AND IMPROVE CR-1366 (DONNELLY DRIVE) FROM KY-1297 TO US-68 IN GLASGOW. (14CCN) (16CCN) | R |  | STP | 2020 | 5470000 | 5470000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | BARREN | 3-8821 | KY 1297 | 1.721 | 11.085 | 12.806 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE KY-1297 FROM CR-1366 (DONNELLY DRIVE) TO US-31E (ROGER WELLS), AND IMPROVE CR-1366 (DONNELLY DRIVE) FROM KY-1297 TO US-68 IN GLASGOW. (14CCN) (16CCN) | U |  | STP | 2022 | 2000000 | 1600000 |  |  | 400000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.229 | 2020-09-14 | INCREASE FUND AMOUNT AND UPDATE FISCAL YEAR FROM 2022 TO 2020; MOD |  |  | BARREN | 3-8821 | KY 1297 | 1.721 | 11.085 | 12.806 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE KY-1297 FROM CR-1366 (DONNELLY DRIVE) TO US-31E (ROGER WELLS), AND IMPROVE CR-1366 (DONNELLY DRIVE) FROM KY-1297 TO US-68 IN GLASGOW. (14CCN) (16CCN) | U |  | STP | 2020 | 4680000 | 4680000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.283 | 2021-03-22 | ADD C PHASE TO STIP; PARENT NO. 99-911.05; NEW |  |  | BARREN | 3-9011 | KY 6335 |  | 6.344 | 13.171 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 63 FROM CR 1186 (MP 6.344) TO LN 9008 UNDERPASS (MP13.171). (2016BOP) | C |  | SAF | 2021 | 1806000 | 1806000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.175 | 2020-04-09 | ADD D PHASE TO STIP; PARENT NO. 99-911.09; NEW |  |  | BARREN | 3-9023 | US 68 |  | 0 | 10.049 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON US 68 FROM MP 0.000 TO MP 10.049 IN BARREN COUNTY, KY. (2018BOP) | D |  | SAF | 2020 | 375000 | 375000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | BARREN | 3-10001 | US 31EX |  | 1.582 | 1.586 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF US 31EX BRIDGE OVER WATER STREET. (005B00058N) | D |  | BR/STP | 2019 | 245000 | 151900 |  |  | 93100 | [5 empty] | 0
STIP | [9 empty] | BARREN | 3-10001 | US 31EX |  | 1.582 | 1.586 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF US 31EX BRIDGE OVER WATER STREET. (005B00058N) | C |  | BR/STP | 2020 | 945000 | 585900 |  |  | 359100 | [5 empty] | 0
STIP | [9 empty] | BARREN | 3-20000 | I 65 |  | 42.89 | 43.307 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-65 BOTH DIRECTION(S) FROM MILEPOINT 42.89 TO MILEPOINT 43.307. | D |  | PM/NH | 2019 | 50000 | 40000 |  |  | 10000 | [5 empty] | 0
STIP | [9 empty] | BARREN | 3-20000 | I 65 |  | 42.89 | 43.307 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-65 BOTH DIRECTION(S) FROM MILEPOINT 42.89 TO MILEPOINT 43.307. | C |  | PM/NH | 2019 | 500000 | 400000 |  |  | 100000 | [5 empty] | 0
STIP | [9 empty] | BARREN | 3-20003 | LN 9008 |  | 16.117 | 20.1 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF LOUIE B. NUNN CUMBERLAND PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 16.117 TO MILEPOINT 20.1 | D |  | PM/NH | 2019 | 320000 | 256000 |  |  | 64000 | [5 empty] | 0
STIP | [9 empty] | BARREN | 3-20003 | LN 9008 |  | 16.117 | 20.1 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF LOUIE B. NUNN CUMBERLAND PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 16.117 TO MILEPOINT 20.1 | C |  | PM/NH | 2019 | 3200000 | 2560000 |  |  | 640000 | [5 empty] | 0
STIP | [9 empty] | BARREN | 3-20004 | LN 9008 |  | 20.1 | 22.357 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF LOUIE B. NUNN CUMBERLAND PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 20.1 TO MILEPOINT 22.357 | D |  | PM/NH | 2021 | 180000 | 144000 |  |  | 36000 | [5 empty] | 0
STIP | [9 empty] | BARREN | 3-20004 | LN 9008 |  | 20.1 | 22.357 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF LOUIE B. NUNN CUMBERLAND PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 20.1 TO MILEPOINT 22.357 | C |  | PM/NH | 2021 | 1800000 | 1440000 |  |  | 360000 | [5 empty] | 0
STIP | [9 empty] | BARREN | 3-20005 | LN 9008 |  | 9.375 | 14.85 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF LOUIE B. NUNN CUMBERLAND PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 9.375 TO MILEPOINT 14.85 | D |  | PM/NH | 2021 | 440000 | 352000 |  |  | 88000 | [5 empty] | 0
STIP | [9 empty] | BARREN | 3-20005 | LN 9008 |  | 9.375 | 14.85 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF LOUIE B. NUNN CUMBERLAND PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 9.375 TO MILEPOINT 14.85 | C |  | PM/NH | 2021 | 4400000 | 3520000 |  |  | 880000 | [5 empty] | 0
STIP | [9 empty] | BARREN | 3-20006 | US 68X |  | 1.692 | 2.523 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT | D |  | PM/STP | 2021 | 400000 | 320000 |  |  | 80000 | [5 empty] | 0
STIP | [9 empty] | BARREN | 3-20006 | US 68X |  | 1.692 | 2.523 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT | C |  | PM/STP | 2021 | 4000000 | 3200000 |  |  | 800000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.254 | 2020-11-06 | ADD D PHASE TO STIP; NEW |  |  | BARREN | 3-20020 | US 69 | 9.7 | 0 | 9.7 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION ON US-68 FROM MILEPOINT 0.00 TO MILEPOINT 9.70 | D |  | NH | 2021 | 250000 | 250000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | BARREN | 3-20020 | US 68 | 9.7 | 0 | 9.7 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION ON US-68 FROM MILEPOINT 0.00 TO MILEPOINT 9.70 | C |  | PM/NH | 2022 | 1180000 | 944000 |  |  | 236000 | [5 empty] | 0
STIP | [9 empty] | BARREN | 3-20021 | US 68 | 6.21 | 16.95 | 23.16 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION ON US-68 FROM MILEPOINT 16.95 TO MILEPOINT 23.16 | C |  | PM/NH | 2022 | 920000 | 736000 |  |  | 184000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.218 | 2020-08-28 | ADD C PHASE TO STIP; PARENT NO. 99-2700.14; NEW |  |  | BARREN | 3-20033 | US 31W |  | 0 | 6.77 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | PAVEMENT RESURFACING ON US 31W FROM MP 0.000 TO MP 6.770 IN BARREN COUNTY. | C |  | STP | 2020 | 715000 | 715000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.175 | 2020-04-09 | ADD PROJECT TO STIP; NEW |  |  | BARREN | 99-352.16 |  |  |  |  | SAFETY | SAFETY-RR PROTECTN(P) | FUNDING FOR CLOSING A CSX RAILROAD CROSSING ON GILLENWATER STREET IN CAVE CITY. | C |  | RRP | 2020 | 2500 | 2250 |  |  | 250 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.175 | 2020-04-09 | ADD PROJECT TO STIP; NEW |  |  | BARREN | 99-352.16 |  |  |  |  | SAFETY | SAFETY-RR PROTECTN(P) | FUNDING FOR CLOSING A CSX RAILROAD CROSSING ON GILLENWATER STREET IN CAVE CITY. | U |  | RRP | 2020 | 7500 | 6750 |  |  | 750 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.265 | 2020-12-23 | ADD C PHASE TO STIP; PARENT NO. 99-911.07; NEW |  |  | BATH ROWAN | 9-9009 | US 60 |  | 17.402 | 7 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON US 60 FROM MP 17.402 IN BATH COUNTY TO MP 7.000 IN ROWAN COUNTY. (2018BOP) | C |  | SAF | 2021 | 1500000 | 1500000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.283 | 2021-03-22 | ADD C PHASE TO STIP; PARENT NO. 99-911.08; NEW |  |  | BATH NICHOLAS | 9-9013 | KY 36 |  | 0.000 5.335 | .890 13.642 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 36 FROM MP 5.335 TO MP 13.642 IN NICHOLAS COUNTY AND MP 0.000 TO MP 0.890 IN BATH COUNTY. (2018BOP) | C |  | SAF | 2021 | 1720000 | 1720000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.314 | 2021-06-25 | ADD D PHASE TO STIP; NEW |  |  | BATH MENIFEE | KY FLAP12 | KY 36 |  |  |  | RELIABILITY | SPOT IMPROVEMENTS(O) | LANDSLIDE REPAIRS ALONG KY 36 AT THE BATH/MENIFEE COUNTY LINE. | D |  | FLAP | 2021 | 30000 | 24000 |  |  | 6000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.314 | 2021-06-25 | ADD R PHASE TO STIP; NEW |  |  | BATH MENIFEE | KY FLAP12 | KY 36 |  |  |  | RELIABILITY | SPOT IMPROVEMENTS(O) | LANDSLIDE REPAIRS ALONG KY 36 AT THE BATH/MENIFEE COUNTY LINE. | R |  | FLAP | 2021 | 25000 | 20000 |  |  | 5000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.314 | 2021-06-25 | ADD C PHASE TO STIP; NEW |  |  | BATH MENIFEE | KY FLAP12 | KY 36 |  |  |  | RELIABILITY | SPOT IMPROVEMENTS(O) | LANDSLIDE REPAIRS ALONG KY 36 AT THE BATH/MENIFEE COUNTY LINE. | C |  | FLAP | 2021 | 545000 | 436000 |  |  | 109000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.314 | 2021-06-25 | ADD D PHASE TO STIP; NEW |  |  | BATH MENIFEE | KY FLAP13 | KY 826 |  |  |  | RELIABILITY | SPOT IMPROVEMENTS(O) | RECONSTRUCTION AND IMPROVE SAFETY AT THE ENTRANCE TO THE CAVE RUN LAKE STONEY COVE RECREATIONAL AREA ALONG KY 826 IN BATH COUNTY. | D |  | FLAP | 2021 | 15000 | 12000 |  |  | 3000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.314 | 2021-06-25 | ADD C PHASE TO STIP; NEW |  |  | BATH MENIFEE | KY FLAP13 | KY 826 |  |  |  | RELIABILITY | SPOT IMPROVEMENTS(O) | RECONSTRUCTION AND IMPROVE SAFETY AT THE ENTRANCE TO THE CAVE RUN LAKE STONEY COVE RECREATIONAL AREA ALONG KY 826 IN BATH COUNTY. | C |  | FLAP | 2021 | 235000 | 188000 |  |  | 47000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.329 | 2021-09-01 | ADD D PHASE TO STIP; NEW |  |  | BATH | KY FLAP 13 | KY 826 |  |  |  |  | SAFETY | IMPROVE SAFETY AT THE ENTRANCE TO THE STONEY COVE RECREATIONAL AREA ALONG KY 826 IN BATH COUNTY. | D |  | FLAP | 2021 | 15000 | 12000 |  |  | 3000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.197 | 2020-07-01 | ADD PROJECT TO STIP; PARENT NO. 9-9009.00; NEW |  |  | BATH | 9-9009.01 | US 60 KY 801 |  | 19.981 0 | 20.111 .1 | SAFETY | SAFETY-HAZARD ELIM(P) | CONSTRUCT A MINI ROUNDABOUT AT THE INTERSECTION OF US 60 & KY 801 IN BATH COUNTY, KY. (2018BOP) | C |  | SAF | 2020 | 585000 | 585000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | BATH | 9-10000 | KY 1106 |  | 3.291 | 3.327 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-1106 BRIDGE OVER FLAT CREEK. (006B00069N) | D |  | BR/STP | 2019 | 595000 | 368900 |  |  | 226100 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030039 | BATH | 9-10000 | KY 1106 |  | 3.291 | 3.327 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-1106 BRIDGE OVER FLAT CREEK. (006B00069N) | C |  | BR/STP | 2020 | 2258000 | 1399960 |  |  | 858040 |  |  | OBLIGATED |  | 965790 | 965790 | 2019 | 2ND QUARTER
STIP | [9 empty] | BATH | 9-10001 | KY 1944 |  | 2.701 | 2.715 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-1944 BRIDGE OVER WHITE OAK CREEK. (006B00076N) | D |  | BR/STP | 2019 | 473000 | 293260 |  |  | 179740 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030040 | BATH | 9-10001 | KY 1944 |  | 2.701 | 2.715 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-1944 BRIDGE OVER WHITE OAK CREEK. (006B00076N) | C |  | BR/STP | 2020 | 1015000 | 629300 |  |  | 385700 |  |  | OBLIGATED |  | 428580 | 428580 | 2019 | 2ND QUARTER
STIP | [9 empty] | BATH | 9-10017 | KY 211 |  | 8.166 | 8.178 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 211 BRIDGE OVER COW CREEK. (006B00043N) | D |  | BR/STP | 2019 | 315000 | 195300 |  |  | 119700 | [5 empty] | 0
STIP | [9 empty] | BATH | 9-10017 | KY 211 |  | 8.166 | 8.178 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 211 BRIDGE OVER COW CREEK. (006B00043N) | C |  | BR/STP | 2020 | 717500 | 444850 |  |  | 272650 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.123 | 2019-09-06 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030198 | BATH | 9-10017 | KY 211 |  | 8.166 | 8.178 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 211 BRIDGE OVER COW CREEK. (006B00043N) | C |  | BR/STP | 2020 | 831119 | 831119 |  |  | 0 |  |  | OBLIGATED |  | 644905 | 644905 | 2019 | 4TH QUARTER
STIP | [9 empty] | BATH | 9-20001 | US 60 |  | 6.35 | 7.724 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT | D |  | PM/STP | 2019 | 410000 | 328000 |  |  | 82000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.306 | 2021-06-16 | ADD D PHASE TO STIP; NEW |  |  | BATH | 9-80101 | KY 36 |  | 13.394 | 17.1 |  | SAFETY (P) | IMPROVE SAFETY ON KY 36 FROM THE INTERSECTION WITH I 64 TO THE INTERSECTION OF KY 965 INCLUDING THE CURVES KNOWN AS CLEAR CREEK FURNACE AND THOMAS HILL (2020CCN) | D |  | SPP | 2021 | 208100 | 100 |  |  | 208000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.306 | 2021-06-16 | ADD D PHASE TO STIP; NEW |  |  | BATH | 9-80102 | KY 36 |  | 12.3 | 12.993 |  | SAFETY (P) | IMPROVE SAFETY AND OPERATIONAL EFFICIENCY ON KY 36 FROM NORTH OF MARIELLA DR TO THE INTERSECTION OF OLD KY 36 (2020CCN) | D |  | SPP | 2021 | 260100 | 100 |  |  | 260000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.291 | 2021-04-23 | ADD C PHASE TO STIP; PARENT NO. 99-911.09; NEW |  |  | BELL | 11-9021 | KY 92 |  | 9.973 | 10.124 | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALL GUARDRAIL ON KY 92 FROM 0.304 MILES EAST OF KY 2077 (9.973) TO 0.636 MILES WEST OF KY 3085 (10.124) IN BELL COUNTY, KY. (2018BOP) | C |  | SAF | 2021 | 63800 | 63800 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.291 | 2021-04-23 | ADD C PHASE TO STIP; PARENT NO. 99-911.09; NEW |  |  | BELL | 11-9022 | KY 441 |  | 2.174 | 2.344 | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALL GUARDRAIL ON KY 441 FROM 0.611 MILES EAST OF KY 1599 (2.174) TO 1.483 MILES WEST OF KY 3486 (2.344). (2018BOP) | C |  | SAF | 2021 | 29000 | 29000 | [8 empty] | 0
STIP | [9 empty] | BELL | 11-10000 | KY 2011 |  | 6.395 | 6.399 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-2011 BRIDGE OVER RED BIRD CREEK. (007B00071N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030077 | BELL | 11-10000 | KY 2011 |  | 6.395 | 6.399 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-2011 BRIDGE OVER RED BIRD CREEK. (007B00071N) | C |  | BR/STP | 2020 | 441000 | 273420 |  |  | 167580 |  |  | OBLIGATED |  | 203100 | 203100 | 2019 | 3RD QUARTER
STIP | [9 empty] | BELL | 11-10001 | KY 2011 |  | 7.534 | 7.54 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-2011 BRIDGE OVER RED BIRD CREEK. (007B00072N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [9 empty] | BELL | 11-10001 | KY 2011 |  | 7.534 | 7.54 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-2011 BRIDGE OVER RED BIRD CREEK. (007B00072N) | C |  | BR/STP | 2020 | 791000 | 490420 |  |  | 300580 | [5 empty] | 0
STIP | [9 empty] | BELL | 11-10002 | CR 1041 |  | 0.091 | 0.097 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF CR-1041 BRIDGE OVER YORK BRANCH. (007C00003N) | D |  | BR/STP | 2019 | 193000 | 119660 |  |  | 73340 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030156 | BELL | 11-10002 | CR 1041 |  | 0.091 | 0.097 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF CR-1041 BRIDGE OVER YORK BRANCH. (007C00003N) | C |  | BR/STP | 2020 | 595000 | 368900 |  |  | 226100 |  |  | OBLIGATED |  | 328633.2 | 328633.2 | 2019 | 4TH QUARTER
STIP | [9 empty] | BELL | 11-10038 | KY 92 |  | 3.142 | 3.148 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 92 BRIDGE OVER GREASY CREEK. (007B00040N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [9 empty] | BELL | 11-10038 | KY 92 |  | 3.142 | 3.148 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 92 BRIDGE OVER GREASY CREEK. (007B00040N) | C |  | BR/STP | 2020 | 490000 | 303800 |  |  | 186200 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.021 | 2019-02-04 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030051 | BELL | 11-10038 | KY 92 |  | 3.142 | 3.148 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 92 BRIDGE OVER GREASY CREEK. (007B00040N) | C |  | STP | 2019 | 754000 | 754000 |  |  | 0 |  |  | OBLIGATED |  | 774510 | 774510 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.244 | 2020-10-16 | ADD C PHASE TO STIP; PARENT NO. 99-514.01; NEW |  |  | BELL | 11-10166 | KY 186 |  | 2.401 | 2.43 | RELIABILITY | AM-BRIDGE (P) | PREVENTATIVE BRIDGE MAINTENANCE CLEANING AND PAINTING ON VARIOUS BRIDGES IN BELL COUNTY. (007B00087N); (007B00088N); (007B00089N); (007B00119N); (007B00129N) | C |  | STP | 2021 | 1360000 | 1360000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | BELL | 11-20000 | KY 2012 |  | 0 | 1.95 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT, SCHOOL BUS SAFETY ISSUE. (CCR) | D |  | PM/STP | 2019 | 61000 | 48800 |  |  | 12200 | [5 empty] | 0
STIP | [9 empty] | BELL | 11-20000 | KY 2012 |  | 0 | 1.95 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT, SCHOOL BUS SAFETY ISSUE. (CCR) | C |  | PM/STP | 2019 | 610000 | 488000 |  |  | 122000 | [5 empty] | 0
STIP | [9 empty] | BELL | 11-20021 | US 25E | 1.96 | 0.9 | 2.86 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION ON US-25E FROM MILEPOINT 0.90 TO MILEPOINT 2.86 | C |  | PM/NH | 2022 | 1391000 | 1112800 |  |  | 278200 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.229 | 2020-09-14 | ADD C PHASE TO STIP; PARENT NO. 99-224.14; NEW |  |  | BELL | 11-20034 | KY 190 |  | 11.174 | 14.58 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | Resurfacing of KY 190 (MP 11.174-14.58) in Bell County, KY. | C |  | STP | 2020 | 500000 | 500000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.229 | 2020-09-14 | ADD D PHASE TO STIP; NEW |  |  | BELL | 11-80150 | KY 74 |  | 16.234 | 16.753 | SAFETY | SAFETY(P) | IMPROVE SAFETY ALONG E. CUMBERLAND AVE. (KY 74) BETWEEN MP 16.234 AND 16.753 FOR PEDESTRIAN TRAFFIC BY REPLACING DETERIORATED SIDEWALKS AND UPDATING RAMPS (2020CCN) | D |  | SAF | 2020 | 50000 | 50000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.229 | 2020-09-14 | ADD D PHASE TO STIP; NEW |  |  | BELL | 11-80151 | KY 74 |  | 15.19 | 16.234 | SAFETY | SAFETY(P) | IMPROVE SAFETY ALONG W. CUMERLAND AVE. (KY 74) FROM MP 15.190 TO MP 16.234 FOR PEDESTRIAN TRAFFIC BY REPLACING DETERIORATED SIDEWALKS AND UPDATING RAMPS (2020CCN) | D |  | SAF | 2020 | 50000 | 50000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.229 | 2020-09-14 | ADD D PHASE TO STIP; NEW |  |  | BELL | 11-80152 | KY 2402 |  | 0 | 0.353 | SAFETY | SAFETY(P) | IMPROVE SAFETY ALONG N 25TH STREET (KY 2402) FOR PEDESTRIAN TRAFFIC BY REPLACING DETERIORATED SIDEWALKS AND UPDATING RAMPS FROM MP 0 TO 0.353 (2020CCN) | D |  | SAF | 2020 | 50000 | 50000 |  |  | 0 | [5 empty] | 0
|  |  |  | AMENDMENT | 2018.003 | 2019-07-25 | TIP REFERENCE FY 20-23 RESOLUTION DATED 5/9/19. NEW |  |  | BOONE CAMPBELL KENTON | [22 empty] | 0
|  |  |  | AMENDMENT | 2018.007 | 2020-07-08 | TIP REFERENCE FY 21-24 RESOLUTION DATED 4/9/20. NEW |  |  | BOONE CAMPBELL KENTON | [12 empty] | 0 | [9 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; ADD PROJECT TO STIP; NEW |  |  | BOONE CAMPBELL KENTON | 6-464 |  |  |  |  | RELIABILITY | SCOPING STUDY (O) | OKI NORTHERN KENTUCKY ACTIVE TRAFFIC DEMAND MANAGEMENT STUDY. | P |  |  | 2021 | 400000 | 400000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.111 | 2019-08-02 | OKI MPO AREA TIP FY 20-23, GROUPED PROJECTS - CHAPTER 7, PG 7-5; KIPDA MPO AREA TIP FY 18-21, GROUPED PROJECTS - PG 6; ADD PROJECT TO STIP; NEW | NHPP | 6000165 | BOONE JEFFERSON |  | I-64 I-265 | [5 empty] | RETROFIT OF ITS DYNAMIC MESSAGE SIGNS ON VARIOUS INTERSTATE ROUTES IN DISTRICT 5 & 6. | C |  | NH | 2019 | 320000 | 320000 | [5 empty] | OBLIGATED |  | 320000 | 320000 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.159 | 2020-01-14 | TIP FY 20-23; AMENDMENT#5; ADD D PHASE TO STIP; NEW |  |  | BOONE | TBD | US 42 | [5 empty] | UPGRADE SIGNALS TO CENTRAL BASED SYSTEM, UPGRADED CONTROLLERS AT 24 INTERSECTIONS, ADAPTIVE SIGNAL CONTROL, EMERGENCY VEHICLE PREEMPTION, CCTV CAMERAS AND FIBER OPTIC NETWORK. | D |  | SNK | 2020 | 309350 | 247480 |  |  |  | 61870 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.159 | 2020-01-14 | TIP FY 20-23; AMENDMENT#5; ADD C PHASE TO STIP; NEW |  |  | BOONE | TBD | US 42 | [5 empty] | UPGRADE SIGNALS TO CENTRAL BASED SYSTEM, UPGRADED CONTROLLERS AT 24 INTERSECTIONS, ADAPTIVE SIGNAL CONTROL, EMERGENCY VEHICLE PREEMPTION, CCTV CAMERAS AND FIBER OPTIC NETWORK. | C |  | SNK | 2022 | 3380340 | 2704272 |  |  |  | 676068 |  |  |  |  | 0
STIP | YES | No | [5 empty] | NHPPIM | 0757144 | BOONE | 6-14 | I 75 | 0.686 | 177.659 | 178.345 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | IMPROVE THE KY-536 (MT. ZION ROAD) INTERCHANGE. (14CCR)(16CCR)(18CCR) | U |  | NH | 2019 | 5430000 | 5430000 |  |  | 0 |  |  | OBLIGATED | 2024000 |  | 2024000 | 2019 | 2ND QUARTER
STIP | YES | No | [5 empty] | NHPPIM | 0757144 | BOONE | 6-14 | I 75 | 0.686 | 177.659 | 178.345 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | IMPROVE THE KY-536 (MT. ZION ROAD) INTERCHANGE. (14CCR)(16CCR)(18CCR) | C |  | NH | 2021 | 5000000 | 4000000 |  |  | 1000000 |  |  | OBLIGATED | 7100000 | 14800000 | 21900000 | 2019 | 2ND QUARTER
STIP | YES | No | [7 empty] | BOONE | 6-14.02 | I 75 | 0.686 | 178.033 | 178.133 | ECONOMIC DEVELOPMENT | PREFINANCD CONVRSN(O) | IMPROVE THE KY-536 (MT. ZION ROAD) INTERCHANGE. (14CCR)(16CCR)(18CCR) | C |  | NH | 2022 | 17080000 | 13664000 |  |  | 3416000 | [5 empty] | 0
STIP |  | No | [5 empty] | NHPP | 2759135 | BOONE | 6-78 | I 275 |  | 7.2 | 8.9 | ECONOMIC DEVELOPMENT | NEW INTERCHANGE(O) | IMPROVE FREIGHT MOBILITY AT I-275 AND GRAVES ROAD (CONTINUATION OF 6-8953: INTERCHANGE JUSTIFICATION STUDY ON I-275/GRAVES RD).(18CCR) | D |  | NH | 2019 | 3000000 | 3000000 |  |  | 0 |  |  | OBLIGATED |  | 1000000 | 1000000 | 2019 | 3RD QUARTER
STIP |  | No | [5 empty] | NHPP | 2759135 | BOONE | 6-78 | I 275 |  | 7.2 | 8.9 | ECONOMIC DEVELOPMENT | NEW INTERCHANGE(O) | IMPROVE FREIGHT MOBILITY AT I-275 AND GRAVES ROAD (CONTINUATION OF 6-8953: INTERCHANGE JUSTIFICATION STUDY ON I-275/GRAVES RD).(18CCR) | R |  | NH | 2020 | 4000000 | 4000000 |  |  | 0 |  |  | OBLIGATED | 2000000 | 8500000 | 10500000 | 2019 | 4TH QUARTER
STIP |  | No | [7 empty] | BOONE | 6-78 | I 275 |  | 7.2 | 8.9 | ECONOMIC DEVELOPMENT | NEW INTERCHANGE(O) | IMPROVE FREIGHT MOBILITY AT I-275 AND GRAVES ROAD (CONTINUATION OF 6-8953: INTERCHANGE JUSTIFICATION STUDY ON I-275/GRAVES RD).(18CCR) | U |  | NH | 2020 | 3000000 | 3000000 |  |  | 0 | [5 empty] | 0
STIP |  | No | [5 empty] | NHPP | 2759135 | BOONE | 6-78 | I 275 |  | 7.2 | 8.9 | ECONOMIC DEVELOPMENT | NEW INTERCHANGE(O) | IMPROVE FREIGHT MOBILITY AT I-275 AND GRAVES ROAD (CONTINUATION OF 6-8953: INTERCHANGE JUSTIFICATION STUDY ON I-275/GRAVES RD).(18CCR) | C |  | NH | 2020 | 5000000 | 5000000 |  |  | 0 |  |  | OBLIGATED | 24550850 | 36550085 | 61100935 | 2019 | 4TH QUARTER
STIP |  | No | [7 empty] | BOONE | 6-78.01 | I 275 |  | 7.2 | 8.9 | ECONOMIC DEVELOPMENT | PREFINANCD CONVRSN(O) | IMPROVE FREIGHT MOBILITY AT I-275 AND GRAVES ROAD (CONTINUATION OF 6-8953: INTERCHANGE JUSTIFICATION STUDY ON I-275/GRAVES RD). (18CCR) | R |  | NH | 2021 | 4000000 | 3200000 |  |  | 800000 | [5 empty] | 0
STIP |  | No | [7 empty] | BOONE | 6-78.01 | I 275 |  | 7.2 | 8.9 | ECONOMIC DEVELOPMENT | PREFINANCD CONVRSN(O) | IMPROVE FREIGHT MOBILITY AT I-275 AND GRAVES ROAD (CONTINUATION OF 6-8953: INTERCHANGE JUSTIFICATION STUDY ON I-275/GRAVES RD). (18CCR) | C |  | NH | 2022 | 10000000 | 8000000 |  |  | 2000000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.118 | 2019-08-19 | ADD PROJECT TO STIP; NEW. TIP FY 20-23, CHAPTER 7 - GROUPED PROJECTS, PAGE 7-5. | STP | 5227007 | BOONE | 6-78.5 | KY 20 |  | 10.87 | 14.68 | SAFETY | SAFETY(P) | GRAVES ROAD IMPROVEMENTS; KY 20 FROM MP 10.87 TO MP 14.68. (2018BOP) | C |  | STP | 2019 | 38640 | 38640 |  |  | 0 |  |  | OBLIGATED | 38640 |  | 38640 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.272 | 2021-01-14 | TIP FY 21-24, ADMIN MOD#6; UPDATE FISCAL YEAR & FUND AMOUNT; MOD | STP | 5227007 | BOONE | 6-78.5 | KY 20 |  | 10.87 | 14.68 | SAFETY | SAFETY(P) | GRAVES ROAD IMPROVEMENTS; KY 20 FROM MP 10.87 TO MP 14.68. (2018BOP) | C |  | STP | 2021 | 50000 | 40000 |  |  | 10000 | [5 empty] | 0
STIP |  | No | [5 empty] | NHPP | 0758103 | BOONE | 6-79 | I 75 |  | 184.148 | 185.34 | RELIABILITY | CONGESTION MITIGTN(O) | IMPROVE SAFETY, MOBILITY, OPERATIONS, AND GEOMETRICS AT THE JUNCTION OF I-75 AND I-275 AND THE SYSTEM-TO-SYSTEM RAMPS. | D |  | NH | 2019 | 2000000 | 2000000 |  |  | 0 |  |  | OBLIGATED | 1886652 | 113348 | 2000000 | 2019 | 1ST QUARTER
STIP | YES | No | [7 empty] | BOONE | 6-80 | I 75 |  | 171 | 171.8 | RELIABILITY | CONGESTION MITIGTN(O) | REDUCE CONGESTION AND IMPROVE TRAFFIC MOBILITY AT THE INTERCHANGE OF I-75 AND KY-14 IN WALTON. | P |  | NH | 2021 | 500000 | 400000 |  |  | 100000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.253 | 2020-10-26 | TIP FY 21-24, AMEND#2; UPDATE FISCAL YEAR AND FUND AMOUNTS; MOD |  |  | BOONE | 6-80 | I 75 |  | 171 | 171.8 | RELIABILITY | CONGESTION MITIGTN(O) | REDUCE CONGESTION AND IMPROVE TRAFFIC MOBILITY AT THE INTERCHANGE OF I-75 AND KY-14 IN WALTON. | P |  | NH | 2022 | 1090000 | 872000 |  |  | 218000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; ADD PROJECT TO STIP; NEW |  |  | BOONE | 6-105 | US 25 |  | 0.47 | 4.859 | RELIABILITY | PLANNING | CONDUCT PLANNING STUDY TO EVALUATE OPTIONS FOR RECONSTRUCTING US 25 BETWEEN KY 14 (MARY GRUBBS HIGHWAY) AND KY 338 (RICHWOOD ROAD). | P |  | STBG | 2021 | 500000 | 400000 |  |  | 100000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; ADD PROJECT TO STIP; NEW |  |  | BOONE | 6-113 | KY 338 |  | 0.756 | 4.613 | RELIABILITY | PLANNING | CONDUCT PLANNING STUDY TO EVALUATE OPTIONS FOR RECONSTRUCTING KY 338 (RICHWOOD ROAD) FROM TRIPLE CROWN BLVD TO US 42. | P |  | STBG | 2022 | 500000 | 400000 |  |  | 100000 | [5 empty] | 0
STIP | YES | No | [7 empty] | BOONE | 6-400.03 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | NORTHERN KENTUCKY RIDESHARE PROGRAM. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C |  | SNK | 2019 | 414000 | 331200 |  |  |  | 82800 |  |  |  |  | 0
STIP | YES | No | [7 empty] | BOONE | 6-400.14 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | NORTHERN KENTUCKY RIDESHARE PROGRAM. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C |  | SNK | 2019 | 44000 | 35200 |  |  |  | 8800 |  |  |  |  | 0
STIP | YES | No | [7 empty] | BOONE | 6-400.15 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | NORTHERN KENTUCKY RIDESHARE PROGRAM. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C |  | SNK | 2020 | 44000 | 35200 |  |  |  | 8800 |  |  |  |  | 0
STIP | YES | No | [7 empty] | BOONE | 6-400.16 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | NORTHERN KENTUCKY RIDESHARE PROGRAM. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C |  | SNK | 2021 | 44000 | 35200 |  |  |  | 8800 |  |  |  |  | 0
STIP | YES | No | [7 empty] | BOONE | 6-400.17 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | NORTHERN KENTUCKY RIDESHARE PROGRAM. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C |  | SNK | 2022 | 44000 | 35200 |  |  |  | 8800 |  |  |  |  | 0
STIP | YES | No | [7 empty] | BOONE | 6-401.09 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | OKI REGIONAL TRANSPORTATION PLANNING. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C |  | SNK | 2019 | 280000 | 224000 |  |  |  | 56000 |  |  |  |  | 0
STIP | YES | No | [7 empty] | BOONE | 6-401.14 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | OKI REGIONAL TRANSPORTATION PLANNING. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C |  | SNK | 2019 | 56000 | 44800 |  |  |  | 11200 |  |  |  |  | 0
STIP | YES | No | [7 empty] | BOONE | 6-401.15 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | OKI REGIONAL TRANSPORTATION PLANNING. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C |  | SNK | 2020 | 56000 | 44800 |  |  |  | 11200 |  |  |  |  | 0
STIP | YES | No | [7 empty] | BOONE | 6-401.16 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | OKI REGIONAL TRANSPORTATION PLANNING. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C |  | SNK | 2021 | 56000 | 44800 |  |  |  | 11200 |  |  |  |  | 0
STIP | YES | No | [7 empty] | BOONE | 6-401.17 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | OKI REGIONAL TRANSPORTATION PLANNING. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C |  | SNK | 2022 | 56000 | 44800 |  |  |  | 11200 |  |  |  |  | 0
STIP | YES | No | [7 empty] | BOONE | 6-401.18 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | N KY PLANNING FY18 AIR QUALITY, FIAM, LAND USE, RIDESHARE. (2016BOP) | P |  | SNK | 2019 | 150000 | 120000 |  |  |  | 30000 |  |  |  |  | 0
STIP | YES | No | [7 empty] | BOONE | 6-401.19 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | N KY PLANNING FY 2019 AIR QUALITY, FIAM, LAND USE, RIDESHARE. (2016BOP) | P |  | SNK | 2019 | 150000 | 120000 |  |  |  | 30000 |  |  |  |  | 0
STIP | YES | No | [7 empty] | BOONE | 6-401.2 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | N KY PLANNING FY 2020 AIR QUALITY, FIAM, LAND USE, RIDESHARE. | P |  | SNK | 2020 | 150000 | 120000 |  |  |  | 30000 |  |  |  |  | 0
STIP | YES | No | [7 empty] | BOONE | 6-401.21 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | N KY PLANNING FY 2021 AIR QUALITY, FIAM, LAND USE, RIDESHARE. | P |  | SNK | 2021 | 150000 | 120000 |  |  |  | 30000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.19 | 2020-05-19 | TIP FY 20-23; ADMIN MOD#9; UPDATE FUND AMOUNTS; MOD |  |  | BOONE CAMPBELL KENTON | 6-401.21 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | N KY PLANNING FY 2021 AIR QUALITY, FIAM, LAND USE, RIDESHARE. | P |  | SNK | 2021 | 179000 | 143200 |  |  |  | 35800 |  |  |  |  | 0
|  |  |  | AMENDMENT | 2018.003 | 2019-07-25 | TIP FY 20-23; ADD PROJECT TO STIP; NEW |  |  | BOONE CAMPBELL KENTON | 6-401.22 | [6 empty] | N KY Planning KY 22 Air Quality, FIAM, Land Use, Ridshare | P |  | SNK | 2022 | 187500 | 150000 |  |  |  | 18175 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.295 | 2021-04-13 | TIP FY 21-24; UPDATE FUND AMOUNTS (NOTE: LOCAL - $25,850 & CONTRIB SVCS - $17,300); MOD |  |  | BOONE CAMPBELL KENTON | 6-401.22 | [6 empty] | N KY Planning KY 22 Air Quality, FIAM, Land Use, Ridshare | P |  | SNK | 2022 | 215750 | 172600 |  |  |  | 43150 |  |  |  |  | 0
|  |  |  | AMENDMENT | 2018.003 | 2019-07-25 | TIP FY 20-23; ADD PROJECT TO STIP; NEW |  |  | BOONE CAMPBELL KENTON | 6-401.23 | [6 empty] | N KY Planning KY 23 Air Quality, FIAM, Land Use, Ridshare | P |  | SNK | 2023 | 187500 | 150000 |  |  |  | 18175 |  |  |  |  | 0
STIP | YES | No | [7 empty] | BOONE | 6-422 | CR 1002 | 0.558 | 2.1 | 2.658 | RELIABILITY | MATCHED FED FUNDS(O) | RECONSTRUCTION OF THE INTERSECTION OF CAMP ERNST ROAD AND LONGBRANCH ROAD. WIDENING OF 1,900 FEET OF LONGBRANCH ROAD. (2012BOP) | C |  | SNK | 2019 | 524640 | 419712 |  |  |  | 104928 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.038 | 2019-03-18 | TIP FY 18-21; ADMIN MOD#16; UPDATE FUND AMOUNTS; MOD | STPM | 3002329 | BOONE | 6-422 | CR 1002 | 0.558 | 2.1 | 2.658 | RELIABILITY | MATCHED FED FUNDS(O) | RECONSTRUCTION OF THE INTERSECTION OF CAMP ERNST ROAD AND LONGBRANCH ROAD. WIDENING OF 1,900 FEET OF LONGBRANCH ROAD. (2012BOP) | C |  | SNK | 2019 | 730081 | 584064 | 584065 |  |  | 146016 |  | OBLIGATED | 49649.85 |  | 49649.85 | 2020 | 1ST QUARTER | BOONE COUNTY
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.038 | 2019-03-18 | TIP FY 18-21; ADMIN MOD#16; ADD U PHASE TO STIP; NEW | STPM | 3002311 | BOONE | 6-422 | CR 1002 | 0.558 | 2.1 | 2.658 | RELIABILITY | MATCHED FED FUNDS(O) | RECONSTRUCTION OF THE INTERSECTION OF CAMP ERNST ROAD AND LONGBRANCH ROAD. WIDENING OF 1,900 FEET OF LONGBRANCH ROAD. (2012BOP) | U |  | SNK | 2019 | 81899 | 65519 | 65519 |  |  | 16380 |  |  |  |  | 0
STIP | YES | No | [7 empty] | BOONE | 6-423 | KY 3060 | 0.45 | 1.5 | 1.95 | RELIABILITY | MATCHED FED FUNDS(O) | CORRECT GEOMETRIC DEFICIENCIES AND ADD LEFT TURN LANES ON FROGTOWN ROAD AT TRIPLE CROWN BLVD AND CEDARWOOD.(2012BOP)(ADM. BY KYTC) | R |  | SNK | 2019 | 200000 | 160000 |  |  |  | 40000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.149 | 2019-11-15 | TIP FY 20-23; ADMIN MOD#4;UPDATE FUND AMOUNTS & FISCAL YEAR FROM 2019 TO 2020; MOD |  | 3002279 | BOONE | 6-423 | KY 3060 | 0.45 | 1.5 | 1.95 | RELIABILITY | MATCHED FED FUNDS(O) | CORRECT GEOMETRIC DEFICIENCIES AND ADD LEFT TURN LANES ON FROGTOWN ROAD AT TRIPLE CROWN BLVD AND CEDARWOOD.(2012BOP)(ADM. BY KYTC) | R |  | SNK | 2020 | 250000 | 200000 |  |  |  | 50000 |  | OBLIGATED | 160000 |  | 160000 | 2020 | 2ND QUARTER
STIP | YES | No | [7 empty] | BOONE | 6-423 | KY 3060 | 0.45 | 1.5 | 1.95 | RELIABILITY | MATCHED FED FUNDS(O) | CORRECT GEOMETRIC DEFICIENCIES AND ADD LEFT TURN LANES ON FROGTOWN ROAD AT TRIPLE CROWN BLVD AND CEDARWOOD.(2012BOP)(ADM. BY KYTC) | U |  | SNK | 2019 | 120000 | 96000 |  |  |  | 24000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.149 | 2019-11-15 | TIP FY 20-23; ADMIN MOD#4;UPDATE FUND AMOUNTS & FISCAL YEAR FROM 2019 TO 2020; MOD |  | 3002279 | BOONE | 6-423 | KY 3060 | 0.45 | 1.5 | 1.95 | RELIABILITY | MATCHED FED FUNDS(O) | CORRECT GEOMETRIC DEFICIENCIES AND ADD LEFT TURN LANES ON FROGTOWN ROAD AT TRIPLE CROWN BLVD AND CEDARWOOD.(2012BOP)(ADM. BY KYTC) | U |  | SNK | 2020 | 150000 | 120000 |  |  |  | 30000 |  | OBLIGATED | 60000 |  | 60000 | 2020 | 2ND QUARTER
STIP | YES | No | [7 empty] | BOONE | 6-423 | KY 3060 | 0.45 | 1.5 | 1.95 | RELIABILITY | MATCHED FED FUNDS(O) | CORRECT GEOMETRIC DEFICIENCIES AND ADD LEFT TURN LANES ON FROGTOWN ROAD AT TRIPLE CROWN BLVD AND CEDARWOOD.(2012BOP)(ADM. BY KYTC) | C |  | SNK | 2019 | 1200000 | 960000 |  |  |  | 240000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.149 | 2019-11-15 | TIP FY 20-23; ADMIN MOD#4;UPDATE FUND AMOUNTS & FISCAL YEAR FROM 2019 TO 2020; MOD |  |  | BOONE | 6-423 | KY 3060 | 0.45 | 1.5 | 1.95 | RELIABILITY | MATCHED FED FUNDS(O) | CORRECT GEOMETRIC DEFICIENCIES AND ADD LEFT TURN LANES ON FROGTOWN ROAD AT TRIPLE CROWN BLVD AND CEDARWOOD.(2012BOP)(ADM. BY KYTC) | C |  | SNK | 2020 | 1500000 | 1200000 |  |  |  | 300000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; UPDATE FISCAL YEAR; MOD |  |  | BOONE | 6-423 | KY 3060 | 0.45 | 1.5 | 1.95 | RELIABILITY | MATCHED FED FUNDS(O) | CORRECT GEOMETRIC DEFICIENCIES AND ADD LEFT TURN LANES ON FROGTOWN ROAD AT TRIPLE CROWN BLVD AND CEDARWOOD.(2012BOP)(ADM. BY KYTC) | C |  | SNK | 2021 | 1500000 | 1200000 |  |  |  | 300000 |  |  |  |  | 0
STIP | YES | No | [5 empty] | STPM | 8129004 | BOONE | 6-433 | KY 717 | 0.3 | 0.7 | 1 | SAFETY | SAFETY(P) | IMPROVE SAFETY ALONG KY 717 AT THE 90 DEGREE BEND NEAR THE CIN/NKY AIRPORT, 0.337 MI N OF KY 1017. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) (2014BOP) | C |  | SNK | 2019 | 1000000 | 800000 |  |  |  | 200000 |  | OBLIGATED | 1339001 | 184389 | 1523390 | 2019 | 2ND QUARTER
STIP | YES | No | [5 empty] | STPM | 3002303 | BOONE | 6-439 | KY 3159 |  | 0.119 | 0.652 | RELIABILITY | MATCHED FED FUNDS(O) | WIDEN KY 3159 (TED BUSHELMAN BLVD) FROM DOERING DRIVE TO KY 1017 (AERO PARKWAY) TO PROVIDE A TWO-WAY LEFT TURN LANE TO IMPROVE TRAFFIC FLOW FOR FUTURE DEVELOPMENT (2016BOP) | C |  | SNK | 2019 | 1000000 | 800000 |  |  |  | 200000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.002 | 2018-12-06 | TIP FY 18-21, AMENDMENT#11; CHANGE SCOPE WITH ADDITIONAL TRAVEL LANES, CHANGE FY AND ADD FEDERAL & LOCAL FUNDS; MOD | STPM | 3002303 | BOONE | 6-439 | KY 3159 |  | 0.119 | 0.652 | RELIABILITY | MATCHED FED FUNDS(O) | WIDEN KY 3159 (TED BUSHELMAN BLVD) FROM DOERING DRIVE TO KY 1017 (AERO PARKWAY) TO PROVIDE A TWO-WAY LEFT TURN LANE TO IMPROVE TRAFFIC FLOW FOR FUTURE DEVELOPMENT (2016BOP) | C |  | SNK | 2020 | 2515050 | 2012040 | 2012040 |  |  | 503010 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.158 | 2020-01-14 | TIP FY 20-23, ADMIN MOD#5; UPDATE FUND AMOUNTS; MOD | STPM | 3002303 | BOONE | 6-439 | KY 3159 |  | 0.119 | 0.652 | RELIABILITY | MATCHED FED FUNDS(O) | WIDEN KY 3159 (TED BUSHELMAN BLVD) FROM DOERING DRIVE TO KY 1017 (AERO PARKWAY) TO PROVIDE A TWO-WAY LEFT TURN LANE TO IMPROVE TRAFFIC FLOW FOR FUTURE DEVELOPMENT (2016BOP) | C |  | SNK | 2020 | 2707660 | 2166128 | 2166128 |  |  | 541532 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.245 | 2020-10-09 | TIP FY 21-24, ADMIN MOD#4; UPDATE FISCAL YEAR AND FUND AMOUNTS; MOD | STPM | 3002303 | BOONE | 6-439 | KY 3159 |  | 0.119 | 0.652 | RELIABILITY | MATCHED FED FUNDS(O) | WIDEN KY 3159 (TED BUSHELMAN BLVD) FROM DOERING DRIVE TO KY 1017 (AERO PARKWAY) TO PROVIDE A TWO-WAY LEFT TURN LANE TO IMPROVE TRAFFIC FLOW FOR FUTURE DEVELOPMENT (2016BOP) | C |  | SNK | 2021 | 3043571 | 2434857 |  |  |  | 608714 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.002 | 2018-12-06 | TIP FY 18-21, AMENDMENT#11; ADD D PHASE; CHANGE SCOPE WITH ADDITIONAL TRAVEL LANES; NEW | STPM | 3002303 | BOONE | 6-439 | KY 3159 |  | 0.119 | 0.652 | RELIABILITY | MATCHED FED FUNDS(O) | WIDEN KY 3159 (TED BUSHELMAN BLVD) FROM DOERING DRIVE TO KY 1017 (AERO PARKWAY) TO PROVIDE A TWO-WAY LEFT TURN LANE TO IMPROVE TRAFFIC FLOW FOR FUTURE DEVELOPMENT (2016BOP) | D |  | SNK | 2019 | 622500 | 498000 | 498000 |  |  | 124500 |  | OBLIGATED | 378000 |  | 378000 | 2019 | 4TH QUARTER | KENTON COUNTY AIRPORT BOARD
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.158 | 2020-01-14 | TIP FY 20-23, ADMIN MOD#5; UPDATE FISCAL YEAR AND FUND AMOUNTS; MOD | STPM | 3002303 | BOONE | 6-439 | KY 3159 |  | 0.119 | 0.652 | RELIABILITY | MATCHED FED FUNDS(O) | WIDEN KY 3159 (TED BUSHELMAN BLVD) FROM DOERING DRIVE TO KY 1017 (AERO PARKWAY) TO PROVIDE A TWO-WAY LEFT TURN LANE TO IMPROVE TRAFFIC FLOW FOR FUTURE DEVELOPMENT (2016BOP) | D |  | SNK | 2020 | 37500 | 30000 |  |  |  | 7500 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.002 | 2018-12-06 | TIP FY 18-21, AMENDMENT#11; ADD U PHASE; CHANGE SCOPE WITH ADDITIONAL TRAVEL LANES; NEW | STPM | 3002303 | BOONE | 6-439 | KY 3159 |  | 0.119 | 0.652 | RELIABILITY | MATCHED FED FUNDS(O) | WIDEN KY 3159 (TED BUSHELMAN BLVD) FROM DOERING DRIVE TO KY 1017 (AERO PARKWAY) TO PROVIDE A TWO-WAY LEFT TURN LANE TO IMPROVE TRAFFIC FLOW FOR FUTURE DEVELOPMENT (2016BOP) | U |  | SNK | 2019 | 230110 | 184088 | 184088 |  |  | 46022 |  |  |  |  | 0
STIP | YES | No | [7 empty] | BOONE | 6-440 | KY 237 |  | 6.617 | 9.418 | RELIABILITY | MATCHED FED FUNDS(O) | CONSTRUCT A MULTI-MODAL PATH ALONG KY 237 FROM STEPHENS ELEMENTARY SCHOOL NORTH TO KY 20/PETERSBURG ROAD (2016BOP). | C |  | SNK | 2019 | 1786400 | 1429120 |  |  |  | 357280 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.038 | 2019-03-18 | TIP FY 18-21; ADMIN MOD#16; UPDATE FISCAL YEAR FROM FY 2019 TO FY 2020 & FUND AMOUNTS; MOD |  |  | BOONE | 6-440 | KY 237 |  | 6.617 | 9.418 | RELIABILITY | MATCHED FED FUNDS(O) | CONSTRUCT A MULTI-MODAL PATH ALONG KY 237 FROM STEPHENS ELEMENTARY SCHOOL NORTH TO KY 20/PETERSBURG ROAD (2016BOP). | C |  | SNK | 2020 | 2233000 | 1786400 | 1786400 |  |  | 446600 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24; ADMIN MOD#3; UPDATE FISCAL YEAR; MOD |  |  | BOONE | 6-440 | KY 237 |  | 6.617 | 9.418 | RELIABILITY | MATCHED FED FUNDS(O) | CONSTRUCT A MULTI-MODAL PATH ALONG KY 237 FROM STEPHENS ELEMENTARY SCHOOL NORTH TO KY 20/PETERSBURG ROAD (2016BOP). | C |  | SNK | 2021 | 2233000 | 1786400 |  |  |  | 446600 |  |  |  |  | 0
STIP | YES | No | [5 empty] | STPM | 3002306 | BOONE KENTON | 6-441 | KY 3076 |  | 0.825 | 1.554 | RELIABILITY | BIKE/PED FACIL(O) | CONSTRUCT NEW SIDEWALKS, DEDICATED BIKE LANES AND RETAINING WALLS ALONG DOLWICK ROAD TO MINEOLA PIKE TO OLYMPIC BLVD IN THE CITY OF ERLANGER. (2016 BOP) | R |  | SNK | 2019 | 80000 | 64000 |  |  |  | 16000 |  | OBLIGATED |  | 48000 | 48000 | 2019 | 4TH QUARTER | CITY OF ERLANGER
STIP | YES | No | [7 empty] | BOONE KENTON | 6-441 | KY 3076 |  | 0.825 | 1.554 | RELIABILITY | BIKE/PED FACIL(O) | CONSTRUCT NEW SIDEWALKS, DEDICATED BIKE LANES AND RETAINING WALLS ALONG DOLWICK ROAD TO MINEOLA PIKE TO OLYMPIC BLVD IN THE CITY OF ERLANGER. (2016 BOP) | U |  | SNK | 2019 | 200000 | 160000 |  |  |  | 40000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.149 | 2019-11-15 | TIP FY 20-23; ADMIN MOD#4; UPDATE FUND AMOUNT & FISCAL YEAR FROM 2019 TO 2020; MOD |  |  | BOONE KENTON | 6-441 | KY 3076 |  | 0.825 | 1.554 | RELIABILITY | BIKE/PED FACIL(O) | CONSTRUCT NEW SIDEWALKS, DEDICATED BIKE LANES AND RETAINING WALLS ALONG DOLWICK ROAD TO MINEOLA PIKE TO OLYMPIC BLVD IN THE CITY OF ERLANGER. (2016 BOP) | U |  | SNK | 2020 | 156250 | 125000 |  |  |  | 31250 |  |  |  |  | 0
STIP | YES | No | [7 empty] | BOONE KENTON | 6-441 | KY 3076 |  | 0.825 | 1.554 | RELIABILITY | BIKE/PED FACIL(O) | CONSTRUCT NEW SIDEWALKS, DEDICATED BIKE LANES AND RETAINING WALLS ALONG DOLWICK ROAD TO MINEOLA PIKE TO OLYMPIC BLVD IN THE CITY OF ERLANGER. (2016 BOP) | C |  | SNK | 2019 | 1576000 | 1260800 |  |  |  | 315200 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.149 | 2019-11-15 | TIP FY 20-23; ADMIN MOD#4; UPDATE FUND AMOUNT & FISCAL YEAR FROM 2019 TO 2020; MOD |  |  | BOONE KENTON | 6-441 | KY 3076 |  | 0.825 | 1.554 | RELIABILITY | BIKE/PED FACIL(O) | CONSTRUCT NEW SIDEWALKS, DEDICATED BIKE LANES AND RETAINING WALLS ALONG DOLWICK ROAD TO MINEOLA PIKE TO OLYMPIC BLVD IN THE CITY OF ERLANGER. (2016 BOP) | C |  | SNK | 2020 | 1375000 | 1100000 |  |  |  | 275000 |  |  |  |  | 0
STIP | YES | No | [7 empty] | BOONE | 6-442 | CR 1001 |  | 2.168 | 2.169 | RELIABILITY | MATCHED FED FUNDS(O) | ADD A LEFT TURN LANE ON SB CAMP ERNST ROAD AT LONGBRANCH ROAD (2016BOP). | R |  | SNK | 2019 | 400000 | 320000 |  |  |  | 80000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.038 | 2019-03-18 | TIP FY 18-21; ADMIN MOD#16; UPDATE FISCAL YEAR FROM FY 2019 TO FY 2020 & FUND AMOUNTS; MOD |  |  | BOONE | 6-442 | CR 1001 |  | 2.168 | 2.169 | RELIABILITY | MATCHED FED FUNDS(O) | ADD A LEFT TURN LANE ON SB CAMP ERNST ROAD AT LONGBRANCH ROAD (2016BOP). | R |  | SNK | 2020 | 500000 | 400000 | 400000 |  |  | 100000 |  |  |  |  | 0
STIP | YES | No | [7 empty] | BOONE | 6-442 | CR 1001 |  | 2.168 | 2.169 | RELIABILITY | MATCHED FED FUNDS(O) | ADD A LEFT TURN LANE ON SB CAMP ERNST ROAD AT LONGBRANCH ROAD (2016BOP). | U |  | SNK | 2019 | 69271 | 55416.8 |  |  |  | 13854.2 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.038 | 2019-03-18 | TIP FY 18-21; ADMIN MOD#16; UPDATE FISCAL YEAR FROM FY 2019 TO FY 2020 & FUND AMOUNTS; MOD |  |  | BOONE | 6-442 | CR 1001 |  | 2.168 | 2.169 | RELIABILITY | MATCHED FED FUNDS(O) | ADD A LEFT TURN LANE ON SB CAMP ERNST ROAD AT LONGBRANCH ROAD (2016BOP). | U |  | SNK | 2020 | 86589 | 69271 | 69271 |  |  | 17318 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.038 | 2019-03-18 | TIP FY 18-21; ADMIN MOD#16; UPDATE FISCAL YEAR FROM FY 2019 TO FY 2020 & FUND AMOUNTS; MOD |  |  | BOONE | 6-442 | CR 1001 |  | 2.168 | 2.169 | RELIABILITY | MATCHED FED FUNDS(O) | ADD A LEFT TURN LANE ON SB CAMP ERNST ROAD AT LONGBRANCH ROAD (2016BOP). | U |  | SNK | 2020 | 577261 | 461809 | 461809 |  |  | 115452 |  |  |  |  | 0
STIP | YES | No | [7 empty] | BOONE | 6-442 | CR 1001 |  | 2.168 | 2.169 | RELIABILITY | MATCHED FED FUNDS(O) | ADD A LEFT TURN LANE ON SB CAMP ERNST ROAD AT LONGBRANCH ROAD (2016BOP). | C |  | SNK | 2019 | 461809 | 369447.2 |  |  |  | 92361.8 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.261 | 2020-11-16 | TIP FY 21-24; ADMIN MOD#5; UPDATE PROEJCT DESCRIPTION, FISCAL YEAR AND FUND AMOUNT; MOD |  |  | BOONE | 6-442 | CR 1001 |  | 2.168 | 2.169 | RELIABILITY | MATCHED FED FUNDS(O) | IMPROVE SAFETY AND TRAFFIC CONGESTION AT THE CAMP ERNST ROAD AND LONGBRANCH ROAD INTERSECTION. | C |  | SNK | 2021 | 577261 | 461809 |  |  |  | 115452
STIP | YES | No | [7 empty] | BOONE | 6-444 | KY 236 | 1.594 | 0 | 1.594 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE SAFETY AND REDUCE CONGESTION ALONG KY-236 (DONALDSON ROAD) FROM KY-842 (HOUSTON ROAD) TO KY-3076 (MINEOLA PIKE). (18CCR) | P |  | STP | 2019 | 2000000 | 2000000 |  |  | 0 | [5 empty] | 0
STIP |  | No | [5 empty] | STP | 3002326 | BOONE | 6-444 | KY 236 | 1.594 | 0 | 1.594 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE SAFETY AND REDUCE CONGESTION ALONG KY-236 (DONALDSON ROAD) FROM KY-842 (HOUSTON ROAD) TO KY-3076 (MINEOLA PIKE). (18CCR) | D |  | STP | 2020 | 5000000 | 5000000 |  |  | 0 |  |  | OBLIGATED | 2000000 |  | 2000000 | 2019 | 1ST QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.253 | 2020-10-26 | TIP FY 21-24, AMEND#2; UPDATE FISCAL YEAR AND FUND AMOUNTS; MOD |  |  | BOONE | 6-444 | KY 236 | 1.594 | 0 | 1.594 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE SAFETY AND REDUCE CONGESTION ALONG KY-236 (DONALDSON ROAD) FROM KY-842 (HOUSTON ROAD) TO KY-3076 (MINEOLA PIKE). (18CCR) | D |  | STP | 2021 | 1412500 | 1130000 |  |  | 282500 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.253 | 2020-10-26 | TIP FY 21-24, AMEND#2; ADD R PHASE TO STIP; NEW |  |  | BOONE | 6-444 | KY 236 | 1.594 | 0 | 1.594 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE SAFETY AND REDUCE CONGESTION ALONG KY-236 (DONALDSON ROAD) FROM KY-842 (HOUSTON ROAD) TO KY-3076 (MINEOLA PIKE). (18CCR) | R |  | STP | 2021 | 750000 | 600000 |  |  | 150000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.253 | 2020-10-26 | TIP FY 21-24, AMEND#2; ADD U PHASE TO STIP; NEW |  |  | BOONE | 6-444 | KY 236 | 1.594 | 0 | 1.594 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE SAFETY AND REDUCE CONGESTION ALONG KY-236 (DONALDSON ROAD) FROM KY-842 (HOUSTON ROAD) TO KY-3076 (MINEOLA PIKE). (18CCR) | U |  | STP | 2021 | 1250000 | 1000000 |  |  | 250000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.253 | 2020-10-26 | TIP FY 21-24, AMEND#2; ADD C PHASE TO STIP; NEW |  |  | BOONE | 6-444 | KY 236 | 1.594 | 0 | 1.594 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE SAFETY AND REDUCE CONGESTION ALONG KY-236 (DONALDSON ROAD) FROM KY-842 (HOUSTON ROAD) TO KY-3076 (MINEOLA PIKE). (18CCR) | C |  | STP | 2022 | 9387500 | 7510000 |  |  | 1877500 | [5 empty] | 0
STIP |  | No | [7 empty] | BOONE | 6-445 | KY 3076 | 1.05 | 0 | 1.05 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE FREIGHT MOBILITY AND REDUCE CONGESTION ON KY-3076 (MINEOLA PIKE) FROM KY-236 TO I-275. (18CCR) | D |  | STP | 2019 | 1500000 | 1500000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.253 | 2020-10-26 | TIP FY 21-24, AMEND#2; UPDATE FISCAL YEAR AND FUND AMOUNTS; MOD |  |  | BOONE | 6-445 | KY 3076 | 1.05 | 0 | 1.05 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE FREIGHT MOBILITY AND REDUCE CONGESTION ON KY-3076 (MINEOLA PIKE) FROM KY-236 TO I-275. (18CCR) | D |  | STP | 2021 | 970000 | 776000 |  |  | 194000 | [5 empty] | 0
STIP |  | No | [7 empty] | BOONE | 6-445 | KY 3076 | 1.05 | 0 | 1.05 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE FREIGHT MOBILITY AND REDUCE CONGESTION ON KY-3076 (MINEOLA PIKE) FROM KY-236 TO I-275. (18CCR) | R |  | STP | 2022 | 4000000 | 3200000 |  |  | 800000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.253 | 2020-10-26 | TIP FY 21-24, AMEND#2; UPDATE FISCAL YEAR AND FUND AMOUNTS; MOD |  |  | BOONE | 6-445 | KY 3076 | 1.05 | 0 | 1.05 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE FREIGHT MOBILITY AND REDUCE CONGESTION ON KY-3076 (MINEOLA PIKE) FROM KY-236 TO I-275. (18CCR) | R |  | STP | 2021 | 3800000 | 3040000 |  |  | 760000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.253 | 2020-10-26 | TIP FY 21-24, AMEND#2; ADD U PHASE TO STIP; NEW |  |  | BOONE | 6-445 | KY 3076 | 1.05 | 0 | 1.05 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE FREIGHT MOBILITY AND REDUCE CONGESTION ON KY-3076 (MINEOLA PIKE) FROM KY-236 TO I-275. (18CCR) | U |  | STP | 2021 | 750000 | 600000 |  |  | 150000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.253 | 2020-10-26 | TIP FY 21-24, AMEND#2; ADD C PHASE TO STIP; NEW |  |  | BOONE | 6-445 | KY 3076 | 1.05 | 0 | 1.05 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE FREIGHT MOBILITY AND REDUCE CONGESTION ON KY-3076 (MINEOLA PIKE) FROM KY-236 TO I-275. (18CCR) | C |  | STP | 2022 | 6400000 | 5120000 |  |  | 1280000 | [5 empty] | 0
STIP | YES | No | [5 empty] | NHPP | 5138069 | BOONE | 6-446 | US 42 |  | 12.508 | 13.489 | NEW ROUTES | NEW ROUTE(O) | PROVIDE EAST-WEST CONNECTIVITY AND IMPROVED MOBILITY FROM KY-237 (PLEASANT VALLEY ROAD) THRU KY-842 (HOPEFUL CHURCH ROAD) TO MALL ROAD/I-75 INTERCHANGE. (18CCR) | D |  | NH | 2020 | 1500000 | 1500000 |  |  | 0 |  |  | OBLIGATED |  | 200000 | 200000 | 2019 | 3RD QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24; ADMIN MOD#3; UPDATE FISCAL YEAR; MOD |  |  | BOONE | 6-446 | US 42 |  | 12.508 | 13.489 | NEW ROUTES | NEW ROUTE(O) | PROVIDE EAST-WEST CONNECTIVITY AND IMPROVED MOBILITY FROM KY-237 (PLEASANT VALLEY ROAD) THRU KY-842 (HOPEFUL CHURCH ROAD) TO MALL ROAD/I-75 INTERCHANGE. (18CCR) | D |  | NH | 2023 | 1875000 | 1500000 |  |  | 375000 | [5 empty] | 0
STIP MOD | YES | No |  | ADMINISTRATIVE MODIFICATION | 2018.002 | 2018-12-06 | TIP FY 18-21; AMENDMENT#11; ADD C PHASE; NEW |  |  | BOONE | 6-446 | US 42 |  | 12.508 | 13.489 | NEW ROUTES | NEW ROUTE(O) | PROVIDE EAST-WEST CONNECTIVITY AND IMPROVED MOBILITY FROM KY-237 (PLEASANT VALLEY ROAD) THRU KY-842 (HOPEFUL CHURCH ROAD) TO MALL ROAD/I-75 INTERCHANGE. (18CCR) | C |  | NH | 2022 | 18270000 | 18270000 |  | 18270000 | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.253 | 2020-10-26 | TIP FY 21-24, AMEND#2; ADD D PHASE TO STIP; NEW |  |  | BOONE | 6-447 | US 25 |  | 5.085 | 9.2 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE MOBILITY AND REDUCE CONGESTION ON US-25 FROM WINNING COLORS DRIVE TO THE NORFOLK SOUTHERN RAILROAD CROSSING SOUTH OF KY-1829 (INDUSTRIAL ROAD); EXCLUDES GRADE SEPARATION AT KY-536. (2020CCR) | D |  | STP | 2021 | 3720000 | 2976000 |  |  | 744000 | [5 empty] | 0
|  |  |  | AMENDMENT | 2018.003 | 2019-07-25 | TIP FY 20-23; ADD PROJECT TO STIP; NEW |  |  | BOONE | 6-459 |  |  |  |  | SAFETY | BIKE/PED FACIL(0) | CONSTRUCT CONNOR ROAD MULTI-USE PATH. (2018BOP) | D |  | SNK | 2020 | 225000 | 102500 |  |  | 10000 | 112500 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.149 | 2019-11-15 | TIP FY 20-23; ADMIN MOD#4; UPDATE DESCRIPTION & FUND AMOUNTS; MOD |  | 3002342 | BOONE | 6-459 |  |  |  |  | SAFETY | BIKE/PED FACIL(0) | ALONG CONNER ROAD BETWEEN KY 237 (NORTH BEND RD) AND KY 20 (PETERSBURG RD). ADDITIONAL SIDEWALK CONNECT. | D |  | SNK | 2020 | 215000 | 102500 |  |  | 10000 | 102500 |  | OBLIGATED | 112500 |  | 112500 | 2020 | 1ST QUARTER | BOONE COUNTY
|  |  |  | AMENDMENT | 2018.003 | 2019-07-25 | TIP FY 20-23; ADD PROJECT TO STIP; NEW |  |  | BOONE | 6-459 |  |  |  |  | SAFETY | BIKE/PED FACIL(0) | CONSTRUCT CONNOR ROAD MULTI-USE PATH. (2018BOP) | R |  | SNK | 2021 | 275000 | 150000 |  |  |  | 125000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.149 | 2019-11-15 | TIP FY 20-23; ADMIN MOD#4; UPDATE DESCRIPTION & FUND AMOUNTS; MOD |  |  | BOONE | 6-459 |  |  |  |  | SAFETY | BIKE/PED FACIL(0) | ALONG CONNER ROAD BETWEEN KY 237 (NORTH BEND RD) AND KY 20 (PETERSBURG RD). ADDITIONAL SIDEWALK CONNECT. | R |  | SNK | 2021 | 300000 | 150000 |  |  |  | 150000 |  |  |  |  | 0
|  |  |  | AMENDMENT | 2018.003 | 2019-07-25 | TIP FY 20-23; ADD PROJECT TO STIP; NEW |  |  | BOONE | 6-459 |  |  |  |  | SAFETY | BIKE/PED FACIL(0) | CONSTRUCT CONNOR ROAD MULTI-USE PATH. (2018BOP) | C |  | SNK | 2022 | 1125000 | 750000 |  |  |  | 375000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.149 | 2019-11-15 | TIP FY 20-23; ADMIN MOD#4; UPDATE DESCRIPTION & FUND AMOUNTS; MOD |  |  | BOONE | 6-459 |  |  |  |  | SAFETY | BIKE/PED FACIL(0) | ALONG CONNER ROAD BETWEEN KY 237 (NORTH BEND RD) AND KY 20 (PETERSBURG RD). ADDITIONAL SIDEWALK CONNECT. | C |  | SNK | 2022 | 1500000 | 750000 |  |  |  | 750000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.291 | 2021-04-23 | OKI MPO AREA TIP FY 21-24, GROUPED PROJECTS, CHAPTER 6, PAGE 6-3. |  |  | BOONE | 6-901 | I 275 | 0 | 0.3 |  | RELIABILITY | SAFETY-HAZARD ELIM(P) | High Friction Surface Treatment on ramp from I-275 WB to KY 237 SB> | C |  | SAF | 2021 | 140000 | 140000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.303 | 2021-05-12 | TIP FY 21-24, ADMIN MOD#10; ADD PROJECT TO STIP; NEW |  |  | BOONE | 6-901 | I 275 | 0 | 0.3 |  | RELIABILITY | SAFETY-HAZARD ELIM(P) | High Friction Surface Treatment on ramp from I-275 WB to KY 237 SB> | C |  | SAF | 2021 | 140000 | 126000 |  |  | 14000 | [5 empty] | 0
STIP | YES | No | [7 empty] | BOONE | 6-966 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | DEDICATED FEDERAL-AID STP FUNDS EARMARKED FOR NKY URBANIZED AREA AND SUBJECT TO MPO CONTROL FOR FY 2018. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C |  | SNK | 2019 | 35140000 | 28112000 |  |  |  | 7028000 |  |  |  |  | 0
STIP | YES | No | [7 empty] | BOONE | 6-966.07 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | DEDICATED FEDERAL-AID STP FUNDS EARMARKED FOR NKY URBANIZED AREA AND SUBJECT TO MPO CONTROL FOR FY 2019 (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C |  | SNK | 2019 | 9100000 | 7280000 |  |  |  | 1820000 |  |  |  |  | 0
STIP | YES | No | [7 empty] | BOONE | 6-966.08 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | DEDICATED FEDERAL-AID STP FUNDS EARMARKED FOR NKY URBANIZED AREA AND SUBJECT TO MPO CONTROL FOR FY 2020. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C |  | SNK | 2020 | 9200000 | 7360000 |  |  |  | 1840000 |  |  |  |  | 0
STIP | YES | No | [7 empty] | BOONE | 6-966.09 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | DEDICATED FEDERAL-AID STP FUNDS EARMARKED FOR NKY URBANIZED AREA AND SUBJECT TO MPO CONTROL FOR FY 2021. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C |  | SNK | 2021 | 9200000 | 7360000 |  |  |  | 1840000 |  |  |  |  | 0
STIP | YES | No | [7 empty] | BOONE | 6-966.1 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | DEDICATED FEDERAL-AID STP FUNDS EARMARKED FOR NKY URBANIZED AREA AND SUBJECT TO MPO CONTROL FOR FY 2022. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C |  | SNK | 2022 | 9200000 | 7360000 |  |  |  | 1840000 |  |  |  |  | 0
STIP |  | No | [7 empty] | BOONE | 6-1087 | KY 842 | 0.074 | 0.094 | 0.141 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER NS (CNO&TP)RR ON RICHARDSON ROAD (KY 842) 0.14 MI E OF US 25 NEAR INDEPENDENCE (008B00092N) | D |  | BR/STP | 2019 | 480000 | 297600 |  |  | 182400 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; UPDATE FISCAL YEAR & FUND AMOUNTS; MOD |  |  | BOONE | 6-1087 | KY 842 | 0.074 | 0.094 | 0.141 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER NS (CNO&TP)RR ON RICHARDSON ROAD (KY 842) 0.14 MI E OF US 25 NEAR INDEPENDENCE (008B00092N) | D |  | STBG | 2021 | 500000 | 400000 |  |  | 100000 | [5 empty] | 0
STIP |  | No | [7 empty] | BOONE | 6-1087 | KY 842 | 0.074 | 0.094 | 0.141 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER NS (CNO&TP)RR ON RICHARDSON ROAD (KY 842) 0.14 MI E OF US 25 NEAR INDEPENDENCE (008B00092N) | R |  | BR/STP | 2020 | 2800000 | 1736000 |  |  | 1064000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; UPDATE FISCAL YEAR & FUND AMOUNTS; MOD |  |  | BOONE | 6-1087 | KY 842 | 0.074 | 0.094 | 0.141 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER NS (CNO&TP)RR ON RICHARDSON ROAD (KY 842) 0.14 MI E OF US 25 NEAR INDEPENDENCE (008B00092N) | R |  | STBG | 2021 | 3000000 | 2400000 |  |  | 600000 | [5 empty] | 0
STIP |  | No | [7 empty] | BOONE | 6-1087 | KY 842 | 0.074 | 0.094 | 0.141 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER NS (CNO&TP)RR ON RICHARDSON ROAD (KY 842) 0.14 MI E OF US 25 NEAR INDEPENDENCE (008B00092N) | U |  | BR/STP | 2020 | 350000 | 217000 |  |  | 133000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; UPDATE FISCAL YEAR & FUND AMOUNTS; MOD |  |  | BOONE | 6-1087 | KY 842 | 0.074 | 0.094 | 0.141 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER NS (CNO&TP)RR ON RICHARDSON ROAD (KY 842) 0.14 MI E OF US 25 NEAR INDEPENDENCE (008B00092N) | U |  | STBG | 2021 | 1000000 | 800000 |  |  | 200000 | [5 empty] | 0
STIP |  | No | [7 empty] | BOONE | 6-1087 | KY 842 | 0.074 | 0.094 | 0.141 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER NS (CNO&TP)RR ON RICHARDSON ROAD (KY 842) 0.14 MI E OF US 25 NEAR INDEPENDENCE (008B00092N) | C |  | BR/STP | 2022 | 3500000 | 2170000 |  |  | 1330000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; UPDATE FISCAL YEAR & FUND AMOUNTS; MOD |  |  | BOONE | 6-1087 | KY 842 | 0.074 | 0.094 | 0.141 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER NS (CNO&TP)RR ON RICHARDSON ROAD (KY 842) 0.14 MI E OF US 25 NEAR INDEPENDENCE (008B00092N) | C |  | STBG | 2023 | 4000000 | 3200000 |  |  | 800000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.039 | 2019-03-19 | ADDING FUNDS TO PROJECT; OKI TIP FY 18-21, GROUPED PROJECTS, APPENDIX C, PG 33; MOD | HSIP | 5138067 | BOONE | 6-9010 | US 42 |  | 0 | 5.673 | SAFETY | SAFETY(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON US 42 FROM THE GALLATIN/BOONE COUNTY LINE TO KY 338. (2014BOP) | C |  | SAF | 2019 | 1816000 | 1816000 |  |  | 0 |  |  | OBLIGATED | 2288626 |  | 2288626 | 2019 | 3RD QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.069 | 2019-05-13 | TIP FY 18-21; ADMIN MOD#18; ADD PROJECT TO STIP; NEW | HSIP | 9010390 | BOONE | 6-9017.5 | KY 1829 |  | 0.225 | 0.375 | SAFETY | SAFETY-HAZARD ELIM(P) | UPDATE THE TRAFFIC SIGNAL TO INCLUDE REFLECTIVE BACKPLATES AND DOUBLE RED SIGNAL HEADS, INSTALL MEDIAN ACCESS CONTROL, AND UPDATES TO THE SIGNING NEAR THE INTERSECTION OF KY 1829 & SAFEWAY DR (2018BOP) | C |  | SAF | 2019 | 75000 | 75000 |  |  | 0 |  |  | OBLIGATED |  | 81000 | 81000 | 2019 | 3RD QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.028 | 2019-02-18 | TIP FY 18-21; ADMIN MOD#15; ADD TO STIP; NEW | HSIP | 9010352 | BOONE | 6-9022 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | PRELIMINARY DESIGN AND STUDY TO DETERMINE LOW COST IMPROVEMENTS AT VARIOUS INTERSECTIONS WITHIN DISTRICT 6. (2018BOP) | D |  | SAF | 2019 | 350000 | 350000 |  |  | 0 |  |  | OBLIGATED |  | 350000 | 350000 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; ADD PROJECT TO STIP; NEW |  |  | BOONE | 6-20001 | I 71 |  | 69.89 | 77.724 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-71 BOTH DIRECTION(S) FROM MILEPOINT 69.89 TO MILEPOINT 77.724. (2020CCR) | D |  | NH | 2022 | 650000 | 520000 |  |  | 130000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; ADD PROJECT TO STIP; NEW |  |  | BOONE | 6-20001 | I 71 |  | 69.89 | 77.724 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-71 BOTH DIRECTION(S) FROM MILEPOINT 69.89 TO MILEPOINT 77.724. (2020CCR) | C |  | NH | 2023 | 3000000 | 2400000 |  |  | 600000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; ADD PROJECT TO STIP; NEW |  |  | BOONE | 6-20001 | I 71 |  | 69.89 | 77.724 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-71 BOTH DIRECTION(S) FROM MILEPOINT 69.89 TO MILEPOINT 77.724. (2020CCR) | C |  | NH | 2024 | 3500000 | 2800000 |  |  | 700000 | [5 empty] | 0
STIP | YES | No | [7 empty] | BOONE | 6-20002 | I 75 |  | 169.439 | 183.08 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-75 BOTH DIRECTION(S) FROM MILEPOINT 169.439 TO MILEPOINT 183.08. | D |  | PM/NH | 2020 | 2180000 | 1744000 |  |  | 436000 | [5 empty] | 0
STIP | YES | No | [7 empty] | BOONE | 6-20002 | I 75 |  | 169.439 | 183.08 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-75 BOTH DIRECTION(S) FROM MILEPOINT 169.439 TO MILEPOINT 183.08. | C |  | PM/NH | 2020 | 21800000 | 17440000 |  |  | 4360000 | [5 empty] | 0
[8 empty] | NHPPIM | 0757148 | BOONE | 6-20002.1 | I 75 |  | 178.02 | 183.08 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-75 BOTH DIRECTION(S) FROM MILEPOINT 178.02 TO MILEPOINT 183.08. (2018BOP)(LET W/ 6-14.50) | C |  | PM/NH | 2019 | [7 empty] | OBLIGATED | 13288330 |  | 13288330 | 2019 | 1ST QUARTER
STIP | YES | Yes | OKI MPO requires the federal funding splits before proceeding to incorporate this project into the OKI TIP. Program Management just confirmed PM/NH federal funds for this project will use NH with a Fed/State split of 90/10 per Ivan - TMH 2/15/19. | [6 empty] | BOONE | 6-20004 | I 75 |  | 183.08 | 183.312 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT ON I-75 BOTH DIRECTION(S) FROM MILEPOINT 183.08 (182.9 NON-CARDINAL) TO MILEPOINT 183.312. | D |  | PM/NH | 2021 | 100000 | 80000 |  |  | 20000 | [5 empty] | 0
STIP | YES | Yes | OKI MPO requires the federal funding splits before proceeding to incorporate this project into the OKI TIP. Program Management just confirmed PM/NH federal funds for this project will use NH with a Fed/State split of 90/10 per Ivan - TMH 2/15/19. | [6 empty] | BOONE | 6-20004 | I 75 |  | 183.08 | 183.312 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT ON I-75 BOTH DIRECTION(S) FROM MILEPOINT 183.08 (182.9 NON-CARDINAL) TO MILEPOINT 183.312. | C |  | PM/NH | 2021 | 1000000 | 800000 |  |  | 200000 | [5 empty] | 0
STIP | YES | Yes | OKI MPO requires the federal funding splits before proceeding to incorporate this project into the OKI TIP. Program Management just confirmed PM/NH federal funds for this project will use NH with a Fed/State split of 90/10 per Ivan - TMH 2/15/19. | [6 empty] | BOONE | 6-20005 | I 275 |  | 13.08 | 13.7 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-275 BOTH DIRECTION(S) FROM MILEPOINT 13.076 TO MILEPOINT 13.7 | D |  | PM/NH | 2021 | 50000 | 40000 |  |  | 10000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; UPDATE FISCAL YEAR; MOD |  |  | BOONE | 6-20005 | I 275 |  | 13.08 | 13.7 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-275 BOTH DIRECTION(S) FROM MILEPOINT 13.076 TO MILEPOINT 13.7 | D |  | PM/NH | 2022 | 50000 | 40000 |  |  | 10000 | [5 empty] | 0
STIP | YES | Yes | OKI MPO requires the federal funding splits before proceeding to incorporate this project into the OKI TIP. Program Management just confirmed PM/NH federal funds for this project will use NH with a Fed/State split of 90/10 per Ivan - TMH 2/15/19. | [6 empty] | BOONE | 6-20005 | I 275 |  | 13.08 | 13.7 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-275 BOTH DIRECTION(S) FROM MILEPOINT 13.076 TO MILEPOINT 13.7 | C |  | PM/NH | 2021 | 500000 | 400000 |  |  | 100000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; UPDATE FISCAL YEAR; MOD |  |  | BOONE | 6-20005 | I 275 |  | 13.08 | 13.7 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-275 BOTH DIRECTION(S) FROM MILEPOINT 13.076 TO MILEPOINT 13.7 | C |  | PM/NH | 2022 | 500000 | 400000 |  |  | 100000 | [5 empty] | 0
STIP | YES | Yes | OKI MPO requires the federal funding splits before proceeding to incorporate this project into the OKI TIP. Program Management just confirmed PM/NH federal funds for this project will use NH with a Fed/State split of 90/10 per Ivan - TMH 2/15/19. | [6 empty] | BOONE | 6-20006 | I 275 |  | 1.58 | 7.25 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT ON I-275 BOTH DIRECTION(S) FROM MILEPOINT 1.58 TO MILEPOINT 7.25 | D |  | PM/NH | 2021 | 850000 | 680000 |  |  | 170000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; UPDATE FISCAL YEAR; MOD |  |  | BOONE | 6-20006 | I 275 |  | 1.58 | 7.25 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT ON I-275 BOTH DIRECTION(S) FROM MILEPOINT 1.58 TO MILEPOINT 7.25 | D |  | PM/NH | 2022 | 850000 | 680000 |  |  | 170000 | [5 empty] | 0
STIP | YES | Yes | OKI MPO requires the federal funding splits before proceeding to incorporate this project into the OKI TIP. Program Management just confirmed PM/NH federal funds for this project will use NH with a Fed/State split of 90/10 per Ivan - TMH 2/15/19. | [6 empty] | BOONE | 6-20006 | I 275 |  | 1.58 | 7.25 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT ON I-275 BOTH DIRECTION(S) FROM MILEPOINT 1.58 TO MILEPOINT 7.25 | C |  | PM/NH | 2021 | 8500000 | 6800000 |  |  | 1700000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; UPDATE FISCAL YEAR & FUND AMOUNTS; MOD |  |  | BOONE | 6-20006 | I 275 |  | 1.58 | 7.25 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT ON I-275 BOTH DIRECTION(S) FROM MILEPOINT 1.58 TO MILEPOINT 7.25 | C |  | PM/NH | 2023 | 4000000 | 3200000 |  |  | 800000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; UPDATE FISCAL YEAR & FUND AMOUNTS; MOD |  |  | BOONE | 6-20006 | I 275 |  | 1.58 | 7.25 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT ON I-275 BOTH DIRECTION(S) FROM MILEPOINT 1.58 TO MILEPOINT 7.25 | C |  | PM/NH | 2024 | 4400000 | 3500000 |  |  | 900000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; ADD PROJECT TO STIP; NEW |  |  | BOONE | 6-20007 | I 275 |  | 7.25 | 13.08 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT ON I-275 BOTH DIRECTION(S) FROM MILEPOINT 7.25 TO MILEPOINT 13.08 (13.56 NON-CARDINAL) | D |  | PM/NH | 2024 | 650000 | 520000 |  |  | 130000 | [5 empty] | 0
STIP | YES | No | [7 empty] | BOONE | 6-20008 | KY 18 |  | 15.256 | 16.632 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT. | D |  | PM/STP | 2019 | 225000 | 180000 |  |  | 45000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.149 | 2019-11-15 | TIP FY 20-23; ADMIN MOD#4; UPDATE FY FROM 2019 TO 2020; MOD |  |  | BOONE | 6-20008 | KY 18 |  | 15.256 | 16.632 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT. | D |  | PM/STP | 2020 | 225000 | 180000 |  |  | 45000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; UPDATE FISCAL YEAR; MOD |  |  | BOONE | 6-20008 | KY 18 |  | 15.256 | 16.632 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT. | D |  | PM/STP | 2021 | 225000 | 180000 |  |  | 45000 | [5 empty] | 0
STIP | YES | No | [7 empty] | BOONE | 6-20008 | KY 18 |  | 15.256 | 16.632 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT. | C |  | PM/STP | 2019 | 2250000 | 1800000 |  |  | 450000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.149 | 2019-11-15 | TIP FY 20-23; ADMIN MOD#4; UPDATE FY FROM 2019 TO 2020; MOD |  |  | BOONE | 6-20008 | KY 18 |  | 15.256 | 16.632 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT. | C |  | PM/STP | 2020 | 2250000 | 1800000 |  |  | 450000
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; UPDATE FISCAL YEAR; MOD |  |  | BOONE | 6-20008 | KY 18 |  | 15.256 | 16.632 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT. | C |  | PM/STP | 2021 | 2250000 | 1800000 |  |  | 450000 | [5 empty] | 0
STIP | YES | No | [7 empty] | BOONE | 6-20009 | KY 237 |  | 9.5 | 10.3 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT. | D |  | PM/NH | 2021 | 320000 | 256000 |  |  | 64000 | [5 empty] | 0
STIP | YES | No | [7 empty] | BOONE | 6-20009 | KY 237 |  | 9.5 | 10.3 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT. | C |  | PM/NH | 2021 | 3200000 | 2560000 |  |  | 640000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.253 | 2020-10-26 | TIP FY 21-24, AMEND#2; ADD D PHASE TO STIP; NEW |  |  | BOONE | 6-80150 | KY 717 |  |  |  | NEW ROUTES | NEW ROUTE(O) | IMPROVE MUTLI-MODAL MOBILITY IMMEDIATELY EAST OF CVG AIRPORT VIA A NEW CONNECTION AT KY 717 (TURFWAY RD), KY 3076 (MINEOLA PK), AND EXTEND KY-236 (DONALDSON HWY) TO S. AIRFIELD RD (PR 1012) (2020CCN) | D |  | STP | 2022 | 1000000 | 800000 |  |  | 200000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.253 | 2020-10-26 | TIP FY 21-24, AMEND#2; ADD R PHASE TO STIP; NEW |  |  | BOONE | 6-80150 | KY 717 |  |  |  | NEW ROUTES | NEW ROUTE(O) | IMPROVE MUTLI-MODAL MOBILITY IMMEDIATELY EAST OF CVG AIRPORT VIA A NEW CONNECTION AT KY 717 (TURFWAY RD), KY 3076 (MINEOLA PK), AND EXTEND KY-236 (DONALDSON HWY) TO S. AIRFIELD RD (PR 1012) (2020CCN) | R |  | STP | 2023 | 3600000 | 2880000 |  |  | 720000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.253 | 2020-10-26 | TIP FY 21-24, AMEND#2; ADD U PHASE TO STIP; NEW |  |  | BOONE | 6-80150 | KY 717 |  |  |  | NEW ROUTES | NEW ROUTE(O) | IMPROVE MUTLI-MODAL MOBILITY IMMEDIATELY EAST OF CVG AIRPORT VIA A NEW CONNECTION AT KY 717 (TURFWAY RD), KY 3076 (MINEOLA PK), AND EXTEND KY-236 (DONALDSON HWY) TO S. AIRFIELD RD (PR 1012) (2020CCN) | U |  | STP | 2023 | 250000 | 200000 |  |  | 50000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.253 | 2020-10-26 | TIP FY 21-24, AMEND#2; ADD C PHASE TO STIP; NEW |  |  | BOONE | 6-80150 | KY 717 |  |  |  | NEW ROUTES | NEW ROUTE(O) | IMPROVE MUTLI-MODAL MOBILITY IMMEDIATELY EAST OF CVG AIRPORT VIA A NEW CONNECTION AT KY 717 (TURFWAY RD), KY 3076 (MINEOLA PK), AND EXTEND KY-236 (DONALDSON HWY) TO S. AIRFIELD RD (PR 1012) (2020CCN) | C |  | STP | 2024 | 22000000 | 17600000 |  |  | 4400000 | [5 empty] | 0
STIP | [9 empty] | BOURBON | 7-365.1 | KY 3364 | 0.1 | 5.389 | 5.489 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF STRUCTURE OVER SCOTTS CREEK ON KY 3364, 0.7 MILE NORTH OF US 460 AT NORTH MIDDLETOWN (BRIDGE IMPROVEMENTS). (03KYDN)(2012BOP) (16CCN) | D |  | KYD | 2019 | 1568000 | 1568000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | BOURBON | 7-8705 | US 460 | 6.302 | 1.394 | 7.696 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE US-460 FROM RUSSELL CAVE ROAD TO US-27 BYPASS IN PARIS.(12CCN)(14CCR)(16CCR) | R |  | STP | 2019 | 1000000 | 1000000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.03 | 2019-03-01 | INCREASE FUNDS ON R PHASE; MOD | STP | 4601050 | BOURBON | 7-8705 | US 460 | 6.302 | 1.394 | 7.696 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE US-460 FROM RUSSELL CAVE ROAD TO US-27 BYPASS IN PARIS.(12CCN)(14CCR)(16CCR) | R |  | STP | 2019 | 6000000 | 6000000 |  |  | 0 |  |  | OBLIGATED | 1343898 | 4656102 | 6000000 | 2019 | 2ND QUARTER
STIP | [9 empty] | BOURBON | 7-8705 | US 460 | 6.302 | 1.394 | 7.696 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE US-460 FROM RUSSELL CAVE ROAD TO US-27 BYPASS IN PARIS.(12CCN)(14CCR)(16CCR) | U |  | STP | 2019 | 1000000 | 1000000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | BOURBON | 7-8705 | US 460 | 6.302 | 1.394 | 7.696 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE US-460 FROM RUSSELL CAVE ROAD TO US-27 BYPASS IN PARIS.(12CCN)(14CCR)(16CCR) | C |  | STP | 2021 | 5620000 | 4496000 |  |  | 1124000 | [5 empty] | 0
STIP | [9 empty] | BOURBON | 7-8705.01 | US 460 | 6.302 | 1.394 | 7.696 | RELIABILITY | PREFINANCD CONVRSN(O) | IMPROVE US-460 FROM RUSSELL CAVE ROAD TO US-27 BYPASS IN PARIS.(12CCN)(14CCR)(16CCR) | R |  | STP | 2021 | 2030000 | 1624000 |  |  | 406000 | [5 empty] | 0
STIP | [9 empty] | BOURBON | 7-8705.01 | US 460 | 6.302 | 1.394 | 7.696 | RELIABILITY | PREFINANCD CONVRSN(O) | IMPROVE US-460 FROM RUSSELL CAVE ROAD TO US-27 BYPASS IN PARIS.(12CCN)(14CCR)(16CCR) | U |  | STP | 2021 | 1500000 | 1200000 |  |  | 300000 | [5 empty] | 0
[8 empty] | HSIP | 9010338 | BOURBON | 7-9011 | KY 537 |  | 0.00 | 3.5 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM SAFETY IMPROVEMENTS ALONG KY 537 CORRIDOR IN BOURBON COUNTY FROM SHOULDERING, DRAINAGE ENHANCEMENTS, AND ROADSIDE IMPROVEMENTS. (2018BOP) | D |  | SAF | 2019 | [7 empty] | OBLIGATED | 50000 |  | 50000 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICAITON | 2018.210 | 2020-07-31 | ADD C PHASE TO STIP; NEW |  |  | BOURBON | 7-9011 | KY 537 |  | 0.00 | 3.5 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM SAFETY IMPROVEMENTS ALONG KY 537 CORRIDOR IN BOURBON COUNTY FROM SHOULDERING, DRAINAGE ENHANCEMENTS, AND ROADSIDE IMPROVEMENTS. (2018BOP) | C |  | SAF | 2020 | 253000 | 253000 | [8 empty] | 0
STIP | [9 empty] | BOURBON | 7-10007 | CR 1205 |  | 1.566 | 1.574 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF HOUSTON ANTIOCH ROAD BRIDGE OVER HOUSTON CREEK. (009C00031N) | D |  | BR/STP | 2019 | 143500 | 88970 |  |  | 54530 | [5 empty] | 0
STIP | [9 empty] | BOURBON | 7-10007 | CR 1205 |  | 1.566 | 1.574 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF HOUSTON ANTIOCH ROAD BRIDGE OVER HOUSTON CREEK. (009C00031N) | C |  | BR/STP | 2020 | 325500 | 201810 |  |  | 123690 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.075 | 2019-05-28 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030113 | BOURBON | 7-10007 | CR 1205 |  | 1.566 | 1.574 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF HOUSTON ANTIOCH ROAD BRIDGE OVER HOUSTON CREEK. (009C00031N) | C |  | STP | 2020 | 576098 | 576098 |  |  | 0 |  |  | OBLIGATED |  | 686240 | 686240 | 2019 | 3RD QUARTER
STIP | [9 empty] | BOURBON | 7-10008 | CR 1320 |  | 4.983 | 4.99 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF PEACOCK ROAD BRIDGE OVER CSX RR. (009R00605N) | D |  | BR/STP | 2019 | 220500 | 136710 |  |  | 83790 | [5 empty] | 0
STIP | [9 empty] | BOURBON | 7-10008 | CR 1320 |  | 4.983 | 4.99 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF PEACOCK ROAD BRIDGE OVER CSX RR. (009R00605N) | C |  | BR/STP | 2020 | 518000 | 321160 |  |  | 196840 | [5 empty] | 0
STIP | [9 empty] | BOURBON | 7-20002 | US 68X |  | 0 | 2.772 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT. | D |  | PM/STP | 2019 | 250000 | 200000 |  |  | 50000 | [5 empty] | 0
STIP | [9 empty] | BOURBON | 7-20002 | US 68X |  | 0 | 2.772 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT. | C |  | PM/STP | 2019 | 2500000 | 2000000 |  |  | 500000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.139 | 2019-10-25 | INCREASE FUNDS BASED ON NEW ESTIMATE; MOD | STP | 7054001 | BOURBON | 7-20002 | US 68X |  | 0 | 2.772 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT. | C |  | PM/STP | 2020 | 7500000 | 7500000 |  |  | 0 |  |  | OBLIGATED | 800000 | 7420435 | 8220435 | 2020 | 1ST QUARTER
|  |  |  | AMENDMENT | 2018.008 | 2020-07-28 | TIP REFERENCE FY 21-24 RESOLUTION DATED 2/21/20. NEW |  |  | BOYD GREENUP
STIP | YES |  | PROJECTS ARE ADDED TO KYOVA TIP AND KY STIP AS PROJECTS ARE APPROVED AND FUNDING AUTHORIZED & COUNTY SHOULD BE BOYD/GREENUP | [6 empty] | BOYD | 9-208.04 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | FEDERAL 'STP' FUNDS DEDICATED TO HUNTINGTON-ASHLAND MPO FOR FY 2018. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C |  | SAH | 2019 | 6265000 | 5012000 |  |  |  | 1253000 |  |  |  |  | 0
STIP | YES |  | PROJECTS ARE ADDED TO KYOVA TIP AND KY STIP AS PROJECTS ARE APPROVED AND FUNDING AUTHORIZED & COUNTY SHOULD BE BOYD/GREENUP | [6 empty] | BOYD | 9-208.05 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | FEDERAL 'STP' FUNDS DEDICATED TO HUNTINGTON-ASHLAND MPO FOR FY 2019. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C |  | SAH | 2019 | 1200000 | 960000 |  |  |  | 240000 |  |  |  |  | 0
STIP | YES |  | PROJECTS ARE ADDED TO KYOVA TIP AND KY STIP AS PROJECTS ARE APPROVED AND FUNDING AUTHORIZED & COUNTY SHOULD BE BOYD/GREENUP | [6 empty] | BOYD | 9-208.06 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | FEDERAL 'STP' FUNDS DEDICATED TO HUNTINGTON-ASHLAND MPO FOR FY 2020. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C |  | SAH | 2020 | 1200000 | 960000 |  |  |  | 240000 |  |  |  |  | 0
STIP | YES |  | PROJECTS ARE ADDED TO KYOVA TIP AND KY STIP AS PROJECTS ARE APPROVED AND FUNDING AUTHORIZED | [6 empty] | BOYD | 9-208.07 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | FEDERAL 'STP' FUNDS DEDICATED TO HUNTINGTON-ASHLAND MPO FOR FY 2021. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C |  | SAH | 2021 | 1600000 | 1280000 |  |  |  | 320000 |  |  |  |  | 0
STIP | YES |  | PROJECTS ARE ADDED TO KYOVA TIP AND KY STIP AS PROJECTS ARE APPROVED AND FUNDING AUTHORIZED & COUNTY SHOULD BE BOYD/GREENUP | [6 empty] | BOYD | 9-208.08 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | FEDERAL 'STP' FUNDS DEDICATED TO HUNTINGTON-ASHLAND MPO FOR FY 2022. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C |  | SAH | 2022 | 1600000 | 1280000 |  |  |  | 320000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.324 | 2021-08-02 | TIP FY 21-24, ADMIN MOD#16; UPDATE FUNDING SOURCE FROM SAH-TAP TO SAH DEDICATED FUNDS; MOD |  |  | BOYD | 9-239 | [5 empty] | BIKE/PED FACIL(O) | DESIGN FOR DAWES STREET RESTORATION AND REHABILITATION FROM BEECH STREET TO BLACKBURN AVENUE TO SAFETLY ACCOMMODATE PEDESTRIAN AND BICYCLE TRAFFIC FOR SAFE ROUTES TO SCHOOL (SRTS) IN ASHLAND, KY. | D |  | SAH | 2021 | 245000 | 196000 |  |  |  | 49000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.324 | 2021-08-02 | TIP FY 21-24, ADMIN MOD#16; UPDATE FUNDING SOURCE FROM SAH-TAP TO SAH DEDICATED FUNDS; MOD |  |  | BOYD | 9-244 | US 23/US 23X |  |  |  |  | BIKE/PED FACIL(O) | DESIGN FOR DOWNTOWN STREET SCAPE (WINCHESTER AVENUE) US-23 FROM 7TH (MP 19.33) THROUGH 12TH STREET (mp 18.63) STREETS AND WINCHESTER AVENUE (US-23X) 28TH (MP 1.18) THROUGH 21ST STREET(MP.962) IN ASHLAND, KY. | D |  | SAH | 2021 | 250000 | 200000 |  |  |  | 50000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.037 | 2019-03-15 | TIP FY 18-21; ADMIN MOD#29; ADD PROJECT TO STIP; NEW | STPM | 3004053 | BOYD GREENUP | 9-406 | KY 168 | 1.5 | 6.875 | 8.179 |  | PLANNING | COMPLETE SMALL URBAN STUDY FOR BOYD AND GREENUP COUNTIES, KY. MATCH TO BE PROVIDED BY TOLL CREDITS. | P |  | STP | 2019 | 200000 | 160000 | 160000 |  |  | 40000 |  | OBLIGATED | 160000 |  | 160000 | 2019 | 3RD QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.181 | 2020-04-21 | TIP FY 18-21; ADMIN MOD#53; ADD PROJECT TO STIP; NEW |  |  | BOYD GREENUP | TBD | [5 empty] | PLANNING | PLANNING FUNDS FOR KYOVA FY 2019 UNIFIED PLANNING WORK PROGRAM ELEMENT #380719 SURFACE TRANSPORTATION PROGRAM PLANNING ACTIVITIES. | P |  | STP | 2021 | 14830 | 11864 | 11864 |  |  | 2966 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.294 | 2021-04-13 | TIP FY 21-24; ADMIN MOD#12; ADD PROJECT TO STIP; NEW |  |  | BOYD GREENUP | TBD | [5 empty] | PLANNING | PLANNING STUDY FUNDS FOR KYOVA FY 2022 UPWP ELEMENT #380722 SURFACE TRANSPORTATION PLANNING. | P |  | STP | 2022 | 14830 | 11864 | 11864 |  |  | 2966 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.294 | 2021-04-13 | TIP FY 21-24; ADMIN MOD#12; ADD PROJECT TO STIP; NEW |  |  | BOYD GREENUP | TBD | [5 empty] | PLANNING | KYOVA 2050 MTP UPDATE/KYOVA UPWP ELEMENT #380522-KYOVA 2050 MTP UPDATE. | P |  | CRRSSA/HIP | 2022 | 50000 | 50000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.06 | 2019-04-29 | TIP FY 18-21, AMENDMENT#9; ADD D PHASE TO STIP; NEW |  |  | BOYD | TBD | US 23 | 0.1 | 20.69 | 20.79 | RELIABILITY | MATCHED FED FUNDS(O) | INSTALL CONTINUOUS GREEN LIGHT FOR THE RIGHT LANES ON NB US-23 AT THE INTERSECTION OF KY-5 WITH CONCRETE ISLAND NEAR THE CENTER OF THE INTERSECTION TO SEPARATE THE FLOW OF TRAFFIC. MATCH TO BE PROVIDED BY TOLL CREDITS. | D |  | STP | 2019 | 5000 | 4000 |  |  |  | 1000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.143 | 2019-10-22 | TIP FY 18-21; ADMIN MOD#45; UPDATE KYTC ITEM NUMBER; MOD | STPM | 0231161 | BOYD | 9-409 | US 23 |  | 20.69 | 20.79 | RELIABILITY | MATCHED FED FUNDS(O) | INSTALL CONTINUOUS GREEN LIGHT FOR THE RIGHT LANES ON NB US-23 AT THE INTERSECTION OF KY-5 WITH CONCRETE ISLAND NEAR THE CENTER OF THE INTERSECTION TO SEPARATE THE FLOW OF TRAFFIC. (2018BOP) | D |  | SAH | 2019 | 5000 | 4000 |  |  |  | 1000 |  | OBLIGATED |  | 5000 | 5000 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.06 | 2019-04-29 | TIP FY 18-21, AMENDMENT#9; ADD C PHASE TO STIP; NEW |  |  | BOYD | TBD | US 23 | 0.1 | 20.69 | 20.79 | RELIABILITY | MATCHED FED FUNDS(O) | INSTALL CONTINUOUS GREEN LIGHT FOR THE RIGHT LANES ON NB US-23 AT THE INTERSECTION OF KY-5 WITH CONCRETE ISLAND NEAR THE CENTER OF THE INTERSECTION TO SEPARATE THE FLOW OF TRAFFIC. MATCH TO BE PROVIDED BY TOLL CREDITS. | C |  | STP | 2019 | 274755 | 219804 |  |  |  | 54951 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.143 | 2019-10-22 | TIP FY 18-21; ADMIN MOD#45; UPDATE KYTC ITEM NUMBER; MOD | STPM | 0231161 | BOYD | 9-409 | US 23 |  | 20.69 | 20.79 | RELIABILITY | MATCHED FED FUNDS(O) | INSTALL CONTINUOUS GREEN LIGHT FOR THE RIGHT LANES ON NB US-23 AT THE INTERSECTION OF KY-5 WITH CONCRETE ISLAND NEAR THE CENTER OF THE INTERSECTION TO SEPARATE THE FLOW OF TRAFFIC. (2018BOP) | C |  | SAH | 2019 | 274755 | 219804 |  |  |  | 54951 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.06 | 2019-04-29 | TIP FY 18-21, AMENDMENT#9; ADD D PHASE TO STIP; NEW |  |  | BOYD | TBD | US 60 | 0.1 | 8.567 | 8.667 | RELIABILITY | MATCHED FED FUNDS(O) | INSTALL CONTINUOUS GREEN LIGHT FOR THE RIGHT LANES ON WB US-60 AT THE INTERSECTION OF KY-1012 (BOY SCOUT ROAD) MP 8.617 WITH CONCRETE ISLAND NEAR THE CENTER OF THE INTERSECTION TO SEPARATE THE FLOW OF TRAFFIC. MATCH TO BE PROVIDED BY TOLL CREDITS. | D |  | STP | 2019 | 5000 | 4000 |  |  |  | 1000
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.143 | 2019-10-22 | TIP FY 18-21; ADMIN MOD#45; UPDATE KYTC ITEM NUMBER; MOD | STPM | 2601031 | BOYD | 9-410 | US 60 |  | 8.567 | 8.667 | RELIABILITY | MATCHED FED FUNDS(O) | INSTALL CONTINUOUS GREEN LIGHT FOR THE RIGHT LANES ON WB US-60 AT THE INTERSECTION OF KY-1012 (BOY SCOUT RD) MP 8.617 WITH CONCRETE INSLAND NEAR THE CENTER OF THE INTERSECTION TO SEPARATE THE FLOW OF TRAFFIC. (2018BOP) | D |  | SAF | 2019 | 5000 | 4000 |  |  |  | 1000 |  | OBLIGATED |  | 5000 | 5000 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.06 | 2019-04-29 | TIP FY 18-21, AMENDMENT#9; ADD C PHASE TO STIP; NEW |  |  | BOYD | TBD | US 60 | 0.1 | 8.567 | 8.667 | RELIABILITY | MATCHED FED FUNDS(O) | INSTALL CONTINUOUS GREEN LIGHT FOR THE RIGHT LANES ON WB US-60 AT THE INTERSECTION OF KY-1012 (BOY SCOUT ROAD) MP 8.617 WITH CONCRETE ISLAND NEAR THE CENTER OF THE INTERSECTION TO SEPARATE THE FLOW OF TRAFFIC. MATCH TO BE PROVIDED BY TOLL CREDITS. | C |  | STP | 2019 | 154547 | 123638 |  |  |  | 30909
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.143 | 2019-10-22 | TIP FY 18-21; ADMIN MOD#45; UPDATE KYTC ITEM NUMBER; MOD | STPM | 2601031 | BOYD | 9-410 | US 60 |  | 8.567 | 8.667 | RELIABILITY | MATCHED FED FUNDS(O) | INSTALL CONTINUOUS GREEN LIGHT FOR THE RIGHT LANES ON WB US-60 AT THE INTERSECTION OF KY-1012 (BOY SCOUT RD) MP 8.617 WITH CONCRETE INSLAND NEAR THE CENTER OF THE INTERSECTION TO SEPARATE THE FLOW OF TRAFFIC. (2018BOP) | C |  | SAH | 2019 | 154547 | 123638 |  |  |  | 30909 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.06 | 2019-04-29 | TIP FY 18-21, AMENDMENT#9; ADD D PHASE TO STIP; NEW |  |  | BOYD | TBD | US 23 | 1.56 | 17.078 | 18.640 | RELIABILITY | MATCHED FED FUNDS(O) | REMOVE RAISED MEDIAN SECTIONS ON GREENUP AVENUE (US-23) IN BOYD COUNTY FROM MP 17.078 TO 18.640 AND ADD A COTINUOUS TWO WAY TURN LANE (TWTL) FROM 20TH STREET TO 31ST STREET. MATCH TO BE PROVIDED BY TOLL CREDITS. | D |  | SAH | 2019 | 5000 | 4000 |  |  |  | 1000
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.143 | 2019-10-22 | TIP FY 18-21; ADMIN MOD#45; UPDATE KYTC ITEM NUMBER; MOD | STPM | 0231162 | BOYD | 9-411 | US 23 |  | 17.078 | 18.64 | RELIABILITY | MATCHED FED FUNDS(O) | REMOVE RAISED MEDIAN SECTIONS ON GREENUP AVENUE (US-23) IN BOYD COUNTY FROM MP 17.078-18.640 AND ADD A CONTINUOUS TWO WAY TURN LANE (TWTL) FROM 20TH STREET TO 31ST STREET. (2018BOP) | D |  | SAH | 2019 | 5000 | 4000 |  |  |  | 1000 |  | OBLIGATED |  | 5000 | 5000 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.06 | 2019-04-29 | TIP FY 18-21, AMENDMENT#9; ADD C PHASE TO STIP; NEW |  |  | BOYD | TBD | US 23 | 1.56 | 17.078 | 18.640 | RELIABILITY | MATCHED FED FUNDS(O) | REMOVE RAISED MEDIAN SECTIONS ON GREENUP AVENUE (US-23) IN BOYD COUNTY FROM MP 17.078 TO 18.640 AND ADD A COTINUOUS TWO WAY TURN LANE (TWTL) FROM 20TH STREET TO 31ST STREET. MATCH TO BE PROVIDED BY TOLL CREDITS. | C |  | SAH | 2019 | 454612 | 363689 |  |  |  | 90923 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.143 | 2019-10-22 | TIP FY 18-21; ADMIN MOD#45; UPDATE KYTC ITEM NUMBER; MOD | STPM | 0231162 | BOYD | 9-411 | US 23 |  | 17.078 | 18.64 | RELIABILITY | MATCHED FED FUNDS(O) | REMOVE RAISED MEDIAN SECTIONS ON GREENUP AVENUE (US-23) IN BOYD COUNTY FROM MP 17.078-18.640 AND ADD A CONTINUOUS TWO WAY TURN LANE (TWTL) FROM 20TH STREET TO 31ST STREET. (2018BOP) | C |  | SAH | 2019 | 454612 | 363689 |  |  |  | 90923 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.297 | 2021-04-20 | TIP FY 21-24, ADMIN MOD#14; ADD C PHASE TO STIP; NEW |  |  | BOYD | 9-4326 | KY 3294 | 7.03 | 7.13 | 0.1 | SAFETY | SAF GUARDRAIL (P) | INSTALL GUARDRAIL ON KY-3294 IN BOYD COUNTY | C |  | STP | 2021 | 12650 | 12650 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.297 | 2021-04-20 | TIP FY 21-24, ADMIN MOD#14; ADD C PHASE TO STIP; NEW |  |  | BOYD | 9-4331 | KY 538 | 0.15 | 5.48 | 5.63 | SAFETY | SAF GUARDRAIL (P) | INSTALL GUARDRAIL ON KY-538 IN BOYD COUNTY | C |  | STP | 2021 | 18400 | 18400 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.228 | 2020-09-02 | TIP FY 21-24, ADMIN MOD#2; ADD PROJECT TO STIP; NEW |  |  | BOYD | 9-8400 | US 60 | 3.82 | 0.2 | 4.02 |  |  | IMPROVE US-60 FROM I-64 AT INTERCHANGE 181 TO THE KY-180 INTERSECTION AT CANNONSBURG (08CCN)(10CCR)(12CCR). | C |  | STP | 2021 | 22600000 | 18080000 |  |  |  | 4520000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.044 | 2019-03-29 | TIP FY 18-21; ADMIN MOD#31; ADD PROJECT TO STIP; NEW | HSIP | 9010297 | BOYD, LEWIS, ROWAN | 9-9007 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | PRELIMINARY DESIGN AND STUDY, INCLUDING ENVIRONMENTAL DOCUMENTATION TO DETERMINE LOW COST IMPROVEMENTS AT VARIOUS INTERSECTIONS WITHIN DISTRICT 9 (PHASE I DESIGN) - | D |  | SAF | 2019 | 200000 | 200000 |  |  |  | 0 |  | OBLIGATED |  | 50000 | 50000 | 2019 | 3RD QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.044 | 2019-03-29 | TIP FY 18-21; ADMIN MOD#31; ADD PROJECT TO STIP; NEW | HSIP | 9010382 | BOYD | 9-9007.1 | US 60 | 0.1 | 11.195 | 11.295 | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALL SUPPLEMENTAL SIGNALS AND UPDATE THE SIGNAL HEADS TO INCLUDE DOUBLE RED HEADS WITH REFLECTIVE BACKPLATES AT THE INTERSECTION OF US-60 (13TH STREET) AND RAMEY STREET. | C |  | SAF | 2019 | 20000 | 20000 |  |  |  | 0 |  | OBLIGATED |  | 21000 | 21000 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.044 | 2019-03-29 | TIP FY 18-21; ADMIN MOD#31; ADD PROJECT TO STIP; NEW | HSIP | 9010384 | BOYD | 9-9007.5 | US 23X US 60 US 60 CS 2400 |  | 1.551 12.182 12.329 0.035 | 1.796 12.329 12.409 0.113 | SAFETY | SAFETY-HAZARD ELIM(P) | CONSTRUCT ON-STREET PARKING BAY ALONG NB WINCHESTER AVE BETWEEN 9TH & 10TH ST, MILL, RESURFACE & RESTRIPE WINCHESTER AVE TO INCLUDE A 2-WAY LEFT TURN LANE, UPDATE STRIPING ON 10TH ST & UPDATE SIGNAL TO INCLUDE FLASHING YELLOW ARROWS AT THE INTERSECTION OF US23X & 10TH STREET (2018BOP) | C |  | SAF | 2019 | 250000 | 250000 |  |  |  | 0 |  | OBLIGATED |  | 500000 | 500000 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.044 | 2019-03-29 | TIP FY 18-21; ADMIN MOD#31; ADD PROJECT TO STIP; NEW | HSIP | 9010385 | BOYD | 9-9007.6 | CS 2350 |  | 0.83 | 0.95 | SAFETY | SAFETY-HAZARD ELIM(P) | RESTRIPE CENTRAL AVE TO ALIGN THE THROUGH MOVEMENT ACROSS THE INTERSECTION, INSTALL A SUPPLEMENTAL SIGNAL HEAD & UPDATE THE THROUGH SIGNAL HEADS TO INCLUDE THE DOUBLE RED HEADS AT THE INTERSECTION OF CENTRAL AVE & 13TH ST. (2018BOP) | C |  | SAF | 2019 | 25000 | 25000 |  |  |  | 0 |  | OBLIGATED |  | 20000 | 20000 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.044 | 2019-03-29 | TIP FY 18-21; ADMIN MOD#31; ADD PROJECT TO STIP; NEW | HSIP | 9010386 | BOYD | 9-9007.7 | US 60 |  | 11.976 | 12.202 | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALL OVERHEAD LANE ASSIGNMENT SIGNS ON THE SIGNAL SPAN WIRE & UPDATE THE STRIPING ALONG MARTIN LUTHER KING BLVD BETWEEN WINCHESTER AVE & CENTRAL AVE. (2018BOP) | C |  | SAF | 2019 | 25000 | 25000 |  |  |  | 0 |  | OBLIGATED |  | 21000 | 21000 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.018 | 2019-01-23 | TIP FY 18-21; ADMIN MOD#25; ADD PROJECT TO STIP; NEW | HSIP | 9010355 | BOYD, GREENUP, ROWAN | 9-9010 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | PRELIMINARY DESIGN AND STUDY TO DETERMINE LOW COST IMPROVEMENTS AT VARIOUS INTERSECTIONS WITHIN DISTRICT 9. (2018BOP) | D |  | SAF | 2019 | 200000 | 200000 |  |  |  | 0 |  | OBLIGATED | 200000 |  | 200000 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.179 | 2020-04-14 | TIP FY 18-21; ADMIN MOD#52; ADD PROJECT TO STIP; NEW |  |  | BOYD | 9-9010.3 | CS 2350 CS 2545 | .183 .111 | 1.571 .295 | 1.754 .406 | SAFETY | SAFETY-HAZARD ELIM(P) | CONVERT THE EXISTING TWO-WAY STOP CONTROL TO ALL-WAY STOP CONTROL AT THE INTERSECTION OF CENTRAL AVE & 23RD STREET. (2018BOP) | C |  | SAF | 2020 | 20000 | 20000 |  |  |  | 0 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.103 | 2019-07-29 | ADD PROJECT TO STIP; PARENT NO. 911-08; KYOVA TIP FY 18-21; BG-126 GROUPED PROJECTS, PG 18; NEW | HSIP | 0648073 | BOYD | 9-9012 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | CABLE MEDIAN BARRIER ON I-64 FROM MP 181.339 TO MP 191.507 IN BOYD COUNTY, KY. (2018BOP) | D |  | SAF | 2019 | 50000 | 50000 |  |  |  | 0 |  | OBLIGATED | 50000 |  | 50000 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.144 | 2019-10-25 | TIP FY 18-21; ADMIN MOD#46; ADD C PHASE TO STIP; NEW | HSIP | 0648073 | BOYD | 9-9012 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | CABLE MEDIAN BARRIER ON I-64 FROM MP 181.339 TO MP 191.507 IN BOYD COUNTY, KY. (2018BOP) | C |  | SAF | 2020 | 1362350 | 1362350 |  |  |  | 0 |  | OBLIGATED | 1734248 |  | 1734248 | 2020 | 1ST QUARTER
STIP | [7 empty] | HSIP | 2601030 | BOYD | 9-10014 | US 23S |  | 0.048 | 0.48 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES ON 12TH STREET BRIDGE OVER THE OHIO RIVER. JOINT PROJECT WITH OHIO. (010B00040N)(BSBP) | C |  | BR/NH | 2019 | 1750000 | 1085000 |  |  | 665000 |  |  | OBLIGATED | 1109769 |  | 1109769 | 2019 | 2ND QUARTER
STIP | YES | [8 empty] | BOYD | 9-10015 | US 60 |  | 12.636 | 12.88 | ASSET MANAGEMENT | AM-BRIDGE (P) | PAINTING AND PREVENTIVE MAINTENANCE ON CATLETTSBURG KENOVA BRIDGE ON 35TH ST. OVER THE OHIO RIVER. JOINT PROJECT WITH OHIO. (010B00062N)(BSBP) | C |  | BR/STP | 2020 | 1200000 | 744000 |  |  | 456000 | [5 empty] | 0
STIP | YES | YES | KYOVA TIP HAS STATE PORTION=$930,000 WITH SPP/FEDERAL STP=$390,000/FEDERAL NH=$40,000/TOTAL PHASE COST=$1,360,000 | [6 empty] | BOYD | 9-10016 | I 64 |  | 191.404 | 191.507 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES ON PERRY GENTRY BRIDGES OVER THE BIG SANDY RIVER. JOINT PROJECT WITH WEST VIRGINIA. (010B00046L AND 010B00046R)(SD) | C |  | BR/NH | 2020 | 1500000 | 930000 |  |  | 570000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.228 | 2020-09-02 | TIP FY 21-24, ADMIN MOD#2; CORRECT MILEPOINTS, FUND TYPE AND FISCAL YEAR; MOD |  |  | BOYD | 9-10016 | I 64 |  | 191.4 | 191.51 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES ON PERRY GENTRY BRIDGES OVER THE BIG SANDY RIVER. JOINT PROJECT WITH WEST VIRGINIA. (010B00046L AND 010B00046R)(SD) | C |  | STP | 2021 | 1500000 | 1200000 |  |  | 300000 | [5 empty] | 0
STIP | YES | [8 empty] | BOYD | 9-10018 | KY 854 |  | 7.068 | 7.076 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 854 BRIDGE OVER GARNER CREEK. (010B00045N) | D |  | BR/STP | 2019 | 525000 | 325500 |  |  | 199500 | [5 empty] | 0
STIP | YES | [8 empty] | BOYD | 9-10018 | KY 854 |  | 7.068 | 7.076 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 854 BRIDGE OVER GARNER CREEK. (010B00045N) | C |  | BR/STP | 2020 | 1085000 | 672700 |  |  | 412300 | [5 empty] | 0
STIP | YES | [8 empty] | BOYD | 9-20002 | I 64 |  | 180.812 | 183.95 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-64 BOTH DIRECTION(S) FROM MILEPOINT 180.812 TO MILEPOINT 183.95. | D |  | PM/NH | 2019 | 250000 | 200000 |  |  | 50000 | [5 empty] | 0
STIP | YES | [6 empty] | NHPPIM | 0648072 | BOYD | 9-20002 | I 64 |  | 180.812 | 183.95 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-64 BOTH DIRECTION(S) FROM MILEPOINT 180.812 TO MILEPOINT 183.95. | C |  | PM/NH | 2019 | 2500000 | 2000000 |  |  | 500000 |  |  | OBLIGATED | 3157200 |  | 3157200 | 2019 | 1ST QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.221 | 2020-08-21 | TIP FY 21-24, ADMIN MOD#1; ADD PROJECT TO STIP; NEW |  |  | BOYD | 9-20003 | I 64 | 7.56 | 183.95 | 191.507 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-64 BOTH DIRECTION(S) FROM MILEPOINT 183.95 TO MILEPOINT 191.507. | D |  | PM/NH | 2021 | 600000 | 480000 |  |  | 120000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.248 | 2020-10-14 | TIP FY 21-24, AMENDMENT#2; ADD C PHASE TO STIP; NEW |  |  | BOYD | 9-20003 | I 64 | 7.56 | 183.95 | 191.507 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-64 BOTH DIRECTION(S) FROM MILEPOINT 183.95 TO MILEPOINT 191.507. | C |  | PM/NH | 2021 | 6000000 | 4800000 |  |  | 1200000 | [5 empty] | 0
STIP | YES | YES | PROJECT IS OUTSIDE KYOVA TIP YEARS 2018-2021. CAN INCLUDE IF NEEDED. | [6 empty] | BOYD | 9-20015 | US 23 | 6.28 | 10.67 | 16.95 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION ON US-23 FROM MILEPOINT 10.67 TO MILEPOINT 16.95 | C |  | PM/NH | 2022 | 2365000 | 1892000 |  |  | 473000 | [5 empty] | 0
STIP | [9 empty] | BOYD |  | US-23/US-23X | 0.7/0.218 | 18.63/.0962 | 18.63/1.18 | SAFETY | TRANSPORTATION ENHANCEMENT | DESIGN FOR DOWNTOWN STREET SCAPE (WINCHESTER AVENUE) US-23 FROM 7TH (MP 19.33) THROUGH 12TH STREET (mp 18.63) STREETS AND WINCHESTER AVENUE (US-23X) 28TH (MP 1.18) THROUGH 21ST STREET(MP.962) IN ASHLAND, KY. | D |  | SAH | 2018 | 250000 | 200000 |  |  | 0 | 50000 |  |  |  |  | 0
STIP | [9 empty] | BOYD |  |  |  |  | 0.25 | SAFETY | PEDESTRIAN BICYCLE | DESIGN FOR DAWES STREET RESTORATION AND REHABILITATION FROM BEECH STREET TO BLACKBURN AVENUE TO SAFETLY ACCOMMODATE PEDESTRIAN AND BICYCLE TRAFFIC FOR SAFE ROUTES TO SCHOOL (SRTS) IN ASHLAND, KY. | D |  | SAH | 2018 | 245000 | 196000 |  |  | 0 | 49000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.21 | 2020-07-31 | ADD P PHASE TO THE STIP; NEW |  |  | BOYLE GARRARD | 7-104 | KY 52 |  |  |  |  | PLANNING | PLANNING STUDY TO EVALUATE OPTIONS FOR IMPROVING SAFETY ON KY 52 BETWEEN DANVILLE AND LANCASTER. | P |  | STP | 2020 | 500000 | 500000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | BOYLE | 7-242 | US 68 |  | 6.4 | 6.418 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF US 68 AND US 150 BRIDGE OVER CHAPLIN RIVER, PERRYVILLE. (SEE 7-242.01 FOR HPP FUNDS)(2005HPP-KY134)(011B00042N)(SD) | C |  | BR/STP | 2020 | 1253000 | 776860 |  |  | 476140 | [5 empty] | 0
[8 empty] | STP | 1501122 | BOYLE | 7-242 | US 68 |  | 6.4 | 6.418 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF US 68 AND US 150 BRIDGE OVER CHAPLIN RIVER, PERRYVILLE. (SEE 7-242.01 FOR HPP FUNDS)(2005HPP-KY134)(011B00042N)(SD) | D |  | BR/STP | 2019 | [7 empty] | OBLIGATED |  | 125000 | 125000 | 2019 | 4TH QUARTER
STIP | [9 empty] | BOYLE | 7-242.01 | US 68 |  | 6.4 | 6.418 | RELIABILITY | AM-BRIDGE (P) | REPLACE US 68 AND US 150 BRIDGE OVER CHAPLIN RIVER, PERRYVILLE. 011B00042N (2005HPP-KY134)(EARMARK DOES NOT COVER TOTAL PROJECT COST OF $1,790,000).(SD) | C |  | HPP | 2019 | 487797 | 487797 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.175 | 2020-04-09 | ADD D PHASE TO STIP; PARENT NO. 99-911.09; NEW |  |  | BOYLE GARRARD | 7-9021 | KY 52 |  | 0 0 | 5.114 4.231 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 52 FROM MP 0.000 TO MP 5.114 IN BOYLE COUNTY, AND MP 0.000 TO MP 4.231 IN GARRARD COUNTY, KY. (2018BOP) | D |  | SAF | 2020 | 375000 | 375000 | [8 empty] | 0
STIP | [9 empty] | BOYLE | 7-20024 | US 127B | 5.27 | 0 | 5.27 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION ON US-127B FROM MILEPOINT 0.00 TO MILEPOINT 5.27 | C |  | PM/NH | 2022 | 2301000 | 1840800 |  |  | 460200 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.229 | 2020-09-14 | ADD C PHASE TO STIP; PARENT NO. 99-224.14; NEW |  |  | BOYLE | 7-20039 | US 150 |  | 13.665 | 16.441 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | Resurfacing of US 150 (MP 13.665-16.441) in Boyle County, KY. | C |  | STP | 2020 | 530000 | 530000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.252 | 2020-10-26 | ADD D PHASE TO STIP; NEW |  |  | BOYLE | 7-80000 | KY 34 US 150 |  |  |  | NEW ROUTES | NEW ROUTE(O) | CONSTRUCT A NEW CONNECTOR ROAD ON THE EAST SIDE OF DANVILLE CONNECTING KY-34 AND US-150 BYPASS(18CCN) (2020CCR) | D |  | STP | 2021 | 2080000 | 2080000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.175 | 2020-04-09 | ADD D PHASE TO STIP; PARENT NO. 99-911.09; NEW |  |  | BRACKEN | 6-9026 | KY 8 |  | 4.218 | 13.95 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 8 FROM MP 4.218 TO MP 13.950 IN BRACKEN COUNTY, KY. (2018BOP) | D |  | SAF | 2020 | 375000 | 375000 | [8 empty] | 0
STIP | [9 empty] | BRACKEN | 6-10008 | KY 8 |  | 1.202 | 1.25 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 8 BRIDGE OVER HOLTS CREEK AT FOSTER. (012B00004N) | D |  | BR/STP | 2019 | 455000 | 282100 |  |  | 172900 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030030 | BRACKEN | 6-10008 | KY 8 |  | 1.202 | 1.25 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 8 BRIDGE OVER HOLTS CREEK AT FOSTER. (012B00004N) | C |  | BR/STP | 2020 | 3325000 | 2061500 |  |  | 1263500 |  |  | OBLIGATED |  | 944232 | 944232 | 2019 | 2ND QUARTER
STIP | [9 empty] | BREATHITT | 10-375 | KY 205 | 2.15 | 7.804 | 9.954 | RELIABILITY | MINOR WIDENING(O) | IMPROVE KY-205 FROM NORTH OF KY-1812 TO SOUTH OF PEGGS FORK RD. | D |  | STP | 2021 | 1000000 | 800000 |  |  | 200000 | [5 empty] | 0
STIP | [7 empty] | NHPP | 0151090 | BREATHITT | 10-376 | KY 15 | 1.15 | 16.75 | 17.9 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE KY-15 FROM THE INTERSECTION OF NEW KY-15/30 TO INTERSECTION OF KY-1812. | D |  | NH | 2019 | 1500000 | 1500000 |  |  | 0 |  |  | OBLIGATED | 630008 | 869992 | 1500000 | 2020 | 2ND QUARTER
STIP | [9 empty] | BREATHITT | 10-376 | KY 15 | 1.15 | 16.75 | 17.9 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE KY-15 FROM THE INTERSECTION OF NEW KY-15/30 TO INTERSECTION OF KY-1812. | R |  | NH | 2021 | 2900000 | 2320000 |  |  | 580000 | [5 empty] | 0
STIP | [9 empty] | BREATHITT | 10-376 | KY 15 | 1.15 | 16.75 | 17.9 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE KY-15 FROM THE INTERSECTION OF NEW KY-15/30 TO INTERSECTION OF KY-1812. | U |  | NH | 2022 | 1150000 | 920000 |  |  | 230000 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 1003267 | BREATHITT | 10-1110 | KY 378 | 0.028 | 0.672 | 0.7 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER FROZEN CREEK ON KY 378 0.7 MI N OF KY 1812. (013B00050N) | C |  | BR/STP | 2020 | 735000 | 455700 |  |  | 279300 |  |  | OBLIGATED |  | 1009424 | 1009424 | 2019 | 3RD QUARTER
STIP | [9 empty] | BREATHITT | 10-10000 | CR 1233 |  | 0.034 | 0.04 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF MORRIS FORK ROAD BRIDGE OVER BURTON FORK. (013C00050N) | D |  | BR/STP | 2019 | 140000 | 86800 |  |  | 53200 | [5 empty] | 0
STIP | [9 empty] | BREATHITT | 10-10000 | CR 1233 |  | 0.034 | 0.04 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF MORRIS FORK ROAD BRIDGE OVER BURTON FORK. (013C00050N) | C |  | BR/STP | 2020 | 315000 | 195300 |  |  | 119700 | [5 empty] | 0
STIP | [9 empty] | BREATHITT | 10-10001 | CR 1124 |  | 0.779 | 0.787 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF LITTLE BUCKHORN ROAD BRIDGE OVER BUCKHORN CREEK. (013C00016N)(SD) | D |  | BR/STP | 2019 | 140000 | 86800 |  |  | 53200 | [5 empty] | 0
STIP | [9 empty] | BREATHITT | 10-10001 | CR 1124 |  | 0.779 | 0.787 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF LITTLE BUCKHORN ROAD BRIDGE OVER BUCKHORN CREEK. (013C00016N)(SD) | C |  | BR/STP | 2020 | 350000 | 217000 |  |  | 133000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.064 | 2019-04-30 | UDPATE FUND AMOUNT; MOD | STPBRZ | 9030085 | BREATHITT | 10-10001 | CR 1124 |  | 0.779 | 0.787 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF LITTLE BUCKHORN ROAD BRIDGE OVER BUCKHORN CREEK. (013C00016N)(SD) | C |  | STP | 2019 | 885000 | 885000 |  |  | 0 |  |  | OBLIGATED |  | 756925 | 756925 | 2019 | 3RD QUARTER
STIP | [9 empty] | BREATHITT | 10-10010 | KY 1812 |  | 14.28 | 14.286 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 1812 BRIDGE OVER JOHNSON FORK. (013B00007N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [9 empty] | BREATHITT | 10-10010 | KY 1812 |  | 14.28 | 14.286 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 1812 BRIDGE OVER JOHNSON FORK. (013B00007N) | C |  | BR/STP | 2020 | 507500 | 314650 |  |  | 192850 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.03 | 2019-03-01 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030066 | BREATHITT | 10-10010 | KY 1812 |  | 14.28 | 14.286 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 1812 BRIDGE OVER JOHNSON FORK. (013B00007N) | C |  | STP | 2019 | 532607 | 532607 |  |  | 0 |  |  | OBLIGATED | 656739 |  | 656739 | 2019 | 3RD QUARTER
STIP | [9 empty] | BREATHITT | 10-10011 | CR 1104 |  | 0.809 | 0.815 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BIG BRANCH ROAD BRIDGE OVER BIG BRANCH CREEK. (013C00008N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [9 empty] | BREATHITT | 10-10011 | CR 1104 |  | 0.809 | 0.815 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BIG BRANCH ROAD BRIDGE OVER BIG BRANCH CREEK. (013C00008N) | C |  | BR/STP | 2020 | 385000 | 238700 |  |  | 146300 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.139 | 2019-10-25 | ADD PROJECT TO STIP; NEW |  |  | BREATHITT | 10-10021 | CR 1409 |  | 0.008 |  | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES ON FLETCHER FORK (CR 1409) OVER STRONG FORK. (013C00078N) | C |  | STP | 2020 | 120000 | 120000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.229 | 2020-09-14 | ADD C PHASE TO STIP; PARENT NO. 99-224.14; NEW |  |  | BREATHITT | 10-20028 | KY 28 KY 30 |  | 0 7.511 | 5.74 10.16 | ASSET MANAGEMENT | AM-PAVEMENT(PRI)(P) | Resurfacing of KY 28 (MP 0.0-5.74) and KY 30 (MP 7.511-10.16) in Breathitt County, KY. | C |  | STP | 2020 | 1060000 | 1060000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.21 | 2020-07-31 | ADD D PHASE TO STIP; NEW |  |  | BRECKINRIDGE | 4-159 | KY 86 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | REALIGN KY 86 FROM JESSIE PRIEST ROAD TO EAST OF ROSETTA CORNERS. (2020CCR) | D |  | STP | 2020 | 600000 | 600000 |  |  | 0 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 403198 | BRECKINRIDGE | 4-1090 | CR 1021 | 0.02 | 1.42 | 1.44 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER SINKING CREEK ON DENTS BRIDGE ROAD (CR 1021) 1.4 MI W OF KY 333 (014C00003N) | C |  | BR/STP | 2020 | 406000 | 251720 |  |  | 154280 |  |  | OBLIGATED |  | 442984 | 442984 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.306 | 2021-06-16 | ADD D PHASE TO STIP; NEW |  |  | BRECKINRIDGE | 2484836 | KY 79 |  | 15.812 | 16.692 | RELIABILITY | RECONSTRUCTION(O) | ADDRESS SAFETY AND GEOMETRIC DEFICIENCIES ON KY 79 FROM KY 477 TO KY 428.(12CCN)(14CCR) (2020CCN)(R,U,C COMBINED UNDER 4-8702) | D |  | SPP | 2021 | 350100 | 100 |  |  | 350000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.123 | 2019-09-06 | ADD PROJECT TO STIP; PARENT NO. 99-65.16 AND 99-65.17; NEW | STPBRZ | 9030188 | BRECKINRIDGE | 4-10016 | CR 1100 |  | 0.162 |  | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES ON CIRCLE K RANCH RD. (CR 1100) OVER SUGAR CREEK. (014C00057N) | C |  | BR | 2020 | 308000 | 308000 |  |  | 0 |  |  | OBLIGATED |  | 547100 | 547100 | 2019 | 4TH QUARTER
STIP | [9 empty] | BRECKINRIDGE | 4-20025 | US 60 | 2.78 | 0 | 2.78 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION ON US-60 FROM MILEPOINT 0.00 TO MILEPOINT 2.78 | C |  | PM/NH | 2022 | 642000 | 513600 |  |  | 128400 | [5 empty] | 0
STIP | [9 empty] | BRECKINRIDGE | 4-20026 | US 60 | 9.29 | 3.45 | 12.74 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION ON US-60 FROM MILEPOINT 3.45 TO MILEPOINT 12.74 | C |  | PM/NH | 2022 | 1739000 | 1391200 |  |  | 347800 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.229 | 2020-09-14 | ADD C PHASE TO STIP; PARENT NO. 99-224.14; NEW |  |  | BRECKINRIDGE | 4-20037 | KY 144 KY 737 |  | 14.377 0 | 19.45 3.421 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | Resurfacing of KY 144 (MP 14.377-19.45) and KY 737 (MP 0.0-3.421) in Breckinridge County, KY. | C |  | STP | 2020 | 990000 | 990000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.279 | 2021-03-05 | ADD C PHASE TO STIP;PARENT NO. 99-224.14; NEW |  |  | BRECKINRIDGE | 4-20040 | KY 1616 |  | 0 | 1.28 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | Resurface KY 1616 from MP 0.00 to MP 1.28 in Breckinridge County, KY. | C |  | STP | 2021 | 152015 | 152015 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.271 | 2021-01-12 | TIP FY 20-25, AMEND#2; ADD PROJECT TO STIP; NEW |  |  | BULLITT | 5-347.5 | KY 44 | [5 empty] | WIDEN KY 44 FROM 2 TO 4 LANES FROM US 31E TO KINGS CHURCH ROAD AND A 3 LANE SECTION FROM KINGS CHURCH ROAD TO SPENCER COUNTY LINE. | D |  | STP | 2021 | 1000000 | 800000 |  |  | 200000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.309 | 2021-06-10 | TIP FY 20-25, ADMIN MOD#17; UPDATE FUND AMOUNTS; MOD |  |  | BULLITT | 5-347.5 | KY 44 | [5 empty] | WIDEN KY 44 FROM 2 TO 4 LANES FROM US 31E TO KINGS CHURCH ROAD AND A 3 LANE SECTION FROM KINGS CHURCH ROAD TO SPENCER COUNTY LINE. | D |  | STP | 2021 | 581966 | 465572 |  |  | 116394 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.309 | 2021-06-10 | TIP FY 20-25, ADMIN MOD#17; ADD CRRSAA FUNDING TO D PHASE; MOD |  |  | BULLITT | 5-347.5 | KY 44 | [5 empty] | WIDEN KY 44 FROM 2 TO 4 LANES FROM US 31E TO KINGS CHURCH ROAD AND A 3 LANE SECTION FROM KINGS CHURCH ROAD TO SPENCER COUNTY LINE. | D |  |  | 2021 | 418034 | 418034 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.227 | 2020-08-31 | TIP FY 20-25, ADMIN MOD#8; ADD PROJECT TO STIP; NEW |  |  | BULLITT | 5-347.51 | KY 44 |  | 23.6 | 23.7 | RELIABILITY | RECONSTRUCTION(O) | NEW TURN LANES IN FRONT OF BULLITT EAST HIGH SCHOOL (BREAKOUT FROM 347.50) (18CCN). | D |  |  | 2020 | 500000 | 400000 |  |  |  | 100000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.227 | 2020-08-31 | TIP FY 20-25, ADMIN MOD#8; ADD PROJECT TO STIP; NEW |  |  | BULLITT | 5-347.51 | KY 44 |  | 23.6 | 23.7 | RELIABILITY | RECONSTRUCTION(O) | NEW TURN LANES IN FRONT OF BULLITT EAST HIGH SCHOOL (BREAKOUT FROM 347.50) (18CCN). | R |  |  | 2021 | 100000 | 80000 |  |  |  | 20000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.227 | 2020-08-31 | TIP FY 20-25, ADMIN MOD#8; ADD PROJECT TO STIP; NEW |  |  | BULLITT | 5-347.51 | KY 44 |  | 23.6 | 23.7 | RELIABILITY | RECONSTRUCTION(O) | NEW TURN LANES IN FRONT OF BULLITT EAST HIGH SCHOOL (BREAKOUT FROM 347.50) (18CCN). | U |  |  | 2021 | 545000 | 436000 |  |  |  | 109000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.227 | 2020-08-31 | TIP FY 20-25, ADMIN MOD#8; ADD PROJECT TO STIP; NEW |  |  | BULLITT | 5-347.51 | KY 44 |  | 23.6 | 23.7 | RELIABILITY | RECONSTRUCTION(O) | NEW TURN LANES IN FRONT OF BULLITT EAST HIGH SCHOOL (BREAKOUT FROM 347.50) (18CCN). | C |  |  | 2022 | 680000 | 544000 |  |  |  | 136000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.183 | 2020-04-24 | TIP FY 20-25; ADMIN MOD#1; ADD PROJECT TO STIP; NEW |  |  | Bullitt, Jefferson, Oldham | 5-384 | [6 empty] | THE KIPDA REGIONAL RIDESHARE PROGRAM PROVIDES RIDE-MATCHING SERVICES, EMPLOYER-BASED AND REGIONAL RIDESHARING, VANPOOL SUBSCRIPTION SERVICES, PROMOTIONAL ACTIVITIES TO SUPPORT RIDESHARING WHICH INCLUDES CARPOOLING, VANPOOLING, TAKING TRANSIT, WALKING, TELECOMMUTING AND BIKEPOOLING. THIS ALSO INCLUDES PROGRAM EVALUATION AND ADMINISTRATION. | C |  | SLO | 2020 | 1391915 | 1113532 |  |  |  | 278383 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.183 | 2020-04-24 | TIP FY 20-25; ADMIN MOD#1; ADD PROJECT TO STIP; NEW |  |  | Bullitt, Jefferson, Oldham | 5-384 | [6 empty] | THE KIPDA REGIONAL RIDESHARE PROGRAM PROVIDES RIDE-MATCHING SERVICES, EMPLOYER-BASED AND REGIONAL RIDESHARING, VANPOOL SUBSCRIPTION SERVICES, PROMOTIONAL ACTIVITIES TO SUPPORT RIDESHARING WHICH INCLUDES CARPOOLING, VANPOOLING, TAKING TRANSIT, WALKING, TELECOMMUTING AND BIKEPOOLING. THIS ALSO INCLUDES PROGRAM EVALUATION AND ADMINISTRATION. | C |  | SLO | 2021 | 1433672 | 1146938 |  |  |  | 286734 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.183 | 2020-04-24 | TIP FY 20-25; ADMIN MOD#1; ADD PROJECT TO STIP; NEW |  |  | Bullitt, Jefferson, Oldham | 5-384 | [6 empty] | THE KIPDA REGIONAL RIDESHARE PROGRAM PROVIDES RIDE-MATCHING SERVICES, EMPLOYER-BASED AND REGIONAL RIDESHARING, VANPOOL SUBSCRIPTION SERVICES, PROMOTIONAL ACTIVITIES TO SUPPORT RIDESHARING WHICH INCLUDES CARPOOLING, VANPOOLING, TAKING TRANSIT, WALKING, TELECOMMUTING AND BIKEPOOLING. THIS ALSO INCLUDES PROGRAM EVALUATION AND ADMINISTRATION. | C |  | SLO | 2022 | 1476683 | 1181346 |  |  |  | 295337 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.183 | 2020-04-24 | TIP FY 20-25; ADMIN MOD#1; ADD PROJECT TO STIP; NEW |  |  | Bullitt, Jefferson, Oldham | 5-384 | [6 empty] | THE KIPDA REGIONAL RIDESHARE PROGRAM PROVIDES RIDE-MATCHING SERVICES, EMPLOYER-BASED AND REGIONAL RIDESHARING, VANPOOL SUBSCRIPTION SERVICES, PROMOTIONAL ACTIVITIES TO SUPPORT RIDESHARING WHICH INCLUDES CARPOOLING, VANPOOLING, TAKING TRANSIT, WALKING, TELECOMMUTING AND BIKEPOOLING. THIS ALSO INCLUDES PROGRAM EVALUATION AND ADMINISTRATION. | C |  | SLO | 2023 | 1520983 | 1216786 |  |  |  | 304197 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.183 | 2020-04-24 | TIP FY 20-25; ADMIN MOD#1; ADD PROJECT TO STIP; NEW |  |  | Bullitt, Jefferson, Oldham | 5-384 | [6 empty] | THE KIPDA REGIONAL RIDESHARE PROGRAM PROVIDES RIDE-MATCHING SERVICES, EMPLOYER-BASED AND REGIONAL RIDESHARING, VANPOOL SUBSCRIPTION SERVICES, PROMOTIONAL ACTIVITIES TO SUPPORT RIDESHARING WHICH INCLUDES CARPOOLING, VANPOOLING, TAKING TRANSIT, WALKING, TELECOMMUTING AND BIKEPOOLING. THIS ALSO INCLUDES PROGRAM EVALUATION AND ADMINISTRATION. | C |  | SLO | 2024 | 1566613 | 1253290 |  |  |  | 313323 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.183 | 2020-04-24 | TIP FY 20-25; ADMIN MOD#1; ADD PROJECT TO STIP; NEW |  |  | Bullitt, Jefferson, Oldham | 5-384 | [6 empty] | THE KIPDA REGIONAL RIDESHARE PROGRAM PROVIDES RIDE-MATCHING SERVICES, EMPLOYER-BASED AND REGIONAL RIDESHARING, VANPOOL SUBSCRIPTION SERVICES, PROMOTIONAL ACTIVITIES TO SUPPORT RIDESHARING WHICH INCLUDES CARPOOLING, VANPOOLING, TAKING TRANSIT, WALKING, TELECOMMUTING AND BIKEPOOLING. THIS ALSO INCLUDES PROGRAM EVALUATION AND ADMINISTRATION. | C |  | SLO | 2025 | 1613611 | 1290889 |  |  |  | 322722 |  |  |  |  | 0
STIP | YES | [5 empty] | NOT IN TIP |  |  | BULLITT | 5-391.2 | KY 480 | 0.83 | 2.01 | 2.84 | RELIABILITY | RECONSTRUCTION(O) | WIDEN CEDAR GROVE ROAD (KY-480) FROM CEDAR GROVE ELEMENTARY SCHOOL TO VALLEY VIEW DRIVE. (12CCR)(14CCR) (SEE 5-391.3 FOR INTERCHANGE IMPROVEMENTS) | C |  | STP | 2022 | 6240000 | 4992000 |  |  | 1248000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; UPDATE FISCAL YEAR AND FUND AMOUNTS; MOD |  |  | BULLITT | 5-391.2 | KY 480 | 0.83 | 2.01 | 2.84 | RELIABILITY | RECONSTRUCTION(O) | WIDEN CEDAR GROVE ROAD (KY-480) FROM CEDAR GROVE ELEMENTARY SCHOOL TO VALLEY VIEW DRIVE. (12CCR)(14CCR) (SEE 5-391.3 FOR INTERCHANGE IMPROVEMENTS) | C |  | STP | 2021 | 7900000 | 6320000 |  |  | 1580000 | [5 empty] | 0
STIP | [9 empty] | Bullitt | 5-391.30 | KY 480 |  | 0.8 | 1.3 | RELIABILITY | RECONSTRUCTION(O) | Improvements to the I-65/KY 480 Interchange including ramp improvements and turning lanes, from MP 1.1 to MP 1.11. | C |  | NHS | 2018 | 5200000 | 5200000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.001 | 2018-12-06 | TIP FY 18-21; AMENDMENT#3; REMOVE CONSTRUCTION IN FY 2018; MOD |  |  | Bullitt | 5-391.30 | KY 480 |  | 0.8 | 1.3 | RELIABILITY | RECONSTRUCTION(O) | Improvements to the I-65/KY 480 Interchange including ramp improvements and turning lanes, from MP 1.1 to MP 1.11. | C |  | NHS |  | 5200000 | 5200000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; UPDATE FISCAL YEAR, FUND AMOUNTS AND FUND TYPE; MOD |  |  | Bullitt | 5-391.30 | KY 480 |  | 0.8 | 1.3 | RELIABILITY | RECONSTRUCTION(O) | Improvements to the I-65/KY 480 Interchange including ramp improvements and turning lanes, from MP 1.1 to MP 1.11. | C |  | STP | 2022 | 9490000 | 7592000 |  |  | 1898000 | [5 empty] | 0
TIP | [6 empty] | NOT IN STIP |  |  | Bullitt, Jefferson, Oldham | 5-440.01 | Various Sidewalks on State Routes in Kentucky | [5 empty] | Installation of sidewalks to fix gaps in pedestrian network on various state maintained roads in Oldham, Jefferson and Bullitt counties. | C |  | SLO | 2019 | 100000 | 100000 | [8 empty] | 0
TIP | [6 empty] | NOT IN STIP |  |  | Bullitt, Jefferson, Oldham | 5-440.01 | Various Sidewalks on State Routes in Kentucky | [5 empty] | Installation of sidewalks to fix gaps in pedestrian network on various state maintained roads in Oldham, Jefferson and Bullitt counties. | C |  | SLO | 2018 | 100000 | 100000 | [8 empty] | 0
TIP | [6 empty] | NOT IN STIP |  |  | Bullitt, Jefferson, Oldham | 5-440.01 | Various Sidewalks on State Routes in Kentucky | [5 empty] | Installation of sidewalks to fix gaps in pedestrian network on various state maintained roads in Oldham, Jefferson and Bullitt counties. | C |  | SLO | 2020 | 100000 | 100000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.271 | 2021-01-12 | TIP FY 20-25, AMENDMENT#2; ADD PROJECT TO STIP; NEW |  |  | Bullitt, Jefferson, Oldham | TBD | Kentuckiana Air Education | [5 empty] | Information/outreach campaign to educate public about air quality issues and encourage the public to make air-friendly choices. |  |  | STP | 2021 | 250000 | 200000 |  |  | 50000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.271 | 2021-01-12 | TIP FY 20-25, AMENDMENT#2; ADD PROJECT TO STIP; NEW |  |  | Bullitt, Jefferson, Oldham | TBD | Kentuckiana Air Education | [5 empty] | Information/outreach campaign to educate public about air quality issues and encourage the public to make air-friendly choices. |  |  | STP | 2022 | 250000 | 200000 |  |  | 50000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.271 | 2021-01-12 | TIP FY 20-25, AMENDMENT#2; ADD PROJECT TO STIP; NEW |  |  | Bullitt, Jefferson, Oldham | TBD | Kentuckiana Air Education | [5 empty] | Information/outreach campaign to educate public about air quality issues and encourage the public to make air-friendly choices. |  |  | STP | 2023 | 250000 | 200000 |  |  | 50000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.271 | 2021-01-12 | TIP FY 20-25, AMENDMENT#2; ADD PROJECT TO STIP; NEW |  |  | Bullitt, Jefferson, Oldham | TBD | Kentuckiana Air Education | [5 empty] | Information/outreach campaign to educate public about air quality issues and encourage the public to make air-friendly choices. |  |  | STP | 2024 | 250000 | 200000 |  |  | 50000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.271 | 2021-01-12 | TIP FY 20-25, AMENDMENT#2; ADD PROJECT TO STIP; NEW |  |  | Bullitt, Jefferson, Oldham | TBD | Kentuckiana Air Education | [5 empty] | Information/outreach campaign to educate public about air quality issues and encourage the public to make air-friendly choices. |  |  | STP | 2025 | 250000 | 200000 |  |  | 50000 | [5 empty] | 0
STIP | YES | [5 empty] | NEW | NHPPIM | 0655120 | BULLITT | 5-538 | I 65 |  | 113.5 | 115 | RELIABILITY | NEW INTERCHANGE(O) | CONSTRUCT NEW I-65 INTERCHANGE BETWEEN KY-480 AND KY-245. | C |  | NH | 2019 | 18720000 | 18720000 |  |  | 0 |  |  | OBLIGATED | 27707722 |  | 27707722 | 2019 | 2ND QUARTER
TIP | [6 empty] | TIP AND STIP AMOUNTS ARE DIFFERENT |  |  | Bullitt | 5-538 | I- 65 | [5 empty] | Construct new I-65 interchange between KY 480 and KY 245, MP 113.50 to MP 115.00. Project includes construction of a 3 lane connector road from KY 61 east to Alpha Way. | C |  | NHS | 2018 | 27000000 | 27000000 | [8 empty] | 0
STIP | [9 empty] | BULLITT | 5-544 | KY 44 | 0.5 | 11.75 | 12.25 | SAFETY | BIKE/PED FACIL(O) | INSTALLATION OF NEW SIDEWALKS AND REHABILITATION OF EXISTING SIDEWALKS TO FIX GAPS IN THE PEDESTRIAN NETWORK ALONG KY 44 FROM FRANK E. SIMON DRIVE (CITY PARK DRIVE) EAST TO KY 61 IN SHEPHERDSVILLE. KY 44 MILEPOINTS FROM 11.75 TO 12.25.(2016BOP) | R |  | SLO | 2019 | 60000 | 48000 |  |  |  | 12000 |  |  |  |  | 0
TIP | [6 empty] | TIP AND STIP AMOUNTS ARE DIFFERENT |  |  | BULLITT | 5-544 | KY 44 | 0.5 | 11.75 | 12.25 | SAFETY | BIKE/PED FACIL(O) | Installation of new sidewalks and rehabilitation existing of sidewalks to fix gaps in the pedestrian network along KY 44 from Frank E. Simon Drive (City Park Drive) east to KY61 in Shepherdsville. MP 11.75 to 12.25. | R |  | SLO | 2019 | 108000 | 108000 | [8 empty] | 0
TIP | [6 empty] | TIP AND STIP AMOUNTS ARE DIFFERENT |  |  | BULLITT | 5-544 | KY 44 | 0.5 | 11.75 | 12.25 | SAFETY | BIKE/PED FACIL(O) | Installation of new sidewalks and rehabilitation existing of sidewalks to fix gaps in the pedestrian network along KY 44 from Frank E. Simon Drive (City Park Drive) east to KY61 in Shepherdsville. MP 11.75 to 12.25. | U |  | SLO | 2019 | 60000 | 60000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.165 | 2020-02-03 | TIP FY 18-21, ADMIN MOD#42; REMOVE FY 2019 UTILITIES PHASE AND ASSOCIATED FUNDS; PROJECT COMPLETED AS OF DEC. 2019; MOD |  |  | BULLITT | 5-544 | KY 44 | 0.5 | 11.75 | 12.25 | SAFETY | BIKE/PED FACIL(O) | Installation of new sidewalks and rehabilitation existing of sidewalks to fix gaps in the pedestrian network along KY 44 from Frank E. Simon Drive (City Park Drive) east to KY61 in Shepherdsville. MP 11.75 to 12.25. | U
STIP | [7 empty] | STPM | 3001507 | BULLITT | 5-544 | KY 44 | 0.5 | 11.75 | 12.25 | SAFETY | BIKE/PED FACIL(O) | INSTALLATION OF NEW SIDEWALKS AND REHABILITATION OF EXISTING SIDEWALKS TO FIX GAPS IN THE PEDESTRIAN NETWORK ALONG KY 44 FROM FRANK E. SIMON DRIVE (CITY PARK DRIVE) EAST TO KY 61 IN SHEPHERDSVILLE. KY 44 MILEPOINTS FROM 11.75 TO 12.25.(2016BOP) | C |  | SLO | 2019 | 220000 | 176000 |  |  |  | 44000 |  | OBLIGATED | 283870 |  | 283870 | 2019 | 3RD QUARTER
TIP | [6 empty] | TIP AND STIP AMOUNTS ARE DIFFERENT |  |  | BULLITT | 5-544 | KY 44 | 0.5 | 11.75 | 12.25 | SAFETY | BIKE/PED FACIL(O) | Installation of new sidewalks and rehabilitation existing of sidewalks to fix gaps in the pedestrian network along KY 44 from Frank E. Simon Drive (City Park Drive) east to KY61 in Shepherdsville. MP 11.75 to 12.25. | C |  | SLO | 2019 | 276000 | 276000 | [8 empty] | 0
STIP | YES | [6 empty] | NHPP | 655123 | BULLITT, JEFFERSON | 5-550 | I 65 | 18.392 | 104.788 | 123.18 | RELIABILITY | MAJOR WIDENING(O) | WIDEN I-65 FROM 6 TO 8 LANES FROM KY-61 (PRESTON HIGHWAY) IN LEBANON JUNCTION TO I-265 (GENE SNYDER FREEWAY) | P |  | NH | 2020 | 250000 | 250000 |  |  | 0 |  |  | OBLIGATED | 250000 |  | 250000 | 2019 | 2ND QUARTER
|  |  |  | ADMINISTRATIVE MODIFCATION | 2018.036 | 2019-03-12 | TIP FY 18-21, ADMIN MOD#27, CHANGE DESCRIPTION TO REVISE ENDING MP FROM 123.18 TO 124.70; MOD | NHPP | 655123 | BULLITT, JEFFERSON | 5-550 | I 65 | 18.392 | 104.788 | 124.70 | RELIABILITY | MAJOR WIDENING(O) | WIDEN I-65 FROM 6 TO 8 LANES FROM KY-61 (PRESTON HIGHWAY) IN LEBANON JUNCTION TO I-265 (GENE SNYDER FREEWAY) | P |  | NH | 2020 | 250000 | 250000 | [5 empty] | OBLIGATED | 266000 |  | 266000 | 2019 | 2ND QUARTER
STIP | YES | [5 empty] | NOT IN TIP |  |  | BULLITT, JEFFERSON | 5-550 | I 65 | 18.392 | 104.788 | 123.18 | RELIABILITY | MAJOR WIDENING(O) | WIDEN I-65 FROM 6 TO 8 LANES FROM KY-61 (PRESTON HIGHWAY) IN LEBANON JUNCTION TO I-265 (GENE SNYDER FREEWAY) | D |  | NH | 2022 | 7470000 | 5976000 |  |  | 1494000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFCATION | 2018.036 | 2019-03-12 | TIP FY 18-21, ADMIN MOD#27, CHANGE DESCRIPTION TO REVISE ENDING MP FROM 123.18 TO 124.70; MOD | NHPP | 655123 | BULLITT, JEFFERSON | 5-550 | I 65 | 18.392 | 104.788 | 124.70 | RELIABILITY | MAJOR WIDENING(O) | WIDEN I-65 FROM 6 TO 8 LANES FROM KY-61 (PRESTON HIGHWAY) IN LEBANON JUNCTION TO I-265 (GENE SNYDER FREEWAY) | D |  | NH | 2022 | 7470000 | 5976000 |  |  | 1494000 | [5 empty] | 0
TIP | [6 empty] | NOT IN STIP |  |  | Bullitt, Clark, Floyd, Jefferson, Oldham | 5-562 | TARC Comprehensive Operations Analysis & Strategic Plan | [5 empty] | Perform a Comprehensive Operations Analysis as Phase I of the project, to analyze and evaluate the existing TARC system and services, in comparison with the community growth, economic trends, land use development patterns, and current and future needs for public transportation system improvements. Phase II of the project is developing a TARC Long Range Plan to address a long-term strategy for transit system improvements, level of investment and explore options for sustainable sources of funding. The overall project will improve the performance of the existing services/maximize service efficiency, and develop a long range plan for major investments as funding becomes available. | P |  | SLO | 2018 | 442500 | 354000 |  |  |  | 88500 |  |  |  |  | 0
TIP | [6 empty] | NOT IN STIP |  |  | Bullitt, Oldham, Shelby | 5-564 | Regional Connector | [5 empty] | Study new connection between I-65 in Bullitt County to I-64 in Shelby County to I-71 in Oldham County. | D |  | STP-ST | 2019 | 2000000 | 2000000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFCATION | 2018.107 | 2019-07-26 | TIP FY 18-21, ADMIN MOD#33; ADD PROJECT TO STIP; NEW | STP | 0655124 | BULLITT | 5-568 | I 65 |  |  |  | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | UPGRADE THE EXISTING WELCOME CENTER FACILITY IN BULLITT COUNTY ALONG THE I-65 CORRIDOR WITH NEW TILE FLOORS, NEW RESTROOM FIXTURES, PARTITIONS, AND DOORS AS WELL AS NEW BUILDING DOORS AND WINDOWS, AMONG SEVERAL OTHER IMPROVEMENTS. (2018BOP) | C |  | STP | 2019 | 1600000 | 1280000 |  |  |  | 320000 |  | OBLIGATED | 1280000 |  | 1280000 | 2019 | 4TH QUARTER
TIP | [6 empty] | NOT IN STIP |  |  | Bullitt, Jefferson | 5-931 | Horizontal Alignment Signing | [5 empty] | Project will provide signage at the following locations as part of the Horizontal Alignment Signing Initiative: *KY 44 in Bullitt County between mile point 0.000 to mile point 26.286; *KY 676 in Franklin County between mile point 0.000 to mile point 5.287; *US 60 in Franklin County between mile point 0.000 to mile point 14.038; *I-64 in Jefferson County between mile point 0.000 to mile point 23.974; and *US 421 in Trimble County between mile point 0.000 to mile point 19.198. | C |  | HSIP | 2018 | 275000 | 275000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFCATION | 2018.057 | 2019-04-26 | TIP FY 18-21, ADMIN MOD#29; ADD PROJECT TO STIP; NEW | HSIP | 5118044 | BULLITT | 5-934 | KY 44 |  | 8.116 | 9.285 | SAFETY | SAFETY-HAZARD ELIM(P) | HIGH FRICTION SURFACE TREATMENT ON KY 44 FROM MP 8.116 TO MP 9.285. (2018BOP) | C |  | SAF | 2019 | 97000 | 97000 | [5 empty] | OBLIGATED | 97000 |  | 97000 | 2019 | 3RD QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFCATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; ADD PROJECT TO STIP; NEW |  |  | BULLITT | 5-4305 | KY 1526 |  | 5.4 | 5.49 | SAFETY | SAF-GUARDRAIL(P) | INSTALL GUARDRAIL ON KY-1526 IN BULLITT COUNTY | C |  | NHPP | 2021 | 18000 | 14400 |  |  | 3600 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFCATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; ADD PROJECT TO STIP; NEW |  |  | BULLITT | 5-4307 | KY 1319 |  | 0.47 | 0.52 | SAFETY | SAF-GUARDRAIL(P) | INSTALL GUARDRAIL ON KY-1319 IN BULLITT COUNTY | C |  | SAF | 2024 | 11000 | 8800 |  |  | 2200 | [5 empty] | 0
STIP | YES | [5 empty] | NOT IN TIP |  |  | BULLITT | 5-8509 | KY 245 | 1.99 | 4.425 | 6.415 | RELIABILITY | MINOR WIDENING(O) | WIDEN KY-245 FROM BERNHEIM FOREST TO THE COMMUNITY COLLEGE. (08CCN)(10CCR)(14CCR)(16CCR) | C |  | STP | 2022 | 12640000 | 10112000 |  |  | 2528000 | [5 empty] | 0
STIP | YES | [5 empty] | NOT IN TIP |  |  | BULLITT | 5-20036 | KY 480 | 5.14 | 0 | 5.14 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION ON KY-480 FROM MILEPOINT 0.00 TO MILEPOINT 5.14 | C |  | PM/STP | 2022 | 910000 | 728000 |  |  | 182000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.077 | 2019-05-28 | TIP FY 18-21; ADMIN MOD#31; KIPDA ID#173; ADD PROJECT TO STIP; NEW |  |  | BULLITT | 5-20043 | I 65 |  | 103.308 | 104.7 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | REPAIR AND GRIND PCC PAVEMENT FROM THE HARDIN COUNTY LINE (MP 103.308) EXTENDING NORTH TO THE SOUTH SIDE OF LEBANON JCT OVERPASS (MP 104.7). (2018BOP) | C |  | NH | 2020 | 10000000 | 10000000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.161 | 2020-02-21 | ADD PROJECT TO STIP; PARENT NO. 99-911.09; NEW |  |  | BUTLER | 3-932 | KY 70 |  | 11.031 | 11.506 | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALLATION OF HIGH FRICTION SURFACE TREATMENT ON KY 70 FROM MP. 11.031 TO MP 11.506 IN BUTLER COUNTY, KY. (2018BOP) | C |  | SAF | 2020 | 150000 | 150000 | [8 empty] | 0
STIP | [9 empty] | BUTLER | 3-2042.3 | WN 9007 |  | 35.7 | 36.1 | RELIABILITY | I-CHANGE RECONST(O) | I-65 SPUR CORRIDOR: IMPROVE THE NATCHER PARKWAY/US-231 INTERCHANGE (EXIT 36). (2016BOP) | C |  | NH | 2021 | 6750000 | 5400000 |  |  | 1350000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.276 | 2021-02-12 | INCREASE FUNDS BASED ON NEW ESTIMATE; MOD |  |  | BUTLER | 3-2042.3 | WN 9007 |  | 35.7 | 36.1 | RELIABILITY | I-CHANGE RECONST(O) | I-65 SPUR CORRIDOR: IMPROVE THE NATCHER PARKWAY/US-231 INTERCHANGE (EXIT 36). (2016BOP) | C |  | NHPP | 2021 | 8508500 | 8508500 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.111 | 2019-08-02 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 5074009 | BUTLER EDMONSON | 3-9021 | KY 185 |  | 0 0 | 7.232 2.185 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 185 FROM MP 0.000 TO MP 7.232 IN BUTLER COUNTY AND FROM MP 0.000 TO MP 2.185 IN EDMONSON COUNTY. (2018BOP) | D |  | SAF | 2019 | 350000 | 350000 | [5 empty] | OBLIGATED |  | 350000 | 350000 | 2019 | 4TH QUARTER
STIP | [9 empty] | BUTLER | 3-10003 | KY 70 |  | 4.19 | 4.204 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-70 BRIDGE OVER PANTHER CREEK. (016B00019N) | D |  | BR/STP | 2019 | 245000 | 151900 |  |  | 93100 | [5 empty] | 0
STIP | [7 empty] | STP | 9030009 | BUTLER | 3-10003 | KY 70 |  | 4.19 | 4.204 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-70 BRIDGE OVER PANTHER CREEK. (016B00019N) | C |  | BR/STP | 2020 | 889000 | 551180 |  |  | 337820 |  |  | OBLIGATED | 525480 |  | 525480 | 2019 | 2ND QUARTER
STIP | [9 empty] | BUTLER | 3-10004 | CR 1008 |  | 3.903 | 3.909 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF WAVERLY SCHOOL ROAD BRIDGE OVER LITTLE BULL CREEK. (016C00031N) | D |  | BR/STP | 2019 | 157500 | 97650 |  |  | 59850 | [5 empty] | 0
STIP | [9 empty] | BUTLER | 3-10004 | CR 1008 |  | 3.903 | 3.909 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF WAVERLY SCHOOL ROAD BRIDGE OVER LITTLE BULL CREEK. (016C00031N) | C |  | BR/STP | 2020 | 266000 | 164920 |  |  | 101080 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.017 | 2019-01-23 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STP | 9030010 | BUTLER | 3-10004 | CR 1008 |  | 3.903 | 3.909 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF WAVERLY SCHOOL ROAD BRIDGE OVER LITTLE BULL CREEK. (016C00031N) | C |  | STP | 2020 | 552000 | 552000 |  |  | 0 |  |  | OBLIGATED | 427680 |  | 427680 | 2019 | 2ND QUARTER
STIP | [9 empty] | BUTLER | 3-20007 | WK 9001 |  | 87.544 | 88.433 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF WENDELL H. FORD WESTERN KY PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 87.544 TO MILEPOINT 88.433 | D |  | PM/NH | 2021 | 70000 | 56000 |  |  | 14000 | [5 empty] | 0
STIP | [9 empty] | BUTLER | 3-20007 | WK 9001 |  | 87.544 | 88.433 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF WENDELL H. FORD WESTERN KY PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 87.544 TO MILEPOINT 88.433 | C |  | PM/NH | 2021 | 700000 | 560000 |  |  | 140000 | [5 empty] | 0
STIP | [9 empty] | BUTLER | 3-20008 | WN 9007 |  | 21.78 | 28.5 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF WILLIAM H. NATCHER PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 21.78 TO MILEPOINT 28.5 (26.42 NON-CARDINAL) | D |  | PM/NH | 2022 | 540000 | 432000 |  |  | 108000 | [5 empty] | 0
STIP | [9 empty] | BUTLER | 3-20008 | WN 9007 |  | 21.78 | 28.5 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF WILLIAM H. NATCHER PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 21.78 TO MILEPOINT 28.5 (26.42 NON-CARDINAL) | C |  | PM/NH | 2022 | 5400000 | 4320000 |  |  | 1080000 | [5 empty] | 0
STIP | [9 empty] | BUTLER | 3-20010 | WN 9007 |  | 34.724 | 37.143 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT ON WILLIAM H. NATCHER PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 34.724 TO MILEPOINT 37.143 | D |  | PM/NH | 2019 | 240000 | 192000 |  |  | 48000 | [5 empty] | 0
STIP | [9 empty] | BUTLER | 3-20010 | WN 9007 |  | 34.724 | 37.143 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT ON WILLIAM H. NATCHER PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 34.724 TO MILEPOINT 37.143 | C |  | PM/NH | 2019 | 2400000 | 1920000 |  |  | 480000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.126 | 2019-09-20 | ADD PROJECT TO STIP; NEW |  |  | BUTLER | [5 empty] | RELIABILITY | FERRY OPERATION(P) | FABRICATION OF A FERRY BOAT TUG TO INCLUDE A PADDLE WHEEL FOR THE ROCHESTER FERRY. | C |  | FBP | 2019 | 150000 | 120000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.322 | 2021-07-27 | ADD PROJECT TO STIP; NEW (APPLICANT: BUTLER CO FISCAL COURT; PROJECT TITLE: ROCHESTER FERRY RIVER GAUGE) |  |  | BUTLER | [7 empty] | INSTALLATION OF A RIVER GAUGE TO MONITOR WATER LEVELS AT THE FERRY CROSSING IN ROCHESTER. | C |  |  | 2021 | 19200 | 19200 | [8 empty] | 0
STIP | [9 empty] | CALDWELL | 2-10000 | KY 126 |  | 2.26 | 2.36 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-126 BRIDGE OVER DREEN CREEK. (017B00023N) | D |  | BR/STP | 2019 | 245000 | 151900 |  |  | 93100 | [5 empty] | 0
STIP | [9 empty] | CALDWELL | 2-10000 | KY 126 |  | 2.26 | 2.36 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-126 BRIDGE OVER DREEN CREEK. (017B00023N) | C |  | BR/STP | 2020 | 1312500 | 813750 |  |  | 498750 | [5 empty] | 0
STIP | [9 empty] | CALDWELL | 2-20000 | I 24 |  | 54.842 | 57.389 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT ON I-24 BOTH DIRECTION(S) FROM MILEPOINT 54.842 TO MILEPOINT 57.389 | D |  | PM/NH | 2022 | 250000 | 200000 |  |  | 50000 | [5 empty] | 0
STIP | [9 empty] | CALDWELL | 2-20000 | I 24 |  | 54.842 | 57.389 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT ON I-24 BOTH DIRECTION(S) FROM MILEPOINT 54.842 TO MILEPOINT 57.389 | C |  | PM/NH | 2022 | 2500000 | 2000000 |  |  | 500000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.126 | 2019-09-20 | INCREASE FUND AMOUNT AND UPDATE FISCAL YEAR. THIS PROJECT IS IN THE 2018 HIGHWAY PLAN FISCAL YEAR 2022 AND $2,750,000; MOD |  |  | CALDWELL | 2-20000 | I 24 |  | 54.842 | 57.389 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT ON I-24 BOTH DIRECTION(S) FROM MILEPOINT 54.842 TO MILEPOINT 57.389. (LET UNDER 1-20011) | C |  | NH | 2020 | 5946000 | 5946000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | CALDWELL | 2-20004 | I 69 |  | 82.934 | 86.344 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-69 BOTH DIRECTION(S) FROM MILEPOINT 82.934 TO MILEPOINT 86.344. | D |  | PM/NH | 2021 | 400000 | 320000 |  |  | 80000 | [5 empty] | 0
STIP | [9 empty] | CALDWELL | 2-20004 | I 69 |  | 82.934 | 86.344 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-69 BOTH DIRECTION(S) FROM MILEPOINT 82.934 TO MILEPOINT 86.344. | C |  | PM/NH | 2021 | 4000000 | 3200000 |  |  | 800000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.229 | 2020-09-14 | ADD C PHASE TO STIP; PARENT NO. 99-224.14; NEW |  |  | CALDWELL | 2-20055 | US 62 |  | 3.644 | 6.97 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | Resurfacing of US 62 (MP 3.644-6.97) in Caldwell County, KY. | C |  | STP | 2020 | 1315000 | 1315000 |  |  | 0 | [5 empty] | 0
STIP | [7 empty] | NHPP | 6411036 | CALLOWAY | 1-314.2 | US 641 | 5.7 | 0 | 5.666 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE US-641 FROM THE TENNESSEE STATE LINE TO MURRAY PRIORITY SECTION 2; FROM TENN. STATE LINE TO CLARKS RIVER BRIDGE.(SEE 1-8852.00) | D |  | NH | 2019 | 2000000 | 2000000 |  |  | 0 |  |  | OBLIGATED |  | 2875000 | 2875000 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.09 | 2019-06-26 | UPDATE DESCRIPTION & FUNDING. INDOT HAS COMMITED TO FUNDING DESIGN AND RIGHT OF WAY FUNDING IN FY 2019 & FY 2020. FUNDING FOR THE UTILITY PHASE AND THE CONSTRUCTION PHASE FOR THE SECTION OF THE PROJECT IN TENNESSEE NOT SCHEDULED UNTIL BEYOND FY 2020; MOD | NHPP | 6411036 | CALLOWAY | 1-314.2 | US 641 | 5.7 | 0 | 5.666 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE US-641 FROM THE TENNESSEE STATE LINE TO MURRAY PRIORITY SECTION 2; FROM HOWARD ROAD, JUST NORTH OF PURYEAR TENNESSEE, TO CLARKS RIVER BRIDGE SOUTH OF MURRAY KENTUCKY. | D |  | NH | 2019 | 5200000 | 1900000 |  |  | 1800000 |  |  | OBLIGATED | 2875000 |  | 2875000 | 2019 | 4TH QUARTER
STIP | [9 empty] | CALLOWAY | 1-314.2 | US 641 | 5.7 | 0 | 5.666 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE US-641 FROM THE TENNESSEE STATE LINE TO MURRAY PRIORITY SECTION 2; FROM TENN. STATE LINE TO CLARKS RIVER BRIDGE.(SEE 1-8852.00) | R |  | NH | 2019 | 2000000 | 2000000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.09 | 2019-06-26 | UPDATE DESCRIPTION AND FUNDING. INDOT HAS COMMITED TO FUNDING DESIGN AND RIGHT OF WAY FUNDING IN FY 2019 & FY 2020. FUNDING FOR THE UTILITY PHASE AND THE CONSTRUCTION PHASE FOR THE SECTION OF THE PROJECT IN TENNESSEE NOT SCHEDULED UNTIL BEYOND FY 2020; MOD |  |  | CALLOWAY | 1-314.2 | US 641 | 5.7 | 0 | 5.666 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE US-641 FROM THE TENNESSEE STATE LINE TO MURRAY PRIORITY SECTION 2; FROM HOWARD ROAD, JUST NORTH OF PURYEAR TENNESSEE, TO CLARKS RIVER BRIDGE SOUTH OF MURRAY KENTUCKY. | R |  | NH | 2019 | 6700000 | 1700000 |  |  | 3800000 | [5 empty] | 0
STIP | [9 empty] | CALLOWAY | 1-314.2 | US 641 | 5.7 | 0 | 5.666 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE US-641 FROM THE TENNESSEE STATE LINE TO MURRAY PRIORITY SECTION 2; FROM TENN. STATE LINE TO CLARKS RIVER BRIDGE.(SEE 1-8852.00) | U |  | NH | 2019 | 3000000 | 3000000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.09 | 2019-06-26 | UPDATE DESCRIPTION AND FUNDING. INDOT HAS COMMITED TO FUNDING DESIGN AND RIGHT OF WAY FUNDING IN FY 2019 & FY 2020. FUNDING FOR THE UTILITY PHASE AND THE CONSTRUCTION PHASE FOR THE SECTION OF THE PROJECT IN TENNESSEE NOT SCHEDULED UNTIL BEYOND FY 2020; MOD |  |  | CALLOWAY | 1-314.2 | US 641 | 5.7 | 0 | 5.666 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE US-641 FROM THE TENNESSEE STATE LINE TO MURRAY PRIORITY SECTION 2; FROM HOWARD ROAD, JUST NORTH OF PURYEAR TENNESSEE, TO CLARKS RIVER BRIDGE SOUTH OF MURRAY KENTUCKY. | U |  | NH | 2020 | 6000000 | 2300000 |  |  | 2100000 | [5 empty] | 0
STIP | [9 empty] | CALLOWAY | 1-314.2 | US 641 | 5.7 | 0 | 5.666 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE US-641 FROM THE TENNESSEE STATE LINE TO MURRAY PRIORITY SECTION 2; FROM TENN. STATE LINE TO CLARKS RIVER BRIDGE.(SEE 1-8852.00) | C |  | NH | 2021 | 15000000 | 12000000 |  |  | 3000000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.09 | 2019-06-26 | UPDATE DESCRIPTION AND FUNDING. INDOT HAS COMMITED TO FUNDING DESIGN AND RIGHT OF WAY FUNDING IN FY 2019 & FY 2020. FUNDING FOR THE UTILITY PHASE AND THE CONSTRUCTION PHASE FOR THE SECTION OF THE PROJECT IN TENNESSEE NOT SCHEDULED UNTIL BEYOND FY 2020; MOD |  |  | CALLOWAY | 1-314.2 | US 641 | 5.7 | 0 | 5.666 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE US-641 FROM THE TENNESSEE STATE LINE TO MURRAY PRIORITY SECTION 2; FROM HOWARD ROAD, JUST NORTH OF PURYEAR TENNESSEE, TO CLARKS RIVER BRIDGE SOUTH OF MURRAY KENTUCKY. | C |  | NH | 2020 | 64300000 | 12100000 |  |  | 9200000 | 1000000 |  |  |  |  | 0
STIP | [9 empty] | CALLOWAY | 1-314.21 | US 641 | 5.7 | 0 | 5.666 | RELIABILITY | PREFINANCD CONVRSN(O) | IMPROVE US-641 FROM THE TENNESSEE STATE LINE TO MURRAY PRIORITY SECTION 2; FROM TENN. STATE LINE TO CLARKS RIVER BRIDGE.(SEE 1-8852.00) | C |  | NH | 2022 | 10000000 | 8000000 |  |  | 2000000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.306 | 2021-06-16 | ADD D PHASE TO STIP; NEW |  |  | CALLOWAY | 1-8952 | KY 748 |  | 0 | 0.307 | RELIABILITY | SAFETY (P) | IMPROVE N 16TH STREET FROM KY 1327 (5 POINTS) TO KY 121 (2020CCN) | D |  | SPP | 2021 | 420100 | 100 |  |  | 420000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.015 | 2019-01-25 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 9010346 | CALLOWAY, MCCRACKEN, MARSHALL | 1-9012 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | PRELIMINARY DESIGN AND STUDY TO DETERMINE LOW COST IMPROVEMENTS AT VARIOUS INTERSECTIONS WITHIN DISTRICT 1. (2018BOP) | D |  | SAF | 2019 | 200000 | 200000 |  |  | 0 |  |  | OBLIGATED | 200000 |  | 200000 | 2019 | 2ND QUARTER
STIP | [9 empty] | CALLOWAY | 1-10008 | KY 280 |  | 11.015 | 11.027 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 280 BRIDGE OVER PANTHER CREEK. (018B00054N) | D |  | BR/STP | 2019 | 140000 | 86800 |  |  | 53200 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030153 | CALLOWAY | 1-10008 | KY 280 |  | 11.015 | 11.027 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 280 BRIDGE OVER PANTHER CREEK. (018B00054N) | C |  | BR/STP | 2020 | 735000 | 455700 |  |  | 279300 |  |  | OBLIGATED |  | 620065 | 620065 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.075 | 2019-05-28 | ADD PROJECT TO STIP; NEW | STPBRZ | 9030130 | CALLOWAY | 1-10016 | CR 1415 |  | 0.403 |  | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES ON SPRING RD (CR 1415) OVER W.FK ROCKHOUSE CREEK. (018C00111N) | C |  | STP | 2020 | 475000 | 475000 |  |  | 0 |  |  | OBLIGATED |  | 448970 | 448970 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.123 | 2019-09-06 | ADD PROJECT TO STIP; PARENT NO. 99-65.16 AND 99-65.17; NEW | STPBRZ | 9030175 | CALLOWAY | 1-10022 | CR 1199 |  | 1.574 | 1.58 | ASSET MANAGEMENT | AM-BRIDGE (P) | STATELINE ROAD E OVER BULLFROG BR-MCCULLOUGH F (018C00035N) | C |  | BR | 2020 | 250000 | 250000 |  |  | 0 |  |  | OBLIGATED |  | 307219 | 307219 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.123 | 2019-09-06 | ADD PROJECT TO STIP; PARENT NO. 99-65.16 AND 99-65.17; NEW | STPBRZ | 9030176 | CALLOWAY | 1-10023 | CR 1428 |  | 0.663 | 0.671 | ASSET MANAGEMENT | AM-BRIDGE (P) | HICKORY GROVE CHUR OVER WADES CREEK (018C00121N) | C |  | BR | 2020 | 385000 | 385000 |  |  | 0 |  |  | OBLIGATED |  | 337599 | 337599 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.123 | 2019-09-06 | ADD PROJECT TO STIP; PARENT NO. 99-65.16 AND 99-65.17; NEW |  | 9030174 | CALLOWAY | 1-10024 | CR 1183 |  | 0.081 | 0.087 | ASSET MANAGEMENT | AM-BRIDGE (P) | BEECHY RD OVER BEECHY FORK (018C00123N) | C |  | BR | 2020 | 256000 | 256000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.123 | 2019-09-06 | ADD PROJECT TO STIP; PARENT NO. 99-65.16 AND 99-65.17; NEW | STPBRZ | 9030178 | CALLOWAY | 1-10025 | CR 1439 |  | 0.81 | 0.818 | ASSET MANAGEMENT | AM-BRIDGE (P) | KELLY ROAD OVER WADES CREEK (018C00142N). | C |  | BR | 2020 | 262000 | 262000 |  |  | 0 |  |  | OBLIGATED |  | 338451 | 338451 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.123 | 2019-09-06 | ADD PROJECT TO STIP; PARENT NO. 99-65.16 AND 99-65.17; NEW | STPBRZ | 9030179 | CALLOWAY | 1-10026 | CR 1366 |  | 1.329 | 1.335 | ASSET MANAGEMENT | AM-BRIDGE (P) | WATSON ROAD OVER MAYFIELD CREEK (018C00155N) | C |  | BR | 2020 | 271000 | 271000 |  |  | 0 |  |  | OBLIGATED |  | 294703 | 294703 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.123 | 2019-09-06 | ADD PROJECT TO STIP; PARENT NO. 99-65.16 AND 99-65.17; NEW | STPBRZ | 9030174 | CALLOWAY | 1-10031 | CR 1197 |  | 5.593 | 5.597 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES ON CR-1197 BRIDGE OVER BRANCH OF BLOOD RIVER.(018C00033N) | C |  | BR | 2020 | 193000 | 193000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | CALLOWAY | 1-20001 | KY 1327 |  | 0 | 2.035 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT. | D |  | PM/STP | 2019 | 175000 | 140000 |  |  | 35000 | [5 empty] | 0
STIP | [9 empty] | CALLOWAY | 1-20001 | KY 1327 |  | 0 | 2.035 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT. | C |  | PM/STP | 2019 | 1750000 | 1400000 |  |  | 350000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; ADD PROJECT TO STIP; NEW |  |  | CAMPBELL | 6-81 | I 471 |  | 0 | 5.016 | RELIABILITY | MAJOR WIDENING(O) | REDUCE CONGESTION ALONG THE I-471 CORRIDOR FROM US-27 TO OHIO STATE LINE. | P |  | NH | 2024 | 1500000 | 1200000 |  |  | 300000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.287 | 2021-03-12 | TIP FY 21-24, AMEND#4; ADD D PHASE TO STIP; NEW |  |  | CAMPBELL | 6-124 | Riverfront Commons Trail at Newport Festival Park |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | Riverfront Commons Trail at Newport Festival Park. Construction of a new multi-use path portion of 11.5 mile Regional Riverfront Commons Bicycle/Pedestrian Trail between Taylor Southgate Bridge and Purple People Bridge in Newport. | D |  | SNK | 2023 | 12500 | 10000 |  |  | 2500 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.287 | 2021-03-12 | TIP FY 21-24, AMEND#4; ADD C PHASE TO STIP; NEW |  |  | CAMPBELL | 6-124 | Riverfront Commons Trail at Newport Festival Park |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | Riverfront Commons Trail at Newport Festival Park. Construction of a new multi-use path portion of 11.5 mile Regional Riverfront Commons Bicycle/Pedestrian Trail between Taylor Southgate Bridge and Purple People Bridge in Newport. | C |  | SNK | 2024 | 3023035 | 2418428 |  |  |  | 604607 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.287 | 2021-03-12 | TIP FY 21-24, AMEND#4; ADD D PHASE TO STIP; NEW |  |  | CAMPBELL | 6-127 | Bellevue Riverfront Commons |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | Bellevue Riverfront Commons. Construction of a new multi-use path 1200' between Patchen Drive and Lafayette. Portion of 11.5 mile Regional Riverfront Commons Bicycle/Pedestrian Trail. | D |  | SNK | 2022 | 172500 | 138000 |  |  | 2500 | 32000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.287 | 2021-03-12 | TIP FY 21-24, AMEND#4; ADD C PHASE TO STIP; NEW |  |  | CAMPBELL | 6-127 | Bellevue Riverfront Commons |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | Bellevue Riverfront Commons. Construction of a new multi-use path 1200' between Patchen Drive and Lafayette. Portion of 11.5 mile Regional Riverfront Commons Bicycle/Pedestrian Trail. | C |  | SNK | 2023 | 777500 | 622000 |  |  |  | 155500 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.287 | 2021-03-12 | TIP FY 21-24, AMEND#4; ADD D PHASE TO STIP; NEW |  |  | CAMPBELL | 6-128 | CS 2032 |  | 0 | 0.876 | RELIABILITY | MATCHED FED FUNDS(O) | Resurfacing and partial sidewalk replacement on Berry Avenue, Taylor Avenue, Bonnie Leslie Avenue and Wilson Road Boulevard in Bellevue | D |  | SNK | 2023 | 21250 | 17000 |  |  | 1250 | 3000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.287 | 2021-03-12 | TIP FY 21-24, AMEND#4; ADD C PHASE TO STIP; NEW |  |  | CAMPBELL | 6-128 | CS 2032 |  | 0 | 0.876 | RELIABILITY | MATCHED FED FUNDS(O) | Resurfacing and partial sidewalk replacement on Berry Avenue, Taylor Avenue, Bonnie Leslie Avenue and Wilson Road Boulevard in Bellevue | C |  | SNK | 2024 | 248750 | 199000 |  |  |  | 49750 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.287 | 2021-03-12 | TIP FY 21-24, AMEND#4; ADD D PHASE TO STIP; NEW |  |  | CAMPBELL | 6-177 | KY 2238 |  | 0 | 2.442 | RELIABILITY | MATCHED FED FUNDS(O) | Construct new sidewalk with curb, gutter and storm inlets on 3 Mile Road between existing roundabouts at Nunn Drive and Norse Blvd. | D |  | SNK | 2022 | 127500 | 102000 |  |  | 2500 | 23000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.287 | 2021-03-12 | TIP FY 21-24, AMEND#4; ADD C PHASE TO STIP; NEW |  |  | CAMPBELL | 6-177 | KY 2238 |  | 0 | 2.442 | RELIABILITY | MATCHED FED FUNDS(O) | Construct new sidewalk with curb, gutter and storm inlets on 3 Mile Road between existing roundabouts at Nunn Drive and Norse Blvd. | C |  | SNK | 2024 | 737500 | 590000 |  |  |  | 147500 |  |  |  |  | 0
STIP |  | No | [7 empty] | CAMPBELL | 6-183 | I 471 | 5.016 | 0 | 5.016 | RELIABILITY | RECONSTRUCTION(O) | STUDY AND REHABILITATE THE I-471 CORRIDOR, CAMPBELL COUNTY, KENTUCKY. (SEE ALSO 6-8104.00)(2005HPP-KY120) | C |  | HPP | 2019 | 1439840 | 1439840 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24; ADMIN MOD#3; ADD R PHASE TO STIP; NEW |  |  | CAMPBELL | 6-427 | KY 1892 | 0.173 | 2.395 | 2.568 | RELIABILITY | MATCHED FED FUNDS(O) | ROADWAY REHABILITATION ON CAROTHERS ROAD FROM MONMOUTH STREET (US 27) TO RIGHT TURN LANE INTO NEWPORT SHOPPING CENTER. | R |  | SNK | 2021 | 32500 | 26000 |  |  |  | 6500 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24; ADMIN MOD#3; ADD U PHASE TO STIP; NEW |  |  | CAMPBELL | 6-427 | KY 1892 | 0.173 | 2.395 | 2.568 | RELIABILITY | MATCHED FED FUNDS(O) | ROADWAY REHABILITATION ON CAROTHERS ROAD FROM MONMOUTH STREET (US 27) TO RIGHT TURN LANE INTO NEWPORT SHOPPING CENTER. | U |  | SNK | 2021 | 17000 | 13600 |  |  |  | 3400 |  |  |  |  | 0
STIP | YES | No | [7 empty] | CAMPBELL | 6-427 | KY 1892 | 0.173 | 2.395 | 2.568 | RELIABILITY | MATCHED FED FUNDS(O) | ROADWAY REHABILITATION ON CAROTHERS ROAD FROM MONMOUTH STREET (US 27) TO RIGHT TURN LANE INTO NEWPORT SHOPPING CENTER. | C |  | SNK | 2019 | 1005052 | 804041.6 |  |  |  | 201010.4 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.149 | 2019-11-15 | TIP FY 20-23; ADMIN MOD#4; UPDATE FUND AMOUNTS & FISCAL YEAR FROM 2019 TO 2020; MOD |  |  | CAMPBELL | 6-427 | KY 1892 | 0.173 | 2.395 | 2.568 | RELIABILITY | MATCHED FED FUNDS(O) | ROADWAY REHABILITATION ON CAROTHERS ROAD FROM MONMOUTH STREET (US 27) TO RIGHT TURN LANE INTO NEWPORT SHOPPING CENTER. | C |  | SNK | 2020 | 1256315 | 1005052 |  |  |  | 251263 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24; ADMIN MOD#3; UPDATE FISCAL YEAR AND FUND AMOUNTS; MOD |  |  | CAMPBELL | 6-427 | KY 1892 | 0.173 | 2.395 | 2.568 | RELIABILITY | MATCHED FED FUNDS(O) | ROADWAY REHABILITATION ON CAROTHERS ROAD FROM MONMOUTH STREET (US 27) TO RIGHT TURN LANE INTO NEWPORT SHOPPING CENTER. | C |  | SNK | 2021 | 1220146 | 976117 |  |  |  | 244029 |  |  |  |  | 0
STIP | YES | No | [5 empty] | STPM | 3002295 | CAMPBELL | 6-434 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | NEWPORT RIVERFRONT COMMONS - CONSTRUCT TWO NEW PEDESTRIAN/BICYCLE BRIDGES TO CONNECT BOTH SIDES OF THE TAYLOR SOUTHGATE BRIDGE TO THE TRAILS ON TOP OF THE LEVEE (2016BOP) | C |  | SNK | 2019 | 1097427 | 877941.6 |  |  |  | 219485.4 |  | OBLIGATED | 1097427 |  | 1097427 | 2019 | 4TH QUARTER | CITY OF NEWPORT
STIP | YES | No | [7 empty] | CAMPBELL | 6-443 | US 27 |  | 16.333 | 16.507 | RELIABILITY | MATCHED FED FUNDS(O) | ADD LANE ON US 27 TO PROVIDE THREE CONTINUOUS SOUTHBOUND THROUGH-LANES FROM MARSHALL LANE TO JOHNS HILL ROAD (KY 3490). (2016BOP) | R |  | SNK | 2019 | 200000 | 160000 |  |  |  | 40000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.149 | 2019-11-15 | TIP FY 20-23; ADMIN MOD#4; UPDATE FUNDS AMOUNTS & FISCAL YEAR FROM 2019 TO 2020; MOD | STPM | 0272114 | CAMPBELL | 6-443 | US 27 |  | 16.333 | 16.507 | RELIABILITY | MATCHED FED FUNDS(O) | ADD LANE ON US 27 TO PROVIDE THREE CONTINUOUS SOUTHBOUND THROUGH-LANES FROM MARSHALL LANE TO JOHNS HILL ROAD (KY 3490). (2016BOP) | R |  | SNK | 2020 | 200000 | 200000 | [5 empty] | OBLIGATED | 204600 |  | 204600 | 2020 | 2ND QUARTER
STIP | YES | No | [7 empty] | CAMPBELL | 6-443 | US 27 |  | 16.333 | 16.507 | RELIABILITY | MATCHED FED FUNDS(O) | ADD LANE ON US 27 TO PROVIDE THREE CONTINUOUS SOUTHBOUND THROUGH-LANES FROM MARSHALL LANE TO JOHNS HILL ROAD (KY 3490). (2016BOP) | U |  | SNK | 2019 | 100000 | 80000 |  |  |  | 20000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.149 | 2019-11-15 | TIP FY 20-23; ADMIN MOD#4; UPDATE FUNDS AMOUNTS & FISCAL YEAR FROM 2019 TO 2020; MOD |  |  | CAMPBELL | 6-443 | US 27 |  | 16.333 | 16.507 | RELIABILITY | MATCHED FED FUNDS(O) | ADD LANE ON US 27 TO PROVIDE THREE CONTINUOUS SOUTHBOUND THROUGH-LANES FROM MARSHALL LANE TO JOHNS HILL ROAD (KY 3490). (2016BOP) | U |  | SNK | 2020 | 100000 | 100000 | [8 empty] | 0
STIP | YES | No | [7 empty] | CAMPBELL | 6-443 | US 27 |  | 16.333 | 16.507 | RELIABILITY | MATCHED FED FUNDS(O) | ADD LANE ON US 27 TO PROVIDE THREE CONTINUOUS SOUTHBOUND THROUGH-LANES FROM MARSHALL LANE TO JOHNS HILL ROAD (KY 3490). (2016BOP) | C |  | SNK | 2019 | 500000 | 400000 |  |  |  | 100000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.149 | 2019-11-15 | TIP FY 20-23; ADMIN MOD#4; UPDATE FUNDS AMOUNTS & FISCAL YEAR FROM 2019 TO 2020; MOD |  |  | CAMPBELL | 6-443 | US 27 |  | 16.333 | 16.507 | RELIABILITY | MATCHED FED FUNDS(O) | ADD LANE ON US 27 TO PROVIDE THREE CONTINUOUS SOUTHBOUND THROUGH-LANES FROM MARSHALL LANE TO JOHNS HILL ROAD (KY 3490). (2016BOP) | C |  | SNK | 2020 | 500000 | 500000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.174 | 2020-03-17 | TIP FY 20-23; ADMIN MOD#7; UPDATE FUND AMOUNT; MOD |  |  | CAMPBELL | 6-443 | US 27 |  | 16.333 | 16.507 | RELIABILITY | MATCHED FED FUNDS(O) | ADD LANE ON US 27 TO PROVIDE THREE CONTINUOUS SOUTHBOUND THROUGH-LANES FROM MARSHALL LANE TO JOHNS HILL ROAD (KY 3490). (2016BOP) | C |  | SNK | 2020 | 600000 | 600000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; UPDATE FISCAL YEAR; MOD |  |  | CAMPBELL | 6-443 | US 27 |  | 16.333 | 16.507 | RELIABILITY | MATCHED FED FUNDS(O) | ADD LANE ON US 27 TO PROVIDE THREE CONTINUOUS SOUTHBOUND THROUGH-LANES FROM MARSHALL LANE TO JOHNS HILL ROAD (KY 3490). (2016BOP) | C |  | SNK | 2021 | 600000 | 600000 | [8 empty] | 0
STIP | YES | No | [7 empty] | CAMPBELL | 6-448 | KY 9 |  | 17.525 | 17.978 | RELIABILITY | CONGESTION MITIGTN(O) | IMPROVE SAFETY AND REDUCE CONGESTION AT THE I-275 INTERCHANGE WITH KY-9 (AA HWY.) | P |  | NH | 2021 | 700000 | 560000 |  |  | 140000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; UPDATE FISCAL YEAR; MOD |  |  | CAMPBELL | 6-448 | KY 9 |  | 17.525 | 17.978 | RELIABILITY | CONGESTION MITIGTN(O) | IMPROVE SAFETY AND REDUCE CONGESTION AT THE I-275 INTERCHANGE WITH KY-9 (AA HWY.) | P |  | NH | 2022 | 700000 | 560000 |  |  | 140000 | [5 empty] | 0
STIP | YES | No | [7 empty] | CAMPBELL | 6-451 | US 27 |  | 20.623 | 21.209 | RELIABILITY | BIKE/PED FACIL(O) | SOUTH MONMOUTH PHASE 1. IMPROVE/ADD SIDEWALKS, ACCESS MANAGEMENT, STREET LIGHTING, IMPROVE SAFETY FROM NEWPORT/SOUTHGATE CITY LIMITS TO CAROTHERS ROAD. | D |  | SNK | 2019 | 454960 | 363968 |  |  |  | 90992 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.028 | 2019-02-18 | TIP FY 18-21; ADMIN MOD#15; COMBINE PHASE 1 & PHASE 2 (FORMERLY ITEM# 6-452) OF THIS PROJECT; UPDATED FUND AMOUNTS; MOD | STPM | 6-451 | CAMPBELL | 6-451 | US 27 |  | 20.623 | 21.209 | RELIABILITY | BIKE/PED FACIL(O) | SOUTH MONMOUTH PHASE 1. IMPROVE/ADD SIDEWALKS, ACCESS MANAGEMENT, STREET LIGHTING, IMPROVE SAFETY FROM NEWPORT/SOUTHGATE CITY LIMITS TO CAROTHERS ROAD. | D |  | SNK | 2019 | 1041700 | 833360 |  |  |  | 208340 |  | OBLIGATED | 426400 |  | 426400 | 2019 | 4TH QUARTER | CITY OF NEWPORT
STIP | YES | No | [7 empty] | CAMPBELL | 6-451 | US 27 |  | 20.623 | 21.209 | RELIABILITY | BIKE/PED FACIL(O) | SOUTH MONMOUTH PHASE 1. IMPROVE/ADD SIDEWALKS, ACCESS MANAGEMENT, STREET LIGHTING, IMPROVE SAFETY FROM NEWPORT/SOUTHGATE CITY LIMITS TO CAROTHERS ROAD. | R |  | SNK | 2019 | 61600 | 49280 |  |  |  | 12320 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.028 | 2019-02-18 | TIP FY 18-21; ADMIN MOD#15; COMBINE PHASE 1 & PHASE 2 (FORMERLY ITEM# 6-452) OF THIS PROJECT; UPDATED FUND AMOUNTS; MOD |  |  | CAMPBELL | 6-451 | US 27 |  | 20.623 | 21.209 | RELIABILITY | BIKE/PED FACIL(O) | SOUTH MONMOUTH PHASE 1. IMPROVE/ADD SIDEWALKS, ACCESS MANAGEMENT, STREET LIGHTING, IMPROVE SAFETY FROM NEWPORT/SOUTHGATE CITY LIMITS TO CAROTHERS ROAD. | R |  | SNK | 2020 | 117000 | 93600 |  |  |  | 23400 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.178 | 2020-04-14 | TIP FY 18-21, ADMIN MOD#8; UPDATE PROJECT DESCRIPTION; MOD |  |  | CAMPBELL | 6-451 | US 27 |  | 20.623 | 21.209 | RELIABILITY | BIKE/PED FACIL(O) | SOUTH MONMOUTH PHASE 1 & 2. IMPROVE/ADD SIDEWALKS, ACCESS MANAGEMENT, STREET LIGHTING, IMPROVE SAFETY, REPLACE OBSOLETE STAIRS/WALKWAY AT UNDERPASS WITH SIDEWALK, LIGHTING BUS STOPS. | R |  | SNK | 2020 | 117000 | 93600 |  |  |  | 23400 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; UPDATE FISCAL YEAR; MOD |  |  | CAMPBELL | 6-451 | US 27 |  | 20.623 | 21.209 | RELIABILITY | BIKE/PED FACIL(O) | SOUTH MONMOUTH PHASE 1 & 2. IMPROVE/ADD SIDEWALKS, ACCESS MANAGEMENT, STREET LIGHTING, IMPROVE SAFETY, REPLACE OBSOLETE STAIRS/WALKWAY AT UNDERPASS WITH SIDEWALK, LIGHTING BUS STOPS. | R |  | SNK | 2021 | 117000 | 93600 |  |  |  | 23400 |  |  |  |  | 0
STIP | YES | No | [7 empty] | CAMPBELL | 6-451 | US 27 |  | 20.623 | 21.209 | RELIABILITY | BIKE/PED FACIL(O) | SOUTH MONMOUTH PHASE 1. IMPROVE/ADD SIDEWALKS, ACCESS MANAGEMENT, STREET LIGHTING, IMPROVE SAFETY FROM NEWPORT/SOUTHGATE CITY LIMITS TO CAROTHERS ROAD. | U |  | SNK | 2019 | 1496000 | 1196800 |  |  |  | 299200 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.028 | 2019-02-18 | TIP FY 18-21; ADMIN MOD#15; COMBINE PHASE 1 & PHASE 2 (FORMERLY ITEM# 6-452) OF THIS PROJECT; UPDATED FUND AMOUNTS; MOD |  |  | CAMPBELL | 6-451 | US 27 |  | 20.623 | 21.209 | RELIABILITY | BIKE/PED FACIL(O) | SOUTH MONMOUTH PHASE 1. IMPROVE/ADD SIDEWALKS, ACCESS MANAGEMENT, STREET LIGHTING, IMPROVE SAFETY FROM NEWPORT/SOUTHGATE CITY LIMITS TO CAROTHERS ROAD. | U |  | SNK | 2020 | 1900000 | 1520000 |  |  |  | 380000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.178 | 2020-04-14 | TIP FY 18-21, ADMIN MOD#8; UPDATE PROJECT DESCRIPTION; MOD |  |  | CAMPBELL | 6-451 | US 27 |  | 20.623 | 21.209 | RELIABILITY | BIKE/PED FACIL(O) | SOUTH MONMOUTH PHASE 1 & 2. IMPROVE/ADD SIDEWALKS, ACCESS MANAGEMENT, STREET LIGHTING, IMPROVE SAFETY, REPLACE OBSOLETE STAIRS/WALKWAY AT UNDERPASS WITH SIDEWALK, LIGHTING BUS STOPS. | U |  | SNK | 2020 | 1900000 | 1520000 |  |  |  | 380000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; UPDATE FISCAL YEAR; MOD |  |  | CAMPBELL | 6-451 | US 27 |  | 20.623 | 21.209 | RELIABILITY | BIKE/PED FACIL(O) | SOUTH MONMOUTH PHASE 1 & 2. IMPROVE/ADD SIDEWALKS, ACCESS MANAGEMENT, STREET LIGHTING, IMPROVE SAFETY, REPLACE OBSOLETE STAIRS/WALKWAY AT UNDERPASS WITH SIDEWALK, LIGHTING BUS STOPS. | U |  | SNK | 2021 | 1900000 | 1520000 |  |  |  | 380000 |  |  |  |  | 0
STIP | YES | No | [7 empty] | CAMPBELL | 6-451 | US 27 |  | 20.623 | 21.209 | RELIABILITY | BIKE/PED FACIL(O) | SOUTH MONMOUTH PHASE 1. IMPROVE/ADD SIDEWALKS, ACCESS MANAGEMENT, STREET LIGHTING, IMPROVE SAFETY FROM NEWPORT/SOUTHGATE CITY LIMITS TO CAROTHERS ROAD. | C |  | SNK | 2020 | 1200000 | 960000 |  |  |  | 240000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.028 | 2019-02-18 | TIP FY 18-21; ADMIN MOD#15; COMBINE PHASE 1 & PHASE 2 (FORMERLY ITEM# 6-452) OF THIS PROJECT; UPDATED FUND AMOUNTS; MOD |  |  | CAMPBELL | 6-451 | US 27 |  | 20.623 | 21.209 | RELIABILITY | BIKE/PED FACIL(O) | SOUTH MONMOUTH PHASE 1. IMPROVE/ADD SIDEWALKS, ACCESS MANAGEMENT, STREET LIGHTING, IMPROVE SAFETY FROM NEWPORT/SOUTHGATE CITY LIMITS TO CAROTHERS ROAD. | C |  | SNK | 2021 | 4800000 | 3840000 |  |  |  | 960000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.178 | 2020-04-14 | TIP FY 18-21, ADMIN MOD#8; UPDATE PROJECT DESCRIPTION; MOD |  |  | CAMPBELL | 6-451 | US 27 |  | 20.623 | 21.209 | RELIABILITY | BIKE/PED FACIL(O) | SOUTH MONMOUTH PHASE 1 & 2. IMPROVE/ADD SIDEWALKS, ACCESS MANAGEMENT, STREET LIGHTING, IMPROVE SAFETY, REPLACE OBSOLETE STAIRS/WALKWAY AT UNDERPASS WITH SIDEWALK, LIGHTING BUS STOPS. | C |  | SNK | 2021 | 4800000 | 3840000 |  |  |  | 960000 |  |  |  |  | 0
STIP | YES | No | [7 empty] | CAMPBELL | 6-452 | US 27 |  | 21.32 | 21.463 | RELIABILITY | BIKE/PED FACIL(O) | US 27 SOUTH MONMOUTH UNDERPASS. IMPROVE FOR PEDESTRIANS BY REPLACING OBSOLETE STAIRS/WALKWAY WITH 10' SIDEWALK, LIGHTING BUS STOPS AT THE UNDERPASS OF THE CSX RAILROAD BRIDGE BETWEEN 11TH STREET AND 13TH STREET. | D |  | SNK | 2020 | 378400 | 302720 |  |  |  | 75680 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.028 | 2019-02-18 | TIP FY 18-21; ADMIN MOD#15; COMBINE PHASE 1 & PHASE 2 (FORMERLY ITEM# 6-452) OF THIS PROJECT; MOD |  |  | CAMPBELL | 6-451 | US 27 |  | 20.623 | 21.209 | RELIABILITY | BIKE/PED FACIL(O) | SOUTH MONMOUTH PHASE 1. IMPROVE/ADD SIDEWALKS, ACCESS MANAGEMENT, STREET LIGHTING, IMPROVE SAFETY FROM NEWPORT/SOUTHGATE CITY LIMITS TO CAROTHERS ROAD. | D | [13 empty] | 0
STIP | YES | No | [7 empty] | CAMPBELL | 6-452 | US 27 |  | 21.32 | 21.463 | RELIABILITY | BIKE/PED FACIL(O) | US 27 SOUTH MONMOUTH UNDERPASS. IMPROVE FOR PEDESTRIANS BY REPLACING OBSOLETE STAIRS/WALKWAY WITH 10' SIDEWALK, LIGHTING BUS STOPS AT THE UNDERPASS OF THE CSX RAILROAD BRIDGE BETWEEN 11TH STREET AND 13TH STREET. | R |  | SNK | 2020 | 32000 | 25600 |  |  |  | 6400 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.028 | 2019-02-18 | TIP FY 18-21; ADMIN MOD#15; COMBINE PHASE 1 & PHASE 2 (FORMERLY ITEM# 6-452) OF THIS PROJECT; MOD |  |  | CAMPBELL | 6-451 | US 27 |  | 20.623 | 21.209 | RELIABILITY | BIKE/PED FACIL(O) | SOUTH MONMOUTH PHASE 1. IMPROVE/ADD SIDEWALKS, ACCESS MANAGEMENT, STREET LIGHTING, IMPROVE SAFETY FROM NEWPORT/SOUTHGATE CITY LIMITS TO CAROTHERS ROAD. | R | [13 empty] | 0
STIP | YES | No | [7 empty] | CAMPBELL | 6-452 | US 27 |  | 21.32 | 21.463 | RELIABILITY | BIKE/PED FACIL(O) | US 27 SOUTH MONMOUTH UNDERPASS. IMPROVE FOR PEDESTRIANS BY REPLACING OBSOLETE STAIRS/WALKWAY WITH 10' SIDEWALK, LIGHTING BUS STOPS AT THE UNDERPASS OF THE CSX RAILROAD BRIDGE BETWEEN 11TH STREET AND 13TH STREET. | U |  | SNK | 2020 | 24000 | 19200 |  |  |  | 4800 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.028 | 2019-02-18 | TIP FY 18-21; ADMIN MOD#15; COMBINE PHASE 1 & PHASE 2 (FORMERLY ITEM# 6-452) OF THIS PROJECT; MOD |  |  | CAMPBELL | 6-451 | US 27 |  | 20.623 | 21.209 | RELIABILITY | BIKE/PED FACIL(O) | SOUTH MONMOUTH PHASE 1. IMPROVE/ADD SIDEWALKS, ACCESS MANAGEMENT, STREET LIGHTING, IMPROVE SAFETY FROM NEWPORT/SOUTHGATE CITY LIMITS TO CAROTHERS ROAD. | U | [13 empty] | 0
STIP | YES | No | [7 empty] | CAMPBELL | 6-452 | US 27 |  | 21.32 | 21.463 | RELIABILITY | BIKE/PED FACIL(O) | US 27 SOUTH MONMOUTH UNDERPASS. IMPROVE FOR PEDESTRIANS BY REPLACING OBSOLETE STAIRS/WALKWAY WITH 10' SIDEWALK, LIGHTING BUS STOPS AT THE UNDERPASS OF THE CSX RAILROAD BRIDGE BETWEEN 11TH STREET AND 13TH STREET. | C |  | SNK | 2021 | 1320000 | 1056000 |  |  |  | 264000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.028 | 2019-02-18 | TIP FY 18-21; ADMIN MOD#15; COMBINE PHASE 1 & PHASE 2 (FORMERLY ITEM# 6-452) OF THIS PROJECT; MOD |  |  | CAMPBELL | 6-451 | US 27 |  | 20.623 | 21.209 | RELIABILITY | BIKE/PED FACIL(O) | SOUTH MONMOUTH PHASE 1. IMPROVE/ADD SIDEWALKS, ACCESS MANAGEMENT, STREET LIGHTING, IMPROVE SAFETY FROM NEWPORT/SOUTHGATE CITY LIMITS TO CAROTHERS ROAD. | C | [13 empty] | 0
STIP | YES | No | [5 empty] | STPM | 3002332 | CAMPBELL | 6-453 |  |  |  |  | RELIABILITY | BIKE/PED FACIL(O) | RIVERFRONT COMMONS. CONSTRUCT A 15' WIDE CONCRETE BICYCLE/PEDESTRIAN TRAIL AND CONDUIT FOR FUTURE LIGHTING FROM BERRY STREET TO FOURTH AVENUE. PART OF 11.5 MILE PROJECT. | D |  | SNK | 2019 | 126000 | 100800 |  |  |  | 25200 |  | OBLIGATED | 142000 |  | 142000 | 2019 | 2ND QUARTER | CITY OF DAYTON
STIP | YES | No | [7 empty] | CAMPBELL | 6-453 |  |  |  |  | RELIABILITY | BIKE/PED FACIL(O) | RIVERFRONT COMMONS. CONSTRUCT A 15' WIDE CONCRETE BICYCLE/PEDESTRIAN TRAIL AND CONDUIT FOR FUTURE LIGHTING FROM BERRY STREET TO FOURTH AVENUE. PART OF 11.5 MILE PROJECT. | C |  | SNK | 2020 | 760000 | 608000 |  |  |  | 152000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.295 | 2021-04-13 | TIP FY 21-24, ADMIN MOD#9; UPDATE PROJECT DESCRIPTION, FISCAL YEAR & FUND AMOUNTS; MOD |  |  | CAMPBELL | 6-453 |  |  |  |  | RELIABILITY | BIKE/PED FACIL(O) | 12' WIDE CONCRETE BICYCLE/PEDESTRIAN TRAIL AND CONDUIT FOR FUTURE LIGHTING. PART OF 11.5 MI PROJECT. | C |  | SNK | 2021 | 950000 | 760000 |  |  |  | 190000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.016 | 2019-01-15 | TIP FY 18-21, AMENDMENT#3, ADD PROJECT TO STIP; NEW | STPM | 3002334 | CAMPBELL | 6-460 |  |  |  |  | RELIABILITY | BIKE/PED FACIL(O) | IMPROVED ACCESS TO NEW DEVELOPMENT WITH NEW TURN LANE FROM SB US 27 TO NUNN DR, UPGRADE AND RECONSTRUCTION OF OLD SIDEWALKS, TRANSIT SUPER STOP AND NEW BIKE/PED PATH LINKING NKU CAMPUS. | D |  | SNK | 2019 | 77400 | 54180 | 54180 |  |  | 23220 |  | OBLIGATED | 60180 |  | 60180 | 2019 | 2ND QUARTER | CAMPBELL COUNTY
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.016 | 2019-01-15 | TIP FY 18-21, AMENDMENT#3, ADD PROJECT TO STIP; NEW |  |  | CAMPBELL | 6-460 |  |  |  |  | RELIABILITY | BIKE/PED FACIL(O) | IMPROVED ACCESS TO NEW DEVELOPMENT WITH NEW TURN LANE FROM SB US 27 TO NUNN DR, UPGRADE AND RECONSTRUCTION OF OLD SIDEWALKS, TRANSIT SUPER STOP AND NEW BIKE/PED PATH LINKING NKU CAMPUS. | R |  | SNK | 2021 | 279390 | 195573 | 195573 |  |  | 83817 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.016 | 2019-01-15 | TIP FY 18-21, AMENDMENT#3, ADD PROJECT TO STIP; NEW |  |  | CAMPBELL | 6-460 |  |  |  |  | RELIABILITY | BIKE/PED FACIL(O) | IMPROVED ACCESS TO NEW DEVELOPMENT WITH NEW TURN LANE FROM SB US 27 TO NUNN DR, UPGRADE AND RECONSTRUCTION OF OLD SIDEWALKS, TRANSIT SUPER STOP AND NEW BIKE/PED PATH LINKING NKU CAMPUS. | C |  | SNK | 2022 | 874216 | 611951 | 611951 |  |  | 262265 |  |  |  |  | 0
|  |  |  | AMENDMENT | 2018.003 | 2019-07-25 | TIP FY 20-23; ADD PROJECT TO STIP; NEW |  |  | CAMPBELL | 6-462 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | RIVERFRONT COMMONS: DAYTON EASTERN TRAIL (2018BOP) | D |  | SNK | 2020 | 104363 | 75630 |  |  | 10000 | 18733 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; UPDATE FISCAL YEAR; MOD |  |  | CAMPBELL | 6-462 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | RIVERFRONT COMMONS: DAYTON EASTERN TRAIL (2018BOP) | D |  | SNK | 2021 | 104363 | 75630 |  |  | 10000 | 18733 |  |  |  |  | 0
|  |  |  | AMENDMENT | 2018.003 | 2019-07-25 | TIP FY 20-23; ADD PROJECT TO STIP; NEW |  |  | CAMPBELL | 6-462 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | RIVERFRONT COMMONS: DAYTON EASTERN TRAIL (2018BOP) | U |  | SNK | 2021 | 50000 | 40000 |  |  |  | 10000 |  |  |  |  | 0
|  |  |  | AMENDMENT | 2018.003 | 2019-07-25 | TIP FY 20-23; ADD PROJECT TO STIP; NEW |  |  | CAMPBELL | 6-462 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | RIVERFRONT COMMONS: DAYTON EASTERN TRAIL (2018BOP) | C |  | SNK | 2022 | 856294 | 685035 |  |  |  | 171259 |  |  |  |  | 0
STIP |  | No | [7 empty] | CAMPBELL | 6-1085 | KY 8 | 0.054 | 18.017 | 18.071 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER TWELVEMILE CREEK ON KY 8 0.1 MI N OF NEISES ROAD (CR 1009). (019B00003N) | R |  | BR/STP | 2019 | 50000 | 31000 |  |  | 19000 | [5 empty] | 0
STIP |  | No | [7 empty] | CAMPBELL | 6-1085 | KY 8 | 0.054 | 18.017 | 18.071 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER TWELVEMILE CREEK ON KY 8 0.1 MI N OF NEISES ROAD (CR 1009). (019B00003N) | U |  | BR/STP | 2019 | 150000 | 93000 |  |  | 57000 | [5 empty] | 0
STIP |  | No | [7 empty] | CAMPBELL | 6-1085 | KY 8 | 0.054 | 18.017 | 18.071 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER TWELVEMILE CREEK ON KY 8 0.1 MI N OF NEISES ROAD (CR 1009). (019B00003N) | C |  | BR/STP | 2020 | 2500000 | 1550000 |  |  | 950000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.166 | 2020-02-20 | TIP FY 20-23; ADMIN MOD#6; ADD PROJECT TO STIP; NEW |  |  | CAMPBELL | 6-1085.1 | KY 8 |  |  |  | ASSET MANAGEMENT | AM-BRIDGE (P) | BRIDGE REPAIRS ON KY 8 OVER TWELVE MILE CREEK. (019B00003N)(2018BOP) | C |  | STP | 2020 | 1500000 | 1200000 |  |  | 300000 | [5 empty] | 0
STIP |  | No | [7 empty] | CAMPBELL | 6-1095 | CR 1363 |  | 0.045 | 0.051 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON COVERT RUN PIKE (CR-1363) (0.048) OVER TRIBUTARY TO TAYLOR CREEK. 019C00069N | D |  | BR/STP | 2019 | 122500 | 75950 |  |  | 46550 | [5 empty] | 0
STIP |  | No | [7 empty] | CAMPBELL | 6-1095 | CR 1363 |  | 0.045 | 0.051 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON COVERT RUN PIKE (CR-1363) (0.048) OVER TRIBUTARY TO TAYLOR CREEK. 019C00069N | C |  | BR/STP | 2020 | 630000 | 390600 |  |  | 239400 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; ADD PROJECT TO STIP; NEW |  |  | CAMPBELL | 6-4308 | KY 547 |  | 6.12 | 6.27 | SAFETY | SAF-GUARDRAIL(P) | INSTALL GUARDRAIL ON KY-547 IN CAMPBELL COUNTY | C |  | STBG | 2023 | 32000 | 25600 |  |  | 6400 | [5 empty] | 0
STIP | YES | No | [7 empty] | CAMPBELL | 6-8105.01 | I 275 |  |  |  | RELIABILITY | NEW ROUTE(O) | TRANSPORTATION IMPROVEMENTS TO AA-I-275 CONNECTOR, CAMPBELL COUNTY. (2005HPP-KY155)(SEE 6-8105.00 FOR "KYD" COMPONENT)(06CCR)(10CCR) | C |  | HPP | 2019 | 690401 | 690401 |  |  | 0 | [5 empty] | 0
STIP | YES | No | [7 empty] | CAMPBELL | 6-8105.03 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | CONSTRUCT NEW TECHNOLOGY TRIANGLE ACCESS ROAD, CAMPBELL COUNTY, KENTUCKY. (2005HPP-KY126)(2006BOPC).(10CCR) | C |  | HPP | 2019 | 1439840 | 1439840 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; ADD PROJECT TO STIP; NEW |  |  | CAMPBELL | 6-8105.06 | I 275 AA |  |  |  | RELIABILITY | RECONSTRUCTION(O) | TRANSPORTATION IMPROVEMENTS TO AA I 275; CONSTRUCT A NEW CONNECTOR RD FROM THE KY 9 TO THE END OF NEW CONSTRUCTION JUST SOUTH OF JOHN'S HILL RD (2020CCN) | D |  | STBG | 2022 | 1000000 | 800000 |  |  | 200000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.069 | 2019-05-13 | TIP FY 18-21; ADMIN MOD#18, ADD PROJECT TO STIP; NEW | HSIP | 5462030 | CAMPBELL | 6-9017.1 | KY 9 |  | 16.3 | 16.8 | SAFETY | SAFETY-HAZARD ELIM(P) | CONSTRUCT RIGHT TURN LANES ALONG KY 9, UPDATE THE SIGNING AND STRIPING, AND UPDATE THE TRAFFIC SIGNAL TO INCLUDE REFLECTIVE BACKPLATES, DOUBLE RED SIGNAL HEADS, AND SUPPLEMENTAL SIGNAL HEADS AT THE INTERSECTION OF KY 9 & GLORIA TERRELL RD (2018BOP) | C |  | SAF | 2019 | 320000 | 320000 |  |  | 0 |  |  | OBLIGATED | 102686 | 370000 | 472686 | 2019 | 3RD QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.069 | 2019-05-13 | TIP FY 18-21; ADMIN MOD#18, ADD PROJECT TO STIP; NEW | HSIP | 0272118 | CAMPBELL | 6-9017.3 | US 27 |  | 15.65 | 15.8 | SAFETY | SAFETY-HAZARD ELIM(P) | UPDATE THE TRAFFIC SIGNAL TO INCLUDE FLASHING YELLOW ARROW, REFLECTIVE BACKPLATES, DOUBLE RED SIGNAL HEADS, AND SUPPLEMENTAL SIGNAL HEADS, AND INSTALL MEDIAN ACCESS CONTROL NEAR THE INTERSECTION OF US 27 & KY 1998 (2018BOP) | C |  | SAF | 2019 | 75000 | 75000 |  |  | 0 |  |  | OBLIGATED |  | 80000 | 80000 | 2019 | 3RD QUARTER
STIP |  | No | [7 empty] | CAMPBELL | 6-10000 | KY 2238 |  | 1.682 | 1.69 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF GIBSON ROAD BRIDGE OVER THREEMILE CREEK. (019B00060N) | D |  | BR/STP | 2019 | 140000 | 86800 |  |  | 53200 | [5 empty] | 0
STIP |  | No | [5 empty] | STPBRZ | 9030152 | CAMPBELL | 6-10000 | KY 2238 |  | 1.682 | 1.69 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF GIBSON ROAD BRIDGE OVER THREEMILE CREEK. (019B00060N) | C |  | BR/STP | 2020 | 318500 | 197470 |  |  | 121030 |  |  | OBLIGATED |  | 1247610 | 1247610 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.106 | 2019-07-29 | TIP FY 20-23; AMENDMENT#1; UPDATE FUND AMOUNT; MOD |  |  | CAMPBELL | 6-10000 | KY 2238 |  | 1.682 | 1.69 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF GIBSON ROAD BRIDGE OVER THREEMILE CREEK. (019B00060N) | C |  | BR/STP | 2020 | 1480000 | 1184000 | 1184000 |  | 296000 | [5 empty] | 0
STIP |  | No | [7 empty] | CAMPBELL | 6-10007 | US 27 |  | 22.363 | 22.764 | ASSET MANAGEMENT | AM-BRIDGE (P) | SAFETY CABLE REPAIR AND PREVENTIVE MAINTENANCE ON TAYLOR SOUTHGATE BRIDGE OVER THE OHIO RIVER. JOINT PROJECT WITH OHIO. (019B00076N)(BSBP) | C |  | BR/NH | 2019 | 250000 | 155000 |  |  | 95000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; UPDATE FISCAL YEAR & FUND AMOUNT; MOD |  |  | CAMPBELL | 6-10007 | US 27 |  | 22.363 | 22.764 | ASSET MANAGEMENT | AM-BRIDGE (P) | SAFETY CABLE REPAIR AND PREVENTIVE MAINTENANCE ON TAYLOR SOUTHGATE BRIDGE OVER THE OHIO RIVER. JOINT PROJECT WITH OHIO. (019B00076N)(BSBP) | C |  | BR/NH | 2021 | 250000 | 200000 |  |  | 50000 | [5 empty] | 0
[8 empty] | STPBRZ | 9030096 | CAMPBELL | 6-10085 | KY 8 |  |  |  | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER TWELVEMILE CREEK ON KY 8 0.1 MI N OF NEISES ROAD (CR 1009). (019B00003N) | C |  | STP | 2019 | [7 empty] | OBLIGATED |  | 76555 | 76555 | 2019 | 3RD QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; ADD PROJECT TO STIP; NEW |  |  | CAMPBELL | 6-20011 | I 471 |  | 0 | 4.75 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-471 BOTH DIRECTION(S) FROM MILEPOINT 0 TO MILEPOINT 4.75 | D |  | NH | 2024 | 575000 | 460000 |  |  | 115000 | [5 empty] | 0
STIP | YES | Yes | OKI MPO requires the federal funding splits before proceeding to incorporate this project into the OKI TIP. Program Management just confirmed PM/STP federal funds for this project will use federal STP-State with an 80/20 -Fed/State split per Ivan - TMH 2/15/19. | [6 empty] | CAMPBELL | 6-20012 | KY 8 |  | 5.033 | 7.814 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT. | D |  | PM/STP | 2021 | 225000 | 180000 |  |  | 45000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; UPDATE FISCAL YEAR; MOD |  |  | CAMPBELL | 6-20012 | KY 6335 |  | 1.717 | 4.498 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT. | D |  | PM/STP | 2023 | 225000 | 180000 |  |  | 45000 | [5 empty] | 0
STIP | YES | Yes | OKI MPO requires the federal funding splits before proceeding to incorporate this project into the OKI TIP. Program Management just confirmed PM/STP federal funds for this project will use federal STP-State with an 80/20 -Fed/State split per Ivan - TMH 2/15/19. | [6 empty] | CAMPBELL | 6-20012 | KY 8 |  | 5.033 | 7.814 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT. | C |  | PM/STP | 2021 | 2250000 | 1800000 |  |  | 450000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; UPDATE FISCAL YEAR; MOD |  |  | CAMPBELL | 6-20012 | KY 6335 |  | 1.717 | 4.498 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT. | C |  | PM/STP | 2023 | 2250000 | 1800000 |  |  | 450000 | [5 empty] | 0
STIP | YES | No | [7 empty] | CAMPBELL | 6-20013 | KY 9 |  | 20.392 | 21.85 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT. | D |  | PM/STP | 2021 | 225000 | 180000 |  |  | 45000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; UPDATE FISCAL YEAR; MOD |  |  | CAMPBELL | 6-20013 | KY 9 |  | 20.392 | 21.85 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT. | D |  | PM/STP | 2024 | 225000 | 180000 |  |  | 45000 | [5 empty] | 0
STIP | YES | No | [7 empty] | CAMPBELL | 6-20013 | KY 9 |  | 20.392 | 21.85 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT. | C |  | PM/STP | 2021 | 2250000 | 1800000 |  |  | 450000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; UPDATE FUND AMOUNTS; MOD |  |  | CAMPBELL | 6-20013 | KY 9 |  | 20.392 | 21.85 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT. | C |  | PM/STP | FUTURE DATE | 2295000 | 2250000 |  |  | 45000 | [5 empty] | 0
STIP | YES | No | [7 empty] | CAMPBELL | 6-20014 | KY 1892 |  | 1.47 | 2.1 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | D |  | PM/STP | 2021 | 250000 | 200000 |  |  | 50000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; UPDATE FISCAL YEAR; MOD |  |  | CAMPBELL | 6-20014 | KY 1892 |  | 1.47 | 2.1 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | D |  | PM/STP | 2024 | 250000 | 200000 |  |  | 50000 | [5 empty] | 0
STIP | YES | No | [7 empty] | CAMPBELL | 6-20014 | KY 1892 |  | 1.47 | 2.1 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | C |  | PM/STP | 2021 | 2500000 | 2000000 |  |  | 500000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; UPDATE FUND AMOUNTS; MOD |  |  | CAMPBELL | 6-20014 | KY 1892 |  | 1.47 | 2.1 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | C |  | PM/STP | FUTURE DATE | 3125000 | 2500000 |  |  | 625000 | [5 empty] | 0
STIP | YES | No | [7 empty] | CAMPBELL | 6-20015 | US 27 |  | 16.748 | 18.6 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT | D |  | PM/STP | 2021 | 275000 | 220000 |  |  | 55000 | [5 empty] | 0
STIP | YES | No | [7 empty] | CAMPBELL | 6-20015 | US 27 |  | 16.748 | 18.6 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT | C |  | PM/STP | 2021 | 2750000 | 2200000 |  |  | 550000 | [5 empty] | 0
STIP | YES | No | [7 empty] | CAMPBELL | 6-20016 | US 27 |  | 19.4 | 19.85 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | D |  | PM/NH | 2019 | 75000 | 60000 |  |  | 15000 | [5 empty] | 0
STIP | YES | No | [7 empty] | CAMPBELL | 6-20016 | US 27 |  | 19.4 | 19.85 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | C |  | PM/NH | 2019 | 750000 | 600000 |  |  | 150000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.028 | 2019-02-18 | TIP FY 18-21; ADMIN MOD#15; ADJUST FUND AMOUNTS; MOD | NHPP | 0272117 | CAMPBELL | 6-20016 | US 27 |  | 19.4 | 19.85 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | C |  | NH | 2019 | 2035100 | 1729835 |  | 1729835 | 305265 |  |  | OBLIGATED | 1730515 |  | 1730515 | 2019 | 2ND QUARTER
STIP | YES | No | [7 empty] | CAMPBELL | 6-20017 | US 27 |  | 8.831 | 10.517 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | D |  | PM/STP | 2021 | 75000 | 60000 |  |  | 15000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; UPDATE FISCAL YEAR & FUND AMOUNTS; MOD |  |  | CAMPBELL | 6-20017 | US 27 |  | 8.831 | 10.517 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | D |  | PM/STP | FUTURE DATE | 93750 | 75000 |  |  | 18750 | [5 empty] | 0
STIP | YES | No | [7 empty] | CAMPBELL | 6-20017 | US 27 |  | 8.831 | 10.517 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | C |  | PM/STP | 2021 | 750000 | 600000 |  |  | 150000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; UPDATE FISCAL YEAR & FUND AMOUNTS; MOD |  |  | CAMPBELL | 6-20017 | US 27 |  | 8.831 | 10.517 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | C |  | PM/STP | FUTURE DATE | 937500 | 750000 |  |  | 187500 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.123 | 2019-09-06 | ADD PROJECT TO STIP; PARENT NO. 99-65.16 AND 99-65.17; NEW | STPBRZ | 9030180 | CARLISLE | 1-10021 | KY 1377 |  |  |  | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 1377 BRIDGE OVER HORN CREEK. (020B00038N) | C |  | BR | 2020 | 742000 | 742000 |  |  | 0 |  |  | OBLIGATED |  | 644395 | 644395 | 2019 | 4TH QUARTER
STIP | [7 empty] | STP | 0511049 | CARLISLE | 1-20027 | US 51 | 4.8 | 7.86 | 12.66 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION ON US-51 FROM MILEPOINT 7.86 TO MILEPOINT 12.66. (18CCR) | C |  | PM/NH | 2020 | 746000 | 596800 |  |  | 149200 |  |  | OBLIGATED | 1355000 | 163380 | 1518380 | 2019 | 4TH QUARTER
STIP | [7 empty] | STPBRZ | 5138068 | CARROLL | 6-1084 | US 42 | 0.25 | 5.697 | 5.947 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER KENTUCKY RIVER ON US 42 IN PRESTONSVILLE/CARROLLTON 0.13 MI E OF KY 55. (021B00043N) | D |  | BR/STP | 2019 | 1460000 | 905200 |  |  | 554800 |  |  | OBLIGATED |  | 1460000 | 1460000 | 2019 | 2ND QUARTER
STIP | [9 empty] | CARROLL | 6-1084 | US 42 | 0.25 | 5.697 | 5.947 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER KENTUCKY RIVER ON US 42 IN PRESTONSVILLE/CARROLLTON 0.13 MI E OF KY 55. (021B00043N) | R |  | BR/STP | 2020 | 1218000 | 755160 |  |  | 462840 | [5 empty] | 0
STIP | [9 empty] | CARROLL | 6-1084 | US 42 | 0.25 | 5.697 | 5.947 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER KENTUCKY RIVER ON US 42 IN PRESTONSVILLE/CARROLLTON 0.13 MI E OF KY 55. (021B00043N) | U |  | BR/STP | 2020 | 476000 | 295120 |  |  | 180880 | [5 empty] | 0
STIP | [9 empty] | CARROLL | 6-1084 | US 42 | 0.25 | 5.697 | 5.947 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER KENTUCKY RIVER ON US 42 IN PRESTONSVILLE/CARROLLTON 0.13 MI E OF KY 55. (021B00043N) | C |  | BR/STP | 2022 | 17717000 | 10984540 |  |  | 6732460 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.103 | 2019-07-29 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 0712078 | CARROLL GALLATIN | 6-9023 | I 71 |  | 52.298 53.433 | 53.433 56.5 | SAFETY | SAFETY-HAZARD ELIM(P) | CABLE MEDIAN BARRIER ON I-71 FROM MP 52.298 TO MP 56.500 IN CARROLL AND GALLATIN COUNTIES. (2018BOP) | D |  | SAF | 2019 | 50000 | 50000 |  |  | 0 |  |  | OBLIGATED | 50000 |  | 50000 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.139 | 2019-10-25 | ADD C PHASE TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 0712078 | CARROLL GALLATIN | 6-9023 | I 71 |  | 52.298 53.433 | 53.433 56.5 | SAFETY | SAFETY-HAZARD ELIM(P) | CABLE MEDIAN BARRIER ON I-71 FROM MP 52.298 TO MP 56.500 IN CARROLL AND GALLATIN COUNTIES. (2018BOP) | C |  | SAF | 2020 | 706200 | 706200 |  |  | 0 |  |  | OBLIGATED | 915202 |  | 915202 | 2020 | 1ST QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.111 | 2019-08-02 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 5295002 | CARROLL | 6-9024 | KY 36 |  | 2.182 | 8.132 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 36 FROM MP 2.182 TO MP 8.132 IN CARROLL COUNTY. (2018BOP) | D |  | SAF | 2019 | 350000 | 350000 |  |  | 0 |  |  | OBLIGATED |  | 350000 | 350000 | 2019 | 4TH QUARTER
STIP | [9 empty] | CARROLL | 6-10009 | KY 55 |  | 4.614 | 4.62 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 55 BRIDGE OVER MAJORS RUN CREEK. (021B00019N) | D |  | BR/STP | 2019 | 140000 | 86800 |  |  | 53200 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030072 | CARROLL | 6-10009 | KY 55 |  | 4.614 | 4.62 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 55 BRIDGE OVER MAJORS RUN CREEK. (021B00019N) | C |  | BR/STP | 2020 | 980000 | 607600 |  |  | 372400 |  |  | OBLIGATED |  | 557600 | 557600 | 2019 | 3RD QUARTER
STIP | [9 empty] | CARROLL | 6-20050 | KY 467 | 4.52 | 0 | 4.52 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION ON KY-467 FROM MILEPOINT 0.00 TO MILEPOINT 4.52 | C |  | PM/STP | 2022 | 365000 | 292000 |  |  | 73000 | [5 empty] | 0
STIP | [7 empty] | NHPP | 0648071 | CARTER | 9-62 | I 64 | 0.2 | 171.6 | 171.8 | RELIABILITY | CONGESTION MITIGTN(O) | IMPROVE MOBILITY AND REDUCE CONGESTION AT THE KY 1/I-64 WESTBOUND OFF-RAMP INTERSECTION. | D |  | NH | 2019 | 80000 | 80000 |  |  | 0 |  |  | OBLIGATED | 96000 |  | 96000 | 2020 | 2ND QUARTER
STIP | [9 empty] | CARTER | 9-62 | I 64 | 0.2 | 171.6 | 171.8 | RELIABILITY | CONGESTION MITIGTN(O) | IMPROVE MOBILITY AND REDUCE CONGESTION AT THE KY 1/I-64 WESTBOUND OFF-RAMP INTERSECTION. | R |  | NH | 2019 | 80000 | 80000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | CARTER | 9-62 | I 64 | 0.2 | 171.6 | 171.8 | RELIABILITY | CONGESTION MITIGTN(O) | IMPROVE MOBILITY AND REDUCE CONGESTION AT THE KY 1/I-64 WESTBOUND OFF-RAMP INTERSECTION. | U |  | NH | 2019 | 80000 | 80000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | CARTER | 9-62 | I 64 | 0.2 | 171.6 | 171.8 | RELIABILITY | CONGESTION MITIGTN(O) | IMPROVE MOBILITY AND REDUCE CONGESTION AT THE KY 1/I-64 WESTBOUND OFF-RAMP INTERSECTION. | C |  | NH | 2019 | 500000 | 500000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.25 | 2020-10-22 | INCREASE FUNDS AMOUNT BASED ON NEW ESTIMATE; MOD |  |  | CARTER | 9-62 | I 64 | 0.2 | 171.6 | 171.8 | RELIABILITY | CONGESTION MITIGTN(O) | IMPROVE MOBILITY AND REDUCE CONGESTION AT THE KY 1/I-64 WESTBOUND OFF-RAMP INTERSECTION. | C |  | NH | 2021 | 700000 | 700000 |  |  | 0 | [5 empty] | 0
STIP | YES | PENDING | [7 empty] | CARTER | 9-397 | KY 67 |  |  |  | SAFETY | SAFETY(P) | SAFETY, SPOT IMPROVEMENTS AND CONGESTION MITIGATION FOR INDUSTRIAL PARKWAY (KY 67) IN CARTER, BOYD, AND GREENUP COUNTIES FOR BRAIDY INDUSTRIES ALUMINUM PLANT DEVELOPMENT. | D |  | NH | 2019 | 2000000 | 2000000 |  |  | 0 | [5 empty] | 0
STIP | YES | PENDING | [7 empty] | CARTER | 9-397 | KY 67 |  |  |  | SAFETY | SAFETY(P) | SAFETY, SPOT IMPROVEMENTS AND CONGESTION MITIGATION FOR INDUSTRIAL PARKWAY (KY 67) IN CARTER, BOYD, AND GREENUP COUNTIES FOR BRAIDY INDUSTRIES ALUMINUM PLANT DEVELOPMENT. | R |  | NH | 2019 | 2500000 | 2500000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.248 | 2020-10-14 | TIP FY 21-24, AMENDMENT#2; UPDATE FISCAL YEAR; MOD |  |  | CARTER | 9-397 | KY 67 |  |  |  | SAFETY | SAFETY(P) | SAFETY, SPOT IMPROVEMENTS AND CONGESTION MITIGATION FOR INDUSTRIAL PARKWAY (KY 67) IN CARTER, BOYD, AND GREENUP COUNTIES FOR BRAIDY INDUSTRIES ALUMINUM PLANT DEVELOPMENT. | R |  | NH | 2023 | 2500000 | 2000000 |  |  |  | 500000 |  |  |  |  | 0
STIP | YES | PENDING | [7 empty] | CARTER | 9-397 | KY 67 |  |  |  | SAFETY | SAFETY(P) | SAFETY, SPOT IMPROVEMENTS AND CONGESTION MITIGATION FOR INDUSTRIAL PARKWAY (KY 67) IN CARTER, BOYD, AND GREENUP COUNTIES FOR BRAIDY INDUSTRIES ALUMINUM PLANT DEVELOPMENT. | U |  | NH | 2019 | 2500000 | 2500000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.248 | 2020-10-14 | TIP FY 21-24, AMENDMENT#2; UPDATE FISCAL YEAR; MOD |  |  | CARTER | 9-397 | KY 67 |  |  |  | SAFETY | SAFETY(P) | SAFETY, SPOT IMPROVEMENTS AND CONGESTION MITIGATION FOR INDUSTRIAL PARKWAY (KY 67) IN CARTER, BOYD, AND GREENUP COUNTIES FOR BRAIDY INDUSTRIES ALUMINUM PLANT DEVELOPMENT. | U |  | NH | 2024 | 2500000 | 2000000 |  |  |  | 500000 |  |  |  |  | 0
STIP | YES | PENDING | [7 empty] | CARTER | 9-397 | KY 67 |  |  |  | SAFETY | SAFETY(P) | SAFETY, SPOT IMPROVEMENTS AND CONGESTION MITIGATION FOR INDUSTRIAL PARKWAY (KY 67) IN CARTER, BOYD, AND GREENUP COUNTIES FOR BRAIDY INDUSTRIES ALUMINUM PLANT DEVELOPMENT. | C |  | NH | 2020 | 2000000 | 2000000 |  |  | 0 | [5 empty] | 0
STIP | YES | PENDING | [7 empty] | CARTER | 9-397.01 | KY 67 |  |  |  | SAFETY | PREFINANCD CONVRSN(O) | SAFETY, SPOT IMPROVEMENTS AND CONGESTION MITIGATION FOR INDUSTRIAL PARKWAY (KY 67) IN CARTER, BOYD, AND GREENUP COUNTIES FOR BRAIDY INDUSTRIES ALUMINUM PLANT DEVELOPMENT. (ADDITIONAL FUNDING FOR 9-397.00) | C |  | STP | 2021 | 5000000 | 4000000 |  |  | 1000000 | [5 empty] | 0
STIP MOD | YES | PENDING |  | ADMINISTRATIVE MODIFICATION | 2018.007 | 2019-01-31 | TIP FY 18-21; AMENDMENT#6; CHANGE FEDERAL FUNDING AMOUNT; MOD |  |  | CARTER | 9-397.01 | KY 67 |  |  |  | SAFETY | PREFINANCD CONVRSN(O) | SAFETY, SPOT IMPROVEMENTS AND CONGESTION MITIGATION FOR INDUSTRIAL PARKWAY (KY 67) IN CARTER, BOYD, AND GREENUP COUNTIES FOR BRAIDY INDUSTRIES ALUMINUM PLANT DEVELOPMENT. (ADDITIONAL FUNDING FOR 9-397.00) | C |  | STP | 2021 | 5000000 | 5000000 |  |  | 0 | [5 empty] | 0
STIP MOD | YES | PENDING |  | ADMINISTRATIVE MODIFICATION | 2018.007 | 2019-01-31 | TIP FY 18-21; AMENDMENT#6; ADD PROJECT TO STIP; NEW |  |  | CARTER | 9-397.02 | KY 67 |  |  |  | SAFETY | PREFINANCD CONVRSN(O) | SAFETY, SPOT IMPROVEMENTS AND CONGESTION MITIGATION FOR INDUSTRIAL PARKWAY (KY 67) IN CARTER, BOYD, AND GREENUP COUNTIES FOR BRAIDY INDUSTRIES ALUMINUM PLANT DEVELOPMENT. (ADDITIONAL FUNDING FOR 9-397.00) | C |  | STP | 2023 | 5000000 | 5000000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | CARTER | 9-1075 | US 60 | 0.1 | 4.061 | 4.161 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON US-60 (MP 4.111) OVER TYGARTS CREEK; .75 MI E OF JCT KY 1662; 022B00037N | C |  | BR/STP | 2019 | 693000 | 429660 |  |  | 263340 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.269 | 2021-01-22 | UPDATE FISCAL YEAR TO FY 2021 & FUND AMOUNT BASED ON NEW ESTIMATE; MOD |  |  | CARTER | 9-1075 | US 60 | 0.1 | 4.061 | 4.161 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON US-60 (MP 4.111) OVER TYGARTS CREEK; .75 MI E OF JCT KY 1662; 022B00037N | C |  | BR/STP | 2021 | 1403575 | 1403575 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.263 | 2020-12-11 | ADD R PHASE TO STIP; NEW |  |  | CARTER | 9-8311 | KY 1 |  | 9.83 | 10.24 | SAFETY | SAFETY(P) | IMPROVE SAFETY AT THE EAST CARTER HIGH SCHOOL ON KY 1 STARTING AT MP 9.830 TO MP 10.240). (06CCN)(08CCR)(12CCR) (2020CCR) | R |  | STP | 2021 | 650000 | 650000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.276 | 2021-02-12 | INCREASE FUNDS BASED ON NEW ESTIMATE; MOD |  |  | CARTER | 9-8311 | KY 1 |  | 9.83 | 10.24 | SAFETY | SAFETY(P) | IMPROVE SAFETY AT THE EAST CARTER HIGH SCHOOL ON KY 1 STARTING AT MP 9.830 TO MP 10.240). (06CCN)(08CCR)(12CCR) (2020CCR) | R |  | STP | 2021 | 711000 | 711000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.263 | 2020-12-11 | ADD U PHASE TO STIP; NEW |  |  | CARTER | 9-8311 | KY 1 |  | 9.83 | 10.24 | SAFETY | SAFETY(P) | IMPROVE SAFETY AT THE EAST CARTER HIGH SCHOOL ON KY 1 STARTING AT MP 9.830 TO MP 10.240). (06CCN)(08CCR)(12CCR) (2020CCR) | U |  | STP | 2021 | 450000 | 450000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.276 | 2021-02-12 | INCREASE FUNDS BASED ON NEW ESTIMATE; MOD |  |  | CARTER | 9-8311 | KY 1 |  | 9.83 | 10.24 | SAFETY | SAFETY(P) | IMPROVE SAFETY AT THE EAST CARTER HIGH SCHOOL ON KY 1 STARTING AT MP 9.830 TO MP 10.240). (06CCN)(08CCR)(12CCR) (2020CCR) | U |  | STP | 2021 | 975000 | 975000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.263 | 2020-12-11 | ADD C PHASE TO STIP; NEW |  |  | CARTER | 9-8311 | KY 1 |  | 9.83 | 10.24 | SAFETY | SAFETY(P) | IMPROVE SAFETY AT THE EAST CARTER HIGH SCHOOL ON KY 1 STARTING AT MP 9.830 TO MP 10.240). (06CCN)(08CCR)(12CCR) (2020CCR) | C |  | STP | 2021 | 1860000 | 1860000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.291 | 2021-04-23 | ADD C PHASE TO STIP; NEW |  |  | CARTER | 9-4335 | KY 174 |  | 5.5 | 5.6 |  | SAF GUARDRAIL (P) | INSTALL GUARDRAIL ON KY-174 IN CARTER COUNTY | C |  | STP | 2021 | 12075 | 12075 | [8 empty] | 0
STIP | [9 empty] | CARTER | 9-8506 | KY 773 |  | 1 | 1.3 | ASSET MANAGEMENT | AM-BRIDGE (P) | REPLACEMENT OF TWO TRUSS BRIDGES ON KY 773 OVER THE LITTLE SANDY RIVER. (022B00074N)(022B00075N) | C |  | BR/STP | 2019 | 5019000 | 3111780 |  |  | 1907220 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.291 | 2021-04-23 | ADD C PHASE TO STIP; NEW |  |  | CARTER | 9-4329 | KY 504 |  | 1.12 | 1.34 |  | SAF GUARDRAIL (P) | INSTALL GUARDRAIL ON KY-504 IN CARTER COUNTY | C |  | STP | 2021 | 32200 | 32200 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.291 | 2021-04-23 | ADD C PHASE TO STIP; NEW |  |  | CARTER | 9-4335 | KY 174 |  | 5.5 | 5.6 |  | SAF GUARDRAIL (P) | INSTALL GUARDRAIL ON KY-174 IN CARTER COUNTY | C |  | STP | 2021 | 12075 | 12075 | [8 empty] | 0
STIP | [9 empty] | CARTER | 9-10002 | KY 1 |  | 6.915 | 6.919 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-1 BRIDGE OVER POWELL BRANCH. (022B00006N) | D |  | BR/STP | 2019 | 525000 | 325500 |  |  | 199500 | [5 empty] | 0
STIP | [9 empty] | CARTER | 9-10002 | KY 1 |  | 6.915 | 6.919 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-1 BRIDGE OVER POWELL BRANCH. (022B00006N) | C |  | BR/STP | 2020 | 1015000 | 629300 |  |  | 385700 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.283 | 2021-03-22 | UPDATE FISCAL YEAR AND FUND AMOUNT; MOD |  |  | CARTER | 9-10002 | KY 1 |  | 6.915 | 6.919 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-1 BRIDGE OVER POWELL BRANCH. (022B00006N) | C |  | STP | 2021 | 2227000 | 2227000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | CARTER | 9-10003 | KY 182 |  | 2.206 | 2.22 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-182 BRIDGE OVER SINKING CREEK. (022B00140N) | D |  | BR/STP | 2019 | 490000 | 303800 |  |  | 186200 | [5 empty] | 0
STIP | [9 empty] | CARTER | 9-10003 | KY 182 |  | 2.206 | 2.22 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-182 BRIDGE OVER SINKING CREEK. (022B00140N) | C |  | BR/STP | 2020 | 1750000 | 1085000 |  |  | 665000 | [5 empty] | 0
STIP | [9 empty] | CARTER | 9-20006 | KY 9 |  | 0 | 6.98 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION | D |  | PM/NH | 2021 | 320000 | 256000 |  |  | 64000 | [5 empty] | 0
STIP | [9 empty] | CARTER | 9-20006 | KY 9 |  | 0 | 6.98 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION | C |  | PM/NH | 2021 | 3200000 | 2560000 |  |  | 640000 | [5 empty] | 0
STIP | [9 empty] | CARTER | 9-20007 | KY 9 |  | 14.98 | 18.262 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION | D |  | PM/NH | 2021 | 150000 | 120000 |  |  | 30000 | [5 empty] | 0
STIP | [9 empty] | CARTER | 9-20007 | KY 9 |  | 14.98 | 18.262 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION | C |  | PM/NH | 2021 | 1500000 | 1200000 |  |  | 300000 | [5 empty] | 0
STIP | [9 empty] | CARTER | 9-20008 | KY 9 |  | 6.98 | 14.985 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION | D |  | PM/NH | 2021 | 350000 | 280000 |  |  | 70000 | [5 empty] | 0
STIP | [9 empty] | CARTER | 9-20008 | KY 9 |  | 6.98 | 14.985 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION | C |  | PM/NH | 2021 | 3500000 | 2800000 |  |  | 700000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.177 | 2020-04-24 | ADD C PHASE TO STIP; PARENT NO. 99-911.09; NEW |  |  | CASEY PULASKI LINCOLN | 8-945 | KY 70 |  | 0 0 0 | 26 13.814 2.958 | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALLATION OF STRIPING ALONG KY 70 IN CASEY, PULASKI, AND LINCOLN COUNTIES. (2018BOP) | C |  | SAF | 2020 | 627000 | 627000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | CASEY | 8-1067 | CR 1169 |  | 0.051 | 0.067 | ASSET MANAGEMENT | AM-BRIDGE (P) | REPLACE BRIDGE ON CR-1169 (0.059) OVER SOUTH FORK CREEK. (023C00029N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [9 empty] | CASEY | 8-1067 | CR 1169 |  | 0.051 | 0.067 | ASSET MANAGEMENT | AM-BRIDGE (P) | REPLACE BRIDGE ON CR-1169 (0.059) OVER SOUTH FORK CREEK. (023C00029N) | C |  | BR/STP | 2020 | 532000 | 329840 |  |  | 202160 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.274 | 2021-02-04 | ADD D PHASE TO STIP; NEW |  |  | CASEY | 8-8703 | KY 70 |  | 10.4 | 11.9 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT BELL HILL FROM MP 10.4 TO MP 11.9.(12CCN)(16CCR)(18CCN) (2020CCR) | D |  | STP | 2021 | 1100000 | 1100000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.274 | 2021-02-04 | ADD D PHASE TO STIP; NEW |  |  | CASEY | 8-8704 | KY 49 |  | 1.8 | 2.8 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT BRUSHY CREEK HILL FROM MP 1.8 TO MP 2.8.(12CCN)(16CCR)(18CCN) (2020CCR) | D |  | STP | 2021 | 850000 | 850000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.306 | 2021-06-16 | ADD D PHASE TO STIP; NEW |  |  | CASEY | 8-8705 | KY 501 |  | 11 | 11.18 | RELIABILITY | RECONSTRUCTION(O) | REALIGN KY 501 TO INTERSECT KY 70 EAST OF EXISTING LOCATION AND CORRECT VERTICAL ALIGNMENT OF KY 70 NEAR EXISTING INTERSECTION.(12CCN) (2020CCN) | D |  | SPP | 2021 | 520100 | 100 |  |  | 520000 | [5 empty] | 0
STIP | [9 empty] | CASEY | 8-10000 | KY 2310 |  | 0.178 | 0.19 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-2310 BRIDGE OVER LUTTRELL CREEK. (023B00066N) | D |  | BR/STP | 2019 | 192500 | 119350 |  |  | 73150 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030124 | CASEY | 8-10000 | KY 2310 |  | 0.178 | 0.19 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-2310 BRIDGE OVER LUTTRELL CREEK. (023B00066N) | C |  | BR/STP | 2020 | 927500 | 575050 |  |  | 352450 |  |  | OBLIGATED |  | 899675 | 899675 | 2019 | 3RD QUARTER
STIP | [9 empty] | CASEY | 8-10006 | KY 1552 |  | 0.12 | 0.126 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 1552 BRIDGE OVER BR OF BRUSH CREEK. (023B00061N) | D |  | BR/STP | 2019 | 70000 | 43400 |  |  | 26600 | [5 empty] | 0
STIP | [9 empty] | CASEY | 8-10006 | KY 1552 |  | 0.12 | 0.126 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 1552 BRIDGE OVER BR OF BRUSH CREEK. (023B00061N) | C |  | BR/STP | 2020 | 266000 | 164920 |  |  | 101080 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.021 | 2019-02-04 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030037 | CASEY | 8-10006 | KY 1552 |  | 0.12 | 0.126 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 1552 BRIDGE OVER BR OF BRUSH CREEK. (023B00061N) | C |  | STP | 2019 | 400000 | 400000 |  |  | 0 |  |  | OBLIGATED |  | 434330 | 434330 | 2019 | 2ND QUARTER
STIP | [9 empty] | CASEY | 8-10007 | KY 1552 |  | 1.218 | 1.224 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 1552 BRIDGE OVER LONG BRANCH. (023B00062N) | D |  | BR/STP | 2019 | 70000 | 43400 |  |  | 26600 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 0803212 | CASEY | 8-10007 | KY 1552 |  | 1.218 | 1.224 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 1552 BRIDGE OVER LONG BRANCH. (023B00062N) | C |  | BR/STP | 2020 | 266000 | 164920 |  |  | 101080 |  |  | OBLIGATED | 556467 | 44913 | 601380 | 2019 | 2ND QUARTER
STIP | [9 empty] | CASEY | 8-10008 | KY 3270 |  | 3.475 | 3.479 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 3270 BRIDGE OVER HOWE BRANCH. (023B00077N) | D |  | BR/STP | 2019 | 70000 | 43400 |  |  | 26600 | [5 empty] | 0
STIP | [9 empty] | CASEY | 8-10008 | KY 3270 |  | 3.475 | 3.479 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 3270 BRIDGE OVER HOWE BRANCH. (023B00077N) | C |  | BR/STP | 2020 | 234500 | 145390 |  |  | 89110 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.03 | 2019-03-01 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030062 | CASEY | 8-10008 | KY 3270 |  | 3.475 | 3.479 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 3270 BRIDGE OVER HOWE BRANCH. (023B00077N) | C |  | STP | 2019 | 235249 | 235249 |  |  | 0 |  |  | OBLIGATED |  | 236159.6 | 236159.6 | 2019 | 2ND QUARTER
STIP | [9 empty] | CASEY | 8-20001 | KY 70 |  | 0 | 4 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION | D |  | PM/STP | 2019 | 375000 | 300000 |  |  | 75000 | [5 empty] | 0
STIP | [7 empty] | STP | 5105049 | CASEY | 8-20001 | KY 70 |  | 0 | 4 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION | C |  | PM/STP | 2019 | 3750000 | 3000000 |  |  | 750000 |  |  | OBLIGATED | 4496628 |  | 4496628 | 2019 | 3RD QUARTER
|  |  |  | AMENDMENT | 2018.005 | 2020-01-30 | TIP REFERENCE FY 2020-2023 RESOLUTION DATED 10/31/19. NEW |  |  | CHRISTIAN
STIP | YES | YES | The TIP shows Utilities for 2,310,000 and Const for 8,800,000. This covers the amount for Const. Has Utilities been obligated? |  |  |  |  | STP | 6000027 | CHRISTIAN | 2-180 | KY 911 | 1.835 | 0 | 1.835 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE KY-911 FROM US-41A TO OAK GROVE.(12CCR). | C |  | STP | 2020 | 2530000 | 2530000 |  |  | 0 | [5 empty] | 0
STIP | YES | YES | The Const phase in the TIP has more funds than in the STIP. I have not planned any action to be taken since the TIP covers the Const cost estimated. Please Advise. | [6 empty] | CHRISTIAN | 2-180.01 | KY 911 | 1.835 | 0 | 1.835 | RELIABILITY | PREFINANCD CONVRSN(O) | IMPROVE KY-911 FROM US-41A TO OAK GROVE.(12CCR) | C |  | STP | 2021 | 5910000 | 4728000 |  |  | 1182000 | [5 empty] | 0
[8 empty] | STP | 6000166 | CHRISTIAN | 2-180.10 | KY 911 |  | 0 | 0.448 | RELIABILITY | MAJOR WIDENING(O) | WIDEN KY 911 TO A 5 LANE FROM US 41A TO THE DEPARTMENT OF DEFENSE RAILROAD.(SECTION 1)(D,R,U UNDER 2-180)(2018BOP) | C |  | STP | 2020 | 2530000 | 2530000 |  |  | 0 |  |  | OBLIGATED |  | 3166941 | 3166941 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.269 | 2021-01-22 | ADD D PHASE TO STIP; NEW |  |  | CHRISTIAN | 2-381 | US 41 |  |  |  | RELIABILITY | NEW ROUTE(O) | CONSTRUCT NEW CONNECTOR FROM US 41 NEAR THE INDUSTRIAL PARK TO KY 115 SOUTH OF PEMBROKE. (16CCR)(18CCN) (2020CCR) | D |  | STP | 2021 | 500000 | 500000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.269 | 2021-01-22 | ADD R PHASE TO STIP; NEW |  |  | CHRISTIAN | 2-381 | US 41 |  |  |  | RELIABILITY | NEW ROUTE(O) | CONSTRUCT NEW CONNECTOR FROM US 41 NEAR THE INDUSTRIAL PARK TO KY 115 SOUTH OF PEMBROKE. (16CCR)(18CCN) (2020CCR) | R |  | STP | 2022 | 450000 | 450000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.269 | 2021-01-22 | ADD U PHASE TO STIP; NEW |  |  | CHRISTIAN | 2-381 | US 41 |  |  |  | RELIABILITY | NEW ROUTE(O) | CONSTRUCT NEW CONNECTOR FROM US 41 NEAR THE INDUSTRIAL PARK TO KY 115 SOUTH OF PEMBROKE. (16CCR)(18CCN) (2020CCR) | U |  | STP | 2022 | 790000 | 790000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.269 | 2021-01-22 | ADD C PHASE TO STIP; NEW |  |  | CHRISTIAN | 2-381 | US 41 |  |  |  | RELIABILITY | NEW ROUTE(O) | CONSTRUCT NEW CONNECTOR FROM US 41 NEAR THE INDUSTRIAL PARK TO KY 115 SOUTH OF PEMBROKE. (16CCR)(18CCN) (2020CCR) | C |  | STP | 2023 | 5850000 | 5850000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | CHRISTIAN | 2-898 | EB 9004 |  | 11.6 | 11.78 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT THE BREATHITT PARKWAY INTERCHANGE AT KY 1682 NORTH OF HOPKINSVILLE. (BREATHITT PARKWAY/FUTURE INTERSTATE SPUR PROJECT) (16CCR)(18CCN) | R |  | NH | 2020 | 1000000 | 1000000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | CHRISTIAN | 2-898 | EB 9004 |  | 11.6 | 11.78 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT THE BREATHITT PARKWAY INTERCHANGE AT KY 1682 NORTH OF HOPKINSVILLE. (BREATHITT PARKWAY/FUTURE INTERSTATE SPUR PROJECT) (16CCR)(18CCN) | U |  | NH | 2021 | 1000000 | 800000 |  |  | 200000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.3 | 2021-05-28 | ADD R PHASE TO STIP; NEW |  |  | CHRISTIAN | 2-899 | US 68 |  | 9.221 | 10.137 | RELIABILITY | RECONSTRUCTION(O) | ADDRESS CONGESTION AND MOBILITY OF US 68 FROM KY 91 TO KY 1007 IN HOPKINSVILLE. (18CCN) (2020CCR) | R |  | NHPP | 2021 | 1840000 | 1840000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.3 | 2021-05-28 | ADD U PHASE TO STIP; NEW |  |  | CHRISTIAN | 2-899 | US 68 |  | 9.221 | 10.137 | RELIABILITY | RECONSTRUCTION(O) | ADDRESS CONGESTION AND MOBILITY OF US 68 FROM KY 91 TO KY 1007 IN HOPKINSVILLE. (18CCN) (2020CCR) | U |  | NHPP | 2021 | 4050000 | 4050000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.067 | 2019-05-13 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 0411028 | CHRISTIAN | 2-915 | US 41 NB |  | 0 | 31.574 | SAFETY | SAFETY-HAZARD ELIM(P) | REPLACEMENT OF TARGETED GUARDRAIL END TREATMENTS ON US 41 NB FROM MP 0.000 TO MP 31.574 (2018BOP). | C |  | SAF | 2019 | 530000 | 530000 |  |  | 0 |  |  | OBLIGATED | 506500 |  | 506500 | 2019 | 3RD QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.067 | 2019-05-13 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 0411029 | CHRISTIAN | 2-916 | US 41 SB |  | 0 | 31.574 | SAFETY | SAFETY-HAZARD ELIM(P) | REPLACEMENT OF TARGETED GUARDRAIL END TREATMENTS ON US 41 SB FROM MP 0.000 TO MP 31.574 (2018BOP). | C |  | SAF | 2019 | 400000 | 400000 |  |  | 0 |  |  | OBLIGATED |  | 365500 | 365500 | 2019 | 3RD QUARTER
STIP | [7 empty] | STPBRZ | 0203328 | CHRISTIAN | 2-1085 | CR 1116 |  | 0.019 | 0.059 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON SUB STATION RD (CR 1116) OVER CSX RR 0.04 MILE E OF US 41 024C00034N | C |  | BR/STP | 2019 | 880000 | 545600 |  |  | 334400 |  |  | OBLIGATED | 1157310 | 265814 | 1423124 | 2019 | 4TH QUARTER
STIP | [9 empty] | CHRISTIAN | 2-1089 | US 41A | 0.032 | 15.386 | 15.418 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER CSX RR ON WALNUT STREET (US 41A) IN HOPKINSVILLE 475 FT NE OF EAST 21ST STREET (CS 1016) (024B00112N) | D |  | BR/STP | 2019 | 385000 | 238700 |  |  | 146300 | [5 empty] | 0
STIP | [9 empty] | CHRISTIAN | 2-1089 | US 41A | 0.032 | 15.386 | 15.418 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER CSX RR ON WALNUT STREET (US 41A) IN HOPKINSVILLE 475 FT NE OF EAST 21ST STREET (CS 1016) (024B00112N) | C |  | BR/STP | 2020 | 2002000 | 1241240 |  |  | 760760 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 203345 | CHRISTIAN | 2-1094 | CS 1262 | 0.038 | 0.372 | 0.41 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER N FORK LITTLE RIVER ON MILBROOKE DRIVE (CS 1262) 500 FT SW OF KAREN DRIVE (CS 1268) 024C00081N | C |  | BR/STP | 2020 | 1470000 | 911400 |  |  | 558600 |  |  | OBLIGATED | 1368112 | 148064 | 1516176 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.269 | 2021-01-22 | ADD D PHASE TO STIP; NEW |  |  | CHRISTIAN | 2-8953 | KY 115 |  | 6.87 | 9.625 | RELIABILITY | MINOR WIDENING(O) | IMPROVE AND WIDEN KY 115 FROM ANDERSON ROAD (MP 6.87) TO JUST SOUTH OF PEMBROKE (MP 9.625)(16CCN)(18CCN) | D |  | STP | 2021 | 1040000 | 1040000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.269 | 2021-01-22 | ADD R PHASE TO STIP; NEW |  |  | CHRISTIAN | 2-8953 | KY 115 |  | 6.87 | 9.625 | RELIABILITY | MINOR WIDENING(O) | IMPROVE AND WIDEN KY 115 FROM ANDERSON ROAD (MP 6.87) TO JUST SOUTH OF PEMBROKE (MP 9.625)(16CCN)(18CCN) | R |  | STP | 2025 | 2020000 | 2020000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.269 | 2021-01-22 | ADD U PHASE TO STIP; NEW |  |  | CHRISTIAN | 2-8953 | KY 115 |  | 6.87 | 9.625 | RELIABILITY | MINOR WIDENING(O) | IMPROVE AND WIDEN KY 115 FROM ANDERSON ROAD (MP 6.87) TO JUST SOUTH OF PEMBROKE (MP 9.625)(16CCN)(18CCN) | U |  | STP | 2025 | 2540000 | 2540000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.296 | 2021-04-23 | TIP FY 20-23, AMEND#5; ADD PROJECT TO STIP; NEW |  |  | CHRISTIAN | 2-8954 | KY 115 |  | 2.901 | 6.87 | SAFETY | SAFETY (P) | IMPROVE AND WIDEN KY 115 FROM I-24 (MP 2.901) TO ANDERSON ROAD (MP 6.87).(16CCN) | D |  | STP | 2021 | 1360000 | 1360000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.296 | 2021-04-23 | TIP FY 20-23, AMEND#5; ADD PROJECT TO STIP; NEW |  |  | CHRISTIAN | 2-8954 | KY 115 |  | 2.901 | 6.87 | SAFETY | SAFETY (P) | IMPROVE AND WIDEN KY 115 FROM I-24 (MP 2.901) TO ANDERSON ROAD (MP 6.87).(16CCN) | R |  | STP | 2021 | 1440000 | 1440000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.296 | 2021-04-23 | TIP FY 20-23, AMEND#5; ADD PROJECT TO STIP; NEW |  |  | CHRISTIAN | 2-8954 | KY 115 |  | 2.901 | 6.87 | SAFETY | SAFETY (P) | IMPROVE AND WIDEN KY 115 FROM I-24 (MP 2.901) TO ANDERSON ROAD (MP 6.87).(16CCN) | U |  | STP | 2022 | 2440000 | 2440000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.296 | 2021-04-23 | TIP FY 20-23, AMEND#5; ADD PROJECT TO STIP; NEW |  |  | CHRISTIAN | 2-8954 | KY 115 |  | 2.901 | 6.87 | SAFETY | SAFETY (P) | IMPROVE AND WIDEN KY 115 FROM I-24 (MP 2.901) TO ANDERSON ROAD (MP 6.87).(16CCN) | C |  | STP | 2023 | 9470000 | 9470000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.059 | 2019-04-29 | TIP FY 17-20, ADMIN MOD#1; ADD PROJECT TO STIP; NEW | HSIP | 9010314 | CHRISTIAN | 2-9008.2 | KY 115 |  | 2.3 | 2.8 | SAFETY | SAFETY-HAZARD ELIM(P) | RECONSTRUCT THE SHOULDERS WITH FULL DEPTH ASPHALT ALONG KY 115 AND RESTRIPE TO PROVIDE A 6' WIDE MEDIAN NEAR THE INTERSECTION OF KY 115 AND WALTER GARRET LN. | C |  | SAF | 2019 | 1100000 | 1100000 |  |  | 0 |  |  | OBLIGATED | 569884 |  | 569884 | 2019 | 3RD QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.258 | 2020-11-13 | TIP FY 20-23, ADMIN MOD#5; ADD PROJECT TO STIP; NEW |  |  | CHRISTIAN | 2-9010 | KY 115 |  | 3 | 9.929 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 115 FROM MP 3.000 TO MP 9.929 IN CHRISTIAN COUNTY. (2018BOP) | C |  | SAF | 2021 | 2260500 | 2034450 |  |  | 226050 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.029 | 2019-02-21 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 7200002 | CHRISTIAN | 2-9011 | KY 107 |  | 18.272 | 18.472 | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALLATION OF RAISED ISLAND FOR CHANNELIZING TRAFFIC FROM TWO WAY STREET TO ONE WAY COUPLET. ADDITIONAL SIGNING AND PAVEMENT MARKINGS TO DELINEATE TRAFFIC DIRECTIONS. (2018BOP) | C |  | SAF | 2019 | 51000 | 51000 |  |  | 0 |  |  | OBLIGATED |  | 101816 | 101816 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.175 | 2020-04-09 | ADD D PHASE TO STIP; PARENT NO. 99-911.09; NEW |  |  | CHRISTIAN | 2-9014 | KY 107 |  | 21.546 | 27.016 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 107 FROM MP 21.546 TO MP 27.016 IN CHRISTIAN COUNTY, KY. (2018BOP) | D |  | SAF | 2020 | 150000 | 150000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | CHRISTIAN | 2-10001 | KY 189 |  | 3.179 | 3.187 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-189 BRIDGE OVER BRANCH OF BUCK FORK. (024B00064N) | D |  | BR/STP | 2019 | 245000 | 151900 |  |  | 93100 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030100 | CHRISTIAN | 2-10001 | KY 189 |  | 3.179 | 3.187 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-189 BRIDGE OVER BRANCH OF BUCK FORK. (024B00064N) | C |  | BR/STP | 2020 | 1032500 | 640150 |  |  | 392350 |  |  | OBLIGATED |  | 695985 | 695985 | 2019 | 4TH QUARTER
STIP | [9 empty] | CHRISTIAN | 2-10022 | US 41 |  | 15.333 | 15.347 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF US 41 BRIDGE OVER NORTH FORK LITTLE RIVER. (024B00005N) | D |  | BR/NH | 2019 | 35000 | 21700 |  |  | 13300 | [5 empty] | 0
STIP | [9 empty] | CHRISTIAN | 2-10022 | US 41 |  | 15.333 | 15.347 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF US 41 BRIDGE OVER NORTH FORK LITTLE RIVER. (024B00005N) | C |  | BR/NH | 2020 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.03 | 2019-03-01 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030057 | CHRISTIAN | 2-10022 | US 41 |  | 15.333 | 15.347 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF US 41 BRIDGE OVER NORTH FORK LITTLE RIVER. (024B00005N) | C |  | STP | 2019 | 665433 | 665433 |  |  | 0 |  |  | OBLIGATED |  | 617560 | 617560 | 2019 | 2ND QUARTER
STIP | [9 empty] | CHRISTIAN | 2-20005 | EB 9004 |  | 0 | 4.719 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF EDWARD T. BREATHITT PENNYRILE PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 0 TO MILEPOINT 4.719 | D |  | PM/STP | 2019 | 400000 | 320000 |  |  | 80000 | [5 empty] | 0
STIP | [9 empty] | CHRISTIAN | 2-20005 | EB 9004 |  | 0 | 4.719 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF EDWARD T. BREATHITT PENNYRILE PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 0 TO MILEPOINT 4.719 | C |  | PM/STP | 2020 | 4000000 | 3200000 |  |  | 800000 | [5 empty] | 0
STIP | [7 empty] | NHPP | 0411030 | CHRISTIAN | 2-20006 | EB 9004 |  | 12.13 | 16.5 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF EDWARD T. BREATHITT PENNYRILE PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 12.13 TO MILEPOINT 16.5 (16.7 NON-CARDINAL) | C |  | PM/NH | 2020 | 4120000 | 3296000 |  |  | 824000 |  |  | OBLIGATED | 3063189 |  | 3063189 | 2019 | 4TH QUARTER
STIP | [9 empty] | CHRISTIAN | 2-20010 | I 24 |  | 69.83 | 76.142 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT ON I-24 CARDINAL DIRECTION(S) FROM MILEPOINT 69.83 TO MILEPOINT 76.142. | D |  | PM/NH | 2022 | 325000 | 260000 |  |  | 65000 | [5 empty] | 0
STIP | [9 empty] | CHRISTIAN | 2-20010 | I 24 |  | 69.83 | 76.142 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT ON I-24 CARDINAL DIRECTION(S) FROM MILEPOINT 69.83 TO MILEPOINT 76.142. | C |  | PM/NH | 2022 | 3250000 | 2600000 |  |  | 650000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.311 | 2021-07-21 | ADD C PHASE TO STIP; NEW |  |  | CHRISTIAN | 2-20012 | I 24 |  | 76.142 | 85.563 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-24 CARDINAL DIRECTION(S) FROM MILEPOINT 76.142 TO MILEPOINT 85.563. | C |  | NHPP | 2021 | 4125000 | 4125000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | CHRISTIAN | 2-20013 | I 24 |  | 85.563 | 92 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT ON I-24 BOTH DIRECTION(S) FROM MILEPOINT 85.563 TO MILEPOINT 92. | D |  | PM/NH | 2022 | 650000 | 520000 |  |  | 130000 | [5 empty] | 0
STIP | [9 empty] | CHRISTIAN | 2-20013 | I 24 |  | 85.563 | 92 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT ON I-24 BOTH DIRECTION(S) FROM MILEPOINT 85.563 TO MILEPOINT 92. | C |  | PM/NH | 2022 | 6500000 | 5200000 |  |  | 1300000 | [5 empty] | 0
STIP | [9 empty] | CHRISTIAN | 2-20016 | US 68 |  | 10.93 | 11.563 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | D |  | PM/STP | 2021 | 75000 | 60000 |  |  | 15000 | [5 empty] | 0
STIP | [9 empty] | CHRISTIAN | 2-20016 | US 68 |  | 10.93 | 11.563 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | C |  | PM/STP | 2021 | 750000 | 600000 |  |  | 150000 | [5 empty] | 0
STIP | [9 empty] | CHRISTIAN | 2-20046 | US 41 | 16.78 | 14.79 | 31.57 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION ON US-41 FROM MILEPOINT 14.79 TO MILEPOINT 31.57 | C |  | PM/NH | 2022 | 1635000 | 1308000 |  |  | 327000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.229 | 2020-09-14 | ADD C PHASE TO STIP; PARENT NO. 99-224.14; NEW |  |  | CHRISTIAN | 2-20056 | KY 1979 US 68 |  | 0 12.62 | .236 13.64 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | Resurfacing of KY 1979 (MP 0.0-0.236) and US 68 (MP 12.62-13.64) in Christian County, KY. | C |  | STP | 2020 | 250000 | 250000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | CHRISTIAN | 2-80000 | KY 115 |  | 3.137 | 10.662 | ASSET MANAGEMENT | RESURFACING(P) | RESURFACING ON KY 115 FROM CARNEAL LANE TO US 41. (18CCN) | C |  | PM/STP | 2019 | 730000 | 584000 |  |  | 146000 | [5 empty] | 0
STIP | [9 empty] | CHRISTIAN | 2-80002 | KY 1026 |  |  |  | ASSET MANAGEMENT | RESURFACING(P) | RESURFACING ON KY 1026 FROM GRACEY SINKING FORK ROAD TO SHURDAN CREEK ROAD(18CCN) | C |  | PM/STP | 2019 | 200000 | 160000 |  |  | 40000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.175 | 2020-04-09 | ADD PROJECT TO STIP; NEW |  |  | CHRISTIAN | 99-352.14 |  |  |  |  | SAFETY | SAFETY-RR PROTECTN(P) | ADD GATES TO EXISTING FLASHING LIGHTS AND BELL SYSTEM AT CSX CROSSING ON EAST 14TH STREET IN HOPKINSVILLE. (DOT#245262L) | U |  | RRP | 2020 | 399740 | 363400 |  |  | 36340 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.21 | 2020-07-31 | ADD D PHASE TO STIP; NEW |  |  | CLARK MONTGOMERY | 7-9022 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | CABLE MEDIAN BARRIER ON I-64 FROM MP 98.000 TO MP 115.647 IN CLARK AND MONTGOMERY COUNTIES. | D |  | SAF | 2020 | 50000 | 50000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.233 | 2020-09-21 | ADD D PHASE TO STIP; NEW |  |  | CLARK | 7-8401 | KY 1958 |  |  |  | RELIABILITY | NEW ROUTE(O) | EXTEND THE WINCHESTER EAST BYPASS (KY 1958) FROM IRVINE ROAD (KY 89) TO KY 627 SOUTH OF WINCHESTER. (08CCN)(10CCR)(18CCN) | D |  | STP | 2020 | 250000 | 250000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | CLARK | 7-20004 | I 64 |  | 89.48 | 94.7 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-64 BOTH DIRECTION(S) FROM MILEPOINT 89.48 TO MILEPOINT 94.7. | D |  | PM/NH | 2022 | 630000 | 504000 |  |  | 126000 | [5 empty] | 0
STIP | [9 empty] | CLARK | 7-20004 | I 64 |  | 89.48 | 94.7 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-64 BOTH DIRECTION(S) FROM MILEPOINT 89.48 TO MILEPOINT 94.7. | C |  | PM/NH | 2022 | 6300000 | 5040000 |  |  | 1260000 | [5 empty] | 0
STIP | [9 empty] | CLARK | 7-20005 | I 64 |  | 94.65 | 98.1 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-64 BOTH DIRECTION(S) FROM MILEPOINT 94.65 TO MILEPOINT 98.1. | D |  | PM/NH | 2022 | 525000 | 420000 |  |  | 105000 | [5 empty] | 0
STIP | [9 empty] | CLARK | 7-20005 | I 64 |  | 94.65 | 98.1 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-64 BOTH DIRECTION(S) FROM MILEPOINT 94.65 TO MILEPOINT 98.1. | C |  | PM/NH | 2022 | 5250000 | 4200000 |  |  | 1050000 | [5 empty] | 0
STIP | [9 empty] | CLARK | 7-20006 | I 64 |  | 98.1 | 101.78 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-64 BOTH DIRECTION(S) FROM MILEPOINT 98.1 TO MILEPOINT 101.78. | D |  | PM/NH | 2020 | 430000 | 344000 |  |  | 86000 | [5 empty] | 0
STIP | [9 empty] | CLARK | 7-20006 | I 64 |  | 98.1 | 101.78 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-64 BOTH DIRECTION(S) FROM MILEPOINT 98.1 TO MILEPOINT 101.78. | C |  | PM/NH | 2020 | 4300000 | 3440000 |  |  | 860000 | [5 empty] | 0
STIP | [9 empty] | CLARK | 7-20007 | KY 9000 |  | 9.45 | 11.913 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF BERT T. COMBS MOUNTAIN PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 9.45 (5.311 NON-CARDINAL) TO MILEPOINT 11.913 | D |  | PM/NH | 2021 | 530000 | 424000 |  |  | 106000 | [5 empty] | 0
STIP | [9 empty] | CLARK | 7-20007 | KY 9000 |  | 9.45 | 11.913 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF BERT T. COMBS MOUNTAIN PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 9.45 (5.311 NON-CARDINAL) TO MILEPOINT 11.913 | C |  | PM/NH | 2021 | 5300000 | 4240000 |  |  | 1060000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.306 | 2021-06-16 | ADD D PHASE TO STIP; NEW |  |  | CLARK | 7-80100 | KY 627 |  | 6.3 | 6.317 |  | CONGESTION MITIGTN(O) | ADD A LEFT TURN LANE BY THE ENTRANCE OF 1520 BOONESBORO RD. (2020CCN) | D |  | SPP | 2021 | 20100 | 100 |  |  | 20000 | [5 empty] | 0
STIP | [9 empty] | CLAY | 11-1099 | CR 1160 | 0.016 | 2.01 | 2.026 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER OTTER CREEK ON OTTER CREEK ROAD (CR 1160) AT JUNCTION WITH MAY FORK ROAD (CR 1158)(026C00031N) | D |  | BR/STP | 2019 | 105000 | 65100 |  |  | 39900 | [5 empty] | 0
STIP | [9 empty] | CLAY | 11-1099 | CR 1160 | 0.016 | 2.01 | 2.026 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER OTTER CREEK ON OTTER CREEK ROAD (CR 1160) AT JUNCTION WITH MAY FORK ROAD (CR 1158)(026C00031N) | C |  | BR/STP | 2020 | 364000 | 225680 |  |  | 138320 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.075 | 2019-05-28 | ADD C PHASE TO STIP; PARENT NO. 99-911.04; NEW | HSIP | 5286015 | CLAY | 11-9004 | KY 11 |  | 8.89 | 26.62 | SAFETY | SAFETY(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 11 FROM US 421(MP 8.89) EXTENDING NE TO THE OWSLEY CO. LINE (MP 26.62) IN CLAY COUNTY, KY. (2014BOP) | C |  | SAF | 2019 | 1200000 | 1200000 |  |  | 0 |  |  | OBLIGATED |  | 1558580 | 1558580 | 2019 | 3RD QUARTER
STIP | [9 empty] | CLAY | 11-10003 | KY 1850 |  | 2.754 | 2.764 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-1850 BRIDGE OVER PHILLIPS FORK. (026B00087N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [9 empty] | CLAY | 11-10003 | KY 1850 |  | 2.754 | 2.764 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-1850 BRIDGE OVER PHILLIPS FORK. (026B00087N) | C |  | BR/STP | 2020 | 595000 | 368900 |  |  | 226100 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.155 | 2020-01-22 | INCREASE FUND AMOUNT BASED ON NEW ESTIMATE; MOD | STPBRZ | 9030253 | CLAY | 11-10003 | KY 1850 |  | 2.754 | 2.764 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-1850 BRIDGE OVER PHILLIPS FORK. (026B00087N) | C |  | BR/STP | 2020 | 1121825 | 1121825 |  |  | 0 |  |  | OBLIGATED | 100000 | 977135 | 1077135 | 2020 | 2ND QUARTER
STIP | [9 empty] | CLAY | 11-10004 | KY 577 |  | 6.991 | 6.999 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-577 BRIDGE OVER LITTLE SEXTON CREEK. (026B00093N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [9 empty] | CLAY | 11-10004 | KY 577 |  | 6.991 | 6.999 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-577 BRIDGE OVER LITTLE SEXTON CREEK. (026B00093N) | C |  | BR/STP | 2020 | 424000 | 262880 |  |  | 161120 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.021 | 2019-02-04 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030052 | CLAY | 11-10004 | KY 577 |  | 6.991 | 6.999 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-577 BRIDGE OVER LITTLE SEXTON CREEK. (026B00093N) | C |  | STP | 2019 | 561000 | 561000 |  |  | 0 |  |  | OBLIGATED |  | 815730 | 815730 | 2019 | 2ND QUARTER
STIP | [9 empty] | CLAY | 11-10005 | CR 1055 |  | 0.006 | 0.012 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF CR-1055 BRIDGE OVER WILES BRANCH. (026C00010N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [9 empty] | CLAY | 11-10005 | CR 1055 |  | 0.006 | 0.012 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF CR-1055 BRIDGE OVER WILES BRANCH. (026C00010N) | C |  | BR/STP | 2020 | 400000 | 248000 |  |  | 152000 | [5 empty] | 0
STIP | [9 empty] | CLAY | 11-10006 | CR 1117 |  | 0.073 | 0.079 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF ARNETTS FORK ROAD BRIDGE OVER DOUBLE CREEK. (026C00018N) | D |  | BR/STP | 2019 | 140000 | 86800 |  |  | 53200 | [5 empty] | 0
STIP | [9 empty] | CLAY | 11-10006 | CR 1117 |  | 0.073 | 0.079 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF ARNETTS FORK ROAD BRIDGE OVER DOUBLE CREEK. (026C00018N) | C |  | BR/STP | 2020 | 364000 | 225680 |  |  | 138320 | [5 empty] | 0
STIP | [9 empty] | CLAY | 11-10007 | CR 1160 |  | 0.062 | 0.068 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF OTTER CREEK ROAD BRIDGE OVER GOOSE CREEK. (026C00032N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [9 empty] | CLAY | 11-10007 | CR 1160 |  | 0.062 | 0.068 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF OTTER CREEK ROAD BRIDGE OVER GOOSE CREEK. (026C00032N) | C |  | BR/STP | 2020 | 595000 | 368900 |  |  | 226100 | [5 empty] | 0
STIP | [9 empty] | CLAY | 11-10008 | CR 1255 |  | 0.074 | 0.08 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF CR-1255 BRIDGE OVER HORSE CREEK. (026C00070N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030047 | CLAY | 11-10008 | CR 1255 |  | 0.074 | 0.08 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF CR-1255 BRIDGE OVER HORSE CREEK. (026C00070N) | C |  | BR/STP | 2020 | 371000 | 230020 |  |  | 140980 |  |  | OBLIGATED |  | 459245 | 459245 | 2019 | 3RD QUARTER
STIP | [9 empty] | CLAY | 11-10009 | CR 1118 |  | 0.087 | 0.103 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF OLD HIGHWAY 66 BRIDGE OVER RED BIRD RIVER. (026C00099N) | D |  | BR/STP | 2019 | 350000 | 217000 |  |  | 133000 | [5 empty] | 0
STIP | [9 empty] | CLAY | 11-10009 | CR 1118 |  | 0.087 | 0.103 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF OLD HIGHWAY 66 BRIDGE OVER RED BIRD RIVER. (026C00099N) | C |  | BR/STP | 2020 | 2177000 | 1349740 |  |  | 827260 | [5 empty] | 0
STIP | [9 empty] | CLAY | 11-10039 | US 421 |  | 21.204 | 21.21 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF US 421 BRIDGE OVER BRANCH OF ISLAND CREEK. (026B00002N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030068 | CLAY | 11-10039 | US 421 |  | 21.204 | 21.21 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF US 421 BRIDGE OVER BRANCH OF ISLAND CREEK. (026B00002N) | C |  | BR/STP | 2020 | 647500 | 401450 |  |  | 246050 |  |  | OBLIGATED |  | 588408.52 | 588408.52 | 2019 | 3RD QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.123 | 2019-09-06 | ADD PROJECT TO STIP; PARENT NO. 99-65.16 AND 99-65.17; NEW |  |  | CLAY | 11-10065 | CR 1298 |  | 0.019 |  | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES ON CR-1298 OVER LITTLE GOOSE CREEK. (026C00052N) | C |  | BR | 2020 | 385000 | 385000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.155 | 2020-01-22 | ADD PROJECT TO STIP; NEW | STPBRZ | 9030229 | CLAY | 11-10082 | CR 1041 |  | 10.877 |  | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES ON NEWFOUND ROAD (CR 1041) OVER S. FORK KY RIVER. (026C00114N) | C |  | STP | 2020 | 277725 | 277725 |  |  | 0 |  |  | OBLIGATED | 20000 | 242565 | 262565 | 2020 | 2ND QUARTER
STIP | [9 empty] | CLAY | 11-20001 | HR 9006 |  | 13.9 | 16 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF HAL ROGERS DANIEL BOONE PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 13.93 TO MILEPOINT 15.958 | D |  | PM/NH | 2022 | 80000 | 64000 |  |  | 16000 | [5 empty] | 0
STIP | [9 empty] | CLAY | 11-20001 | HR 9006 |  | 13.9 | 16 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF HAL ROGERS DANIEL BOONE PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 13.93 TO MILEPOINT 15.958 | C |  | PM/NH | 2022 | 800000 | 640000 |  |  | 160000 | [5 empty] | 0
STIP | [9 empty] | CLAY | 11-20003 | HR 9006 |  | 19.527 | 28.4 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF HAL ROGERS DANIEL BOONE PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 19.527 TO MILEPOINT 28.4 | D |  | PM/NH | 2019 | 350000 | 280000 |  |  | 70000 | [5 empty] | 0
STIP | [9 empty] | CLAY | 11-20003 | HR 9006 |  | 19.527 | 28.4 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF HAL ROGERS DANIEL BOONE PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 19.527 TO MILEPOINT 28.4 | C |  | PM/NH | 2019 | 3500000 | 2800000 |  |  | 700000 | [5 empty] | 0
STIP | [9 empty] | CLAY | 11-20004 | HR 9006 |  | 28.4 | 31 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF HAL ROGERS DANIEL BOONE PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 28.4 TO MILEPOINT 31 | D |  | PM/NH | 2019 | 100000 | 80000 |  |  | 20000 | [5 empty] | 0
STIP | [9 empty] | CLAY | 11-20004 | HR 9006 |  | 28.4 | 31 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF HAL ROGERS DANIEL BOONE PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 28.4 TO MILEPOINT 31 | C |  | PM/NH | 2019 | 1000000 | 800000 |  |  | 200000 | [5 empty] | 0
STIP | [9 empty] | CLAY | 11-20005 | HR 9006 |  | 31 | 35.08 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF HAL ROGERS DANIEL BOONE PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 31 TO MILEPOINT 35.08 | D |  | PM/NH | 2019 | 160000 | 128000 |  |  | 32000 | [5 empty] | 0
STIP | [9 empty] | CLAY | 11-20005 | HR 9006 |  | 31 | 35.08 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF HAL ROGERS DANIEL BOONE PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 31 TO MILEPOINT 35.08 | C |  | PM/NH | 2019 | 1600000 | 1280000 |  |  | 320000 | [5 empty] | 0
STIP | [9 empty] | CLAY | 11-20006 | HR 9006 |  | 35.08 | 39 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF HAL ROGERS DANIEL BOONE PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 35.08 TO MILEPOINT 39 | D |  | PM/NH | 2022 | 150000 | 120000 |  |  | 30000 | [5 empty] | 0
STIP | [9 empty] | CLAY | 11-20006 | HR 9006 |  | 35.08 | 39 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF HAL ROGERS DANIEL BOONE PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 35.08 TO MILEPOINT 39 | C |  | PM/NH | 2022 | 1500000 | 1200000 |  |  | 300000 | [5 empty] | 0
STIP | [9 empty] | CLINTON | 8-1062 | KY 738 | 0.01 | 6.478 | 6.488 | ASSET MANAGEMENT | AM-BRIDGE (P) | REPLACE BRIDGE OVER CLEAR FORK CREEK ON KY 738 0.2 MI S OF US 127X. (027B00011N)(SR=31.5) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [9 empty] | CLINTON | 8-1062 | KY 738 | 0.01 | 6.478 | 6.488 | ASSET MANAGEMENT | AM-BRIDGE (P) | REPLACE BRIDGE OVER CLEAR FORK CREEK ON KY 738 0.2 MI S OF US 127X. (027B00011N)(SR=31.5) | C |  | BR/STP | 2020 | 525000 | 325500 |  |  | 199500 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.229 | 2020-09-14 | ADD C PHASE TO STIP; PARENT NO. 99-224.14; NEW |  |  | CLINTON | 8-20013 | KY 90 |  | 5.257 | 12.816 | ASSET MANAGEMENT | AM-PAVEMENT(PRI)(P) | RESURFACING OF KY 90 (MP 5.257-12.816) IN CLINTON COUNTY, KY. | C |  | STP | 2020 | 1990000 | 1990000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.161 | 2020-02-21 | ADD PROJECT TO STIP; PARENT NO. 99-911.09; NEW |  |  | CRITTENDEN | 1-984 | KY 120 |  | 8.849 | 9.124 | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALLATION OF HIGH FRICTION SURFACE TREATMENT ON KY 120 FROM 8.849 ON MP 9.124 IN CRITTENDEN COUNTY, KY. (2018BOP) | C |  | SAF | 2020 | 50000 | 50000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | CRITTENDEN | 1-1159 | CR 1085 |  | 0.044 | 0.052 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON CR-1085 (0.048) OVER HUGHES BRANCH 028C00053N | D |  | BR/STP | 2019 | 210000 | 130200 |  |  | 79800 | [5 empty] | 0
STIP | [9 empty] | CRITTENDEN | 1-1159 | CR 1085 |  | 0.044 | 0.052 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON CR-1085 (0.048) OVER HUGHES BRANCH 028C00053N | C |  | BR/STP | 2020 | 546000 | 338520 |  |  | 207480 | [5 empty] | 0
STIP | [9 empty] | CRITTENDEN | 1-10000 | KY 91 |  | 0.678 | 0.694 | RELIABILITY | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-91 BRIDGE OVER CROOKED CREEK. (028B00021N) | D |  | BR/STP | 2019 | 245000 | 151900 |  |  | 93100 | [5 empty] | 0
STIP | [9 empty] | CRITTENDEN | 1-10000 | KY 91 |  | 0.678 | 0.694 | RELIABILITY | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-91 BRIDGE OVER CROOKED CREEK. (028B00021N) | C |  | BR/STP | 2020 | 980000 | 607600 |  |  | 372400 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.123 | 2019-09-06 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD |  |  | CRITTENDEN | 1-10000 | KY 91 |  | 0.678 | 0.694 | RELIABILITY | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-91 BRIDGE OVER CROOKED CREEK. (028B00021N) | C |  | BR | 2020 | 1013713 | 1013713 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | CUMBERLAND | 8-10001 | CR 1012 |  | 1.767 | 1.779 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF WHETSTONE ROAD BRIDGE OVER BIG WHETSTONE CREEK. (029C00057N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [9 empty] | CUMBERLAND | 8-10001 | CR 1012 |  | 1.767 | 1.779 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF WHETSTONE ROAD BRIDGE OVER BIG WHETSTONE CREEK. (029C00057N) | C |  | BR/STP | 2020 | 556500 | 345030 |  |  | 211470 | [5 empty] | 0
STIP | [9 empty] | CUMBERLAND | 8-10009 | KY 379 |  | 3.285 | 3.315 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 379 BRIDGE OVER BIG WILLIS CREEK. (029B00005N) | D |  | BR/STP | 2019 | 129500 | 80290 |  |  | 49210 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030207 | CUMBERLAND | 8-10009 | KY 379 |  | 3.285 | 3.315 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 379 BRIDGE OVER BIG WILLIS CREEK. (029B00005N) | C |  | BR/STP | 2020 | 952000 | 590240 |  |  | 361760 |  |  | OBLIGATED |  | 1566556.28 | 1566556.28 | 2019 | 4TH QUARTER
|  |  |  | AMENDMENT | 2018.001 | 2019-02-08 | TIP REFERENCE FY 19-24 RESOLUTION DATED 1/29/19. NEW |  |  | DAVIESS | [22 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.225 | 2020-08-25 | TIP FY 19-24, ADMIN MOD#7; ADD PROJECT TO STIP; NEW |  |  | DAVIESS | 2-229 | KY 298 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT INTERSECTION AT FAIRVIEW DRIVE (KY 3143) AND KY 298. | D |  | STP | 2021 | 500000 | 500000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.225 | 2020-08-25 | TIP FY 19-24, ADMIN MOD#7; ADD PROJECT TO STIP; NEW |  |  | DAVIESS | 2-229 | KY 298 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT INTERSECTION AT FAIRVIEW DRIVE (KY 3143) AND KY 298. | R |  | STP | 2021 | 670000 | 670000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.225 | 2020-08-25 | TIP FY 19-24, ADMIN MOD#7; ADD PROJECT TO STIP; NEW |  |  | DAVIESS | 2-229 | KY 298 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT INTERSECTION AT FAIRVIEW DRIVE (KY 3143) AND KY 298. | U |  | STP | 2021 | 1090000 | 1090000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.225 | 2020-08-25 | TIP FY 19-24, ADMIN MOD#7; ADD PROJECT TO STIP; NEW |  |  | DAVIESS | 2-229 | KY 298 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT INTERSECTION AT FAIRVIEW DRIVE (KY 3143) AND KY 298. | C |  | STP | 2022 | 2170000 | 2170000 | [8 empty] | 0
STIP | [7 empty] | STP | 5053029 | DAVIESS | 2-237 | US 60 | 0.592 | 5.69 | 6.282 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT ON US 60 BETWEEN OAKFORD RD LOOP (CR 1370) TO ADDRESS FLOODING PROBLEM IN THE VICINITY OF THE KIMBERLY-CLARK PLANT (14CCR)(18CCN) | C |  | STP | 2019 | 2000000 | 2000000 |  |  | 0 |  |  | OBLIGATED | 1750000 | 1588900 | 3338900 | 2019 | 3RD QUARTER
[8 empty] | PL | 0020028 | DAVIESS | 2-402 | KY 2831 US 431 |  |  |  | RELIABILITY | SCOPING STUDY (O) | ACCESS MANAGEMENT AND SAFETY STUDY ALONG FREDERICA STREET IN OWENSBORO (2018BOP). | P |  | PL | 2020 | 250000 | 250000 |  |  | 0 |  |  | OBLIGATED | 250000 |  | 250000 | 2020 | 3RD QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.067 | 2019-05-13 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW - THIS PROJECT IS IN THE OWENSBORO-DAVIESS CO MPO TIP FY 19-24, GROUPED PROJECTS TABLE I, PG 8 | HSIP | 4311045 | DAVIESS | 2-919 | US 431 |  | 0 | 10.246 | SAFETY | SAFETY-HAZARD ELIM(P) | REPLACEMENT OF TARGETED GUARDRAIL END TREATMENTS ON US 431 FROM MP 0.000 TO MP 10.246 (2018BOP). | C |  | SAF | 2019 | 345000 | 345000 |  |  | 0 |  |  | OBLIGATED | 343000 |  | 343000 | 2019 | 3RD QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.073 | 2019-05-14 | TIP FY 19-24; ADMIN MOD#1; ADD PROJECT TO STIP; NEW | HSIP | 9010387 | DAVIESS | 2-923 | CR 1215 |  | 0.1 | 0.6 | SAFETY | SAFETY-HAZARD ELIM(P) | HIGH FRICTION SURFACE TREATMENT ON CR 1215 FROM MP 0.10 TO MP 0.60 IN DAVIESS COUNTY. (2018BOP)(MATCH PROVIDED BY DAVIESS COUNTY) | C |  | SAF | 2019 | 90059 | 90059 |  |  | 0 |  |  | OBLIGATED | 81000 |  | 81000 | 2019 | 3RD QUARTER
STIP | [9 empty] | DAVIESS | 2-2092.1 | WN 9007 |  | 61.557 | 72.264 | ECONOMIC DEVELOPMENT | RECONSTRUCTION(O) | I-65 SPUR CORRIDOR; MODERNIZATION OF EXISTING NATCHER PARKWAY FROM THE OHIO-BUTLER COUNTY LINE (MP 37.143) TO THE US-60 INTERCHANGE (MP 72.264) IN OWENSBORO. (2016BOP) | R |  | NH | 2019 | 200000 | 200000 |  |  | 0 | [5 empty] | 0
[8 empty] | STP | 5078015 | DAVIESS | 2-8300 | KY 54 |  | 2.47 | 8.003 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE KY-54 FROM WEST OF THE US-60 BYPASS TO CR-1021 (JACK HINTON ROAD). (06CCN)(10CCR)(12CCR)(14CCR)(16CCR) | R |  | STP | 2019 | [7 empty] | OBLIGATED |  | 7000000 | 7000000 | 2019 | 1ST QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.274 | 2021-02-04 | ADD U PHASE TO STIP; NEW; OWENSBORO-DAVIESS CO MPO AREA TIP FY 19-24, PAGE 11. |  |  | DAVIESS | 2-8300 | KY 54 |  | 2.47 | 8.003 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE KY-54 FROM WEST OF THE US-60 BYPASS TO CR-1021 (JACK HINTON ROAD). (06CCN)(10CCR)(12CCR)(14CCR)(16CCR) | U |  | STP | 2021 | 5750000 | 5750000 | [8 empty] | 0
STIP | [9 empty] | DAVIESS | 2-8813 | CR 1053 | 0.004 | 1 | 1.014 | ASSET MANAGEMENT | AM-BRIDGE (P) | GRAVES LANE BRIDGE REPLACEMENT-0.2 MI E JCT KY 405 (MM 1.005-1.009) OVER ALLGOOD DITCH. (14CCN) 030C00016N | C |  | BR/STP | 2020 | 619500 | 384090 |  |  | 235410 | [5 empty] | 0
STIP | [9 empty] | DAVIESS | 2-8854 | KY 3143 | 1.129 | 1.829 | 2.958 | RELIABILITY | MINOR WIDENING(O) | IMPROVE KY-3143 FROM KY-3335 TO KY 54. (14CCN) | D |  | STP | 2021 | 680000 | 544000 |  |  | 136000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.015 | 2019-01-25 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; OWENSBORO-DAVIESS CO MPO TIP FY 19-24, GROUP PROJECTS, TABLE I, PG 8; NEW | HSIP | 9010347 | DAVIESS, MUHLENBERG | 2-9012 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | PRELIMINARY DESIGN AND STUDY TO DETERMINE LOW COST IMPROVEMENTS AT VARIOUS INTERSECTIONS WITHIN DISTRICT 2. (2018BOP) | D |  | SAF | 2019 | 200000 | 200000 |  |  | 0 |  |  | OBLIGATED | 200000 |  | 200000 | 2019 | 2ND QUARTER
STIP | [9 empty] | DAVIESS | 2-10002 | CR 1068 |  | 0.073 | 0.08 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF ROCKPORT FERRY RD BRIDGE OVER KELLY CREEK. (030C00021N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [9 empty] | DAVIESS | 2-10002 | CR 1068 |  | 0.073 | 0.08 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF ROCKPORT FERRY RD BRIDGE OVER KELLY CREEK. (030C00021N) | C |  | BR/STP | 2020 | 647500 | 401450 |  |  | 246050 | [5 empty] | 0
STIP | [9 empty] | DAVIESS | 2-10003 | CR 1129 |  | 3.547 | 3.552 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF OLD KY 54 BRIDGE OVER BR OF N FK PANTHER CREEK. (030C00029N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [9 empty] | DAVIESS | 2-10003 | CR 1129 |  | 3.547 | 3.552 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF OLD KY 54 BRIDGE OVER BR OF N FK PANTHER CREEK. (030C00029N) | C |  | BR/STP | 2020 | 647500 | 401450 |  |  | 246050 | [5 empty] | 0
STIP | [9 empty] | DAVIESS | 2-10004 | CR 1257 |  | 0.703 | 0.709 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF LYDANNE BRIDGE S BRIDGE OVER FLAT LICK CREEK. (030C00069N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [9 empty] | DAVIESS | 2-10004 | CR 1257 |  | 0.703 | 0.709 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF LYDANNE BRIDGE S BRIDGE OVER FLAT LICK CREEK. (030C00069N) | C |  | BR/STP | 2020 | 717500 | 444850 |  |  | 272650 | [5 empty] | 0
STIP | [9 empty] | DAVIESS | 2-10020 | KY 2262 |  | 0.699 | 1.494 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES WITH GLOVER CARY BRIDGE OVER OHIO RIVER. JOINT PROJECT WITH INDIANA. (030B00118N)(BSBP) | D |  | BR/STP | 2019 | 200000 | 124000 |  |  | 76000 | [5 empty] | 0
STIP | [9 empty] | DAVIESS | 2-10020 | KY 2262 |  | 0.699 | 1.494 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES WITH GLOVER CARY BRIDGE OVER OHIO RIVER. JOINT PROJECT WITH INDIANA. (030B00118N)(BSBP) | C |  | BR/STP | 2020 | 2250000 | 1395000 |  |  | 855000 | [5 empty] | 0
STIP | [9 empty] | DAVIESS | 2-10021 | US 231 |  | 13.99 | 14.844 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES WITH NATCHER BRIDGE OVER OHIO RIVER. JOINT PROJECT WITH INDIANA. (030B00164N)(BSBP) | D |  | BR/NH | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [9 empty] | DAVIESS | 2-10021 | US 231 |  | 13.99 | 14.844 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES WITH NATCHER BRIDGE OVER OHIO RIVER. JOINT PROJECT WITH INDIANA. (030B00164N)(BSBP) | C |  | BR/NH | 2020 | 10000000 | 6200000 |  |  | 3800000 | [5 empty] | 0
STIP | [9 empty] | DAVIESS | 2-10023 | KY 764 |  | 2.261 | 2.271 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 764 BRIDGE OVER UNNAMED STREAM. (030B00111N) | D |  | BR/STP | 2019 | 70000 | 43400 |  |  | 26600 | [5 empty] | 0
STIP | [9 empty] | DAVIESS | 2-10023 | KY 764 |  | 2.261 | 2.271 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 764 BRIDGE OVER UNNAMED STREAM. (030B00111N) | C |  | BR/STP | 2020 | 350000 | 217000 |  |  | 133000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.021 | 2019-02-04 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; OWENSBORO-DAVIESS COUNTY TIP MOD#13 | STPBRZ | 9030013 | DAVIESS | 2-10023 | KY 764 |  | 2.261 | 2.271 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 764 BRIDGE OVER UNNAMED STREAM. (030B00111N) | C |  | STP | 2019 | 670000 | 670000 |  |  | 0 |  |  | OBLIGATED |  | 603850 | 603850 | 2019 | 2ND QUARTER
STIP | YES | [8 empty] | DAVIESS | 2-20017 | KY 81 |  | 11.891 | 13.32 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | D |  | PM/NH | 2022 | 250000 | 200000 |  |  | 50000 | [5 empty] | 0
STIP | YES | [8 empty] | DAVIESS | 2-20017 | KY 81 |  | 11.891 | 13.32 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | C |  | PM/NH | 2022 | 2500000 | 2000000 |  |  | 500000 | [5 empty] | 0
STIP | YES | [8 empty] | DAVIESS | 2-20018 | KY 331 |  | 0 | 0.435 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC & AC PAVEMENT | D |  | PM/STP | 2021 | 50000 | 40000 |  |  | 10000 | [5 empty] | 0
STIP | YES | [8 empty] | DAVIESS | 2-20018 | KY 331 |  | 0 | 0.435 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC & AC PAVEMENT | C |  | PM/STP | 2021 | 500000 | 400000 |  |  | 100000 | [5 empty] | 0
STIP | [9 empty] | DAVIESS | 2-20019 | KY 2155 |  | 0 | 1.991 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | D |  | PM/NH | 2019 | 150000 | 120000 |  |  | 30000 | [5 empty] | 0
STIP | [9 empty] | DAVIESS | 2-20019 | KY 2155 |  | 0 | 1.991 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | C |  | PM/NH | 2019 | 1500000 | 1200000 |  |  | 300000 | [5 empty] | 0
STIP | [9 empty] | DAVIESS | 2-20020 | WN 9007 |  | 61.553 | 66.08 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF WILLIAM H. NATCHER PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 61.553 TO MILEPOINT 66.08 | C |  | PM/NH | 2020 | 4238000 | 3390400 |  |  | 847600 | [5 empty] | 0
STIP | [9 empty] | DAVIESS | 2-20021 | WN 9007 |  | 66.08 | 72.26 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF WILLIAM H. NATCHER PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 66.08 TO MILEPOINT 72.26 | C |  | PM/NH | 2020 | 5768000 | 4614400 |  |  | 1153600 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.218 | 2020-08-28 | OWENSBORO-DAVIESS CO MPO AREA TIP FY 19-24, GROUPED PROJECTS, PG 7-8, TABLE 1 (SEE ITEM# 2-20018, TABLE 5, PG 12). |  |  | DAVIESS | 2-20045 | KY 331 |  | 0 | 0.44 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | PAVEMENT RESURFACING ON KY 331 FROM MP 0.000 TO MP 0.440 IN DAVIESS COUNTY. | C |  | PM/NH | 2020 | 150000 | 150000 |  |  | 0 | [5 empty] | 0
STIP | YES | [8 empty] | DAVIESS | 2-20047 | US 60 | 3.77 | 23.77 | 27.54 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION ON US-60 FROM MILEPOINT 23.77 TO MILEPOINT 27.54 | C |  | PM/NH | 2022 | 1609000 | 1287200 |  |  | 321800 | [5 empty] | 0
STIP | [9 empty] | EDMONSON | 3-10012 | KY 743 |  | 7.028 | 7.034 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 743 BRIDGE OVER BEAVER DAM CREEK. (031B00004N) | D |  | BR/STP | 2019 | 157500 | 97650 |  |  | 59850 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030104 | EDMONSON | 3-10012 | KY 743 |  | 7.028 | 7.034 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 743 BRIDGE OVER BEAVER DAM CREEK. (031B00004N) | C |  | BR/STP | 2020 | 402500 | 249550 |  |  | 152950 |  |  | OBLIGATED |  | 486600 | 486600 | 2019 | 3RD QUARTER
STIP | [9 empty] | EDMONSON | 3-20011 | I 65 |  | 43.307 | 43.6 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-065 BOTH DIRECTION(S) FROM MILEPOINT 43.307 TO MILEPOINT 43.6 | D |  | PM/NH | 2019 | 40000 | 32000 |  |  | 8000 | [5 empty] | 0
STIP | [9 empty] | EDMONSON | 3-20011 | I 65 |  | 43.307 | 43.6 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-065 BOTH DIRECTION(S) FROM MILEPOINT 43.307 TO MILEPOINT 43.6 | C |  | PM/NH | 2019 | 400000 | 320000 |  |  | 80000 | [5 empty] | 0
STIP | [9 empty] | EDMONSON | 3-20022 | US 31W | 8 | 0 | 8 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION ON US-31W FROM MILEPOINT 0.00 TO MILEPOINT 8.00 | C |  | PM/NH | 2022 | 1301000 | 1040800 |  |  | 260200 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.306 | 2021-06-16 | ADD D PHASE TO STIP; NEW |  |  | EDMONSON | 3-80107 | KY 259 |  | 15.633 | 22.24 | RELIABILITY | SAFETY (P) | IMPROVE SAFETY AND MOBILITY ON KY 259 FROM NORTH OF KYROCK ROAD TO THE GRAYSON COUNTY LINE. (2020CCN) | D |  | SPP | 2021 | 270100 | 100 |  |  | 270000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.074 | 2019-05-14 | ADD PROJECT TO STIP; NEW |  |  | EDMONSON | N/A |  |  |  |  | RELIABILITY | FERRY OPERATION(P) | REHABILITATE AND UPGRADE GREEN RIVER FERRY CROSSING. | C |  | FBP | 2019 | 155665 | 124532 | [8 empty] | 0
STIP | [9 empty] | ELLIOTT | 9-192.01 | KY 32 | 6.656 | 2 | 8.656 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE KY-32 FROM WEST OF STEGALL COLD SPRING ROAD TO KY-7 NEAR NEWFOUNDLAND. (PRIORITY SECTION I)(06CCR) (08CCR) (10CCR)(12CCR)(14CCR)(16CCR)(18CCR) | U |  | STP | 2022 | 5000000 | 4000000 |  |  | 1000000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.321 | 2021-08-17 | ADD R PHASE TO STIP; PARENT NO. 9-192.00; NEW |  |  | ELLIOTT | 9-192.01 | KY 32 | 6.656 | 2 | 8.656 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE KY-32 FROM WEST OF STEGALL COLD SPRING ROAD TO KY-7 NEAR NEWFOUNDLAND. (PRIORITY SECTION I)(06CCR) (08CCR) (10CCR)(12CCR)(14CCR)(16CCR)(18CCR) | R |  | STP | 2021 | 3665000 | 3665000 | [8 empty] | 0
STIP | [9 empty] | ELLIOTT | 9-192.02 | KY 32 | 6.656 | 2 | 8.656 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT KY-32 FROM 0.408 MILES WEST OF STEGALL COLD SPRING ROAD TO KY-7 NEAR NEWFOUNDLAND. (PRIORITY SECTION I)(16CCR)(18CCN) | R |  | STP | 2021 | 3820000 | 3056000 |  |  | 764000 | [5 empty] | 0
STIP | [9 empty] | ELLIOTT | 9-192.02 | KY 32 | 6.656 | 2 | 8.656 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT KY-32 FROM 0.408 MILES WEST OF STEGALL COLD SPRING ROAD TO KY-7 NEAR NEWFOUNDLAND. (PRIORITY SECTION I)(16CCR)(18CCN) | C |  | STP | 2022 | 15500000 | 12400000 |  |  | 3100000 | [5 empty] | 0
STIP | [9 empty] | ELLIOTT | 9-228 | KY 7 | 6.956 | 0 | 6.956 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE KY-7 FROM SOUTH CITY LIMITS OF SANDY HOOK TOWARD WRIGLEY. (12CCR)(16CCR)(18CCR) | R |  | STP | 2022 | 6620000 | 5296000 |  |  | 1324000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.21 | 2020-07-31 | ADD D PHASE TO STIP; NEW |  |  | ELLIOTT | 9-228.3 | KY 7 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | IMPROVE KY-7 FROM SOUTH CITY LIMITS OF SANDY HOOK TOWARD WRIGLEY TO KY 11 AT WRIGLEY. (12CCR)(16CCR)(18CCR) | D |  | STP | 2020 | 300000 | 300000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.3 | 2021-05-28 | ADD R PHASE TO STIP; PARENT NO. 9-228.00; NEW |  |  | ELLIOTT | 9-228.3 | KY 7 |  | 6.5 | 6.9 | RELIABILITY | RECONSTRUCTION(O) | 3-LANE CURB AND GUTTER IN THE VICINITY OF ELLIOT COUNTY SCHOOLS IN SANDY HOOK. (2020CCR) | R |  | STP | 2021 | 891000 | 891000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.3 | 2021-05-28 | ADD U PHASE TO STIP; PARENT NO. 9-228.00; NEW |  |  | ELLIOTT | 9-228.3 | KY 7 |  | 6.5 | 6.9 | RELIABILITY | RECONSTRUCTION(O) | 3-LANE CURB AND GUTTER IN THE VICINITY OF ELLIOT COUNTY SCHOOLS IN SANDY HOOK. (2020CCR) | U |  | STP | 2021 | 510000 | 510000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | ELLIOTT | 9-8802 | KY 32 | 1 | 9.2 | 10.2 | RELIABILITY | MAJOR WIDENING(O) | KY-32 FROM 9.2 MILE MARKER TO 10.2 MILE MARKER WIDENING. (14CCN)(16CCR)(18CCN) | R |  | STP | 2022 | 480000 | 384000 |  |  | 96000 | [5 empty] | 0
STIP | [9 empty] | ELLIOTT | 9-10004 | CR 1206 |  | 0.902 | 0.942 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF CR 1206 BRIDGE OVER LITTLE SANDY. (030C00032N) | D |  | BR/STP | 2019 | 455000 | 282100 |  |  | 172900 | [5 empty] | 0
STIP | [9 empty] | ELLIOTT | 9-10004 | CR 1206 |  | 0.902 | 0.942 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF CR 1206 BRIDGE OVER LITTLE SANDY. (030C00032N) | C |  | BR/STP | 2020 | 1663000 | 1031060 |  |  | 631940 | [5 empty] | 0
STIP | [9 empty] | ESTILL | 10-206 | KY 2459 | 0.373 | 0 | 0.373 | SAFETY | SPOT IMPROVEMENTS(O) | IMPROVE SAFETY ON KY-2459 (CARHARTT AVE.) FROM KY-89 TO THE RAILROAD BRIDGE.(18CCR) | D |  | STP | 2020 | 250000 | 250000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | ESTILL | 10-206 | KY 2459 | 0.373 | 0 | 0.373 | SAFETY | SPOT IMPROVEMENTS(O) | IMPROVE SAFETY ON KY-2459 (CARHARTT AVE.) FROM KY-89 TO THE RAILROAD BRIDGE.(18CCR) | R |  | STP | 2021 | 250000 | 200000 |  |  | 50000 | [5 empty] | 0
STIP | [9 empty] | ESTILL | 10-206 | KY 2459 | 0.373 | 0 | 0.373 | SAFETY | SPOT IMPROVEMENTS(O) | IMPROVE SAFETY ON KY-2459 (CARHARTT AVE.) FROM KY-89 TO THE RAILROAD BRIDGE.(18CCR) | U |  | STP | 2021 | 250000 | 200000 |  |  | 50000 | [5 empty] | 0
STIP | [9 empty] | ESTILL | 10-207 | KY 89 | 2.622 | 19.806 | 22.428 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE GEOMETRICS ON KY-89 IN ESTILL COUNTY FROM KY-1886 TO THE ESTILL/CLARK COUNTY LINE. | D |  | STP | 2021 | 1200000 | 960000 |  |  | 240000 | [5 empty] | 0
STIP | [7 empty] | STP | 6000139 | ESTILL | 10-208 | KY 1645 | 0.4 | 1.7 | 2.1 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE SAFETY AND MOBILITY ON KY-1645 (KIRKLAND AVE) NEAR CR-1087 (LOCK 12 ROAD). | D |  | STP | 2019 | 100000 | 100000 |  |  | 0 |  |  | OBLIGATED | 100000 |  | 100000 | 2019 | 1ST QUARTER
STIP | [7 empty] | STP | 6000139 | ESTILL | 10-208 | KY 1645 | 0.4 | 1.7 | 2.1 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE SAFETY AND MOBILITY ON KY-1645 (KIRKLAND AVE) NEAR CR-1087 (LOCK 12 ROAD). | R |  | STP | 2020 | 100000 | 100000 |  |  | 0 |  |  | OBLIGATED | 30000 |  | 30000 | 2019 | 4TH QUARTER
STIP | [7 empty] | STP | 6000139 | ESTILL | 10-208 | KY 1645 | 0.4 | 1.7 | 2.1 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE SAFETY AND MOBILITY ON KY-1645 (KIRKLAND AVE) NEAR CR-1087 (LOCK 12 ROAD). | U |  | STP | 2020 | 50000 | 50000 |  |  | 0 |  |  | OBLIGATED | 20000 |  | 20000 | 2020 | 3RD QUARTER
STIP | [7 empty] | STP | 6000139 | ESTILL | 10-208 | KY 1645 | 0.4 | 1.7 | 2.1 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE SAFETY AND MOBILITY ON KY-1645 (KIRKLAND AVE) NEAR CR-1087 (LOCK 12 ROAD). | C |  | STP | 2020 | 320000 | 320000 |  |  | 0 |  |  | OBLIGATED | 165600 |  | 165600 | 2020 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.015 | 2019-01-25 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 5261001 | ESTILL | 10-9014 | KY 82 |  | 0 | 5.029 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 82 IN ESTILL COUNTY, KY. (2018BOP) | D |  | SAF | 2019 | 275000 | 275000 |  |  | 0 |  |  | OBLIGATED |  | 275000 | 275000 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.238 | 2020-09-25 | ADD R PHASE TO STIP; PARENT NO. 99-911.08; NEW |  |  | ESTILL | 10-9014 | KY 82 |  | 0 | 5.029 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 82 IN ESTILL COUNTY, KY. (2018BOP) | R |  | SAF | 2020 | 75000 | 75000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.238 | 2020-09-25 | ADD U PHASE TO STIP; PARENT NO. 99-911.08; NEW |  |  | ESTILL | 10-9014 | KY 82 |  | 0 | 5.029 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 82 IN ESTILL COUNTY, KY. (2018BOP) | U |  | SAF | 2020 | 125000 | 125000 | [8 empty] | 0
STIP | [9 empty] | ESTILL | 10-10012 | KY 794 |  | 0.298 | 0.308 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 794 BRIDGE OVER WHITE OAK CREEK. (033B00038N) | D |  | BR/STP | 2019 | 245000 | 151900 |  |  | 93100 | [5 empty] | 0
STIP | [9 empty] | ESTILL | 10-10012 | KY 794 |  | 0.298 | 0.308 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 794 BRIDGE OVER WHITE OAK CREEK. (033B00038N) | C |  | BR/STP | 2020 | 735000 | 455700 |  |  | 279300 | [5 empty] | 0
|  |  |  | AMENDMENT | 2018.009 | 2020-12-01 | TIP REFERENCE FY 2021-2024 RESOLUTION DATED 11/9/20. NEW |  |  | FAYETTE
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.268 | 12/32/20 | TIP FY 21-24, ADMIN MOD#1; ADD PROJECT TO STIP; NEW |  |  | FAYETTE | TBD | Newtown Pike Extension | [5 empty] | NEWTOWN PIKE EXTENSION W MAIN TO S LIMESTONE. | C |  | STP | 2021 | 4855000 | 4655000 |  |  |  | 200000
STIP | YES | [8 empty] | FAYETTE | 7-113.02 | KY 4 | 1 | 7.26 | 8.26 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE NEW CIRCLE ROAD FROM LEESTOWN ROAD TO NEAR GEORGETOWN ROAD. (12CCR)(14CCR)(18CCR) | R |  | NH | 2021 | 1300000 | 1040000 |  |  | 260000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.116 | 2019-08-09 | TIP FY 17-20; ADMIN MOD#20, UPDATE FUND TYPE & FY; MOD |  | 2681037 | FAYETTE | 7-113.02 | KY 4 | 1 | 7.26 | 8.26 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE NEW CIRCLE ROAD FROM LEESTOWN ROAD TO NEAR GEORGETOWN ROAD. (12CCR)(14CCR)(18CCR) | R |  | SLX | 2019 | 1300000 | 1040000 |  |  | 260000 |  |  | OBLIGATED | 1040000 |  | 1040000 | 2020 | 3RD QUARTER
STIP | YES | [8 empty] | FAYETTE | 7-113.02 | KY 4 | 1 | 7.26 | 8.26 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE NEW CIRCLE ROAD FROM LEESTOWN ROAD TO NEAR GEORGETOWN ROAD. (12CCR)(14CCR)(18CCR) | U |  | NH | 2021 | 1500000 | 1200000 |  |  | 300000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.116 | 2019-08-09 | TIP FY 17-20; ADMIN MOD#20, UPDATE FUND AMOUNT; MOD |  |  | FAYETTE | 7-113.02 | KY 4 | 1 | 7.26 | 8.26 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE NEW CIRCLE ROAD FROM LEESTOWN ROAD TO NEAR GEORGETOWN ROAD. (12CCR)(14CCR)(18CCR) | U |  | NH | 2021 |  | 3000000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.134 | 2019-09-26 | TIP FY 17-20; ADMIN MOD#22, CHANGE FUND AMOUNT AND UPDATE FISCAL YEAR FROM 2021 TO 2020; MOD |  |  | FAYETTE | 7-113.02 | KY 4 | 1 | 7.26 | 8.26 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE NEW CIRCLE ROAD FROM LEESTOWN ROAD TO NEAR GEORGETOWN ROAD. (12CCR)(14CCR)(18CCR) | U |  | SLX | 2020 | 3000000 | 3000000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.116 | 2019-08-09 | TIP FY 17-20; ADMIN MOD#20, ADD C PHASE TO STIP; NEW |  |  | FAYETTE | 7-113.02 | KY 4 | 1 | 7.26 | 8.26 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE NEW CIRCLE ROAD FROM LEESTOWN ROAD TO NEAR GEORGETOWN ROAD. (12CCR)(14CCR)(18CCR) | C |  | NH | 2021 | 11780000 | 11780000 |  |  | 0 | [5 empty] | 0
STIP | YES | [8 empty] | FAYETTE | 7-113.03 | KY 4 | 1 | 7.26 | 8.26 | RELIABILITY | PREFINANCD CONVRSN(O) | IMPROVE NEW CIRCLE ROAD FROM LEESTOWN ROAD TO NEAR GEORGETOWN ROAD. (12CCR)(14CCR) | U |  | NH | 2021 | 1500000 | 1200000 |  |  | 300000 | [5 empty] | 0
STIP | [9 empty] | FAYETTE | 7-224.1 | CS 4174 | 1.9 | 0 | 2.01 | RELIABILITY | MINOR WIDENING(O) | CLAYS MILL ROAD; WIDEN FROM HARRODSBURG ROAD TO NEW CIRCLE ROAD (SECTION 1) (LFUCG T.I.P.) (LOCAL MATCH) (ALL WORK BY LFUCG) (CONSTRUCTION SEQU. 2) (SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | C |  | SLX | 2019 | 11000000 | 8800000 |  |  |  | 2200000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.116 | 2019-08-09 | TIP FY 17-20; ADMIN MOD#20, UPDATE FUNDING TYPE TO CMAQ; MOD (SEE CMAQ SPREADSHEET) |  |  | FAYETTE | 7-224.1 | CS 4174 | 1.9 | 0 | 2.01 | RELIABILITY | MINOR WIDENING(O) | CLAYS MILL ROAD; WIDEN FROM HARRODSBURG ROAD TO NEW CIRCLE ROAD (SECTION 1) (LFUCG T.I.P.) (LOCAL MATCH) (ALL WORK BY LFUCG) (CONSTRUCTION SEQU. 2) (SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | C |  |  | 2019
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.185 | 2020-05-06 | TIP FY 20-25; ADMIN MOD#28; |  |  | FAYETTE | 7-227.00 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | VARIOUS CONTINUING PROGRAMS: IMPLEMENT THE UNIFIED PLANNING WORK PROGRAM (UPWP) TO INCLUDE UPDATING AND IMPLEMENTING THE METROPOLITAN TRANSPORTATION PLAN, BICYCLE & PEDESTRIAN MASTER PLAN AND CONGESTION MANAGEMENT PROCESS; PUBLIC OUTREACH & PARTICIPATION; TRAFFIC & LAND USE IMPACT ANALYSIS; AND STAFF DEVELOPMENT. | C |  | SLX | 2020 | 1720 | 1376 |  |  |  | 344 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.185 | 2020-05-06 | TIP FY 20-25; ADMIN MOD#28; |  |  | FAYETTE | 7-227.00 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | ITS & CMS TRAFFIC IMPROVEMENTS - INTELLIGENT TRANSPORTATION SYSTEMS (ITS) & CONGESTION MANAGEMENT SYSTEM (CMS) IMPROVEMENTS AND ACTIVITIES. | C |  | SLX | 2020 | 2400 | 1920 |  |  |  | 480 |  |  |  |  | 0
STIP | [9 empty] | FAYETTE | 7-227.07 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | VARIOUS 'SLX' CONTINUING PROGRAM PROJECTS (RIDESHARE/MOBILITY, AIR QUALITY PLANNING, TRAFFIC SIGNAL) FOR FY 2018. (LOCAL MATCH) (ALL WORK BY LFUCG) (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | C |  | SLX | 2019 | 730000 | 584000 |  |  |  | 146000 |  |  |  |  | 0
STIP | [9 empty] | FAYETTE | 7-227.08 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | VARIOUS 'SLX' CONTINUING PROGRAM PROJECTS (RIDESHARE/MOBILITY, AIR QUALITY PLANNING, TRAFFIC SIGNAL) FOR FY 2019. (LOCAL MATCH) (ALL WORK BY LFUCG) (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | C |  | SLX | 2019 | 756000 | 604800 |  |  |  | 151200 |  |  |  |  | 0
STIP | [9 empty] | FAYETTE | 7-227.09 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | VARIOUS 'SLX' CONTINUING PROGRAM PROJECTS (RIDESHARE/MOBILITY, AIR QUALITY PLANNING, TRAFFIC SIGNAL) FOR FY 2020. (LOCAL MATCH) (ALL WORK BY LFUCG) (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | C |  | SLX | 2020 | 756000 | 604800 |  |  |  | 151200 |  |  |  |  | 0
STIP | [9 empty] | FAYETTE | 7-227.1 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | DEDICATED FEDERAL-AID STP FUNDS EARMARKED FOR LEXINGTON URBANIZED AREA AND SUBJECT TO MPO CONTROL FOR FY 2018. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C |  | SLX | 2019 | 12400000 | 9920000 |  |  |  | 2480000 |  |  |  |  | 0
STIP | [9 empty] | FAYETTE | 7-227.13 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | DEDICATED FEDERAL-AID STP FUNDS EARMARKED FOR LEXINGTON URBANIZED AREA AND SUBJECT TO MPO CONTROL FOR FY 2019. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C |  | SLX | 2019 | 8000000 | 6400000 |  |  |  | 1600000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.055 | 2019-04-25 | TIP FY 17-20, ADMIN MOD#17; UPDATE DESCRIPTION & FUND AMOUNTS; MOD |  |  | FAYETTE | 7-227.13 | I 75 |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | I-75 SB EXIT RAMP AT MAN O' WAR BLVD. - SAFETY PROJECT TO WIDEN I-75 SB EXIT RAMP AT MAN O' WAR TO CONSTRUCT LEFT TURN LANES AND INSTALL TRAFFIC SIGNAL. | C |  | SLX | 2019 | 550000 | 550000 |  |  |  | 0 |  |  |  |  | 0
STIP | [9 empty] | FAYETTE | 7-227.14 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | DEDICATED FEDERAL-AID STP FUNDS EARMARKED FOR LEXINGTON URBANIZED AREA AND SUBJECT TO MPO CONTROL FOR FY 2020. (FUNDING SUBJECT TO FISCAL CONTRAINT PENDING MPO TIP) | C |  | SLX | 2020 | 8200000 | 6560000 |  |  |  | 1640000 |  |  |  |  | 0
STIP | [9 empty] | FAYETTE | 7-227.15 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | DEDICATED FEDERAL-AID STP FUNDS EARMARKED FOR LEXINGTON URBANIZED AREA AND SUBJECT TO MPO CONTROL FOR FY 2021. (FUNDING SUBJECT TO FISCAL CONTRAINT PENDING MPO TIP) | C |  | SLX | 2021 | 8200000 | 6560000 |  |  |  | 1640000 |  |  |  |  | 0
STIP | [9 empty] | FAYETTE | 7-227.16 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | DEDICATED FEDERAL-AID STP FUNDS EARMARKED FOR LEXINGTON URBANIZED AREA AND SUBJECT TO MPO CONTROL FOR FY 2022. (FUNDING SUBJECT TO FISCAL CONTRAINT PENDING MPO TIP) | C |  | SLX | 2022 | 8200000 | 6560000 |  |  |  | 1640000 |  |  |  |  | 0
STIP | [9 empty] | FAYETTE | 7-227.17 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | VARIOUS 'SLX' CONTINUING PROGRAM PROJECTS (RIDESHARE/MOBILITY, AIR QUALITY PLANNING, TRAFFIC SIGNAL) FOR FY 2021. (LOCAL MATCH) (ALL WORK BY LFUCG) (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | C |  | SLX | 2021 | 756000 | 604800 |  |  |  | 151200 |  |  |  |  | 0
STIP | [9 empty] | FAYETTE | 7-227.18 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | VARIOUS 'SLX' CONTINUING PROGRAM PROJECTS (RIDESHARE/MOBILITY, AIR QUALITY PLANNING, TRAFFIC SIGNAL) FOR FY 2022. (LOCAL MATCH) (ALL WORK BY LFUCG) (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | C |  | SLX | 2022 | 756000 | 604800 |  |  |  | 151200 |  |  |  |  | 0
STIP | [9 empty] | FAYETTE | 7-229.2 |  | 0.3 |  |  | SAFETY | BIKE/PED FACIL(O) | SOUTH ELKHORN TRAIL IN LEXINGTON (PRIORITY SECTION 2); FROM JOSEPH BRYAN WAY THROUGH NS RAILROAD TUNNEL TO WAVELAND HISTORIC SITE (ALL WORK BY LFUCG). (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | C |  | SLX | 2019 | 400000 | 320000 |  |  |  | 80000 |  |  |  |  | 0
STIP | [9 empty] | FAYETTE | 7-229.3 |  | 0.3 |  |  | SAFETY | BIKE/PED FACIL(O) | SOUTH ELKHORN TRAIL(PRIORITY SECTION 3); FROM LOCHDALE TERRACE, EXTENDING NORTHERLY UNDER MAN O' WAR BOULEVARD TO SHILLITO PARK.(LOCAL MATCH)(DESIGN BY LFUCG)(ALL WORK BY LFUCG)(2004BOPC)(FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | C |  | SLX | 2019 | 625000 | 500000 |  |  |  | 125000 |  |  |  |  | 0
STIP | [9 empty] | FAYETTE | 7-252 | KY 922 | 1.75 | 1.47 | 3.22 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE NEWTOWN PIKE FROM KY-4 TO I-75. (16CCR)(18CCR) | R |  | NH | 2019 | 2000000 | 2000000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | FAYETTE | 7-252 | KY 922 | 1.75 | 1.47 | 3.22 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE NEWTOWN PIKE FROM KY-4 TO I-75. (16CCR)(18CCR) | U |  | NH | 2019 | 3000000 | 3000000 |  |  | 0 | [5 empty] | 0
STIP | YES | [8 empty] | FAYETTE | 7-252 | KY 922 | 1.75 | 1.47 | 3.22 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE NEWTOWN PIKE FROM KY-4 TO I-75. (16CCR)(18CCR) | C |  | NH | 2021 | 4950000 | 3960000 |  |  | 990000 | [5 empty] | 0
STIP | YES | [8 empty] | FAYETTE | 7-252.02 | KY 922 | 1.75 | 1.47 | 3.22 | RELIABILITY | PREFINANCD CONVRSN(O) | IMPROVE NEWTOWN PIKE FROM KY-4 TO I-75. (16CCR) | C |  | NH | 2021 | 10050000 | 8040000 |  |  | 2010000 | [5 empty] | 0
STIP | [9 empty] | FAYETTE | 7-366.02 | KY 4 | 1.3 | 8.731 | 10.015 | RELIABILITY | PREFINANCD CONVRSN(O) | WIDEN NEW CIRCLE ROAD IN LEXINGTON FROM GEORGETOWN ROAD TO BOARDWALK AVENUE INCLUDING INTERCHANGE RECONSTRUCTION AT NEWTOWN PIKE. (ADDITIONAL C-FUNDS FOR 7-366.00)(18CCR) | C |  | NH | 2021 | 22300000 | 17840000 |  |  | 4460000 | [5 empty] | 0
[8 empty] | STPM | 0754064 | FAYETTE | 7-442 | I-75 |  | 0 | 0.305 | SAFETY | SAFETY | SAFETY PROJECT TO WIDEN I-75 SOUTHBOUND EXIT RAMP AT MAN O'WAR TO CONSTRUCT LEFT TURN LANES AND INSTALL TRAFFIC SIGNAL. (2018BOP) | C |  | SLX | 2019 | [7 empty] | OBLIGATED | 617126 |  | 617126 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.161 | 2020-02-21 | LEXINGTON MPO AREA, TIP FY 17-20, GROUPED PROJECTS, TABLE 6, PG 32; ADD PROJECT TO STIP; NEW (THIS PROJECT IS ALSO LISTED ON ADMIN MOD#27) |  | 5196011 | FAYETTE | 7-951 | US 421 |  | 0 | 8.166 | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALLATION OF STRIPING ON US 421 IN FAYETTE COUNTY. (2018BOP) | C |  | SAF | 2020 | 605000 | 605000 | [5 empty] | OBLIGATED | 605000 |  | 605000 | 2020 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.161 | 2020-02-21 | LEXINGTON MPO AREA, TIP FY 17-20, GROUPED PROJECTS, TABLE 6, PG 32; ADD PROJECT TO STIP; NEW (THIS PROJECT IS ALSO LISTED ON ADMIN MOD#26) |  |  | FAYETTE | 7-956 | I-75 I-64 |  | 0.55 | 0.82 | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALLATION OF HIGH FRICTION SURFACE TREATMENT ON RAMP I-75 SB TO I-64 WB FROM MP .550 TO MP .820 IN FAYETTE COUNTY (2018BOP) | C |  | SAF | 2020 | 100000 | 100000 | [8 empty] | 0
STIP | [7 empty] | BRZ | 0703329 | FAYETTE | 7-1132 | CS 3605 |  | 1.656 | 1.696 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON MALABU DRIVE (CS 3605) OVER BRANCH HICKMAN CREEK AT JCT WITH TATES CREEK ROAD (KY 1974) 034C00038N | C |  | BR/STP | 2019 | 427000 | 264740 |  |  | 162260 |  |  | OBLIGATED | 70000 | 505344 | 575344 | 2019 | 2ND QUARTER
STIP | [9 empty] | FAYETTE | 7-1141 | CR 1001 | 0.04 | 1.6 | 1.64 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER BRANCH OF NORTH ELKHORN CREEK ON HUME ROAD (CR 1001) 0.7 MI NW OF US 60 (034C00001N) | D |  | BR/STP | 2019 | 210000 | 130200 |  |  | 79800 | [5 empty] | 0
STIP | [9 empty] | FAYETTE | 7-1141 | CR 1001 | 0.04 | 1.6 | 1.64 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER BRANCH OF NORTH ELKHORN CREEK ON HUME ROAD (CR 1001) 0.7 MI NW OF US 60 (034C00001N) | C |  | BR/STP | 2020 | 735000 | 455700 |  |  | 279300 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.123 | 2019-09-06 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD. LEXINGTON MPO AREA TIP FY 17-20, CHAPTER 4, TABLE 6-GROUPED PROJECTS, PG. 18. | STPBRZ | 9030161 | FAYETTE | 7-1141 | CR 1001 | 0.04 | 1.6 | 1.64 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER BRANCH OF NORTH ELKHORN CREEK ON HUME ROAD (CR 1001) 0.7 MI NW OF US 60 (034C00001N) | C |  | BR | 2020 | 818000 | 818000 |  |  | 0 |  |  | OBLIGATED |  | 716800 | 716800 | 2019 | 4TH QUARTER
STIP | [9 empty] | FAYETTE | 7-1145 | CS 7038 |  | 1.667 | 1.675 | RELIABILITY | MATCHED FED FUNDS(O) | REPLACE DETERIORATED WEST BOUND LANE BRIDGE SECTION OF WILSON DOWNING ROAD BRIDGE ACROSS WEST HICKMAN CREEK. | D |  | SLX | 2019 | 75000 | 60000 |  |  |  | 15000 |  |  |  |  | 0
STIP | [9 empty] | FAYETTE | 7-1145 | CS 7038 |  | 1.667 | 1.675 | RELIABILITY | MATCHED FED FUNDS(O) | REPLACE DETERIORATED WEST BOUND LANE BRIDGE SECTION OF WILSON DOWNING ROAD BRIDGE ACROSS WEST HICKMAN CREEK. | C |  | SLX | 2019 | 275000 | 220000 |  |  |  | 55000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.134 | 2019-09-26 | TIP FY 17-20; ADMIN MOD#22, ADD R PHASE TO STIP;NEW |  |  | FAYETTE | 7-3219 | CS 4735 | [5 empty] | ROSEMONT GARDEN SIDEWALKS - CONSTRUCT SIDEWALK ALONG THREE BLOCKS JUST EAST OF SOUTHLAND DR. LENGTH=0.2 MI. | R |  | SLX | 2020 | 30000 | 24000 |  |  |  | 6000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.24 | 2020-09-30 | TIP FY 27-20; ADMIN MOD#35; MOVE $30,000 SLX FUNDS FROM R PHASE TO C PHASE; MOD |  |  | FAYETTE | 7-3219 | CS 4735 | [5 empty] | ROSEMONT GARDEN SIDEWALKS - CONSTRUCT SIDEWALK ALONG THREE BLOCKS JUST EAST OF SOUTHLAND DR. LENGTH=0.2 MI. | R |  | SLX | 2020 | 0 | [9 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.134 | 2019-09-26 | TIP FY 17-20; ADMIN MOD#22, ADD C PHASE TO STIP;NEW |  |  | FAYETTE | 7-3219 | CS 4735 | [5 empty] | ROSEMONT GARDEN SIDEWALKS - CONSTRUCT SIDEWALK ALONG THREE BLOCKS JUST EAST OF SOUTHLAND DR. LENGTH=0.2 MI. | C |  | SLX | 2020 | 360000 | 288000 |  |  |  | 72000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.24 | 2020-09-30 | TIP FY 27-20; ADMIN MOD#35; MOVE $30,000 SLX FUNDS FROM R PHASE TO C PHASE; MOD |  |  | FAYETTE | 7-3219 | CS 4735 | [5 empty] | ROSEMONT GARDEN SIDEWALKS - CONSTRUCT SIDEWALK ALONG THREE BLOCKS JUST EAST OF SOUTHLAND DR. LENGTH=0.2 MI. | C |  | SLX | 2020 | 390000 | 312000 |  |  |  | 78000 |  |  |  |  | 0
STIP | [9 empty] | FAYETTE | 7-8507 | CS 2548 |  |  |  | RELIABILITY | NEW ROUTE(O) | COMPLETE CONSTRUCTION ON POLO CLUB BOULEVARD AT DEERHAVEN LANE AND TODDS ROAD. (08CCN)(FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP)(LET BY CITY) | C |  | SLX | 2019 | 1600000 | 1280000 |  |  |  | 320000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.024 | 2019-02-01 | TIP FY 17-20; ADMIN MOD#15; UPDATE FUND AMOUNT WITH TOLL CREDIT MATCH; MOD | STPM | 3003302 | FAYETTE | 7-8507 | CS 2548 |  |  |  | RELIABILITY | NEW ROUTE(O) | COMPLETE CONSTRUCTION ON POLO CLUB BOULEVARD AT DEERHAVEN LANE AND TODDS ROAD. (08CCN)(FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP)(LET BY CITY) | C |  | SLX | 2019 | 2230000 | 2230000 | 2230000 |  |  |  |  | OBLIGATED |  | 2235000 | 2235000 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.081 | 2019-06-14 | TIP FY 17-20; ADMIN MOD#19; UPDATE FUND AMOUNT; MOD | STPM | 3003302 | FAYETTE | 7-8507 | CS 2548 |  |  |  | RELIABILITY | NEW ROUTE(O) | COMPLETE CONSTRUCTION ON POLO CLUB BOULEVARD AT DEERHAVEN LANE AND TODDS ROAD. (08CCN)(FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP)(LET BY CITY) | C |  | SLX | 2019 | 2891000 | 2759000 | 2759000 |  |  | 132000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.1 | 2019-07-12 | TIP FY 17-20; ADMIN MOD#19- REVISED; UPDATE FUND AMOUNT; MOD | STPM | 3003302 | FAYETTE | 7-8507 | CS 2548 |  |  |  | RELIABILITY | NEW ROUTE(O) | COMPLETE CONSTRUCTION ON POLO CLUB BOULEVARD AT DEERHAVEN LANE AND TODDS ROAD. (08CCN)(FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP)(LET BY CITY) | C |  | SLX | 2019 | 2891250 | 2891250 | 2891250 |  |  |  |  | OBLIGATED |  | 661000 | 661000 | 2019 | 4TH QUARTER
STIP | YES | [8 empty] | FAYETTE | 7-8902 | KY 1927 | 1.145 | 0 | 1.145 | NEW ROUTES | MAJOR WIDENING(O) | IMPROVE LIBERTY ROAD FROM GRAFTONS MILL LANE TO NEW CIRCLE ROAD AND IMPROVE INTERSECTION WITH NEW CIRCLE ROAD. (16CCN)(18CCR) | R |  | STP | 2021 | 1000000 | 800000 |  |  | 200000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.116 | 2019-08-09 | TIP FY 17-20; ADMIN MOD#20, UPDATE FUND AMOUNT, FUND TYPE & FY; MOD |  |  | FAYETTE | 7-8902 | KY 1927 | 1.145 | 0 | 1.145 | NEW ROUTES | MAJOR WIDENING(O) | IMPROVE LIBERTY ROAD FROM GRAFTONS MILL LANE TO NEW CIRCLE ROAD AND IMPROVE INTERSECTION WITH NEW CIRCLE ROAD. (16CCN)(18CCR) | R |  | SLX | 2020 | 4300000 | 4300000 | [8 empty] | 0
STIP | YES | [8 empty] | FAYETTE | 7-8902 | KY 1927 | 1.145 | 0 | 1.145 | NEW ROUTES | MAJOR WIDENING(O) | IMPROVE LIBERTY ROAD FROM GRAFTONS MILL LANE TO NEW CIRCLE ROAD AND IMPROVE INTERSECTION WITH NEW CIRCLE ROAD. (16CCN)(18CCR) | U |  | STP | 2022 | 1730000 | 1384000 |  |  | 346000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.116 | 2019-08-09 | TIP FY 17-20; ADMIN MOD#20, UPDATE FUND AMOUNT, FUND TYPE & FY; MOD |  |  | FAYETTE | 7-8902 | KY 1927 | 1.145 | 0 | 1.145 | NEW ROUTES | MAJOR WIDENING(O) | IMPROVE LIBERTY ROAD FROM GRAFTONS MILL LANE TO NEW CIRCLE ROAD AND IMPROVE INTERSECTION WITH NEW CIRCLE ROAD. (16CCN)(18CCR) | U |  | SLX | 2020 | 4300000 | 4300000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.116 | 2019-08-09 | TIP FY 17-20; ADMIN MOD#20, ADD C PHASE TO STIP; NEW |  |  | FAYETTE | 7-8902 | KY 1927 | 1.145 | 0 | 1.145 | NEW ROUTES | MAJOR WIDENING(O) | IMPROVE LIBERTY ROAD FROM GRAFTONS MILL LANE TO NEW CIRCLE ROAD AND IMPROVE INTERSECTION WITH NEW CIRCLE ROAD. (16CCN)(18CCR) | C |  | STP | 2021 | 6190000 | 6190000 | [8 empty] | 0
STIP | YES | [8 empty] | FAYETTE | 7-8902.01 | KY 1927 | 1.145 | 0 | 1.145 | NEW ROUTES | PREFINANCD CONVRSN(O) | IMPROVE LIBERTY ROAD FROM GRAFTONS MILL LANE TO NEW CIRCLE ROAD AND IMPROVE INTERSECTION WITH NEW CIRCLE ROAD. (16CCN) | R |  | STP | 2021 | 3300000 | 2640000 |  |  | 660000 | [5 empty] | 0
STIP | YES | [8 empty] | FAYETTE | 7-8909 | I 75 | 6.665 | 111 | 117.665 | RELIABILITY | MAJOR WIDENING(O) | REDUCE CONGESTION ON I-64/I-75 FROM THE C&O RAILROAD BRIDGE TO THE NORTHERN SPLIT (SECTION 1). (16CCN)(18CCR) | R |  | NH | 2021 | 1000000 | 800000 |  |  | 200000 | [5 empty] | 0
STIP | YES | [8 empty] | FAYETTE | 7-8909 | I 75 | 6.665 | 111 | 117.665 | RELIABILITY | MAJOR WIDENING(O) | REDUCE CONGESTION ON I-64/I-75 FROM THE C&O RAILROAD BRIDGE TO THE NORTHERN SPLIT (SECTION 1). (16CCN)(18CCR) | U |  | NH | 2021 | 1000000 | 800000 |  |  | 200000 | [5 empty] | 0
STIP | YES | [8 empty] | FAYETTE | 7-8909 | I 75 | 6.665 | 111 | 117.665 | RELIABILITY | MAJOR WIDENING(O) | REDUCE CONGESTION ON I-64/I-75 FROM THE C&O RAILROAD BRIDGE TO THE NORTHERN SPLIT (SECTION 1). (16CCN)(18CCR) | C |  | NH | 2022 | 25000000 | 20000000 |  |  | 5000000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.161 | 2020-02-21 | LEXINGTON MPO AREA, TIP FY 17-20, GROUPED PROJECTS, TABLE 6, PG 32; ADD PROJECT TO STIP; NEW (THIS PROJECT IS ALSO LISTED ON ADMIN MOD#26) |  | 8547010 | FAYETTE | 7-9006.10 | US 27 CS 1376 |  | 7.81 .14 | 7.964 .29 | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALL SUPPLEMENTAL SIGNAL HEADS, CONSTRUCT MEDIAN ACCESS CONTROL ALONG US 27, CLOSE AN ENTRANCE ON W LOUDON AVE, AND UPDATE THE STRIPING NEAR THE INTERSECTION OF US 27 & W LOUDON AVE. (2018BOP) | C |  | SAF | 2020 | 77000 | 77000 |  |  | 0 |  |  | OBLIGATED | 68400 |  | 68400 | 2020 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.161 | 2020-02-21 | LEXINGTON MPO AREA, TIP FY 17-20, GROUPED PROJECTS, TABLE 6, PG 32; ADD PROJECT TO STIP; NEW |  | 8547011 | FAYETTE | 7-9006.20 | US 27 |  | 6.713 | 6.763 | SAFETY | SAFETY-HAZARD ELIM(P) | UPDATE THE TRAFFIC SIGNAL TO INCLUDE REFLECTIVE BACKPLATES, DOUBLE RED SIGNAL HEADS, AND SUPPLEMENTAL SIGNAL HEADS AT THE INTERSECTION OF US 27 & W MAIN ST (2018BOP) | C |  | SAF | 2020 | 21000 | 21000 |  |  | 0 |  |  | OBLIGATED | 19350 |  | 19350 | 2020 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.161 | 2020-02-21 | LEXINGTON MPO AREA, TIP FY 17-20, GROUPED PROJECTS, TABLE 6, PG 32; ADD PROJECT TO STIP; NEW (THIS PROJECT IS ALSO LISTED ON ADMIN MOD#26) |  | 8610005 | FAYETTE | 7-9006.40 | US 25 |  | 17.665 | 17.735 | SAFETY | SAFETY-HAZARD ELIM(P) | UPDATE THE TRAFFIC SIGNAL TO INCLUDE REFLECTIVE BACKPLATES AND IMPROVE THE TURNING RADIUS OF THE NB US 25 LEFT TURN LANE AT THE INTERSECTION OF US 25 & CITATION BLVD. (2018BOP) | C |  | SAF | 2020 | 38000 | 38000 |  |  | 0 |  |  | OBLIGATED | 32490 |  | 32490 | 2020 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.167 | 2020-02-24 | TIP FY 17-20, ADMIN MOD#26, ADD PROJECT TO STIP; NEW |  |  | FAYETTE | 7-9006.50 | US 27 |  | 6.402 | 6.452 | SAFETY | SAFETY-HAZARD ELIM(P) | REBUILD THE TRAFFIC SIGNAL AND CONSTRUCT PEDESTRIAN IMPROVEMENTS AT THE INTERSECTION OF US 27 & W MAXWELL ST. (2018BOP) | C |  | SAF | 2020 | 21000 | 21000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.161 | 2020-02-21 | LEXINGTON MPO AREA, TIP FY 17-20, GROUPED PROJECTS, TABLE 6, PG 32; ADD PROJECT TO STIP; NEW (THIS PROJECT IS ALSO LISTED ON ADMIN MOD#26) | HSIP | 9010409 | FAYETTE | 7-9006.60 | CS 4524 |  | 1.169 | 1.369 | SAFETY | SAFETY-HAZARD ELIM(P) | UPDATE THE TRAFFIC SIGNAL TO INCLUDE REFLECTIVE BACKPLATES AND UPDATE THE SIGNING AND STRIPING NEAR THE INTERSECTION OF MAN O WAR & PARKERS MILL RD. (2018BOP) | C |  | SAF | 2020 | 56000 | 56000 |  |  | 0 |  |  | OBLIGATED | 51300 |  | 51300 | 2020 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.015 | 2019-01-25 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; LEXINGTON MPO TIP 17-20, GROUP PROJECTS, CHAPER 4, PG 18, TABLE 6; NEW | HSIP | 9010353 | FAYETTE, ANDERSON, JESSAMINE | 7-9012 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | PRELIMINARY DESIGN AND STUDY TO DETERMINE LOW COST IMPROVEMENTS AT VARIOUS INTERSECTIONS WITHIN DISTRICT 7. (2018BOP) | D |  | SAF | 2019 | 600000 | 600000 |  |  | 0 |  |  | OBLIGATED |  | 600000 | 600000 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.202 | 2020-07-01 | TIP FY 17-20, ADMIN MOD #30; ADD C PHASE TO STIP; NEW |  |  | FAYETTE | 7-9012.1 | US 27 US 68 |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | UPGRADE THE TRAFFIC SIGNAL TO INCLUDE REFLECTIVE BACKPLATES AND SUPPLEMENTAL SIGNAL HEADS AND INSTALL LANE SEPARATOR CURB AT THE INTERSECTION OF US 27 AND US 68. | C |  | SAF | 2020 | 50000 | 50000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.202 | 2020-07-01 | TIP FY 17-20, ADMIN MOD #30; ADD C PHASE TO STIP; NEW |  |  | FAYETTE | 7-9012.2 | KY 353 CS 1321 |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | UPGRADE THE TRAFFIC SIGNAL TO INCLUDE REFLECTIVE BACKPLATES AND INSTALL LANE SEPARATOR CURB ALONG RUSSELL CAVE RD NEAR THE INTERSECTION OF RUSSELL CAVE RD & NEW CIRCLE ROAD. | C |  | SAF | 2020 | 60000 | 60000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.202 | 2020-07-01 | TIP FY 17-20, ADMIN MOD #30; ADD C PHASE TO STIP; NEW |  |  | FAYETTE | 7-9012.3 | US 60 CS 4009 |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALL LANE SEPARATOR CURB ALONG ALEXANDRIA DR NEAR THE INTERSECTION OF US 60 & ALEXANDRIA DRIVE. | C |  | SAF | 2020 | 35000 | 35000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.202 | 2020-07-01 | TIP FY 17-20, ADMIN MOD #30; ADD C PHASE TO STIP; NEW |  |  | FAYETTE | 7-9012.4 | KY 4 CS 2241 |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | UPGRADE THE TRAFFIC SIGNAL TO INCLUDE REFLECTIVE BACKPLATES AND INSTALL LANE SEPARATOR CURB ALONG RUSSELL CAVE RD NEAR THE INTERSECTION OF NEW CIRCLE ROAD & EASTLAND PKWY. | C |  | SAF | 2020 | 70000 | 70000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.202 | 2020-07-01 | TIP FY 17-20, ADMIN MOD #30; ADD C PHASE TO STIP; NEW |  |  | FAYETTE | 7-9012.6 | US 60 |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | UPGRADE THE TRAFFIC SIGNAL TO INCLUDE REFLECTIVE BACKPLATES AND INSTALL LANE SEPARATOR CURB NEAR THE INTERSECTION OF US 60 & S FORBES ROAD. | C |  | SAF | 2020 | 30000 | 30000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.202 | 2020-07-01 | TIP FY 17-20, ADMIN MOD #30; ADD C PHASE TO STIP; NEW |  |  | FAYETTE | 7-9012.7 | US 27 CS 1157 |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | UPGRADE THE TRAFFIC SIGNALS ALONG US 27 TO INCLUDE REFLECTIVE BACKPLATES AND IMPROVE ACCESS CONTROL NEAR THE INTERSECTION OF US 27 & HAGGARD LANE. | C |  | SAF | 2020 | 60000 | 54000 |  |  | 6000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.112 | 2019-08-08 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW. LEXINGTON MPO TIP FY 17-20, CHAPTER 4 GROUPED PROJECTS, PG 18. | HSIP | 5205022 | FAYETTE | 7-9015 | KY 353 |  | 1.372 | 10.153 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 353 FROM MP 1.372 TO MP 10.153 IN FAYETTE COUNTY. (2018BOP) | D |  | SAF | 2019 | 350000 | 350000 |  |  | 0 |  |  | OBLIGATED |  | 350000 | 350000 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.112 | 2019-08-08 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW. LEXINGTON MPO TIP FY 17-20, CHAPTER 4 GROUPED PROJECTS, PG 18. | HSIP | 5210007 | FAYETTE | 7-9017 | KY 57 |  | 1.292 | 7.8 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 57 FROM MP 1.292 TO MP 7.800 IN FAYETTE COUNTY. (2018BOP) | D |  | SAF | 2019 | 200000 | 200000 |  |  | 0 |  |  | OBLIGATED |  | 200000 | 200000 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.239 | 2020-09-25 | TIP FY 27-20, ADMIN MOD#34; ADD PROJECT TO STIP; NEW |  |  | FAYETTE | 7-9023 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | KYTC-LFUCG Joint Roadway Safety Plan for All Public Roads in Fayette County. | P |  | SAF | 2019 | 350000 | 315000 |  |  | 35000
STIP | [9 empty] | FAYETTE | 7-10009 | CR 1121 |  | 0.708 | 0.72 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF MCCALLS MILL RD BRIDGE OVER BOGGS FORK. (034C00009N) | D |  | BR/STP | 2019 | 157500 | 97650 |  |  | 59850 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030137 | FAYETTE | 7-10009 | CR 1121 |  | 0.708 | 0.72 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF MCCALLS MILL RD BRIDGE OVER BOGGS FORK. (034C00009N) | C |  | BR/STP | 2020 | 360500 | 223510 |  |  | 136990 |  |  | OBLIGATED |  | 690030 | 690030 | 2019 | 3RD QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.112 | 2019-08-08 | ADD PROJECT TO STIP; NEW. LEXINGTON MPO TIP FY 17-20, CHAPTER 4 GROUPED PROJECTS, PG 18. | STPBRZ | 9030162 | FAYETTE | 7-10016 | CR 1018 |  | 1.601 |  | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES ON FERGUSON RD (CR 1018) OVER GOOSE CREEK. | C |  | STP | 2020 | 552000 | 552000 |  |  | 0 |  |  | OBLIGATED |  | 464060 | 464060 | 2019 | 4TH QUARTER
STIP | YES | YES | This project has no phases in the current TIP. It will be added to the next TIP. | [6 empty] | FAYETTE | 7-20008 | I 64 |  | 71 | 73.94 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-064 NON-CARDINAL DIRECTION(S) FROM MILEPOINT 71 TO MILEPOINT 73.94 | D |  | PM/NH | 2022 | 390000 | 312000 |  |  | 78000 | [5 empty] | 0
STIP | YES | YES | This project has no phases in the current TIP. It will be added to the next TIP. | [6 empty] | FAYETTE | 7-20008 | I 64 |  | 71 | 73.94 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-064 NON-CARDINAL DIRECTION(S) FROM MILEPOINT 71 TO MILEPOINT 73.94 | C |  | PM/NH | 2022 | 3900000 | 3120000 |  |  | 780000 | [5 empty] | 0
STIP | [9 empty] | FAYETTE | 7-20009 | I 64 |  | 73.94 | 74.729 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-064 CARDINAL DIRECTION(S) FROM MILEPOINT 73.94 TO MILEPOINT 74.729 | D |  | PM/NH | 2019 | 30000 | 24000 |  |  | 6000 | [5 empty] | 0
STIP | [9 empty] | FAYETTE | 7-20009 | I 64 |  | 73.94 | 74.729 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-064 CARDINAL DIRECTION(S) FROM MILEPOINT 73.94 TO MILEPOINT 74.729 | C |  | PM/NH | 2019 | 3000000 | 2400000 |  |  | 600000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.224 | 2020-08-25 | TIP FY 17-20, ADMIN MOD#33; ADD PROJECT TO STIP; NEW |  |  | FAYETTE | 7-20010 | I 64 |  | 81.037 | 82.19 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF PAVEMENT ON I-64 BOTH DIRECTIONS FROM MILEPOINT 81.037 TO MILEPOINT 82.19. | D |  | PM/NH | 2020 | 175000 | 140000 |  |  | 35000 | [5 empty] | 0
STIP | YES | YES | This project has no phases in the current TIP. It will be added to the next TIP. | [6 empty] | FAYETTE | 7-20011 | I 64 |  | 82.19 | 89.48 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-064 BOTH DIRECTION(S) FROM MILEPOINT 82.19 TO MILEPOINT 89.48. (18CCR) | D |  | PM/NH | 2021 | 870000 | 696000 |  |  | 174000 | [5 empty] | 0
STIP | YES | YES | This project has no phases in the current TIP. It will be added to the next TIP. | [6 empty] | FAYETTE | 7-20011 | I 64 |  | 82.19 | 89.48 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-064 BOTH DIRECTION(S) FROM MILEPOINT 82.19 TO MILEPOINT 89.48. (18CCR) | C |  | PM/NH | 2021 | 8700000 | 6960000 |  |  | 1740000 | [5 empty] | 0
STIP | YES | YES | This project has no phases in the current TIP. It will be added to the next TIP. | [6 empty] | FAYETTE | 7-20013 | I 75 |  | 107.453 | 110.213 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-075 BOTH DIRECTION(S) FROM MILEPOINT 107.453 TO MILEPOINT 110.213 | D |  | PM/NH | 2021 | 330000 | 264000 |  |  | 66000 | [5 empty] | 0
STIP | YES | YES | This project has no phases in the current TIP. It will be added to the next TIP. | [6 empty] | FAYETTE | 7-20013 | I 75 |  | 107.453 | 110.213 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-075 BOTH DIRECTION(S) FROM MILEPOINT 107.453 TO MILEPOINT 110.213 | C |  | PM/NH | 2021 | 3300000 | 2640000 |  |  | 660000 | [5 empty] | 0
STIP | YES | YES | This project has no phases in the current TIP. It will be added to the next TIP. | [6 empty] | FAYETTE | 7-20014 | I 75 |  | 110.264 | 111.82 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-075 BOTH DIRECTION(S) FROM MILEPOINT 110.264 TO MILEPOINT 111.82 | D |  | PM/NH | 2022 | 190000 | 152000 |  |  | 38000 | [5 empty] | 0
STIP | YES | YES | This project has no phases in the current TIP. It will be added to the next TIP. | [6 empty] | FAYETTE | 7-20014 | I 75 |  | 110.264 | 111.82 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-075 BOTH DIRECTION(S) FROM MILEPOINT 110.264 TO MILEPOINT 111.82 | C |  | PM/NH | 2022 | 1900000 | 1520000 |  |  | 380000 | [5 empty] | 0
STIP | [9 empty] | FAYETTE | 7-20015 | I 75 |  | 111.82 | 120.792 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-075 BOTH DIRECTION(S) FROM MILEPOINT 111.82 TO MILEPOINT 120.792 | D |  | PM/NH | 2020 | 1080000 | 864000 |  |  | 216000 | [5 empty] | 0
STIP | [9 empty] | FAYETTE | 7-20015 | I 75 |  | 111.82 | 120.792 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-075 BOTH DIRECTION(S) FROM MILEPOINT 111.82 TO MILEPOINT 120.792 | C |  | PM/NH | 2020 | 10800000 | 8640000 |  |  | 2160000 | [5 empty] | 0
STIP | [9 empty] | FAYETTE | 7-20016 | US 421 |  | 6.935 | 7.3 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT | D |  | PM/NH | 2019 | 50000 | 40000 |  |  | 10000 | [5 empty] | 0
STIP | [9 empty] | FAYETTE | 7-20016 | US 421 |  | 6.935 | 7.3 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT | C |  | PM/NH | 2019 | 500000 | 400000 |  |  | 100000 | [5 empty] | 0
STIP | YES | YES | This project has no phases in the current TIP. It will be added to the next TIP. | [6 empty] | FAYETTE | 7-20025 | US 25 | 3.19 | 19.1 | 22.29 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION ON US-25 FROM MILEPOINT 19.10 TO MILEPOINT 22.29 | C |  | PM/NH | 2022 | 1440000 | 1152000 |  |  | 288000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.289 | 2021-03-22 | TIP FY 21-24, ADMIN MOD#4; ADD PROJECT TO STIP; NEW |  |  | FAYETTE | 7-20044 | US 68 |  | 2.8 | 3.49 | RELIABILITY | AM-PAVEMENT (PRI)(P) | Resurface US 68 from MP 2.80 to MP 3.49 in Fayette County, KY. | C |  | NHPP | 2021 | 1033000 | 826000 |  |  | 207000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.289 | 2021-03-22 | TIP FY 21-24, ADMIN MOD#4; ADD PROJECT TO STIP; NEW |  |  | FAYETTE | 7-20045 | US 25 |  | 13.43 | 14.63 | RELIABILITY | AM-PAVEMENT (PRI)(P) | Resurface US 25 from MP 13.43 to MP 14.63 in Fayette County, KY. | C |  | NHPP | 2021 | 733000 | 586000 |  |  | 147000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.289 | 2021-03-22 | TIP FY 21-24, ADMIN MOD#4; ADD PROJECT TO STIP; NEW |  |  | FAYETTE | 7-20046 | US 27 |  | 6.28 | 6.61 | RELIABILITY | AM-PAVEMENT (PRI)(P) | Resurface US 27 from MP 6.28 to MP 6.61 in Fayette County, KY. | C |  | NHPP | 2021 | 218000 | 174000 |  |  | 44000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.207 | 2020-07-13 | TIP FY 17-20, ADMIN MOD#31; ADD PROJECT TO STIP; NEW |  |  | FAYETTE |  | KY 169 | [5 empty] | AVENUE OF CHAMPIONS AND EUCLID AVENUE MULTIMODAL IMPROVEMENTS; RESURFACE ROADWAY TO INSTALL BUFFERED BIKE LANES FROM SOUTH LIMESTONE TO HIGH STREET AND ADD A PEDESTRIAN CROSSING WITH REFUGE ISLAND AT KROGER STORE. | C |  | SLX | 2020 | 600000 | 480000 |  |  |  | 120000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.07 | 2019-05-13 | TIP FY 17-20; ADMIN MOD#18; ADD PROJECT TO STIP; NEW |  |  | FAYETTE |  | KY 169 | [5 empty] | RESTORATION AND PRESERVATION OF THE VALLEY VIEW FERRY CAR BARGE AND SAFETY CABLE GUIDANCE SYSTEM. | C |  | FBP | 2019 | 80000 | 64000 |  |  | 0 | 16000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.316 | 2021-06-25 | TIP FY 21-24, ADMIN MOD#5; ADD PROJECT TO STIP; NEW |  |  | FAYETTE | TBD | [6 empty] | EAST FAYETTE TRAIL CONNECTIVITY STUDY: STUDY TO DETERMINE ALIGNMENT OF PRIMARY TRAIL FROM LIBERTY RD AT NEW CIRCLE RD TO 3RD STREET/IMAGG TRAILHEAD. | P |  | SLX | 2022 | 150000 | 120000 |  |  |  | 30000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.316 | 2021-06-25 | TIP FY 21-24, ADMIN MOD#5; ADD PROJECT TO STIP; NEW |  |  | FAYETTE | TBD | [6 empty] | NORTHEAST NEW CIRCLE ROAD CORRIDOR PLAN: A COORDINATED CORRIDOR LAND USE PLAN AND TRANSPORTATION STUDY FOR THE SIGNALIZED PORTION OF NORTHEAST NEW CIRCLE ROAD. | C |  | SLX | 2022 | 250000 | 200000 |  |  |  | 50000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.096 | 2019-07-02 | ADD PROJECT TO STIP; NEW | FBP | 6000155 | FAYETTE MADISON | 7-488 | KY 169 |  | 0 12.411 | .1 12.511 | RELIABILITY | FERRY OPERATION(P) | HAULOUT AND INSPECTION OF THE VALLEY VIEW FERRY TO COMPLY WITH USCG SAFETY REQUIREMENTS. | C |  | FBP | 2019 | 80000 | 64000 |  |  |  | 16000 |  | OBLIGATED | 64000 |  | 64000 | 2019 | 4TH QUARTER | Valley View Ferry
STIP | [9 empty] | FLEMING | 9-1084 | KY 32 | 0.04 | 7.76 | 7.8 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON KY 32 OVER MUD LICK CREEK 0.2 MILES W OF CRAINTOWN RD (CR 1302)035B00038N | C |  | BR/STP | 2020 | 560000 | 347200 |  |  | 212800 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.161 | 2020-02-21 | INCREASE FUNDS BASED ON NEW ESTIMATE; MOD | BRO | 5215011 | FLEMING | 9-1084 | KY 32 | 0.04 | 7.76 | 7.8 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON KY 32 OVER MUD LICK CREEK 0.2 MILES W OF CRAINTOWN RD (CR 1302)035B00038N | C |  | BR/STP | 2020 | 1280000 | 1280000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.283 | 2021-03-22 | UPDATE FISCAL YEAR AND FUND AMOUNT; MOD | BRO | 5215011 | FLEMING | 9-1084 | KY 32 | 0.04 | 7.76 | 7.8 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON KY 32 OVER MUD LICK CREEK 0.2 MILES W OF CRAINTOWN RD (CR 1302)035B00038N | C |  | BR/STP | 2021 | 1285000 | 1285000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.005 | 2018-12-17 | ADD U PHASE TO STIP; NEW | BRO | 5215011 | FLEMING | 9-1084 | KY 32 | 0.04 | 7.76 | 7.8 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON KY 32 OVER MUD LICK CREEK 0.2 MILES W OF CRAINTOWN RD (CR 1302)035B00038N | U |  | BR/STP | 2019 | 205000 | 205000 |  |  | 0 |  |  | OBLIGATED |  | 205000 | 205000 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.005 | 2018-12-17 | ADD R PHASE TO STIP; NEW | BRO | 5215011 | FLEMING | 9-1084 | KY 32 | 0.04 | 7.76 | 7.8 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON KY 32 OVER MUD LICK CREEK 0.2 MILES W OF CRAINTOWN RD (CR 1302)035B00038N | R |  | BR/STP | 2019 | 69500 | 69500 |  |  | 0 |  |  | OBLIGATED | 20000 | 69500 | 89500 | 2019 | 2ND QUARTER
STIP | [7 empty] | STPBRZ | 9030043 | FLEMING | 9-1091 | KY 111 | 0.02 | 11.84 | 11.86 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER ALLISON CREEK ON KY 111 1.2 MI N OF KY 156. (035B00016N)(EBRP) | C |  | BR/STP | 2020 | 2135000 | 1323700 |  |  | 811300 |  |  | OBLIGATED |  | 315430 | 315430 | 2019 | 2ND QUARTER
STIP | [7 empty] | STPBRZ | 0903205 | FLEMING | 9-1092 | CR 1240 | 0.024 | 2.04 | 2.064 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER FLEMING CREEK ON MCINTIRE ROAD (CR 1240) AT THE JCT WITH PIKE BLUFF (CR 1305)(035C00065N) | R |  | BR/STP | 2019 | 75000 | 46500 |  |  | 28500 |  |  | OBLIGATED | 31000 |  | 31000 | 2019 | 2ND QUARTER
STIP | [7 empty] | STPBRZ | 0903205 | FLEMING | 9-1092 | CR 1240 | 0.024 | 2.04 | 2.064 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER FLEMING CREEK ON MCINTIRE ROAD (CR 1240) AT THE JCT WITH PIKE BLUFF (CR 1305)(035C00065N) | U |  | BR/STP | 2019 | 50000 | 31000 |  |  | 19000 |  |  | OBLIGATED | 35000 |  | 35000 | 2019 | 2ND QUARTER
STIP | [7 empty] | STPBRZ | 0903205 | FLEMING | 9-1092 | CR 1240 | 0.024 | 2.04 | 2.064 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER FLEMING CREEK ON MCINTIRE ROAD (CR 1240) AT THE JCT WITH PIKE BLUFF (CR 1305)(035C00065N) | C |  | BR/STP | 2020 | 600000 | 372000 |  |  | 228000 |  |  | OBLIGATED | 634523.64 | 842511.36 | 1477035 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.103 | 2019-07-29 | UPDATE FUNDING AMOUNT; MOD | STPBRZ | 0903205 | FLEMING | 9-1092 | CR 1240 | 0.024 | 2.04 | 2.064 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER FLEMING CREEK ON MCINTIRE ROAD (CR 1240) AT THE JCT WITH PIKE BLUFF (CR 1305)(035C00065N) | C |  | STP | 2019 | 1370000 | 1370000 |  |  | 0 |  |  | OBLIGATED | 100000 | 742511.36 | 842511.36 | 2019 | 4TH QUARTER
STIP | [9 empty] | FLEMING | 9-8804 | KY 111 |  |  |  | RELIABILITY | BRIDGE REHAB(P) | RESTORATION OF GRANGE CITY COVERED BRIDGE LOCATED ON KY-111 BETWEEN FLEMINGSBURG AND GRANGE CITY. (14CCN) (16CCR)(18CCN) | C |  | TE | 2019 | 1200000 | 960000 |  |  |  | 240000 |  |  |  |  | 0
STIP | [9 empty] | FLEMING | 9-10005 | KY 111 |  | 7.568 | 7.576 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-111 BRIDGE OVER BR OF HILLSBORO CREEK. (035B00018N) | D |  | BR/STP | 2019 | 455000 | 282100 |  |  | 172900 | [5 empty] | 0
STIP | [9 empty] | FLEMING | 9-10005 | KY 111 |  | 7.568 | 7.576 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-111 BRIDGE OVER BR OF HILLSBORO CREEK. (035B00018N) | C |  | BR/STP | 2020 | 1015000 | 629300 |  |  | 385700 | [5 empty] | 0
STIP | [9 empty] | FLEMING | 9-10006 | KY 367 |  | 0.999 | 1.007 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-367 BRIDGE OVER JOHNSON CREEK. (035B00074N) | D |  | BR/STP | 2019 | 375000 | 232500 |  |  | 142500 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030042 | FLEMING | 9-10006 | KY 367 |  | 0.999 | 1.007 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-367 BRIDGE OVER JOHNSON CREEK. (035B00074N) | C |  | BR/STP | 2020 | 980000 | 607600 |  |  | 372400 |  |  | OBLIGATED |  | 337740 | 337740 | 2019 | 2ND QUARTER
STIP | [9 empty] | FLEMING | 9-10019 | KY 2508 |  | 0.081 | 0.087 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 2508 BRIDGE OVER TOWN BRANCH. (035B00030N) | D |  | BR/STP | 2019 | 315000 | 195300 |  |  | 119700 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030046 | FLEMING | 9-10019 | KY 2508 |  | 0.081 | 0.087 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 2508 BRIDGE OVER TOWN BRANCH. (035B00030N) | C |  | BR/STP | 2020 | 875000 | 542500 |  |  | 332500 |  |  | OBLIGATED |  | 262850 | 262850 | 2019 | 2ND QUARTER
STIP | [9 empty] | FLEMING | 9-10020 | KY 111 |  | 3.863 | 3.866 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 111 BRIDGE OVER DAVIS BRANCH. (035B00075N) | D |  | BR/STP | 2019 | 315000 | 195300 |  |  | 119700 | [5 empty] | 0
STIP | [9 empty] | FLEMING | 9-10020 | KY 111 |  | 3.863 | 3.866 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 111 BRIDGE OVER DAVIS BRANCH. (035B00075N) | C |  | BR/STP | 2020 | 752500 | 466550 |  |  | 285950 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.03 | 2019-03-01 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030065 | FLEMING | 9-10020 | KY 111 |  | 3.863 | 3.866 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 111 BRIDGE OVER DAVIS BRANCH. (035B00075N) | C |  | STP | 2019 | 764158 | 764158 |  |  | 0 |  |  | OBLIGATED |  | 752925 | 752925 | 2019 | 3RD QUARTER
STIP | [9 empty] | FLEMING | 9-10021 | KY 681 |  | 1.545 | 1.555 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 681 BRIDGE OVER DELANEY CREEK. (035B00103N) | D |  | BR/STP | 2019 | 315000 | 195300 |  |  | 119700 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030041 | FLEMING | 9-10021 | KY 681 |  | 1.545 | 1.555 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 681 BRIDGE OVER DELANEY CREEK. (035B00103N) | C |  | BR/STP | 2020 | 822500 | 509950 |  |  | 312550 |  |  | OBLIGATED |  | 590920 | 590920 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.123 | 2019-09-06 | ADD PROJECT TO STIP; PARENT NO. 99-65.16 AND 99-65.17; NEW |  |  | FLEMING | 9-10030 | KY 3110 |  | 0.011 |  | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES ON KY-3110 OVER SAND LICK CREEK. (035B00073N) | C |  | BR | 2020 | 522000 | 522000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | FLEMING | 9-20009 | KY 32 |  | 13 | 28.29 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT | D |  | PM/STP | 2019 | 1250000 | 1000000 |  |  | 250000 | [5 empty] | 0
STIP | [7 empty] | STP | 0321027 | FLEMING | 9-20009 | KY 32 |  | 13 | 28.29 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT | C |  | PM/STP | 2019 | 12500000 | 10000000 |  |  | 2500000 |  |  | OBLIGATED | 1905652.16 | 11306997.84 | 13212650 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.229 | 2020-09-14 | ADD D PHASE TO STIP; NEW |  |  | FLEMING ROWAN | 9-80051 | KY 32 |  | 27.893 | 28.293 | SAFETY | SAFETY(P) | IMPROVE SAFETY AND SIGHT DISTANCE ON KY-32 BEGINNING AT 0.4 MILES WEST OF FLEMING/ROWAN CO LINE AND ENDING 0.3 MILES EAST OF THE LINE.(18CCN) (2020CCR) | D |  | SAF | 2020 | 500000 | 500000 |  |  | 0 | [5 empty] | 0
STIP | [7 empty] | NHPP | 0231148 | FLOYD | 12-191 | US 23 | 1 | 12.775 | 13.775 | SAFETY | SAFETY(P) | IMPROVE SAFETY AND ACCESS ON US-23 BETWEEN KY-80 AND KY-3384.(12CCR) | R |  | NH | 2019 | 420000 | 420000 |  |  | 0 |  |  | OBLIGATED | 100000 |  | 100000 | 2019 | 3RD QUARTER
STIP | [7 empty] | NHPP | 0231148 | FLOYD | 12-191 | US 23 | 1 | 12.775 | 13.775 | SAFETY | SAFETY(P) | IMPROVE SAFETY AND ACCESS ON US-23 BETWEEN KY-80 AND KY-3384.(12CCR) | U |  | NH | 2019 | 520000 | 520000 |  |  | 0 |  |  | OBLIGATED | 410000 |  | 410000 | 2019 | 3RD QUARTER
STIP | [9 empty] | FLOYD | 12-191 | US 23 | 1 | 12.775 | 13.775 | SAFETY | SAFETY(P) | IMPROVE SAFETY AND ACCESS ON US-23 BETWEEN KY-80 AND KY-3384.(12CCR) | C |  | NH | 2021 | 1880000 | 1504000 |  |  | 376000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.283 | 2021-03-22 | ADD R PHASE TO STIP; NEW |  |  | FLOYD | 12-195 | KY 979 |  | 12.398 | 13.95 | RELIABILITY | SPOT IMPROVEMENTS(O) | SPOT IMPROVEMENTS FROM BRANHAM'S CREEK TO JOHN M. STUMBO SCHOOL.(12CCR)(16CCR) (2020CCR) | R |  | STP | 2021 | 2500000 | 2500000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | FLOYD | 12-1119 | KY 2557 | 0.146 | 0.152 | 0.298 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER LEVISA FORK ON KY 2557 AT JCT US 23 IN JUSTELL. (036B00040N) | D |  | BR/STP | 2019 | 525000 | 325500 |  |  | 199500 | [5 empty] | 0
STIP | [9 empty] | FLOYD | 12-1119 | KY 2557 | 0.146 | 0.152 | 0.298 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER LEVISA FORK ON KY 2557 AT JCT US 23 IN JUSTELL. (036B00040N) | C |  | BR/STP | 2020 | 3010000 | 1866200 |  |  | 1143800 | [5 empty] | 0
STIP | [9 empty] | FLOYD | 12-1121 | KY 550 | 0.04 | 2.03 | 2.07 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER BRUSH CREEK ON KY 550 AT JCT WITH KY 850. (036B00015N)(EBRP) | D |  | BR/STP | 2019 | 210000 | 130200 |  |  | 79800 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030075 | FLOYD | 12-1121 | KY 550 | 0.04 | 2.03 | 2.07 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER BRUSH CREEK ON KY 550 AT JCT WITH KY 850. (036B00015N)(EBRP) | C |  | BR/STP | 2020 | 1050000 | 651000 |  |  | 399000 |  |  | OBLIGATED |  | 989420 | 989420 | 2019 | 3RD QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.111 | 2019-08-02 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 5357024 | FLOYD | 12-9013 | KY 122 |  | 8.522 | 15.479 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 122 FROM MP 8.520 TO MP 15.479 IN FLOYD COUNTY. (2018BOP) | D |  | SAF | 2019 | 350000 | 350000 |  |  | 0 |  |  | OBLIGATED | 350000 |  | 350000 | 2019 | 4TH QUARTER
STIP | [9 empty] | FLOYD | 12-10000 | CR 1253Q3 |  | 0.158 | 0.168 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRYANT BRANCH LEFT FORK OF CLEAR CREEK ROAD BRIDGE OVER LEFT FK OF BEAVER CREEK. (036C00017N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [9 empty] | FLOYD | 12-10000 | CR 1253Q3 |  | 0.158 | 0.168 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRYANT BRANCH LEFT FORK OF CLEAR CREEK ROAD BRIDGE OVER LEFT FK OF BEAVER CREEK. (036C00017N) | C |  | BR/STP | 2020 | 384000 | 238080 |  |  | 145920 | [5 empty] | 0
STIP | [9 empty] | FLOYD | 12-10014 | KY 466 |  | 2.588 | 2.592 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 466 BRIDGE OVER LEFT FORK BEAVER CREEK. (036B00032N) | D |  | BR/STP | 2019 | 140000 | 86800 |  |  | 53200 | [5 empty] | 0
STIP | [9 empty] | FLOYD | 12-10014 | KY 466 |  | 2.588 | 2.592 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 466 BRIDGE OVER LEFT FORK BEAVER CREEK. (036B00032N) | C |  | BR/STP | 2020 | 274750 | 170345 |  |  | 104405 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.075 | 2019-05-28 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD |  |  | FLOYD | 12-10014 | KY 466 |  | 2.588 | 2.592 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 466 BRIDGE OVER LEFT FORK BEAVER CREEK. (036B00032N) | C |  | STP | 2020 | 704859 | 704859 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | FLOYD | 12-20000 | KY 80 |  | 2.5 | 8.656 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT | D |  | PM/NH | 2019 | 1225000 | 980000 |  |  | 245000 | [5 empty] | 0
STIP | [9 empty] | FLOYD | 12-20000 | KY 80 |  | 2.5 | 8.656 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT | C |  | PM/NH | 2019 | 12250000 | 9800000 |  |  | 2450000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.21 | 2020-07-31 | ADD D PHASE TO STIP; NEW |  |  | FLOYD | 12-80000 | US 23 |  |  |  | SAFETY | SAFETY (P) | CONSTRUCT NEW INTERSECTION ON US-23 AT THE ENTRANCE TO BETSY LANE HIGH SCHOOL (18CCN). | D |  | STP | 2020 | 250000 | 250000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.211 | 2021-07-21 | ADD C PHASE TO STIP; NEW |  |  | FRANKLIN | 5-187 | US 60 |  | 13.25 | 13.4 | SAFETY | SAFETY (P) | CONSTRUCT ADDITIONAL LEFT-TURN LANE STORAGE ALONG US 60 FOR LEFT TURNS ONTO I-64 EB AND I-64 WB RAMPS. (2020CCR) | C |  | NHPP | 2021 | 1811700 | 1811700 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | FRANKLIN | 5-551 | I 64 | 4.75 | 53.11 | 57.86 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE SAFETY, TRUCK MOBILITY, AND REDUCE CONGESTION ALONG I-64 FROM DIRECTLY EAST OF US-127 TO US-60 SOUTH OF FRANKFORT. | D |  | NH | 2022 | 4300000 | 3440000 |  |  | 860000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.015 | 2019-01-25 | ADD PROJECT TO STIP; NEW |  |  | FRANKLIN | 5-565 | US 60 |  | 7.922 | 8.622 | RELIABILITY | TRANSP ENHANCEMENT(P) | SECOND ST CORRIDOR TIGER PROJECT - RECONSTRUCT SECOND ST (US 60) CORRIDOR, FROM KY 1211 (TAYLOR AVE) TO E. BROADWAY INTO A COMPLETE STREET WITH WIDER SIDEWALKS, IMPROVED SIGNALING/INTERSECTIONS, ADA ACCESSIBILITY, STREETSCAPE, BIKE LANES (2018BOP) | C |  | TGR | 2019 | 12365000 | 7990000 | [8 empty] | 0
[8 empty] | TGR | 3005023 | FRANKLIN | 5-565 | US 60 |  | 7.922 | 8.622 | RELIABILITY | TRANSP ENHANCEMENT(P) | SECOND ST CORRIDOR TIGER PROJECT - RECONSTRUCT SECOND ST (US 60) CORRIDOR, FROM KY 1211 (TAYLOR AVE) TO E. BROADWAY INTO A COMPLETE STREET WITH WIDER SIDEWALKS, IMPROVED SIGNALING/INTERSECTIONS, ADA ACCESSIBILITY, STREETSCAPE, BIKE LANES (2018BOP) | D |  | TGR | 2019 | [5 empty] | 100000 |  | OBLIGATED | 890000 |  | 890000 | 2019 | 2ND QUARTER | CITY OF FRANKFORT
STIP | [9 empty] | FRANKLIN | 5-805 | KY 3506 |  | 0.111 | 0.15 | ASSET MANAGEMENT | AM-BRIDGE (P) | DEMOLITION OF THE CLOSED ROADWAY SECTION OF THE BROADWAY BRIDGE IN FRANKFORT. | C |  | BR/STP | 2019 | 300000 | 186000 |  |  | 114000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.203 | 2020-07-15 | ADD D PHASE TO STIP; NEW |  |  | FRANKLIN | 5-805 | KY 3506 |  | 0.111 | 0.15 | ASSET MANAGEMENT | AM-BRIDGE (P) | DEMOLITION OF THE CLOSED ROADWAY SECTION OF THE BROADWAY BRIDGE IN FRANKFORT. | D |  | STP | 2020 | 200000 | 160000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.161 | 2020-02-21 | ADD PROJECT TO STIP; PARENT NO. 99-911.09; NEW |  | 5196016 | FRANKLIN | 5-936 | US 421 |  | 0 | 3.072 | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALLATION OF STRIPING ON US 421 IN FRANKLIN COUNTY. (2018BOP) | C |  | SAF | 2020 | 245000 | 245000 | [5 empty] | OBLIGATED | 246000 |  | 246000 | 2020 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.161 | 2020-02-21 | ADD PROJECT TO STIP; PARENT NO. 99-911.09; NEW | HSIP | 9010428 | FRANKLIN | 5-937 | KY 676 |  | 0 | 5.287 | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALLATION OF STRIPING ON KY 676 IN FRANKLIN COUNTY. (2018BOP) | C |  | SAF | 2020 | 415000 | 415000 | [5 empty] | OBLIGATED | 415000 |  | 415000 | 2020 | 2ND QUARTER
STIP | [9 empty] | FRANKLIN | 5-1078 | CR 1230 | 0.025 | 0.04 | 0.065 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER BENSON CREEK ON CRAB ORCHARD ROAD (CR 1230) 200 FT NW OF KY 151 NEAR I-64 EXIT 48 (037C00010N) (EBRP)(16CCR) | C |  | BR/STP | 2019 | 633500 | 392770 |  |  | 240730 | [5 empty] | 0
STIP | [9 empty] | FRANKLIN | 5-2035.7 | I 64 | 6.05 | 47.7 | 53.75 | RELIABILITY | MAJOR WIDENING(O) | WIDEN I-64 TO 6 LANES FROM KY-151 TO WEST OF THE KY-420 BRIDGE. (2004BOPC)(DESIGN FUNDED UNDER 5-2035.40)(16CCN) | R |  | NH | 2022 | 120000 | 96000 |  |  | 24000 | [5 empty] | 0
STIP | [9 empty] | FRANKLIN | 5-2035.7 | I 64 | 6.05 | 47.7 | 53.75 | RELIABILITY | MAJOR WIDENING(O) | WIDEN I-64 TO 6 LANES FROM KY-151 TO WEST OF THE KY-420 BRIDGE. (2004BOPC)(DESIGN FUNDED UNDER 5-2035.40)(16CCN) | U |  | NH | 2022 | 120000 | 96000 |  |  | 24000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.311 | 2021-07-21 | ADD C PHASE TO STIP; PARENT NO. 5-2035.70; NEW |  |  | FRANKLIN | 5-2035.8 | I 64 |  | 47 | 52 | RELIABILITY | MAJOR WIDENING(O) | Address deficiencies with I-64 bridges between MP 47 – MP 52. (Item Nos. 5-1029, 5-103, 5-1040, 5-1089 & 5-1090) | C |  | NHPP | 2021 | 32653500 | 32653500 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.306 | 2021-06-16 | ADD D PHASE TO STIP; NEW |  |  | FRANKLIN | 5-8101 | KY 55 |  | 57.95 | 58.05 | RELIABILITY | DRAINAGE IMPROVE(P) | IMPROVE KY 55 FROM ELK CREEK TO THE SHELBY COUNTY LINE (2020CCN) | D |  | SPP | 2021 | 270100 | 100 |  |  | 270000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.111 | 2019-08-02 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 4201087 | FRANKLIN | 5-9022 | US 421 |  | 5.315 | 11.132 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON US 421 FROM MP 5.315 TO 11.132 IN FRANKLIN COUNTY. (2018BOP) | D |  | SAF | 2019 | 350000 | 350000 |  |  | 0 |  |  | OBLIGATED |  | 350000 | 350000 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.3 | 2021-05-28 | ADD R PHASE TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 4201087 | FRANKLIN | 5-9022 | US 421 |  | 5.315 | 11.132 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON US 421 FROM MP 5.315 TO 11.132 IN FRANKLIN COUNTY. (2018BOP) | R |  | SAF | 2021 | 10000 | 10000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.3 | 2021-05-28 | ADD U PHASE TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 4201087 | FRANKLIN | 5-9022 | US 421 |  | 5.315 | 11.132 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON US 421 FROM MP 5.315 TO 11.132 IN FRANKLIN COUNTY. (2018BOP) | U |  | SAF | 2021 | 100000 | 100000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | FRANKLIN | 5-10000 | KY 420 |  | 1.948 | 1.956 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 420 BRIDGE OVER CEDAR RUN CREEK. (037B00011N) | D |  | BR/STP | 2019 | 210000 | 130200 |  |  | 79800 | [5 empty] | 0
STIP | [9 empty] | FRANKLIN | 5-10000 | KY 420 |  | 1.948 | 1.956 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 420 BRIDGE OVER CEDAR RUN CREEK. (037B00011N) | C |  | BR/STP | 2020 | 350000 | 217000 |  |  | 133000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.065 | 2019-05-06 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030107 | FRANKLIN | 5-10000 | KY 420 |  | 1.948 | 1.956 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 420 BRIDGE OVER CEDAR RUN CREEK. (037B00011N) | C |  | BR/STP | 2019 | 1217530 | 1217530 |  |  | 0 |  |  | OBLIGATED |  | 995306 | 995306 | 2019 | 3RD QUARTER
STIP | [9 empty] | FRANKLIN | 5-10001 | KY 1689 |  | 3.581 | 3.587 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 1689 BRIDGE OVER TRIB TO N. ELKHORN CREEK. (037B00034N) | D |  | BR/STP | 2019 | 210000 | 130200 |  |  | 79800 | [5 empty] | 0
STIP | [9 empty] | FRANKLIN | 5-10001 | KY 1689 |  | 3.581 | 3.587 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 1689 BRIDGE OVER TRIB TO N. ELKHORN CREEK. (037B00034N) | C |  | BR/STP | 2020 | 332500 | 206150 |  |  | 126350 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.075 | 2019-05-28 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030108 | FRANKLIN | 5-10001 | KY 1689 |  | 3.581 | 3.587 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 1689 BRIDGE OVER TRIB TO N. ELKHORN CREEK. (037B00034N) | C |  | STP | 2020 | 512349 | 512349 |  |  | 0 |  |  | OBLIGATED |  | 459270 | 459270 | 2019 | 3RD QUARTER
|  |  |  | ADMINISTRATIVE MODIFICATION | 2018.05 | 2019-04-16 | ADD PROJECT TO STIP; PARENT NO. 99-514.00; NEW | NHPPIM | 0644093 | FRANKLIN | 5-10030 | I 64 |  |  |  | ASSET MANAGEMENT | AM-BRIDGE (P) | BRIDGE PAINTING ON I-64 STRUCTURES OVER CEDAR RUN IN FRANKLIN COUNTY. (037B00051L, 037B00051R) | C |  | NH | 2019 | 993000 | 993000 |  |  | 0 |  |  | OBLIGATED | 839580 |  | 839580 | 2019 | 3RD QUARTER
|  |  |  | ADMINISTRATIVE MODIFICATION | 2018.05 | 2019-04-16 | ADD PROJECT TO STIP; PARENT NO. 99-514.00; NEW | NHPPIM | 0644094 | FRANKLIN | 5-10030.1 | I 64 |  |  |  | ASSET MANAGEMENT | AM-BRIDGE (P) | BRIDGE PREVENTATIVE MAINTENANCE PAINTING, OVERLAY AND JOINT REPAIRS ON I-64 STRUCTURES OVER KY RIVER IN FRANKLIN COUNTY. (037B00052L, 037B00052R) | C |  | NH | 2019 | 4178000 | 4178000 |  |  | 0 |  |  | OBLIGATED | 4314330 |  | 4314330 | 2019 | 3RD QUARTER
|  |  |  | ADMINISTRATIVE MODIFICATION | 2018.05 | 2019-04-16 | ADD PROJECT TO STIP; PARENT NO. 99-514.00; NEW | NHPPIM | 0644095 | FRANKLIN | 5-10030.2 | I 64 |  |  |  | ASSET MANAGEMENT | AM-BRIDGE (P) | BRIDGE PAINTING ON I-64 STRUCTURES OVER US 60 IN FRANKLIN COUNTY. (037B00053L, 037B00053R) | C |  | NH | 2019 | 1100000 | 1100000 |  |  | 0 |  |  | OBLIGATED | 756334 |  | 756334 | 2019 | 3RD QUARTER
STIP | [9 empty] | FRANKLIN | 5-20001 | US 60 |  | 8.475 | 10.667 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT | D |  | PM/STP | 2021 | 200000 | 160000 |  |  | 40000 | [5 empty] | 0
STIP | [9 empty] | FRANKLIN | 5-20001 | US 60 |  | 8.475 | 10.667 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT | C |  | PM/STP | 2021 | 2000000 | 1600000 |  |  | 400000 | [5 empty] | 0
STIP | [9 empty] | FRANKLIN | 5-20038 | US 127 | 7.1 | 11.9 | 19 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION ON US-127 FROM MILEPOINT 11.90 TO MILEPOINT 19.00 | C |  | PM/NH | 2022 | 1228000 | 982400 |  |  | 245600 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.229 | 2020-09-14 | ADD C PHASE TO STIP; PARENT NO. 99-224.14; NEW |  |  | FRANKLIN | 5-20058 | KY 2261 KY 3505 US 127 |  | .795 0 6.23 | 1.83 .176 7.1 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | Resurfacing of KY 2261 (MP 0.795-1.83), KY 3505 (MP 0.0-0.176), and US 127 (MP 6.23-7.1) in Franklin County, KY. | C |  | NH | 2020 | 765000 | 765000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.139 | 2019-10-25 | THIS PROJECT IS LISTED ON THE 2018 SIX YEAR PLAN; HOWEVER IT WAS INADVERTANTLY LEFT OFF THE STIP FY 19-22 SPREADSHEET. |  |  | FULTON | 1-25 | JC 9003 |  | 0 | 1.66 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE THE PURCHASE PARKWAY AT THE KENTUCKY/TENNESSEE LINE TO SOUTHWEST OF THE US-51 INTERCHANGE.(I-69 CORRIDOR IMPROVEMENT)(2012BOP) | R |  | NH | 2022 | 2500000 | 2500000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.229 | 2020-09-14 | ADD R PHASE TO STIP; NEW |  |  | FULTON HICKMAN GRAVES | 1-26 | JC 9003 |  | 1.2 | 3.434 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE THE PURCHASE PARKWAY FROM SOUTHWEST OF THE US-51 INTERCHANGE TO CARDINAL ROAD NEAR MAYFIELD INCLUDING THE KY-339 INTERCHANGE IN WINGO, KY. (I-69 CORRIDOR IMPROVEMENT) (2012BOP) (2020CCR) | R |  | NH | 2020 | 830000 | 830000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.269 | 2021-01-22 | ADD U PHASE TO STIP; NEW |  |  | FULTON HICKMAN GRAVES | 1-26 | JC 9003 |  | 1.2 | 3.434 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE THE PURCHASE PARKWAY FROM SOUTHWEST OF THE US-51 INTERCHANGE TO CARDINAL ROAD NEAR MAYFIELD INCLUDING THE KY-339 INTERCHANGE IN WINGO, KY. (I-69 CORRIDOR IMPROVEMENT) (2012BOP) (2020CCR) | U |  | NH | 2021 | 320000 | 320000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | FULTON | 1-10009 | KY 1909 |  | 0.794 | 0.802 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 1909 BRIDGE OVER LITTLE BAYOU DE CHIEN CR. (038B00075N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [7 empty] | STP | 9030002 | FULTON | 1-10009 | KY 1909 |  | 0.794 | 0.802 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 1909 BRIDGE OVER LITTLE BAYOU DE CHIEN CR. (038B00075N) | C |  | BR/STP | 2020 | 490000 | 303800 |  |  | 186200 |  |  | OBLIGATED | 715875 |  | 715875 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.017 | 2019-01-23 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD |  |  | FULTON | 1-10009 | KY 1909 |  | 0.794 | 0.802 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 1909 BRIDGE OVER LITTLE BAYOU DE CHIEN CR. (038B00075N) | C |  | STP | 2020 | 667000 | 667000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.123 | 2019-09-06 | ADD PROJECT TO STIP; PARENT NO. 99-65.16 AND 99-65.17; NEW | STPBRZ | 9030182 | FULTON | 1-10027 | KY 1128 |  | 5.336 | 5.342 | ASSET MANAGEMENT | AM-BRIDGE (P) | KY-1128 OVER FORK OF MUD CREEK (038C00042N) | C |  | BR | 2020 | 240000 | 240000 |  |  | 0 |  |  | OBLIGATED |  | 290185 | 290185 | 2019 | 4TH QUARTER
STIP | [9 empty] | FULTON | 1-20002 | JC 9003 |  | 0 | 1.78 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF JULIAN M. CARROLL PURCHASE PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 0 TO MILEPOINT 1.78 | D |  | PM/STP | 2019 | 175000 | 140000 |  |  | 35000 | [5 empty] | 0
STIP | [9 empty] | FULTON | 1-20002 | JC 9003 |  | 0 | 1.78 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF JULIAN M. CARROLL PURCHASE PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 0 TO MILEPOINT 1.78 | C |  | PM/STP | 2019 | 1750000 | 1400000 |  |  | 350000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.101 | 2019-07-18 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 0713068 | GALLATIN | 6-940 | I 71 |  | 63.5 | 63.7 | SAFETY | SAFETY-HAZARD ELIM(P) | HIGH FRICTION SURFACE TREATMENT ON I-71 BETWEEN MP 63.5 AND MP 63.7 IN GALLATIN COUNTY, KY. | C |  | SAF | 2019 | 130000 | 130000 |  |  | 0 |  |  | OBLIGATED | 130000 |  | 130000 | 2019 | 4TH QUARTER
STIP | [9 empty] | GALLATIN | 6-8910 | I 71 | 1.2 | 62.8 | 64 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE GEOMETRICS ON I-71 FROM US-127 TO MP 64. (16CCN)(18CCR) | D |  | NH | 2021 | 2200000 | 1760000 |  |  | 440000 | [5 empty] | 0
STIP | [9 empty] | GALLATIN | 6-8910 | I 71 | 1.2 | 62.8 | 64 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE GEOMETRICS ON I-71 FROM US-127 TO MP 64. (16CCN)(18CCR) | R |  | NH | 2022 | 1500000 | 1200000 |  |  | 300000 | [5 empty] | 0
STIP | [9 empty] | GALLATIN | 6-8910 | I 71 | 1.2 | 62.8 | 64 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE GEOMETRICS ON I-71 FROM US-127 TO MP 64. (16CCN)(18CCR) | U |  | NH | 2022 | 500000 | 400000 |  |  | 100000 | [5 empty] | 0
STIP | [9 empty] | GALLATIN | 6-20022 | I 71 |  | 59.673 | 69.89 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-071 BOTH DIRECTION(S) FROM MILEPOINT 59.673 TO MILEPOINT 69.89 | D |  | PM/NH | 2022 | 1025000 | 820000 |  |  | 205000 | [5 empty] | 0
STIP | [9 empty] | GALLATIN | 6-20022 | I 71 |  | 59.673 | 69.89 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-071 BOTH DIRECTION(S) FROM MILEPOINT 59.673 TO MILEPOINT 69.89 | C |  | PM/NH | 2022 | 10250000 | 8200000 |  |  | 2050000 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 0703345 | GARRARD | 7-1122 | KY 563 | 0.1 | 3.84 | 3.915 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON KY-563 (MP 3.89) OVER SUGAR CREEK; E-@ JCT KY 39; 040B00034N | C |  | BR/STP | 2019 | 406000 | 251720 |  |  | 154280 |  |  | OBLIGATED | 52000 |  | 52000 | 2020 | 1ST QUARTER
STIP | [9 empty] | GARRARD | 7-1138 | KY 1972 | 0.01 | 1.76 | 1.77 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER GILBERTS CREEK ON KY 1972 1.4 MI E OF CRAB ORCHARD ROAD (CR 1226) AT SECL OF LANCASTER. (040B00024N)(EBRP) | D |  | BR/STP | 2019 | 210000 | 130200 |  |  | 79800 | [5 empty] | 0
STIP | [9 empty] | GARRARD | 7-1138 | KY 1972 | 0.01 | 1.76 | 1.77 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER GILBERTS CREEK ON KY 1972 1.4 MI E OF CRAB ORCHARD ROAD (CR 1226) AT SECL OF LANCASTER. (040B00024N)(EBRP) | C |  | BR/STP | 2020 | 647500 | 401450 |  |  | 246050 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.075 | 2019-05-28 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030138 | GARRARD | 7-1138 | KY 1972 | 0.01 | 1.76 | 1.77 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER GILBERTS CREEK ON KY 1972 1.4 MI E OF CRAB ORCHARD ROAD (CR 1226) AT SECL OF LANCASTER. (040B00024N)(EBRP) | C |  | STP | 2020 | 991310 | 991310 |  |  | 0 |  |  | OBLIGATED |  | 795975 | 795975 | 2019 | 3RD QUARTER
STIP | [9 empty] | GARRARD | 7-10010 | KY 1972 |  | 2.099 | 2.105 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 1972 BRIDGE OVER BRANCH OF GILBERTS CREEK. (040B00025N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [9 empty] | GARRARD | 7-10010 | KY 1972 |  | 2.099 | 2.105 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 1972 BRIDGE OVER BRANCH OF GILBERTS CREEK. (040B00025N) | C |  | BR/STP | 2020 | 416500 | 258230 |  |  | 158270 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.075 | 2019-05-28 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030115 | GARRARD | 7-10010 | KY 1972 |  | 2.099 | 2.105 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 1972 BRIDGE OVER BRANCH OF GILBERTS CREEK. (040B00025N) | C |  | STP | 2020 | 605360 | 605360 |  |  | 0 |  |  | OBLIGATED |  | 769575 | 769575 | 20129 | 3RD QUARTER
STIP | [7 empty] | STPBRZ | 603263 | GRANT | 6-8714 | CR 1138 | 0.05 | 0.28 | 0.33 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON SOUTH END OF BLANCHET ROAD 0.3 MILES NORTHEAST OF US 25. 041C00012N (12CCN) | R |  | BR/STP | 2019 | 1141000 | 707420 |  |  | 433580 |  |  | OBLIGATED | 270000 |  | 270000 | 2019 | 2ND QUARTER
STIP | [7 empty] | STPBRZ | 603263 | GRANT | 6-8714 | CR 1138 | 0.05 | 0.28 | 0.33 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON SOUTH END OF BLANCHET ROAD 0.3 MILES NORTHEAST OF US 25. 041C00012N (12CCN) | C |  | BR/STP | 2019 | 1141000 | 707420 |  |  | 433580 |  |  | OBLIGATED | 2454870 |  | 2454870 | 2019 | 2ND QUARTER
STIP | [9 empty] | GRANT | 6-8715 | CR 1138 | 0.07 | 1.95 | 2.02 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON NORTH END OF BLANCHET ROAD 0.2 MILES SOUTHEAST OF THE JUNCTION WITH US 25. 041C00014N (12CCN) | C |  | BR/STP | 2020 | 2604000 | 1614480 |  |  | 989520 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.283 | 2021-03-22 | UPDATE FISCAL YEAR AND FUND AMOUNT; MOD |  |  | GRANT | 6-8715 | CR 1138 | 0.07 | 1.95 | 2.02 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON NORTH END OF BLANCHET ROAD 0.2 MILES SOUTHEAST OF THE JUNCTION WITH US 25. 041C00014N (12CCN) | C |  | STP | 2021 | 3329700 | 3329700 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | GRANT | 6-8716 | CR 1142 | 0.05 | 0.02 | 0.07 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON NORTH END OF DELANEY ROAD 0.1 MILE NORTH OF THE JUNCTION WITH US 25. 041C00016N (12CCN) | C |  | BR/STP | 2020 | 2240000 | 1388800 |  |  | 851200 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.139 | 2019-10-25 | ADD PROJECT TO STIP; PARENT NO. 99-911.07; NEW | HSIP | 5140041 | GRANT | 6-9019 | KY 22 |  | 5.758 | 10.522 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 22 FROM MP 5.758 TO MP 10.522 IN GRANT COUNTY. (2018BOP) | C |  | SAF | 2020 | 2258000 | 2258000 |  |  | 0 |  |  | OBLIGATED | 2258000 |  | 2258000 | 2020 | 1ST QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.175 | 2020-04-09 | ADD D PHASE TO STIP; PARENT NO. 99-911.09; NEW |  |  | GRANT | 6-9025 | KY 467 |  | 3.8 | 9 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 467 FROM MP 3.800 TO MP 9.000 IN GRANT COUNTY, KY. (2018BOP) | D |  | SAF | 2020 | 300000 | 300000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | GRANT | 6-10001 | KY 22 |  | 6.594 | 6.64 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-22 BRIDGE OVER CLARKS CRK+BATON ROUGE R. (041B00011N) | D |  | BR/STP | 2019 | 210000 | 130200 |  |  | 79800 | [5 empty] | 0
STIP | [9 empty] | GRANT | 6-10001 | KY 22 |  | 6.594 | 6.64 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-22 BRIDGE OVER CLARKS CRK+BATON ROUGE R. (041B00011N) | C |  | BR/STP | 2020 | 1732500 | 1074150 |  |  | 658350 | [5 empty] | 0
STIP | [9 empty] | GRANT | 6-10002 | KY 22 |  | 3.371 | 3.431 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-22 BRIDGES OVER EAGLE CREEK (041B00014N) AND RATTLESNAKE CREEK (041B00013N). | D |  | BR/STP | 2019 | 577500 | 358050 |  |  | 219450 | [5 empty] | 0
STIP | [9 empty] | GRANT | 6-10002 | KY 22 |  | 3.371 | 3.431 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-22 BRIDGES OVER EAGLE CREEK (041B00014N) AND RATTLESNAKE CREEK (041B00013N). | C |  | BR/STP | 2020 | 4165000 | 2582300 |  |  | 1582700 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.021 | 2019-02-04 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030031 | GRANT | 6-10002 | KY 22 |  | 3.371 | 3.431 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-22 BRIDGES OVER EAGLE CREEK (041B00014N) AND RATTLESNAKE CREEK (041B00013N). | C |  | STP | 2019 | 483700 | 483700 |  |  | 0 |  |  | OBLIGATED |  | 1789241 | 1789241 | 2019 | 2ND QUARTER
[8 empty] | STPBRZ | 9030033 | GRANT | 6-10002.1 | KY 22 |  | 3.371 | 3.431 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-22 BRIDGES OVER EAGLE CREEK (041B00014N) AND RATTLESNAKE CREEK (041B00013N). | C |  | STP | 2019 | [7 empty] | OBLIGATED |  | 419325 | 419325 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.123 | 2019-09-06 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030033 | GRANT | 6-10002.1 | KY 22 |  | 3.371 | 3.431 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-22 BRIDGES OVER EAGLE CREEK (041B00014N) AND RATTLESNAKE CREEK (041B00013N). | C |  | BR | 2020 | 543646 | 543646 | [5 empty] | OBLIGATED |  | 948153 | 948153 | 2019 | 2ND QUARTER
STIP | [9 empty] | GRANT | 6-10003 | CR 1108 |  | 3.007 | 3.013 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF CYNTHIANA ROAD BRIDGE OVER COOPERTOWN CREEK. (041C00008N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [9 empty] | GRANT | 6-10003 | CR 1108 |  | 3.007 | 3.013 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF CYNTHIANA ROAD BRIDGE OVER COOPERTOWN CREEK. (041C00008N) | C |  | BR/STP | 2020 | 367500 | 227850 |  |  | 139650 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.046 | 2019-04-07 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030098 | GRANT | 6-10003 | CR 1108 |  | 3.007 | 3.013 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF CYNTHIANA ROAD BRIDGE OVER COOPERTOWN CREEK. (041C00008N) | C |  | BR/STP | 2019 | 440310 | 440310 |  |  | 0 |  |  | OBLIGATED | 478085 |  | 478085 | 2019 | 3RD QUARTER
STIP | [9 empty] | GRANT | 6-10010 | KY 22 |  | 6.594 | 6.64 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 22 BRIDGE OVER CLARKS CRK+BATON ROUGE R. (041B00011N) | D |  | BR/STP | 2019 | 420000 | 260400 |  |  | 159600 | [5 empty] | 0
STIP | [9 empty] | GRANT | 6-10010 | KY 22 |  | 6.594 | 6.64 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 22 BRIDGE OVER CLARKS CRK+BATON ROUGE R. (041B00011N) | C |  | BR/STP | 2020 | 2940000 | 1822800 |  |  | 1117200 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.021 | 2019-02-04 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030032 | GRANT | 6-10010 | KY 22 |  | 6.594 | 6.64 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 22 BRIDGE OVER CLARKS CRK+BATON ROUGE R. (041B00011N) | C |  | STP | 2019 | 1750000 | 1750000 |  |  | 0 |  |  | OBLIGATED |  | 1798294 | 1798294 | 2019 | 2ND QUARTER
STIP | [9 empty] | GRANT | 6-20023 | I 75 |  | 143.239 | 145.5 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-075 NON-CARDINAL DIRECTION(S) FROM MILEPOINT 143.239 TO MILEPOINT 145.5 | D |  | PM/NH | 2020 | 90000 | 72000 |  |  | 18000 | [5 empty] | 0
STIP | [9 empty] | GRANT | 6-20023 | I 75 |  | 143.239 | 145.5 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-075 NON-CARDINAL DIRECTION(S) FROM MILEPOINT 143.239 TO MILEPOINT 145.5 | C |  | PM/NH | 2020 | 900000 | 720000 |  |  | 180000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.118 | 2019-08-19 | COST INCREASE BASED ON NEW ENGINEERING ESTIMATE; MOD | NHPPIM | 0756104 | GRANT | 6-20023 | I 75 |  | 143.239 | 145.5 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-075 NON-CARDINAL DIRECTION(S) FROM MILEPOINT 143.239 TO MILEPOINT 145.5 | C |  | PM/NH | 2019 | 1530650 | 1530650 |  |  | 0 |  |  | OBLIGATED | 500000 | 1171625 | 1671625 | 2019 | 4TH QUARTER
STIP | [9 empty] | GRANT | 6-20024 | I 75 |  | 145.5 | 152.122 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-075 NON-CARDINAL DIRECTION(S) FROM MILEPOINT 145.5 TO MILEPOINT 152.122 | D |  | PM/NH | 2022 | 275000 | 220000 |  |  | 55000 | [5 empty] | 0
STIP | [9 empty] | GRANT | 6-20024 | I 75 |  | 145.5 | 152.122 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-075 NON-CARDINAL DIRECTION(S) FROM MILEPOINT 145.5 TO MILEPOINT 152.122 | C |  | PM/NH | 2022 | 2750000 | 2200000 |  |  | 550000 | [5 empty] | 0
STIP | [9 empty] | GRANT | 6-20025 | I 75 |  | 152.112 | 157.7 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-075 BOTH DIRECTION(S) FROM MILEPOINT 152.112 TO MILEPOINT 157.7 | D |  | PM/NH | 2019 | 970000 | 776000 |  |  | 194000 | [5 empty] | 0
STIP | [7 empty] | NHPP | 0756103 | GRANT | 6-20025 | I 75 |  | 152.112 | 157.7 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-075 BOTH DIRECTION(S) FROM MILEPOINT 152.112 TO MILEPOINT 157.7 | C |  | PM/NH | 2019 | 9700000 | 7760000 |  |  | 1940000 |  |  | OBLIGATED | 4000000 |  | 4000000 | 2019 | 4TH QUARTER
STIP | [9 empty] | GRANT | 6-20027 | I 75 |  | 162.52 | 164.4 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-075 BOTH DIRECTION(S) FROM MILEPOINT 162.52 TO MILEPOINT 164.4 | D |  | PM/NH | 2019 | 220000 | 176000 |  |  | 44000 | [5 empty] | 0
STIP | [7 empty] | NHPPIM | 0757149 | GRANT | 6-20027 | I 75 |  | 162.52 | 164.4 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-075 BOTH DIRECTION(S) FROM MILEPOINT 162.52 TO MILEPOINT 164.4 | C |  | PM/NH | 2019 | 2200000 | 1760000 |  |  | 440000 |  |  | OBLIGATED | 3499420 |  | 3499420 | 2019 | 2ND QUARTER
STIP | [9 empty] | GRANT | 6-20029 | KY 22 |  | 10.748 | 11.544 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | D |  | PM/STP | 2021 | 47500 | 38000 |  |  | 9500 | [5 empty] | 0
STIP | [9 empty] | GRANT | 6-20029 | KY 22 |  | 10.748 | 11.544 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | C |  | PM/STP | 2021 | 475000 | 380000 |  |  | 95000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.218 | 2020-08-28 | ADD D PHASE TO STIP; NEW |  |  | GRANT | 6-20057 | I-75 |  | 143.239 | 145.5 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRSS PAVEMENT CONDITIONS OF I-75 CARDINAL DIRECTION FROM MP 143.239 TO MP 145.500 IN GRANT COUNTY. | D |  | NH | 2020 | 180000 | 180000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.321 | 2021-08-17 | ADD C PHASE TO STIP; NEW |  |  | GRANT | 6-20057 | I-75 |  | 143.239 | 145.5 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRSS PAVEMENT CONDITIONS OF I-75 CARDINAL DIRECTION FROM MP 143.239 TO MP 145.500 IN GRANT COUNTY. | C |  | NH | 2021 | 2700000 | 2700000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.229 | 2020-09-14 | ADD C PHASE TO STIP; PARENT NO. 99-224.14; NEW |  |  | GRANT | 6-20058 | KY 467 KY 2944 |  | 2.5 0 | 11.704 .889 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | RESURFACING OF KY 467 (MP 2.500-11.704) AND KY 2944 (MP 0.000-0.889) IN GRANT COUNTY, KY. | C |  | STP | 2020 | 1945187 | 1945187 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | GRAVES | 1-1157 | CR 1088 | 0.1 | 0.3 | 0.4 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER PANTHER CREEK ON MCKENDREE CHURCH RD (CR 1088) 0.3 MI E OF KY 301 042C00010N | D |  | BR/STP | 2019 | 280000 | 173600 |  |  | 106400 | [5 empty] | 0
STIP | [9 empty] | GRAVES | 1-1157 | CR 1088 | 0.1 | 0.3 | 0.4 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER PANTHER CREEK ON MCKENDREE CHURCH RD (CR 1088) 0.3 MI E OF KY 301 042C00010N | C |  | BR/STP | 2022 | 553000 | 342860 |  |  | 210140 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.123 | 2019-09-06 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030184 | GRAVES | 1-1157 | CR 1088 | 0.1 | 0.3 | 0.4 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER PANTHER CREEK ON MCKENDREE CHURCH RD (CR 1088) 0.3 MI E OF KY 301 042C00010N | C |  | BR | 2020 | 790218 | 790218 |  |  | 0 |  |  | OBLIGATED |  | 662785 | 662785 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.087 | 2019-06-21 | ADD PROJECT TO STIP; PARENT NO. 1-9008.00; NEW | HSIP | 9010377 | GRAVES | 1-9008.2 | KY 58 KY 131 |  | 8 0 | 8.3 .1 | SAFETY | SAFETY-HAZARD ELIM(P) | UPDATE THE SIGNING AND STRIPING AND ACCESS MANAGEMENT IMPROVEMENTS NEAR THE INTERSECTION OF KY 58 & KY 131. (2018BOP) | C |  | SAF | 2019 | 53000 | 53000 |  |  | 0 |  |  | OBLIGATED |  | 84450 | 84450 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.311 | 2021-07-21 | ADD C PHASE TO STIP; PARENT NO. 99-911.08; NEW |  |  | GRAVES | 1-9011 | KY 80 |  | 2.3 | 8.51 | SAFETY | SAFETY-HAZARD ELIM(P) | EXTEND 4 REINFORCED CONCRETE BOX CULVERTS ALONG KY 80. (2018BOP) | C |  | SAF | 2021 | 359000 | 359000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.053 | 2019-04-25 | ADD D PHASE TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 0451008 | GRAVES | 1-9013 | US 45 |  | 25.077 | 25.645 | SAFETY | SAFETY-HAZARD ELIM(P) | CONSTRUCTION OF A J-TURN AT THE INTERSECTION OF US 45 AND KY 408. (2018BOP) | D |  | SAF | 2019 | 175000 | 175000 |  |  | 0 |  |  | OBLIGATED |  | 175000 | 175000 | 2019 | 3RD QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.177 | 2020-04-24 | ADD C PHASE TO STIP; PARENT NO. 99-911.08; NEW |  |  | GRAVES | 1-9013 | US 45 |  | 25.077 | 25.645 | SAFETY | SAFETY-HAZARD ELIM(P) | CONSTRUCTION OF A J-TURN AT THE INTERSECTION OF US 45 AND KY 408. (2018BOP) | C |  | SAF | 2020 | 1045000 | 1045000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.175 | 2020-04-09 | ADD D PHASE TO STIP; PARENT NO. 99-911.09; NEW |  |  | GRAVES | 1-9020 | KY 129 |  | 8.734 | 15.402 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 129 FROM MP 8.734 TO MP 15.402 IN GRAVES COUNTY, KY. (2018BOP) | D |  | SAF | 2020 | 300000 | 300000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | GRAVES | 1-10001 | KY 1890 |  | 1.718 | 1.768 | ASSET MANAGEMENT | AM-BRIDGE (P) | REPLACE KY-1890 BRIDGE OVER LITTLE MAYFIELD CREEK. (042B00191N) | D |  | BR/STP | 2019 | 140000 | 86800 |  |  | 53200 | [5 empty] | 0
STIP | [9 empty] | GRAVES | 1-10001 | KY 1890 |  | 1.718 | 1.768 | ASSET MANAGEMENT | AM-BRIDGE (P) | REPLACE KY-1890 BRIDGE OVER LITTLE MAYFIELD CREEK. (042B00191N) | C |  | BR/STP | 2020 | 507500 | 314650 |  |  | 192850 | [5 empty] | 0
STIP | [9 empty] | GRAVES | 1-10002 | CR 1214 |  | 0.555 | 0.563 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF MARTIN ROAD BRIDGE OVER BRANCH-OBION CREEK. (042C00250N) | D |  | BR/STP | 2019 | 200000 | 124000 |  |  | 76000 | [5 empty] | 0
STIP | [9 empty] | GRAVES | 1-10002 | CR 1214 |  | 0.555 | 0.563 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF MARTIN ROAD BRIDGE OVER BRANCH-OBION CREEK. (042C00250N) | C |  | BR/STP | 2021 | 423500 | 262570 |  |  | 160930 | [5 empty] | 0
STIP | [9 empty] | GRAVES | 1-10010 | KY 1485 |  | 2.532 | 2.519 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 1485 BRIDGE OVER TERRAPIN CREEK. (042B00136N) | D |  | BR/STP | 2019 | 210000 | 130200 |  |  | 79800 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030248 | GRAVES | 1-10010 | KY 1485 |  | 2.532 | 2.519 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 1485 BRIDGE OVER TERRAPIN CREEK. (042B00136N) | C |  | BR/STP | 2020 | 875000 | 542500 |  |  | 332500 |  |  | OBLIGATED | 120000 | 1134105 | 1254105 | 2020 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.123 | 2019-09-06 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD |  |  | GRAVES | 1-10010 | KY 1485 |  | 2.532 | 2.519 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 1485 BRIDGE OVER TERRAPIN CREEK. (042B00136N) | C |  | BR | 2020 | 1051000 | 1051000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.075 | 2019-05-28 | ADD PROJECT TO STIP; NEW | STPBRZ | 9030134 | GRAVES | 1-10015 | CR 1408 |  | 1.314 |  | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES ON ALBEN BARKLEY ROAD (CR 1408) OVER BRANCH-WILSON CREEK. (042C00219N) | C |  | STP | 2020 | 647295 | 647295 |  |  | 0 |  |  | OBLIGATED |  | 670105 | 670105 | 2019 | 4TH QUARTER
STIP | [9 empty] | GRAVES | 1-20004 | JC 9003 |  | 22 | 34.49 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF JULIAN M. CARROLL PURCHASE PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 22 TO MILEPOINT 34.49 | D |  | PM/NH | 2022 | 1000000 | 800000 |  |  | 200000 | [5 empty] | 0
STIP | [9 empty] | GRAVES | 1-20004 | JC 9003 |  | 22 | 34.49 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF JULIAN M. CARROLL PURCHASE PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 22 TO MILEPOINT 34.49 | C |  | PM/NH | 2022 | 1000000 | 800000 |  |  | 200000 | [5 empty] | 0
STIP | [9 empty] | GRAVES | 1-20028 | KY 94 | 5.3 | 10.49 | 15.78 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION ON KY-94 FROM MILEPOINT 10.49 TO MILEPOINT 15.78 | C |  | PM/STP | 2022 | 825000 | 660000 |  |  | 165000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.306 | 2021-06-16 | ADD D PHASE TO STIP; NEW |  |  | GRAVES | 1-80103 | KY 303 |  | 16.034 | 16.807 | RELIABILITY | MINOR WIDENING(O) | WIDEN KY 303 FROM MP 16.034 (EAST FARTHING ST) TO MP 16.807 (CHARLES DR) (2020CCN) | D |  | SPP | 2021 | 850100 | 100 |  |  | 850000 | [5 empty] | 0
STIP | [9 empty] | GRAYSON | 4-8502.1 | US 62 |  | 23 | 24.3 | RELIABILITY | MINOR WIDENING(O) | IMPROVE US 62 FROM LEITCHFIELD BYPASS (KY3155) TO JUST EAST OF BEEHIVE CURVE. CONSTRUCTION SEGMENT 1. | C |  | STP | 2020 | 2000000 | 2000000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.265 | 2020-12-23 | INCREASE FUND AMOUNT BASED ON NEW ESTIMATE; MOD |  |  | GRAYSON | 4-8502.1 | US 62 |  | 23 | 24.3 | RELIABILITY | MINOR WIDENING(O) | IMPROVE US 62 FROM LEITCHFIELD BYPASS (KY3155) TO JUST EAST OF BEEHIVE CURVE. CONSTRUCTION SEGMENT 1. | C |  | STP | 2021 | 7200000 | 7200000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.274 | 2021-02-04 | ADD U PHASE TO STIP; PARENT NO. 4-8502.00; NEW |  |  | GRAYSON | 4-8502.2 | US 62 |  | 24.2 | 25.5 | RELIABILITY | MINOR WIDENING(O) | IMPROVE US 62 FROM JUST EAST OF BEEHIVE CURVE TO KY224. CONSTRUCTION SEGMENT 2. | U |  | STP | 2021 | 1500000 | 1500000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | GRAYSON | 4-8502.11 | US 62 |  | 23 | 24.3 | RELIABILITY | PREFINANCD CONVRSN(O) | IMPROVE US 62 FROM LEITCHFIELD BYPASS (KY3155) TO JUST EAST OF BEEHIVE CURVE. CONSTRUCTION SEGMENT 1. | C |  | STP | 2021 | 2000000 | 1600000 |  |  | 400000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.015 | 2019-01-25 | ADD PROJECT TO STIP; D PHASE; NEW | STP | 5374011 | GRAYSON | 4-8954 | KY 3155 |  |  |  | RELIABILITY | NEW ROUTE(O) | EXTEND THE WILLIAM THOMASON BYWAY (KY 3155) FROM THE SOUTHERN INTERSECTION AT KY 259 WESTERLY TO KY 54. (16CCN)(18CCN) | D |  | STP | 2019 | 1000000 | 1000000 | 1000000 |  | 0 |  |  | OBLIGATED | 750000 | 600000 | 1350000 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.015 | 2019-01-25 | ADD PROJECT TO STIP; R PHASE; NEW | STP | 5374011 | GRAYSON | 4-8954 | KY 3155 |  |  |  | RELIABILITY | NEW ROUTE(O) | EXTEND THE WILLIAM THOMASON BYWAY (KY 3155) FROM THE SOUTHERN INTERSECTION AT KY 259 WESTERLY TO KY 54. (16CCN)(18CCN) | R |  | STP | 2021 | 5800000 | 5800000 | 5800000 |  | 0 |  |  | OBLIGATED |  | 4720000 | 4720000 | 2020 | 1ST QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.015 | 2019-01-25 | ADD PROJECT TO STIP; U PHASE; NEW |  |  | GRAYSON | 4-8954 | KY 3155 |  |  |  | RELIABILITY | NEW ROUTE(O) | EXTEND THE WILLIAM THOMASON BYWAY (KY 3155) FROM THE SOUTHERN INTERSECTION AT KY 259 WESTERLY TO KY 54. (16CCN)(18CCN) | U |  | STP | 2021 | 1700000 | 1700000 | 1700000 |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.015 | 2019-01-25 | ADD PROJECT TO STIP; C PHASE; NEW |  |  | GRAYSON | 4-8954 | KY 3155 |  |  |  | RELIABILITY | NEW ROUTE(O) | EXTEND THE WILLIAM THOMASON BYWAY (KY 3155) FROM THE SOUTHERN INTERSECTION AT KY 259 WESTERLY TO KY 54. (16CCN)(18CCN) | C |  | STP | 2022 | 9000000 | 9000000 | 9000000 |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.087 | 2019-06-21 | ADD PROJECT TO STIP; PARENT NO. 99-911.06; NEW | HSIP | 9010299 | GRAYSON | 4-9007 | KY 1214 |  | 6.3 | 14.028 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ALONG KY 1214 BETWEEN MP 6.300 AND MP 14.028 IN GRAYSON COUNTY, KY. (2016BOP) | C |  | SAF | 2019 | 1475000 | 1475000 |  |  | 0 |  |  | OBLIGATED |  | 2243024 | 2243024 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.111 | 2019-08-02 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 0051035 | GRAYSON | 4-9013 | KY 259 |  | 16.39 0 | 21.459 1.921 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 259 FROM MP 16.390 TO MP 21.459 IN GRAYSON COUNTY AND MP 0.000 TO MP 1.921 IN BRECKINRIDGE COUNTY.(2018BOP) | D |  | SAF | 2019 | 350000 | 350000 |  |  | 0 |  |  | OBLIGATED |  | 350000 | 350000 | 2019 | 4TH QUARTER
STIP | [9 empty] | GRAYSON | 4-10000 | CR 1161 |  | 2.945 | 2.953 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF HORNTOWN RD BRIDGE OVER ROCK CREEK. (043C00011N) | D |  | BR/STP | 2019 | 100000 | 62000 |  |  | 38000 | [5 empty] | 0
STIP | [9 empty] | GRAYSON | 4-10000 | CR 1161 |  | 2.945 | 2.953 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF HORNTOWN RD BRIDGE OVER ROCK CREEK. (043C00011N) | C |  | BR/STP | 2020 | 220000 | 136400 |  |  | 83600 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.075 | 2019-05-28 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030129 | GRAYSON | 4-10000 | CR 1161 |  | 2.945 | 2.953 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF HORNTOWN RD BRIDGE OVER ROCK CREEK. (043C00011N) | C |  | STP | 2020 | 545000 | 545000 |  |  | 0 |  |  | OBLIGATED |  | 480535 | 480535 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.123 | 2019-09-06 | ADD PROJECT TO STIP; PARENT NO. 99-65.16 AND 99-65.17; NEW | STPBRZ | 9030190 | GRAYSON | 4-10017 | CR 1690 |  | 0.02 |  | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES ON TAYLORS FORK ROAD (CR 1690) OVER TAYLORS FORK CREEK. (043C00062N) | C |  | BR | 2020 | 525000 | 525000 |  |  | 0 |  |  | OBLIGATED |  | 648975 | 648975 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.123 | 2019-09-06 | ADD PROJECT TO STIP; PARENT NO. 99-65.16 AND 99-65.17; NEW |  |  | GRAYSON | 4-10018 | CR 1564 |  | 1.144 |  | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES ON SHAW WELL RD (CR 1564) OVER SHORT CREEK. (043C00027N) | C |  | BR | 2020 | 850000 | 850000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.25 | 2020-10-22 | ADD C PHASE TO STIP; NEW |  |  | GRAYSON | 4-10023 | CR 1100 |  | 0.142 | 0.148 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF CR 1100 BRIDGE OVER BIG RUN BRANCH. 043C00057N | C |  | STP | 2021 | 255000 | 255000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.244 | 2020-10-16 | ADD C PHASE TO STIP; PARENT NO. 99-514.01; NEW |  |  | GRAYSON | 4-10044 | KY 88 |  | 11.05 | 11.18 | RELIABILITY | AM-BRIDGE (P) | PREVENTATIVE BRIDGE MAINTENANCE CLEANING AND PAINTING FOR BRIDGE ON KY 88 OVER ROCK CREEK. (043N00008N) | C |  | STP | 2021 | 1126950 | 1126950 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | GRAYSON | 4-20000 | WK 9001 |  | 108 | 111.25 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF WENDELL H. FORD WESTERN KY PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 108.00 TO MILEPOINT 111.25 (110.50 NON-CARDINAL) | D |  | PM/NH | 2020 | 230000 | 184000 |  |  | 46000 | [5 empty] | 0
STIP | [9 empty] | GRAYSON | 4-20000 | WK 9001 |  | 108 | 111.25 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF WENDELL H. FORD WESTERN KY PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 108.00 TO MILEPOINT 111.25 (110.50 NON-CARDINAL) | C |  | PM/NH | 2020 | 2300000 | 1840000 |  |  | 460000 | [5 empty] | 0
STIP | [9 empty] | GRAYSON | 4-20001 | WK 9001 |  | 111.25 | 112.48 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF WENDELL H. FORD WESTERN KY PARKWAY CARDINAL DIRECTION(S) FROM MILEPOINT 111.25 TO MILEPOINT 112.48 | D |  | PM/NH | 2022 | 50000 | 40000 |  |  | 10000 | [5 empty] | 0
STIP | [9 empty] | GRAYSON | 4-20001 | WK 9001 |  | 111.25 | 112.48 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF WENDELL H. FORD WESTERN KY PARKWAY CARDINAL DIRECTION(S) FROM MILEPOINT 111.25 TO MILEPOINT 112.48 | C |  | PM/NH | 2022 | 500000 | 400000 |  |  | 100000 | [5 empty] | 0
STIP | [9 empty] | GRAYSON | 4-20002 | WK 9001 |  | 112.4 | 114.8 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF WENDELL H. FORD WESTERN KY PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 112.4 TO MILEPOINT 114.8 | D |  | PM/NH | 2021 | 190000 | 152000 |  |  | 38000 | [5 empty] | 0
STIP | [9 empty] | GRAYSON | 4-20002 | WK 9001 |  | 112.4 | 114.8 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF WENDELL H. FORD WESTERN KY PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 112.4 TO MILEPOINT 114.8 | C |  | PM/NH | 2021 | 1900000 | 1520000 |  |  | 380000 | [5 empty] | 0
STIP | [7 empty] | NHPP | 0021047 | GRAYSON | 4-20004 | WK 9001 |  | 88.433 | 91.2 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF WENDELL H. FORD WESTERN KY PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 88.433 TO MILEPOINT 91.2 | C |  | PM/NH | 2020 | 2590000 | 2072000 |  |  | 518000 |  |  | OBLIGATED |  | 2026300 | 2026300 | 2019 | 3RD QUARTER
STIP | [9 empty] | GRAYSON | 4-20006 | WK 9001 |  | 91.2 | 95 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF WENDELL H. FORD WESTERN KY PARKWAY NON-CARDINAL DIRECTION(S) FROM MILEPOINT 91.2 TO MILEPOINT 95 | D |  | PM/NH | 2020 | 150000 | 120000 |  |  | 30000 | [5 empty] | 0
STIP | [7 empty] | NHPP | 0021049 | GRAYSON | 4-20006 | WK 9001 |  | 91.2 | 95 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF WENDELL H. FORD WESTERN KY PARKWAY NON-CARDINAL DIRECTION(S) FROM MILEPOINT 91.2 TO MILEPOINT 95 | C |  | PM/NH | 2020 | 1500000 | 1200000 |  |  | 300000 |  |  | OBLIGATED | 1426916 |  | 1426916 | 2019 | 3RD QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.279 | 2021-03-05 | ADD C PHASE TO STIP; PARENT NO. 99-224.14; NEW |  |  | GRAYSON | 4-20038 | KY 259 |  | 0 | 6.07 | RELIABILITY | AM-PAVEMENT (PRI)(P) | Resurface KY 259 from MP 0.00 to MP 6.07 in Grayson County, KY. | C |  | STP | 2021 | 612819 | 612819 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | GREEN | 4-397.12 | US 68 | 1.093 | 9.682 | 10.775 | RELIABILITY | RECONSTRUCTION(O) | ADDRESS SAFETY, GEOMETRIC DEFICIENCIES AND MAINTENANCE ISSUES ALONG US 68 FROM 1600 FEET WEST OF SOUTH THURLOW RD (MP 9.682) EXTENDING TO THE RUSSELL CREEK BRIDGE (MP 10.775) (3-203.00 STUDY RECOMMENDATION #11)(DESIGN UNDER 4-397)(2016BOP)(18CCN) | R |  | NH | 2019 | 250000 | 250000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | GREEN | 4-397.12 | US 68 | 1.093 | 9.682 | 10.775 | RELIABILITY | RECONSTRUCTION(O) | ADDRESS SAFETY, GEOMETRIC DEFICIENCIES AND MAINTENANCE ISSUES ALONG US 68 FROM 1600 FEET WEST OF SOUTH THURLOW RD (MP 9.682) EXTENDING TO THE RUSSELL CREEK BRIDGE (MP 10.775) (3-203.00 STUDY RECOMMENDATION #11)(DESIGN UNDER 4-397)(2016BOP)(18CCN) | U |  | NH | 2019 | 720000 | 720000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | GREEN | 4-397.12 | US 68 | 1.093 | 9.682 | 10.775 | RELIABILITY | RECONSTRUCTION(O) | ADDRESS SAFETY, GEOMETRIC DEFICIENCIES AND MAINTENANCE ISSUES ALONG US 68 FROM 1600 FEET WEST OF SOUTH THURLOW RD (MP 9.682) EXTENDING TO THE RUSSELL CREEK BRIDGE (MP 10.775) (3-203.00 STUDY RECOMMENDATION #11)(DESIGN UNDER 4-397)(2016BOP)(18CCN) | C |  | NH | 2020 | 2740000 | 2740000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.254 | 2020-11-06 | ADD D PHASE TO STIP; PARENT NO. 8-8712.00; NEW |  |  | GREEN | 4-8712 | KY 61 |  | 11.113 | 14.093 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE SAFETY AND MOBILITY ON KY-61 FROM PITMAN CREEK BRIDGE TO DOC WARD RD (CR 1314). (12CCN)(14CCR)(16CCR) (2020CCR) | D |  | STP | 2021 | 750000 | 750000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | GREEN | 4-10001 | CR 1347 |  | 0.045 | 0.051 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF JONES SCHOOL RD BRIDGE OVER BRUSH CREEK. (044C00023N) | D |  | BR/STP | 2019 | 100000 | 62000 |  |  | 38000 | [5 empty] | 0
STIP | [9 empty] | GREEN | 4-10001 | CR 1347 |  | 0.045 | 0.051 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF JONES SCHOOL RD BRIDGE OVER BRUSH CREEK. (044C00023N) | C |  | BR/STP | 2020 | 203000 | 125860 |  |  | 77140 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.03 | 2019-03-01 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030071 | GREEN | 4-10001 | CR 1347 |  | 0.045 | 0.051 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF JONES SCHOOL RD BRIDGE OVER BRUSH CREEK. (044C00023N) | C |  | STP | 2019 | 313548 | 313548 |  |  | 0 |  |  | OBLIGATED |  | 261245 | 261245 | 2019 | 3RD QUARTER
STIP | [9 empty] | GREEN | 4-10009 | US 68 |  | 2.995 | 3.003 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF US 68 BRIDGE OVER GREASY CREEK. (044B00013N) | D |  | BR/NH | 2019 | 105000 | 65100 |  |  | 39900 | [5 empty] | 0
STIP | [9 empty] | GREEN | 4-10009 | US 68 |  | 2.995 | 3.003 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF US 68 BRIDGE OVER GREASY CREEK. (044B00013N) | C |  | BR/NH | 2020 | 402500 | 249550 |  |  | 152950 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.046 | 2019-04-07 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030080 | GREEN | 4-10009 | US 68 |  | 2.995 | 3.003 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF US 68 BRIDGE OVER GREASY CREEK. (044B00013N) | C |  | BR/NH | 2019 | 1067000 | 1067000 |  |  | 0 |  |  | OBLIGATED |  | 876234 | 876234 | 2019 | 3RD QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.123 | 2019-09-06 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030080 | GREEN | 4-10009 | US 68 |  | 2.995 | 3.003 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF US 68 BRIDGE OVER GREASY CREEK. (044B00013N) | C |  | BR | 2020 | 900000 | 900000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.306 | 2021-06-16 | ADD D PHASE TO STIP; NEW |  |  | GREEN | 4-80102 | US 68 |  | 14.257 | 18.381 | RELIABILITY | SAFETY (P) | IMPROVE SAFETY AND PASSING OPPORTUNITITES ALONG US 68 FROM KY 61 IN GREEN COUNTY TO DAVIS ROAD IN TAYLOR COUNTY (2020CCN) | D |  | SPP | 2021 | 500100 | 100 |  |  | 500000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.248 | 2020-10-14 | TIP FY 21-24, AMENDMENT#2; ADD R PHASE TO STIP; NEW |  |  | GREENUP | 9-132 | KY 2 |  | 13.2 | 17.2 | RELIABILITY | PE & ENVRONMENTAL(O) | RECONSTRUCT KY-2 FROM MP 13.2 TO US-23 (MP 17.2)(08CCN)(14CCR)(16CCR)(18CCN) | R |  | STP | 2024 | 5780000 | 4624000 |  |  | 1156000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.248 | 2020-10-14 | TIP FY 21-24, AMENDMENT#2; ADD U PHASE TO STIP; NEW |  |  | GREENUP | 9-132 | KY 2 |  | 13.2 | 17.2 | RELIABILITY | PE & ENVRONMENTAL(O) | RECONSTRUCT KY-2 FROM MP 13.2 TO US-23 (MP 17.2)(08CCN)(14CCR)(16CCR)(18CCN) | U |  | STP | 2024 | 3380000 | 2704000 |  |  | 676000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.294 | 2021-04-13 | TIP FY 21-24, ADMIN MOD#12; ADD PROJECT TO STIP; NEW |  |  | GREENUP | 9-257 | [6 empty] | RESTORATION OF HISTORIC SCALE HOUSE ADJACENT TO MCCONNELL HOUSE TOURIST CENTER. PROPERTY TO SERVE AS 20% MATCH. | D |  | STP | 2021 | 20000 | 16000 |  |  |  | 4000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.294 | 2021-04-13 | TIP FY 21-24, ADMIN MOD#12; ADD PROJECT TO STIP; NEW |  |  | GREENUP | 9-257 | [6 empty] | RESTORATION OF HISTORIC SCALE HOUSE ADJACENT TO MCCONNELL HOUSE TOURIST CENTER. PROPERTY TO SERVE AS 20% MATCH. | C |  | STP | 2021 | 80000 | 64000 |  |  |  | 16000 |  |  |  |  | 0
STIP | [9 empty] | GREENUP | 9-401 | CS 3060 |  | 0 | 0.225 | SAFETY | BIKE/PED FACIL(O) | CONSTRUCT SIDEWALKS-PHASE B ALONG GESLING RD (CS-3060) FROM INTERSECTION OF CARDINAL RD (CS-3061) & SEATON DR (KY-750) TO KENWOOD DR (CS-3054/KY-1093) & PHASE C ALONG KENWOOD DR BEGINNING AT GESLING RD & ENDING AT CARDINAL RD. (2014BOP) | U |  | SAH | 2019 | 100000 | 80000 |  |  |  | 20000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.168 | 2020-02-26 | TIP FY 18-21, ADMIN MOD#49; REMOVE FUNDING FROM U PHASE BASED ON UPDATED ESTIMATE AND ADD TO C PHASE; MOD | STPM | 3004049 | GREENUP | 9-401 | CS 3060 |  | 0 | 0.225 | SAFETY | BIKE/PED FACIL(O) | CONSTRUCT SIDEWALKS-PHASE B ALONG GESLING RD (CS-3060) FROM INTERSECTION OF CARDINAL RD (CS-3061) & SEATON DR (KY-750) TO KENWOOD DR (CS-3054/KY-1093) & PHASE C ALONG KENWOOD DR BEGINNING AT GESLING RD & ENDING AT CARDINAL RD. (2014BOP) | U |  | SAH | 2019 | [10 empty] | 0
STIP | [9 empty] | GREENUP | 9-401 | CS 3060 |  | 0 | 0.225 | SAFETY | BIKE/PED FACIL(O) | CONSTRUCT SIDEWALKS-PHASE B ALONG GESLING RD (CS-3060) FROM INTERSECTION OF CARDINAL RD (CS-3061) & SEATON DR (KY-750) TO KENWOOD DR (CS-3054/KY-1093) & PHASE C ALONG KENWOOD DR BEGINNING AT GESLING RD & ENDING AT CARDINAL RD. (2014BOP) | C |  | SAH | 2019 | 555000 | 444000 |  |  |  | 111000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.168 | 2020-02-26 | TIP FY 18-21, ADMIN MOD#49; REMOVE FUNDING FROM U PHASE BASED ON UPDATED ESTIMATE AND ADD TO C PHASE. UPDATE FISCAL YEAR; MOD | STPM | 3004049 | GREENUP | 9-401 | CS 3060 |  | 0 | 0.225 | SAFETY | BIKE/PED FACIL(O) | CONSTRUCT SIDEWALKS-PHASE B ALONG GESLING RD (CS-3060) FROM INTERSECTION OF CARDINAL RD (CS-3061) & SEATON DR (KY-750) TO KENWOOD DR (CS-3054/KY-1093) & PHASE C ALONG KENWOOD DR BEGINNING AT GESLING RD & ENDING AT CARDINAL RD. (2014BOP) | C |  | SAH | 2020 | 655000 | 524000 |  |  |  | 131000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.193 | 2020-05-29 | TIP FY 18-21, ADMIN MOD#54; UPDATE FUND AMOUNTS; MOD | STPM | 3004049 | GREENUP | 9-401 | CS 3060 |  | 0 | 0.225 | SAFETY | BIKE/PED FACIL(O) | CONSTRUCT SIDEWALKS-PHASE B ALONG GESLING RD (CS-3060) FROM INTERSECTION OF CARDINAL RD (CS-3061) & SEATON DR (KY-750) TO KENWOOD DR (CS-3054/KY-1093) & PHASE C ALONG KENWOOD DR BEGINNING AT GESLING RD & ENDING AT CARDINAL RD. (2014BOP) | C |  | SAH | 2020 | 974464 | 779571 |  |  |  | 194893 |  |  |  |  | 0
STIP | [9 empty] | GREENUP | 9-402 | KY 750 |  | 1.74 | 1.81 | RELIABILITY | MATCHED FED FUNDS(O) | DESIGN AND CONSTRUCTION OF SIDEWALKS ALONG POWELL LANE (KY-750) IN FLATWOODS, KY BEGINNING AT END OF THE EXISTING SIDEWALK AT MP 1.74 AND EXTENDING APPROXIMATELY 0.7 MILES EAST TO THE INTERSECTION OF KY-750 WITH KY-1172 (RED DEVIL LANE).(2014BOP) | R |  | SAH | 2019 | 32000 | 25600 |  |  |  | 6400 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.236 | 2020-09-21 | TIP FY 21-24, ADMIN MOD#6; UPDATE FY & FUND AMOUNTS; MOD |  |  | GREENUP | 9-402 | KY 750 KY 1172 |  | 1.65 .47 | 2.48 .482 | RELIABILITY | MATCHED FED FUNDS(O) | DESIGN AND CONSTRUCTION OF SIDEWALKS ALONG POWELL LANE (KY-750) IN FLATWOODS, KY BEGINNING AT END OF THE EXISTING SIDEWALK AT MP 1.74 AND EXTENDING APPROXIMATELY 0.7 MILES EAST TO THE INTERSECTION OF KY-750 WITH KY-1172 (RED DEVIL LANE).(2014BOP) | R |  | SAH | 2020 | 146000 | 116800 |  |  |  | 29200 |  |  |  |  | 0
STIP |  | YES | U PHASE TOTAL COST=$80,000 NOT WHAT IS SHOWN IN THE STIP AS $64,000/ FED=$64,000/LOCAL=$16,000 | [6 empty] | GREENUP | 9-402 | KY 750 |  | 1.74 | 1.81 | RELIABILITY | MATCHED FED FUNDS(O) | DESIGN AND CONSTRUCTION OF SIDEWALKS ALONG POWELL LANE (KY-750) IN FLATWOODS, KY BEGINNING AT END OF THE EXISTING SIDEWALK AT MP 1.74 AND EXTENDING APPROXIMATELY 0.7 MILES EAST TO THE INTERSECTION OF KY-750 WITH KY-1172 (RED DEVIL LANE).(2014BOP) | U |  | SAH | 2019 | 64000 | 51200 |  |  |  | 12800 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.236 | 2020-09-21 | TIP FY 21-24, ADMIN MOD#6; UPDATE FY & FUND AMOUNTS; MOD |  |  | GREENUP | 9-402 | KY 750 KY 1172 |  | 1.65 .47 | 2.48 .482 | RELIABILITY | MATCHED FED FUNDS(O) | DESIGN AND CONSTRUCTION OF SIDEWALKS ALONG POWELL LANE (KY-750) IN FLATWOODS, KY BEGINNING AT END OF THE EXISTING SIDEWALK AT MP 1.74 AND EXTENDING APPROXIMATELY 0.7 MILES EAST TO THE INTERSECTION OF KY-750 WITH KY-1172 (RED DEVIL LANE).(2014BOP) | U |  | SAH | 2020 | 80000 | 64000 |  |  |  | 16000 |  |  |  |  | 0
STIP |  | YES | C PHASE TOTAL COST IN TIP=$283,600/FED=226,880/LOCAL=$56,720 | [6 empty] | GREENUP | 9-402 | KY 750 |  | 1.74 | 1.81 | RELIABILITY | MATCHED FED FUNDS(O) | DESIGN AND CONSTRUCTION OF SIDEWALKS ALONG POWELL LANE (KY-750) IN FLATWOODS, KY BEGINNING AT END OF THE EXISTING SIDEWALK AT MP 1.74 AND EXTENDING APPROXIMATELY 0.7 MILES EAST TO THE INTERSECTION OF KY-750 WITH KY-1172 (RED DEVIL LANE).(2014BOP) | C |  | SAH | 2019 | 370000 | 296000 |  |  |  | 74000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.236 | 2020-09-21 | TIP FY 21-24, ADMIN MOD#6; UPDATE FY & FUND AMOUNTS; MOD |  |  | GREENUP | 9-402 | KY 750 KY 1172 |  | 1.65 .47 | 2.48 .482 | RELIABILITY | MATCHED FED FUNDS(O) | DESIGN AND CONSTRUCTION OF SIDEWALKS ALONG POWELL LANE (KY-750) IN FLATWOODS, KY BEGINNING AT END OF THE EXISTING SIDEWALK AT MP 1.74 AND EXTENDING APPROXIMATELY 0.7 MILES EAST TO THE INTERSECTION OF KY-750 WITH KY-1172 (RED DEVIL LANE).(2014BOP) | C |  | SAH | 2021 | 169600 | 135680 |  |  |  | 33920 |  |  |  |  | 0
[8 empty] | STPM | 3004051 | GREENUP | 9-405 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | RAILROAD CROSSING IMPROVEMENTS NEAR LERITA STREET IN LLOYD. (CONSTRUCTION TO BE COMPLETED BY CSX). (2018BOP) | U |  | SAH | 2019 | [7 empty] | OBLIGATED | 335000 |  | 335000 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.143 | 2019-10-22 | TIP FY 18-21; ADMIN MOD#45, UPDATE FISCAL YEAR AND FUND AMOUNTS; MOD | STPM | 3004051 | GREENUP | 9-405 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | RAILROAD CROSSING IMPROVEMENTS NEAR LERITA STREET IN LLOYD. (CONSTRUCTION TO BE COMPLETED BY CSX). (2018BOP) | U |  | SAH | 2020 | 549860 | 494874 |  |  |  | 54986 |  | OBLIGATED | 159874 |  | 159874 | 2020 | 1ST QUARTER
[8 empty] | STPM | 3004051 | GREENUP | 9-405 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | RAILROAD CROSSING IMPROVEMENTS NEAR LERITA STREET IN LLOYD. (CONSTRUCTION TO BE COMPLETED BY CSX). (2018BOP) | C |  | SAH | 2019 | 15000 | 15000 | [5 empty] | OBLIGATED | 15000 |  | 15000 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.143 | 2019-10-22 | TIP FY 18-21; ADMIN MOD#45, UPDATE FISCAL YEAR; MOD | STPM | 3004051 | GREENUP | 9-405 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | RAILROAD CROSSING IMPROVEMENTS NEAR LERITA STREET IN LLOYD. (CONSTRUCTION TO BE COMPLETED BY CSX). (2018BOP) | C |  | SAH | 2020 | 15000 | 15000 | [5 empty] | OBLIGATED |  |  | 0
[8 empty] | STPM | 0231163 | GREENUP | 9-412 | US 23 |  | 0.03 | 0.85 | RELIABILITY | MATCHED FED FUNDS(O) | REPLACE GRASS MEDIAN ALONG US-23 BETWEEN MP 0.03 TO 0.07 AND MO 0.51 TO 0.85 WITH CONCRETE MOUNTABLE MEDIAN. (2018BOP) | D |  | SAH | 2019 | 15000 | 15000 | [5 empty] | OBLIGATED |  | 15000 | 15000 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.143 | 2019-10-22 | TIP FY 18-21; ADMIN MOD#45, ADD C PHASE TO STIP; NEW | STPM | 0231163 | GREENUP | 9-412 | US 23 |  | 0.03 | 0.85 | RELIABILITY | MATCHED FED FUNDS(O) | REPLACE GRASS MEDIAN ALONG US-23 BETWEEN MP 0.03 TO 0.07 AND MO 0.51 TO 0.85 WITH CONCRETE MOUNTABLE MEDIAN. (2018BOP) | C |  | SAH | 2019 | 501337 | 401070 |  |  |  | 100267
STIP | [7 empty] | STPBRZ | 9030190 | GREENUP | 9-1073 | KY 244 | 0.1 | 0 | 0.207 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON KY-244 (MP 0.103) OVER CSX RAILROAD; .05 MI N.E. OF JCT US 23; 045B00039N (16CCR) | C |  | BR/STP | 2019 | 11655000 | 7226100 |  |  | 4428900 |  |  | OBLIGATED | 2000000 | 12674000 | 14674000 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.135 | 2019-09-30 | TIP FY 18-21; ADMIN MOD#44; UPDATE FISCAL YEAR AND FUND AMOUNT BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030190 | GREENUP | 9-1073 | KY 244 | 0.1 | 0 | 0.207 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON KY-244 (MP 0.103) OVER CSX RAILROAD; .05 MI N.E. OF JCT US 23; 045B00039N (16CCR) | C |  | BR/STP | 2020 | 18342500 | 14674000 |  |  | 3668500 |  |  | OBLIGATED | 3460600 |  | 3460600 | 2020 | 2ND QUARTER
STIP | [7 empty] | STPBRZ | 9030045 | GREENUP | 9-1094 | CS 4041 | 0.016 | 0.05 | 0.066 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER POND RUN ON WILLIAMS AVE (CS 4041) IN RACELAND 250 FT NW OF POND RUN ROAD (CS 4001) (045C00119N) | D |  | BR/STP | 2019 | 245000 | 151900 |  |  | 93100 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030045 | GREENUP | 9-1094 | CS 4041 | 0.016 | 0.05 | 0.066 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER POND RUN ON WILLIAMS AVE (CS 4041) IN RACELAND 250 FT NW OF POND RUN ROAD (CS 4001) (045C00119N) | C |  | BR/STP | 2020 | 840000 | 520800 |  |  | 319200 |  |  | OBLIGATED | 280320 |  | 280320 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.297 | 2021-04-20 | TIP FY 21-24, ADMIN MOD#14; ADD C PHASE TO STIP; NEW |  |  | GREENUP | 9-4332 | KY 1 | 0.05 | 13.93 | 13.98 | SAFETY | SAF GUARDRAIL (P) | INSTALL GUARDRAIL ON KY-1 IN GREENUP COUNTY | C |  | STP | 2021 | 17250 | 17250 | [8 empty] | 0
STIP | [9 empty] | GREENUP | 9-8509 | KY-207 | NEW | NEW | NEW | RELIABILITY | NEW ROUTE | RECONSTRUCT KY-207 FROM KY-67 (INDUSTRIAL PARKWAY) TO KY-693/KY-207 INTERSECTION AT FLATAWOODS - NO ADDITIONAL LANES [WIDEN 2-LANE WITH MINIMAL SHOULDERS TO A SUPER TWO ROAD WAY SECTION TO IMPROVE SAFETY, CONGESTION AND CONNECTIVITY TO ADDRESS EXISTING GEOMETRIC DEFICIENCIES IN THE RURAL SECTION AND EXISTING MOVEMENT INEFFICIENCIES IN THE URBAN SECTION. | C |  | STP | 2020 | 26000000 | 0 |  |  | 0 | 0 | 0 |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.179 | 2020-04-14 | TIP FY 18-21; ADMIN MOD#52; ADD PROJECT TO STIP; NEW |  |  | GREENUP | 9-9010.2 | KY 693 | 0.1 | 4.884 | 4.984 | SAFETY | SAFETY-HAZARD ELIM(P) | PAVEMENT MARKING IMPROVEMENTS, INSTALL LANE SEPARATOR CURB, AND UPDATE THE SIGNAL TO INCLUDE REFLECTIVE BACKPLATES AT THE INTERSECTION OF KY 693 & KY 1093. (2018BOP) | C |  | SAF | 2020 | 94000 | 94000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.137 | 2019-10-15 | TIP FY 18-21; AMENDMENT#10; ADD D PHASE TO STIP; NEW |  |  | GREENUP | TBD | KY 1 |  | 12.9 | 13.2 |  |  | CONSTRUCT LEFT AND RIGHT TURN LANES ON KY-1 AT THE ENTRANCE OF ARGILLITE ELEMENTARY TO PROVIDE SAFETY AND EFFICIENCY FOR SCHOOL INGRESS. MATCH TO BE PROVIDED BY TOLL CREDITS. | D |  | STP | 2021 | 100000 | 80000 |  |  | 20000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.294 | 2021-04-13 | TIP FY 21-24; ADMIN MOD#12; UPDATE ITEM NUMBER TO PROJECT & UPDATE FUND AMOUNTS; MOD |  |  | GREENUP | 9-9019 | KY 1 |  | 12.9 | 13.2 | SAFETY | SAFETY-HAZARD ELIM(P) | CONSTRUCT LEFT AND RIGHT TURN LANES ON KY 1 AT THE ENTRANCE OF ARGILLITE ELEMENTARY TO PROVIDE SAFETY AND EFFICIENCY FOR SCHOOL INGRESS. | D |  | STP | 2021 | 250000 | 200000 |  |  | 50000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.137 | 2019-10-15 | TIP FY 18-21; AMENDMENT#10; ADD R PHASE TO STIP; NEW |  |  | GREENUP | TBD | KY 1 |  | 12.9 | 13.2 |  |  | CONSTRUCT LEFT AND RIGHT TURN LANES ON KY-1 AT THE ENTRANCE OF ARGILLITE ELEMENTARY TO PROVIDE SAFETY AND EFFICIENCY FOR SCHOOL INGRESS. MATCH TO BE PROVIDED BY TOLL CREDITS. | R |  | STP | 2021 | 75000 | 60000 |  |  | 15000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.294 | 2021-04-13 | TIP FY 21-24; ADMIN MOD#12; UPDATE ITEM NUMBER ON PROEJCT; MOD |  |  | GREENUP | 9-9019 | KY 1 |  | 12.9 | 13.2 | SAFETY | SAFETY-HAZARD ELIM(P) | CONSTRUCT LEFT AND RIGHT TURN LANES ON KY 1 AT THE ENTRANCE OF ARGILLITE ELEMENTARY TO PROVIDE SAFETY AND EFFICIENCY FOR SCHOOL INGRESS. | R |  | STP | 2021 | 75000 | 60000 |  |  | 15000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.137 | 2019-10-15 | TIP FY 18-21; AMENDMENT#10; UPDATE ITEM NUMBER ON PROJECT; MOD |  |  | GREENUP | TBD | KY 1 |  | 12.9 | 13.2 |  |  | CONSTRUCT LEFT AND RIGHT TURN LANES ON KY-1 AT THE ENTRANCE OF ARGILLITE ELEMENTARY TO PROVIDE SAFETY AND EFFICIENCY FOR SCHOOL INGRESS. MATCH TO BE PROVIDED BY TOLL CREDITS. | U |  | STP | 2021 | 50000 | 40000 |  |  | 10000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.294 | 2021-04-13 | TIP FY 21-24; ADMIN MOD#12; ADD PROJECT TO STIP; NEW |  |  | GREENUP | 9-9019 | KY 1 |  | 12.9 | 13.2 | SAFETY | SAFETY-HAZARD ELIM(P) | CONSTRUCT LEFT AND RIGHT TURN LANES ON KY 1 AT THE ENTRANCE OF ARGILLITE ELEMENTARY TO PROVIDE SAFETY AND EFFICIENCY FOR SCHOOL INGRESS. | U |  | STP | 2021 | 50000 | 40000 |  |  | 10000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.137 | 2019-10-15 | TIP FY 18-21; AMENDMENT#10; ADD C PHASE TO STIP; NEW |  |  | GREENUP | TBD | KY 1 |  | 12.9 | 13.2 |  |  | CONSTRUCT LEFT AND RIGHT TURN LANES ON KY-1 AT THE ENTRANCE OF ARGILLITE ELEMENTARY TO PROVIDE SAFETY AND EFFICIENCY FOR SCHOOL INGRESS. MATCH TO BE PROVIDED BY TOLL CREDITS. | C |  | STP | 2021 | 1000000 | 800000 |  |  | 200000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.294 | 2021-04-13 | TIP FY 21-24; ADMIN MOD#12; UPDATE ITEM NUMBER ON PROJECT & UPDATE FUND AMOUNTS; MOD |  |  | GREENUP | 9-9019 | KY 1 |  | 12.9 | 13.2 | SAFETY | SAFETY-HAZARD ELIM(P) | CONSTRUCT LEFT AND RIGHT TURN LANES ON KY 1 AT THE ENTRANCE OF ARGILLITE ELEMENTARY TO PROVIDE SAFETY AND EFFICIENCY FOR SCHOOL INGRESS. | C |  | STP | 2021 | 850000 | 680000 |  |  | 170000 | [5 empty] | 0
STIP | YES | YES | KYOVA TIP TOTAL PHASE COST=$280,000/FED=173,600/STATE=$106,400 | [6 empty] | GREENUP | 9-10007 | KY 503 |  | 5.328 | 5.336 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-503 BRIDGE OVER INDIAN RUN CREEK. (045B00033N) | D |  | BR/STP | 2019 | 245000 | 151900 |  |  | 93100 | [5 empty] | 0
STIP | YES | YES | KYOVA TIP TOTAL PHASE COST=$595,000/FED=368,900/STATE=$226,100 | [6 empty] | GREENUP | 9-10007 | KY 503 |  | 5.328 | 5.336 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-503 BRIDGE OVER INDIAN RUN CREEK. (045B00033N) | C |  | BR/STP | 2020 | 753000 | 466860 |  |  | 286140 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.121 | 2019-08-26 | TIP FY 18-21; ADMIN MOD#40; INCREASE FUNDS BASED ON NEEDS AFTER BRIDGE INSPECTION; MOD | STPBRZ | 9030126 | GREENUP | 9-10007 | KY 503 |  | 5.328 | 5.336 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-503 BRIDGE OVER INDIAN RUN CREEK. (045B00033N) | C |  | BR/STP | 2019 | 1053444 | 842755 |  |  | 210689 |  |  | OBLIGATED |  | 594077 | 594077 | 2019 | 4TH QUARTER
STIP | YES | YES | KYOVA TIP PHASE = $280,000 ALL FED NO STATE MATCH | [6 empty] | GREENUP | 9-10008 | CR 1018 |  | 2.221 | 2.227 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF SMITH BRANCH RD BRIDGE OVER LEFT FK SMITH BRANCH. (045C00114N) | D |  | BR/STP | 2019 | 280000 | 173600 |  |  | 106400 | [5 empty] | 0
STIP | YES | YES | KYOVA TIP PHASE = $595,000 ALL FED NO STATE MATCH |  |  |  |  | STPBRZ | 9030127 | GREENUP | 9-10008 | CR 1018 |  | 2.221 | 2.227 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF SMITH BRANCH RD BRIDGE OVER LEFT FK SMITH BRANCH. (045C00114N) | C |  | BR/STP | 2020 | 595000 | 368900 |  |  | 226100 |  |  | OBLIGATED |  | 341512 | 341512 | 2019 | 4TH QUARTER
STIP | YES | [6 empty] | STPBRZ | 9030044 | GREENUP | 9-10009 | LA 1001 |  | 0.055 | 0.059 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF MUSKETEER DRIVE BRIDGE OVER SLASH BRANCH. (045C00150N) | D |  | BR/NH | 2019 | 245000 | 151900 |  |  | 93100 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.023 | 2019-02-01 | TIP FY 18-21; ADMIN MOD#27; ADJUST COST ESTIMATES; MOD | STPBRZ | 9030044 | GREENUP | 9-10009 | LA 1001 |  | 0.055 | 0.059 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF MUSKETEER DRIVE BRIDGE OVER SLASH BRANCH. (045C00150N) | D |  | BR/NH | 2019 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
STIP | YES | [6 empty] | STPBRZ | 9030044 | GREENUP | 9-10009 | LA 1001 |  | 0.055 | 0.059 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF MUSKETEER DRIVE BRIDGE OVER SLASH BRANCH. (045C00150N) | C |  | BR/NH | 2020 | 300000 | 186000 |  |  | 114000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.023 | 2019-02-01 | TIP FY 18-21; ADMIN MOD#27; ADJUST COST ESTIMATES; MOD | STPBRZ | 9030044 | GREENUP | 9-10009 | LA 1001 |  | 0.055 | 0.059 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF MUSKETEER DRIVE BRIDGE OVER SLASH BRANCH. (045C00150N) | C |  | STP | 2020 | 425000 | 340000 | 340000 | 0 | 85000 |  |  | OBLIGATED |  | 505090 | 505090 | 2019 | 2ND QUARTER
STIP | YES | [8 empty] | GREENUP | 9-10022 | KY 1 |  | 1.146 | 1.152 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 1 BRIDGE OVER LOST CREEK. (045B00006N) | D |  | BR/STP | 2019 | 350000 | 217000 |  |  | 133000 | [5 empty] | 0
STIP | YES | [6 empty] | STPBRZ | 9030099 | GREENUP | 9-10022 | KY 1 |  | 1.146 | 1.152 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 1 BRIDGE OVER LOST CREEK. (045B00006N) | C |  | BR/STP | 2020 | 1015000 | 629300 |  |  | 385700 |  |  | OBLIGATED |  | 996455 | 996455
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.131 | 2019-09-18 | TIP FY 18-21; ADMIN MOD#41; ADD PROJECT TO STIP; NEW |  |  | GREENUP | 9-10027 | KY 3112 |  | 0.013 |  | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES ON BENNETT'S MILL COV (KY 3112) OVER TYGARTS CREEK. (045B00085N) | C |  | STP | 2019 | 175000 | 140000 |  |  | 35000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.256 | 2020-11-06 | TIP FY 21-24, ADMIN MOD#9; ADD D PHASE TO STIP; NEW |  |  | GREENUP | 9-20026 | US 23 | 5.76 | 23.002 | 28.76 | RELIABILITY | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION ON US-23 FROM MP 23.002 TO MP 28.76. | D |  | NH | 2021 | 250000 | 200000 |  |  | 50000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.297 | 2021-04-20 | TIP FY 21-24, ADMIN MOD#14; ADD C PHASE TO STIP; NEW |  |  | GREENUP | 9-20026 | US 23 | 5.76 | 23.002 | 28.76 | RELIABILITY | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION ON US-23 FROM MP 23.002 TO MP 28.76. | C |  | NH | 2021 | 4270750 | 3416600 |  |  | 854150 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.06 | 2019-04-29 | TIP FY 18-21; AMENDMENT#9; ADD D PHASE TO STIP; NEW |  |  | GREENUP | TBD | US 23 | 0.37 | 0.03 0.07 | 0.51 0.85 |  |  | REPLACE GRASS MEDIAN ALONG US-23 BETWEEN MP 0.03 TO 0.07 AND MP 0.51 TO 0.85 WITH CONCRETE MOUTABLE MEDIAN. MATCH TO BE PROVIDED BY TOLL CREDITS. | D |  | STP | 2019 | 12000 | 12000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.06 | 2019-04-29 | TIP FY 18-21; AMENDMENT#9; ADD C PHASE TO STIP; NEW |  |  | GREENUP | TBD | US 23 | 0.37 | 0.03 0.07 | 0.51 0.85 |  |  | REPLACE GRASS MEDIAN ALONG US-23 BETWEEN MP 0.03 TO 0.07 AND MP 0.51 TO 0.85 WITH CONCRETE MOUTABLE MEDIAN. MATCH TO BE PROVIDED BY TOLL CREDITS. | C |  | STP | 2019 | 100267 | 100267 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.143 | 2019-10-22 | TIP FY 18-21; ADMIN MOD#45;ADD D PHASE TO STIP; NEW |  |  | GREENUP | TBD | [6 empty] | PHASE II - LLOYD SIDEWALK CONSTRUCTION OF 1500 LF OF 4' WIDE SIDEWALK ALONG OHIO RIVER ROAD. | D |  | SAH | 2020 | 15000 | 12000 |  |  |  | 3000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.143 | 2019-10-22 | TIP FY 18-21; ADMIN MOD#45;ADD D PHASE TO STIP; NEW |  |  | GREENUP | TBD | [6 empty] | PHASE II - LLOYD SIDEWALK CONSTRUCTION OF 1500 LF OF 4' WIDE SIDEWALK ALONG OHIO RIVER ROAD. | C |  | SAH | 2020 | 156000 | 124800 |  |  |  | 31200 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.176 | 2020-04-09 | TIP FY 18-21; ADMIN MOD#50; ADD D PHASE TO STIP; NEW |  |  | GREENUP | TBD | [6 empty] | CONSTRUCT SIDEWALK THROUGHOUT THE CITY OF GREENUP, KY RIVERFRONT PARK WITH CONNECTION TO THE PREVIOUS WALKING PATH PROJECT. MATCH TO BE PROVIDED BY THE CITY OF GREENUP, KY. | D |  | SAH | 2020 | 36000 | 28800 |  |  |  | 7200 | [7 empty] | CITY OF GREENUP
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.176 | 2020-04-09 | TIP FY 18-21; ADMIN MOD#50; ADD C PHASE TO STIP; NEW |  |  | GREENUP | TBD | [6 empty] | CONSTRUCT SIDEWALK THROUGHOUT THE CITY OF GREENUP, KY RIVERFRONT PARK WITH CONNECTION TO THE PREVIOUS WALKING PATH PROJECT. MATCH TO BE PROVIDED BY THE CITY OF GREENUP, KY. | C |  | SAH | 2020 | 306100 | 244880 |  |  |  | 61220 |  |  |  |  | 0 |  |  | CITY OF GREENUP
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.231 | 2020-09-14 | TIP FY 21-24, ADMIN MOD#4; ADD PROJECT TO STIP; NEW |  |  | GREENUP | TBD | [6 empty] | DESIGN/CONSTRUCTION OF SIDEWALK THROUGHOUT THE CITY OF GREENUP, KY RIVERFRONT PARK WITH CONNECTION TO THE PREVIOUS WALKING PATH PROJECT. MATCH TO BE PROVIDED BY THE CITY OF GREENUP, KY. | D |  | SAH | 2020 | 75000 | 60000 |  |  |  | 15000 |  |  |  |  | 0 |  |  | CITY OF GREENUP
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.231 | 2020-09-14 | TIP FY 21-24, ADMIN MOD#4; ADD PROJECT TO STIP; NEW |  |  | GREENUP | TBD | [6 empty] | DESIGN/CONSTRUCTION OF SIDEWALK THROUGHOUT THE CITY OF GREENUP, KY RIVERFRONT PARK WITH CONNECTION TO THE PREVIOUS WALKING PATH PROJECT. MATCH TO BE PROVIDED BY THE CITY OF GREENUP, KY. | C |  | SAH | 2020 | 267100 | 213680 |  |  |  | 53420 |  |  |  |  | 0 |  |  | CITY OF GREENUP
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.283 | 2021-03-22 | ADD R PHASE TO STIP; NEW |  |  | HANCOCK | 2-226 | US 60 |  | 4.8 | 8.684 | RELIABILITY | MINOR WIDENING(O) | IMPROVE THE WESTBOUND LANES OF US-60 FROM KY-1957 TO 0.2 MILE WEST OF KY-6106. (12CCR)(14CCR)(18CCR) (2020CCR) | R |  | STP | 2021 | 90000 | 90000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.283 | 2021-03-22 | ADD U PHASE TO STIP; NEW |  |  | HANCOCK | 2-226 | US 60 |  | 4.8 | 8.684 | RELIABILITY | MINOR WIDENING(O) | IMPROVE THE WESTBOUND LANES OF US-60 FROM KY-1957 TO 0.2 MILE WEST OF KY-6106. (12CCR)(14CCR)(18CCR) (2020CCR) | U |  | STP | 2021 | 960000 | 960000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.139 | 2019-10-25 | ADD PROJECT TO STIP; NEW |  |  | HANCOCK | 2-10028 | CR 1324 |  | 0.99 |  | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES ON TOLER BRIDGE ROAD (CR 1324) OVER BLACKFORD CREEK. (046C00028N) | C |  | STP | 2020 | 150000 | 150000 | [8 empty] | 0
STIP | [9 empty] | HANCOCK | 2-20022 | US 60 |  | 1.933 | 9.4 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | D |  | PM/STP | 2022 | 525000 | 420000 |  |  | 105000 | [5 empty] | 0
STIP | [9 empty] | HANCOCK | 2-20022 | US 60 |  | 1.933 | 9.4 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | C |  | PM/STP | 2022 | 5250000 | 4200000 |  |  | 1050000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.218 | 2020-08-28 | ADD C PHASE TO STIP; PARENT NO. 99-2700.14; NEW |  |  | HANCOCK | 2-20051 | KY 3543 |  | 0 | 1.999 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | PAVEMENT RESURFACING ON KY 3543 FROM MP 0.000 TO MP 1.999 IN HANCOCK COUNTY. | C |  | STP | 2020 | 190000 | 190000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.222 | 2020-08-25 | TIP FY 18-22; AMEND#3; ADD PROJECT TO STIP; NEW |  |  | HARDIN | 4-153.01 | KY 251 |  | 2.681 | 6.288 | RELIABILITY | PHASE I DESIGN(O) | KY 251 IMPROVEMENTS FROM KY 3005 TO KY 434. | D |  | STP | 2020 | 500000 | 500000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.222 | 2020-08-25 | TIP FY 18-22; AMEND#3; ADD PROJECT TO STIP; NEW |  |  | HARDIN | 4-153.01 | KY 251 |  | 2.681 | 6.288 | RELIABILITY | PHASE I DESIGN(O) | KY 251 IMPROVEMENTS FROM KY 3005 TO KY 434. | U |  | STP | 2022 | 4200000 | 4200000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.222 | 2020-08-25 | TIP FY 18-22; AMEND#3; ADD PROJECT TO STIP; NEW |  |  | HARDIN | 4-153.01 | KY 251 |  | 2.681 | 6.288 | RELIABILITY | PHASE I DESIGN(O) | KY 251 IMPROVEMENTS FROM KY 3005 TO KY 434. | C |  | STP | 2023 | 9400000 | 9400000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.18 | 2020-04-21 | TIP FY 18-22; ADMIN MOD#13; ADD PROJECT TO STIP; NEW |  |  | HARDIN | 4-154.2 | US 31W |  | 18.827 | 20.772 | RELIABILITY | CONGESTION MITIGTN(O) | IMPROVE SAFETY AND MOBILITY AND, REDUCE CONGESTION ON US-31W FROM US-31WB TO KY 447. (CONSTRUCTION SEGMENT 1)(2018BOP) | C |  | STP | 2020 | 2750000 | 2750000 |  |  | 0 | [5 empty] | 0
STIP | [7 empty] | STP | 0311033 | HARDIN | 4-199 | US 31W | 0.4 | 36.4 | 36.8 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER P&L AND CSX RAILROADS (MP 36.4 TO 36.8 IN WEST POINT) (047B00007N).(16CCR) | C |  | BR/NH | 2019 | 10500000 | 6510000 |  |  | 3990000 |  |  | OBLIGATED | 7168000 |  | 7168000 | 2019 | 2ND QUARTER
STIP | YES | YES | Not in TIP. | [6 empty] | HARDIN | 4-442 | US 62 | 3.247 | 20.104 | 23.351 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE SAFETY, MOBILITY AND GEOMETRICS ON US-62 FROM I-65 TO UPPER COLESBURG ROAD (CR-1038) | D |  | STP | 2022 | 1500000 | 1200000 |  |  | 300000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.279 | 2021-03-05 | RADCLIFF/ETOWN MPO AREA TIP FY 18-22, GROUP PROJECTS, TABLE 4, PAGE 14; NEW |  |  | HARDIN | 4-943 | CR 1100 |  | 1.8 | 2 | RELIABILITY | SAFETY-HAZARD ELIM(P) | Installation of High Friction Surface Treatment from MP 1.8 to MP 2.0 on CR 1100 in Hardin County. | C |  | SAF | 2021 | 100000 | 100000 |  |  | 0 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 5038109 | HARDIN | 4-1093 | US 62 | 0.139 | 28.157 | 28.194 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON US 62 OVER ROLLING FORK AT THE HARDIN-NELSON CO LINE. 047B00023N | C |  | BR/STP | 2020 | 3381000 | 2096220 |  |  | 1284780 |  |  | OBLIGATED | 400000 | 3625460 | 4025460 | 2020 | 1ST QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.157 | 2020-01-14 | TIP FY 18-22; AMENDMENT#2; UPDATE FUND AMOUNTS; MOD | STPBRZ | 5038109 | HARDIN | 4-1093 | US 62 | 0.139 | 28.157 | 28.194 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON US 62 OVER ROLLING FORK AT THE HARDIN-NELSON CO LINE. 047B00023N | C |  | BR/STP | 2020 | 4815000 | 3852000 |  |  | 963000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.014 | 2019-01-15 | TIP FY 18-22; AMENDMENT#1; NEW |  |  | HARDIN | 4-8801 | KY 1357 |  | 14.614 | 16.292 | SAFETY | SAFETY(P) | IMPROVE SAFETY, GEOMETRICS, DRAINAGE AND MAINTENANCE ISSUES ALONG KY-1357 (ST. JOHNS RD) FROM US-31W BYPASS TO KY-3005 (RING ROAD). (14CCN) | R |  | STP | 2020 | 3000000 | 3000000 | 3000000 |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.014 | 2019-01-15 | TIP FY 18-22; AMENDMENT#1; NEW |  |  | HARDIN | 4-8801 | KY 1357 |  | 14.614 | 16.292 | SAFETY | SAFETY(P) | IMPROVE SAFETY, GEOMETRICS, DRAINAGE AND MAINTENANCE ISSUES ALONG KY-1357 (ST. JOHNS RD) FROM US-31W BYPASS TO KY-3005 (RING ROAD). (14CCN) | U |  | STP | 2021 | 2500000 | 2500000 | 2500000 |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.267 | 2020-12-30 | TIP FY 18-22; ADMIN MOD#19;ADD D PHASE TO STIP; NEW |  |  | HARDIN | 4-9002 | KY 3005 |  | 1.1 | 1.7 | RELIABILITY | SAFETY-HAZARD ELIM(P) | Construction of an RCUT at the Intersection of KY 3005 and KY 1904. | D |  | SAF | 2021 | 75000 | 75000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.267 | 2020-12-30 | TIP FY 18-22; ADMIN MOD#19;ADD C PHASE TO STIP; NEW |  |  | HARDIN | 4-9002 | KY 3005 |  | 1.1 | 1.7 | RELIABILITY | SAFETY-HAZARD ELIM(P) | Construction of an RCUT at the Intersection of KY 3005 and KY 1904. | C |  | SAF | 2021 | 750000 | 750000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.015 | 2019-01-25 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; RADCLIFF/ETOWN MPO TIP FY 18-22, GROUP PROJECT, PG 14, TABLE 4; NEW | HSIP | 9010358 | HARDIN, NELSON, TAYLOR | 4-9003.1 | US 68 |  | 4.6 | 4.87 | SAFETY | SAFETY-HAZARD ELIM(P) | INTERSECTION IMPROVEMENTS AT VARIOUS LOCATIONS IN HARDIN, NELSON AND TAYLOR COUNTIES LOCATED IN DISTRICT 4. EXTEND THE LEFT TURN LANE ALONG EB US 68 AT THE INTERSECTION WITH KY 55 AND KY 210. (2018BOP) | C |  | SAF | 2019 | 250000 | 250000 |  |  | 0 |  |  | OBLIGATED |  | 277446 | 277446 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.003 | 2018-12-10 | TIP FY 18-22; ADMIN MOD#5; ADD PROJECT TO STIP; NEW | HSIP | 0311040 | HARDIN | 4-9008 | US 31W |  | 18.032 | 26.191 | SAFETY | SAFETY-HAZARD ELIM(P) | INTERSECTION AND CORRIDOR IMPROVEMENTS TO ENHANCE SAFETY & CAPACITY ALONG US 31W FROM RING RD TO GRAHAM AVE. (2016BOP) | R |  | SAF | 2019 | 1100000 | 1100000 |  |  | 0 |  |  | OBLIGATED | 2125000 | 400000 | 2525000 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.003 | 2018-12-10 | TIP FY 18-22; ADMIN MOD#5; ADD PROJECT TO STIP; NEW | HSIP | 0311040 | HARDIN | 4-9008 | US 31W |  | 18.032 | 26.191 | SAFETY | SAFETY-HAZARD ELIM(P) | INTERSECTION AND CORRIDOR IMPROVEMENTS TO ENHANCE SAFETY & CAPACITY ALONG US 31W FROM RING RD TO GRAHAM AVE. (2016BOP) | U |  | SAF | 2019 | 425000 | 425000 |  |  | 0 |  |  | OBLIGATED |  | 425000 | 425000 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.003 | 2018-12-10 | TIP FY 18-22; ADMIN MOD#5; ADD PROJECT TO STIP; NEW |  |  | HARDIN | 4-9008.1 | US 31W |  | 18.032 | 18.874 | SAFETY | SAFETY-HAZARD ELIM(P) | INTERSECTION AND CORRIDOR IMPROVEMENTS TO REDUCE CONFLICT POINTS AND ENHANCE SAFETY & CAPACITY ALONG US 31W FROM DIECKS DR TO WAREHOUSE CT. (2016BOP) | C |  | SAF | 2019 | 900000 | 900000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.003 | 2018-12-10 | TIP FY 18-22; ADMIN MOD#5; ADD PROJECT TO STIP; NEW |  |  | HARDIN | 4-9008.2 | US 31W |  | 19.704 | 20.08 | SAFETY | SAFETY-HAZARD ELIM(P) | INTERSECTION AND CORRIDOR IMPROVEMENTS TO REDUCE CONFLICT POINTS AND ENHANCE SAFETY & CAPACITY ALONG US 31W FROM WALMART DR TO SKYBLUE AVE. (2016BOP) | C |  | SAF | 2019 | 850000 | 850000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.003 | 2018-12-10 | TIP FY 18-22; ADMIN MOD#5; ADD PROJECT TO STIP; NEW |  |  | HARDIN | 4-9008.3 | US 31W |  | 20.432 | 21.143 | SAFETY | SAFETY-HAZARD ELIM(P) | INTERSECTION AND CORRIDOR IMPROVEMENTS TO REDUCE CONFLICT POINTS AND ENHANCE SAFETY & CAPACITY ALONG US 31W FROM PEAR ORCHARD RD TO PINE VALLEY DR. (2016BOP) | C |  | SAF | 2019 | 625000 | 625000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.003 | 2018-12-10 | TIP FY 18-22; ADMIN MOD#5; ADD PROJECT TO STIP; NEW | HSIP | 0311042 | HARDIN | 4-9008.4 | US 31W |  | 22.099 | 26.251 | SAFETY | SAFETY-HAZARD ELIM(P) | INTERSECTION AND CORRIDOR IMPROVEMENTS TO REDUCE CONFLICT POINTS AND ENHANCE SAFETY & CAPACITY ALONG US 31W FROM FIRST ST TO KY 1500. (2016BOP) | C |  | SAF | 2019 | 1600000 | 1600000 |  |  | 0 |  |  | OBLIGATED |  | 2310442 | 2310442 | 2020 | 1ST QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.162 | 2020-01-27 | TIP FY 18-22; ADMIN MOD#12; ADD PROJECT TO STIP; NEW |  |  | HARDIN | 4-9008.5 | US 31W |  | 18.032 | 21.143 | SAFETY | SAFETY-HAZARD ELIM(P) | INTERSECTION AND CORRIDOR IMPROVEMENTS TO REDUCE CONFLICT POINTS AND ENHANCE SAFETY & CAPACITY ALONG US 31W FROM DIECKS DR TO PINE VALLEY DR. (2018BOP) | C |  | SAF | 2020 | 2375000 | 2375000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.18 | 2020-04-21 | TIP FY 18-22; ADMIN MOD#13; INCREASE FUND AMOUNT; MOD |  |  | HARDIN | 4-9008.5 | US 31W |  | 18.032 | 21.143 | SAFETY | SAFETY-HAZARD ELIM(P) | INTERSECTION AND CORRIDOR IMPROVEMENTS TO REDUCE CONFLICT POINTS AND ENHANCE SAFETY & CAPACITY ALONG US 31W FROM DIECKS DR TO PINE VALLEY DR. (2018BOP) | C |  | SAF | 2020 | 4911000 | 4911000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.015 | 2019-01-25 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; RADCLIFF/ETOWN MPO TIP FY 18-22, GROUP PROJECT, PG 14, TABLE 4; NEW | HSIP | 9010349 | HARDIN, MEADE, NELSON | 4-9011 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | PRELIMINARY DESIGN AND STUDY TO DETERMINE LOW COST IMPROVEMENTS AT VARIOUS INTERSECTIONS WITHIN DISTRICT 4. (2018BOP) | D |  | SAF | 2019 | 275000 | 275000 |  |  | 0 |  |  | OBLIGATED | 275000 |  | 275000 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.056 | 2019-04-26 | TIP FY 18-22, ADMIN MOD#7; ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 9010388 | HARDIN | 4-9012 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | PRELIMINARY DESIGN AND STUDY OF MINI-ROUNDABOUTS AT VARIOUS INTERSECTIONS WITHIN THE CITY OF ELIZABETHTOWN. (2018BOP) | D |  | SAF | 2019 | 550000 | 550000 |  |  | 0 |  |  | OBLIGATED |  | 550000 | 550000 | 2019 | 3RD QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.266 | 2020-12-18 | TIP FY 18-22, ADMIN MOD#18; ADD R PHASE TO STIP; NEW | HSIP | 9010388 | HARDIN | 4-9012 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | PRELIMINARY DESIGN AND STUDY OF MINI-ROUNDABOUTS AT VARIOUS INTERSECTIONS WITHIN THE CITY OF ELIZABETHTOWN. (2018BOP) | R |  | SAF | 2021 | 300000 | 300000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.266 | 2020-12-18 | TIP FY 18-22, ADMIN MOD#18; ADD U PHASE TO STIP; NEW | HSIP | 9010388 | HARDIN | 4-9012 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | PRELIMINARY DESIGN AND STUDY OF MINI-ROUNDABOUTS AT VARIOUS INTERSECTIONS WITHIN THE CITY OF ELIZABETHTOWN. (2018BOP) | U |  | SAF | 2021 | 200000 | 200000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.266 | 2020-12-18 | TIP FY 18-22, ADMIN MOD#18; ADD C PHASE TO STIP; NEW |  |  | HARDIN | 4-9012.10 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | CONSTRUCT A MINI ROUNDABOUT AT THE INTERSECTION OF NORTH MAIN ST & CRUTCHER ST. (2020BOP) | C |  | SAF | 2021 | 225000 | 225000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.266 | 2020-12-18 | TIP FY 18-22, ADMIN MOD#18; ADD C PHASE TO STIP; NEW |  |  | HARDIN | 4-9012.20 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | CONSTRUCT A MINI ROUNDABOUT AT THE INTERSECTION OF DOLPHIN DR & JOSALE DR(2020BOP) | C |  | SAF | 2021 | 265000 | 265000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.266 | 2020-12-18 | TIP FY 18-22, ADMIN MOD#18; ADD C PHASE TO STIP; NEW |  |  | HARDIN | 4-9012.30 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | CONSTRUCT A MINI ROUNDABOUT AT THE INTERSECTION OF COMMERCE DR & EXECUTIVE DR(2020BOP) | C |  | SAF | 2021 | 350000 | 350000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.266 | 2020-12-18 | TIP FY 18-22, ADMIN MOD#18; ADD C PHASE TO STIP; NEW |  |  | HARDIN | 4-9012.40 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | CONSTRUCT A MINI ROUNDABOUT AT THE INTERSECTION OF NORTH MAIN ST & POPLAR ST(2020BOP) | C |  | SAF | 2021 | 240000 | 240000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.266 | 2020-12-18 | TIP FY 18-22, ADMIN MOD#18; ADD C PHASE TO STIP; NEW |  |  | HARDIN | 4-9012.50 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | CONSTRUCT A MINI ROUNDABOUT AT THE INTERSECTION OF WOODLAND DR & LAYMAN LN(2020BOP) | C |  | SAF | 2021 | 240000 | 240000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.266 | 2020-12-18 | TIP FY 18-22, ADMIN MOD#18; ADD C PHASE TO STIP; NEW |  |  | HARDIN | 4-9012.60 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | CONSTRUCT A MINI ROUNDABOUT AT THE INTERSECTION OF WEST POPLAR ST & SYCAMORE ST.(2020BOP) | C |  | SAF | 2021 | 250000 | 250000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.266 | 2020-12-18 | TIP FY 18-22, ADMIN MOD#18; ADD C PHASE TO STIP; NEW |  |  | HARDIN | 4-9012.70 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | CONSTRUCT A MINI ROUNDABOUT AT THE INTERSECTION OF WEST POPLAR ST & NORTH MANTLE AVE (2020BOP) | C |  | SAF | 2021 | 215000 | 215000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.175 | 2020-04-09 | RADCLIFF/ETOWN MPO AREA TIP FY 18-22, GROUP PROJECTS, TABLE 4, PAGE 13-14; ADD D PHASE TO STIP; NEW |  |  | HARDIN | 4-9015 | US 62 |  | 7.844 | 10.9 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON US 62 FROM MP 7.844 TO MP 10.900 IN HARDIN COUNTY, KY. (2018BOP) | D |  | SAF | 2020 | 200000 | 200000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.312 | 2021-06-22 | TIP FY 18-22, ADMIN MOD#20; UPDATE FY FROM 2020 TO FY 2021; MOD |  |  | HARDIN | 4-9015 | US 62 |  | 7.844 | 10.9 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON US 62 FROM MP 7.844 TO MP 10.900 IN HARDIN COUNTY, KY. (2018BOP) | D |  | SAF | 2021 | 200000 | 200000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.312 | 2021-06-22 | TIP FY 18-22, ADMIN MOD#20; ADD R PHASE TO STIP; NEW |  |  | HARDIN | 4-9015 | US 62 |  | 7.844 | 10.9 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON US 62 FROM MP 7.844 TO MP 10.900 IN HARDIN COUNTY, KY. (2018BOP) | R |  | SAF | 2021 | 15000 | 15000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.312 | 2021-06-22 | TIP FY 18-22, ADMIN MOD#20; ADD U PHASE TO STIP; NEW |  |  | HARDIN | 4-9015 | US 62 |  | 7.844 | 10.9 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON US 62 FROM MP 7.844 TO MP 10.900 IN HARDIN COUNTY, KY. (2018BOP) | U |  | SAF | 2021 | 100000 | 100000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.198 | 2020-06-16 | TIP FY 18-22, ADMIN MOD#15; ADD PROJECT TO STIP; NEW |  |  | HARDIN | 4-9016 | KY 251 |  | 0 | 1.458 | SAFETY | SAFETY-HAZARD ELIM(P) | OVERLAY AND RESTRIPE KY 251 TO CONVERT FROM A 4 LANE SECTION TO A 3 LANE SECTION BETWEEN W DIXIE AVE AND PEAR ORCHARD RD AND CONSTRUCT MINI ROUNDABOUTS ALONG KY 251 AT THE INTERSECTIONS WITH W POPLAR ST, BEECH ST, PANTHER LN, AND PEAR ORCHARD RD (2020BOP) | D |  | SAF | 2020 | 200000 | 200000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.198 | 2020-06-16 | TIP FY 18-22, ADMIN MOD#15; ADD PROJECT TO STIP; NEW |  |  | HARDIN | 4-9016 | KY 251 |  | 0 | 1.458 | SAFETY | SAFETY-HAZARD ELIM(P) | OVERLAY AND RESTRIPE KY 251 TO CONVERT FROM A 4 LANE SECTION TO A 3 LANE SECTION BETWEEN W DIXIE AVE AND PEAR ORCHARD RD AND CONSTRUCT MINI ROUNDABOUTS ALONG KY 251 AT THE INTERSECTIONS WITH W POPLAR ST, BEECH ST, PANTHER LN, AND PEAR ORCHARD RD (2020BOP) | R |  | SAF | 2021 | 50000 | 50000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.198 | 2020-06-16 | TIP FY 18-22, ADMIN MOD#15; ADD PROJECT TO STIP; NEW |  |  | HARDIN | 4-9016 | KY 251 |  | 0 | 1.458 | SAFETY | SAFETY-HAZARD ELIM(P) | OVERLAY AND RESTRIPE KY 251 TO CONVERT FROM A 4 LANE SECTION TO A 3 LANE SECTION BETWEEN W DIXIE AVE AND PEAR ORCHARD RD AND CONSTRUCT MINI ROUNDABOUTS ALONG KY 251 AT THE INTERSECTIONS WITH W POPLAR ST, BEECH ST, PANTHER LN, AND PEAR ORCHARD RD (2020BOP) | U |  | SAF | 2021 | 30000 | 30000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.198 | 2020-06-16 | TIP FY 18-22, ADMIN MOD#15; ADD PROJECT TO STIP; NEW |  |  | HARDIN | 4-9016 | KY 251 |  | 0 | 1.458 | SAFETY | SAFETY-HAZARD ELIM(P) | OVERLAY AND RESTRIPE KY 251 TO CONVERT FROM A 4 LANE SECTION TO A 3 LANE SECTION BETWEEN W DIXIE AVE AND PEAR ORCHARD RD AND CONSTRUCT MINI ROUNDABOUTS ALONG KY 251 AT THE INTERSECTIONS WITH W POPLAR ST, BEECH ST, PANTHER LN, AND PEAR ORCHARD RD (2020BOP) | C |  | SAF | 2021 | 800000 | 800000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.198 | 2020-06-16 | TIP FY 18-22, ADMIN MOD#15; ADD PROJECT TO STIP; NEW |  |  | HARDIN | 4-9017 | KY 1136 |  | 9.751 | 10.123 | SAFETY | SAFETY-HAZARD ELIM(P) | CONSTRUCTION OF A ROUNDABOUT AT THE INTERSECTION OF KY 1136 & US 31W BYPASS. (2020BOP) | D |  | SAF | 2020 | 250000 | 250000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.198 | 2020-06-16 | TIP FY 18-22, ADMIN MOD#15; ADD PROJECT TO STIP; NEW |  |  | HARDIN | 4-9017 | KY 1136 |  | 9.751 | 10.123 | SAFETY | SAFETY-HAZARD ELIM(P) | CONSTRUCTION OF A ROUNDABOUT AT THE INTERSECTION OF KY 1136 & US 31W BYPASS. (2020BOP) | R |  | SAF | 2021 | 50000 | 50000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.198 | 2020-06-16 | TIP FY 18-22, ADMIN MOD#15; ADD PROJECT TO STIP; NEW |  |  | HARDIN | 4-9017 | KY 1136 |  | 9.751 | 10.123 | SAFETY | SAFETY-HAZARD ELIM(P) | CONSTRUCTION OF A ROUNDABOUT AT THE INTERSECTION OF KY 1136 & US 31W BYPASS. (2020BOP) | U |  | SAF | 2021 | 100000 | 100000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.198 | 2020-06-16 | TIP FY 18-22, ADMIN MOD#15; ADD PROJECT TO STIP; NEW |  |  | HARDIN | 4-9017 | KY 1136 |  | 9.751 | 10.123 | SAFETY | SAFETY-HAZARD ELIM(P) | CONSTRUCTION OF A ROUNDABOUT AT THE INTERSECTION OF KY 1136 & US 31W BYPASS. (2020BOP) | C |  | SAF | 2021 | 600000 | 600000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | HARDIN | 4-10010 | KY 220 |  | 5.071 | 5.077 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 220 BRIDGE OVER MARTINS BRANCH CREEK. (047B00080N) | D |  | BR/STP | 2019 | 87500 | 54250 |  |  | 33250 | [5 empty] | 0
STIP | [9 empty] | HARDIN | 4-10010 | KY 220 |  | 5.071 | 5.077 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 220 BRIDGE OVER MARTINS BRANCH CREEK. (047B00080N) | C |  | BR/STP | 2020 | 192500 | 119350 |  |  | 73150 | [5 empty] | 0
STIP | [9 empty] | HARDIN | 4-10011 | KY 2212 |  | 2.705 | 2.711 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 2212 BRIDGE OVER PAWLEY CREEK. (047B00134N) | D |  | BR/STP | 2019 | 91000 | 56420 |  |  | 34580 | [5 empty] | 0
STIP | [9 empty] | HARDIN | 4-10011 | KY 2212 |  | 2.705 | 2.711 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 2212 BRIDGE OVER PAWLEY CREEK. (047B00134N) | C |  | BR/STP | 2020 | 206500 | 128030 |  |  | 78470 | [5 empty] | 0
STIP | [9 empty] | HARDIN | 4-10012 | KY 2800 |  | 3.689 | 3.695 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 2800 BRIDGE OVER SANDY CREEK. (047B00137N) | D |  | BR/STP | 2019 | 87500 | 54250 |  |  | 33250 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030021 | HARDIN | 4-10012 | KY 2800 |  | 3.689 | 3.695 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 2800 BRIDGE OVER SANDY CREEK. (047B00137N) | C |  | BR/STP | 2020 | 206500 | 128030 |  |  | 78470 |  |  | OBLIGATED |  | 179970 | 179970 | 2019 | 2ND QUARTER
STIP | [9 empty] | HARDIN | 4-10013 | CR 1100 |  | 1.046 | 1.052 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BEWLEY HOLLOW RD BRIDGE OVER MILL CREEK. (047C00014N) | D |  | BR/STP | 2019 | 91000 | 56420 |  |  | 34580 | [5 empty] | 0
STIP | [9 empty] | HARDIN | 4-10013 | CR 1100 |  | 1.046 | 1.052 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BEWLEY HOLLOW RD BRIDGE OVER MILL CREEK. (047C00014N) | C |  | BR/STP | 2020 | 227500 | 141050 |  |  | 86450 | [5 empty] | 0
STIP | [9 empty] | HARDIN | 4-20007 | BG 9002 |  | 5.82 | 8.837 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF MARTHA LAYNE COLLINS BLUEGRASS PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 5.82 TO MILEPOINT 8.837 | D |  | PM/NH | 2019 | 240000 | 192000 |  |  | 48000 | [5 empty] | 0
STIP | [7 empty] | NHPP | 0021051 | HARDIN | 4-20007 | BG 9002 |  | 5.82 | 8.837 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF MARTHA LAYNE COLLINS BLUEGRASS PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 5.82 TO MILEPOINT 8.837 | C |  | PM/NH | 2019 | 2400000 | 1920000 |  |  | 480000 |  |  | OBLIGATED | 5182360 |  | 5182360 | 2019 | 3RD QUARTER
STIP | [9 empty] | HARDIN | 4-20011 | US 31W |  | 17.677 | 19.5 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION | D |  | PM/NH | 2019 | 550000 | 440000 |  |  | 110000 | [5 empty] | 0
STIP | [9 empty] | HARDIN | 4-20011 | US 31W |  | 17.677 | 19.5 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION | C |  | PM/NH | 2019 | 5500000 | 4400000 |  |  | 1100000 | [5 empty] | 0
STIP | [9 empty] | HARDIN | 4-20012 | US 31W |  | 19.5 | 20.432 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION | D |  | PM/NH | 2019 | 250000 | 200000 |  |  | 50000 | [5 empty] | 0
STIP | [9 empty] | HARDIN | 4-20012 | US 31W |  | 19.5 | 20.432 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION | C |  | PM/NH | 2019 | 2500000 | 2000000 |  |  | 500000 | [5 empty] | 0
STIP | YES | [8 empty] | HARDIN | 4-20013 | US 31W |  | 27.732 | 29.5 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION | D |  | PM/NH | 2021 | 325000 | 260000 |  |  | 65000 | [5 empty] | 0
STIP | YES | [8 empty] | HARDIN | 4-20013 | US 31W |  | 27.732 | 29.5 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION | C |  | PM/NH | 2021 | 3250000 | 2600000 |  |  | 650000 | [5 empty] | 0
STIP | [9 empty] | HARDIN | 4-20014 | US 31WB |  | 0 | 0.25 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | D |  | PM/NH | 2020 | 25000 | 20000 |  |  | 5000 | [5 empty] | 0
STIP | [9 empty] | HARDIN | 4-20014 | US 31WB |  | 0 | 0.25 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | C |  | PM/NH | 2020 | 250000 | 200000 |  |  | 50000 | [5 empty] | 0
STIP | YES | [8 empty] | HARDIN | 4-20016 | WK 9001 |  | 120.93 | 132.4 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF WENDELL H. FORD WESTERN KY PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 120.93 (120.65 NON-CARDINAL) TO MILEPOINT 132.4 (130.95 NON-CARDINAL) | D |  | PM/NH | 2021 | 920000 | 736000 |  |  | 184000 | [5 empty] | 0
STIP | YES | [8 empty] | HARDIN | 4-20016 | WK 9001 |  | 120.93 | 132.4 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF WENDELL H. FORD WESTERN KY PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 120.93 (120.65 NON-CARDINAL) TO MILEPOINT 132.4 (130.95 NON-CARDINAL) | C |  | PM/NH | 2021 | 9200000 | 7360000 |  |  | 1840000 | [5 empty] | 0
STIP | [9 empty] | HARDIN | 4-20018 | WK 9001 |  | 132.4 | 134.92 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF WENDELL H. FORD WESTERN KY PARKWAY CARDINAL DIRECTION(S) FROM MILEPOINT 132.4 TO MILEPOINT 134.923 | D |  | PM/NH | 2019 | 200000 | 160000 |  |  | 40000 | [5 empty] | 0
STIP | [9 empty] | HARDIN | 4-20018 | WK 9001 |  | 132.4 | 134.92 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF WENDELL H. FORD WESTERN KY PARKWAY CARDINAL DIRECTION(S) FROM MILEPOINT 132.4 TO MILEPOINT 134.923 | C |  | PM/NH | 2019 | 2000000 | 1600000 |  |  | 400000 | [5 empty] | 0
STIP | YES | [8 empty] | HARDIN | 4-20028 | US 62 | 4.2 | 9.57 | 13.77 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION ON US-62 FROM MILEPOINT 9.57 TO MILEPOINT 13.77 | C |  | PM/NH | 2022 | 689000 | 551200 |  |  | 137800 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.211 | 2020-07-20 | TIP FY 18-22, ADMIN MOD#16; ADD PROJECT TO STIP; NEW |  |  | HARDIN | 4-20032 | I 65 |  | 102.1 | 103.308 | ASSET MANAGEMENT | AM-PAVEMENT(INT)(P) | REPAIR AND GRIND PCC PAVEMENT FROM JUST SOUTH OF JOE PRATHER HIGHWAY (MP 102.100) EXTENDING NORTH TO THE BULLITT COUNTY LINE (MP 103.308). | C |  | PM/NH | 2020 | 9130000 | 9130000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.229 | 2020-09-14 | ADD D PHASE TO STIP; PARENT NO. 11-269.10; NEW |  |  | HARLAN | 11-269.11 | US 421 |  | 0 | 3.65 | RELIABILITY | MAJOR WIDENING(O) | HARLAN-VIRGINIA STATE LINE; RECONSTRUCT US 421 FROM END OF THE EXISTING 4-LANE SECTION TO THE VIRGINIA STATE LINE. (2020CCR) | D |  | STP | 2020 | 500000 | 500000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | HARLAN | 11-1097 | KY 219 | 0.02 | 1.033 | 1.053 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER WALLINS CREEK ON KY 219 3.0 MILE SOUTH OF SCL OF WALLINS CREEK. (048B00047N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [9 empty] | HARLAN | 11-1097 | KY 219 | 0.02 | 1.033 | 1.053 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER WALLINS CREEK ON KY 219 3.0 MILE SOUTH OF SCL OF WALLINS CREEK. (048B00047N) | C |  | BR/STP | 2020 | 510000 | 316200 |  |  | 193800 | [5 empty] | 0
STIP | [9 empty] | HARLAN | 11-1101 | US 119 | 0.118 | 34.787 | 34.905 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON US 119 OVER KY 160/MAIN ST IN HARLAN COUNTY, KY. 048B00126N | D |  | BR/NH | 2019 | 560000 | 347200 |  |  | 212800 | [5 empty] | 0
STIP | [9 empty] | HARLAN | 11-1101 | US 119 | 0.118 | 34.787 | 34.905 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON US 119 OVER KY 160/MAIN ST IN HARLAN COUNTY, KY. 048B00126N | C |  | BR/NH | 2020 | 5460000 | 3385200 |  |  | 2074800 | [5 empty] | 0
STIP | [9 empty] | HARLAN | 11-1107 | CR 1328 |  | 0.171 | 0.179 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON SWEET BALL RD (CR-1328) (0.175) OVER AGES BRANCH. 048C00072N | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [9 empty] | HARLAN | 11-1107 | CR 1328 |  | 0.171 | 0.179 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON SWEET BALL RD (CR-1328) (0.175) OVER AGES BRANCH. 048C00072N | C |  | BR/STP | 2020 | 455000 | 282100 |  |  | 172900 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.218 | 2020-08-28 | ADD R PHASE TO STIP; PARENT NO. 11-9016; NEW |  |  | HARLAN | 11-9016.3 | KY 38 KY 72 |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | CONSTRUCT A MINI ROUNDABOUT AT THE INTERSECTION OF KY 38 & KY 72 (2020BOP). | R |  | SAF | 2020 | 15000 | 15000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.218 | 2020-08-28 | ADD C PHASE TO STIP; PARENT NO. 11-9016; NEW |  |  | HARLAN | 11-9016.3 | KY 38 KY 72 |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | CONSTRUCT A MINI ROUNDABOUT AT THE INTERSECTION OF KY 38 & KY 72 (2020BOP). | C |  | SAF | 2020 | 585000 | 585000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.175 | 2020-04-09 | ADD D PHASE TO STIP; PARENT NO. 99-911.09; NEW |  |  | HARLAN | 11-9020 | US 421 | [20 empty] | 0
STIP | [9 empty] | HARLAN | 11-10010 | KY 219 |  | 1.475 | 1.485 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-219 BRIDGE OVER WALLINS CREEK. (048B00046N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030143 | HARLAN | 11-10010 | KY 219 |  | 1.475 | 1.485 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-219 BRIDGE OVER WALLINS CREEK. (048B00046N) | C |  | BR/STP | 2020 | 490000 | 303800 |  |  | 186200 |  |  | OBLIGATED |  | 375910 | 375910 | 2019 | 3RD QUARTER
STIP | [9 empty] | HARLAN | 11-10011 | KY 219 |  | 0.325 | 0.333 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-219 BRIDGE OVER WALLINS CREEK. (048B00048N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [9 empty] | HARLAN | 11-10011 | KY 219 |  | 0.325 | 0.333 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-219 BRIDGE OVER WALLINS CREEK. (048B00048N) | C |  | BR/STP | 2020 | 367500 | 227850 |  |  | 139650 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.03 | 2019-03-01 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030069 | HARLAN | 11-10011 | KY 219 |  | 0.325 | 0.333 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-219 BRIDGE OVER WALLINS CREEK. (048B00048N) | C |  | STP | 2019 | 449970 | 449970 |  |  | 0 |  |  | OBLIGATED |  | 419465 | 419465 | 2019 | 3RD QUARTER
STIP | [9 empty] | HARLAN | 11-10012 | KY 72 |  | 11.773 | 11.821 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-72 BRIDGE OVER CLOVER FK CUMBERLAND RVR. (048B00095N) | D |  | BR/STP | 2019 | 245000 | 151900 |  |  | 93100 | [5 empty] | 0
STIP | [9 empty] | HARLAN | 11-10012 | KY 72 |  | 11.773 | 11.821 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-72 BRIDGE OVER CLOVER FK CUMBERLAND RVR. (048B00095N) | C |  | BR/STP | 2020 | 910000 | 564200 |  |  | 345800 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.123 | 2019-09-06 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD |  |  | HARLAN | 11-10012 | KY 72 |  | 11.773 | 11.821 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-72 BRIDGE OVER CLOVER FK CUMBERLAND RVR. (048B00095N) | C |  | BR | 2020 | 1601000 | 1601000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.311 | 2021-07-21 | INCREASE FUNDS BASED ON NEW ESTIMATE; MOD |  |  | HARLAN | 11-10012 | KY 72 |  | 11.773 | 11.821 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-72 BRIDGE OVER CLOVER FK CUMBERLAND RVR. (048B00095N) | C |  | BR | 2020 | 1794000 | 1794000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | HARLAN | 11-10013 | KY 179 |  | 0.081 | 0.087 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-179 BRIDGE OVER FUGETT CREEK. (048B00097N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [9 empty] | HARLAN | 11-10013 | KY 179 |  | 0.081 | 0.087 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-179 BRIDGE OVER FUGETT CREEK. (048B00097N) | C |  | BR/STP | 2020 | 612500 | 379750 |  |  | 232750 | [5 empty] | 0
STIP | [9 empty] | HARLAN | 11-10014 | KY 3451 |  | 1.521 | 1.527 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-3451 BRIDGE OVER EWING CREEK. (048B00146N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [9 empty] | HARLAN | 11-10014 | KY 3451 |  | 1.521 | 1.527 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-3451 BRIDGE OVER EWING CREEK. (048B00146N) | C |  | BR/STP | 2020 | 525000 | 325500 |  |  | 199500 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.075 | 2019-05-28 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030141 | HARLAN | 11-10014 | KY 3451 |  | 1.521 | 1.527 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-3451 BRIDGE OVER EWING CREEK. (048B00146N) | C |  | STP | 2020 | 540181 | 540181 |  |  | 0 |  |  | OBLIGATED |  | 676015 | 676015 | 2019 | 3RD QUARTER
STIP | [9 empty] | HARLAN | 11-10015 | KY 2007 |  | 3.204 | 3.214 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-2007 BRIDGE OVER WALLINS CREEK. (048B00179N) | D |  | BR/STP | 2019 | 192500 | 119350 |  |  | 73150 | [5 empty] | 0
STIP | [9 empty] | HARLAN | 11-10015 | KY 2007 |  | 3.204 | 3.214 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-2007 BRIDGE OVER WALLINS CREEK. (048B00179N) | C |  | BR/STP | 2020 | 469000 | 290780 |  |  | 178220 | [5 empty] | 0
STIP | [9 empty] | HARLAN | 11-10016 | CR 1020W |  | 0.012 | 0.022 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF RASNICK RD BRIDGE OVER POOR FK CUMBERLAND RVR. (048C00008N) | D |  | BR/STP | 2019 | 192500 | 119350 |  |  | 73150 | [5 empty] | 0
STIP | [9 empty] | HARLAN | 11-10016 | CR 1020W |  | 0.012 | 0.022 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF RASNICK RD BRIDGE OVER POOR FK CUMBERLAND RVR. (048C00008N) | C |  | BR/STP | 2020 | 630000 | 390600 |  |  | 239400 | [5 empty] | 0
STIP | [9 empty] | HARLAN | 11-10017 | CR 1218U |  | 0.015 | 0.019 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BLUE LN BRIDGE OVER PATH FK OF PUCKETT CREEK. (048C00043N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [9 empty] | HARLAN | 11-10017 | CR 1218U |  | 0.015 | 0.019 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BLUE LN BRIDGE OVER PATH FK OF PUCKETT CREEK. (048C00043N) | C |  | BR/STP | 2020 | 581000 | 360220 |  |  | 220780 | [5 empty] | 0
STIP | [9 empty] | HARLAN | 11-10018 | CS 1041 |  | 0.126 | 0.182 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KENTUCKY AV BRIDGE OVER MARTINS FK CUMBERLAND RV. (048C00067N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [9 empty] | HARLAN | 11-10018 | CS 1041 |  | 0.126 | 0.182 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KENTUCKY AV BRIDGE OVER MARTINS FK CUMBERLAND RV. (048C00067N) | C |  | BR/STP | 2020 | 647500 | 401450 |  |  | 246050 | [5 empty] | 0
STIP | [9 empty] | HARLAN | 11-10019 | CR 1082D |  | 0.004 | 0.02 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF PRICE LN BRIDGE OVER CLOVER FK CUMBERLAND RVR. (048C00094N) | D |  | BR/STP | 2019 | 192500 | 119350 |  |  | 73150 | [5 empty] | 0
STIP | [9 empty] | HARLAN | 11-10019 | CR 1082D |  | 0.004 | 0.02 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF PRICE LN BRIDGE OVER CLOVER FK CUMBERLAND RVR. (048C00094N) | C |  | BR/STP | 2020 | 598500 | 371070 |  |  | 227430 | [5 empty] | 0
STIP | [9 empty] | HARLAN | 11-10020 | CR 1253 |  | 0.03 | 0.036 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BANNER FORK RD BRIDGE OVER WALLINS CREEK. (048C00138N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [9 empty] | HARLAN | 11-10020 | CR 1253 |  | 0.03 | 0.036 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BANNER FORK RD BRIDGE OVER WALLINS CREEK. (048C00138N) | C |  | BR/STP | 2020 | 427000 | 264740 |  |  | 162260 | [5 empty] | 0
STIP | [9 empty] | HARLAN | 11-10040 | KY 1604 |  | 1.984 | 1.99 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 1601 BRIDGE OVER JONES CREEK. (048B00073N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030088 | HARLAN | 11-10040 | KY 1604 |  | 1.984 | 1.99 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 1601 BRIDGE OVER JONES CREEK. (048B00073N) | C |  | BR/STP | 2020 | 740600 | 459172 |  |  | 281428 |  |  | OBLIGATED |  | 310346 | 310346 | 2019 | 3RD QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.075 | 2019-05-28 | ADD PROJECT TO STIP; NEW |  |  | HARLAN | 11-10050 | CR 1124 |  | 0.013 |  | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES ON KELLY-CLOSEPLINT (CR 1124) OVER CLOVER FK CUMBERLAND RVR. (048C00093N) | C |  | STP | 2020 | 565000 | 565000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.123 | 2019-09-06 | ADD PROJECT TO STIP; PARENT NO. 99-65.16 AND 99-65.17; NEW |  |  | HARLAN | 11-10055 | CR 1215 |  | 0.015 |  | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES ON KELLY SMITH RD (CR 1215) OVER MARTINS FK CUMBERLAND RV. (048C00076N) | C |  | BR | 2020 | 284000 | 284000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.155 | 2020-01-22 | INCREASE FUND AMOUNT BASED ON NEW ESTIMATE; MOD | STPBRZ | 9030245 | HARLAN | 11-10055 | CR 1215 |  | 0.015 |  | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES ON KELLY SMITH RD (CR 1215) OVER MARTINS FK CUMBERLAND RV. (048C00076N) | C |  | BR | 2020 | 397900 | 397900 |  |  | 0 |  |  | OBLIGATED | 20000 | 361460 | 381460 | 2020 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.229 | 2020-09-14 | ADD C PHASE TO STIP; PARENT NO. 99-224.14; NEW |  |  | HARLAN | 11-20032 | KY 221 |  | 0 | 5.9 | ASSET MANAGEMENT | AM-PAVEMENT(PRI)(P) | RESURFACING OF KY 221 (MP 0.0-5.9) IN HARLAN COUNTY, KY. | C |  | STP | 2020 | 276000 | 276000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | HART | 4-441 | KY 335 |  | 1.2 | 2.545 | ECONOMIC DEVELOPMENT | ECONOMIC DEVEL(O) | IMPROVE MOBILITY, CONNECTIVITY AND SAFETY BY ADDRESSING COMMERCIAL AND INDUSTRIAL TRAFFIC MOVEMENT FROM US-31W SOUTH OF KY-218 TO I-65. (16CCR)(18CCR) | R |  | NH | 2020 | 1500000 | 1500000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.229 | 2020-09-14 | INCREASE FUND AMOUNT PER NEW ESTIMATE & CHANGE FUND TYPE FROM NH TO STP; MOD |  |  | HART | 4-441 | KY 335 |  | 1.2 | 2.545 | ECONOMIC DEVELOPMENT | ECONOMIC DEVEL(O) | IMPROVE MOBILITY, CONNECTIVITY AND SAFETY BY ADDRESSING COMMERCIAL AND INDUSTRIAL TRAFFIC MOVEMENT FROM US-31W SOUTH OF KY-218 TO I-65. (16CCR)(18CCR) | R |  | STP | 2020 | 2100000 | 2100000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | HART | 4-441 | KY 335 |  | 1.2 | 2.545 | ECONOMIC DEVELOPMENT | ECONOMIC DEVEL(O) | IMPROVE MOBILITY, CONNECTIVITY AND SAFETY BY ADDRESSING COMMERCIAL AND INDUSTRIAL TRAFFIC MOVEMENT FROM US-31W SOUTH OF KY-218 TO I-65. (16CCR)(18CCR) | U |  | NH | 2021 | 1000000 | 800000 |  |  | 200000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.229 | 2020-09-14 | INCREASE FUND AMOUNT PER NEW ESTIMATE & CHANGE FUND TYPE FROM NH TO STP; MOD |  |  | HART | 4-441 | KY 335 |  | 1.2 | 2.545 | ECONOMIC DEVELOPMENT | ECONOMIC DEVEL(O) | IMPROVE MOBILITY, CONNECTIVITY AND SAFETY BY ADDRESSING COMMERCIAL AND INDUSTRIAL TRAFFIC MOVEMENT FROM US-31W SOUTH OF KY-218 TO I-65. (16CCR)(18CCR) | U |  | STP | 2020 | 1500000 | 1500000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.184 | 2020-05-22 | ADD R PHASE TO STIP; NEW |  |  | HARRISON | 6-8708 | US 27 |  | 11.9 | 12.4 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT US 27 FROM MP 11.9 TO MP 12.4. (12CCN)(14CCR)(18CCN) | R |  | STP | 2022 | 480000 | 480000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.184 | 2020-05-22 | ADD C PHASE TO STIP; NEW |  |  | HARRISON | 6-8708 | US 27 |  | 11.9 | 12.4 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT US 27 FROM MP 11.9 TO MP 12.4. (12CCN)(14CCR)(18CCN) | C |  | STP | 2023 | 5500000 | 5500000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | AMENDMENT | 2018.002 | 2019-05-13 | TIP REFERENCE FY 20-24; RESOLUTION DATED 3/14/2019; NEW |  |  | HENDERSON | [22 empty] | 0
STIP MOD |  |  |  | AMENDMENT | 2018.010 | 2021-05-18 | TIP REFERENCE FY 22-26; RESOLUTION DATED 3/11/21; NEW |  |  | HENDERSON
STIP | YES | YES | PE in the TIP for FY 2018. Amount in TIP is greater but does not require revision. Adding RW and CN in the FY 2020-2024 TIP. |  |  |  |  | STPM | 9020010 | HENDERSON | 2-382 | US 60 |  | 0 | 1.226 | RELIABILITY | RECONSTRUCTION(O) | WATHEN LANE: UPGRADE WITH WIDENED LANES, CURB, GUTTER AND SIDEWALK FROM US 60 TO CITY LIMITS. | D |  | SHN | 2019 | 304000 | 243200 |  |  |  | 60800 |  | OBLIGATED | 306000 |  | 306000 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.045 | 2019-04-04 | TIP FY 18-21, ADMIN MOD; UPDATE FUND AMOUNT; MOD | STPM | 9020010 | HENDERSON | 2-382 | US 60 |  | 0 | 1.226 | RELIABILITY | RECONSTRUCTION(O) | WATHEN LANE: UPGRADE WITH WIDENED LANES, CURB, GUTTER AND SIDEWALK FROM US 60 TO CITY LIMITS. | D |  | SHN |  | 380000 | 304000 |  |  |  | 76000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.285 | 2021-03-22 | TIP FY 20-24, ADMIN MOD; ADD R PHASE TO STIP; NEW |  |  | HENDERSON | 2-382 | US 60 |  | 0 | 1.226 | RELIABILITY | RECONSTRUCTION(O) | WATHEN LANE: UPGRADE WITH WIDENED LANES, CURB, GUTTER AND SIDEWALK FROM US 60 TO CITY LIMITS. | R |  | SHN | 2021 | 400000 | 320000 |  |  |  | 80000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.293 | 2021-04-09 | TIP FY 20-24, ADMIN MOD; UPDATE FUND AMOUNTS; MOD |  |  | HENDERSON | 2-382 | US 60 |  | 0 | 1.226 | RELIABILITY | RECONSTRUCTION(O) | WATHEN LANE: UPGRADE WITH WIDENED LANES, CURB, GUTTER AND SIDEWALK FROM US 60 TO CITY LIMITS. | R |  | SHN | 2021 | 419000 | 335000 |  |  |  | 84000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.304 | 2021-05-25 | TIP FY 22-26, AMEND#1; REMOVE R/W PHASE; MOD |  |  | HENDERSON | 2-382 | US 60 |  | 0 | 1.226 | RELIABILITY | RECONSTRUCTION(O) | WATHEN LANE: UPGRADE WITH WIDENED LANES, CURB, GUTTER AND SIDEWALK FROM US 60 TO CITY LIMITS. | R |  | SHN | 2022 | 0 | 0 |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.285 | 2021-03-22 | TIP FY 20-24, ADMIN MOD; ADD U PHASE TO STIP; NEW; (NOTE: $272,587 IS FUNDED BY CRRSAA FUNDS FOR A TOTAL OF $350,000 FOR U PHASE.) |  |  | HENDERSON | 2-382 | US 60 |  | 0 | 1.226 | RELIABILITY | RECONSTRUCTION(O) | WATHEN LANE: UPGRADE WITH WIDENED LANES, CURB, GUTTER AND SIDEWALK FROM US 60 TO CITY LIMITS. | U |  | SHN | 2021 | 77386 | 61903.4 |  |  |  | 15482.6 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.293 | 2021-04-09 | TIP FY 20-24, ADMIN MOD; UPDATE FUND AMOUNTS; MOD |  |  | HENDERSON | 2-382 | US 60 |  | 0 | 1.226 | RELIABILITY | RECONSTRUCTION(O) | WATHEN LANE: UPGRADE WITH WIDENED LANES, CURB, GUTTER AND SIDEWALK FROM US 60 TO CITY LIMITS. | U |  | SHN | 2021 | 710000 | 623000 |  |  |  | 87000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.304 | 2021-05-25 | TIP FY 22-26, AMEND#1; REMOVE U PHASE; MOD |  |  | HENDERSON | 2-382 | US 60 |  | 0 | 1.226 | RELIABILITY | RECONSTRUCTION(O) | WATHEN LANE: UPGRADE WITH WIDENED LANES, CURB, GUTTER AND SIDEWALK FROM US 60 TO CITY LIMITS. | U |  | SHN | 2022 | 0 | 0 |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.285 | 2021-03-22 | TIP FY 20-24, ADMIN MOD; ADD C PHASE TO STIP; NEW |  |  | HENDERSON | 2-382 | US 60 |  | 0 | 1.226 | RELIABILITY | RECONSTRUCTION(O) | WATHEN LANE: UPGRADE WITH WIDENED LANES, CURB, GUTTER AND SIDEWALK FROM US 60 TO CITY LIMITS. | C |  | SHN | 2022 | 3300000 | 2640000 |  |  |  | 660000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.247 | 2020-10-15 | TIP FY 20-24, AMENDMENT; ADD D PHASE TO STIP; NEW |  |  | HENDERSON | 2-383 | CS 1372 |  | 0.309 | 1.395 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE SAFETY AND REDUCE CONGESTION ON CS-1372 (WATSON LANE). (18CCR) | D |  | STP | 2021 | 500000 | [9 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.247 | 2020-10-15 | TIP FY 20-24, AMENDMENT; ADD R PHASE TO STIP; NEW |  |  | HENDERSON | 2-383 | CS 1372 |  | 0.309 | 1.395 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE SAFETY AND REDUCE CONGESTION ON CS-1372 (WATSON LANE). (18CCR) | R |  | STP | 2021 | 1630000 | [9 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.247 | 2020-10-15 | TIP FY 20-24, AMENDMENT; ADD U PHASE TO STIP; NEW |  |  | HENDERSON | 2-383 | CS 1372 |  | 0.309 | 1.395 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE SAFETY AND REDUCE CONGESTION ON CS-1372 (WATSON LANE). (18CCR) | U |  | STP | 2021 | 1580000 | [9 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.247 | 2020-10-15 | TIP FY 20-24, AMENDMENT; ADD C PHASE TO STIP; NEW |  |  | HENDERSON | 2-383 | CS 1372 |  | 0.309 | 1.395 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE SAFETY AND REDUCE CONGESTION ON CS-1372 (WATSON LANE). (18CCR) | C |  | STP | 2023 | 6340000 | [9 empty] | 0
STIP |  |  | Have specific projects identified in TIP. | [6 empty] | HENDERSON | 2-700.13 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | FEDERAL 'STP' FUNDS DEDICATED TO HENDERSON FOR FY 2018. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C |  | SHN | 2019 | 1176000 | 940800 |  |  |  | 235200 |  |  |  |  | 0
STIP |  |  | Have specific projects identified in TIP. | [6 empty] | HENDERSON | 2-700.14 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | FEDERAL 'STP' FUNDS DEDICATED TO HENDERSON FOR FY 2019. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | C |  | SHN | 2019 | 700000 | 560000 |  |  |  | 140000 |  |  |  |  | 0
STIP |  |  | Have specific projects identified in TIP. | [6 empty] | HENDERSON | 2-700.15 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | FEDERAL 'STP' FUNDS DEDICATED TO HENDERSON FOR FY 2020. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | C |  | SHN | 2020 | 700000 | 560000 |  |  |  | 140000 |  |  |  |  | 0
STIP |  |  | Have specific projects identified in TIP. | [6 empty] | HENDERSON | 2-700.16 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | FEDERAL 'STP' FUNDS DEDICATED TO HENDERSON FOR FY 2021. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | C |  | SHN | 2021 | 700000 | 560000 |  |  |  | 140000 |  |  |  |  | 0
STIP |  |  | Have specific projects identified in TIP. | [6 empty] | HENDERSON | 2-700.17 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | FEDERAL 'STP' FUNDS DEDICATED TO HENDERSON FOR FY 2022. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | C |  | SHN | 2022 | 700000 | 560000 |  |  |  | 140000 |  |  |  |  | 0
STIP | YES | YES | Discussion ongoing as to the exact amount needed. Once decided, we can make the amendment to the TIP | [6 empty] | HENDERSON | 2-711 | US 41 | 0.14 | 12.766 | 12.906 | SAFETY | SAFETY(P) | US 41/KY 812 INTERSECTION UPGRADE: ADD RIGHT TURN AND LEFT TURN LANES INCLUDING SIGNAL PHASING. KYTC PROJECT WITH KYTC PROVIDING 20% MATCH.(TOLL CREDITS)(FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | R |  | SHN | 2019 | 50000 | 40000 |  |  |  | 10000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.173 | 2020-03-06 | TIP FY 20-24, ADMIN MOD; UPDATE FISCAL YEAR AND FUND AMOUNT; MOD |  |  | HENDERSON | 2-711 | US 41 | 0.14 | 12.766 | 12.906 | SAFETY | SAFETY(P) | US 41/KY 812 INTERSECTION UPGRADE: ADD RIGHT TURN AND LEFT TURN LANES INCLUDING SIGNAL PHASING. KYTC PROJECT WITH KYTC PROVIDING 20% MATCH.(TOLL CREDITS)(FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | R |  | SHN | 2020 | 100000 | 100000 |  |  |  | 0 |  |  |  |  | 0
STIP | YES | YES | Discussion ongoing as to the exact amount needed - more UT $ required. Once decided, we can make the amendment to the TIP | [6 empty] | HENDERSON | 2-711 | US 41 | 0.14 | 12.766 | 12.906 | SAFETY | SAFETY(P) | US 41/KY 812 INTERSECTION UPGRADE: ADD RIGHT TURN AND LEFT TURN LANES INCLUDING SIGNAL PHASING. KYTC PROJECT WITH KYTC PROVIDING 20% MATCH.(TOLL CREDITS)(FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | U |  | SHN | 2019 | 100000 | 80000 |  |  |  | 20000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.173 | 2020-03-06 | TIP FY 20-24, ADMIN MOD; UPDATE FISCAL YEAR AND FUND AMOUNT; MOD |  |  | HENDERSON | 2-711 | US 41 | 0.14 | 12.766 | 12.906 | SAFETY | SAFETY(P) | US 41/KY 812 INTERSECTION UPGRADE: ADD RIGHT TURN AND LEFT TURN LANES INCLUDING SIGNAL PHASING. KYTC PROJECT WITH KYTC PROVIDING 20% MATCH.(TOLL CREDITS)(FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | U |  | SHN | 2020 | 200000 | 200000 |  |  |  | 0 |  |  |  |  | 0
STIP |  | YES | CN being moved to FY 2020 in the new FY 2020-2024 TIP per concurrence with District and LPA. | [6 empty] | HENDERSON | 2-711 | US 41 | 0.14 | 12.766 | 12.906 | SAFETY | SAFETY(P) | US 41/KY 812 INTERSECTION UPGRADE: ADD RIGHT TURN AND LEFT TURN LANES INCLUDING SIGNAL PHASING. KYTC PROJECT WITH KYTC PROVIDING 20% MATCH.(TOLL CREDITS)(FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C |  | SHN | 2019 | 950000 | 760000 |  |  |  | 190000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.173 | 2020-03-06 | TIP FY 20-24, ADMIN MOD; UPDATE FISCAL YEAR; MOD |  |  | HENDERSON | 2-711 | US 41 | 0.14 | 12.766 | 12.906 | SAFETY | SAFETY(P) | US 41/KY 812 INTERSECTION UPGRADE: ADD RIGHT TURN AND LEFT TURN LANES INCLUDING SIGNAL PHASING. KYTC PROJECT WITH KYTC PROVIDING 20% MATCH.(TOLL CREDITS)(FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C |  | SHN | 2021 | 200000 | 200000 |  |  |  | 0 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.319 | 2021-07-15 | TIP FY 22-26, AMENDMENT; UPDATE FISCAL YEAR AND FUND AMOUNT; MOD |  |  | HENDERSON | 2-711 | US 41 | 0.14 | 12.766 | 12.906 | SAFETY | SAFETY(P) | US 41/KY 812 INTERSECTION UPGRADE: ADD RIGHT TURN AND LEFT TURN LANES INCLUDING SIGNAL PHASING. KYTC PROJECT WITH KYTC PROVIDING 20% MATCH.(TOLL CREDITS)(FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C |  | SHN | 2022 | 950000 | 950000 | [8 empty] | 0
STIP | YES | YES | CN in the TIP for FY 2018. Amount in TIP is greater but does not require revision. |  |  |  |  | STPM | 3020009 | HENDERSON | 2-713 | CS 1453 |  | 0.72 | 0.77 | RELIABILITY | AM-BRIDGE (P) | WATHEN BRIDGE REPLACEMENT: REPLACE EXISTING BRIDGE WITH 6FT PRECAST CONCRETE BOX CULVERT, PAVEMENT AND GUARDRAIL. LPA PROJECT. CITY TO PROVIDE MATCH.(FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP)(051C00014) | C |  | SHN | 2019 | 160000 | 128000 |  |  |  | 32000 |  | OBLIGATED |  | 165000 | 165000 | 2019 | 2ND QUARTER | CITY OF HENDERSON
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.045 | 2019-04-04 | TIP FY 18-21; ADMIN MOD; REVISE FUNDS; MOD | STPM | 3020009 | HENDERSON | 2-713 | CS 1453 |  | 0.72 | 0.77 | RELIABILITY | AM-BRIDGE (P) | WATHEN BRIDGE REPLACEMENT: REPLACE EXISTING BRIDGE WITH 6FT PRECAST CONCRETE BOX CULVERT, PAVEMENT AND GUARDRAIL. LPA PROJECT. CITY TO PROVIDE MATCH.(FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP)(051C00014) | C |  | SHN | 2019 | 318000 | 254000 |  |  |  | 64000 |  | OBLIGATED |  | 184000 | 184000 | 2019 | 2ND QUARTER | CITY OF HENDERSON
STIP | YES |  | Moving the funding for RW and UT to 2022 in the new FY 2020-2024 TIP per concurrence with District and LPA. | [6 empty] | HENDERSON | 2-714 | KY 2183 | 0.1 | 1.693 | 1.793 | RELIABILITY | MATCHED FED FUNDS(O) | KY 2183 / KY 1539 INTERSECTION AND UPGRADE: PROJECT WILL RECONSTRUCT THE INTERSECTION AND MAKE IMPROVEMENTS TO THE SOUTHBOUND APPROACH. (2012BOP) | R |  | SHN | 2019 | 150000 | 120000 |  |  |  | 30000 |  |  |  |  | 0
STIP | YES | YES | Moving the funding for RW and UT to 2022 in the new FY 2020-2024 TIP per concurrence with District and LPA. | [6 empty] | HENDERSON | 2-714 | KY 2183 | 0.1 | 1.693 | 1.793 | RELIABILITY | MATCHED FED FUNDS(O) | KY 2183 / KY 1539 INTERSECTION AND UPGRADE: PROJECT WILL RECONSTRUCT THE INTERSECTION AND MAKE IMPROVEMENTS TO THE SOUTHBOUND APPROACH. (2012BOP) | U |  | SHN | 2019 | 400000 | 320000 |  |  |  | 80000 |  |  |  |  | 0
STIP | YES | [8 empty] | HENDERSON | 2-714 | KY 2183 | 0.1 | 1.693 | 1.793 | RELIABILITY | MATCHED FED FUNDS(O) | KY 2183 / KY 1539 INTERSECTION AND UPGRADE: PROJECT WILL RECONSTRUCT THE INTERSECTION AND MAKE IMPROVEMENTS TO THE SOUTHBOUND APPROACH. (2012BOP) | C |  | SHN | 2019 | 600000 | 480000 |  |  |  | 120000 |  |  |  |  | 0
STIP | YES | YES | Moving the funding for RW to 2024 in the new FY 2020-2024 TIP per concurrence with District and LPA. | [6 empty] | HENDERSON | 2-715 | US 41 | 0.1 | 18.488 | 18.588 | RELIABILITY | MATCHED FED FUNDS(O) | US 41/ WOLF HILLS ROAD INTERSECTION UPGRADE: PROJECT WILL ADD DEDICATED RIGHT TURN AND LEFT TURN LANES INCLUDING SIGNAL PHASING TO BE MODIFIED OR ADDED TO EACH LEG OF THE INTERSECTION. (2012BOP) | R |  | SHN | 2019 | 50000 | 40000 |  |  |  | 10000 |  |  |  |  | 0
STIP | YES | YES | Moving the funding for UT and CN to Cost to Complete column in the new FY 2020-2024 TIP per concurrence with District and LPA. | [6 empty] | HENDERSON | 2-715 | US 41 | 0.1 | 18.488 | 18.588 | RELIABILITY | MATCHED FED FUNDS(O) | US 41/ WOLF HILLS ROAD INTERSECTION UPGRADE: PROJECT WILL ADD DEDICATED RIGHT TURN AND LEFT TURN LANES INCLUDING SIGNAL PHASING TO BE MODIFIED OR ADDED TO EACH LEG OF THE INTERSECTION. (2012BOP) | U |  | SHN | 2019 | 100000 | 80000 |  |  |  | 20000 |  |  |  |  | 0
STIP | YES | YES | Moving the funding for UT and CN to Cost to Complete column in the new FY 2020-2024 TIP per concurrence with District and LPA. | [6 empty] | HENDERSON | 2-715 | US 41 | 0.1 | 18.488 | 18.588 | RELIABILITY | MATCHED FED FUNDS(O) | US 41/ WOLF HILLS ROAD INTERSECTION UPGRADE: PROJECT WILL ADD DEDICATED RIGHT TURN AND LEFT TURN LANES INCLUDING SIGNAL PHASING TO BE MODIFIED OR ADDED TO EACH LEG OF THE INTERSECTION. (2012BOP) | C |  | SHN | 2019 | 500000 | 400000 |  |  |  | 100000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.208 | 2020-07-13 | TIP FY 20-24, AMENDMENT RESOLUTION NO. 20-24 TIP 12; REMOVE PROJECT FROM TIP/STIP; MOD |  |  | HENDERSON | 2-715 | US 41 | 0.1 | 18.488 | 18.588 | RELIABILITY | MATCHED FED FUNDS(O) | US 41/ WOLF HILLS ROAD INTERSECTION UPGRADE: PROJECT WILL ADD DEDICATED RIGHT TURN AND LEFT TURN LANES INCLUDING SIGNAL PHASING TO BE MODIFIED OR ADDED TO EACH LEG OF THE INTERSECTION. (2012BOP)
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.009 | 2018-12-26 | TIP FY 18-21; ADMIN MOD; ADDING PROJECT TO STIP; NEW | HSIP | 0416020 | HENDERSON | 2-913 | US 41 |  | 16 | 16.4 | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALL HIGH FRICTION SURFACE ON US 41 FROM MP 16.00 TO MP 16.40 IN HENDERSON COUNTY. (2016BOP) | C |  | SAF | 2019 | 220000 | 220000 |  |  |  | 0 |  | OBLIGATED |  | 220000 | 220000 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.082 | 2019-06-18 | TIP FY 18-21; AMENDMENT, RESOLUTION NO. 18-21, TIP 14; ADD PROJECT TO STIP; NEW | HSIP | 5047018 | HENDERSON | 2-920 | US 41 |  | 0 | 17.436 | SAFETY | SAFETY-HAZARD ELIM(P) | REPLACEMENT OF TARGETED GUARDRAIL END TREATMENTS ON US 41A FROM MP 0.000 TO MP 17.436 (2018BOP). | C |  | SAF | 2019 | 90000 | 90000 |  |  |  | 0 |  | OBLIGATED |  | 89010 | 89010 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.082 | 2019-06-18 | TIP FY 18-21; AMENDMENT, RESOLUTION NO. 18-21, TIP 14; ADD PROJECT TO STIP; NEW | HSIP | 0601207 | HENDERSON | 2-994 | US 60 |  | 0 | 25.111 | SAFETY | SAFETY-HAZARD ELIM(P) | REPLACEMENT OF TARGETED GUARDRAIL END TREATMENTS. (2018BOP) | C |  | SAF | 2019 | 385000 | 385000 |  |  |  | 0 |  | OBLIGATED |  | 500720 | 500720 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.235 | 2020-09-17 | TIP FY 20-24, ADMIN MOD; ADD PROJECT TO STIP; NEW |  |  | HENDERSON | 2-997 | US 41 |  | 0 | 18.407 | SAFETY | SAFETY-HAZARD ELIM(P) | REPLACEMENT OF TARGETED GUARDRAIL END TREATMENTS ALONG US 41 IN HENDERSON COUNTY, KY. (2018BOP) | C |  | SAF | 2021 | 520000 | 520000 |  |  |  | 0 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.235 | 2020-09-17 | TIP FY 20-24, ADMIN MOD; ADD PROJECT TO STIP; NEW |  |  | HENDERSON | 2-998 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | REPLACEMENT OF TARGETED GUARDRAIL END TREATMENTS AT VARIOUS INTERCHANGES IN HENDERSON COUNTY, KY. (2018BOP) | C |  | SAF | 2021 | 335000 | 335000 |  |  |  | 0 |  |  |  |  | 0
STIP | YES | YES | CN in FY 2018 in the current TIP. Will amend if needed at time of obligation request. Placing CN in FY 2020 in the new FY 2020-2024 TIP per discussion with District. Changed the funding split per the STIP split. |  |  |  |  | STPBRO | 5053031 | HENDERSON | 2-1080 | US 60 | 0.208 | 19.236 | 19.444 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON US 60 OVER GREEN RIVER AT INTERSECTION WITH KY 1078 051B00015N.(12CCR) | C |  | BR/STP | 2019 | 6000000 | 3720000 |  |  | 2280000 |  |  | OBLIGATED | 4000000 | 31437527.4 | 35437527.4 | 2019 | 4TH QUARTER
STIP | YES | YES | CN in FY 2018 in the current TIP. Will amend if needed at time of obligation request. Placing CN in FY 2020 in the new FY 2020-2024 TIP per discussion with District. Changed the funding split per the STIP split. | [6 empty] | HENDERSON | 2-1080.01 | US 60 | 0.208 | 19.236 | 19.444 | ASSET MANAGEMENT | PREFINANCD CONVRSN(O) | ADDRESS DEFICIENCIES OF BRIDGE ON US 60 OVER GREEN RIVER AT INTERSECTION WITH KY 1078. (SR 39) 051B00015N (ADDITIONAL FUNDING FOR C PHASE) | C |  | BR/STP | 2020 | 6000000 | 3720000 |  |  | 2280000 | [5 empty] | 0
STIP |  |  | CN in FY 2019 in the current TIP. Will amend if needed at time of obligation request. Placing CN in FY 2020 in the new FY 2020-2024 TIP per discussion with District. Changed funding split per the STIP split. | [6 empty] | HENDERSON | 2-1080.02 | US 60 | 0.208 | 19.236 | 19.444 | ASSET MANAGEMENT | PREFINANCD CONVRSN(O) | ADDRESS DEFICIENCIES OF BRIDGE ON US 60 OVER GREEN RIVER AT INTERSECTION WITH KY 1078. (SR 39) 051B00015N (ADDITIONAL FUNDING FOR C PHASE) | C |  | BR/STP | 2020 | 5000000 | 3100000 |  |  | 1900000 | [5 empty] | 0
STIP MOD |  |  |  | AMENDMENT | 2018.189 | 2020-05-22 | TIP FY 20-24, AMENDMENT RESOLUTION NO. 20-24 TIP 10; ADD D PHASE TO STIP; NEW |  |  | HENDERSON | 2-1088.1 | I 69 |  |  |  | RELIABILITY | NEW ROUTE(O) | DEVELOP ALIGNMENT FOR I-69 HENDERSON/EVANSVILLE OHIO RIVER CROSSING (TO BE DEVELOPED IN CONCERT WITH 2-1088.00).(16CCR)(C-COST=$1.0 BILLION; KYTC SHARE $600 MILLION) | D |  | NH | 2020 | 15000000 | 15000000 | [8 empty] | 0
STIP | YES | YES | Updating the estimates in the FY 2020-2024 TIP. | [6 empty] | HENDERSON | 2-1088.1 | I 69 |  |  |  | RELIABILITY | NEW ROUTE(O) | DEVELOP ALIGNMENT FOR I-69 HENDERSON/EVANSVILLE OHIO RIVER CROSSING (TO BE DEVELOPED IN CONCERT WITH 2-1088.00).(16CCR)(C-COST=$1.1 BILLION; KYTC SHARE $715 MILLION) | R |  | NH | 2021 | 19900000 | 15920000 |  |  | 3980000 | [5 empty] | 0
STIP | YES | YES | FY 2022 not in our current TIP. Updating the estimates in the FY 2020-2024 TIP. | [6 empty] | HENDERSON | 2-1088.1 | I 69 |  |  |  | RELIABILITY | NEW ROUTE(O) | DEVELOP ALIGNMENT FOR I-69 HENDERSON/EVANSVILLE OHIO RIVER CROSSING (TO BE DEVELOPED IN CONCERT WITH 2-1088.00).(16CCR)(C-COST=$1.1 BILLION; KYTC SHARE $715 MILLION) | U |  | NH | 2022 | 8000000 | 6400000 |  |  | 1600000 | [5 empty] | 0
STIP | YES | YES | FY 2022 not in our current TIP. Updating the estimates in the FY 2020-2024 TIP. | [6 empty] | HENDERSON | 2-1088.1 | I 69 |  |  |  | RELIABILITY | NEW ROUTE(O) | DEVELOP ALIGNMENT FOR I-69 HENDERSON/EVANSVILLE OHIO RIVER CROSSING (TO BE DEVELOPED IN CONCERT WITH 2-1088.00).(16CCR)(C-COST=$1.1 BILLION; KYTC SHARE $715 MILLION)(SPECIAL FINANCING MECHANISM KY SHARE) | C |  | NH | 2022 | 687500000 | 687500000 |  |  | 0 |  | YES |  |  |  | 0
STIP | YES | YES | FY 2022 not in our current TIP. Adding the project to the FY 2020-2024 TIP. | [6 empty] | HENDERSON | 2-2091.1 | US 41 | 1.028 | 19.14 | 20.168 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES AND PAINTING ON US 41 BRIDGES OVER OHIO RIVER. JOINT PROJECT WITH INDIANA. (051B0002R, 051B0007L)(BSBP) | C |  | BR/NH | 2022 | 21200000 | 13144000 |  |  | 8056000 | [5 empty] | 0
STIP | YES | YES | Adding the project to the FY 2020-2024 TIP. | [6 empty] | HENDERSON | 2-20023 | I 69 |  | 142.146 | 148.09 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-069 BOTH DIRECTION(S) FROM MILEPOINT 142.146 TO MILEPOINT 148.09 (150.142 NON-CARDINAL) | D |  | PM/NH | 2021 | 640000 | 512000 |  |  | 128000 | [5 empty] | 0
STIP | YES | YES | Adding the project to the FY 2020-2024 TIP. | [6 empty] | HENDERSON | 2-20023 | I 69 |  | 142.146 | 148.09 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-069 BOTH DIRECTION(S) FROM MILEPOINT 142.146 TO MILEPOINT 148.09 (150.142 NON-CARDINAL) | C |  | PM/NH | 2021 | 6400000 | 5120000 |  |  | 1280000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.259 | 2020-11-13 | TIP FY 20-24, ADMIN MOD; ADD D PHASE TO STIP; NEW |  |  | HENDERSON | 2-20058 | US 41 |  | 15.983 | 19.581 | RELIABILITY | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION ON US-41 FROM MP 15.983 TO MP 19.581. | D |  | NHPP | 2021 | 375000 | 300000 |  |  | 75000 | [5 empty] | 0
STIP | [9 empty] | HENRY | 5-10002 | KY 997 |  | 1.9 | 1.906 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 997 BRIDGE OVER WHITE SULPHUR CREEK. (052B00060N) | D |  | BR/STP | 2019 | 192500 | 119350 |  |  | 73150 | [5 empty] | 0
STIP | [9 empty] | HENRY | 5-10002 | KY 997 |  | 1.9 | 1.906 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 997 BRIDGE OVER WHITE SULPHUR CREEK. (052B00060N) | C |  | BR/STP | 2020 | 266000 | 164920 |  |  | 101080 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.021 | 2019-02-04 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030028 | HENRY | 5-10002 | KY 997 |  | 1.9 | 1.906 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 997 BRIDGE OVER WHITE SULPHUR CREEK. (052B00060N) | C |  | STP | 2019 | 539000 | 539000 |  |  | 0 |  |  | OBLIGATED |  | 435445 | 435445 | 2019 | 2ND QUARTER
STIP | [9 empty] | HENRY | 5-10003 | KY 3175 |  | 0.065 | 0.081 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 3175 BRIDGE OVER WHITE SULPHUR FORK. (052B00064N) | D |  | BR/STP | 2019 | 262500 | 162750 |  |  | 99750 | [5 empty] | 0
STIP | [9 empty] | HENRY | 5-10003 | KY 3175 |  | 0.065 | 0.081 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 3175 BRIDGE OVER WHITE SULPHUR FORK. (052B00064N) | C |  | BR/STP | 2020 | 574000 | 355880 |  |  | 218120 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.075 | 2019-05-28 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030144 | HENRY | 5-10003 | KY 3175 |  | 0.065 | 0.081 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 3175 BRIDGE OVER WHITE SULPHUR FORK. (052B00064N) | C |  | STP | 2020 | 627000 | 627000 |  |  | 0 |  |  | OBLIGATED |  | 1168115 | 1168115 | 2019 | 4TH QUARTER
STIP | [9 empty] | HENRY | 5-10004 | KY 3320 |  | 1.816 | 1.822 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 3320 BRIDGE OVER TRIB OF HARRODS CREEK. (052B00070N) | D |  | BR/STP | 2019 | 210000 | 130200 |  |  | 79800 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030082 | HENRY | 5-10004 | KY 3320 |  | 1.816 | 1.822 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 3320 BRIDGE OVER TRIB OF HARRODS CREEK. (052B00070N) | C |  | BR/STP | 2020 | 287000 | 177940 |  |  | 109060 |  |  | OBLIGATED |  | 539525 | 539525 | 2019 | 3RD QUARTER
STIP | [9 empty] | HENRY | 5-10006 | CR 1027 |  | 2.423 | 2.429 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF GULLION RUN RD BRIDGE OVER TRIB OF GULLION RUN. (052C00045N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030083 | HENRY | 5-10006 | CR 1027 |  | 2.423 | 2.429 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF GULLION RUN RD BRIDGE OVER TRIB OF GULLION RUN. (052C00045N) | C |  | BR/STP | 2020 | 231000 | 143220 |  |  | 87780 |  |  | OBLIGATED | 370695 |  | 370695 | 2019 | 3RD QUARTER
STIP | [9 empty] | HENRY | 5-10017 | KY 1606 |  | 6.326 | 6.354 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 1606 BRIDGE OVER WHITE SULPHUR FORK. (052B00048N) | D |  | BR/STP | 2019 | 245000 | 151900 |  |  | 93100 | [5 empty] | 0
STIP | [9 empty] | HENRY | 5-10017 | KY 1606 |  | 6.326 | 6.354 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 1606 BRIDGE OVER WHITE SULPHUR FORK. (052B00048N) | C |  | BR/STP | 2020 | 1022000 | 633640 |  |  | 388360 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.046 | 2019-04-07 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030094 | HENRY | 5-10017 | KY 1606 |  | 6.326 | 6.354 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 1606 BRIDGE OVER WHITE SULPHUR FORK. (052B00048N) | C |  | BR/STP | 2019 | 940000 | 940000 |  |  | 0 |  |  | OBLIGATED |  | 793470 | 793470 | 2019 | 3RD QUARTER
STIP | [9 empty] | HENRY | 5-20002 | I 71 |  | 24.727 | 28.173 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-071 BOTH DIRECTION(S) FROM MILEPOINT 24.727 TO MILEPOINT 28.173. | D |  | PM/NH | 2019 | 450000 | 360000 |  |  | 90000 | [5 empty] | 0
STIP | [9 empty] | HENRY | 5-20002 | I 71 |  | 24.727 | 28.173 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-071 BOTH DIRECTION(S) FROM MILEPOINT 24.727 TO MILEPOINT 28.173. | C |  | PM/NH | 2019 | 4500000 | 3600000 |  |  | 900000 | [5 empty] | 0
STIP | [9 empty] | HENRY | 5-20007 | I 71 |  | 37.183 | 38.086 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-071 CARDINAL DIRECTION(S) FROM MILEPOINT 37.183 TO MILEPOINT 38.086 | D |  | PM/NH | 2020 | 40000 | 32000 |  |  | 8000 | [5 empty] | 0
STIP | [9 empty] | HENRY | 5-20007 | I 71 |  | 37.183 | 38.086 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-071 CARDINAL DIRECTION(S) FROM MILEPOINT 37.183 TO MILEPOINT 38.086 | C |  | PM/NH | 2020 | 400000 | 320000 |  |  | 80000 | [5 empty] | 0
STIP | [9 empty] | HICKMAN | 1-1156 | CR 1011 | 0.055 | 0.25 | 0.305 | RELIABILITY | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER IC RR ON BALTIMORE RD (CR 1011) 0.3 MI NW OF HICKMAN/GRAVES CO LINE 053C00003N | D |  | BR/STP | 2019 | 266000 | 164920 |  |  | 101080 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030232 | HICKMAN | 1-1156 | CR 1011 | 0.055 | 0.25 | 0.305 | RELIABILITY | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER IC RR ON BALTIMORE RD (CR 1011) 0.3 MI NW OF HICKMAN/GRAVES CO LINE 053C00003N | C |  | BR/STP | 2020 | 1613500 | 1000370 |  |  | 613130 |  |  | OBLIGATED | 200000 | 1669280 | 1869280 | 2020 | 1ST QUARTER
STIP | [9 empty] | HICKMAN | 1-10011 | KY 2206 |  | 0.653 | 0.671 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 2206 BRIDGE OVER CANE CR FK -OBION CRK. (053B00090N) | D |  | BR/STP | 2019 | 210000 | 130200 |  |  | 79800 | [5 empty] | 0
STIP | [7 empty] | STP | 9030003 | HICKMAN | 1-10011 | KY 2206 |  | 0.653 | 0.671 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 2206 BRIDGE OVER CANE CR FK -OBION CRK. (053B00090N) | C |  | BR/STP | 2020 | 875000 | 542500 |  |  | 332500 |  |  | OBLIGATED | 1017750 |  | 1017750 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.291 | 2021-04-23 | ADD C PHASE TO STIP; NEW |  |  | HICKMAN | 1-10063 | KY 80 |  | 2.906 | 2.918 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 80 BRIDGE OVER BOWLES CREEK. 053B00044N | C |  | STP | 2021 | 667000 | 667000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.229 | 2020-09-14 | ADD C PHASE TO STIP; PARENT NO. 99-224.14; NEW |  |  | HICKMAN | 1-20033 | US 45 |  | 0 | 3.37 | ASSET MANAGEMENT | AM-PAVEMENT(PRI)(P) | RESURFACING OF US 45 (MP 0.00-3.37) IN HICKMAN COUNTY, KY. | C |  | STP | 2020 | 589076 | 589076 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | HOPKINS | 2-137.02 | US 41A | 3.6 | 0 | 3.426 | RELIABILITY | MAJOR WIDENING(O) | US 41A PHASE II DESIGN AND RIGHT-OF-WAY. (2005HPP-KY135)(SEE 2-137.01 FOR "STP" COMPONENT) | C |  | HPP | 2019 | 2879680 | 2879680 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.3 | 2021-05-28 | ADD D PHASE TO STIP; NEW |  |  | HOPKINS | 2-804 |  |  |  |  | NEW ROUTES | NEW ROUTE(O) | CONSTRUCT CENTER ST CONNECTOR RD BEGIN AT CENTER ST/PROCEED TO CSX RR, SECT.1, 5,173 LI. FT.PROCEED THRU PORTION OF SECT. 2,END AT I-SECTION OF CONNECTOR RD BEING CONSTRUCTED WITH ISLAND FD DR.ALL DEEDED TO CITY-MADISONVILLE, ALL 100FT WIDE.(14CCR)(18CCN) (2020CCR) | D |  | STP | 2021 | 450000 | 450000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | HOPKINS | 2-1072 | KY 260 | 0.1 | 2.09 | 2.19 | RELIABILITY | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON KY-260 (MP 2.14) OVER OTTER CREEK; .20 MI EAST OF PENNYRILE PARKWAY; 054B00022N (14CCR) | C |  | BR/STP | 2019 | 1085000 | 672700 |  |  | 412300 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.279 | 2021-03-05 | ADD C PHASE TO STIP; NEW |  |  | HOPKINS | 2-4310 | KY 109 |  | 6 | 6.08 | SAFETY | SAF-GUARDRAIL(P) | INSTALL GUARDRAIL ON KY-109 IN HOPKINS COUNTY | C |  | STP | 2021 | 25000 | 25000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.279 | 2021-03-05 | ADD C PHASE TO STIP; NEW |  |  | HOPKINS | 2-4320 | US 62 |  | 7.99 | 8.2 | SAFETY | SAF-GUARDRAIL(P) | INSTALL GUARDRAIL ON US-62 IN HOPKINS COUNTY | C |  | STP | 2021 | 53000 | 53000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.279 | 2021-03-05 | ADD C PHASE TO STIP; NEW |  |  | HOPKINS | 2-4322 | KY 109 |  | 5.4 | 5.6 | SAFETY | SAF-GUARDRAIL(P) | INSTALL GUARDRAIL ON KY-109 IN HOPKINS COUNTY | C |  | STP | 2021 | 25000 | 25000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | HOPKINS | 2-8305 | US 41 | 0.6 | 16.989 | 17.548 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE NORTH MAIN STREET FROM HOSPITAL DRIVE TO KY-281. (06CCN)(12CCR)(18CCR) | D |  | STP | 2021 | 900000 | 720000 |  |  | 180000 | [5 empty] | 0
STIP | [9 empty] | HOPKINS | 2-8305 | US 41 | 0.6 | 16.989 | 17.548 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE NORTH MAIN STREET FROM HOSPITAL DRIVE TO KY-281. (06CCN)(12CCR)(18CCR) | R |  | STP | 2021 | 1180000 | 944000 |  |  | 236000 | [5 empty] | 0
STIP | [9 empty] | HOPKINS | 2-8305 | US 41 | 0.6 | 16.989 | 17.548 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE NORTH MAIN STREET FROM HOSPITAL DRIVE TO KY-281. (06CCN)(12CCR)(18CCR) | U |  | STP | 2022 | 1440000 | 1152000 |  |  | 288000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.279 | 2021-03-05 | ADD C PHASE TO STIP; NEW |  |  | HOPKINS | 2-8501 | US 62 |  | 0.829 | 1.35 | RELIABILITY | MINOR WIDENING(O) | US-62; THREE LANES FROM BOARD OF EDUCATION TO CITY PARK IN DAWSON SPRINGS. (08CCN)(10CCR)(12CCR)(16CCN) (2020CCR) | C |  | STP | 2021 | 1358500 | 1358500 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | HOPKINS | 2-10005 | KY 70 |  | 13.46 | 13.474 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-70 BRIDGE OVER SUGAR CREEK. (054B00088N) | D |  | BR/STP | 2019 | 210000 | 130200 |  |  | 79800 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030058 | HOPKINS | 2-10005 | KY 70 |  | 13.46 | 13.474 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-70 BRIDGE OVER SUGAR CREEK. (054B00088N) | C |  | BR/STP | 2020 | 1242500 | 770350 |  |  | 472150 |  |  | OBLIGATED |  | 672360 | 672360 | 2019 | 2ND QUARTER
STIP | [9 empty] | HOPKINS | 2-10006 | KY 70 |  | 14.248 | 14.272 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-70 BRIDGE OVER CLEAR CREEK. (054B00182N) | D |  | BR/STP | 2019 | 210000 | 130200 |  |  | 79800 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030059 | HOPKINS | 2-10006 | KY 70 |  | 14.248 | 14.272 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-70 BRIDGE OVER CLEAR CREEK. (054B00182N) | C |  | BR/STP | 2020 | 1295000 | 802900 |  |  | 492100 |  |  | OBLIGATED |  | 942115 | 942115 | 2019 | 2ND QUARTER
STIP | [9 empty] | HOPKINS | 2-10024 | KY 138 |  | 8.457 | 8.493 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 138 BRIDGE OVER POND RIVER. (054B00009N) | D |  | BR/STP | 2019 | 35000 | 21700 |  |  | 13300 | [5 empty] | 0
STIP | [9 empty] | HOPKINS | 2-10024 | KY 138 |  | 8.457 | 8.493 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 138 BRIDGE OVER POND RIVER. (054B00009N) | C |  | BR/STP | 2020 | 245000 | 151900 |  |  | 93100 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.03 | 2019-03-01 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD |  |  | HOPKINS | 2-10024 | KY 138 |  | 8.457 | 8.493 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 138 BRIDGE OVER POND RIVER. (054B00009N) | C |  | STP | 2019 | 346362 | 346362 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | HOPKINS | 2-10025 | KY 109 |  | 0.092 | 0.154 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 109 BRIDGE OVER TRADEWATER RIVER. (054B00079N) | D |  | BR/STP | 2019 | 35000 | 21700 |  |  | 13300 | [5 empty] | 0
STIP | [9 empty] | HOPKINS | 2-10025 | KY 109 |  | 0.092 | 0.154 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 109 BRIDGE OVER TRADEWATER RIVER. (054B00079N) | C |  | BR/STP | 2020 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.075 | 2019-05-28 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030151 | HOPKINS | 2-10025 | KY 109 |  | 0.092 | 0.154 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 109 BRIDGE OVER TRADEWATER RIVER. (054B00079N) | C |  | STP | 2020 | 1462643 | 1462643 |  |  | 0 |  |  | OBLIGATED |  | 1856920 | 1856920 | 2019 | 4TH QUARTER
STIP | [9 empty] | HOPKINS | 2-20025 | EB 9004 |  | 32.825 | 34.256 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF EDWARD T. BREATHITT PENNYRILE PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 32.825 TO MILEPOINT 34.256 | D |  | PM/NH | 2021 | 170000 | 136000 |  |  | 34000 | [5 empty] | 0
STIP | [9 empty] | HOPKINS | 2-20025 | EB 9004 |  | 32.825 | 34.256 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF EDWARD T. BREATHITT PENNYRILE PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 32.825 TO MILEPOINT 34.256 | C |  | PM/NH | 2021 | 1700000 | 1360000 |  |  | 340000 | [5 empty] | 0
STIP | [9 empty] | HOPKINS | 2-20033 | I 69 |  | 93.724 | 95.604 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-069 BOTH DIRECTION(S) FROM MILEPOINT 93.724 TO MILEPOINT 95.604 | D |  | PM/NH | 2022 | 150000 | 120000 |  |  | 30000 | [5 empty] | 0
STIP | [9 empty] | HOPKINS | 2-20033 | I 69 |  | 93.724 | 95.604 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-069 BOTH DIRECTION(S) FROM MILEPOINT 93.724 TO MILEPOINT 95.604 | C |  | PM/NH | 2022 | 1500000 | 1200000 |  |  | 300000 | [5 empty] | 0
STIP | [9 empty] | HOPKINS | 2-20034 | I 69 |  | 95.604 | 105.046 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-069 BOTH DIRECTION(S) FROM MILEPOINT 95.604 TO MILEPOINT 105.046 | D |  | PM/NH | 2021 | 760000 | 608000 |  |  | 152000 | [5 empty] | 0
STIP | [9 empty] | HOPKINS | 2-20034 | I 69 |  | 95.604 | 105.046 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-069 BOTH DIRECTION(S) FROM MILEPOINT 95.604 TO MILEPOINT 105.046 | C |  | PM/NH | 2021 | 7600000 | 6080000 |  |  | 1520000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.3 | 2021-05-28 | ADD C PHASE TO STIP; NEW |  |  | HOPKINS | 2-20035 | WK 9001 |  | 42.807 | 43.424 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF WENDELL H. FORD WESTERN KY PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 42.807 TO MILEPOINT 43.424 | C |  | NHPP | 2021 | 550000 | 550000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.229 | 2020-09-14 | ADD C PHASE TO STIP; PARENT NO. 99-224.14; NEW |  |  | HOPKINS | 2-20052 | KY 109 US 41A US 62 |  | 2.069 9.690 10.981 | 10.990 13.278 14.940 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | RESURFACING OF KY 109 (MP 2.069-10.990), US 41A (MP 9.690-13.278) AND US 62 (MP 10.981-14.940) IN HOPKINS COUNTY, KY. | C |  | STP | 2020 | 1728344 | 1728344 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.279 | 2021-03-05 | ADD C PHASE TO STIP; PARENT NO. 99-224.14; NEW |  |  | HOPKINS | 2-20059 | KY 336 |  | 2.32 | 3.34 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | Resurface KY 336 from MP 2.32 to MP 3.34 in Hopkins County, KY. | C |  | STP | 2021 | 93270 | 93270 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | JACKSON | 11-278.3 | KY 30 | 8.396 | 9.121 | 17.517 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE KY-30 FROM US-421 TO THE OWSLEY COUNTY LINE. (14CCR)(SEE 10-279.60 FOR PE & ENVIR)(16CCR)(TO BE LET WITH 10-279.61) | C |  | STP | 2019 | 18500000 | 18500000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.111 | 2019-08-02 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 4211051 | JACKSON | 11-9017 | US 421 |  | 22.127 | 29.574 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON US 421 FROM MP 22.127 TO MP 29.574 IN JACKSON COUNTY. (2018BOP) | D |  | SAF | 2019 | 350000 | 350000 |  |  | 0 |  |  | OBLIGATED |  | 350000 | 350000 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.175 | 2020-04-09 | ADD D PHASE TO STIP; PARENT NO. 99-911.09; NEW |  |  | JACKSON | 11-9019 | US 421 |  | 3.6 | 7.9 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON US 421 FROM MP 3.600 TO MP 7.900 IN JACKSON COUNTY, KY. (2018BOP) | D |  | SAF | 2020 | 275000 | 275000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | JACKSON | 11-10041 | KY 89 |  | 0 | 0.01 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 89 BRIDGE OVER HORSE LICK CREEK. (055B00028N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [9 empty] | JACKSON | 11-10041 | KY 89 |  | 0 | 0.01 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 89 BRIDGE OVER HORSE LICK CREEK. (055B00028N) | C |  | BR/STP | 2020 | 1820000 | 1128400 |  |  | 691600 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.306 | 2021-06-16 | ADD D PHASE TO STIP; NEW |  |  | JACKSON | 11-80104 | US 421 |  | 26.7 | 27.312 |  | RECONSTRUCTION(O) | ADDRESS SUBSTARNDARD HORIZONTAL AND VERTICAL ALIGNMENT OF US 421 IN THE CLOVER BOTTOM AREA NEAR THE STONE QUARRY. (2020CCN) | D |  | SPP | 2021 | 362100 | 100 |  |  | 362000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.306 | 2021-06-16 | ADD D PHASE TO STIP; NEW |  |  | JACKSON | 11-80105 | US 421 |  | 11.6 | 12.6 |  | SAFETY (P) | ADDRESS SAFETY ISSUES WITH VERTICAL AND HORIZONTAL ALIGNMENT ON US 421 FROM MP 11.6 EAST OF PILGRIMS REST RD TO MP 12.6 (2020CCN) | D |  | SPP | 2021 | 949100 | 100 |  |  | 949000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.306 | 2021-06-16 | ADD D PHASE TO STIP; NEW |  |  | JACKSON | 11-80106 | US 421 |  | 1.5 | 1.97 |  | RIDESHARE(P) | ADDRESS SAFETY AND HORIZONTAL ALIGNMENT OF THE CURVE ON US 421 WITH ITS INTERSECTION AT KY 3443 (2020CCN) | D |  | SPP | 2021 | 365100 | 100 |  |  | 365000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.314 | 2021-06-25 | ADD C PHASE TO STIP; NEW |  |  | JACKSON | KY FLAP14 | CR 1931 CR 1049 CR 1048 CR 1282 |  |  |  | RELIABILITY | RESURFACING(P) | RESURFACING OF TREE TOWER ROAD (CR 1931); CALVARY CHURCH ROAD (CR 1049); WILD DOG TRAIL (CR 1048); AND LOW GAP ROAD (CR 1282). | C |  | FLAP | 2021 | 205000 | 164000 |  |  |  | 41000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.111 | 2019-08-02 | OKI MPO AREA TIP FY 20-23, GROUPED PROJECTS - CHAPTER 7, PG 7-5; KIPDA MPO AREA TIP FY 18-21, GROUPED PROJECTS - PG 6; ADD PROJECT TO STIP; NEW |  |  | BOONE JEFFERSON |  | I-64 I-265 | [5 empty] | RETROFIT OF ITS DYNAMIC MESSAGE SIGNS ON VARIOUS INTERSTATE ROUTES IN DISTRICT 5 & 6. | C |  | NH | 2019 | 320000 | 320000 | [8 empty] | 0
|  |  |  | AMENDMENT | 2018.006 | 2020-04-09 | TIP REFERENCE FY 20-25; RESOLUTION DATED 2/27/20. NEW |  |  | JEFFERSON
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.141 | 2019-10-18 | TIP FY 18-21, ADMIN MOD#37; UPDATE PROJECT NAME TO "RETROFIT OF DYNAMIC MESSAGING SIGNS ON I-64 AND I-265" AND UPDATE PROJECT DESCRIPTION; MOD |  |  | JEFFERSON |  | I-64 I-265 | [5 empty] | RETROFIT NEW DYNAMIC MESSAGING SYSTEMS (DMS) IN THE PLACE OF THE EXISTING DMS IDENTIFIED AT THE FOLLOWING LOCATIONS IN JEFFERSON COUNTY: I-64@MP 13.4; I-64@MP 24.1; I-264@MP 3.1; AND I-265@MP 4.0. | C |  | NH | 2019 | 320000 | 320000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; ADD P PHASE TO STIP; NEW |  |  | JEFFERSON | TBD | US 42 | [5 empty] | PLANNING STUDY TO IDENTIFY POTENTIAL IMPROVEMENTS ON US 42 BETWEEN THE GENE SYNDER FREEWAY AND KY 3222 (ROSE ISLAND ROAD). | P |  | STP | 2021 | 375000 | 300000 |  |  | 75000 | [5 empty] | 0
STIP | YES | [8 empty] | JEFFERSON | 5-48.1 | I 71 | 2.5 | 0 | 2.5 | RELIABILITY | RECONSTRUCTION(O) | ADDITION OF NB AND SB AUXILIARY LANES ON I-71 NEAR KENNEDY, INCLUDING OPERATIONAL IMPROVEMENTS TO THE ZORN INTERCHANGE. (2004BOPC) | D |  | NH | 2019 | 800000 | 800000 |  |  | 0 | [5 empty] | 0
STIP | YES | [8 empty] | JEFFERSON | 5-48.1 | I 71 | 2.5 | 0 | 2.5 | RELIABILITY | RECONSTRUCTION(O) | ADDITION OF NB AND SB AUXILIARY LANES ON I-71 NEAR KENNEDY, INCLUDING OPERATIONAL IMPROVEMENTS TO THE ZORN INTERCHANGE. (2004BOPC) | R |  | NH | 2020 | 1500000 | 1500000 |  |  | 0 | [5 empty] | 0
STIP | YES | [8 empty] | JEFFERSON | 5-48.1 | I 71 | 2.5 | 0 | 2.5 | RELIABILITY | RECONSTRUCTION(O) | ADDITION OF NB AND SB AUXILIARY LANES ON I-71 NEAR KENNEDY, INCLUDING OPERATIONAL IMPROVEMENTS TO THE ZORN INTERCHANGE. (2004BOPC) | U |  | NH | 2020 | 1000000 | 1000000 |  |  | 0 | [5 empty] | 0
STIP | YES | [5 empty] | NOT IN TIP |  |  | JEFFERSON | 5-48.1 | I 71 | 2.5 | 0 | 2.5 | RELIABILITY | RECONSTRUCTION(O) | ADDITION OF NB AND SB AUXILIARY LANES ON I-71 NEAR KENNEDY, INCLUDING OPERATIONAL IMPROVEMENTS TO THE ZORN INTERCHANGE. (2004BOPC) | C |  | NH | 2022 | 12380000 | 9904000 |  |  | 2476000 | [5 empty] | 0
TIP | [6 empty] | 5-48.11 in TIP but not in STIP |  |  | Jefferson | 5-48.10 5-48.11 | I- 71 | [5 empty] | Addition of north and southbound auxiliary lanes on I-71 near the Kennedy Interchange, including operational improvements to the Zorn Avenue Interchange. (2004BOPC) From MP 0 to MP 2.5. | U |  | NHS | 2020 | 1000000 | 1000000 | [8 empty] | 0
TIP | [6 empty] | 5-48.11 in TIP but not in STIP |  |  | Jefferson | 5-48.10 5-48.11 | I- 71 | [5 empty] | Addition of north and southbound auxiliary lanes on I-71 near the Kennedy Interchange, including operational improvements to the Zorn Avenue Interchange. (2004BOPC) From MP 0 to MP 2.5. | R |  | NHS | 2020 | 1500000 | 1500000 | [8 empty] | 0
TIP | [6 empty] | 5-48.11 in TIP but not in STIP |  |  | Jefferson | 5-48.10 5-48.11 | I- 71 | [5 empty] | Addition of north and southbound auxiliary lanes on I-71 near the Kennedy Interchange, including operational improvements to the Zorn Avenue Interchange. (2004BOPC) From MP 0 to MP 2.5. | D |  | NHS | 2019 | 800000 | 800000 | [8 empty] | 0
STIP | YES | [8 empty] | JEFFERSON | 5-64 | I 64 | 0.3 | 0 | 0.316 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES ON I-64 SHERMAN MINTON BRIDGE OVER THE OHIO RIVER. (JOINT PROJECT WITH INDIANA)(056B00279N)(BSBP) | D |  | BR/NH | 2019 | 2000000 | 1240000 |  |  | 760000 | [5 empty] | 0
STIP | YES | [8 empty] | JEFFERSON | 5-64 | I 64 | 0.3 | 0 | 0.316 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES ON I-64 SHERMAN MINTON BRIDGE OVER THE OHIO RIVER. (JOINT PROJECT WITH INDIANA)(056B00279N)(BSBP) | C |  | BR/NH | 2020 | 5000000 | 3100000 |  |  | 1900000 | [5 empty] | 0
TIP | [6 empty] | NOT IN STIP |  |  | Jefferson | 5-64 | I- 64 | [5 empty] | Address deficiencies on I-64 Sherman Minton Bridge over the Ohio River. (Joint project with Indiana)(056B00279N) (BSBP) From MP 0 to MP 0.316. | C |  | NHPP | 2021 | 3600000 | 3600000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25; ADMIN MOD#9; UPDATE FUND AMOUNTS; MOD |  |  | Jefferson | 5-64 | I- 64 | 0.3 | 0 | 0.316 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES ON I-64 SHERMAN MINTON BRIDGE OVER THE OHIO RIVER. (JOINT PROJECT WITH INDIANA)(056B00279N)(BSBP) | C |  | NHPP | 2021 | 14000000 | 4000000 |  |  |  | 10000000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25; ADMIN MOD#9; ADD FY 2022 FOR C PHASE; MOD |  |  | Jefferson | 5-64 | I- 64 | 0.3 | 0 | 0.316 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES ON I-64 SHERMAN MINTON BRIDGE OVER THE OHIO RIVER. (JOINT PROJECT WITH INDIANA)(056B00279N)(BSBP) | C |  | NHPP | 2022 | 10000000 | 8000000 |  |  |  | 2000000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25; ADMIN MOD#9; ADD FY 2023 FOR C PHASE; MOD |  |  | Jefferson | 5-64 | I- 64 | 0.3 | 0 | 0.316 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES ON I-64 SHERMAN MINTON BRIDGE OVER THE OHIO RIVER. (JOINT PROJECT WITH INDIANA)(056B00279N)(BSBP) | C |  | NHPP | 2023 | 15000000 | 12000000 |  |  |  | 3000000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25; ADMIN MOD#9; ADD FY 2024 FOR C PHASE; MOD |  |  | Jefferson | 5-64 | I- 64 | 0.3 | 0 | 0.316 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES ON I-64 SHERMAN MINTON BRIDGE OVER THE OHIO RIVER. (JOINT PROJECT WITH INDIANA)(056B00279N)(BSBP) | C |  | NHPP | 2024 | 16000000 | 12800000 |  |  |  | 3200000 |  |  |  |  | 0
TIP | [6 empty] | NOT IN STIP |  |  | Jefferson | 5-64 | I- 64 | [5 empty] | Address deficiencies on I-64 Sherman Minton Bridge over the Ohio River. (Joint project with Indiana)(056B00279N) (BSBP) From MP 0 to MP 0.316. | C |  | STP-ST | 2021 | 6400000 | 2600000 | [8 empty] | 0
STIP | YES | [5 empty] | NOT IN TIP |  |  | JEFFERSON | 5-64.01 | I 64 |  | 0 | 0.316 | ASSET MANAGEMENT | PREFINANCD CONVRSN(O) | ADDRESS DEFICIENCIES ON I-64 SHERMAN MINTON BRIDGE OVER THE OHIO RIVER. (JOINT PROJECT WITH INDIANA)(056B00279N) | C |  | BR/NH | 2021 | 10000000 | 6200000 |  |  | 3800000 | [5 empty] | 0
STIP | YES | [5 empty] | NOT IN TIP |  |  | JEFFERSON | 5-64.02 | I 64 |  | 0 | 0.316 | ASSET MANAGEMENT | PREFINANCD CONVRSN(O) | ADDRESS DEFICIENCIES ON I-64 SHERMAN MINTON BRIDGE OVER THE OHIO RIVER. (JOINT PROJECT WITH INDIANA)(056B00279N) | C |  | BR/NH | 2022 | 10000000 | 6200000 |  |  | 3800000 | [5 empty] | 0
TIP | [9 empty] | JEFFERSON | 5-91.02 | CS 1001B | 1.5 | 1.6 | 2.925 | RELIABILITY | MAJOR WIDENING(O) | Widen River Road from 2 to 4 lanes from east of Beargrass Creek near Pope Avenue to Zorn Avenue. To include bike lanes and shared use path. Project length is 1.3 miles. | C |  | SLO | 2020 | 11500000 | 11500000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; UPDATE PROJECT DESCRIPTION & INCREASE FUND AMOUNTS; MOD |  |  | JEFFERSON | 5-91.02 | CS 1001B | 1.5 | 1.6 | 2.925 | RELIABILITY | MAJOR WIDENING(O) | WIDEN RIVER ROAD FROM 2 TO 4 LANES FROM EAST OF BEARGRASS CREEK NEAR POPE AVENUE TO ZORN AVENUE. TO INCLUDE BIKE LANES AND SHARED USE PATH. PROJECT LENGTH IS 1.5 MILES. | C |  | STP | 2020 | 17270000 | 17270000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; UPDATE FISCAL YEAR & FUND AMOUNTS; MOD |  |  | JEFFERSON | 5-91.02 | CS 1001B | 1.5 | 1.6 | 2.925 | RELIABILITY | MAJOR WIDENING(O) | WIDEN RIVER ROAD FROM 2 TO 4 LANES FROM EAST OF BEARGRASS CREEK NEAR POPE AVENUE TO ZORN AVENUE. TO INCLUDE BIKE LANES AND SHARED USE PATH. PROJECT LENGTH IS 1.5 MILES. | C |  | STP | 2022 | 21587500 | 17270000 |  |  | 4317500 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.309 | 2021-06-10 | TIP FY 20-25, ADMIN MOD#17; UPDATE FUND AMOUNTS; MOD |  |  | JEFFERSON | 5-91.02 | CS 1001B | 1.5 | 1.6 | 2.925 | RELIABILITY | MAJOR WIDENING(O) | WIDEN RIVER ROAD FROM 2 TO 4 LANES FROM EAST OF BEARGRASS CREEK NEAR POPE AVENUE TO ZORN AVENUE. TO INCLUDE BIKE LANES AND SHARED USE PATH. PROJECT LENGTH IS 1.5 MILES. | C |  | STP | 2022 | 12066488 | 9942715 |  |  | 2123773 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.309 | 2021-06-10 | TIP FY 20-25, ADMIN MOD#17; ADD CRRSAA FUNDS TO THE C PHASE; MOD |  |  | JEFFERSON | 5-91.02 | CS 1001B | 1.5 | 1.6 | 2.925 | RELIABILITY | MAJOR WIDENING(O) | WIDEN RIVER ROAD FROM 2 TO 4 LANES FROM EAST OF BEARGRASS CREEK NEAR POPE AVENUE TO ZORN AVENUE. TO INCLUDE BIKE LANES AND SHARED USE PATH. PROJECT LENGTH IS 1.5 MILES. | C |  |  | 2022 | 5981134 | 5981134 | [8 empty] | 0
TIP | [6 empty] | NOT IN STIP |  |  | JEFFERSON | 5-91.02 | CS 1001B | 1.5 | 1.6 | 2.925 | RELIABILITY | MAJOR WIDENING(O) | Widen River Road from 2 to 4 lanes from east of Beargrass Creek near Pope Avenue to Zorn Avenue. To include bike lanes and shared use path. Project length is 1.3 miles. | D |  | SLO | 2018 | 350000 | 350000 | [8 empty] | 0
TIP | [9 empty] | JEFFERSON | 5-91.08 | CS 1001B |  |  |  | RELIABILITY | NEW ROUTE(O) | Extend River Road west from 7th Street to Northwestern Parkway. The project is feasible using a low design speed criteria and a two-lane section. | D |  | SLO | 2019 | 673750 | 550000 |  |  |  | 123750 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; UPDATE FISCAL YEAR FROM 2019 TO 2020; MOD |  |  | JEFFERSON | 5-91.08 | CS 1001B |  |  |  | RELIABILITY | NEW ROUTE(O) | Extend River Road west from 7th Street to Northwestern Parkway. The project is feasible using a low design speed criteria and a two-lane section. | D |  | STP | 2020 | 673750 | 550000 |  |  |  | 123750 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; THIS PROJECT IS NOW UNDER ITEM # 5-512.00; MOD |  |  | JEFFERSON | 5-91.08 | CS 1001B |  |  |  | RELIABILITY | NEW ROUTE(O) | Extend River Road west from 7th Street to Northwestern Parkway. The project is feasible using a low design speed criteria and a two-lane section. | D
TIP | [9 empty] | JEFFERSON | 5-91.08 | CS 1001B |  |  |  | RELIABILITY | NEW ROUTE(O) | Extend River Road west from 7th Street to Northwestern Parkway. The project is feasible using a low design speed criteria and a two-lane section. | R |  | SLO | 2019 | 661500 | 540000 |  |  |  | 121500 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; UPDATE FISCAL YEAR FROM 2019 TO 2020; MOD |  |  | JEFFERSON | 5-91.08 | CS 1001B |  |  |  | RELIABILITY | NEW ROUTE(O) | Extend River Road west from 7th Street to Northwestern Parkway. The project is feasible using a low design speed criteria and a two-lane section. | R |  | STP | 2020 | 661500 | 540000 |  |  |  | 121500 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; THIS PROJECT IS NOW UNDER ITEM # 5-512.00; MOD |  |  | JEFFERSON | 5-91.08 | CS 1001B |  |  |  | RELIABILITY | NEW ROUTE(O) | Extend River Road west from 7th Street to Northwestern Parkway. The project is feasible using a low design speed criteria and a two-lane section. | R
TIP | [9 empty] | JEFFERSON | 5-91.08 | CS 1001B |  |  |  | RELIABILITY | NEW ROUTE(O) | Extend River Road west from 7th Street to Northwestern Parkway. The project is feasible using a low design speed criteria and a two-lane section. | U |  | SLO | 2020 | 661500 | 540000 |  |  |  | 121500 |  |  |  |  | 0
STIP | [9 empty] | JEFFERSON | 5-136 | I 265 |  |  |  | ASSET MANAGEMENT | AM-BRG PAINTING(P) | CLEAN AND PAINT ALL STEEL BRIDGES AND STEEL BEARINGS ON THE GENE SNYDER FREEWAY(10CCR)(SD) | C |  | BR/NH | 2021 | 3790000 | 2349800 |  |  | 1440200 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; UPDATE FUND AMOUNTS; MOD |  |  | JEFFERSON | 5-136 | I 265 |  |  |  | ASSET MANAGEMENT | AM-BRG PAINTING(P) | CLEAN AND PAINT ALL STEEL BRIDGES AND STEEL BEARINGS ON THE GENE SNYDER FREEWAY(10CCR)(SD) | C |  | BR/NH | 2021 | 6000000 | 4800000 |  |  | 1200000 | [5 empty] | 0
TIP | [6 empty] | Not in STIP |  |  | Jefferson | 5-159 | I-264 / I- 64 | [5 empty] | Widen ramp from westbound I-64 to westbound I-264 (Henry Watterson Expressway) from 1 to 2 lanes and other needed improvements to address the weave issues at merge on I-264. | C |  | NHS | 2018 | 9680000 | 9680000 | [8 empty] | 0
STIP | YES | [8 empty] | JEFFERSON | 5-247.1 | KY 1450 | 1.669 | 1.873 | 3.542 | RELIABILITY | MAJOR WIDENING(O) | WIDEN BLUE LICK ROAD FROM SNYDER FREEWAY NORTH TO KY-61 (LOU T.I.P.) (SECTION 2) (RU-04DEOB)(08CCR)(12CCR)(16CCR) | C |  | STP | 2020 | 4500000 | 4500000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; ADD C PHASE FOR FY 2022; MOD |  |  | JEFFERSON | 5-247.1 | KY 1450 | 1.669 | 1.873 | 3.542 | RELIABILITY | MAJOR WIDENING(O) | WIDEN BLUE LICK ROAD FROM SNYDER FREEWAY NORTH TO KY-61 (LOU T.I.P.) (SECTION 2) (RU-04DEOB)(08CCR)(12CCR)(16CCR) | C |  | STP | 2022 | 5000000 | 4000000 |  |  | 1000000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; ADD C PHASE FOR FY 2023; MOD |  |  | JEFFERSON | 5-247.1 | KY 1450 | 1.669 | 1.873 | 3.542 | RELIABILITY | MAJOR WIDENING(O) | WIDEN BLUE LICK ROAD FROM SNYDER FREEWAY NORTH TO KY-61 (LOU T.I.P.) (SECTION 2) (RU-04DEOB)(08CCR)(12CCR)(16CCR) | C |  | STP | 2023 | 5500000 | 4400000 |  |  | 1100000 | [5 empty] | 0
STIP | YES | [8 empty] | JEFFERSON | 5-247.11 | KY 1450 | 1.669 | 1.873 | 3.542 | RELIABILITY | PREFINANCD CONVRSN(O) | WIDEN BLUE LICK ROAD FROM SNYDER FREEWAY NORTH TO KY-61 (LOU T.I.P.) (SECTION 2) (RU-04DEOB)(08CCR)(12CCR)(16CCR) | C |  | STP | 2021 | 6500000 | 5200000 |  |  | 1300000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.001 | 2018-12-06 | TIP FY 18-21; AMENDMENT#3; UPDATE FUND AMOUNTS; MOD |  |  | JEFFERSON | 5-247.11 | KY 1450 | 1.669 | 1.873 | 3.542 | RELIABILITY | PREFINANCD CONVRSN(O) | WIDEN BLUE LICK ROAD FROM SNYDER FREEWAY NORTH TO KY-61 (LOU T.I.P.) (SECTION 2) (RU-04DEOB)(08CCR)(12CCR)(16CCR) | C |  | STP | 2021 | 6500000 | 6500000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.194 | 2020-05-29 | TIP FY 20-25; ADMIN MOD#3; ADD PROJECT TO STIP; NEW |  |  | JEFFERSON | 5-264.11 | US 31E | [5 empty] | IMPROVE OPERATIONAL EFFICIENCY AND ACCESS ALONG US 31E SOUTH OF THE I-265 INTERCHANGE BY PROVIDING DUAL LEFT TURN LANES TO SOUTHBOUND US 31E AT THE CURRENTLY SIGNALIZED INTERSECTION WITH SOUTHPOINTE BOULEVARD (RELOCATED WINGFIELD ROAD). PEDESTRIAN HEADS, PEDESTALS AND CROSSWALKS WILL ALSO BE ADDED. THE DUAL LEFT TURN LANES WILL SERVE BATES ELEMENTARY SCHOOL AND THE NEW PROPOSED SOUTHPOINTE COMMONS DEVELOPMENT. | C |  | NH | 2020 | 785000 | 628000 |  |  |  | 157000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.282 | 2021-03-04 | TIP FY 20-25, ADMIN MOD#13; ADD PROJECT TO STIP; NEW |  |  | JEFFERSON | 5-323.01 | KY 1931 |  | 0.54 | 3.148 | RELIABILITY | MAJOR WIDENING(O) | WIDEN GREENWOOD ROAD FROM GREENBELT HWY TO DIXIE HWY (US-31W) (3-LANE IMPROVEMENT) FROM MP 0.54 TO MP 3.148. (98CCR)(R-04DEOB)(04CCR)(BOP2006P)(10CCR)(12CCR) (2020CCR) | C |  | STP | 2022 | 7340000 | 5872000 |  |  | 1468000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.282 | 2021-03-04 | TIP FY 20-25, ADMIN MOD#13; ADD PROJECT TO STIP; NEW |  |  | JEFFERSON | 5-323.01 | KY 1931 |  | 0.54 | 3.148 | RELIABILITY | MAJOR WIDENING(O) | WIDEN GREENWOOD ROAD FROM GREENBELT HWY TO DIXIE HWY (US-31W) (3-LANE IMPROVEMENT) FROM MP 0.54 TO MP 3.148. (98CCR)(R-04DEOB)(04CCR)(BOP2006P)(10CCR)(12CCR) (2020CCR) | C |  | STP | 2023 | 7340000 | 5872000 |  |  | 1468000 | [5 empty] | 0
TIP | [6 empty] | Not in STIP |  |  | Jefferson | 5-344.01 | KY 1747 | [5 empty] | Widen southbound Hurstbourne Lane to 3 lanes from Linn Station Road to Eden Avenue. | C |  | STP-ST | 2018 | 3000000 | 3000000 | [8 empty] | 0
STIP | [9 empty] | JEFFERSON | 5-353 | CR 1006C | 0.85 | 0.457 | 1.232 | RELIABILITY | MINOR WIDENING(O) | WIDEN ENGLISH STATION ROAD FROM 2 TO 3 LANES (3RD LANE WILL BE A CENTER TURN LANE) FROM AIKEN ROAD TO AVOCA ROAD.(FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | C |  | SLO | 2020 | 6408000 | 5126400 |  |  |  | 1281600 |  |  |  |  | 0
TIP | [6 empty] | TIP AND STIP AMOUNTS ARE DIFFERENT |  |  | JEFFERSON | 5-353 | CR 1006C | 0.85 | 0.457 | 1.232 | RELIABILITY | MINOR WIDENING(O) | WIDEN ENGLISH STATION ROAD FROM 2 TO 3 LANES (3RD LANE WILL BE A CENTER TURN LANE) FROM AIKEN ROAD TO AVOCA ROAD.(FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | C |  | SLO | 2020 | 6408000 | 6408000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; UDPATE FISCAL YEAR; MOD |  |  | JEFFERSON | 5-353 | CR 1006C | 0.85 | 0.457 | 1.232 | RELIABILITY | MINOR WIDENING(O) | WIDEN ENGLISH STATION ROAD FROM 2 TO 3 LANES (3RD LANE WILL BE A CENTER TURN LANE) FROM AIKEN ROAD TO AVOCA ROAD.(FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | C |  | STP | 2021 | 6408000 | 6408000 |  |  | 0 | [5 empty] | 0
STIP | YES | [5 empty] | NOT IN TIP |  |  | JEFFERSON | 5-371.1 | KY 22 | 0.357 | 1.432 | 1.789 | SAFETY | SAFETY(P) | RECONSTRUCT KY-22 AT SPRINGCREST DRIVE. (06CCN) (2004BOPC)(14CCR)(EMERGENCY CULVERT REPLACEMENT AWARDED UNDER 5-371.12) | C |  | STP | 2022 | 1740000 | 1392000 |  |  | 348000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; UPDATE FISCAL YEAR AND FUND AMOUNTS; MOD |  |  | JEFFERSON | 5-371.1 | KY 22 | 0.357 | 1.432 | 1.789 | SAFETY | SAFETY(P) | RECONSTRUCT KY-22 AT SPRINGCREST DRIVE. (06CCN) (2004BOPC)(14CCR)(EMERGENCY CULVERT REPLACEMENT AWARDED UNDER 5-371.12) | C |  | STP | 2023 | 2020000 | 1616000 |  |  | 404000 | [5 empty] | 0
STIP | YES | [6 empty] | STP | 8714014 | JEFFERSON | 5-371.13 | KY 22 | 0.4 | 2.537 | 2.937 | SAFETY | SAFETY(P) | RECONSTRUCT KY-22 AT GOOSE CREEK ROAD. (06CCN) (2004BOPC)(14CCR)(18CCR) | C |  | STP | 2020 | 1320000 | 1320000 |  |  | 0 |  |  | OBLIGATED | 100000 | 1942035 | 2042035 | 2019 | 4TH QUARTER
STIP | [6 empty] | not in TIP |  |  | JEFFERSON | 5-378.1 | I 65 | 0.1 | 0 | 0.155 | RELIABILITY | RECONSTRUCTION(O) | EXTEND AND RECONSTRUCT I-65 SB RAMP TO BROOK STREET AND FLOYD STREET. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | U |  | SLO | 2019 | 750000 | 600000 |  |  |  | 150000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.051 | 2019-04-18 | TIP FY 18-21, ADMIN MOD#28; UPDATE FUND AMOUNTS; MOD |  |  | JEFFERSON | 5-378.1 | I 65 | 0.1 | 0 | 0.155 | RELIABILITY | RECONSTRUCTION(O) | EXTEND AND RECONSTRUCT I-65 SB RAMP TO BROOK STREET AND FLOYD STREET. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | U |  | SLO | 2019 | 900000 | 750000 |  |  |  | 150000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; UPDATE FISCAL YEAR FROM 2019 TO 2020; MOD |  |  | JEFFERSON | 5-378.1 | I 65 | 0.1 | 0 | 0.155 | RELIABILITY | RECONSTRUCTION(O) | Extend and reconstruct I-65 southbound ramp to Brook Street and Floyd Street. The project will include the consideration of bicycle and pedestrian facilities. | U |  | STP | 2020 | 900000 | 750000 |  |  |  | 150000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.153 | 2019-12-13 | TIP FY 18-21, ADMIN MOD#39; UPDATE FUND AMOUNT; MOD |  |  | JEFFERSON | 5-378.1 | I 65 | 0.1 | 0 | 0.155 | RELIABILITY | RECONSTRUCTION(O) | Extend and reconstruct I-65 southbound ramp to Brook Street and Floyd Street. The project will include the consideration of bicycle and pedestrian facilities. | U |  | STP | 2020 | 480000 | 480000 |  |  |  | 0 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.186 | 2020-05-06 | TIP FY 20-25, ADMIN MOD#2; UPDATE FUND AMOUNT; MOD |  |  | JEFFERSON | 5-378.1 | I 65 | 0.1 | 0 | 0.155 | RELIABILITY | RECONSTRUCTION(O) | Extend and reconstruct I-65 southbound ramp to Brook Street and Floyd Street. The project will include the consideration of bicycle and pedestrian facilities. | U |  | STP | 2020 | 550000 | 440000 |  |  |  | 110000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; UPDATE FISCAL YEAR; MOD |  |  | JEFFERSON | 5-378.1 | I 65 | 0.1 | 0 | 0.155 | RELIABILITY | RECONSTRUCTION(O) | Extend and reconstruct I-65 southbound ramp to Brook Street and Floyd Street. The project will include the consideration of bicycle and pedestrian facilities. | U |  | STP | 2021 | 550000 | 440000 |  |  |  | 110000 |  |  |  |  | 0
TIP | [6 empty] | Not in STIP |  |  | Jefferson | 5-378.1 | I- 65 | [5 empty] | Extend and reconstruct I-65 southbound ramp to Brook Street and Floyd Street. The project will include the consideration of bicycle and pedestrian facilities. | D |  | SLO | 2019 | 750000 | 750000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; UPDATE FISCAL YEAR FROM 2019 TO 2020; MOD |  |  | Jefferson | 5-378.1 | I- 65 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | Extend and reconstruct I-65 southbound ramp to Brook Street and Floyd Street. The project will include the consideration of bicycle and pedestrian facilities. | D |  | STP | 2020 | 750000 | 750000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.153 | 2019-12-13 | TIP FY 18-21, ADMIN MOD#39; UPDATE FUND AMOUNT; MOD |  |  | Jefferson | 5-378.1 | I- 65 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | Extend and reconstruct I-65 southbound ramp to Brook Street and Floyd Street. The project will include the consideration of bicycle and pedestrian facilities. | D |  | STP | 2020 | 1020000 | 1020000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.186 | 2020-05-06 | TIP FY 20-25, ADMIN MOD#2; UPDATE FUND AMOUNT; MOD |  |  | JEFFERSON | 5-378.1 | I 65 | 0.1 | 0 | 0.155 | RELIABILITY | RECONSTRUCTION(O) | Extend and reconstruct I-65 southbound ramp to Brook Street and Floyd Street. The project will include the consideration of bicycle and pedestrian facilities. | D |  | STP | 2020 | 1005000 | 820000 |  |  |  | 185000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.114 | 2019-08-12 | TIP FY 18-21, AMENDMENT#6; CHANGE OPEN TO PUBLIC DATE FROM 2020 TO 2024; MOD |  |  | Jefferson | 5-378.1 | I- 65 | 0.1 | 0 | 0.155 | RELIABILITY | RECONSTRUCTION(O) | Extend and reconstruct I-65 southbound ramp to Brook Street and Floyd Street. The project will include the consideration of bicycle and pedestrian facilities. |  |  | SLO | 2024 | [10 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.186 | 2020-05-06 | TIP FY 20-25, ADMIN MOD#2; ADD C PHASE TO STIP; MOD |  |  | Jefferson | 5-378.1 | I- 65 | 0.1 | 0 | 0.155 | RELIABILITY | RECONSTRUCTION(O) | Extend and reconstruct I-65 southbound ramp to Brook Street and Floyd Street. The project will include the consideration of bicycle and pedestrian facilities. | C |  | STP | 2025 | 10300000 | 8240000 |  |  |  | 2060000 |  |  |  |  | 0
STIP | [9 empty] | JEFFERSON | 5-404.01 |  | 2.7 |  |  | RELIABILITY | NEW ROUTE(O) | PHASE 3.EXTEND AND CONSTRUCT 2 LANE ROADWAY WITH CONTINUOUS CENTER-TURN LANE FROM KY 864 (BEULAH CHURCH RD) TO US 31E (BARDSTOWN RD) AT BARDSTOWN FALLS RD. PROJECT WILL INCORPORATE SIDEWALKS AND 10' PAVED SHOULDERS. | R |  | SLO | 2019 | 3200000 | 2560000 |  |  |  | 640000 |  |  |  |  | 0
TIP | [6 empty] | TIP AND STIP AMOUNTS ARE DIFFERENT | STPM | 9061018 | JEFFERSON | 5-404.01 |  | 2.7 |  |  | RELIABILITY | NEW ROUTE(O) | Phase 3: Extend and construct 2 lane roadway with a continuous center-turn lane from KY 864 (Beulah Church Road) to US 31E (Bardstown Road) at Bardstown Falls Road. Project will include consideration of bicycle and pedestrian facilities. | R |  | SLO | 2019 | 3920000 | 3200000 |  |  |  | 720000 |  | OBLIGATED |  | 2947200 | 2947200 | 2019 | 4TH QUARTER | LOUISVILLE METRO
STIP | [9 empty] | JEFFERSON | 5-404.01 |  | 2.7 |  |  | RELIABILITY | NEW ROUTE(O) | PHASE 3.EXTEND AND CONSTRUCT 2 LANE ROADWAY WITH CONTINUOUS CENTER-TURN LANE FROM KY 864 (BEULAH CHURCH RD) TO US 31E (BARDSTOWN RD) AT BARDSTOWN FALLS RD. PROJECT WILL INCORPORATE SIDEWALKS AND 10' PAVED SHOULDERS. | U |  | SLO | 2019 | 1500000 | 1200000 |  |  |  | 300000 |  |  |  |  | 0
TIP | [6 empty] | TIP AND STIP AMOUNTS ARE DIFFERENT |  |  | JEFFERSON | 5-404.01 |  | 2.7 |  |  | RELIABILITY | NEW ROUTE(O) | Phase 3: Extend and construct 2 lane roadway with a continuous center-turn lane from KY 864 (Beulah Church Road) to US 31E (Bardstown Road) at Bardstown Falls Road. Project will include consideration of bicycle and pedestrian facilities. | U |  | SLO | 2019 | 1837500 | 1500000 |  |  |  | 337500 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; UPDATE FISCAL YEAR; MOD |  |  | JEFFERSON | 5-404.01 |  | 2.7 |  |  | RELIABILITY | NEW ROUTE(O) | Phase 3: Extend and construct 2 lane roadway with a continuous center-turn lane from KY 864 (Beulah Church Road) to US 31E (Bardstown Road) at Bardstown Falls Road. Project will include consideration of bicycle and pedestrian facilities. | U |  | SLO | 2021 | 1837500 | 1500000 |  |  |  | 337500 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; ADD C PHASE TO STIP; NEW |  |  | JEFFERSON | 5-404.01 |  | 2.7 |  |  | RELIABILITY | NEW ROUTE(O) | Phase 3: Extend and construct 2 lane roadway with a continuous center-turn lane from KY 864 (Beulah Church Road) to US 31E (Bardstown Road) at Bardstown Falls Road. Project will include consideration of bicycle and pedestrian facilities. | C |  | SLO | 2023 | 20000000 | 16000000 |  |  | 4000000 | [5 empty] | 0
TIP | [6 empty] | Not in STIP | STPM | 8801008 | Jefferson | 5-413 | Broadway & 18th Street | [5 empty] | Align intersection of Broadway and 18th Street by moving the south leg of 18th Street to the east. | C |  | SLO | 2018 | 1250000 | 1000000 |  |  |  | 250000 |  | OBLIGATED | 37112 |  | 37112 | 2019 | 3RD QUARTER
STIP | [9 empty] | JEFFERSON | 5-439.05 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | REHABILITATION AND CONSTRUCTION OF VARIOUS SIDEWALK PROJECTS IN LOUISVILLE METRO. (2006BOPC) (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | C |  | SLO | 2019 | 100000 | 80000 |  |  |  | 20000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.031 | 2019-03-01 | TIP FY 18-21; ADMIN MOD#21 (ORIGINALLY ADDED TO STIP FY 17-20 ON STIP MOD 2016.225) UPDATE FISCAL YEAR & FUND AMOUNT; MOD |  |  | JEFFERSON | 5-439.05 | Various Sidewalk Projects in Louisville Metro |  |  |  | SAFETY | BIKE/PED FACIL(O) | REHABILITATION AND CONSTRUCTION OF VARIOUS SIDEWALK PROJECTS IN LOUISVILLE METRO. (2006BOPC) (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | C |  | SLO | 2020 |  | 42000 | [8 empty] | 0
TIP | [9 empty] | JEFFERSON | 5-470 | CS 1014B |  | 0 | 0.848 | RELIABILITY | RECONSTRUCTION(O) | Design and construction for the conversion of the following one-way streets in downtown Louisville to two-way traffic flow: Jefferson Street (Floyd to Baxter Avenue); Liberty Street (Jackson to Baxter); Muhammad Ali Blvd. (Jackson to Chestnut Connector); Chestnut Street (Jackson to Chestnut Connector); 8th Street (Kentucky to Main); 7th Street (Oak to Main); Shelby Street (Gray to Main Street); and Campbell Street (Chestnut to Main Street). | C |  | SLO | 2019 | 4000000 | 4000000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; UPDATE FISCAL YEAR FROM 2019 TO 2020; MOD |  |  | JEFFERSON | 5-470 | CS 1014B |  | 0 | 0.848 | RELIABILITY | RECONSTRUCTION(O) | Design and construction for the conversion of the following one-way streets in downtown Louisville to two-way traffic flow: Jefferson Street (Floyd to Baxter Avenue); Liberty Street (Jackson to Baxter); Muhammad Ali Blvd. (Jackson to Chestnut Connector); Chestnut Street (Jackson to Chestnut Connector); 8th Street (Kentucky to Main); 7th Street (Oak to Main); Shelby Street (Gray to Main Street); and Campbell Street (Chestnut to Main Street). | C |  | STP | 2020 | 4000000 | 4000000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.271 | 2021-01-12 | TIP FY 20-25, AMEND#2; UPDATE FISCAL YEAR FROM 2020 TO 2021; MOD |  |  | JEFFERSON | 5-470 | CS 1014B |  | 0 | 0.848 | RELIABILITY | RECONSTRUCTION(O) | Design and construction for the conversion of the following one-way streets in downtown Louisville to two-way traffic flow: Jefferson Street (Floyd to Baxter Avenue); Liberty Street (Jackson to Baxter); Muhammad Ali Blvd. (Jackson to Chestnut Connector); Chestnut Street (Jackson to Chestnut Connector); 8th Street (Kentucky to Main); 7th Street (Oak to Main); Shelby Street (Gray to Main Street); and Campbell Street (Chestnut to Main Street). | C |  | STP | 2021 | 4000000 | 4000000 | [8 empty] | 0
STIP | [6 empty] | NOT IN TIP |  |  | JEFFERSON | 5-470.1 | CS 1049F |  | 0.047 | 0.58 | RELIABILITY | RECONSTRUCTION(O) | CONVERSION OF ONE-WAY STREETS IN DOWNTOWN LOUISVILLE TO TWO-WAY TRAFFIC (8TH, 7TH, SHELBY, CAMPBELL STREETS). PHASE 2 | D |  | SLO | 2019 | 60000 | 48000 |  |  |  | 12000 |  |  |  |  | 0
STIP | [6 empty] | NOT IN TIP |  |  | JEFFERSON | 5-470.1 | CS 1049F |  | 0.047 | 0.58 | RELIABILITY | RECONSTRUCTION(O) | CONVERSION OF ONE-WAY STREETS IN DOWNTOWN LOUISVILLE TO TWO-WAY TRAFFIC (8TH, 7TH, SHELBY, CAMPBELL STREETS). PHASE 2 | C |  | SLO | 2019 | 600000 | 480000 |  |  |  | 120000 |  |  |  |  | 0
STIP | [9 empty] | JEFFERSON | 5-478 | US 31W | 1.503 | 13.837 | 15.34 | SAFETY | SAFETY(P) | DIXIE HIGHWAY ADDITIONAL DESIGN FUNDS. IMPROVE DIXIE HIGHWAY BETWEEN CRUMS LANE (KY 2049) AND ROCKFORD LANE (KY 2051)(12CCR) | C |  | SLO | 2019 | 4000000 | 3200000 |  |  |  | 800000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.057 | 2019-04-26 | TIP FY 18-21, ADMIN MOD#29; KIPDA ID 2232; UPDATE DESCRIPTION, FUND AMOUNTS & PROJECT NAME TO DIXIE TIGER PROJECT; MOD |  |  | JEFFERSON | 5-478 | US 31W | 1.503 | 13.837 | 15.34 | SAFETY | SAFETY(P) | Intelligent Transportation System (ITS)/Signal System and Technology Upgrades to connect Dixie Highway to the city's existing traffic operations center for active traffic management operations. Complete Streets and Safety/Access Management Improvements to include construction of pedestrian pathways and improved multi-modal (especially pedestrian and transit) connectivity. Project will include raised medians, consolidation of access points, modification from TWLTL to dedicated turn lanes, signage and striping upgrades. Bus Rapid Transit to include upgraded facilities along corridor with approximately 36 new, highly visible and easily accessible BRT stations, newly branded vechicles unique to Dixie Corridor, appropriately located queue-jump lanes and bus turnouts. | C |  | SLO | 2019 | 1100000 | 1100000 |  |  |  | 0 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.186 | 2020-05-06 | TIP FY 20-25, ADMIN MOD#2; UPDATE FISCAL YEAR FROM 2019 TO 2020 AND FUND AMOUNT; MOD |  |  | JEFFERSON | 5-478 | US 31W | 1.503 | 13.837 | 15.34 | SAFETY | SAFETY(P) | Intelligent Transportation System (ITS)/Signal System and Technology Upgrades to connect Dixie Highway to the city's existing traffic operations center for active traffic management operations. Complete Streets and Safety/Access Management Improvements to include construction of pedestrian pathways and improved multi-modal (especially pedestrian and transit) connectivity. Project will include raised medians, consolidation of access points, modification from TWLTL to dedicated turn lanes, signage and striping upgrades. Bus Rapid Transit to include upgraded facilities along corridor with approximately 36 new, highly visible and easily accessible BRT stations, newly branded vechicles unique to Dixie Corridor, appropriately located queue-jump lanes and bus turnouts. | C |  | SLO | 2020 | 1500000 | 1500000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.194 | 2020-05-29 | TIP FY 20-25, ADMIN MOD#3; ADD R PHASE TO STIP; NEW |  |  | JEFFERSON | 5-479 | CR 1005B | 0.614 | 0 | 0.614 | RELIABILITY | RECONSTRUCTION(O) | Widen Hubbards Lane from 2 to 3 lanes (3rd lane will be a center turn lane) from US 60 (Shelbyville Road) to KY 1447 (Westport Road). Add bike lanes to Hubbards Lane from Kresge Way to KY 1447. Project length is 1.4 mi. | R |  | STP | 2020 | 312500 | 250000 |  |  |  | 62500 |  |  |  |  | 0
STIP | [7 empty] | STPM | 3001535 | JEFFERSON | 5-479 | CR 1005B | 0.614 | 0 | 0.614 | RELIABILITY | RECONSTRUCTION(O) | WIDEN HUBBARDS LANE FROM 2 TO 3 LANES (3RD LANE WILL BE A CENTER TURN LANE) FROM US 60 (SHELBYVILLE ROAD) TO KY 1447 (WESTPORT ROAD). ADD BIKE LANES TO HUBBARDS LANE FROM KRESGE WAY TO KY 1447. PROJECT LENGTH IS 0.6 MI.(BOPC2010) | U |  | SLO | 2019 | 1380700 | 1125000 |  |  |  | 255700 |  | OBLIGATED | 45411.47 |  | 45411.47 | 2019 | 4TH QUARTER | Lousiville Metro
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; MOVE $1,079,589 (FEDERAL) OF THE #1,125,000 (FEDERAL) FROM FY 2019 TO FY 2020; MOD | STPM | 3001535 | JEFFERSON | 5-479 | CR 1005B | 0.614 | 0 | 0.614 | RELIABILITY | RECONSTRUCTION(O) | Widen Hubbards Lane from 2 to 3 lanes (3rd lane will be a center turn lane) from US 60 (Shelbyville Road) to KY 1447 (Westport Road). Add bike lanes to Hubbards Lane from Kresge Way to KY 1447. Project length is 1.4 mi. | U |  | STP | 2020 | 1125000 | 1079589 |  |  |  | 45411 |  | OBLIGATED | 45411.47 |  | 45411.47 | 2019 | 4TH QUARTER | Lousiville Metro
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.194 | 2020-05-29 | TIP FY 20-25, ADMIN MOD#3; UPDATE FUND AMOUNTS; MOD | STPM | 3001535 | JEFFERSON | 5-479 | CR 1005B | 0.614 | 0 | 0.614 | RELIABILITY | RECONSTRUCTION(O) | Widen Hubbards Lane from 2 to 3 lanes (3rd lane will be a center turn lane) from US 60 (Shelbyville Road) to KY 1447 (Westport Road). Add bike lanes to Hubbards Lane from Kresge Way to KY 1447. Project length is 1.4 mi. | U |  | STP | 2020 | 1036987 | 829589 |  |  |  | 207398 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; UPDATE FISCAL YEAR; MOD |  |  | JEFFERSON | 5-479 | CR 1005B | 0.614 | 0 | 0.614 | RELIABILITY | RECONSTRUCTION(O) | Widen Hubbards Lane from 2 to 3 lanes (3rd lane will be a center turn lane) from US 60 (Shelbyville Road) to KY 1447 (Westport Road). Add bike lanes to Hubbards Lane from Kresge Way to KY 1447. Project length is 1.4 mi. | U |  | STP | 2021 | 1036987 | 829589 |  |  |  | 207398
TIP | [6 empty] | TIP AND STIP AMOUNTS ARE DIFFERENT | STPM | 3001535 | JEFFERSON | 5-479 | CR 1005B | 0.614 | 0 | 0.614 | RELIABILITY | RECONSTRUCTION(O) | Widen Hubbards Lane from 2 to 3 lanes (3rd lane will be a center turn lane) from US 60 (Shelbyville Road) to KY 1447 (Westport Road). Add bike lanes to Hubbards Lane from Kresge Way to KY 1447. Project length is 1.4 mi. | C |  | SLO | 2019 | 2900000 | 2320000 |  |  |  | 580000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; UPDATE FISCAL YEAR FROM 2019 TO 2020; MOD | STPM | 3001535 | JEFFERSON | 5-479 | CR 1005B | 0.614 | 0 | 0.614 | RELIABILITY | RECONSTRUCTION(O) | Widen Hubbards Lane from 2 to 3 lanes (3rd lane will be a center turn lane) from US 60 (Shelbyville Road) to KY 1447 (Westport Road). Add bike lanes to Hubbards Lane from Kresge Way to KY 1447. Project length is 1.4 mi. | C |  | STP | 2020 | 2900000 | 2320000 |  |  |  | 580000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; UPDATE FISCAL YEAR & FUND AMOUNTS; MOD | STPM | 3001535 | JEFFERSON | 5-479 | CR 1005B | 0.614 | 0 | 0.614 | RELIABILITY | RECONSTRUCTION(O) | Widen Hubbards Lane from 2 to 3 lanes (3rd lane will be a center turn lane) from US 60 (Shelbyville Road) to KY 1447 (Westport Road). Add bike lanes to Hubbards Lane from Kresge Way to KY 1447. Project length is 1.4 mi. | C |  | STP | 2021 | 3625000 | 2900000 |  |  | 725000
TIP | [6 empty] | NOT IN STIP | STPM | 3001535 | Jefferson | 5-479 | CR 1005B | 0.614 | 0 | 0.614 | RELIABILITY | RECONSTRUCTION(O) | Widen Hubbards Lane from 2 to 3 lanes (3rd lane will be a center turn lane) from US 60 (Shelbyville Road) to KY 1447 (Westport Road). Add bike lanes to Hubbards Lane from Kresge Way to KY 1447. Project length is 1.4 mi. | D |  | SLO | 2019 | 78350 | 63840 |  |  |  | 14510 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; UPDATE FISCAL YEAR FROM 2019 TO 2020; MOD |  |  | Jefferson | 5-479 | CR 1005B | 0.614 | 0 | 0.614 | RELIABILITY | RECONSTRUCTION(O) | Widen Hubbards Lane from 2 to 3 lanes (3rd lane will be a center turn lane) from US 60 (Shelbyville Road) to KY 1447 (Westport Road). Add bike lanes to Hubbards Lane from Kresge Way to KY 1447. Project length is 1.4 mi. | D |  | STP | 2020 | 78350 | 63840 |  |  |  | 14510 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; UPDATE FISCAL YEAR & FUND AMOUNTS; MOD |  |  | Jefferson | 5-479 | CR 1005B | 0.614 | 0 | 0.614 | RELIABILITY | RECONSTRUCTION(O) | Widen Hubbards Lane from 2 to 3 lanes (3rd lane will be a center turn lane) from US 60 (Shelbyville Road) to KY 1447 (Westport Road). Add bike lanes to Hubbards Lane from Kresge Way to KY 1447. Project length is 1.4 mi. | D |  | STP | 2021 | 59375 | 47500 |  |  | 11875 | [5 empty] | 0
TIP | [9 empty] | JEFFERSON | 5-481 | KY 864 | 1.547 | 1.818 | 3.445 | RELIABILITY | MATCHED FED FUNDS(O) | KY 864 - WIDEN BEULAH CHURCH ROAD FROM 2 TO 3 LANES FROM I-265 TO CEDAR CREEK ROAD.(2010BOP) | R |  | SLO | 2019 | 2950000 | 2950000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.057 | 2019-04-26 | TIP FY 18-21, ADMIN MOD#29; UPDATE DESCRIPTION & FUND AMOUNTS; MOD | STPM | 8743004 | JEFFERSON | 5-481 | KY 864 | 1.547 | 1.818 | 3.445 | RELIABILITY | MATCHED FED FUNDS(O) | WIDEN BEULAH CHURCH ROAD FROM 2 LANES TO 3 LANES FROM I-265 TO CEDAR CREEK ROAD. MP FROM 1.818 TO 3.445. | R |  | SLO | 2019 | 5050000 | 5050000 | [5 empty] | OBLIGATED | 5050000 |  | 5050000 | 2019 | 3RD QUARTER
TIP | [9 empty] | JEFFERSON | 5-481 | KY 864 | 1.547 | 1.818 | 3.445 | RELIABILITY | MATCHED FED FUNDS(O) | KY 864 - WIDEN BEULAH CHURCH ROAD FROM 2 TO 3 LANES FROM I-265 TO CEDAR CREEK ROAD.(2010BOP) | U |  | SLO | 2019 | 1975000 | 1975000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.114 | 2019-08-12 | TIP FY 18-21, AMENDMENT#6; CHANGE OPEN TO PUBLIC DATE FROM 2020 TO 2024; MOD |  |  | JEFFERSON | 5-481 | KY 864 | 1.547 | 1.818 | 3.445 | RELIABILITY | MATCHED FED FUNDS(O) | KY 864 - WIDEN BEULAH CHURCH ROAD FROM 2 TO 3 LANES FROM I-265 TO CEDAR CREEK ROAD.(2010BOP) |  |  | SLO | 2024
STIP | YES | [6 empty] | NHPP | 0711111 | JEFFERSON | 5-483 | I 71 | 5 | 9.1 | 11.315 | RELIABILITY | MAJOR WIDENING(O) | SIX LANE PRIORITY SECTION OF I-71 BETWEEN I-265 AND KY-329.(16CCR) | R |  | NH | 2019 | 500000 | 500000 |  |  | 0 |  |  | OBLIGATED |  | 400000 | 400000 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.057 | 2019-04-26 | TIP FY 18-21, ADMIN MOD#29; UPDATE DESCRIPTION & FUND AMOUNTS; MOD | NHPP | 0711111 | JEFFERSON | 5-483.00 5-483.01 5-483.02 | I 71 | 5 | 9.1 | 11.315 | RELIABILITY | MAJOR WIDENING(O) | SIX LANE PRIORITY SECTION OF I-71 BETWEEN I-265 AND KY-329. PROJECT WILL EVALUATE WIDENING FROM 4 TO 6 LANES AS A POTENTIAL SOLUTION TO CONGESTION. | R |  | NHS | 2019 | 400000 | 400000 | [5 empty] | OBLIGATED |  | 400000 | 400000 | 2019 | 2ND QUARTER
STIP | YES | [6 empty] | NHPP | 0711111 | JEFFERSON | 5-483 | I 71 | 5 | 9.1 | 11.315 | RELIABILITY | MAJOR WIDENING(O) | SIX LANE PRIORITY SECTION OF I-71 BETWEEN I-265 AND KY-329.(16CCR) | U |  | NH | 2019 | 500000 | 500000 |  |  | 0 |  |  | OBLIGATED |  | 565000 | 565000 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.057 | 2019-04-26 | TIP FY 18-21, ADMIN MOD#29; UPDATE DESCRIPTION & FUND AMOUNTS; MOD |  |  | JEFFERSON OLDHAM | 5-483.00 5-483.01 5-483.02 | I 71 | 5 | 9.1 | 11.315 | RELIABILITY | PREFINANCD CONVRSN(O) | SIX LANE PRIORITY SECTION OF I-71 BETWEEN I-265 AND KY-329. PROJECT WILL EVALUATE WIDENING FROM 4 TO 6 LANES AS A POTENTIAL SOLUTION TO CONGESTION. | U |  | NHS | 2018 | 565000 | 565000 |  |  | 0 |  |  | OBLIGATED |  | 565000 | 565000 | 2019 | 2ND QUARTER
STIP | YES | [8 empty] | JEFFERSON | 5-483 | I 71 | 5 | 9.1 | 11.315 | RELIABILITY | MAJOR WIDENING(O) | SIX LANE PRIORITY SECTION OF I-71 BETWEEN I-265 AND KY-329.(16CCR) | C |  | NH | 2019 | 15000000 | 15000000 |  |  | 0 | [5 empty] | 0
STIP | YES | [8 empty] | JEFFERSON | 5-483.01 | I 71 | 5 | 9.1 | 11.315 | RELIABILITY | PREFINANCD CONVRSN(O) | SIX LANE PRIORITY SECTION OF I-71 BETWEEN I-265 AND KY-329.(16CCR) | C |  | NH | 2020 | 15000000 | 15000000 |  |  | 0 | [5 empty] | 0
STIP | YES | [8 empty] | JEFFERSON | 5-483.02 | I 71 | 5 | 9.1 | 11.315 | RELIABILITY | PREFINANCD CONVRSN(O) | SIX LANE PRIORITY SECTION OF I-71 BETWEEN I-265 AND KY-329.(16CCR) | C |  | NH | 2021 | 30000000 | 24000000 |  |  | 6000000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.001 | 2018-12-06 | TIP FY 18-21, AMENDMENT#3; UPDATE FUNDING AMOUNTS; MOD |  |  | JEFFERSON OLDHAM | 5-483.00 5-483.01 5-483.02 | I 71 | 5 | 9.1 | 11.315 | RELIABILITY | PREFINANCD CONVRSN(O) | SIX LANE PRIORITY SECTION OF I-71 BETWEEN I-265 AND KY-329.(16CCR) | C |  | NHS | 2021 | 30000000 | 30000000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.057 | 2019-04-26 | TIP FY 18-21, ADMIN MOD#29; UPDATE DESCRIPTION; MOD |  |  | JEFFERSON OLDHAM | 5-483.00 5-483.01 5-483.02 | I 71 | 5 | 9.1 | 11.315 | RELIABILITY | PREFINANCD CONVRSN(O) | SIX LANE PRIORITY SECTION OF I-71 BETWEEN I-265 AND KY-329. PROJECT WILL EVALUATE WIDENING FROM 4 TO 6 LANES AS A POTENTIAL SOLUTION TO CONGESTION. | C |  | NHS | 2021 | 30000000 | 30000000 |  |  | 0 | [5 empty] | 0
TIP | [7 empty] | STPM | 3001504 | JEFFERSON | 5-486 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | Construct a multi-use bicycle and pedestrian trial along Old Taylorsville Road and Jefferson Street in downtown Jeffersontown connecting the downtown street network to the Good Samaritan Center and the existing bicycle/pedestrian trail at Grand Avenue and Watterson Trail. | C |  | SLO | 2019 | 1515000 | 1300000 |  |  |  | 215000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; UPDATE FISCAL YEAR FROM 2019 TO 2020; MOD | STPM | 3001504 | JEFFERSON | 5-486 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | Construct a multi-use bicycle and pedestrian trial along Old Taylorsville Road and Jefferson Street in downtown Jeffersontown connecting the downtown street network to the Good Samaritan Center and the existing bicycle/pedestrian trail at Grand Avenue and Watterson Trail. | C |  | STP | 2020 | 1515000 | 1300000 |  |  |  | 215000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.186 | 2020-05-06 | TIP FY 20-25, ADMIN MOD#2; UPDATE PROJECT DESCRIPTION AND FUND AMOUNTS; MOD |  |  | JEFFERSON | 5-486 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | Construct a .67 mile multi-use bicycle and pedestrian trail 10 feet wide along portions of Watterson Trail, Grand Avenue, Bluebird Lane and Shelby Street as well as traversing between the Jeffersontown Public Library and the Academy of Individual Excellence School and the Good Samaritan Residential Community in downton Jeffersontown. | C |  | STP | 2020 | 1825000 | 1460000 |  |  |  | 365000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 2025, ADMIN MDO#10; UPDATE FISCAL YEAR; MOD |  |  | JEFFERSON | 5-486 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | Construct a .67 mile multi-use bicycle and pedestrian trail 10 feet wide along portions of Watterson Trail, Grand Avenue, Bluebird Lane and Shelby Street as well as traversing between the Jeffersontown Public Library and the Academy of Individual Excellence School and the Good Samaritan Residential Community in downton Jeffersontown. | C |  | STP | 2022 | 1825000 | 1460000 |  |  |  | 365000 |  |  |  |  | 0
TIP | [6 empty] | Not in STIP | STPM | 3001504 | Jefferson | 5-486 | Good Samaritan Bicycle and Pedestrian Trail Connector | [5 empty] | Construct a multi-use bicycle and pedestrian trial along Old Taylorsville Road and Jefferson Street in downtown Jeffersontown connecting the downtown street network to the Good Samaritan Center and the existing bicycle/pedestrian trail at Grand Avenue and Watterson Trail. | D |  | STP-ST | 2019 | 115000 | 5000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.057 | 2019-04-26 | TIP FY 18-21, ADMIN MOD#29; ADD D PHASE TO STIP; NEW |  |  | Jefferson | 5-489 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | DESIGN & CONSTRUCT SHARED USE PATH & LOUISVILLE LOOP TRAILHEAD FACILITIES THRU JEFFERSON MEMORIAL FOREST FROM NORTH END OF SAND QUARRY TUNNEL AT GENE SNYDER FWY TO WEST TERMINUS OF EXISTING MSD TRAIL APPROX. 2.7 MI WHICH WILL INCLUDE BRIDGE OVER POND CR. | D |  | SLO | 2019 | 583387 | 466710 |  |  |  | 116677 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; UPDATE FISCAL YEAR FROM 2019 TO 2020; MOD |  |  | Jefferson | 5-489 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | DESIGN & CONSTRUCT SHARED USE PATH & LOUISVILLE LOOP TRAILHEAD FACILITIES THRU JEFFERSON MEMORIAL FOREST FROM NORTH END OF SAND QUARRY TUNNEL AT GENE SNYDER FWY TO WEST TERMINUS OF EXISTING MSD TRAIL APPROX. 2.7 MI WHICH WILL INCLUDE BRIDGE OVER POND CR. | D |  | STP | 2020 | 583387 | 466710 |  |  |  | 116677 |  |  |  |  | 0
STIP | [9 empty] | JEFFERSON | 5-489 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | DESIGN & CONSTRUCT SHARED USE PATH & LOUISVILLE LOOP TRAILHEAD FACILITIES THRU JEFFERSON MEMORIAL FOREST FROM NORTH END OF SAND QUARRY TUNNEL AT GENE SNYDER FWY TO WEST TERMINUS OF EXISTING MSD TRAIL APPROX. 2.7 MI WHICH WILL INCLUDE BRIDGE OVER POND CR. | R |  | SLO | 2019 | 100000 | 80000 |  |  |  | 20000 |  |  |  |  | 0
TIP | [6 empty] | TIP AND STIP AMOUNTS ARE DIFFERENT |  |  | JEFFERSON | 5-489 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | DESIGN & CONSTRUCT SHARED USE PATH & LOUISVILLE LOOP TRAILHEAD FACILITIES THRU JEFFERSON MEMORIAL FOREST FROM NORTH END OF SAND QUARRY TUNNEL AT GENE SNYDER FWY TO WEST TERMINUS OF EXISTING MSD TRAIL APPROX. 2.7 MI WHICH WILL INCLUDE BRIDGE OVER POND CR. | R |  | SLO | 2019 | 120000 | 100000 |  |  |  | 20000 |  |  |  |  | 0
STIP | [9 empty] | JEFFERSON | 5-489 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | DESIGN & CONSTRUCT SHARED USE PATH & LOUISVILLE LOOP TRAILHEAD FACILITIES THRU JEFFERSON MEMORIAL FOREST FROM NORTH END OF SAND QUARRY TUNNEL AT GENE SNYDER FWY TO WEST TERMINUS OF EXISTING MSD TRAIL APPROX. 2.7 MI WHICH WILL INCLUDE BRIDGE OVER POND CR. | U |  | SLO | 2019 | 55000 | 44000 |  |  |  | 11000 |  |  |  |  | 0
TIP | [6 empty] | TIP AND STIP AMOUNTS ARE DIFFERENT |  |  | JEFFERSON | 5-489 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | DESIGN & CONSTRUCT SHARED USE PATH & LOUISVILLE LOOP TRAILHEAD FACILITIES THRU JEFFERSON MEMORIAL FOREST FROM NORTH END OF SAND QUARRY TUNNEL AT GENE SNYDER FWY TO WEST TERMINUS OF EXISTING MSD TRAIL APPROX. 2.7 MI WHICH WILL INCLUDE BRIDGE OVER POND CR. | U |  | SLO | 2019 | 68750 | 55000 |  |  |  | 13750 |  |  |  |  | 0
STIP | [9 empty] | JEFFERSON | 5-489 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | DESIGN & CONSTRUCT SHARED USE PATH & LOUISVILLE LOOP TRAILHEAD FACILITIES THRU JEFFERSON MEMORIAL FOREST FROM NORTH END OF SAND QUARRY TUNNEL AT GENE SNYDER FWY TO WEST TERMINUS OF EXISTING MSD TRAIL APPROX. 2.7 MI WHICH WILL INCLUDE BRIDGE OVER POND CR. | C |  | SLO | 2019 | 2000000 | 1600000 |  |  |  | 400000 |  |  |  |  | 0
TIP | [6 empty] | TIP AND STIP AMOUNTS ARE DIFFERENT |  |  | JEFFERSON | 5-489 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | DESIGN & CONSTRUCT SHARED USE PATH & LOUISVILLE LOOP TRAILHEAD FACILITIES THRU JEFFERSON MEMORIAL FOREST FROM NORTH END OF SAND QUARRY TUNNEL AT GENE SNYDER FWY TO WEST TERMINUS OF EXISTING MSD TRAIL APPROX. 2.7 MI WHICH WILL INCLUDE BRIDGE OVER POND CR. | C |  | SLO | 2020 | 2500000 | 2000000 |  |  |  | 500000 |  |  |  |  | 0
STIP | [6 empty] | NOT IN TIP |  |  | JEFFERSON | 5-493 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | MISCELLANEOUS SIDEWALKS AND HANDICAP RAMPS: CONSTRUCT AND REPLACE VARIOUS SIDEWALKS AND HANDICAP RAMPS THROUGHOUT THE CITY ON A REOCCURRING ANNUAL BASIS. | C |  | SLO | 2019 | 37800 | 30240 |  |  |  | 7560 |  |  |  |  | 0
STIP | [9 empty] | JEFFERSON | 5-495 | KY 1020 |  | 7.837 | 9.15 | SAFETY | BIKE/PED FACIL(O) | OLMSTED PARKWAYS MULTI-USE PATH SYSTEM-SOUTHERN PKWY: CONSTRUCTION OF A 2.5 MILE SHARED USE PATH SYSTEM ALONG SOUTHERN PARKWAY BETWEEN SOUTH 3RD AND NEW CUT ROAD. | R |  | SLO | 2019 | 400000 | 320000 |  |  |  | 80000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.01 | 2018-12-27 | TIP FY 18-21, ADMIN MOD#25; REMOVE THE R PHASE-THIS PROJECT IS STILL BEING CONSTRUCTED BUT UNDER NEW KIPDA ID 1273; MOD |  |  | JEFFERSON | 5-495 | KY 1020 |  | 7.837 | 9.15 | SAFETY | BIKE/PED FACIL(O) | OLMSTED PARKWAYS MULTI-USE PATH SYSTEM-SOUTHERN PKWY: CONSTRUCTION OF A 2.5 MILE SHARED USE PATH SYSTEM ALONG SOUTHERN PARKWAY BETWEEN SOUTH 3RD AND NEW CUT ROAD. | R | [13 empty] | 0
STIP | [9 empty] | JEFFERSON | 5-495 | KY 1020 |  | 7.837 | 9.15 | SAFETY | BIKE/PED FACIL(O) | OLMSTED PARKWAYS MULTI-USE PATH SYSTEM-SOUTHERN PKWY: CONSTRUCTION OF A 2.5 MILE SHARED USE PATH SYSTEM ALONG SOUTHERN PARKWAY BETWEEN SOUTH 3RD AND NEW CUT ROAD. | U |  | SLO | 2019 | 100000 | 80000 |  |  |  | 20000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.01 | 2018-12-27 | TIP FY 18-21, ADMIN MOD#25; REMOVE THE U PHASE-THIS PROJECT IS STILL BEING CONSTRUCTED BUT UNDER NEW KIPDA ID 1273; MOD |  |  | JEFFERSON | 5-495 | KY 1020 |  | 7.837 | 9.15 | SAFETY | BIKE/PED FACIL(O) | OLMSTED PARKWAYS MULTI-USE PATH SYSTEM-SOUTHERN PKWY: CONSTRUCTION OF A 2.5 MILE SHARED USE PATH SYSTEM ALONG SOUTHERN PARKWAY BETWEEN SOUTH 3RD AND NEW CUT ROAD. | U | [13 empty] | 0
STIP | [9 empty] | JEFFERSON | 5-495 | KY 1020 |  | 7.837 | 9.15 | SAFETY | BIKE/PED FACIL(O) | OLMSTED PARKWAYS MULTI-USE PATH SYSTEM-SOUTHERN PKWY: CONSTRUCTION OF A 2.5 MILE SHARED USE PATH SYSTEM ALONG SOUTHERN PARKWAY BETWEEN SOUTH 3RD AND NEW CUT ROAD. | C |  | SLO | 2021 | 4672877 | 3738301.6 |  |  |  | 934575.4 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.01 | 2018-12-27 | TIP FY 18-21, ADMIN MOD#25; REMOVE THE C PHASE-THIS PROJECT IS STILL BEING CONSTRUCTED BUT UNDER NEW KIPDA ID 1273; MOD |  |  | JEFFERSON | 5-495 | KY 1020 |  | 7.837 | 9.15 | SAFETY | BIKE/PED FACIL(O) | OLMSTED PARKWAYS MULTI-USE PATH SYSTEM-SOUTHERN PKWY: CONSTRUCTION OF A 2.5 MILE SHARED USE PATH SYSTEM ALONG SOUTHERN PARKWAY BETWEEN SOUTH 3RD AND NEW CUT ROAD. | C | [13 empty] | 0
STIP | [9 empty] | JEFFERSON | 5-496 | KY 2054 |  | 0.72 | 1.22 | SAFETY | BIKE/PED FACIL(O) | CONSTRUCTION OF A 0.5 MILE SHARED USE PATH SYSTEM ALONG ALGONQUIN PARKWAY BETWEEN WILSON AVENUE AND CYPRESS STREET. | R |  | SLO | 2019 | 160000 | 128000 |  |  |  | 32000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.01 | 2018-12-27 | TIP FY 18-21, ADMIN MOD#25; REMOVE THE R PHASE-THIS PROJECT IS STILL BEING CONSTRUCTED BUT UNDER NEW KIPDA ID 1273; MOD |  |  | JEFFERSON | 5-496 | KY 2054 |  | 0.72 | 1.22 | SAFETY | BIKE/PED FACIL(O) | CONSTRUCTION OF A 0.5 MILE SHARED USE PATH SYSTEM ALONG ALGONQUIN PARKWAY BETWEEN WILSON AVENUE AND CYPRESS STREET. | R | [13 empty] | 0
STIP | [9 empty] | JEFFERSON | 5-496 | KY 2054 |  | 0.72 | 1.22 | SAFETY | BIKE/PED FACIL(O) | CONSTRUCTION OF A 0.5 MILE SHARED USE PATH SYSTEM ALONG ALGONQUIN PARKWAY BETWEEN WILSON AVENUE AND CYPRESS STREET. | U |  | SLO | 2019 | 80000 | 64000 |  |  |  | 16000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.01 | 2018-12-27 | TIP FY 18-21, ADMIN MOD#25; REMOVE THE U PHASE-THIS PROJECT IS STILL BEING CONSTRUCTED BUT UNDER NEW KIPDA ID 1273; MOD |  |  | JEFFERSON | 5-496 | KY 2054 |  | 0.72 | 1.22 | SAFETY | BIKE/PED FACIL(O) | CONSTRUCTION OF A 0.5 MILE SHARED USE PATH SYSTEM ALONG ALGONQUIN PARKWAY BETWEEN WILSON AVENUE AND CYPRESS STREET. | U | [13 empty] | 0
STIP | [9 empty] | JEFFERSON | 5-496 | KY 2054 |  | 0.72 | 1.22 | SAFETY | BIKE/PED FACIL(O) | CONSTRUCTION OF A 0.5 MILE SHARED USE PATH SYSTEM ALONG ALGONQUIN PARKWAY BETWEEN WILSON AVENUE AND CYPRESS STREET. | C |  | SLO | 2020 | 1500000 | 1200000 |  |  |  | 300000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.01 | 2018-12-27 | TIP FY 18-21, ADMIN MOD#25; REMOVE THE C PHASE-THIS PROJECT IS STILL BEING CONSTRUCTED BUT UNDER NEW KIPDA ID 1273; MOD |  |  | JEFFERSON | 5-496 | KY 2054 |  | 0.72 | 1.22 | SAFETY | BIKE/PED FACIL(O) | CONSTRUCTION OF A 0.5 MILE SHARED USE PATH SYSTEM ALONG ALGONQUIN PARKWAY BETWEEN WILSON AVENUE AND CYPRESS STREET. | C | [13 empty] | 0
STIP | [9 empty] | JEFFERSON | 5-497 | KY 2054 |  | 1.22 | 1.64 | SAFETY | BIKE/PED FACIL(O) | CONSTRUCTION OF A 0.45 MILE SHARED USE PATH SYSTEM ALONG ALGONQUIN PARKWAY BETWEEN CYPRESS STREET AND DIXIE HWY. | R |  | SLO | 2019 | 160000 | 128000 |  |  |  | 32000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.01 | 2018-12-27 | TIP FY 18-21, ADMIN MOD#25; REMOVE THE R PHASE-THIS PROJECT IS STILL BEING CONSTRUCTED BUT UNDER NEW KIPDA ID 1273; MOD |  |  | JEFFERSON | 5-497 | KY 2054 |  | 1.22 | 1.64 | SAFETY | BIKE/PED FACIL(O) | CONSTRUCTION OF A 0.45 MILE SHARED USE PATH SYSTEM ALONG ALGONQUIN PARKWAY BETWEEN CYPRESS STREET AND DIXIE HWY. | R | [13 empty] | 0
STIP | [9 empty] | JEFFERSON | 5-497 | KY 2054 |  | 1.22 | 1.64 | SAFETY | BIKE/PED FACIL(O) | CONSTRUCTION OF A 0.45 MILE SHARED USE PATH SYSTEM ALONG ALGONQUIN PARKWAY BETWEEN CYPRESS STREET AND DIXIE HWY. | U |  | SLO | 2019 | 80000 | 64000 |  |  |  | 16000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.01 | 2018-12-27 | TIP FY 18-21, ADMIN MOD#25; REMOVE THE U PHASE-THIS PROJECT IS STILL BEING CONSTRUCTED BUT UNDER NEW KIPDA ID 1273; MOD |  |  | JEFFERSON | 5-497 | KY 2054 |  | 1.22 | 1.64 | SAFETY | BIKE/PED FACIL(O) | CONSTRUCTION OF A 0.45 MILE SHARED USE PATH SYSTEM ALONG ALGONQUIN PARKWAY BETWEEN CYPRESS STREET AND DIXIE HWY. | U | [13 empty] | 0
STIP | [9 empty] | JEFFERSON | 5-497 | KY 2054 |  | 1.22 | 1.64 | SAFETY | BIKE/PED FACIL(O) | CONSTRUCTION OF A 0.45 MILE SHARED USE PATH SYSTEM ALONG ALGONQUIN PARKWAY BETWEEN CYPRESS STREET AND DIXIE HWY. | C |  | SLO | 2019 | 1148945 | 919156 |  |  |  | 229789 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.01 | 2018-12-27 | TIP FY 18-21, ADMIN MOD#25; REMOVE THE C PHASE-THIS PROJECT IS STILL BEING CONSTRUCTED BUT UNDER NEW KIPDA ID 1273; MOD |  |  | JEFFERSON | 5-497 | KY 2054 |  | 1.22 | 1.64 | SAFETY | BIKE/PED FACIL(O) | CONSTRUCTION OF A 0.45 MILE SHARED USE PATH SYSTEM ALONG ALGONQUIN PARKWAY BETWEEN CYPRESS STREET AND DIXIE HWY. | C | [13 empty] | 0
STIP | [9 empty] | JEFFERSON | 5-498 | KY 2054 |  | 1.64 | 2.717 | SAFETY | BIKE/PED FACIL(O) | CONSTRUCTION OF A 1.2 MILE SHARED USE PATH SYSTEM ALONG ALGONQUIN PARKWAY BETWEEN DIXIE HIGHWAY AND SHARP AVE. | R |  | SLO | 2019 | 200000 | 160000 |  |  |  | 40000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.01 | 2018-12-27 | TIP FY 18-21, ADMIN MOD#25; REMOVE THE R PHASE-THIS PROJECT IS STILL BEING CONSTRUCTED BUT UNDER NEW KIPDA ID 1273; MOD |  |  | JEFFERSON | 5-498 | KY 2054 |  | 1.64 | 2.717 | SAFETY | BIKE/PED FACIL(O) | CONSTRUCTION OF A 1.2 MILE SHARED USE PATH SYSTEM ALONG ALGONQUIN PARKWAY BETWEEN DIXIE HIGHWAY AND SHARP AVE. | R | [13 empty] | 0
STIP | [9 empty] | JEFFERSON | 5-498 | KY 2054 |  | 1.64 | 2.717 | SAFETY | BIKE/PED FACIL(O) | CONSTRUCTION OF A 1.2 MILE SHARED USE PATH SYSTEM ALONG ALGONQUIN PARKWAY BETWEEN DIXIE HIGHWAY AND SHARP AVE. | U |  | SLO | 2019 | 160000 | 128000 |  |  |  | 32000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.01 | 2018-12-27 | TIP FY 18-21, ADMIN MOD#25; REMOVE THE U PHASE-THIS PROJECT IS STILL BEING CONSTRUCTED BUT UNDER NEW KIPDA ID 1273; MOD |  |  | JEFFERSON | 5-498 | KY 2054 |  | 1.64 | 2.717 | SAFETY | BIKE/PED FACIL(O) | CONSTRUCTION OF A 1.2 MILE SHARED USE PATH SYSTEM ALONG ALGONQUIN PARKWAY BETWEEN DIXIE HIGHWAY AND SHARP AVE. | U | [13 empty] | 0
STIP | [9 empty] | JEFFERSON | 5-498 | KY 2054 |  | 1.64 | 2.717 | SAFETY | BIKE/PED FACIL(O) | CONSTRUCTION OF A 1.2 MILE SHARED USE PATH SYSTEM ALONG ALGONQUIN PARKWAY BETWEEN DIXIE HIGHWAY AND SHARP AVE. | C |  | SLO | 2020 | 3063854 | 2451083.2 |  |  |  | 612770.8 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.01 | 2018-12-27 | TIP FY 18-21, ADMIN MOD#25; REMOVE THE C PHASE-THIS PROJECT IS STILL BEING CONSTRUCTED BUT UNDER NEW KIPDA ID 1273; MOD |  |  | JEFFERSON | 5-498 | KY 2054 |  | 1.64 | 2.717 | SAFETY | BIKE/PED FACIL(O) | CONSTRUCTION OF A 1.2 MILE SHARED USE PATH SYSTEM ALONG ALGONQUIN PARKWAY BETWEEN DIXIE HIGHWAY AND SHARP AVE. | C | [13 empty] | 0
STIP | [9 empty] | JEFFERSON | 5-499 | CR 1001B |  | 0 | 6.761 | SAFETY | BIKE/PED FACIL(O) | RIVER ROAD BICYCLE AND PEDESTRIAN IMPROVEMENTS FROM DOWNTOWN LOUISVILLE TO THE CITY OF PROSPECT (US 42), 8.5 MILES. (SEE 5-3036.00) | D |  | SLO | 2020 | 200000 | 160000 |  |  |  | 40000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; UPDATE FISCAL YEAR & FUND AMOUNTS; MOD |  |  | JEFFERSON | 5-499 | CR 1001B |  | 0 | 6.761 | SAFETY | BIKE/PED FACIL(O) | RIVER ROAD BICYCLE AND PEDESTRIAN IMPROVEMENTS FROM DOWNTOWN LOUISVILLE TO THE CITY OF PROSPECT (US 42), 8.5 MILES. (SEE 5-3036.00) | D |  | SLO | 2022 | 250000 | 200000 |  |  |  | 50000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; ADD C PHASE TO STIP; NEW |  |  | JEFFERSON | 5-499 | CR 1001B |  | 0 | 6.761 | SAFETY | BIKE/PED FACIL(O) | RIVER ROAD BICYCLE AND PEDESTRIAN IMPROVEMENTS FROM DOWNTOWN LOUISVILLE TO THE CITY OF PROSPECT (US 42), 8.5 MILES. (SEE 5-3036.00) | C |  | SLO | 2025 | 2812500 | 2250000 |  |  |  | 562500 |  |  |  |  | 0
STIP | [9 empty] | JEFFERSON | 5-505 | KY 2051 |  | 2.7 | 6 | SAFETY | BIKE/PED FACIL(O) | OHIO RIVER LEVEE TRAIL PHASE III. CONSTRUCT BICYCLE/PEDESTRIAN FACILITIES ALONG CAMPGROUND RD FROM END OF SHARED USE PATH AT THE RAILROAD CROSSING ON CAMPGROUND RD NEAR I-264 TO LEES LANE & THE CONNECTION TO RIVERSIDE GARDENS PK AT 2899 LEES LANE.(18CCR) | R |  | SLO | 2019 | 800000 | 640000 |  |  |  | 160000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.117 | 2019-08-09 | TIP FY 18-21; ADMIN MOD#34, UPDATE FUND TYPE FROM SLO TO TAP; MOD (SEE TAP SPREADSHEET) |  |  | JEFFERSON | 5-505 | KY 2051 |  | 2.7 | 6 | SAFETY | BIKE/PED FACIL(O) | OHIO RIVER LEVEE TRAIL PHASE III. CONSTRUCT BICYCLE/PEDESTRIAN FACILITIES ALONG CAMPGROUND RD FROM END OF SHARED USE PATH AT THE RAILROAD CROSSING ON CAMPGROUND RD NEAR I-264 TO LEES LANE & THE CONNECTION TO RIVERSIDE GARDENS PK AT 2899 LEES LANE.(18CCR) | R |  | TAP | 2019 | [10 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.122 | 2019-08-26 | TIP FY 18-21; ADMIN MOD#35, UPDATE FUND TYPE FROM TAP TO SLO FUNDS; MOD |  |  | JEFFERSON | 5-505 | KY 2051 |  | 2.7 | 6 | SAFETY | BIKE/PED FACIL(O) | OHIO RIVER LEVEE TRAIL PHASE III. CONSTRUCT BICYCLE/PEDESTRIAN FACILITIES ALONG CAMPGROUND RD FROM END OF SHARED USE PATH AT THE RAILROAD CROSSING ON CAMPGROUND RD NEAR I-264 TO LEES LANE & THE CONNECTION TO RIVERSIDE GARDENS PK AT 2899 LEES LANE.(18CCR) | R |  | SLO | 2019 | 1000000 | 800000 |  |  |  | 200000 |  |  |  |  | 0
TIP | [6 empty] | TIP AND STIP AMOUNTS ARE DIFFERENT |  |  | JEFFERSON | 5-505 | KY 2051 |  | 2.7 | 6 | SAFETY | BIKE/PED FACIL(O) | Construct bicycle/pedestrian facilities along Campground Road from the end of the shared use path at the railroad crossing on Campground Road near I-264 to Lees Lane and the connection to Riverside Gardens Park at 2899 Lees Lane. | R |  | SLO | 2019 | 1000000 | 800000 |  |  |  | 200000 |  |  |  |  | 0
TIP | [9 empty] | JEFFERSON | 5-505 | KY 2051 |  | 2.7 | 6 | SAFETY | BIKE/PED FACIL(O) | Construct bicycle/pedestrian facilities along Campground Road from the end of the shared use path at the railroad crossing on Campground Road near I-264 to Lees Lane and the connection to Riverside Gardens Park at 2899 Lees Lane. | U |  | SLO | 2019 | 937500 | 750000 |  |  |  | 187500 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38, UPDATE FISCAL YEAR FROM 2019 TO 2020; MOD |  |  | JEFFERSON | 5-505 | KY 2051 |  | 2.7 | 6 | SAFETY | BIKE/PED FACIL(O) | Construct bicycle/pedestrian facilities along Campground Road from the end of the shared use path at the railroad crossing on Campground Road near I-264 to Lees Lane and the connection to Riverside Gardens Park at 2899 Lees Lane. | U |  | STP | 2020 | 937500 | 750000 |  |  |  | 187500 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; UPDATE FISCAL YEAR; MOD |  |  | JEFFERSON | 5-505 | KY 2051 |  | 2.7 | 6 | SAFETY | BIKE/PED FACIL(O) | Construct bicycle/pedestrian facilities along Campground Road from the end of the shared use path at the railroad crossing on Campground Road near I-264 to Lees Lane and the connection to Riverside Gardens Park at 2899 Lees Lane. | U |  | STP | 2022 | 937500 | 750000 |  |  | 187500 | [5 empty] | 0
TIP | [6 empty] | NOT IN STIP |  |  | Jefferson | 5-505 | Ohio River Levee Trail - Phase III | [5 empty] | Construct bicycle/pedestrian facilities along Campground Road from the end of the shared use path at the railroad crossing on Campground Road near I-264 to Lees Lane and the connection to Riverside Gardens Park at 2899 Lees Lane. | C |  | SLO | 2020 | 3750000 | 3000000 |  |  |  | 750000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38, UPDATE FISCAL YEAR FROM 2019 TO 2020; MOD |  |  | Jefferson | 5-505 | Ohio River Levee Trail - Phase III |  | 2.7 | 6 | SAFETY | BIKE/PED FACIL(O) | Construct bicycle/pedestrian facilities along Campground Road from the end of the shared use path at the railroad crossing on Campground Road near I-264 to Lees Lane and the connection to Riverside Gardens Park at 2899 Lees Lane. | C |  | STP | 2021 | 3750000 | 3000000 |  |  |  | 750000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; UPDATE FISCAL YEAR; MOD |  |  | JEFFERSON | 5-505 | KY 2051 |  | 2.7 | 6 | SAFETY | BIKE/PED FACIL(O) | Construct bicycle/pedestrian facilities along Campground Road from the end of the shared use path at the railroad crossing on Campground Road near I-264 to Lees Lane and the connection to Riverside Gardens Park at 2899 Lees Lane. | C |  | STP | 2022 | 3750000 | 3000000 |  |  | 750000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; THIS PROJECT IS NOW UNDER ITEM # 5-512.00; MOD |  |  | JEFFERSON | 5-512 | CS 1001B |  |  |  | RELIABILITY | NEW ROUTE(O) | Extend River Road west from 7th Street to Northwestern Parkway. The project is feasible using a low design speed criteria and a two-lane section. | D |  | STP | 2021 | 1362500 | 1090000 |  |  | 272500 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; THIS PROJECT IS NOW UNDER ITEM # 5-512.00; MOD |  |  | JEFFERSON | 5-512 | CS 1001B |  |  |  | RELIABILITY | NEW ROUTE(O) | Extend River Road west from 7th Street to Northwestern Parkway. The project is feasible using a low design speed criteria and a two-lane section. | R |  | STP | 2022 | 675000 | 540000 |  |  | 135000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; ADD C PHASE TO STIP; NEW |  |  | JEFFERSON | 5-512 | CS 1001B |  |  |  | RELIABILITY | NEW ROUTE(O) | Extend River Road west from 7th Street to Northwestern Parkway. The project is feasible using a low design speed criteria and a two-lane section. | C |  | STP | 2024 | 8750000 | 7000000 |  |  | 1750000 | [5 empty] | 0
TIP | [9 empty] | JEFFERSON | 5-518 | CR 1004H | 0.151 | 3.179 | 3.33 | RELIABILITY | MINOR WIDENING(O) | Widen Watterson Trail from 2 to 3 lanes from Ruckriegel Parkway to Maple Road and widen Watterson Trail from 2 to 3 lanes from Old Taylorsville Road to Ruckriegel Parkway. Project to include streetscape enhancements to improve the corridor. | R |  | SLO | 2019 | 195226 | 156181 |  |  |  | 39045 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; UPDATE FISCAL YEAR FROM 2019 TO 2020; MOD |  |  | JEFFERSON | 5-518 | CR 1004H | 0.151 | 3.179 | 3.33 | RELIABILITY | MINOR WIDENING(O) | Widen Watterson Trail from 2 to 3 lanes from Ruckriegel Parkway to Maple Road and widen Watterson Trail from 2 to 3 lanes from Old Taylorsville Road to Ruckriegel Parkway. Project to include streetscape enhancements to improve the corridor. | R |  | STP | 2020 | 195226 | 156181 |  |  |  | 39045 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; UPDATE FISCAL YEAR; MOD |  |  | JEFFERSON | 5-518 | CR 1004H | 0.151 | 3.179 | 3.33 | RELIABILITY | MINOR WIDENING(O) | Widen Watterson Trail from 2 to 3 lanes from Ruckriegel Parkway to Maple Road and widen Watterson Trail from 2 to 3 lanes from Old Taylorsville Road to Ruckriegel Parkway. Project to include streetscape enhancements to improve the corridor. | R |  | STP | 2022 | 195226 | 156181 |  |  |  | 39045 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.315 | 2021-06-25 | TIP FY 20-25, ADMIN MOD#18; UPDATE FISCAL YEAR; MOD |  |  | JEFFERSON | 5-518 | CR 1004H | 0.151 | 3.179 | 3.33 | RELIABILITY | MINOR WIDENING(O) | Widen Watterson Trail from 2 to 3 lanes from Ruckriegel Parkway to Maple Road and widen Watterson Trail from 2 to 3 lanes from Old Taylorsville Road to Ruckriegel Parkway. Project to include streetscape enhancements to improve the corridor. | R |  | STP | 2021 | 195226 | 156181 |  |  |  | 39045 |  |  |  |  | 0
TIP | [9 empty] | JEFFERSON | 5-518 | CR 1004H | 0.151 | 3.179 | 3.33 | RELIABILITY | MINOR WIDENING(O) | Widen Watterson Trail from 2 to 3 lanes from Ruckriegel Parkway to Maple Road and widen Watterson Trail from 2 to 3 lanes from Old Taylorsville Road to Ruckriegel Parkway. Project to include streetscape enhancements to improve the corridor. | U |  | SLO | 2019 | 440000 | 352000 |  |  |  | 88000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; UPDATE FISCAL YEAR FROM 2019 TO 2020; MOD |  |  | JEFFERSON | 5-518 | CR 1004H | 0.151 | 3.179 | 3.33 | RELIABILITY | MINOR WIDENING(O) | Widen Watterson Trail from 2 to 3 lanes from Ruckriegel Parkway to Maple Road and widen Watterson Trail from 2 to 3 lanes from Old Taylorsville Road to Ruckriegel Parkway. Project to include streetscape enhancements to improve the corridor. | U |  | STP | 2020 | 440000 | 352000 |  |  |  | 88000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; UPDATE FISCAL YEAR; MOD |  |  | JEFFERSON | 5-518 | CR 1004H | 0.151 | 3.179 | 3.33 | RELIABILITY | MINOR WIDENING(O) | Widen Watterson Trail from 2 to 3 lanes from Ruckriegel Parkway to Maple Road and widen Watterson Trail from 2 to 3 lanes from Old Taylorsville Road to Ruckriegel Parkway. Project to include streetscape enhancements to improve the corridor. | U |  | STP | 2022 | 440000 | 352000 |  |  |  | 88000 |  |  |  |  | 0
TIP | [9 empty] | JEFFERSON | 5-518 | CR 1004H | 0.151 | 3.179 | 3.33 | RELIABILITY | MINOR WIDENING(O) | Widen Watterson Trail from 2 to 3 lanes from Ruckriegel Parkway to Maple Road and widen Watterson Trail from 2 to 3 lanes from Old Taylorsville Road to Ruckriegel Parkway. Project to include streetscape enhancements to improve the corridor. | C |  | SLO | 2019 | 1540000 | 1232000 |  |  |  | 308000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; UPDATE FISCAL YEAR FROM 2019 TO 2020; MOD |  |  | JEFFERSON | 5-518 | CR 1004H | 0.151 | 3.179 | 3.33 | RELIABILITY | MINOR WIDENING(O) | Widen Watterson Trail from 2 to 3 lanes from Ruckriegel Parkway to Maple Road and widen Watterson Trail from 2 to 3 lanes from Old Taylorsville Road to Ruckriegel Parkway. Project to include streetscape enhancements to improve the corridor. | C |  | STP | 2020 | 1540000 | 1232000 |  |  |  | 308000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; UPDATE FISCAL YEAR; MOD |  |  | JEFFERSON | 5-518 | CR 1004H | 0.151 | 3.179 | 3.33 | RELIABILITY | MINOR WIDENING(O) | Widen Watterson Trail from 2 to 3 lanes from Ruckriegel Parkway to Maple Road and widen Watterson Trail from 2 to 3 lanes from Old Taylorsville Road to Ruckriegel Parkway. Project to include streetscape enhancements to improve the corridor. | C |  | STP | 2023 | 1540000 | 1232000 |  |  |  | 308000 |  |  |  |  | 0
TIP | [9 empty] | Jefferson | 5-518 | CR 1004H | 0.151 | 3.179 | 3.33 | RELIABILITY | MINOR WIDENING(O) | Widen Watterson Trail from 2 to 3 lanes from Ruckriegel Parkway to Maple Road and widen Watterson Trail from 2 to 3 lanes from Old Taylorsville Road to Ruckriegel Parkway. Project to include streetscape enhancements to improve the corridor. | D |  | SLO | 2019 | 134774 | 107819 |  |  |  | 26955 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.117 | 2019-08-09 | TIP FY 18-21, ADMIN MOD#34; UPDATE FUND TYPE FROM SLO TO TAP; MOD (SEE TAP SPREADSHEET) |  |  | Jefferson | 5-518 | CR 1004H | 0.151 | 3.179 | 3.33 | RELIABILITY | MINOR WIDENING(O) | Widen Watterson Trail from 2 to 3 lanes from Ruckriegel Parkway to Maple Road and widen Watterson Trail from 2 to 3 lanes from Old Taylorsville Road to Ruckriegel Parkway. Project to include streetscape enhancements to improve the corridor. | D |  | TAP | [11 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.122 | 2019-08-26 | TIP FY 18-21, ADMIN MOD#35; UPDATE FUND TYPE FROM TAP TO SLO FUNDS; MOD |  |  | Jefferson | 5-518 | CR 1004H | 0.151 | 3.179 | 3.33 | RELIABILITY | MINOR WIDENING(O) | Widen Watterson Trail from 2 to 3 lanes from Ruckriegel Parkway to Maple Road and widen Watterson Trail from 2 to 3 lanes from Old Taylorsville Road to Ruckriegel Parkway. Project to include streetscape enhancements to improve the corridor. | D |  | SLO | 2019 | 134774 | 107819 |  |  |  | 26955 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; UPDATE FISCAL YEAR FROM 2019 TO 2020; MOD | STPM | 3001489 | Jefferson | 5-518 | CR 1004H | 0.151 | 3.179 | 3.33 | RELIABILITY | MINOR WIDENING(O) | Widen Watterson Trail from 2 to 3 lanes from Ruckriegel Parkway to Maple Road and widen Watterson Trail from 2 to 3 lanes from Old Taylorsville Road to Ruckriegel Parkway. Project to include streetscape enhancements to improve the corridor. | D |  | STP | 2020 | 134774 | 107819 |  |  |  | 26955 |  | OBLIGATED | 107819 |  | 107819 | 2020 | 2ND QUARTER | CITY OF JEFFERSONTOWN
STIP | [9 empty] | JEFFERSON | 5-521 | I 64 |  | 1.387 | 1.891 | ASSET MANAGEMENT | AM-BRIDGE (P) | REPAIR DRAINAGE SYSTEM ON THE I-64 BRIDGE OVER N.S. RAILROAD AND THE LEVEE AND REPAIR THE LEVEE.(056B00284N)(2014BOP)(SD) | C |  | BR/NH | 2020 | 400000 | 248000 |  |  | 152000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.122 | 2019-08-26 | TIP FY 18-21, ADMIN MOD#35; UPDATE FUND TYPE FROM TAP TO SLO FUNDS; MOD |  |  | JEFFERSON | 5-522 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | Design and construct shared use path and Louisville Loop trailhead facilities through Jefferson Memorial Forest from north end of sand quarry tunnel at Gene Synder FWY to west terminus of the existing MSD trail approximately 2.7 miles which will include a bridge over Pond Creek. | [14 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.057 | 2019-04-23 | TIP FY 18-21, ADMIN MOD#29; ADD D PHASE TO STIP; NEW |  |  | JEFFERSON | 5-523 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | Design and construct shared use path and Louisville Loop trailhead facilities through Jefferson Memorial Forest from Blevins Gap Road to north end of sand quarry tunnel at Gene Snyder Freeway (the tunnel will be part of this segment), approximately 2.5 miles. | D |  | SLO | 2019 | 323517 | 258814 |  |  |  | 64703 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.117 | 2019-08-09 | TIP FY 18-21, ADMIN MOD#34; UPDATE FUND TYPE FROM SLO TO TAP; MOD (SEE TAP SPREADSHEET) |  |  | JEFFERSON | 5-523 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | Design and construct shared use path and Louisville Loop trailhead facilities through Jefferson Memorial Forest from Blevins Gap Road to north end of sand quarry tunnel at Gene Snyder Freeway (the tunnel will be part of this segment), approximately 2.5 miles. | D
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.122 | 2019-08-26 | TIP FY 18-21, ADMIN MOD#35; UPDATE FUND TYPE FROM TAP TO SLO FUNDS; MOD |  |  | JEFFERSON | 5-523 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | Design and construct shared use path and Louisville Loop trailhead facilities through Jefferson Memorial Forest from Blevins Gap Road to north end of sand quarry tunnel at Gene Snyder Freeway (the tunnel will be part of this segment), approximately 2.5 miles. | D |  | SLO | 2019 | 323517 | 258814 |  |  |  | 64703 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; UPDATE FISCAL YEAR FROM 2019 TO 2020; MOD |  |  | JEFFERSON | 5-523 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | Design and construct shared use path and Louisville Loop trailhead facilities through Jefferson Memorial Forest from Blevins Gap Road to north end of sand quarry tunnel at Gene Snyder Freeway (the tunnel will be part of this segment), approximately 2.5 miles. | D |  | STP | 2020 | 323517 | 258814 |  |  |  | 64703 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.186 | 2020-05-06 | TIP FY 20-25, ADMIN MOD#2; UPDATE FUND AMOUNT; MOD |  |  | JEFFERSON | 5-523 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | Design and construct shared use path and Louisville Loop trailhead facilities through Jefferson Memorial Forest from Blevins Gap Road to north end of sand quarry tunnel at Gene Snyder Freeway (the tunnel will be part of this segment), approximately 2.5 miles. | D |  | STP | 2020 | 989768 | 791814 |  |  |  | 197954 |  |  |  |  | 0
TIP | [9 empty] | JEFFERSON | 5-523 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | Design and construct shared use path and Louisville Loop trailhead facilities through Jefferson Memorial Forest from Blevins Gap Road to north end of sand quarry tunnel at Gene Snyder Freeway (the tunnel will be part of this segment), approximately 2.5 miles. | R |  | SLO | 2019 | 68750 | 55000 |  |  |  | 13750 |  |  |  |  | 0
TIP | [9 empty] | JEFFERSON | 5-523 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | Design and construct shared use path and Louisville Loop trailhead facilities through Jefferson Memorial Forest from Blevins Gap Road to north end of sand quarry tunnel at Gene Snyder Freeway (the tunnel will be part of this segment), approximately 2.5 miles. | U |  | SLO | 2019 | 453660 | 393660 |  |  |  | 60000 |  |  |  |  | 0
TIP | [9 empty] | JEFFERSON | 5-523 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | Design and construct shared use path and Louisville Loop trailhead facilities through Jefferson Memorial Forest from Blevins Gap Road to north end of sand quarry tunnel at Gene Snyder Freeway (the tunnel will be part of this segment), approximately 2.5 miles. | C |  | SLO | 2019 | 2500000 | 2000000 |  |  |  | 500000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.057 | 2019-04-26 | TIP FY 18-21, ADMIN MOD#29; ADD D PHASE TO STIP; NEW |  |  | JEFFERSON | 5-524 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | Design and construct shared use path and Louisville Loop trailhead facilities through Jefferson Memorial Forest from Pendleton Road at Medora Road to the beginning of Jefferson Memorial Forest property on Blevins Gap Road, approximately 1.3 miles. | D |  | SLO | 2019 | 183536 | 146829 |  |  |  | 36707 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.117 | 2019-08-09 | TIP FY 18-21, ADMIN MOD#34; UPDATE FUND TYPE FROM SLO TO TAP; MOD ( SEE TAP SPREADSHEET) |  |  | JEFFERSON | 5-524 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | Design and construct shared use path and Louisville Loop trailhead facilities through Jefferson Memorial Forest from Pendleton Road at Medora Road to the beginning of Jefferson Memorial Forest property on Blevins Gap Road, approximately 1.3 miles. | D
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.122 | 2019-08-26 | TIP FY 18-21, ADMIN MOD#35; UPDATE FUND TYPE FROM TAP TO SLO FUNDS; MOD | STPM | 3001457 | JEFFERSON | 5-524 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | Design and construct shared use path and Louisville Loop trailhead facilities through Jefferson Memorial Forest from Pendleton Road at Medora Road to the beginning of Jefferson Memorial Forest property on Blevins Gap Road, approximately 1.3 miles. | D |  | SLO | 2019 | 183536 | 146829 |  |  |  | 36707 |  | OBLIGATED | 146829 |  | 146829 | 2020 | 1ST QUARTER | LOUISVILLE METRO
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; UPDATE FISCAL YEAR FROM 2019 TO 2020; MOD | STPM | 3001457 | JEFFERSON | 5-524 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | Design and construct shared use path and Louisville Loop trailhead facilities through Jefferson Memorial Forest from Pendleton Road at Medora Road to the beginning of Jefferson Memorial Forest property on Blevins Gap Road, approximately 1.3 miles. | D |  | STP | 2020 | 183536 | 146829 |  |  |  | 36707 |  | OBLIGATED | 146829 |  | 146829 | 2020 | 1ST QUARTER | LOUISVILLE METRO
TIP | [9 empty] | JEFFERSON | 5-524 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | Design and construct shared use path and Louisville Loop trailhead facilities through Jefferson Memorial Forest from Pendleton Road at Medora Road to the beginning of Jefferson Memorial Forest property on Blevins Gap Road, approximately 1.3 miles. | U |  | SLO | 2019 | 120000 | 100000 |  |  |  | 20000 |  |  |  |  | 0
TIP | [9 empty] | JEFFERSON | 5-524 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | Design and construct shared use path and Louisville Loop trailhead facilities through Jefferson Memorial Forest from Pendleton Road at Medora Road to the beginning of Jefferson Memorial Forest property on Blevins Gap Road, approximately 1.3 miles. | C |  | SLO | 2019 | 1250000 | 1000000 |  |  |  | 250000 |  |  |  |  | 0
STIP | [9 empty] | JEFFERSON | 5-525 | KY 2841 |  | 0.03 | 0.4 | RELIABILITY | MATCHED FED FUNDS(O) | NORTHEAST LOUISVILLE LOOP SECTION II. CONSTRUCT A SHARED USE PATH ALONG US 60 FROM EASTWOOD CUTOFF TO EASTWOOD RECREATION CENTER. (METRO PARKS PROJECT) (2014BOP) | R |  | SLO | 2019 | 533333 | 426666.4 |  |  |  | 106666.6 |  |  |  |  | 0
TIP | [6 empty] | TIP AND STIP AMOUNTS ARE DIFFERENT |  |  | JEFFERSON | 5-525 | KY 2841 |  | 0.03 | 0.4 | RELIABILITY | MATCHED FED FUNDS(O) | Design and construct a shared-use path system from Eastwood Cut Off Road to Eastwood Recreation Center (16300 Eastwood Cut Off). | R |  | SLO | 2018 | 404085 | 323268 |  |  |  | 80817 |  |  |  |  | 0
STIP | [9 empty] | JEFFERSON | 5-525 | KY 2841 |  | 0.03 | 0.4 | RELIABILITY | MATCHED FED FUNDS(O) | NORTHEAST LOUISVILLE LOOP SECTION II. CONSTRUCT A SHARED USE PATH ALONG US 60 FROM EASTWOOD CUTOFF TO EASTWOOD RECREATION CENTER. (METRO PARKS PROJECT) (2014BOP) | U |  | SLO | 2020 | 45000 | 36000 |  |  |  | 9000 |  |  |  |  | 0
TIP | [6 empty] | TIP AND STIP AMOUNTS ARE DIFFERENT |  |  | JEFFERSON | 5-525 | KY 2841 |  | 0.03 | 0.4 | RELIABILITY | MATCHED FED FUNDS(O) | Design and construct a shared-use path system from Eastwood Cut Off Road to Eastwood Recreation Center (16300 Eastwood Cut Off). | U |  | SLO | 2020 | 56250 | 45000 |  |  |  | 11250 |  |  |  |  | 0
STIP | [9 empty] | JEFFERSON | 5-525 | KY 2841 |  | 0.03 | 0.4 | RELIABILITY | MATCHED FED FUNDS(O) | NORTHEAST LOUISVILLE LOOP SECTION II. CONSTRUCT A SHARED USE PATH ALONG US 60 FROM EASTWOOD CUTOFF TO EASTWOOD RECREATION CENTER. (METRO PARKS PROJECT) (2014BOP) | C |  | SLO | 2021 | 825081 | 660065 |  |  |  | 165016 |  |  |  |  | 0
STIP | [9 empty] | JEFFERSON | 5-529 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | CONSTRUCT A MULTI-USE PATH THROUGH A.B. SAWYER PARK AND CONNECTING TO SURROUNDING NEIGHBORHOODS INCLUDING AN UNDERPASS, BRIDGE AND SIT AMENITIES, AND CONSTRUCTION OF PEDESTRIAN FACILITIES ALONG HURTSBORNE PARKWAY FROM MIDDLE FORK OF BEARGRASS CREEK BRIDGE TO ORMSBY STATION ROAD. | R |  | SLO | 2019 | 300000 | 300000 |  |  |  | 0 |  |  |  |  | 0
|  |  |  | ADMINISTRATIVE MODIFICATION | 2018.117 | 2019-08-09 | TIP FY 18-21; ADMIN MOD#34, UPDATE FUND TYPE FROM SLO TO TAP; MOD (SEE TAP SPREADSHEET) | STPM | 3001468 | JEFFERSON | 5-529 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | CONSTRUCT A MULTI-USE PATH THROUGH A.B. SAWYER PARK AND CONNECTING TO SURROUNDING NEIGHBORHOODS INCLUDING AN UNDERPASS, BRIDGE AND SIT AMENITIES, AND CONSTRUCTION OF PEDESTRIAN FACILITIES ALONG HURTSBORNE PARKWAY FROM MIDDLE FORK OF BEARGRASS CREEK BRIDGE TO ORMSBY STATION ROAD. | R | [13 empty] | 0
STIP | [9 empty] | JEFFERSON | 5-529 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | CONSTRUCT A MULTI-USE PATH THROUGH A.B. SAWYER PARK AND CONNECTING TO SURROUNDING NEIGHBORHOODS INCLUDING AN UNDERPASS, BRIDGE AND SIT AMENITIES, AND CONSTRUCTION OF PEDESTRIAN FACILITIES ALONG HURTSBORNE PARKWAY FROM MIDDLE FORK OF BEARGRASS CREEK BRIDGE TO ORMSBY STATION ROAD. | U |  | SLO | 2019 | 30000 | 30000 |  |  |  | 0 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; UPDATE FISCAL YEAR FROM 2019 TO 2020; MOD |  |  | JEFFERSON | 5-529 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | CONSTRUCT A MULTI-USE PATH THROUGH A.B. SAWYER PARK AND CONNECTING TO SURROUNDING NEIGHBORHOODS INCLUDING AN UNDERPASS, BRIDGE AND SIT AMENITIES, AND CONSTRUCTION OF PEDESTRIAN FACILITIES ALONG HURTSBORNE PARKWAY FROM MIDDLE FORK OF BEARGRASS CREEK BRIDGE TO ORMSBY STATION ROAD. | U |  | STP | 2020 | 30000 | 30000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; UPDATE FISCAL YEAR & FUND AMOUNTS; MOD |  |  | JEFFERSON | 5-529 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | CONSTRUCT A MULTI-USE PATH THROUGH A.B. SAWYER PARK AND CONNECTING TO SURROUNDING NEIGHBORHOODS INCLUDING AN UNDERPASS, BRIDGE AND SIT AMENITIES, AND CONSTRUCTION OF PEDESTRIAN FACILITIES ALONG HURTSBORNE PARKWAY FROM MIDDLE FORK OF BEARGRASS CREEK BRIDGE TO ORMSBY STATION ROAD. | U |  | STP | 2021 | 37500 | 30000 |  |  | 7500 | [5 empty] | 0
STIP | [9 empty] | JEFFERSON | 5-529 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | CONSTRUCT A MULTI-USE PATH THROUGH A.B. SAWYER PARK AND CONNECTING TO SURROUNDING NEIGHBORHOODS INCLUDING AN UNDERPASS, BRIDGE AND SIT AMENITIES, AND CONSTRUCTION OF PEDESTRIAN FACILITIES ALONG HURTSBORNE PARKWAY FROM MIDDLE FORK OF BEARGRASS CREEK BRIDGE TO ORMSBY STATION ROAD. | C |  | SLO | 2019 | 1500000 | 1200000 |  |  |  | 300000 |  |  |  |  | 0
TIP | [6 empty] | TIP AND STIP AMOUNTS ARE DIFFERENT |  |  | JEFFERSON | 5-529 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | CONSTRUCT A MULTI-USE PATH THROUGH A.B. SAWYER PARK AND CONNECTING TO SURROUNDING NEIGHBORHOODS INCLUDING AN UNDERPASS, BRIDGE AND SIT AMENITIES, AND CONSTRUCTION OF PEDESTRIAN FACILITIES ALONG HURTSBORNE PARKWAY FROM MIDDLE FORK OF BEARGRASS CREEK BRIDGE TO ORMSBY STATION ROAD. | C |  | SLO | 2020 | 1500000 | 1500000 |  |  |  | 0 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.057 | 2019-04-26 | TIP FY 18-21, ADMIN MOD#29; UPDATE FUND AMOUNTS; MOD |  |  | JEFFERSON | 5-529 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | CONSTRUCT A MULTI-USE PATH THROUGH A.B. SAWYER PARK AND CONNECTING TO SURROUNDING NEIGHBORHOODS INCLUDING AN UNDERPASS, BRIDGE AND SIT AMENITIES, AND CONSTRUCTION OF PEDESTRIAN FACILITIES ALONG HURTSBORNE PARKWAY FROM MIDDLE FORK OF BEARGRASS CREEK BRIDGE TO ORMSBY STATION ROAD. | C |  | SLO | 2020 | 2300000 | 2300000 |  |  |  | 0 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; UPDATE FISCAL YEAR; MOD |  |  | JEFFERSON | 5-529 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | CONSTRUCT A MULTI-USE PATH THROUGH A.B. SAWYER PARK AND CONNECTING TO SURROUNDING NEIGHBORHOODS INCLUDING AN UNDERPASS, BRIDGE AND SIT AMENITIES, AND CONSTRUCTION OF PEDESTRIAN FACILITIES ALONG HURTSBORNE PARKWAY FROM MIDDLE FORK OF BEARGRASS CREEK BRIDGE TO ORMSBY STATION ROAD. | C |  | SLO | 2021 | 2300000 | 2300000 |  |  |  | 0 |  |  |  |  | 0
TIP | [9 empty] | Jefferson | 5-531 | KY 1932 |  | 5.523 | 6.59 | RELIABILITY | MATCHED FED FUNDS(O) | Improve the safety and congestion of KY 1932 (Chenoweth Lane) from US 60 (Shelbyville Road) to US 42 (Brownsboro Road), approximately 1.07 miles. From MP 5.523 to MP 6.590. | R |  | SLO | 2019 | 707000 | 707000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; UPDATE FISCAL YEAR FROM 2019 TO 2020; MOD |  |  | Jefferson | 5-531 | KY 1932 |  | 5.523 | 6.59 | RELIABILITY | MATCHED FED FUNDS(O) | Improve the safety and congestion of KY 1932 (Chenoweth Lane) from US 60 (Shelbyville Road) to US 42 (Brownsboro Road), approximately 1.07 miles. From MP 5.523 to MP 6.590. | R |  | STP | 2020 | 707000 | 707000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.227 | 2020-08-31 | TIP FY 20-25, ADMIN MOD#8; UPDATE FUND AMOUNTS; MOD |  |  | Jefferson | 5-531 | KY 1932 |  | 5.523 | 6.59 | RELIABILITY | MATCHED FED FUNDS(O) | Improve the safety and congestion of KY 1932 (Chenoweth Lane) from US 60 (Shelbyville Road) to US 42 (Brownsboro Road), approximately 1.07 miles. From MP 5.523 to MP 6.590. | R |  | STP | 2020 | 943250 | 896000 |  |  |  | 47250 |  |  |  |  | 0
TIP | [9 empty] | Jefferson | 5-531 | KY 1932 |  | 5.523 | 6.59 | RELIABILITY | MATCHED FED FUNDS(O) | Improve the safety and congestion of KY 1932 (Chenoweth Lane) from US 60 (Shelbyville Road) to US 42 (Brownsboro Road), approximately 1.07 miles. From MP 5.523 to MP 6.590. | D |  | SLO | 2019 | 650000 | 650000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; UPDATE FISCAL YEAR FROM 2019 TO 2020; MOD |  |  | Jefferson | 5-531 | KY 1932 |  | 5.523 | 6.59 | RELIABILITY | MATCHED FED FUNDS(O) | Improve the safety and congestion of KY 1932 (Chenoweth Lane) from US 60 (Shelbyville Road) to US 42 (Brownsboro Road), approximately 1.07 miles. From MP 5.523 to MP 6.590. | D |  | STP | 2020 | 650000 | 650000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.194 | 2020-05-29 | TIP FY 20-25, ADMIN MOD#3; ADD THE U PHASE TO THE STIP; NEW |  |  | Jefferson | 5-531 | KY 1932 |  | 5.523 | 6.59 | RELIABILITY | MATCHED FED FUNDS(O) | Improve the safety and congestion of KY 1932 (Chenoweth Lane) from US 60 (Shelbyville Road) to US 42 (Brownsboro Road), approximately 1.07 miles. From MP 5.523 to MP 6.590. | U |  | STP | 2023 | 625000 | 625000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25; ADMIN MOD#10; UDPATE FISCAL YEAR & FUND AMOUNTS; MOD |  |  | Jefferson | 5-531 | KY 1932 |  | 5.523 | 6.59 | RELIABILITY | MATCHED FED FUNDS(O) | Improve the safety and congestion of KY 1932 (Chenoweth Lane) from US 60 (Shelbyville Road) to US 42 (Brownsboro Road), approximately 1.07 miles. From MP 5.523 to MP 6.590. | U |  | STP | 2021 | 705000 | 705000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25; ADMIN MOD#10; ADD C PHASE TO STIP; NEW |  |  | Jefferson | 5-531 | KY 1932 |  | 5.523 | 6.59 | RELIABILITY | MATCHED FED FUNDS(O) | Improve the safety and congestion of KY 1932 (Chenoweth Lane) from US 60 (Shelbyville Road) to US 42 (Brownsboro Road), approximately 1.07 miles. From MP 5.523 to MP 6.590. | C |  | STP | 2024 | 1940000 | 1940000 | [8 empty] | 0
TIP | [6 empty] | NOT IN STIP |  |  | Jefferson | 5-535 | Sidewalk Connections on US 60, KY 1747 & KY 22 | [5 empty] | Installation of sidewalks to fix gaps in pedestrian network on US 60 (Shelbyville Road) , KY 1747 (Westport Road), and KY 22 (Brownsboro Road). Includes: westbound US 60 from end of U of L trail to Eden Avenue MP 7.717 to MP7.734, westbound US 60 from Daventry Lane to Wildwood Lane MP 7.966 to MP 8.051, eastbound US 60 from Wildwood Lane to Cambridge Station Frontage Road MP 8.062 to MP 8.241, eastbound US 60 from Dorsey Lane to Country Squire Florist entrance MP 8.535 to MP 8.641, southbound KY 1747 from Hurstbourne Trace to Eden Avenue MP 13.635 to MP 13.869, and eastbound KY 22 from Paul's Fruit Market to Herr Lane MP 0.370 to MP 0.432. | C |  | SLO | 2018 | 63458 | 63458 | [8 empty] | 0
TIP | [6 empty] | NOT IN STIP |  |  | Jefferson | 5-535 | Sidewalk Connections on US 60, KY 1747 & KY 22 | [5 empty] | Installation of sidewalks to fix gaps in pedestrian network on US 60 (Shelbyville Road) , KY 1747 (Westport Road), and KY 22 (Brownsboro Road). Includes: westbound US 60 from end of U of L trail to Eden Avenue MP 7.717 to MP7.734, westbound US 60 from Daventry Lane to Wildwood Lane MP 7.966 to MP 8.051, eastbound US 60 from Wildwood Lane to Cambridge Station Frontage Road MP 8.062 to MP 8.241, eastbound US 60 from Dorsey Lane to Country Squire Florist entrance MP 8.535 to MP 8.641, southbound KY 1747 from Hurstbourne Trace to Eden Avenue MP 13.635 to MP 13.869, and eastbound KY 22 from Paul's Fruit Market to Herr Lane MP 0.370 to MP 0.432. | C |  | SLO | 2019 | 26542 | 26542 | [8 empty] | 0
STIP | [7 empty] | STPM | 8776031 | JEFFERSON | 5-536 | KY 1931 |  | 3.148 | 4.887 | RELIABILITY | MINOR WIDENING(O) | WIDEN KY 1931 (ST. ANDREWS CHURCH ROAD) FROM TWO TO THREE LANES FROM US 31W (DIXIE HIGHWAY) TO DOSS HIGH SCHOOL. THIS PROJECT WILL INCLUDE BICYCLE AND PEDESTRIAN FACILITIES. FROM MP 3.148 TO MP 4.887. | R |  | SLO | 2019 | 3000000 | 2400000 |  |  |  | 600000 |  | OBLIGATED | 1860000 | 1780000 | 3640000 | 2019 | 3RD QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; MOVE $1,220,000 (FEDERAL) OF THE $3,000,000 (FEDERAL) FROM FY 2019 TO FY 2020; MOD | STPM | 8776031 | JEFFERSON | 5-536 | KY 1931 |  | 3.148 | 4.887 | RELIABILITY | MINOR WIDENING(O) | WIDEN KY 1931 (ST. ANDREWS CHURCH ROAD) FROM TWO TO THREE LANES FROM US 31W (DIXIE HIGHWAY) TO DOSS HIGH SCHOOL. THIS PROJECT WILL INCLUDE BICYCLE AND PEDESTRIAN FACILITIES. FROM MP 3.148 TO MP 4.887. | R |  | STP | 2020 | 3000000 | 1220000 | [5 empty] | OBLIGATED | 1860000 | 1780000 | 3640000 | 2019 | 3RD QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; UDPATE FISCAL YEAR; MOD |  |  | JEFFERSON | 5-536 | KY 1931 |  | 3.148 | 4.887 | RELIABILITY | MINOR WIDENING(O) | WIDEN KY 1931 (ST. ANDREWS CHURCH ROAD) FROM TWO TO THREE LANES FROM US 31W (DIXIE HIGHWAY) TO DOSS HIGH SCHOOL. THIS PROJECT WILL INCLUDE BICYCLE AND PEDESTRIAN FACILITIES. FROM MP 3.148 TO MP 4.887. | R |  | STP | 2021 | 1220000 | 1220000 | [8 empty] | 0
STIP | [7 empty] | STPM | 8776031 | JEFFERSON | 5-536 | KY 1931 |  | 3.148 | 4.887 | RELIABILITY | MINOR WIDENING(O) | WIDEN KY 1931 (ST. ANDREWS CHURCH ROAD) FROM TWO TO THREE LANES FROM US 31W (DIXIE HIGHWAY) TO DOSS HIGH SCHOOL. THIS PROJECT WILL INCLUDE BICYCLE AND PEDESTRIAN FACILITIES. FROM MP 3.148 TO MP 4.887. | U |  | SLO | 2019 | 6000000 | 4800000 |  |  |  | 1200000 |  | OBLIGATED |  | 6000000 | 6000000 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; ADD C PHASE TO STIP; NEW |  |  | JEFFERSON | 5-536 | KY 1931 |  | 3.148 | 4.887 | RELIABILITY | MINOR WIDENING(O) | WIDEN KY 1931 (ST. ANDREWS CHURCH ROAD) FROM TWO TO THREE LANES FROM US 31W (DIXIE HIGHWAY) TO DOSS HIGH SCHOOL. THIS PROJECT WILL INCLUDE BICYCLE AND PEDESTRIAN FACILITIES. FROM MP 3.148 TO MP 4.887. | C |  | STP | 2025 | 10780000 | 10780000 | [8 empty] | 0
STIP | YES | [8 empty] | JEFFERSON | 5-537 | I 265 | 11.318 | 23.409 | 34.727 | RELIABILITY | MAJOR WIDENING(O) | SIX LANE PRIORITY SECTION OF I-265 BETWEEN TAYLORSVILLE ROAD AND I-71. | D |  | NH | 2019 | 5800000 | 5800000 |  |  | 0 | [5 empty] | 0
STIP | YES | [6 empty] | NHPPIM | 2653040 | JEFFERSON | 5-537 | I 265 | 11.318 | 23.409 | 34.727 | RELIABILITY | MAJOR WIDENING(O) | SIX LANE PRIORITY SECTION OF I-265 BETWEEN TAYLORSVILLE ROAD AND I-71. | R |  | NH | 2020 | 1580000 | 1580000 |  |  | 0 |  |  | OBLIGATED | 25000 |  | 25000 | 2019 | 4TH QUARTER
STIP | YES | [8 empty] | JEFFERSON | 5-537 | I 265 | 11.318 | 23.409 | 34.727 | RELIABILITY | MAJOR WIDENING(O) | SIX LANE PRIORITY SECTION OF I-265 BETWEEN TAYLORSVILLE ROAD AND I-71. | U |  | NH | 2020 | 2080000 | 2080000 |  |  | 0 | [5 empty] | 0
STIP | YES | [8 empty] | JEFFERSON | 5-537 | I 265 | 11.318 | 23.409 | 34.727 | RELIABILITY | MAJOR WIDENING(O) | SIX LANE PRIORITY SECTION OF I-265 BETWEEN TAYLORSVILLE ROAD AND I-71. | C |  | NH | 2022 | 15000000 | 12000000 |  |  | 3000000 | [5 empty] | 0
TIP | [6 empty] | TIP and STIP Items numbers are different |  |  | Jefferson | 5-537.00 5-537.01 5-537.02 | I-265 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | Widen I-265 (Gene Snyder Freeway) from 4 to 6 lanes from Taylorsville Road to I-71. Approximately 11.3 miles. From MP 23.409 to MP 34.727. | R |  | NHS | 2021 | 1580000 | 1580000 | [8 empty] | 0
TIP | [6 empty] | TIP and STIP Items numbers are different |  |  | Jefferson | 5-537.00 5-537.01 5-537.02 | I-265 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | Widen I-265 (Gene Snyder Freeway) from 4 to 6 lanes from Taylorsville Road to I-71. Approximately 11.3 miles. From MP 23.409 to MP 34.727. | D |  | NHS | 2018 | 5800000 | 5800000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.057 | 2019-04-26 | TIP FY 18-21, ADMIN MOD#29; KIPDA ID 958; ADD R PHASE TO STIP FOR FY 2019; NEW |  |  | Jefferson | 5-537.00 5-537.01 5-537.02 | I-265 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | SIX LANE PRIORITY SECTION OF I-265 BETWEEN TAYLORSVILLE ROAD AND I-71. APPROXIMATELY 11.3 MILES. FROM MP 23.409 TO MP 34.727. PROJECT DESIGN WILL EVALUATE WIDENING FROM 4 TO 6 LANES AS A POTENTIAL SOLUTION TO THE CONGESTION. | R |  | NHS | 2019 | 300000 | 300000 | [8 empty] | 0
TIP | [6 empty] | TIP and STIP Items numbers are different |  |  | Jefferson | 5-537.00 5-537.01 5-537.02 | I-265 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | Widen I-265 (Gene Snyder Freeway) from 4 to 6 lanes from Taylorsville Road to I-71. Approximately 11.3 miles. From MP 23.409 to MP 34.727. | R |  | NHS | 2020 | 1580000 | 1580000 | [8 empty] | 0
TIP | [6 empty] | TIP and STIP Items numbers are different |  |  | Jefferson | 5-537.00 5-537.01 5-537.02 | I-265 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | Widen I-265 (Gene Snyder Freeway) from 4 to 6 lanes from Taylorsville Road to I-71. Approximately 11.3 miles. From MP 23.409 to MP 34.727. | U |  | NHS | 2020 | 2080000 | 2000000 | [8 empty] | 0
TIP | [6 empty] | TIP and STIP Items numbers are different |  |  | Jefferson | 5-537.00 5-537.01 5-537.02 | I-265 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | Widen I-265 (Gene Snyder Freeway) from 4 to 6 lanes from Taylorsville Road to I-71. Approximately 11.3 miles. From MP 23.409 to MP 34.727. | U |  | NHS | 2021 | 2080000 | 2080000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.057 | 2019-04-26 | TIP FY 18-21, ADMIN MOD#29; KIPDA ID 958 ADD C PHASE TO STIP & UPDATE DESCRIPTION; NEW |  |  | Jefferson | 5-537.00 5-537.01 5-537.02 | I-265 |  | 23.409 | 34.727 | RELIABILITY | MAJOR WIDENING(O) | SIX LANE PRIORITY SECTION OF I-265 BETWEEN TAYLORSVILLE ROAD AND I-71. APPROXIMATELY 11.3 MILES. FROM MP 23.409 TO MP 34.727. PROJECT DESIGN WILL EVALUATE WIDENING FROM 4 TO 6 LANES AS A POTENTIAL SOLUTION TO THE CONGESTION. | C |  | NH | 2020 | 20000000 | 20000000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.057 | 2019-04-26 | TIP FY 18-21, ADMIN MOD#29;KIPDA ID 958 CONSTRUCTION FUNDS FOR FY 2021; MOD |  |  | Jefferson | 5-537.00 5-537.01 5-537.02 | I-265 |  | 23.409 | 34.727 | RELIABILITY | MAJOR WIDENING(O) | SIX LANE PRIORITY SECTION OF I-265 BETWEEN TAYLORSVILLE ROAD AND I-71. APPROXIMATELY 11.3 MILES. FROM MP 23.409 TO MP 34.727. PROJECT DESIGN WILL EVALUATE WIDENING FROM 4 TO 6 LANES AS A POTENTIAL SOLUTION TO THE CONGESTION. | C |  | NH | 2021 | 20000000 | 20000000 | [8 empty] | 0
STIP | YES | [8 empty] | JEFFERSON | 5-537.01 | I 265 | 11.318 | 23.409 | 34.727 | RELIABILITY | PREFINANCD CONVRSN(O) | SIX LANE PRIORITY SECTION OF I-265 BETWEEN TAYLORSVILLE ROAD AND I-71. | R |  | NH | 2021 | 1580000 | 1264000 |  |  | 316000 | [5 empty] | 0
STIP | YES | [8 empty] | JEFFERSON | 5-537.01 | I 265 | 11.318 | 23.409 | 34.727 | RELIABILITY | PREFINANCD CONVRSN(O) | SIX LANE PRIORITY SECTION OF I-265 BETWEEN TAYLORSVILLE ROAD AND I-71. | U |  | NH | 2021 | 2080000 | 1664000 |  |  | 416000 | [5 empty] | 0
STIP | YES | [8 empty] | JEFFERSON | 5-539 | I 71 |  | 8.6 | 9.5 | RELIABILITY | RECONSTRUCTION(O) | PROVIDE COLLECTOR-DISTRIBUTOR LANE ON SOUTHBOUND I-71 TO FACILITATE RAMP MOVEMENTS TO AND FROM I-265. | C |  | NH | 2019 | 5400000 | 5400000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.057 | 2019-04-26 | TIP FY 18-21, ADMIN MOD#29; UPDATE FISCAL YEAR FROM 2019 TO 2020; MOD |  |  | JEFFERSON | 5-539 | I 71 |  | 8.6 | 9.5 | RELIABILITY | RECONSTRUCTION(O) | PROVIDE COLLECTOR-DISTRIBUTOR LANE ON SOUTHBOUND I-71 TO FACILITATE RAMP MOVEMENTS TO AND FROM I-265. | C |  | NH | 2020 | 5400000 | 5400000 | [8 empty] | 0
STIP | [9 empty] | JEFFERSON | 5-543 | CS 1002H |  | 2.474 | 2.927 | RELIABILITY | MATCHED FED FUNDS(O) | CONSTRUCT A TRAIL ALONG BLUEGRASS PARKWAY FROM WATTERSON TRAIL TO CAMPUS PLACE AND ALONG CAMPUS PLACE FROM BLUEGRASS PARKWAY TO PLANTSIDE DRIVE. THE TRAIL WILL BE EITHER ASPHALT OR CONCRETE SEPARATED MULTI-USE PATH, 8-10 FEET WIDE. | C |  | SLO | 2019 | 1300000 | 1040000 |  |  |  | 260000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; UPDATE FISCAL YEAR FROM 2019 TO 2020; MOD |  |  | JEFFERSON | 5-543 | CS 1002H |  | 2.474 | 2.927 | RELIABILITY | MATCHED FED FUNDS(O) | CONSTRUCT A TRAIL ALONG BLUEGRASS PARKWAY FROM WATTERSON TRAIL TO CAMPUS PLACE AND ALONG CAMPUS PLACE FROM BLUEGRASS PARKWAY TO PLANTSIDE DRIVE. THE TRAIL WILL BE EITHER ASPHALT OR CONCRETE SEPARATED MULTI-USE PATH, 8-10 FEET WIDE. | C |  | STP | 2020 | 1300000 | 1040000 |  |  |  | 260000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.186 | 2020-05-06 | TIP FY 20-25, ADMIN MOD#2; UPDATE PROJECT DESCRIPTION AND FUND AMOUNTS; MOD |  |  | JEFFERSON | 5-543 | CS 1002H |  | 2.474 | 2.927 | RELIABILITY | MATCHED FED FUNDS(O) | Construct a 10 foot wide multi-use bicycle/pedestrian trail along one side of Bluegrass Parkway from Watterson Trail to Campus Place and along Campus Place from Bluegrass Parkway to Plantside Drive. The trail will be constructed with concrete. Project length is 1.61 miles. | C |  | STP | 2020 | 1887500 | 1510000 |  |  |  | 377500 |  |  |  |  | 0
STIP | [9 empty] | Jefferson | 5-543 | CS 1002H |  | 2.474 | 2.927 | RELIABILITY | MATCHED FED FUNDS(O) | CONSTRUCT A TRAIL ALONG BLUEGRASS PARKWAY FROM WATTERSON TRAIL TO CAMPUS PLACE AND ALONG CAMPUS PLACE FROM BLUEGRASS PARKWAY TO PLANTSIDE DRIVE. THE TRAIL WILL BE EITHER ASPHALT OR CONCRETE SEPARATED MULTI-USE PATH, 8-10 FEET WIDE. | D |  | SLO | 2019 | 115000 | 5000 |  |  |  | 110000 |  |  |  |  | 0
STIP | [9 empty] | Jefferson | 5-549.00 5-549.01 | I-265 | [5 empty] | Reconstruction of the I-265/I-64 interchange (2016BOP) from MP 24.6 to MP 26.4. Project will evaluate a Spill Thru Flyover Interchange configuration as a potential solution to eliminate all four weaving segments of the existing interchange. | C |  | NHS | 2020 | 10000000 | 10000000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.001 | 2018-12-06 | TIP FY 18-21; AMENDMENT#3; CHANGE DESCRIPTION; MOD |  |  | JEFFERSON | 5-549.00 5-549.01 | I-265 |  |  |  | RELIABILITY | I-CHANGE RECONST(O) | RECONSTRUCTION OF THE I-265/I-64 INTERCHANGE. FROM MP 24.6 TO MP 26.4. PROJECT WILL EVALUATE A SPILL THRU FLYOVER INTERCHANGE CONFIGURATION AS A POTENTIAL SOLUTION TO ELIMINATE ALL FOUR WEAVING SEGMENTS OF THE EXISTING INTERCHANGE. | C |  | NHS | 2020 | 10000000 | 10000000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.057 | 2019-04-26 | TIP FY 18-21, ADMIN MOD#29; UPDATE FUND AMOUNTS; MOD |  |  | JEFFERSON | 5-549.00 5-549.01 | I-265 |  |  |  | RELIABILITY | I-CHANGE RECONST(O) | RECONSTRUCTION OF THE I-265/I-64 INTERCHANGE. FROM MP 24.6 TO MP 26.4. PROJECT WILL EVALUATE A SPILL THRU FLYOVER INTERCHANGE CONFIGURATION AS A POTENTIAL SOLUTION TO ELIMINATE ALL FOUR WEAVING SEGMENTS OF THE EXISTING INTERCHANGE. | C |  | NHS | 2020 | 8500000 | 8500000 | [8 empty] | 0
STIP | [9 empty] | Jefferson | 5-549.00 5-549.01 | I-265 | [5 empty] | Reconstruction of the I-265/I-64 interchange (2016BOP) from MP 24.6 to MP 26.4. Project will evaluate a Spill Thru Flyover Interchange configuration as a potential solution to eliminate all four weaving segments of the existing interchange. | D |  | NHS | 2018 | 1000000 | 1000000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.001 | 2018-12-06 | TIP FY 18-21; AMENDMENT#3; CHANGE DESCRIPTION & UPDATE FUND AMOUNTS; MOD |  |  | Jefferson | 5-549.00 5-549.01 | I-265 |  |  |  | RELIABILITY | I-CHANGE RECONST(O) | RECONSTRUCTION OF THE I-265/I-64 INTERCHANGE. FROM MP 24.6 TO MP 26.4. PROJECT WILL EVALUATE A SPILL THRU FLYOVER INTERCHANGE CONFIGURATION AS A POTENTIAL SOLUTION TO ELIMINATE ALL FOUR WEAVING SEGMENTS OF THE EXISTING INTERCHANGE. | D |  | NHS | 2018 | 1000000 | 1000000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.057 | 2019-04-26 | TIP FY 18-21, ADMIN MOD#29; UPDATE FUND AMOUNTS; MOD |  |  | Jefferson | 5-549.00 5-549.01 | I-265 |  |  |  | RELIABILITY | I-CHANGE RECONST(O) | RECONSTRUCTION OF THE I-265/I-64 INTERCHANGE. FROM MP 24.6 TO MP 26.4. PROJECT WILL EVALUATE A SPILL THRU FLYOVER INTERCHANGE CONFIGURATION AS A POTENTIAL SOLUTION TO ELIMINATE ALL FOUR WEAVING SEGMENTS OF THE EXISTING INTERCHANGE. | D |  | NHS | 2018 | 1460000 | 1460000 | [8 empty] | 0
STIP | [9 empty] | Jefferson | 5-549.00 5-549.01 | I-265 | [5 empty] | Reconstruction of the I-265/I-64 interchange (2016BOP) from MP 24.6 to MP 26.4. Project will evaluate a Spill Thru Flyover Interchange configuration as a potential solution to eliminate all four weaving segments of the existing interchange. | R |  | NHS | 2019 | 1000000 | 1000000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.001 | 2018-12-06 | TIP FY 18-21; AMENDMENT#3; CHANGE DESCRIPTION; MOD | NHPPIM | 0642196 | Jefferson | 5-549.00 5-549.01 | I-265 |  |  |  | RELIABILITY | I-CHANGE RECONST(O) | RECONSTRUCTION OF THE I-265/I-64 INTERCHANGE. FROM MP 24.6 TO MP 26.4. PROJECT WILL EVALUATE A SPILL THRU FLYOVER INTERCHANGE CONFIGURATION AS A POTENTIAL SOLUTION TO ELIMINATE ALL FOUR WEAVING SEGMENTS OF THE EXISTING INTERCHANGE. | R |  | NHS | 2019 | 1000000 | 1000000 | [5 empty] | OBLIGATED |  | 300000 | 300000 | 2019 | 4TH QUARTER
STIP | [9 empty] | Jefferson | 5-549.00 5-549.01 | I-265 | [5 empty] | Reconstruction of the I-265/I-64 interchange (2016BOP) from MP 24.6 to MP 26.4. Project will evaluate a Spill Thru Flyover Interchange configuration as a potential solution to eliminate all four weaving segments of the existing interchange. | U |  | NHS | 2019 | 1000000 | 1000000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.001 | 2018-12-06 | TIP FY 18-21; AMENDMENT#3; CHANGE DESCRIPTION; MOD |  |  | Jefferson | 5-549.00 5-549.01 | I-265 |  |  |  | RELIABILITY | I-CHANGE RECONST(O) | RECONSTRUCTION OF THE I-265/I-64 INTERCHANGE. FROM MP 24.6 TO MP 26.4. PROJECT WILL EVALUATE A SPILL THRU FLYOVER INTERCHANGE CONFIGURATION AS A POTENTIAL SOLUTION TO ELIMINATE ALL FOUR WEAVING SEGMENTS OF THE EXISTING INTERCHANGE. | U |  | NHS | 2019 | 1000000 | 1000000 | [8 empty] | 0
STIP | [9 empty] | Jefferson | 5-549.00 5-549.01 | I-265 | [5 empty] | Reconstruction of the I-265/I-64 interchange (2016BOP) from MP 24.6 to MP 26.4. Project will evaluate a Spill Thru Flyover Interchange configuration as a potential solution to eliminate all four weaving segments of the existing interchange. | C |  | NHS | 2021 | 15000000 | 15000000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.001 | 2018-12-06 | TIP FY 18-21; AMENDMENT#3; CHANGE DESCRIPTION; MOD |  |  | Jefferson | 5-549.00 5-549.01 | I-265 |  |  |  | RELIABILITY | I-CHANGE RECONST(O) | RECONSTRUCTION OF THE I-265/I-64 INTERCHANGE. FROM MP 24.6 TO MP 26.4. PROJECT WILL EVALUATE A SPILL THRU FLYOVER INTERCHANGE CONFIGURATION AS A POTENTIAL SOLUTION TO ELIMINATE ALL FOUR WEAVING SEGMENTS OF THE EXISTING INTERCHANGE. | C |  | NHS | 2021 | 15000000 | 15000000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.057 | 2019-04-26 | TIP FY 18-21, ADMIN MOD#29; UPDATE FUND AMOUNTS; MOD |  |  | Jefferson | 5-549.00 5-549.01 | I-265 |  |  |  | RELIABILITY | I-CHANGE RECONST(O) | RECONSTRUCTION OF THE I-265/I-64 INTERCHANGE. FROM MP 24.6 TO MP 26.4. PROJECT WILL EVALUATE A SPILL THRU FLYOVER INTERCHANGE CONFIGURATION AS A POTENTIAL SOLUTION TO ELIMINATE ALL FOUR WEAVING SEGMENTS OF THE EXISTING INTERCHANGE. | C |  | NHS | 2021 | 8500000 | 8500000 | [8 empty] | 0
STIP | [9 empty] | Jefferson | 5-549.00 5-549.01 | I-265 | [5 empty] | Reconstruction of the I-265/I-64 interchange (2016BOP) from MP 24.6 to MP 26.4. Project will evaluate a Spill Thru Flyover Interchange configuration as a potential solution to eliminate all four weaving segments of the existing interchange. | D |  | IM | 2018 | 1460000 | 1460000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.001 | 2018-12-06 | TIP FY 18-21; AMENDMENT#3; CHANGE DESCRIPTION; MOD |  |  | Jefferson | 5-549.00 5-549.01 | I-265 |  |  |  | RELIABILITY | I-CHANGE RECONST(O) | RECONSTRUCTION OF THE I-265/I-64 INTERCHANGE. FROM MP 24.6 TO MP 26.4. PROJECT WILL EVALUATE A SPILL THRU FLYOVER INTERCHANGE CONFIGURATION AS A POTENTIAL SOLUTION TO ELIMINATE ALL FOUR WEAVING SEGMENTS OF THE EXISTING INTERCHANGE. | D |  | IM | 2018 | 1460000 | 1460000 | [8 empty] | 0
STIP | YES | [8 empty] | JEFFERSON | 5-549.01 | I 265 | 3.7 | 24.6 | 26.4 | RELIABILITY | I-CHANGE RECONST(O) | RECONSTRUCTION OF THE I-265/I-64 INTERCHANGE. (2016BOP) | C |  | NH | 2021 | 15000000 | 12000000 |  |  | 3000000 | [5 empty] | 0
STIP | YES | [6 empty] | NHPPIM | 0642199 | JEFFERSON | 5-553 | I 64 | 7.171 | 5.104 | 12.275 | RELIABILITY | CONGESTION MITIGTN(O) | IMPROVEMENTS WITHIN THE I-64 CORRIDOR FROM THE KENNEDY INTERCHANGE TO I-264 (WATTERSON EXPRESSWAY) ADDRESSING SAFETY AND CONGESTION ISSUES. THE IMPROVEMENTS MAY INCLUDE BUT ARE NOT LIMITED TO: CONSIDERATION OF ALTERNATIVE TRANSPORTATION MODES, DEPLOYMENT | P |  | NH | 2019 | 250000 | 250000 |  |  | 0 |  |  | OBLIGATED | 375000 |  | 375000 | 2019 | 4TH QUARTER
STIP | YES | [5 empty] | NOT IN TIP |  |  | JEFFERSON | 5-553 | I 64 | 7.171 | 5.104 | 12.275 | RELIABILITY | CONGESTION MITIGTN(O) | IMPROVEMENTS WITHIN THE I-64 CORRIDOR FROM THE KENNEDY INTERCHANGE TO I-264 (WATTERSON EXPRESSWAY) ADDRESSING SAFETY AND CONGESTION ISSUES. THE IMPROVEMENTS MAY INCLUDE BUT ARE NOT LIMITED TO: CONSIDERATION OF ALTERNATIVE TRANSPORTATION MODES, DEPLOYMENT | D |  | NH | 2022 | 2550000 | 2040000 |  |  | 510000 | [5 empty] | 0
STIP | YES | [8 empty] | JEFFERSON | 5-554 | I 265 | 7.05 | 10.25 | 17.3 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE SAFETY AND REDUCE CONGESTION ON I-265 FROM I-65 TO US-31E. | P |  | NH | 2021 | 1000000 | 800000 |  |  | 200000 | [5 empty] | 0
STIP | YES | [6 empty] | NHPP | 8725011 | JEFFERSON | 5-555 | KY 1747 | 1.495 | 10.5 | 11.995 | RELIABILITY | CONGESTION MITIGTN(O) | REDUCE CONGESTION AND IMPROVE SAFETY ALONG KY-1747 (HURSTBOURNE PARKWAY) FROM STONY BROOK DRIVE TO I-64. | P |  | NH | 2019 | 250000 | 250000 |  |  | 0 |  |  | OBLIGATED |  | 250000 | 250000 | 2019 | 4TH QUARTER
STIP | YES | [8 empty] | JEFFERSON | 5-557 | I 71 | 4 | 5 | 9 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE SAFETY AND REDUCE CONGESTION ON I-71 FROM I-264 TO I-265. | P |  | NH | 2019 | 2000000 | 2000000 |  |  | 0 | [5 empty] | 0
STIP | YES | [5 empty] | NOT IN TIP | NHPPIM | 0711123 | JEFFERSON | 5-557 | I 71 | 4 | 5 | 9 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE SAFETY AND REDUCE CONGESTION ON I-71 FROM I-264 TO I-265. | D |  | NH | 2022 | 3000000 | 2400000 |  |  | 600000 |  |  | OBLIGATED | 2000000 |  | 2000000 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFCATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; ADD PROJECT TO STIP; NEW |  |  | JEFFERSON | 5-558 | I 265 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | IMPROVE SAFETY AND REDUCE CONGESTION ON I-265 FROM US-31E (BARDSTOWN RD) TO KY-155 (TAYLORSVILLE RD). | D |  | NH | 2023 | 7500000 | 6000000 |  |  | 1500000 | [5 empty] | 0
STIP | YES | [6 empty] | NHPPIM | 0655122 | JEFFERSON | 5-559 | I 65 | 2.298 | 129.289 | 131.587 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE SAFETY AND REDUCE CONGESTION AT THE I-65/I-264 (WATTERSON EXPRESSWAY) INTERCHANGE. | P |  | NH | 2019 | 500000 | 500000 |  |  | 0 |  |  | OBLIGATED |  | 500000 | 500000 | 2019 | 2ND QUARTER
STIP | YES | [8 empty] | JEFFERSON | 5-559 | I 65 | 2.298 | 129.289 | 131.587 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE SAFETY AND REDUCE CONGESTION AT THE I-65/I-264 (WATTERSON EXPRESSWAY) INTERCHANGE. | D |  | NH | 2021 | 3000000 | 2400000 |  |  | 600000 | [5 empty] | 0
TIP | YES | [5 empty] | TIP AND STIP AMOUNTS ARE DIFFERENT |  |  | JEFFERSON | 5-559.01 | I 65 | 2.298 | 129.289 | 131.587 | RELIABILITY | PREFINANCD CONVRSN(O) | IMPROVE SAFETY AND REDUCE CONGESTION AT THE I-65/I-264 (WATTERSON EXPRESSWAY) INTERCHANGE. | D |  | NH | 2022 | 3000000 | 3000000 |  |  | 0 | [5 empty] | 0
STIP | YES | [8 empty] | JEFFERSON | 5-560 | I 65 | 1 | 124.7 | 125.7 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE SAFETY AND REDUCE CONGESTION AT THE I-65/I-265 (GENE SNYDER FREEWAY) INTERCHANGE. | P |  | NH | 2021 | 400000 | 320000 |  |  | 80000 | [5 empty] | 0
TIP | [9 empty] | JEFFERSON | 5-561 | US 42 |  | 0 | 0.056 | RELIABILITY | RECONSTRUCTION(O) | INTERSECTION RE-BUILD AT MAIN STREET/ STORY AVENUE / BAXTER AVENUE INCLUDING TRANSITIONS BETWEEN WENTZEL STREET TO THE WEST AND JOHNSON STREET TO THE EAST.(18CCR) | D |  | SLO | 2019 | 220000 | 176000 |  |  |  | 44000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.186 | 2020-05-06 | TIP FY 20-25, ADMIN MOD#2; CHANGE STATE ITEM# FROM 5-561 TO 5-758; MOD |  |  | JEFFERSON |  | US 42 |  | 0 | 0.056 | RELIABILITY | RECONSTRUCTION(O) | INTERSECTION RE-BUILD AT MAIN STREET/ STORY AVENUE / BAXTER AVENUE INCLUDING TRANSITIONS BETWEEN WENTZEL STREET TO THE WEST AND JOHNSON STREET TO THE EAST.(18CCR) | D |  | SLO | 2019 | 220000 | 176000 |  |  |  | 44000 |  |  |  |  | 0
TIP | [9 empty] | JEFFERSON | 5-561 | US 42 |  | 0 | 0.056 | RELIABILITY | RECONSTRUCTION(O) | INTERSECTION RE-BUILD AT MAIN STREET/ STORY AVENUE / BAXTER AVENUE INCLUDING TRANSITIONS BETWEEN WENTZEL STREET TO THE WEST AND JOHNSON STREET TO THE EAST.(18CCR) | U |  | SLO | 2019 | 220000 | 176000 |  |  |  | 44000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.186 | 2020-05-06 | TIP FY 20-25, ADMIN MOD#2; CHANGE STATE ITEM# FROM 5-561 TO 5-758; MOD |  |  | JEFFERSON |  | US 42 |  | 0 | 0.056 | RELIABILITY | RECONSTRUCTION(O) | INTERSECTION RE-BUILD AT MAIN STREET/ STORY AVENUE / BAXTER AVENUE INCLUDING TRANSITIONS BETWEEN WENTZEL STREET TO THE WEST AND JOHNSON STREET TO THE EAST.(18CCR) | U |  | SLO | 2019 | 220000 | 176000 |  |  |  | 44000 |  |  |  |  | 0
TIP | [9 empty] | JEFFERSON | 5-561 | US 42 |  | 0 | 0.056 | RELIABILITY | RECONSTRUCTION(O) | INTERSECTION RE-BUILD AT MAIN STREET/ STORY AVENUE / BAXTER AVENUE INCLUDING TRANSITIONS BETWEEN WENTZEL STREET TO THE WEST AND JOHNSON STREET TO THE EAST.(18CCR) | C |  | SLO | 2021 | 4142899 | 3314319 |  |  |  | 828580 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.186 | 2020-05-06 | TIP FY 20-25, ADMIN MOD#2; CHANGE STATE ITEM# FROM 5-561 TO 5-758; MOD |  |  | JEFFERSON |  | US 42 |  | 0 | 0.056 | RELIABILITY | RECONSTRUCTION(O) | INTERSECTION RE-BUILD AT MAIN STREET/ STORY AVENUE / BAXTER AVENUE INCLUDING TRANSITIONS BETWEEN WENTZEL STREET TO THE WEST AND JOHNSON STREET TO THE EAST.(18CCR) | C |  | SLO | 2019 | 4142899 | 3314319 |  |  |  | 828580 |  |  |  |  | 0
STIP | [9 empty] | JEFFERSON | 5-562 |  |  |  |  | RELIABILITY | SCOPING STUDY DD (O) | A COMPREHENSIVE OPERATIONAL ANALYSIS (COA) TO ANALYZE AND EVALUATE EXISTING TARC SERVICE IN COMPARISON WITH COMMUNITY GROWTH, ECONOMIC AND LAND USE DEVELOPMENT, AND CURRENT AND FUTURE NEEDS OF PUBLIC TRANSIT USERS. | P |  | SLO | 2019 | 354000 | 283200 |  |  |  | 70800 |  |  |  |  | 0
TIP | [6 empty] | TIP AND STIP AMOUNTS ARE DIFFERENT |  |  | JEFFERSON | 5-562 |  |  |  |  | RELIABILITY | SCOPING STUDY DD (O) | A COMPREHENSIVE OPERATIONAL ANALYSIS (COA) TO ANALYZE AND EVALUATE EXISTING TARC SERVICE IN COMPARISON WITH COMMUNITY GROWTH, ECONOMIC AND LAND USE DEVELOPMENT, AND CURRENT AND FUTURE NEEDS OF PUBLIC TRANSIT USERS. | P |  | SLO | 2018 | 442500 | 354000 |  |  |  | 88500 |  |  |  |  | 0
STIP | [9 empty] | JEFFERSON | 5-563 | KY 2049 |  | 0.514 | 1.72 | RELIABILITY | SCOPING STUDY DD (O) | PLANNING STUDY:EXAMINE NEED FOR BICYCLE/PED/VEHICULAR ACCESS IMPROVEMENTS TO PROPOSED DIXIE BRT IN CORRIDORS: KY 907 FR US 31W TO STONESTREET RD, ROCKFORD LN FR CANE RUN RD TO US 31W, GAGEL AVE FR US 31W TO MANSLICK RD & CRUMS LN FR I-264 TO MANSLICK RD. | P |  | SLO | 2019 | 352000 | 281600 |  |  |  | 70400 |  |  |  |  | 0
[8 empty] | STPM | 3001542 | JEFFERSON | 5-571 | CR 1010 |  | 1.65 | 1.934 | SAFETY | BIKE/PED FACIL(O) | INSTALL NEW ADA COMPLIANT 5' SIDEWALK ALONG STONY BROOK DRIVE FROM STARA WAY TO KIRBY LANE (2018BOP). | D |  | STP | 2020 | [7 empty] | OBLIGATED | 44000 |  | 44000 | 2020 | 2ND QUARTER | LOUISVILLE METRO
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; ADD DESIGN PHASE TO STIP; NEW |  |  | JEFFERSON | 5-758 | Main Street/Story Avenue Intersection | [5 empty] | Intersection rebuild at Main Street/Story Avenue/Baxter Avenue including transitions between Wentzel Street to the west and Johnson Street to the east, taking an unsignalized intersection that accomodates three one-way segments and transforming it into a more traditional four-legged intersection; including a new traffic signal, lane markings, crosswalks and related lane-assignment signage. | D |  | STP | 2020 | 100000 | 100000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.186 | 2020-05-06 | TIP FY 20-25, ADMIN MOD#2; CHANGE STATE ITEM# FROM 5-561 TO 5-758; MOD |  |  | JEFFERSON | 5-758 | US 42 |  | 0 | 0.056 | RELIABILITY | RECONSTRUCTION(O) | INTERSECTION RE-BUILD AT MAIN STREET/ STORY AVENUE / BAXTER AVENUE INCLUDING TRANSITIONS BETWEEN WENTZEL STREET TO THE WEST AND JOHNSON STREET TO THE EAST.(18CCR) | D |  | SLO | 2019 | 220000 | 176000 |  |  |  | 44000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; UPDATE FISCAL YEAR & FUND AMOUNTS; MOD |  |  | JEFFERSON | 5-758 | US 42 |  | 0 | 0.056 | RELIABILITY | RECONSTRUCTION(O) | INTERSECTION RE-BUILD AT MAIN STREET/ STORY AVENUE / BAXTER AVENUE INCLUDING TRANSITIONS BETWEEN WENTZEL STREET TO THE WEST AND JOHNSON STREET TO THE EAST.(18CCR) | D |  | SLO | 2020 | 125000 | 100000 |  |  | 25000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.186 | 2020-05-06 | TIP FY 20-25, ADMIN MOD#2; CHANGE STATE ITEM# FROM 5-561 TO 5-758; MOD |  |  | JEFFERSON | 5-758 | US 42 |  | 0 | 0.056 | RELIABILITY | RECONSTRUCTION(O) | INTERSECTION RE-BUILD AT MAIN STREET/ STORY AVENUE / BAXTER AVENUE INCLUDING TRANSITIONS BETWEEN WENTZEL STREET TO THE WEST AND JOHNSON STREET TO THE EAST.(18CCR) | U |  | SLO | 2019 | 220000 | 176000 |  |  |  | 44000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; ADD RIGHT OF WAY PHASE TO STIP; NEW |  |  | JEFFERSON | 5-758 | US 42 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | INTERSECTION RE-BUILD AT MAIN STREET/ STORY AVENUE / BAXTER AVENUE INCLUDING TRANSITIONS BETWEEN WENTZEL STREET TO THE WEST AND JOHNSON STREET TO THE EAST.(18CCR) | R |  | STP | 2020 | 76000 | 76000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; UPDATE FISCAL YEAR & FUND AMOUNTS; MOD |  |  | JEFFERSON |  | US 42 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | INTERSECTION RE-BUILD AT MAIN STREET/ STORY AVENUE / BAXTER AVENUE INCLUDING TRANSITIONS BETWEEN WENTZEL STREET TO THE WEST AND JOHNSON STREET TO THE EAST.(18CCR) | R |  | STP | 2021 | 95000 | 76000 |  |  | 19000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.186 | 2020-05-06 | TIP FY 20-25, ADMIN MOD#2; CHANGE STATE ITEM# FROM 5-561 TO 5-758; MOD |  |  | JEFFERSON | 5-758 | US 42 |  | 0 | 0.056 | RELIABILITY | RECONSTRUCTION(O) | INTERSECTION RE-BUILD AT MAIN STREET/ STORY AVENUE / BAXTER AVENUE INCLUDING TRANSITIONS BETWEEN WENTZEL STREET TO THE WEST AND JOHNSON STREET TO THE EAST.(18CCR) | C |  | SLO | 2019 | 4142899 | 3314319 |  |  |  | 828580 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; UPDATE FISCAL YEAR; MOD |  |  | JEFFERSON | 5-758 | US 42 |  | 0 | 0.056 | RELIABILITY | RECONSTRUCTION(O) | INTERSECTION RE-BUILD AT MAIN STREET/ STORY AVENUE / BAXTER AVENUE INCLUDING TRANSITIONS BETWEEN WENTZEL STREET TO THE WEST AND JOHNSON STREET TO THE EAST.(18CCR) | C |  | SLO | 2022 | 4142899 | 3314319 |  |  | 828580 | [5 empty] | 0
TIP | [6 empty] | Not in STIP |  |  | Jefferson | 5-759 | KY 146 Sidewalks in Eastern Jefferson County | [5 empty] | Improve pedestrian connectivity along KY 146 from Saddlecreek Drive to the existing sidewalk near the Oldham County line. | R |  | SLO | 2019 | 100000 | 100000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; UPDATE FISCAL YEAR FROM 2019 TO 2020; MOD |  |  | Jefferson | 5-759 | KY 146 Sidewalks in Eastern Jefferson County |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | Improve pedestrian connectivity along KY 146 from Saddlecreek Drive to the existing sidewalk near the Oldham County line. | R |  | STP | 2020 | 100000 | 100000 | [8 empty] | 0
TIP | [6 empty] | Not in STIP |  |  | Jefferson | 5-759 | KY 146 Sidewalks in Eastern Jefferson County | [5 empty] | Improve pedestrian connectivity along KY 146 from Saddlecreek Drive to the existing sidewalk near the Oldham County line. | U |  | SLO | 2020 | 100000 | 100000 | [8 empty] | 0
TIP | [6 empty] | Not in STIP |  |  | Jefferson | 5-759 | KY 146 Sidewalks in Eastern Jefferson County | [5 empty] | Improve pedestrian connectivity along KY 146 from Saddlecreek Drive to the existing sidewalk near the Oldham County line. | D |  | SLO | 2018 | 200000 | 200000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.107 | 2019-07-26 | TIP FY 18-21, ADMIN MOD#33; ADD C PHASE TO STIP; NEW |  |  | Jefferson | 5-759 | KY 146 Sidewalks in Eastern Jefferson County |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | Improve pedestrian connectivity along KY 146 from Saddlecreek Drive to the existing sidewalk near the Oldham County line. | C |  | SLO | 2021 | 250000 | 250000 |  |  |  | 0 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.153 | 2019-12-13 | TIP FY 18-21, ADMIN MOD#39; UPDATE FISCAL YEAR FROM 2021 TO 2020; MOD |  | 8718014 | Jefferson | 5-759 | KY 146 Sidewalks in Eastern Jefferson County |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | Improve pedestrian connectivity along KY 146 from Saddlecreek Drive to the existing sidewalk near the Oldham County line. | C |  | SLO | 2020 | 250000 | 250000 | [5 empty] | OBLIGATED | 92920 |  | 92920 | 2020 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.275 | 2021-02-04 | TIP FY 20-25, ADMIN MOD#12; UPDATE FISCAL YEAR; MOD |  | 8718014 | Jefferson | 5-759 | KY 146 Sidewalks in Eastern Jefferson County |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | Improve pedestrian connectivity along KY 146 from Saddlecreek Drive to the existing sidewalk near the Oldham County line. | C |  | SLO | 2021 | 250000 | 200000 |  |  | 50000 | [5 empty] | 0
STIP | YES | [8 empty] | JEFFERSON | 5-804 | I 264 | 1.7 | 20.9 | 22.6 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT/WIDEN I-264 (WATTERSON EXPRESSWAY) FROM WESTPORT ROAD (KY-1447) TO I-71, INCLUDING THE US-42 INTERCHANGE AS A SPUI.(PROJECT INCLUDES 5-594) (12CCR)(14CCR) | R |  | NH | 2021 | 5280000 | 4224000 |  |  | 1056000 | [5 empty] | 0
STIP | YES | [8 empty] | JEFFERSON | 5-804 | I 264 | 1.7 | 20.9 | 22.6 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT/WIDEN I-264 (WATTERSON EXPRESSWAY) FROM WESTPORT ROAD (KY-1447) TO I-71, INCLUDING THE US-42 INTERCHANGE AS A SPUI.(PROJECT INCLUDES 5-594) (12CCR)(14CCR) | U |  | NH | 2021 | 1270000 | 1016000 |  |  | 254000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; ADD C PHASE FOR FY 2023 TO STIP; NEW |  |  | JEFFERSON | 5-804 | I 264 | 1.7 | 20.9 | 22.6 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT/WIDEN I-264 (WATTERSON EXPRESSWAY) FROM WESTPORT ROAD (KY-1447) TO I-71, INCLUDING THE US-42 INTERCHANGE AS A SPUI.(PROJECT INCLUDES 5-594) (12CCR)(14CCR) | C |  | NH | 2023 | 15000000 | 12000000 |  |  | 3000000 | [5 empty] | 0
|  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; ADD C PHASE FOR FY 2024 TO STIP; NEW |  |  | JEFFERSON | 5-804 | I 264 | 1.7 | 20.9 | 22.6 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT/WIDEN I-264 (WATTERSON EXPRESSWAY) FROM WESTPORT ROAD (KY-1447) TO I-71, INCLUDING THE US-42 INTERCHANGE AS A SPUI.(PROJECT INCLUDES 5-594) (12CCR)(14CCR) | C |  | NH | 2023 | 20000000 | 16000000 |  |  | 4000000 | [5 empty] | 0
STIP | YES | [8 empty] | JEFFERSON | 5-808 | KY 155 | 0.6 | 4.4 | 5 | SAFETY | DESIGN ENGINEERING(O) | SAFETY PROJECT FOR RECONSTRUCTION OF TAYLORSVILLE ROAD AND SOUTH POPE LICK ROAD INTERSECTION AND BRIDGE OVER POPE LICK CREEK. (2016BOP) | R |  | STP | 2019 | 180000 | 180000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.271 | 2021-01-12 | TIP FY 20-25, AMEND#2; UPDATE FISCAL YEAR & FUND AMOUNT; MOD |  |  | JEFFERSON | 5-808 | KY 155 | 0.6 | 4.4 | 5 | SAFETY | DESIGN ENGINEERING(O) | SAFETY PROJECT FOR RECONSTRUCTION OF TAYLORSVILLE ROAD AND SOUTH POPE LICK ROAD INTERSECTION AND BRIDGE OVER POPE LICK CREEK. (2016BOP) | R |  | STP | 2021 | 180000 | 144000 |  |  | 36000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.275 | 2021-02-04 | TIP FY 20-25, ADMIN MOD#12; UPDATE FUND AMOUNTS; MOD |  |  | JEFFERSON | 5-808 | KY 155 | 0.6 | 4.4 | 5 | SAFETY | DESIGN ENGINEERING(O) | SAFETY PROJECT FOR RECONSTRUCTION OF TAYLORSVILLE ROAD AND SOUTH POPE LICK ROAD INTERSECTION AND BRIDGE OVER POPE LICK CREEK. (2016BOP) | R |  | STP | 2021 | 650000 | 520000 |  |  | 130000 | [5 empty] | 0
STIP | YES | [8 empty] | JEFFERSON | 5-808 | KY 155 | 0.6 | 4.4 | 5 | SAFETY | DESIGN ENGINEERING(O) | SAFETY PROJECT FOR RECONSTRUCTION OF TAYLORSVILLE ROAD AND SOUTH POPE LICK ROAD INTERSECTION AND BRIDGE OVER POPE LICK CREEK. (2016BOP) | U |  | STP | 2019 | 150000 | 150000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.271 | 2021-01-12 | TIP FY 20-25, AMEND#2; UPDATE FISCAL YEAR & FUND AMOUNT; MOD |  |  | JEFFERSON | 5-808 | KY 155 | 0.6 | 4.4 | 5 | SAFETY | DESIGN ENGINEERING(O) | SAFETY PROJECT FOR RECONSTRUCTION OF TAYLORSVILLE ROAD AND SOUTH POPE LICK ROAD INTERSECTION AND BRIDGE OVER POPE LICK CREEK. (2016BOP) | U |  | STP | 2021 | 150000 | 120000 |  |  | 30000 | [5 empty] | 0
STIP | YES | [8 empty] | JEFFERSON | 5-808 | KY 155 | 0.6 | 4.4 | 5 | SAFETY | DESIGN ENGINEERING(O) | SAFETY PROJECT FOR RECONSTRUCTION OF TAYLORSVILLE ROAD AND SOUTH POPE LICK ROAD INTERSECTION AND BRIDGE OVER POPE LICK CREEK. (2016BOP) | C |  | STP | 2019 | 1800000 | 1800000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.271 | 2021-01-12 | TIP FY 20-25, AMEND#2; UPDATE FISCAL YEAR & FUND AMOUNT; MOD |  |  | JEFFERSON | 5-808 | KY 155 | 0.6 | 4.4 | 5 | SAFETY | DESIGN ENGINEERING(O) | SAFETY PROJECT FOR RECONSTRUCTION OF TAYLORSVILLE ROAD AND SOUTH POPE LICK ROAD INTERSECTION AND BRIDGE OVER POPE LICK CREEK. (2016BOP) | C |  | STP | 2023 | 5000000 | 4000000 |  |  | 1000000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.226 | 2020-08-28 | TIP FY 20-25, ADMIN MOD#7, ADD PROJECT TO STIP; NEW |  |  | JEFFERSON | 5-938 | I-264 |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | UPGRADE PAVEMENT MARKINGS ALONG I-264 FROM KY 864 TO I-71. | C |  | NHPP | 2021 | 900000 | 900000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.29 | 2021-04-01 | TIP FY 20-25, ADMIN MOD#14; ADD PROJECT TO STIP; NEW |  |  | JEFFERSON | 5-941 | KY 1819 |  | 12.4 | 12.6 | RELIABILITY | SAFETY-HAZARD ELIM(P) | Installation of High Friction Surface Treatment on KY 1819 from MP 12.4 to MP 12.6 in Jefferson County, KY. | C |  | SAF | 2021 | 41000 | 36900 |  |  | 4100 | [5 empty] | 0
STIP | [6 empty] | NOT IN TIP |  |  | JEFFERSON | 5-965.16 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | DEDICATED FEDERAL AID STP FUNDS EARMARKED FOR LOUISVILLE URBANIZED AREA AND SUBJECT TO MPO CONTROL FOR FY 2018 (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C |  | SLO | 2019 | 24007000 | 19205600 |  |  |  | 4801400 |  |  |  |  | 0
STIP | [6 empty] | NOT IN TIP |  |  | JEFFERSON | 5-965.19 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | DEDICATED FEDERAL AID STP FUNDS EARMARKED FOR LOUISVILLE URBANIZED AREA AND SUBJECT TO MPO CONTROL FOR FY 2021. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | C |  | SLO | 2021 | 11670000 | 9336000 |  |  |  | 2334000 |  |  |  |  | 0
STIP | YES | [5 empty] | NOT IN TIP |  |  | JEFFERSON | 5-965.2 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | DEDICATED FEDERAL AID STP FUNDS EARMARKED FOR LOUISVILLE URBANIZED AREA AND SUBJECT TO MPO CONTROL FOR FY 2022. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | C |  | SLO | 2022 | 23500000 | 18800000 |  |  |  | 4700000 |  |  |  |  | 0
STIP | [9 empty] | JEFFERSON | 5-1067 | US 150 | 0.04 | 3.6 | 3.64 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON E BROADWAY (US 150) OVER SOUTH FORK BEARGRASS CREEK AT INTERSECTION WITH BRENT STREET (CS 1312G)056B00348N (SD) | C |  | BR/NH | 2019 | 850000 | 527000 |  |  | 323000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.156 | 2020-01-08 | TIP FY 18-21, ADMIN MOD#41; UPDATE FY FROM 2019 TO 2020; UPDATE FUNDS FROM NHPP TO STP FUNDING AND INCREASE FUND AMOUNT; MOD | STPBRO | 8801009 | JEFFERSON | 5-1067 | US 150 | 0.04 | 3.6 | 3.64 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON E BROADWAY (US 150) OVER SOUTH FORK BEARGRASS CREEK AT INTERSECTION WITH BRENT STREET (CS 1312G)056B00348N (SD) | C |  | STP | 2020 | 1565000 | 1252000 |  |  |  | 313000 |  | OBLIGATED | 155200 | 1158560 | 1313760 | 2020 | 2ND QUARTER
STIP | [9 empty] | JEFFERSON | 5-1070 | CS 1017G | 0.04 | 1.293 | 1.333 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON E KENTUCKY ST (CS 1017G) OVER SOUTH FORK BEARGRASS CREEK 0.01 MILE E OF SCHILLER AVE (CS 1138G) 056C00083N | C |  | BR/STP | 2019 | 497000 | 308140 |  |  | 188860 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; UPDATE FISCAL YEAR AND FUND AMOUNTS; MOD |  |  | JEFFERSON | 5-1070 | CS 1017G | 0.04 | 1.293 | 1.333 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON E KENTUCKY ST (CS 1017G) OVER SOUTH FORK BEARGRASS CREEK 0.01 MILE E OF SCHILLER AVE (CS 1138G) 056C00083N | C |  | BR/STP | 2021 | 990000 | 792000 |  |  |  | 198000 |  |  |  |  | 0
TIP | [9 empty] | JEFFERSON | 5-1077 | CR 1001G | 0.02 | 2.48 | 2.5 | ASSET MANAGEMENT | AM-BRIDGE (P) | Replace bridge over northern ditch on Grade Lane (CR 1001G) 0.34 miles south of KY 1747 (Fern Valley Road) (SR=25.4). | R |  | BR/STP | 2019 | 20000 | 20000 | [8 empty] | 0
TIP | [9 empty] | JEFFERSON | 5-1077 | CR 1001G | 0.02 | 2.48 | 2.5 | ASSET MANAGEMENT | AM-BRIDGE (P) | Replace bridge over northern ditch on Grade Lane (CR 1001G) 0.34 miles south of KY 1747 (Fern Valley Road) (SR=25.4). | U |  | BR/STP | 2019 | 50000 | 50000 |  |  | 0 | [5 empty] | 0
TIP | [7 empty] | STPBRZ | 8760004 | JEFFERSON | 5-1077 | CR 1001G | 0.02 | 2.48 | 2.5 | ASSET MANAGEMENT | AM-BRIDGE (P) | Replace bridge over northern ditch on Grade Lane (CR 1001G) 0.34 miles south of KY 1747 (Fern Valley Road) (SR=25.4). | C |  | BR/STP | 2020 | 850000 | 850000 |  |  | 0 |  |  | OBLIGATED | 1004400 |  | 1004400 | 2019 | 4TH QUARTER
STIP | [9 empty] | JEFFERSON | 5-1079 | CR 1001B | 0.07 | 3.8 | 3.87 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER GOOSE CREEK ON RIVER ROAD (CR 1001B) 0.2 MI N OF LIME KILN ROAD (CR 1002B) (056C00130N) | D |  | BR/STP | 2019 | 315000 | 195300 |  |  | 119700 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.136 | 2019-09-30 | TIP FY 18-21; ADMIN MOD#36; UPDATE KIPDA ID TO 2675 & FISCAL YEAR TO 2020; MOD |  |  | Jefferson | 5-1079 | CR 1001B | 0.07 | 3.8 | 3.87 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER GOOSE CREEK ON RIVER ROAD (CR 1001B) 0.2 MI N OF LIME KILN ROAD (CR 1002B) (056C00130N) FROM MP 3.80 TO MP 3.87. | D |  | STP | 2020 | 315000 | 195300 |  |  | 119700 | [5 empty] | 0
STIP | [9 empty] | JEFFERSON | 5-1079 | CR 1001B | 0.07 | 3.8 | 3.87 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER GOOSE CREEK ON RIVER ROAD (CR 1001B) 0.2 MI N OF LIME KILN ROAD (CR 1002B) (056C00130N) | C |  | BR/STP | 2020 | 917000 | 568540 |  |  | 348460 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.136 | 2019-09-30 | TIP FY 18-21; ADMIN MOD#36; UPDATE KIPDA ID TO 2675 & INCREASE FUND AMOUNTS; MOD |  |  | Jefferson | 5-1079 | CR 1001B | 0.07 | 3.8 | 3.87 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER GOOSE CREEK ON RIVER ROAD (CR 1001B) 0.2 MI N OF LIME KILN ROAD (CR 1002B) (056C00130N) FROM MP 3.80 TO MP 3.87. | C |  | STP | 2020 | 2602000 | 1613240 |  |  |  | 988760 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; UPDATE FISCAL YEAR AND FUND AMOUNTS; MOD |  |  | Jefferson | 5-1079 | CR 1001B | 0.07 | 3.8 | 3.87 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER GOOSE CREEK ON RIVER ROAD (CR 1001B) 0.2 MI N OF LIME KILN ROAD (CR 1002B) (056C00130N) FROM MP 3.80 TO MP 3.87. | C |  | STP | 2021 | 2820000 | 2256000 |  |  |  | 564000 |  |  |  |  | 0
TIP | [6 empty] | NOT IN STIP |  |  | Jefferson | 5-2086.01 | I- 64 East of KY 1932 to West of Oxmoor Avenue | [5 empty] | JPC repair and diamond grind on I-64 from 0.129 miles east of KY 1932 (Breckenridge Lane) (MP 11.574) to 0.412 miles west of Oxmoor Avenue (MP 13.160) in Jefferson County (2016BOP). | C |  | IM | 2018 | 800000 | 800000 | [8 empty] | 0
TIP | [6 empty] | NOT IN STIP | IM | 2651020 | Jefferson | 5-2087 | I-265 |  | 10.25 | 15.66 | RELIABILITY | PAVEMENT REHAB-INT(P) | Repair and grind concrete pavement on I-265 from I-65 (MP 10.250), extending and ending 0.476 miles east of KY 864 Underpass (MP 15.660) in Jefferson County (2016BOP). | C |  | STP-ST | 2018 | 8200000 | 8200000 | [5 empty] | OBLIGATED | 8037300 |  | 8037300 | 2019 | 3RD QUARTER
TIP | [9 empty] | JEFFERSON | 5-3030.1 | US 60 |  | 12.895 | 14.718 | RELIABILITY | TRANSP ENHANCEMENT(P) | Construct a shared-use path along US 60 (Shelbyville Road) from Beckley Woods to Beckley Station, 0.5 miles. | U |  | SLO | 2019 | 62500 | 50000 |  |  |  | 12500 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; UPDATE FISCAL YEAR FROM 2019 TO 2020; MOD |  |  | JEFFERSON | 5-3030.1 | US 60 |  | 12.895 | 14.718 | RELIABILITY | TRANSP ENHANCEMENT(P) | Construct a shared-use path along US 60 (Shelbyville Road) from Beckley Woods to Beckley Station, 0.5 miles. | U |  | STP | 2020 | 62500 | 50000 |  |  |  | 12500 |  |  |  |  | 0
TIP | [9 empty] | JEFFERSON | 5-3030.1 | US 60 |  | 12.895 | 14.718 | RELIABILITY | TRANSP ENHANCEMENT(P) | Construct a shared-use path along US 60 (Shelbyville Road) from Beckley Woods to Beckley Station, 0.5 miles. | C |  | SLO | 2019 | 875000 | 700000 |  |  |  | 175000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; UPDATE FISCAL YEAR FROM 2019 TO 2020; MOD |  |  | JEFFERSON | 5-3030.1 | US 60 |  | 12.895 | 14.718 | RELIABILITY | TRANSP ENHANCEMENT(P) | Construct a shared-use path along US 60 (Shelbyville Road) from Beckley Woods to Beckley Station, 0.5 miles. | C |  | STP | 2020 | 875000 | 700000 |  |  |  | 175000 |  |  |  |  | 0
TIP | [9 empty] | Jefferson | 5-3030.2 | US 60 |  | 12.895 | 14.718 | RELIABILITY | TRANSP ENHANCEMENT(P) | Construct a shared-use path along US 60 (Shelbyville Road) from Beckley Station to Bircham Road, 0.7 miles. | R |  | SLO | 2018 | 500000 | 400000 |  |  |  | 100000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.035 | 2019-03-11 | TIP FY 18-21; (THIS PROJECT WAS PREVIOUSLY ADDED TO THE 2016 STIP ON STIP MOD 2016.218); MOD |  |  | Jefferson | 5-3030.2 | US 60 |  | 12.895 | 14.718 | RELIABILITY | TRANSP ENHANCEMENT(P) | Construct a shared-use path along US 60 (Shelbyville Road) from Beckley Station to Bircham Road, 0.7 miles. | R |  | SLO | 2018 | 500000 | 400000 |  |  |  | 100000 |  |  |  |  | 0
TIP | [9 empty] | Jefferson | 5-3030.2 | US 60 |  | 12.895 | 14.718 | RELIABILITY | TRANSP ENHANCEMENT(P) | Construct a shared-use path along US 60 (Shelbyville Road) from Beckley Station to Bircham Road, 0.7 miles. | U |  | SLO | 2019 | 125000 | 100000 |  |  |  | 25000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.035 | 2019-03-11 | TIP FY 18-21; (THIS PROJECT WAS PREVIOUSLY ADDED TO THE 2016 STIP ON STIP MOD 2016.218); MOD |  |  | Jefferson | 5-3030.2 | US 60 |  | 12.895 | 14.718 | RELIABILITY | TRANSP ENHANCEMENT(P) | Construct a shared-use path along US 60 (Shelbyville Road) from Beckley Station to Bircham Road, 0.7 miles. | U |  | SLO | 2019 | 125000 | 100000 |  |  |  | 25000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; UPDATE FISCAL YEAR FROM 2019 TO 2021; MOD |  |  | Jefferson | 5-3030.2 | US 60 |  | 12.895 | 14.718 | RELIABILITY | TRANSP ENHANCEMENT(P) | Construct a shared-use path along US 60 (Shelbyville Road) from Beckley Station to Bircham Road, 0.7 miles. | U |  | STP | 2021 | 125000 | 100000 |  |  |  | 25000 |  |  |  |  | 0
TIP | [9 empty] | Jefferson | 5-3030.2 | US 60 |  | 12.895 | 14.718 | RELIABILITY | TRANSP ENHANCEMENT(P) | Construct a shared-use path along US 60 (Shelbyville Road) from Beckley Station to Bircham Road, 0.7 miles. | C |  | SLO | 2019 | 1375000 | 1100000 |  |  |  | 275000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.035 | 2019-03-11 | TIP FY 18-21; (THIS PROJECT WAS PREVIOUSLY ADDED TO THE 2016 STIP ON STIP MOD 2016.218); MOD |  |  | Jefferson | 5-3030.2 | US 60 |  | 12.895 | 14.718 | RELIABILITY | TRANSP ENHANCEMENT(P) | Construct a shared-use path along US 60 (Shelbyville Road) from Beckley Station to Bircham Road, 0.7 miles. | C |  | SLO | 2019 | 1375000 | 1100000 |  |  |  | 275000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; UPDATE FISCAL YEAR FROM 2019 TO 2021; MOD |  |  | Jefferson | 5-3030.2 | US 60 |  | 12.895 | 14.718 | RELIABILITY | TRANSP ENHANCEMENT(P) | Construct a shared-use path along US 60 (Shelbyville Road) from Beckley Station to Bircham Road, 0.7 miles. | C |  | STP | 2021 | 1375000 | 1100000 |  |  |  | 275000 |  |  |  |  | 0
STIP | [9 empty] | JEFFERSON | 5-3030.3 | US 60 |  | 12.895 | 14.718 | RELIABILITY | TRANSP ENHANCEMENT(P) | NORTHEAST LOUISVILLE LOOP MET SECTION 3 BIRCHAM ROAD TO BECKLEY CREEK PARK. CONSTRUCT A SHARED USE PATH ALONG US 60 FROM BIRCHAM ROAD TO BECKLEY CREEK PARK, 0.5 MILE. (2016BOP) | R |  | SLO | 2019 | 50000 | 40000 |  |  |  | 10000 |  |  |  |  | 0
TIP | [6 empty] | TIP AND STIP AMOUNTS ARE DIFFERENT |  |  | JEFFERSON | 5-3030.3 | US 60 |  | 12.895 | 14.718 | RELIABILITY | TRANSP ENHANCEMENT(P) | Construct a shared-use path along US 60 (Shelbyville Road) from Bircham Road to Beckley Creek Park, 0.5 miles, includes the construction of the pedestrian bridge over Floyds Fork Creek. | R |  | SLO | 2019 | 62500 | 50000 |  |  |  | 12500 |  |  |  |  | 0
STIP | [9 empty] | JEFFERSON | 5-3030.3 | US 60 |  | 12.895 | 14.718 | RELIABILITY | TRANSP ENHANCEMENT(P) | NORTHEAST LOUISVILLE LOOP MET SECTION 3 BIRCHAM ROAD TO BECKLEY CREEK PARK. CONSTRUCT A SHARED USE PATH ALONG US 60 FROM BIRCHAM ROAD TO BECKLEY CREEK PARK, 0.5 MILE. (2016BOP) | U |  | SLO | 2019 | 75000 | 60000 |  |  |  | 15000 |  |  |  |  | 0
TIP | [6 empty] | TIP AND STIP AMOUNTS ARE DIFFERENT |  |  | JEFFERSON | 5-3030.3 | US 60 |  | 12.895 | 14.718 | RELIABILITY | TRANSP ENHANCEMENT(P) | Construct a shared-use path along US 60 (Shelbyville Road) from Bircham Road to Beckley Creek Park, 0.5 miles, includes the construction of the pedestrian bridge over Floyds Fork Creek. | U |  | SLO | 2019 | 93750 | 75000 |  |  |  | 18750 |  |  |  |  | 0
STIP | [9 empty] | JEFFERSON | 5-3030.3 | US 60 |  | 12.895 | 14.718 | RELIABILITY | TRANSP ENHANCEMENT(P) | NORTHEAST LOUISVILLE LOOP MET SECTION 3 BIRCHAM ROAD TO BECKLEY CREEK PARK. CONSTRUCT A SHARED USE PATH ALONG US 60 FROM BIRCHAM ROAD TO BECKLEY CREEK PARK, 0.5 MILE. (2016BOP) | C |  | SLO | 2019 | 2000000 | 1600000 |  |  |  | 400000 |  |  |  |  | 0
TIP | [6 empty] | TIP AND STIP AMOUNTS ARE DIFFERENT |  |  | JEFFERSON | 5-3030.3 | US 60 |  | 12.895 | 14.718 | RELIABILITY | TRANSP ENHANCEMENT(P) | Construct a shared-use path along US 60 (Shelbyville Road) from Bircham Road to Beckley Creek Park, 0.5 miles, includes the construction of the pedestrian bridge over Floyds Fork Creek. | C |  | SLO | 2019 | 2500000 | 2000000 |  |  |  | 500000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.035 | 2019-03-11 | TIP FY 18-21; (THIS PROJECT WAS PREVIOUSLY ADDED TO THE 2016 STIP ON STIP MOD 2016.218); MOD |  |  | Jefferson | 5-3030.3 | US 60 |  | 12.895 | 14.718 | RELIABILITY | TRANSP ENHANCEMENT(P) | Construct a shared-use path along US 60 (Shelbyville Road) from Bircham Road to Beckley Creek Park, 0.5 miles, includes the construction of the pedestrian bridge over Floyds Fork Creek. | C |  | SLO | 2020 | 2500000 | 2000000 |  |  |  | 500000 |  |  |  |  | 0
TIP | [9 empty] | JEFFERSON | 5-3030.4 | US 60 |  | 12.895 | 14.718 | RELIABILITY | TRANSP ENHANCEMENT(P) | Construct a shared-use path along US 60 (Shelbyville Road) from Beckley Creek Park to Eastwood Cut-off, 0.6 miles. | R |  | SLO | 2019 | 437500 | 350000 |  |  |  | 87500 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; UPDATE FISCAL YEAR FROM 2019 TO 2020; MOD |  |  | JEFFERSON | 5-3030.4 | US 60 |  | 12.895 | 14.718 | RELIABILITY | TRANSP ENHANCEMENT(P) | Construct a shared-use path along US 60 (Shelbyville Road) from Beckley Creek Park to Eastwood Cut-off, 0.6 miles. | R |  | STP | 2020 | 437500 | 350000 |  |  |  | 87500 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; UPDATE FISCAL YEAR; MOD |  |  | JEFFERSON | 5-3030.4 | US 60 |  | 12.895 | 14.718 | RELIABILITY | TRANSP ENHANCEMENT(P) | Construct a shared-use path along US 60 (Shelbyville Road) from Beckley Creek Park to Eastwood Cut-off, 0.6 miles. | R |  | STP | 2021 | 437500 | 350000 |  |  | 87500 | [5 empty] | 0
TIP | [9 empty] | JEFFERSON | 5-3030.4 | US 60 |  | 12.895 | 14.718 | RELIABILITY | TRANSP ENHANCEMENT(P) | Construct a shared-use path along US 60 (Shelbyville Road) from Beckley Creek Park to Eastwood Cut-off, 0.6 miles. | U |  | SLO | 2019 | 187500 | 150000 |  |  |  | 37500 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; UPDATE FISCAL YEAR FROM 2019 TO 2021; MOD |  |  | JEFFERSON | 5-3030.4 | US 60 |  | 12.895 | 14.718 | RELIABILITY | TRANSP ENHANCEMENT(P) | Construct a shared-use path along US 60 (Shelbyville Road) from Beckley Creek Park to Eastwood Cut-off, 0.6 miles. | U |  | STP | 2021 | 187500 | 150000 |  |  |  | 37500 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; UPDATE FISCAL YEAR; MOD |  |  | JEFFERSON | 5-3030.4 | US 60 |  | 12.895 | 14.718 | RELIABILITY | TRANSP ENHANCEMENT(P) | Construct a shared-use path along US 60 (Shelbyville Road) from Beckley Creek Park to Eastwood Cut-off, 0.6 miles. | U |  | STP | 2022 | 187500 | 150000 |  |  | 37500 | [5 empty] | 0
STIP | [9 empty] | JEFFERSON | 5-3030.4 | US 60 |  | 12.895 | 14.718 | RELIABILITY | TRANSP ENHANCEMENT(P) | NORTHEAST LOUISVILLE LOOP MET SECTION 4 BECKLEY CREEK PARK TO EASTWOOD CUTOFF. CONSTRUCT A SHARED USE PATH ALONG US 60 FROM BECKLEY CREEK PARK TO EASTWOOD CUT OFF, 0.6 MILE. (2016BOP) | C |  | SLO | 2021 | 1000000 | 800000 |  |  |  | 200000 |  |  |  |  | 0
TIP | [6 empty] | TIP AND STIP AMOUNTS ARE DIFFERENT |  |  | JEFFERSON | 5-3030.4 | US 60 |  | 12.895 | 14.718 | RELIABILITY | TRANSP ENHANCEMENT(P) | Construct a shared-use path along US 60 (Shelbyville Road) from Beckley Creek Park to Eastwood Cut-off, 0.6 miles. | C |  | SLO | 2021 | 1250000 | 1000000 |  |  |  | 250000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; UPDATE FISCAL YEAR; MOD |  |  | JEFFERSON | 5-3030.4 | US 60 |  | 12.895 | 14.718 | RELIABILITY | TRANSP ENHANCEMENT(P) | Construct a shared-use path along US 60 (Shelbyville Road) from Beckley Creek Park to Eastwood Cut-off, 0.6 miles. | C |  | STP | 2022 | 1250000 | 1000000 |  |  | 250000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.275 | 2021-02-04 | TIP FY 20-25, ADMIN MOD#12; ADD D PHASE TO STIP; NEW |  |  | JEFFERSON | 5-3031 | CS 1073H | 0.352 | 0 | 0.352 | RELIABILITY | TRANSP ENHANCEMENT(P) | Construct new curb and gutters as well as new sidewalks on both sides of Watterson Trail from Billtown Road to Old Taylorsville Road and including new ADA compliant rams and MUTCD crosswalks at each street intersection. The proposed sidewalks will be a minimum of 5 feet wide and will exceed that in many areas. The project will relocate the overhead utilities to the secondary streets of Peach Street and Neal Street. New street lights will be constructed along the route in order to provide improved pedestrian and vehicular safety. Enchanced landscaping will also be installed in order to address the heat island effect and ozone alert days and improve air quality. | D |  | SLO | 2021 | 187500 | 150000 |  |  | 37500 | [5 empty] | 0
TIP | [7 empty] | STPM | 3001432 | Jefferson | 5-3031 | CS 1073H | 0.352 | 0 | 0.352 | RELIABILITY | TRANSP ENHANCEMENT(P) | Improve streetscape, reconstruct sidewalks and ADA accessible ramps, access management, and utility relocations, as well as enhance landscaping from Maple Road to Old Taylorsville Road. | U |  | SLO | 2019 | 1540000 | 1232000 |  |  |  | 308000 |  | OBLIGATED | 1182000 |  | 1182000 | 2019 | 3RD QUARTER | CITY OF JEFFERSONTOWN
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.117 | 2019-08-09 | TIP FY 19-22, ADMIN MOD#34, UPDATE FUND TYPE FROM SLO TO TAP; MOD (SEE TAP SPREADSHEET) | STPM | 3001432 | Jefferson | 5-3031 | CS 1073H | 0.352 | 0 | 0.352 | RELIABILITY | TRANSP ENHANCEMENT(P) | Improve streetscape, reconstruct sidewalks and ADA accessible ramps, access management, and utility relocations, as well as enhance landscaping from Maple Road to Old Taylorsville Road. | U | [13 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.122 | 2019-08-26 | TIP FY 19-22, ADMIN MOD#35, UPDATE FUND TYPE FROM TAP TO SLO FUNDS; MOD | STPM | 3001432 | Jefferson | 5-3031 | CS 1073H | 0.352 | 0 | 0.352 | RELIABILITY | TRANSP ENHANCEMENT(P) | Improve streetscape, reconstruct sidewalks and ADA accessible ramps, access management, and utility relocations, as well as enhance landscaping from Maple Road to Old Taylorsville Road. | U |  | SLO | 2019 | 1540000 | 1232000 |  |  |  | 308000 |  |  |  |  | 0
TIP | [9 empty] | Jefferson | 5-3031 | CS 1073H | 0.352 | 0 | 0.352 | RELIABILITY | TRANSP ENHANCEMENT(P) | Improve streetscape, reconstruct sidewalks and ADA accessible ramps, access management, and utility relocations, as well as enhance landscaping from Maple Road to Old Taylorsville Road. | C |  | SLO | 2019 | 2110000 | 1688000 |  |  |  | 422000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.057 | 2019-04-26 | TIP FY 18-21, ADMIN MOD#29; UPDATE FUND AMOUNTS; MOD |  |  | Jefferson | 5-3031 | CS 1073H | 0.352 | 0 | 0.352 | RELIABILITY | TRANSP ENHANCEMENT(P) | Improve streetscape, reconstruct sidewalks and ADA accessible ramps, access management, and utility relocations, as well as enhance landscaping from Maple Road to Old Taylorsville Road. | C |  | STP | 2019 | 2723166 | 2218876 |  |  |  | 504290 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; UPDATE FISCAL YEAR FROM 2019 TO 2020; MOD |  |  | Jefferson | 5-3031 | CS 1073H | 0.352 | 0 | 0.352 | RELIABILITY | TRANSP ENHANCEMENT(P) | Improve streetscape, reconstruct sidewalks and ADA accessible ramps, access management, and utility relocations, as well as enhance landscaping from Maple Road to Old Taylorsville Road. | C |  | STP | 2020 | 2723166 | 2218876 |  |  |  | 504290 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY20-25, ADMIN MOD#10; UPDATE FISCAL YEAR & FUND AMOUNTS; MOD |  |  | Jefferson | 5-3031 | CS 1073H | 0.352 | 0 | 0.352 | RELIABILITY | TRANSP ENHANCEMENT(P) | Improve streetscape, reconstruct sidewalks and ADA accessible ramps, access management, and utility relocations, as well as enhance landscaping from Maple Road to Old Taylorsville Road. | C |  | STP | 2022 | 2773595 | 2218876 |  |  |  | 554719 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.275 | 2021-02-04 | TIP FY 20-25, ADMIN MOD#12; UPDATE PROJECT DESCRIPTION, FISCAL YEAR AND FUND AMOUNTS; MOD |  |  | Jefferson | 5-3031 | CS 1073H | 0.352 | 0 | 0.352 | RELIABILITY | TRANSP ENHANCEMENT(P) | Construct new curb and gutters as well as new sidewalks on both sides of Watterson Trail from Billtown Road to Old Taylorsville Road and including new ADA compliant rams and MUTCD crosswalks at each street intersection. The proposed sidewalks will be a minimum of 5 feet wide and will exceed that in many areas. The project will relocate the overhead utilities to the secondary streets of Peach Street and Neal Street. New street lights will be constructed along the route in order to provide improved pedestrian and vehicular safety. Enchanced landscaping will also be installed in order to address the heat island effect and ozone alert days and improve air quality. | C |  | STP | 2021 | 3128166 | 2548876 |  |  | 579290 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.309 | 2021-06-10 | TIP FY 20-25, ADMIN MOD#17; UPDATE FUND AMOUNTS; MOD |  |  | Jefferson | 5-3031 | CS 1073H | 0.352 | 0 | 0.352 | RELIABILITY | TRANSP ENHANCEMENT(P) | Construct new curb and gutters as well as new sidewalks on both sides of Watterson Trail from Billtown Road to Old Taylorsville Road and including new ADA compliant rams and MUTCD crosswalks at each street intersection. The proposed sidewalks will be a minimum of 5 feet wide and will exceed that in many areas. The project will relocate the overhead utilities to the secondary streets of Peach Street and Neal Street. New street lights will be constructed along the route in order to provide improved pedestrian and vehicular safety. Enchanced landscaping will also be installed in order to address the heat island effect and ozone alert days and improve air quality. | C |  | STP | 2021 | 2764874 | 2259725 |  |  | 505149 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.309 | 2021-06-10 | TIP FY 20-25, ADMIN MOD#17; ADD CRRSAA FUNDS TO THE C PHASE; MOD |  |  | Jefferson | 5-3031 | CS 1073H | 0.352 | 0 | 0.352 | RELIABILITY | TRANSP ENHANCEMENT(P) | Construct new curb and gutters as well as new sidewalks on both sides of Watterson Trail from Billtown Road to Old Taylorsville Road and including new ADA compliant rams and MUTCD crosswalks at each street intersection. The proposed sidewalks will be a minimum of 5 feet wide and will exceed that in many areas. The project will relocate the overhead utilities to the secondary streets of Peach Street and Neal Street. New street lights will be constructed along the route in order to provide improved pedestrian and vehicular safety. Enchanced landscaping will also be installed in order to address the heat island effect and ozone alert days and improve air quality. | C |  |  | 2021 | 370707 | 370707 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.107 | 2019-07-26 | TIP FY 18-21, ADMIN MOD#33; ADD PROJECT TO STIP; MOD |  |  | Jefferson | 5-3037 | CS 1016 |  | 0.455 | 0.662 | SAFETY | BIKE/PED FACIL(O) | REHABILITATION OF SIDEWALKS ALONG HILL STREET BETWEEN 6TH STREET AND 7TH STREET. (2012 BOP) | C |  | STP | 2019 | 143600 | 117000 |  |  |  | 26600 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.117 | 2019-08-09 | TIP FY 18-21, ADMIN MOD#34; UPDATE FUND TYPE FROM STP TO TAP FUNDS; MOD (SEE TAP SPREADSHEET) |  |  | Jefferson | 5-3037 | CS 1016 |  | 0.455 | 0.662 | SAFETY | BIKE/PED FACIL(O) | REHABILITATION OF SIDEWALKS ALONG HILL STREET BETWEEN 6TH STREET AND 7TH STREET. (2012 BOP) | C
STIP | [7 empty] | STPM | 3001523 | JEFFERSON | 5-3039 | CS 1367H |  | 0 | 0.295 | SAFETY | BIKE/PED FACIL(O) | CONSTRUCT SIDEWALKS ALONG KRATZ LANE FOR .35 MILES BETWEEN SHELBYVILLE RD. AND OLD SHELBYVILLE RD./MAIN ST., INCLUDING SOME DRAINAGE IMPROVEMENTS (2016BOP). | C |  | SLO | 2019 | 234382 | 187505.6 |  |  |  | 46876.4 |  | OBLIGATED |  | 234382 | 234382 | 2019 | 4TH QUARTER | City of Middletown
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.058 | 2019-04-29 | TIP FY 18-21, AMENDMENT#11; ADD PROJECT TO STIP; NEW |  |  | JEFFERSON | 5-3204 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | OLMSTEAD STONE ARCH BRIDGE REHAB & TRAIL PROJECT PHASE 2 - RESTORATION OF HISTORIC BRIDGE AT INTERSECTION OF OLD TAYLORSVILLE RD & CHENOWETH RUN RD. CONSTRUCT PH 2 OF VETERAN'S MEMORIAL PARK BIKE/PED PATH FROM OLD TAYLORSVILLE RD INTO PARK (2014BOP). | [14 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; ADD C PHASE TO STIP; NEW |  |  | JEFFERSON | 5-3204 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | OLMSTEAD STONE ARCH BRIDGE REHAB & TRAIL PROJECT PHASE 2 - RESTORATION OF HISTORIC BRIDGE AT INTERSECTION OF OLD TAYLORSVILLE RD & CHENOWETH RUN RD. CONSTRUCT PH 2 OF VETERAN'S MEMORIAL PARK BIKE/PED PATH FROM OLD TAYLORSVILLE RD INTO PARK (2014BOP). | C |  | STP | 2021 | 374973 | 299978 |  |  | 74995 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.264 | 2020-12-07 | TIP FY 20-25, ADMIN MOD#11; ADD D PHASE TO STIP; NEW |  |  | JEFFERSON | 5-3212 | CS 2048 |  | 1.09 | 2.09 | SAFETY | BIKE/PED FACIL(O) | Construction of sidewalk along Cannons Lane between Willis Avenue and Bowman Field (Seneca Loop), 1.0 miles. | D |  | STP | 2021 | 5000 | 5000 | [8 empty] | 0
TIP | [9 empty] | JEFFERSON | 5-3212 | CS 2048 |  | 1.09 | 2.09 | SAFETY | BIKE/PED FACIL(O) | Construction of sidewalk along Cannons Lane between Willis Avenue and Bowman Field (Seneca Loop), 1.0 miles. | R |  | SLO | 2019 | 125000 | 100000 |  |  |  | 25000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.117 | 2019-08-09 | TIP FY 18-21, ADMIN MOD#34; UPDATE FUND TYPE FROM SLO TO TAP & REDUCE FUND AMOUNT; MOD |  |  | JEFFERSON | 5-3212 | CS 2048 |  | 1.09 | 2.09 | SAFETY | BIKE/PED FACIL(O) | Construction of sidewalk along Cannons Lane between Willis Avenue and Bowman Field (Seneca Loop), 1.0 miles. | R | [13 empty] | 0
TIP | [9 empty] | JEFFERSON | 5-3212 | CS 2048 |  | 1.09 | 2.09 | SAFETY | BIKE/PED FACIL(O) | Construction of sidewalk along Cannons Lane between Willis Avenue and Bowman Field (Seneca Loop), 1.0 miles. | U |  | SLO | 2019 | 125000 | 100000 |  |  |  | 25000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; UPDATE FISCAL YEAR FROM 2019 TO 2020; MOD |  |  | JEFFERSON | 5-3212 | CS 2048 |  | 1.09 | 2.09 | SAFETY | BIKE/PED FACIL(O) | Construction of sidewalk along Cannons Lane between Willis Avenue and Bowman Field (Seneca Loop), 1.0 miles. | U |  | STP | 2020 | 125000 | 100000 |  |  |  | 25000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; UPDATE FISCAL YEAR; MOD |  |  | JEFFERSON | 5-3212 | CS 2048 |  | 1.09 | 2.09 | SAFETY | BIKE/PED FACIL(O) | Construction of sidewalk along Cannons Lane between Willis Avenue and Bowman Field (Seneca Loop), 1.0 miles. | U |  | STP | 2021 | 125000 | 100000 |  |  |  | 25000 |  |  |  |  | 0
TIP | [9 empty] | JEFFERSON | 5-3212 | CS 2048 |  | 1.09 | 2.09 | SAFETY | BIKE/PED FACIL(O) | Construction of sidewalk along Cannons Lane between Willis Avenue and Bowman Field (Seneca Loop), 1.0 miles. | C |  | SLO | 2021 | 625000 | 500000 |  |  |  | 125000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.226 | 2020-08-28 | TIP FY 20-25, ADMIN MOD#7; ADD D PHASE TO STIP; NEW |  |  | JEFFERSON | 5-3216 | Historic Memorial Multi-use Path |  |  |  | SAFETY | BIKE/PED FACIL(O) | Construct multi-use path and pedestrian walkway along segment C of the Historic Memorial Multi-use Trail including a Rest Plaza at Landis and US 31 EX. In addition, improve safety along the segment by reducing drainage hazards and installing a signal at Landis Lane. | D |  | STP | 2020 | 70000 | 56000 |  |  |  | 14000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; UPDATE FISCAL YEAR; MOD |  |  | JEFFERSON | 5-3216 | Historic Memorial Multi-use Path |  |  |  | SAFETY | BIKE/PED FACIL(O) | Construct multi-use path and pedestrian walkway along segment C of the Historic Memorial Multi-use Trail including a Rest Plaza at Landis and US 31 EX. In addition, improve safety along the segment by reducing drainage hazards and installing a signal at Landis Lane. | D |  | STP | 2021 | 70000 | 56000 |  |  |  | 14000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.309 | 2021-06-10 | TIP FY 20-25, ADMIN MOD#17; UPDATE PROJECT DESCRIPTION AND FUND AMOUNTS; MOD |  |  | JEFFERSON | 5-3216 | Historic Memorial Multi-use Path |  |  |  | SAFETY | BIKE/PED FACIL(O) | Construct multi-use path and pedestrian walkway along segment C of the Historic Memorial Multi-use Trail including a Rest Plaza at Landis and US 31 EX. In addition, improve safety along the segment by reducing drainage hazards and installing a roundabout at Landis Lane. | D |  | STP | 2021 | 154000 | 123200 |  |  | 30800 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.226 | 2020-08-28 | TIP FY 20-25, ADMIN MOD#7; ADD R PHASE TO STIP; NEW |  |  | JEFFERSON | 5-3216 | Historic Memorial Multi-use Path |  |  |  | SAFETY | BIKE/PED FACIL(O) | Construct multi-use path and pedestrian walkway along segment C of the Historic Memorial Multi-use Trail including a Rest Plaza at Landis and US 31 EX. In addition, improve safety along the segment by reducing drainage hazards and installing a signal at Landis Lane. | R |  | STP | 2020 | 15000 | 12000 |  |  |  | 3000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; UPDATE FISCAL YEAR; MOD |  |  | JEFFERSON | 5-3216 | Historic Memorial Multi-use Path |  |  |  | SAFETY | BIKE/PED FACIL(O) | Construct multi-use path and pedestrian walkway along segment C of the Historic Memorial Multi-use Trail including a Rest Plaza at Landis and US 31 EX. In addition, improve safety along the segment by reducing drainage hazards and installing a signal at Landis Lane. | R |  | STP | 2021 | 15000 | 12000 |  |  |  | 3000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.309 | 2021-06-10 | TIP FY 20-25, ADMIN MOD#17; UPDATE PROJECT DESCRIPTION; MOD |  |  | JEFFERSON | 5-3216 | Historic Memorial Multi-use Path |  |  |  | SAFETY | BIKE/PED FACIL(O) | Construct multi-use path and pedestrian walkway along segment C of the Historic Memorial Multi-use Trail including a Rest Plaza at Landis and US 31 EX. In addition, improve safety along the segment by reducing drainage hazards and installing a roundabout at Landis Lane. | R |  | STP | 2021 | 15000 | 12000 |  |  | 3000
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.226 | 2020-08-28 | TIP FY 20-25, ADMIN MOD#7; ADD C PHASE TO STIP; NEW |  |  | JEFFERSON | 5-3216 | Historic Memorial Multi-use Path |  |  |  | SAFETY | BIKE/PED FACIL(O) | Construct multi-use path and pedestrian walkway along segment C of the Historic Memorial Multi-use Trail including a Rest Plaza at Landis and US 31 EX. In addition, improve safety along the segment by reducing drainage hazards and installing a signal at Landis Lane. | C |  | STP | 2021 | 1015267 | 812213 |  |  |  | 203054 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; UPDATE FISCAL YEAR; MOD |  |  | JEFFERSON | 5-3216 | Historic Memorial Multi-use Path |  |  |  | SAFETY | BIKE/PED FACIL(O) | Construct multi-use path and pedestrian walkway along segment C of the Historic Memorial Multi-use Trail including a Rest Plaza at Landis and US 31 EX. In addition, improve safety along the segment by reducing drainage hazards and installing a signal at Landis Lane. | C |  | STP | 2022 | 1015267 | 812213 |  |  |  | 203054 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.309 | 2021-06-10 | TIP FY 20-25, ADMIN MOD#17; UPDATE PROJECT DESCRIPTION AND FUND AMOUNTS; MOD |  |  | JEFFERSON | 5-3216 | Historic Memorial Multi-use Path |  |  |  | SAFETY | BIKE/PED FACIL(O) | Construct multi-use path and pedestrian walkway along segment C of the Historic Memorial Multi-use Trail including a Rest Plaza at Landis and US 31 EX. In addition, improve safety along the segment by reducing drainage hazards and installing a roundabout at Landis Lane. | C |  | STP | 2022 | 897267 | 717814 |  |  | 179453 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.309 | 2021-06-10 | TIP FY 20-25, ADMIN MOD#17; ADD CRRSSA FUNDS TO THE C PHASE; MOD |  |  | JEFFERSON | 5-3216 | Historic Memorial Multi-use Path |  |  |  | SAFETY | BIKE/PED FACIL(O) | Construct multi-use path and pedestrian walkway along segment C of the Historic Memorial Multi-use Trail including a Rest Plaza at Landis and US 31 EX. In addition, improve safety along the segment by reducing drainage hazards and installing a roundabout at Landis Lane. | C |  |  | 2022 | 118000 | 118000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.117 | 2019-08-09 | TIP FY 18-21, ADMIN MOD#34; UPDATE FUND TYPE FROM TAP TO SLO FUNDS; MOD |  |  | JEFFERSON | 5-3217 | KY 3077 |  | 0.002 | 0.375 | SAFETY | BIKE/PED FACIL(O) | River Road Multimodal improvements-improve safety and comfort of pedestrians and bicyclists along River Road between 3rd Street and 7th Streets. | U |  | SLO | 2019 | 168750 | 135000 |  |  |  | 33750 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.153 | 2019-12-13 | TIP FY 18-21, ADMIN MOD#39; REMOVE THE UTILITY PHASE; MOD |  |  | JEFFERSON | 5-3217 | KY 3077 |  | 0.002 | 0.375 | SAFETY | BIKE/PED FACIL(O) | River Road Multimodal improvements-improve safety and comfort of pedestrians and bicyclists along River Road between 3rd Street and 7th Streets. | U
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.117 | 2019-08-09 | TIP FY 18-21, ADMIN MOD#34; UPDATE FUND TYPE FROM TAP TO SLO FUNDS; MOD |  |  | JEFFERSON | 5-3217 | KY 3077 |  | 0.002 | 0.375 | SAFETY | BIKE/PED FACIL(O) | River Road Multimodal improvements-improve safety and comfort of pedestrians and bicyclists along River Road between 3rd Street and 7th Streets. | C |  | SLO | 2019 | 517135 | 413708 |  |  |  | 103427 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-521, ADMIN MOD#38; UPDATE FUND AMOUNT AND FISCAL YEAR FROM 2019 TO 2020; MOD |  |  | JEFFERSON | 5-3217 | KY 3077 |  | 0.002 | 0.375 | SAFETY | BIKE/PED FACIL(O) | River Road Multimodal improvements-improve safety and comfort of pedestrians and bicyclists along River Road between 3rd Street and 7th Streets. | C |  | STP | 2020 | 1767135 | 1413708 |  |  |  | 353427 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.154 | 2019-12-16 | TIP FY 18-21, ADMIN MOD#40; UPDATE FUND TYPE FROM SLO BACK TO TAP; MOD |  |  | JEFFERSON | 5-3217 | KY 3077 |  | 0.002 | 0.375 | SAFETY | BIKE/PED FACIL(O) | River Road Multimodal improvements-improve safety and comfort of pedestrians and bicyclists along River Road between 3rd Street and 7th Streets. | C
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.117 | 2019-08-09 | TIP FY 18-21, ADMIN MOD#34; UPDATE FUND TYPE FROM TAP TO SLO FUNDS & UPDATE PROJECT DESCRIPTION; MOD |  |  | JEFFERSON | 5-3218 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | University of Louisville pedestrian improvements-lighting. Install or retrofit 400 mor more lighting fixtures throughout campus including the "L Trail", Humanities Building and other campus sidewalk locations. | C |  | SLO | 2019 | 449088 | 359270 |  |  |  | 89818 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; UPDATE FISCAL YEAR FROM 2019 TO 2020; MOD |  |  | JEFFERSON | 5-3218 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | University of Louisville pedestrian improvements-lighting. Install or retrofit 400 mor more lighting fixtures throughout campus including the "L Trail", Humanities Building and other campus sidewalk locations. | C |  | STP | 2020 | 449088 | 359270 |  |  |  | 89818 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; UPDATE FISCAL YEAR; MOD |  |  | JEFFERSON | 5-3218 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | University of Louisville pedestrian improvements-lighting. Install or retrofit 400 mor more lighting fixtures throughout campus including the "L Trail", Humanities Building and other campus sidewalk locations. | C |  | STP | 2021 | 449088 | 359270 |  |  |  | 89818 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.117 | 2019-08-09 | TIP FY 18-21, ADMIN MOD#34; UPDATE FUND TYPE FROM TAP TO SLO FUNDS; MOD |  |  | JEFFERSON | 5-3220 |  |  |  |  | RELIABILITY | TRANSP ENHANCEMENT(P) | UL PED UPGRADES - INSTALL OR UPGRADE ADA ACCESSIBLE CURB CUTS/RAMPS THROUGHOUT BELKNAP CAMPUS. | C |  | SLO | 2019 | 437500 | 350000 |  |  |  | 87500 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; UPDATE FISCAL YEAR FROM 2019 TO 2020; MOD |  |  | JEFFERSON | 5-3220 |  |  |  |  | RELIABILITY | TRANSP ENHANCEMENT(P) | UL PED UPGRADES - INSTALL OR UPGRADE ADA ACCESSIBLE CURB CUTS/RAMPS THROUGHOUT BELKNAP CAMPUS. | C |  | STP | 2020 | 437500 | 350000 |  |  |  | 87500 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; UPDATE FISCAL YEAR; MOD |  |  | JEFFERSON | 5-3220 |  |  |  |  | RELIABILITY | TRANSP ENHANCEMENT(P) | UL PED UPGRADES - INSTALL OR UPGRADE ADA ACCESSIBLE CURB CUTS/RAMPS THROUGHOUT BELKNAP CAMPUS. | C |  | STP | 2021 | 437500 | 350000 |  |  |  | 87500 |  |  |  |  | 0
TIP | [6 empty] | Not in STIP |  |  | Jefferson | 5-8405 | I-264 | [5 empty] | Construct new I-264 (Henry Watterson Expressway) interchange at KY 1931 (Manslick Road). | R |  | NHS | 2019 | 4000000 | 4000000 | [8 empty] | 0
TIP | [6 empty] | Not in STIP |  |  | Jefferson | 5-8405 | I-264 | [5 empty] | Construct new I-264 (Henry Watterson Expressway) interchange at KY 1931 (Manslick Road). | U |  | NHS | 2020 | 1800000 | 1800000 | [8 empty] | 0
TIP | [6 empty] | Not in STIP |  |  | Jefferson | 5-8501 | KY 2055 | [5 empty] | Construction of a roundabout at West Manslick Road/Mount Holly Road at the intersection of Fairdale Road/Mitchell Hill Road as well as pavement rehabilitation from M.P. 1.36 to 1.42 on KY 2055 | C |  | SLO | 2019 | 300000 | 300000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.282 | 2021-03-04 | TIP FY 20-25, ADMIN MOD#13; ADD PROJECT TO STIP; NEW |  |  | Jefferson | 5-8652 | US 60 |  | 14.7 | 15.1 |  |  | WIDEN US 60 TO THREE LANES FROM EASTWOOD CUTOFF (MP 14.7) TO ROCKCREST WAY (MP 15.1) | D |  | STP | 2021 | 330000 | 264000 |  |  | 66000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.282 | 2021-03-04 | TIP FY 20-25, ADMIN MOD#13; ADD PROJECT TO STIP; NEW |  |  | Jefferson | 5-8652 | US 60 |  | 14.7 | 15.1 |  |  | WIDEN US 60 TO THREE LANES FROM EASTWOOD CUTOFF (MP 14.7) TO ROCKCREST WAY (MP 15.1) | R |  | STP | 2023 | 410000 | 328000 |  |  | 82000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.282 | 2021-03-04 | TIP FY 20-25, ADMIN MOD#13; ADD PROJECT TO STIP; NEW |  |  | Jefferson | 5-8652 | US 60 |  | 14.7 | 15.1 |  |  | WIDEN US 60 TO THREE LANES FROM EASTWOOD CUTOFF (MP 14.7) TO ROCKCREST WAY (MP 15.1) | U |  | STP | 2024 | 460000 | 368000 |  |  | 92000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.271 | 2021-01-12 | TIP FY 20-25, AMEND#2; ADD PROJECT TO STIP; NEW |  |  | Jefferson | 5-8805 | Campus Improvements |  |  |  | RELIABILITY | PREFINANCD CONVRSN(O) | Roundabout at the Floyd Street and E. Brandeis Avenue intersection and other Belknap Campus improvements to include multimodal improvements at the South 3rd Street and Brandeis intersection and along W. Brandeis Avenue between South 4rd Street and South 4th Street. Project would provide better connectivity between new university facilities with the main Belknap campus by the creation a multi-modal corridor along W. Brandeis Avenue between South 3rd Street and South 4th Street. The proposed multi-modal corridor would improve pedestrian and bicycle safety with the creation of a designated street crossing location and also include geometric improvements to South 3rd Street with the straightening of the turn lane and thru lanes southbound at the W. Brandeis Avenue Intersection. | D |  | STP | 2021 | 225000 | 180000 |  |  | 45000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.299 | 2021-04-26 | TIP FY 20-25, ADMIN MOD#16; UPDATE FUND AMOUNTS; MOD |  |  | Jefferson | 5-8805 | Campus Improvements |  |  |  | RELIABILITY | PREFINANCD CONVRSN(O) | Roundabout at the Floyd Street and E. Brandeis Avenue intersection and other Belknap Campus improvements to include multimodal improvements at the South 3rd Street and Brandeis intersection and along W. Brandeis Avenue between South 4rd Street and South 4th Street. Project would provide better connectivity between new university facilities with the main Belknap campus by the creation a multi-modal corridor along W. Brandeis Avenue between South 3rd Street and South 4th Street. The proposed multi-modal corridor would improve pedestrian and bicycle safety with the creation of a designated street crossing location and also include geometric improvements to South 3rd Street with the straightening of the turn lane and thru lanes southbound at the W. Brandeis Avenue Intersection. | D |  | STP | 2021 | 294500 | 235600 |  |  | 58900 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.309 | 2021-06-10 | TIP FY 20-25, ADMIN MOD#17; UPDATE FUND AMOUNTS; MOD |  |  | Jefferson | 5-8805 | Campus Improvements |  |  |  | RELIABILITY | PREFINANCD CONVRSN(O) | Roundabout at the Floyd Street and E. Brandeis Avenue intersection and other Belknap Campus improvements to include multimodal improvements at the South 3rd Street and Brandeis intersection and along W. Brandeis Avenue between South 4rd Street and South 4th Street. Project would provide better connectivity between new university facilities with the main Belknap campus by the creation a multi-modal corridor along W. Brandeis Avenue between South 3rd Street and South 4th Street. The proposed multi-modal corridor would improve pedestrian and bicycle safety with the creation of a designated street crossing location and also include geometric improvements to South 3rd Street with the straightening of the turn lane and thru lanes southbound at the W. Brandeis Avenue Intersection. | D |  | STP | 2021 | 232289 | 190800 |  |  | 41489 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.309 | 2021-06-10 | TIP FY 20-25, ADMIN MOD#17; ADD CRRSAA FUNDS TO THE D PHASE; MOD |  |  | Jefferson | 5-8805 | Campus Improvements |  |  |  | RELIABILITY | PREFINANCD CONVRSN(O) | Roundabout at the Floyd Street and E. Brandeis Avenue intersection and other Belknap Campus improvements to include multimodal improvements at the South 3rd Street and Brandeis intersection and along W. Brandeis Avenue between South 4rd Street and South 4th Street. Project would provide better connectivity between new university facilities with the main Belknap campus by the creation a multi-modal corridor along W. Brandeis Avenue between South 3rd Street and South 4th Street. The proposed multi-modal corridor would improve pedestrian and bicycle safety with the creation of a designated street crossing location and also include geometric improvements to South 3rd Street with the straightening of the turn lane and thru lanes southbound at the W. Brandeis Avenue Intersection. | D |  |  | 2021 | 82475 | 82475 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.271 | 2021-01-12 | TIP FY 20-25, AMEND#2; ADD PROJECT TO STIP; NEW |  |  | Jefferson | 5-8805 | Campus Improvements |  |  |  | RELIABILITY | PREFINANCD CONVRSN(O) | Roundabout at the Floyd Street and E. Brandeis Avenue intersection and other Belknap Campus improvements to include multimodal improvements at the South 3rd Street and Brandeis intersection and along W. Brandeis Avenue between South 4rd Street and South 4th Street. Project would provide better connectivity between new university facilities with the main Belknap campus by the creation a multi-modal corridor along W. Brandeis Avenue between South 3rd Street and South 4th Street. The proposed multi-modal corridor would improve pedestrian and bicycle safety with the creation of a designated street crossing location and also include geometric improvements to South 3rd Street with the straightening of the turn lane and thru lanes southbound at the W. Brandeis Avenue Intersection. | U |  | STP | 2022 | 937500 | 750000 |  |  | 187500 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.271 | 2021-01-12 | TIP FY 20-25, AMEND#2; ADD PROJECT TO STIP; NEW |  |  | Jefferson | 5-8805 | Campus Improvements |  |  |  | RELIABILITY | PREFINANCD CONVRSN(O) | Roundabout at the Floyd Street and E. Brandeis Avenue intersection and other Belknap Campus improvements to include multimodal improvements at the South 3rd Street and Brandeis intersection and along W. Brandeis Avenue between South 4rd Street and South 4th Street. Project would provide better connectivity between new university facilities with the main Belknap campus by the creation a multi-modal corridor along W. Brandeis Avenue between South 3rd Street and South 4th Street. The proposed multi-modal corridor would improve pedestrian and bicycle safety with the creation of a designated street crossing location and also include geometric improvements to South 3rd Street with the straightening of the turn lane and thru lanes southbound at the W. Brandeis Avenue Intersection. | C |  | STP | 2022 | 1875000 | 1500000 |  |  | 375000 | [5 empty] | 0
STIP | [9 empty] | Jefferson | 5-8810 | KY 1931 | 0.599 | 4.561 | 5.5 | RELIABILITY | MINOR WIDENING(O) | Three lane widening along KY 1931 from the Doss High School entrance to Palatka Road, including intersection improvements with Palatka Road and turn lanes. | C |  | STP-ST | 2018 | 6080000 | 6080000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.001 | 2018-12-06 | TIP FY 18-21; AMENDMENT#3; REMOVE CONSTRUCTION FROM FY 2018; MOD |  |  | Jefferson | 5-8810 | KY 1931 | 0.599 | 4.561 | 5.5 | RELIABILITY | MINOR WIDENING(O) | Three lane widening along KY 1931 from the Doss High School entrance to Palatka Road, including intersection improvements with Palatka Road and turn lanes. | C |  | STP-ST |  | 6080000 | 6080000 | [8 empty] | 0
STIP | YES | [8 empty] | JEFFERSON | 5-8810 | KY 1931 | 0.599 | 4.561 | 5.5 | RELIABILITY | MINOR WIDENING(O) | THREE LANE WIDENING ALONG KY-1931 FROM THE DOSS HIGH SCHOOL ENTRANCE TO PALATKA ROAD, INCLUDING INTERSECTION IMPROVEMENTS WITH PALATKA ROAD AND TURN LANES. (14CCN) | R |  | STP | 2022 | 2630000 | 2104000 |  |  | 526000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; UPDATE FUND AMOUNTS; MOD |  |  | JEFFERSON | 5-8810 | KY 1931 | 0.599 | 4.561 | 5.5 | RELIABILITY | MINOR WIDENING(O) | THREE LANE WIDENING ALONG KY-1931 FROM THE DOSS HIGH SCHOOL ENTRANCE TO PALATKA ROAD, INCLUDING INTERSECTION IMPROVEMENTS WITH PALATKA ROAD AND TURN LANES. (14CCN) | R |  | STP | 2022 | 2770000 | 2216000 |  |  | 554000 | [5 empty] | 0
STIP | YES | [8 empty] | JEFFERSON | 5-8810 | KY 1931 | 0.599 | 4.561 | 5.5 | RELIABILITY | MINOR WIDENING(O) | THREE LANE WIDENING ALONG KY-1931 FROM THE DOSS HIGH SCHOOL ENTRANCE TO PALATKA ROAD, INCLUDING INTERSECTION IMPROVEMENTS WITH PALATKA ROAD AND TURN LANES. (14CCN) | U |  | STP | 2022 | 4160000 | 3328000 |  |  | 832000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; UPDATE FISCAL YEAR AND FUND AMOUNTS; MOD |  |  | JEFFERSON | 5-8810 | KY 1931 | 0.599 | 4.561 | 5.5 | RELIABILITY | MINOR WIDENING(O) | THREE LANE WIDENING ALONG KY-1931 FROM THE DOSS HIGH SCHOOL ENTRANCE TO PALATKA ROAD, INCLUDING INTERSECTION IMPROVEMENTS WITH PALATKA ROAD AND TURN LANES. (14CCN) | U |  | STP | 2023 | 4330000 | 3464000 |  |  | 866000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; ADD PROJECT TO STIP; NEW |  |  | JEFFERSON | 5-8908 | KY 155 | [5 empty] | IMPROVE SAFETY, MOBILITY FOR ALL MODES AND PROVIDE BETER ACCESS ALONG KY 155 FROM KY 148 TO I-265 NEAR POPE LICK PARK. | D |  | STP | 2021 | 920000 | 736000 |  |  | 184000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; ADD PROJECT TO STIP; NEW |  |  | JEFFERSON | 5-8908 | KY 155 | [5 empty] | IMPROVE SAFETY, MOBILITY FOR ALL MODES AND PROVIDE BETER ACCESS ALONG KY 155 FROM KY 148 TO I-265 NEAR POPE LICK PARK. | R |  | STP | 2023 | 1000000 | 800000 |  |  | 200000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; ADD PROJECT TO STIP; NEW |  |  | JEFFERSON | 5-8908 | KY 155 | [5 empty] | IMPROVE SAFETY, MOBILITY FOR ALL MODES AND PROVIDE BETER ACCESS ALONG KY 155 FROM KY 148 TO I-265 NEAR POPE LICK PARK. | U |  | STP | 2024 | 500000 | 400000 |  |  | 100000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; ADD PROJECT TO STIP; NEW |  |  | JEFFERSON | 5-8908 | KY 155 | [5 empty] | IMPROVE SAFETY, MOBILITY FOR ALL MODES AND PROVIDE BETER ACCESS ALONG KY 155 FROM KY 148 TO I-265 NEAR POPE LICK PARK. | C |  | STP | 2025 | 15930000 | 12744000 |  |  | 3186000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.271 | 2021-01-12 | TIP FY 20-25, AMEND#2; ADD PROJECT TO STIP; NEW |  |  | JEFFERSON | 5-8952 | US 60 |  |  |  | RELIABILITY | MINOR WIDENING(O) | WIDEN US 60 TO THREE LANES FROM EASTWOOD CUTOFF (MP 14.7) TO ROCKCREST WAY (MP 15.1) | D |  | STP | 2021 | 330000 | 264000 |  |  | 66000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.271 | 2021-01-12 | TIP FY 20-25, AMEND#2; ADD PROJECT TO STIP; NEW |  |  | JEFFERSON | 5-8952 | US 60 |  |  |  | RELIABILITY | MINOR WIDENING(O) | WIDEN US 60 TO THREE LANES FROM EASTWOOD CUTOFF (MP 14.7) TO ROCKCREST WAY (MP 15.1) | R |  | STP | 2023 | 410000 | 328000 |  |  | 82000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.271 | 2021-01-12 | TIP FY 20-25, AMEND#2; ADD PROJECT TO STIP; NEW |  |  | JEFFERSON | 5-8952 | US 60 |  |  |  | RELIABILITY | MINOR WIDENING(O) | WIDEN US 60 TO THREE LANES FROM EASTWOOD CUTOFF (MP 14.7) TO ROCKCREST WAY (MP 15.1) | U |  | STP | 2024 | 460000 | 368000 |  |  | 92000 | [5 empty] | 0
TIP | [6 empty] | Not in STIP |  |  | Jefferson | 5-8953 | KY 1747 | [5 empty] | Improve the Hurstbourne Parkway (KY 1747) at Shelbyville Road (US 60) intersection to increase capacity, reduce delays, and improve safety. | U |  | STP-ST | 2019 | 1040000 | 1040000 | [8 empty] | 0
TIP | [6 empty] | Not in STIP |  |  | Jefferson | 5-8953 | KY 1747 | [5 empty] | Improve the Hurstbourne Parkway (KY 1747) at Shelbyville Road (US 60) intersection to increase capacity, reduce delays, and improve safety. | R |  | STP-ST | 2019 | 750000 | 750000 | [8 empty] | 0
TIP | [6 empty] | Not in STIP |  |  | Jefferson | 5-8953 | KY 1747 | [5 empty] | Improve the Hurstbourne Parkway (KY 1747) at Shelbyville Road (US 60) intersection to increase capacity, reduce delays, and improve safety. | C |  | STP-ST | 2021 | 2600000 | 2600000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.271 | 2021-01-12 | TIP FY 20-25, AMEND#2; ADD D PHASE TO STIP; NEW |  |  | Jefferson | 5-8954 | KY 155 |  | 0 | 4.247 | RELIABILITY | RECONSTRUCTION(O) | CONSTRUCT A 2+1 ROAD ON KY 55/155 (TAYLORSVILLE ROAD) IN SPENCER COUNTY AND KY 155 (TAYLORSVILLE LAKE ROAD) IN JEFFERSON COUNTY BY ADDING A CONTINUOUS THIRD LANE THAT SERVES AS AN ALTERNATING PASSING LANE.(16CCN)(18CCN) (2020CCR) | D |  | STP | 2021 | 1000000 | 800000 |  |  | 200000 | [5 empty] | 0
TIP | [6 empty] | Not in STIP |  |  | Jefferson | 5-9010.10 | KY 61 & Grade Lane | [5 empty] | Reconstruct radius for right turn from Grade Lane to SB KY 61, reconstruct sidewalk ramps, rebuild traffic signal, and update signing, striping, and pavement markings at intersection of KY 61 and Grade Lane. | R |  | Safety | 2018 | 40000 | 40000 | [8 empty] | 0
TIP | [6 empty] | Not in STIP | HSIP | 8738033 | Jefferson | 5-9010.10 | KY 61 & Grade Lane | [5 empty] | Reconstruct radius for right turn from Grade Lane to SB KY 61, reconstruct sidewalk ramps, rebuild traffic signal, and update signing, striping, and pavement markings at intersection of KY 61 and Grade Lane. | C |  | Safety | 2018 | 340000 | 340000 | [5 empty] | OBLIGATED | 502397 |  | 502397 | 2019 | 2ND QUARTER
TIP | [6 empty] | Not in STIP |  |  | Jefferson | 5-9010.10 | KY 61 & Grade Lane | [5 empty] | Reconstruct radius for right turn from Grade Lane to SB KY 61, reconstruct sidewalk ramps, rebuild traffic signal, and update signing, striping, and pavement markings at intersection of KY 61 and Grade Lane. | U |  | Safety | 2018 | 25000 | 25000 | [8 empty] | 0
TIP | [6 empty] | Not in STIP |  |  | Jefferson | 5-9010.30 | KY 1065 & KY 1865 | [5 empty] | Construct right turn lanes along KY 1065, reconstruct sidewalk ramps, install pedestrian signals, and update signing, striping, and pavement markings at the intersection of KY 1065 and KY 1865. | R |  | Safety | 2018 | 16000 | 16000 | [8 empty] | 0
TIP | [6 empty] | Not in STIP | HSIP | 8732017 | Jefferson | 5-9010.30 | KY 1065 & KY 1865 | [5 empty] | Construct right turn lanes along KY 1065, reconstruct sidewalk ramps, install pedestrian signals, and update signing, striping, and pavement markings at the intersection of KY 1065 and KY 1865. | C |  | Safety | 2018 | 310000 | 310000 | [5 empty] | OBLIGATED |  | 418039 | 418039 | 2019 | 2ND QUARTER
TIP | [6 empty] | Not in STIP |  |  | Jefferson | 5-9010.30 | KY 1065 & KY 1865 | [5 empty] | Construct right turn lanes along KY 1065, reconstruct sidewalk ramps, install pedestrian signals, and update signing, striping, and pavement markings at the intersection of KY 1065 and KY 1865. | U |  | Safety | 2018 | 150000 | 150000 | [8 empty] | 0
TIP | [6 empty] | Not in STIP |  |  | Jefferson | 5-9010.50 | US 31W & Pendleton Road | [5 empty] | Construct sidewalks and sidewalk ramps, and update signing, striping, and pavement markings at intersection of US 31W and Pendleton Road. | R |  | Safety | 2018 | 15000 | 15000 | [8 empty] | 0
TIP | [6 empty] | Not in STIP | HSIP | 0311041 | Jefferson | 5-9010.50 | US 31W & Pendleton Road | [5 empty] | Construct sidewalks and sidewalk ramps, and update signing, striping, and pavement markings at intersection of US 31W and Pendleton Road. | C |  | Safety | 2018 | 35000 | 35000 | [5 empty] | OBLIGATED |  | 48666 | 48666 | 2019 | 2ND QUARTER
TIP | [6 empty] | Not in STIP | HSIP | 9010323 | Jefferson | 5-9015 | HSIP Roadway Safety Study | [5 empty] | KYTC-Louisvlle Metro Roadway Safety Study Plan for all public roads in the Louisville Metro Area in Jefferson County. | P |  | Safety | 2019 | 500000 | 500000 | [5 empty] | OBLIGATED | 635000 |  | 635000 | 2020 | 2ND QUARTER
TIP | [6 empty] | Not in STIP |  |  | Jefferson | 5-9016 | KY 864 | [5 empty] | Widen KY 864 to create a northbound left turn lane between mile points 5.950 and 6.200. | C |  | Safety | 2019 | 250000 | 250000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.201 | 2020-07-01 | TIP FY 20-25, ADMIN MOD#4; REVISE FY TO 2021 & REVISE FUND AMOUNT; MOD |  |  | Jefferson | 5-9016 | KY 864 |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | Widen KY 864 to create a northbound left turn lane between mile points 5.950 and 6.200. | C |  | SAF | 2021 | 330000 | 330000 | [8 empty] | 0
TIP | [6 empty] | Not in STIP |  |  | Jefferson | 5-9016 | KY 864 | [5 empty] | Widen KY 864 to create a northbound left turn lane between mile points 5.950 and 6.200. | U |  | Safety | 2019 | 220000 | 220000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.201 | 2020-07-01 | TIP FY 20-25, ADMIN MOD#4; REDUCE FUND AMOUNT; MOD |  |  | Jefferson | 5-9016 | KY 864 |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | Widen KY 864 to create a northbound left turn lane between mile points 5.950 and 6.200. | U |  | SAF | 2020 | 25000 | 25000 | [8 empty] | 0
TIP | [6 empty] | Not in STIP |  |  | Jefferson | 5-9016 | KY 864 | [5 empty] | Widen KY 864 to create a northbound left turn lane between mile points 5.950 and 6.200. | D |  | Safety | 2018 | 125000 | 125000 | [8 empty] | 0
TIP | [6 empty] | Not in STIP | HSIP | 9010351 | Jefferson | 5-9019 | Various Intersection Improvement Projects in Jefferson County | [5 empty] | Preliminary design and study to determine low cost improvements at various intersections within Jefferson County: 1. KY 1865 at on and off ramps for EB 1-264 and Exit 9 and West Ashland Ave between mile points 5.404 and 5.604. 2. US 150 at KY 1020 Intersection between mile points 2.460 and 2.660. 3. KY 1065 at Grade Lane between mile points 3.094 and 3.294. 4. KY 1934 at KY 1727 between mile points 7.082 and 7.282. 5. W. Broadway (CS-1021F) at S. 26th Street (CS-1038F) between mile points 0.263 and 0.463. 6. KY 1747 at on and off ramps between mile points 11.890 and 12.090. 7. US 60A at SB KY 61 between mile points 4.450 and 4.650. 8. US 31W at Blanton Lane between mile points 12.435 and 12.635. 9. KY 1934 at KY 2051 between mile points 7.624 and 7.824. 10. KY 61 at Glen Rose Road at Boerste Way between mile points 2.026 and 2.226. 11. US 31W at San Jose Ave between mile points 14.077 and 14.277. | D |  | Safety | 2019 | 900000 | 900000 | [5 empty] | OBLIGATED |  | 900000 | 900000 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.201 | 2020-07-01 | TIP FY 20-25, ADMIN MOD#4; ADD PROJECT TO STIP; NEW |  |  | JEFFERSON | 5-9019.10 | KY 1865 I 264 |  | 5.396 .173 | 5.706 .293 | SAFETY | SAFETY-HAZARD ELIM(P) | IMPROVE THE RIGHT TURN LANE AND RADIUS ON THE EB I-265 OFF RAMP AT EXIT 9 AND UPDATE THE STRIPING, PAVEMENT MARKINGS, AND SIGNING AT THE INTERSECTION OF TAYLOR BLVD & THE I-264 WB OFF RAMP. (2018BOP) | C |  | SAF | 2021 | 250000 | 225000 |  |  |  | 25000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.213 | 2020-07-24 | TIP FY 20-25, ADMIN MOD#5; ADD PROJECT TO STIP; NEW |  |  | JEFFERSON | 5-9019.3 | KY 1065 |  | 3.094 | 3.294 | SAFETY | SAFETY-HAZARD ELIM(P) | REALIGN THE RIGHT TURN SLIP RAMP FROM GRADE LANE ONTO KY 1065. (2018BOP) | C |  | SAF | 2021 | 130000 | 117000 |  |  |  | 13000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.213 | 2020-07-24 | TIP FY 20-25, ADMIN MOD#5; ADD PROJECT TO STIP; NEW |  |  | JEFFERSON | 5-9019.4 | KY 1934 KY 1727 |  | 7.052 3.981 | 7.24 4.055 | SAFETY | SAFETY-HAZARD ELIM(P) | IMPROVEMENTS TO REDUCE CONFLICT POINTS AND ENHANCE SAFETY AT THE INTERSECTION OF KY 1934 & KY 1727. (2018BOP) | C |  | SAF | 2021 | 300000 | 270000 |  |  |  | 30000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.213 | 2020-07-24 | TIP FY 20-25, ADMIN MOD#5; ADD PROJECT TO STIP; NEW |  |  | JEFFERSON | 5-9019.5 | CS 1021 CS 1038 |  | .183 .706 | .457 .874 | SAFETY | SAFETY-HAZARD ELIM(P) | UPDATE THE STRIPING AND PAVEMENT MARKINGS ALONG W BROADWAY AND S 26TH ST NEAR THE INTERSECTION OF W BROADWAY & S 26TH ST. (2018BOP) | C |  | SAF | 2021 | 40000 | 40000 |  |  |  | 0 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.201 | 2020-07-01 | TIP FY 20-25, ADMIN MOD#4; ADD PROJECT TO STIP; NEW |  |  | Jefferson | 5-9019.6 | KY 1747 |  | 11.291 | 12.451 | SAFETY | SAFETY-HAZARD ELIM(P) | UPDATE THE SIGNAL SYSTEM DETECTION FOR THE SIGNALIZED INTERSECTIONS ALONG HURSTBOURNE LANE FROM BUNSEN PARKWAY TO LINN STATION ROAD. (2018BOP) | C |  | SAF | 2021 | 240000 | 240000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.213 | 2020-07-24 | TIP FY 20-25, ADMIN MOD#5; ADD PROJECT TO STIP; NEW |  |  | JEFFERSON | 5-9019.65 | KY 1747 I 64 |  | 11.8 .213 | 12.289 .303 | SAFETY | SAFETY-HAZARD ELIM(P) | IMPROVE LANE ALIGNMENT AND TURNING RADIUS OF THE WB I-64 OFF RAMP AT EXIT 15 AND UPDATE THE STRIPING, PAVEMENT MARKINGS AND SIGNING AT THE INTERSECTION OF HURSTBOURNE LANE & THE I-64 WB OFF RAMP. (2018BOP) | C |  | SAF | 2021 | 125000 | 112500 |  |  |  | 12500 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.226 | 2020-08-28 | TIP FY 20-25, ADMIN MOD#7, ADD PROJECT TO STIP; NEW |  |  | JEFFERSON | 5-9019.7 | US 60A |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALL LIGHTING ALONG EASTERN PARKWAY NEAR THE INTERSECTIONS WITH SOUTH PRESTON STREET AND SOUTH SHELBY STREET. | C |  | SAF | 2021 | 45000 | 40500 |  |  |  | 4500 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.213 | 2020-07-24 | TIP FY 20-25, ADMIN MOD#5; ADD PROJECT TO STIP; NEW |  |  | JEFFERSON | 5-9019.9 | KY 1934 KY 2051 |  | 7.54 1.852 | 7.99 2.089 | SAFETY | SAFETY-HAZARD ELIM(P) | IMPROVEMENTS TO REDUCE CONFLICT POINTS AND ENHANCE SAFETY AT THE INTERSECTION OF KY 1934 & KY 2051. (2018BOP) | C |  | SAF | 2021 | 300000 | 270000 |  |  |  | 30000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.117 | 2019-08-09 | TIP FY 18-21; ADMIN MOD#34, ADD PROJECT TO STIP; NEW | HSIP | 5125016 | JEFFERSON | 5-9021 | KY 155 |  | 4.49 | 5.99 | SAFETY | SAFETY-HAZARD ELIM(P) | STUDY SAFETY IMPROVEMENTS ALONG KY 155 IN JEFFERSON COUNTY FROM MP 4.49 TO 5.99(2018BOP) | D |  | SAF | 2019 | 250000 | 250000 | [5 empty] | OBLIGATED |  | 250000 | 250000 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.117 | 2019-08-09 | TIP FY 18-21; ADMIN MOD#34, ADD PROJECT TO STIP; NEW |  |  | JEFFERSON | 5-9021 | KY 155 |  | 4.49 | 5.99 | SAFETY | SAFETY-HAZARD ELIM(P) | STUDY SAFETY IMPROVEMENTS ALONG KY 155 IN JEFFERSON COUNTY FROM MP 4.49 TO 5.99(2018BOP) | C |  | SAF | 2020 | 750000 | 750000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.299 | 2021-04-26 | TIP FY 20-25, ADMIN MOD#16; ADD PROJECT TO STIP; NEW |  |  | JEFFERSON | 5-9030 | US 31E |  | 14.5 | 16 | RELIABILITY | SAFETY-HAZARD ELIM(P) | Overlay and restripe Bardstown Rd to convert from a reversible 4-Lane section to a 3-Lane section between Eastern Parkway and E Broadway and construct curb bump outs, enhanced crosswalks, and other low-cost safety improvements. | D |  | SAF | 2021 | 50000 | 45000 |  |  | 5000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.299 | 2021-04-26 | TIP FY 20-25, ADMIN MOD#16; ADD PROJECT TO STIP; NEW |  |  | JEFFERSON | 5-9030 | US 31E |  | 14.5 | 16 | RELIABILITY | SAFETY-HAZARD ELIM(P) | Overlay and restripe Bardstown Rd to convert from a reversible 4-Lane section to a 3-Lane section between Eastern Parkway and E Broadway and construct curb bump outs, enhanced crosswalks, and other low-cost safety improvements. | C |  | SAF | 2022 | 925000 | 832500 |  |  | 92500 | [5 empty] | 0
STIP | [9 empty] | JEFFERSON | 5-10007 | CR 1004J |  | 0.488 | 0.498 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF CLARK STATION RD BRIDGE OVER S LONG RUN. (056C00091N) | D |  | BR/STP | 2019 | 280000 | 173600 |  |  | 106400 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; UPDATE FISCAL YEAR; MOD |  |  | JEFFERSON | 5-10007 | CR 1004J |  | 0.488 | 0.498 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF CLARK STATION RD BRIDGE OVER S LONG RUN. (056C00091N) | D |  | BR/STP | 2020 | 280000 | 173600 |  |  |  | 106400 |  |  |  |  | 0
STIP | [9 empty] | JEFFERSON | 5-10007 | CR 1004J |  | 0.488 | 0.498 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF CLARK STATION RD BRIDGE OVER S LONG RUN. (056C00091N) | C |  | BR/STP | 2020 | 350000 | 217000 |  |  | 133000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; UPDATE FISCAL YEAR AND FUND AMOUNTS; MOD |  |  | JEFFERSON | 5-10007 | CR 1004J |  | 0.488 | 0.498 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF CLARK STATION RD BRIDGE OVER S LONG RUN. (056C00091N) | C |  | BR/STP | 2021 | 400000 | 400000 |  |  |  | 100000 |  |  |  |  | 0
STIP | [9 empty] | JEFFERSON | 5-10008 | CS 1079C |  | 0.03 | 0.038 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF OLD WESTPORT RD BRIDGE OVER GOOSE CREEK. (056C00113N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; UPDATE FISCAL YEAR; MOD |  |  | JEFFERSON | 5-10008 | CS 1079C |  | 0.03 | 0.038 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF OLD WESTPORT RD BRIDGE OVER GOOSE CREEK. (056C00113N) | D |  | BR/STP | 2020 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [9 empty] | JEFFERSON | 5-10008 | CS 1079C |  | 0.03 | 0.038 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF OLD WESTPORT RD BRIDGE OVER GOOSE CREEK. (056C00113N) | C |  | BR/STP | 2020 | 301000 | 186620 |  |  | 114380 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; UPDATE FISCAL YEAR AND FUND AMOUNTS; MOD |  |  | JEFFERSON | 5-10008 | CS 1079C |  | 0.03 | 0.038 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF OLD WESTPORT RD BRIDGE OVER GOOSE CREEK. (056C00113N) | C |  | BR/STP | 2021 | 750000 | 600000 |  |  | 150000 | [5 empty] | 0
STIP | [9 empty] | JEFFERSON | 5-10009 | CR 1007L |  | 0.997 | 1.035 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF PENDLETON RD BRIDGE OVER POND CREEK. (056C00118N)(SD) | D |  | BR/STP | 2019 | 245000 | 151900 |  |  | 93100 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030029 | JEFFERSON | 5-10009 | CR 1007L |  | 0.997 | 1.035 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF PENDLETON RD BRIDGE OVER POND CREEK. (056C00118N)(SD) | C |  | BR/STP | 2020 | 1106000 | 685720 |  |  | 420280 |  |  | OBLIGATED | 480525 |  | 480525 | 2019 | 2ND QUARTER
STIP | [9 empty] | JEFFERSON | 5-10010 | CR 1005H |  | 0.685 | 0.691 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF S WATTERSON TRL BRIDGE OVER FERN CREEK. (056C00159N) | D |  | BR/STP | 2019 | 245000 | 151900 |  |  | 93100 | [5 empty] | 0
STIP | [9 empty] | JEFFERSON | 5-10010 | CR 1005H |  | 0.685 | 0.691 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF S WATTERSON TRL BRIDGE OVER FERN CREEK. (056C00159N) | C |  | BR/STP | 2020 | 301000 | 186620 |  |  | 114380 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.036 | 2019-03-12 | TIP FY 18-21; ADMIN MOD#27; UPDATE THE FISCAL YEAR & FUND AMOUNTS ON C PHASE; MOD | STPBRZ | 9030026 | JEFFERSON | 5-10010 | CR 1005H |  | 0.685 | 0.691 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF S WATTERSON TRL BRIDGE OVER FERN CREEK. (056C00159N) | C |  | BR/STP | 2019 | 755670 | 604536 |  |  | 151134 |  |  | OBLIGATED |  | 671895.16 | 671895.16 | 2019 | 2ND QUARTER
STIP | [9 empty] | JEFFERSON | 5-10011 | CS 1096B |  | 0.008 | 0.022 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF STONEBRIDGE RD BRIDGE OVER TRIB MUDDY FK BEARGRASS. (056C00240N) | D |  | BR/STP | 2019 | 210000 | 130200 |  |  | 79800 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.136 | 2019-09-30 | TIP FY 18-21; ADMIN MOD#36; UPDATE KIPDA ID TO 2675 & FISCAL YEAR TO 2020; MOD |  |  | JEFFERSON | 5-10011 | CS 1096B |  | 0.008 | 0.022 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF STONEBRIDGE RD BRIDGE OVER TRIB MUDDY FK BEARGRASS. (056C00240N) | D |  | BR/STP | 2020 | 210000 | 130200 |  |  | 79800 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; UPDATE FISCAL YEAR AND FUND AMOUNTS; MOD |  |  | JEFFERSON | 5-10011 | CS 1096B |  | 0.008 | 0.022 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF STONEBRIDGE RD BRIDGE OVER TRIB MUDDY FK BEARGRASS. (056C00240N) | D |  | BR/STP | 2021 | 160000 | 128000 |  |  | 32000 | [5 empty] | 0
STIP | [9 empty] | JEFFERSON | 5-10011 | CS 1096B |  | 0.008 | 0.022 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF STONEBRIDGE RD BRIDGE OVER TRIB MUDDY FK BEARGRASS. (056C00240N) | C |  | BR/STP | 2020 | 266000 | 164920 |  |  | 101080 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.136 | 2019-09-30 | TIP FY 18-21; ADMIN MOD#36; UPDATE KIPDA ID TO 2675 & INCREASE FUND AMOUNTS; MOD |  |  | JEFFERSON | 5-10011 | CS 1096B |  | 0.008 | 0.022 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF STONEBRIDGE RD BRIDGE OVER TRIB MUDDY FK BEARGRASS. (056C00240N) | C |  | BR/STP | 2020 | 528000 | 327360 |  |  | 200640 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; UPDATE FISCAL YEAR AND FUND AMOUNTS; MOD |  |  | JEFFERSON | 5-10011 | CS 1096B |  | 0.008 | 0.022 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF STONEBRIDGE RD BRIDGE OVER TRIB MUDDY FK BEARGRASS. (056C00240N) | C |  | BR/STP | 2021 | 550000 | 440000 |  |  | 110000 | [5 empty] | 0
TIP | [6 empty] | Not in STIP |  |  | Jefferson | 5-10012 | KY 1488 | [5 empty] | Address deficiencies of KY 1488 bridge over Organ Creek (093B00048N) from MP 2.031 to MP 2.037. | D |  | STP-ST | 2019 | 280000 | 173600 | [8 empty] | 0
TIP | [6 empty] | Not in STIP | STPBRZ | 9030084 | Jefferson | 5-10012 | KY 1488 | [5 empty] | Address deficiencies of KY 1488 bridge over Organ Creek (093B00048N) from MP 2.031 to MP 2.037. | C |  | STP-ST | 2020 | 343000 | 212660 | [5 empty] | OBLIGATED |  | 733145 | 733145 | 2019 | 3RD QUARTER
STIP | [6 empty] | Not in TIP |  |  | JEFFERSON | 5-10015 | I 64 |  |  |  | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES ON I-64 RIVERSIDE EXPRESSWAY BRIDGES. (056B00298N,056B00299N,056B00300N,056B00301N,056B00302N,056B00285N,056B00292N,056B00293N,056B00142N)(SD) | D |  | BR/NH | 2019 | 350000 | 217000 |  |  | 133000 | [5 empty] | 0
STIP | [6 empty] | Not in TIP |  |  | JEFFERSON | 5-10015 | I 64 |  |  |  | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES ON I-64 RIVERSIDE EXPRESSWAY BRIDGES. (056B00298N,056B00299N,056B00300N,056B00301N,056B00302N,056B00285N,056B00292N,056B00293N,056B00142N)(SD) | C |  | BR/NH | 2019 | 4600000 | 2852000 |  |  | 1748000 | [5 empty] | 0
STIP | [6 empty] | Not in TIP |  |  | JEFFERSON | 5-10016 | I 64 |  |  |  | ASSET MANAGEMENT | AM-BRG PAINTING(P) | BRIDGE PAINTING OF I-64 RIVERSIDE EXPRESSWAY BRIDGES.(056B00298N,056B00299N,056B00300N,056B00301N,056B00302N,056B00285N,056B00292N,056B00293N,056B00142N) | C |  | BR/NH | 2021 | 30000000 | 18600000 |  |  | 11400000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.271 | 2021-01-12 | TIP FY 20-25, AMEND#2; UPDATE FISCAL YEAR & FUND AMOUNTS; MOD |  |  | JEFFERSON | 5-10016 | I 64 |  |  |  | ASSET MANAGEMENT | AM-BRG PAINTING(P) | BRIDGE PAINTING OF I-64 RIVERSIDE EXPRESSWAY BRIDGES.(056B00298N,056B00299N,056B00300N,056B00301N,056B00302N,056B00285N,056B00292N,056B00293N,056B00142N) | C |  | BR/NH | 2024 | 5000000 | 4000000 |  |  | 1000000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.271 | 2021-01-12 | TIP FY 20-25, AMEND#2; UPDATE FISCAL YEAR & FUND AMOUNTS; MOD |  |  | JEFFERSON | 5-10016 | I 64 |  |  |  | ASSET MANAGEMENT | AM-BRG PAINTING(P) | BRIDGE PAINTING OF I-64 RIVERSIDE EXPRESSWAY BRIDGES.(056B00298N,056B00299N,056B00300N,056B00301N,056B00302N,056B00285N,056B00292N,056B00293N,056B00142N) | C |  | BR/NH | 2025 | 15000000 | 12000000 |  |  | 3000000 | [5 empty] | 0
STIP | [9 empty] | JEFFERSON | 5-10018 | US 31E |  | 16.353 | 16.361 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF US 31E BRIDGE OVER S FK BEARGRASS CREEK. (056B00137N) | D |  | BR/NH | 2019 | 350000 | 217000 |  |  | 133000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; UPDATE FISCAL YEAR AND FUND AMOUNTS; MOD |  |  | JEFFERSON | 5-10018 | US 31E |  | 16.353 | 16.361 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF US 31E BRIDGE OVER S FK BEARGRASS CREEK. (056B00137N) | D |  | BR/STP | 2020 | 224000 | 91000 |  |  | 133000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; UPDATE FISCAL YEAR, FUND TYPE AND FUND AMOUNT; MOD |  |  | JEFFERSON | 5-10018 | US 31E |  | 16.353 | 16.361 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF US 31E BRIDGE OVER S FK BEARGRASS CREEK. (056B00137N) | D |  | NHPP | 2020 | 126000 | 126000 | [8 empty] | 0
STIP | [7 empty] | STPBRZ | 9030243 | JEFFERSON | 5-10018 | US 31E |  | 16.353 | 16.361 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF US 31E BRIDGE OVER S FK BEARGRASS CREEK. (056B00137N) | C |  | BR/NH | 2020 | 966000 | 598920 |  |  | 367080 |  |  | OBLIGATED | 200000 | 875760 | 1075760 | 2020 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; UPDATE FISCAL YEAR AND FUND AMOUNTS; MOD |  |  | JEFFERSON | 5-10018 | US 31E |  | 16.353 | 16.361 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF US 31E BRIDGE OVER S FK BEARGRASS CREEK. (056B00137N) | C |  | NHPP | 2021 | 690000 | 552000 |  |  | 138000 | [5 empty] | 0
STIP | [9 empty] | JEFFERSON | 5-10019 | CS 1003G |  | 1.796 | 1.808 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF SCENIC LOOP BRIDGE OVER MID FK BEARGRASS CREEK. (056C00027N) | D |  | BR/STP | 2019 | 140000 | 86800 |  |  | 53200 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; UPDATE FISCAL YEAR AND FUND AMOUNTS; MOD |  |  | JEFFERSON | 5-10019 | CS 1003G |  | 1.796 | 1.808 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF SCENIC LOOP BRIDGE OVER MID FK BEARGRASS CREEK. (056C00027N) | D |  | BR/STP | 2021 | 60000 | 48000 |  |  | 12000 | [5 empty] | 0
STIP | [9 empty] | JEFFERSON | 5-10019 | CS 1003G |  | 1.796 | 1.808 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF SCENIC LOOP BRIDGE OVER MID FK BEARGRASS CREEK. (056C00027N) | C |  | BR/STP | 2020 | 406000 | 251720 |  |  | 154280 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; UPDATE FISCAL YEAR AND FUND AMOUNTS; MOD |  |  | JEFFERSON | 5-10019 | CS 1003G |  | 1.796 | 1.808 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF SCENIC LOOP BRIDGE OVER MID FK BEARGRASS CREEK. (056C00027N) | C |  | BR/STP | 2021 | 440000 | 352000 |  |  | 88000 | [5 empty] | 0
STIP | [9 empty] | JEFFERSON | 5-10020 | CS 3396 |  | 0.01 | 0.018 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF PARK BOUNDARY RD BRIDGE OVER MID FK BEARGRASS CREEK. (056C00033N) | D |  | BR/STP | 2019 | 140000 | 86800 |  |  | 53200 | [5 empty] | 0
STIP | [9 empty] | JEFFERSON | 5-10020 | CS 3396 |  | 0.01 | 0.018 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF PARK BOUNDARY RD BRIDGE OVER MID FK BEARGRASS CREEK. (056C00033N) | C |  | BR/STP | 2020 | 441000 | 273420 |  |  | 167580 | [5 empty] | 0
STIP | [9 empty] | JEFFERSON | 5-10021 | CR 1021 |  | 0.71 | 0.728 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF CHAMPIONS TRACE LN BRIDGE OVER S FK BEARGRASS CREEK. (056C00096N) | D |  | BR/STP | 2019 | 280000 | 173600 |  |  | 106400 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030095 | JEFFERSON | 5-10021 | CR 1021 |  | 0.71 | 0.728 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF CHAMPIONS TRACE LN BRIDGE OVER S FK BEARGRASS CREEK. (056C00096N) | C |  | BR/STP | 2020 | 1190000 | 737800 |  |  | 452200 |  |  | OBLIGATED |  | 1154895 | 1154895 | 2019 | 3RD QUARTER
STIP | [9 empty] | JEFFERSON | 5-10022 | CS 1004J |  | 0.006 | 0.014 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF OLD CLARK STATION BRIDGE OVER BRUSH RUN. (056C00167N) | D |  | BR/STP | 2019 | 140000 | 86800 |  |  | 53200 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; UPDATE FISCAL YEAR; MOD |  |  | JEFFERSON | 5-10022 | CS 1004J |  | 0.006 | 0.014 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF OLD CLARK STATION BRIDGE OVER BRUSH RUN. (056C00167N) | D |  | BR/STP | 2020 | 140000 | 86800 |  |  | 53200 | [5 empty] | 0
STIP | [9 empty] | JEFFERSON | 5-10022 | CS 1004J |  | 0.006 | 0.014 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF OLD CLARK STATION BRIDGE OVER BRUSH RUN. (056C00167N) | C |  | BR/STP | 2020 | 357000 | 221340 |  |  | 135660 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; UPDATE FISCAL YEAR AND FUND AMOUNTS; MOD |  |  | JEFFERSON | 5-10022 | CS 1004J |  | 0.006 | 0.014 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF OLD CLARK STATION BRIDGE OVER BRUSH RUN. (056C00167N) | C |  | BR/STP | 2021 | 357000 | 285600 |  |  | 71400 | [5 empty] | 0
STIP | [9 empty] | JEFFERSON | 5-10023 | CS 1325H |  | 0.059 | 0.063 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KIMBERLY WAY BRIDGE OVER LITTLE CEDAR CREEK. (056C00182N) | D |  | BR/STP | 2019 | 140000 | 86800 |  |  | 53200 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030154 | JEFFERSON | 5-10023 | CS 1325H |  | 0.059 | 0.063 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KIMBERLY WAY BRIDGE OVER LITTLE CEDAR CREEK. (056C00182N) | C |  | BR/STP | 2020 | 217000 | 134540 |  |  | 82460 |  |  | OBLIGATED |  | 386400 | 386400 | 2019 | 4TH QUARTER
STIP | [7 empty] | NHPPIM | 0655121 | Jefferson | 5-10028 | Various Interstate Bridge Maintenance | [5 empty] | Preventative maintenance on various structures along I-65 and at intersection of Preston Highway/I-264 in Jefferson County. (056B00342N, 056B00388N, 056B00391N, 056B00394N) | C |  | IM | 2019 | 2275000 | 2275000 | [5 empty] | OBLIGATED | 2656820 |  | 2656820 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.165 | 2020-02-03 | TIP 18-21, ADMIN MOD#42; ADD PROJECT TO STIP; GROUP ID 2675 (ROADWAY & BRIDGE PRESERVATION & REHABILITATION); NEW |  |  | JEFFERSON | 5-10029 | KY 1450 |  | 3.02 | 3.03 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES ON KY 1450 OVER FISHPOOL CREEK. (056B00078N) | C |  | STP | 2020 | 505000 | 404000 |  |  |  | 101000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.223 | 2020-08-25 | TIP FY 20-25, ADMIN MOD#6; ADD PROJECT TO STIP; NEW |  |  | JEFFERSON | 5-10032 | I-65 |  |  |  | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES ON I-65 BROOK STREET STRUCTURE BRIDGE. | C |  | NHPP | 2020 | 625000 | 562500 |  |  |  | 62500 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; ADD PROJECT TO STIP; NEW |  |  | JEFFERSON | 5-20009 | I 64 |  |  |  | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-064 BOTH DIRECTION(S) FROM MILEPOINT 6 TO MILEPOINT 11.57 (2020CCR) | D |  | NHPP | 2022 | 575000 | 460000 |  |  | 115000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; ADD C PHASE TO STIP FOR FY 2023; NEW |  |  | JEFFERSON | 5-20009 | I 64 |  |  |  | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-064 BOTH DIRECTION(S) FROM MILEPOINT 6 TO MILEPOINT 11.57 (2020CCR) | C |  | NHPP | 2023 | 2500000 | 2000000 |  |  | 500000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; ADD C PHASE TO STIP FOR FY 2024; NEW |  |  | JEFFERSON | 5-20009 | I 64 |  |  |  | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-064 BOTH DIRECTION(S) FROM MILEPOINT 6 TO MILEPOINT 11.57 (2020CCR) | C |  | NHPP | 2024 | 3250000 | 2600000 |  |  | 650000 | [5 empty] | 0
STIP | [9 empty] | JEFFERSON | 5-20010 | I 64 |  | 0.65 | 0.828 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT ON I-064 CARDINAL DIRECTION(S) FROM MILEPOINT 0.65 TO MILEPOINT 0.828 | D |  | PM/NH | 2019 | 10000 | 8000 |  |  | 2000 | [5 empty] | 0
STIP | [9 empty] | JEFFERSON | 5-20010 | I 64 |  | 0.65 | 0.828 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT ON I-064 CARDINAL DIRECTION(S) FROM MILEPOINT 0.65 TO MILEPOINT 0.828 | C |  | PM/NH | 2019 | 100000 | 80000 |  |  | 20000 | [5 empty] | 0
STIP | YES | [5 empty] | NOT IN TIP |  |  | JEFFERSON | 5-20012 | I 65 |  | 128.13 | 131.24 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-065 BOTH DIRECTION(S) FROM MILEPOINT 128.13 TO MILEPOINT 131.24 | D |  | PM/NH | 2020 | 620000 | 496000 |  |  | 124000 | [5 empty] | 0
TIP | [6 empty] | NOT IN STIP |  |  | Jefferson | 5-20012 | I-65 Repavement from Fern Valley Road to Phillips Lane | [5 empty] | Mill and place a thin asphalt overlay on I-65 (NB & SB) from the south limits of the Fern Valley Road interchange at milepoint 127.58 north to Phillips Lane at milepoint 131.24 in Jefferson County. | C |  | IM | 2018 | 3400000 | 3400000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; ADD PROJECT TO STIP; NEW |  |  | Jefferson | 5-20014 | I 71 |  | 0 | 11.32 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-071 BOTH DIRECTION(S) FROM MILEPOINT 0 TO MILEPOINT 11.32 | D |  | NHPP | 2023 | 475000 | 380000 |  |  | 95000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; ADD PROJECT TO STIP; NEW |  |  | Jefferson | 5-20014 | I 71 |  | 0 | 11.32 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-071 BOTH DIRECTION(S) FROM MILEPOINT 0 TO MILEPOINT 11.32 | C |  | NHPP | 2024 | 2400000 | 1920000 |  |  | 480000 | [5 empty] | 0
STIP | [9 empty] | JEFFERSON | 5-20015 | I 264 |  | 0 | 0.46 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-264 CARDINAL DIRECTION(S) FROM MILEPOINT 0 TO MILEPOINT 0.46 | D |  | PM/NH | 2019 | 30000 | 24000 |  |  | 6000 | [5 empty] | 0
TIP | [6 empty] | TIP AND STIP AMOUNTS ARE DIFFERENT |  |  | JEFFERSON | 5-20015 | I 264 |  | 0 | 0.46 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-264 CARDINAL DIRECTION(S) FROM MILEPOINT 0 TO MILEPOINT 0.46 | D |  | PM/NH | 2019 | 30000 | 30000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | JEFFERSON | 5-20015 | I 264 |  | 0 | 0.46 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-264 CARDINAL DIRECTION(S) FROM MILEPOINT 0 TO MILEPOINT 0.46 | C |  | PM/NH | 2019 | 300000 | 240000 |  |  | 60000 | [5 empty] | 0
TIP | [6 empty] | TIP AND STIP AMOUNTS ARE DIFFERENT |  |  | JEFFERSON | 5-20015 | I 264 |  | 0 | 0.46 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-264 CARDINAL DIRECTION(S) FROM MILEPOINT 0 TO MILEPOINT 0.46 | C |  | PM/NH | 2019 | 300000 | 300000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25; ADMIN MOD#9; ADD PROJECT TO STIP; NEW |  |  | JEFFERSON | 5-20016 | I 264 |  | 12.7 | 18.41 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT ON I-264 BOTH DIRECTION(S) FROM MILEPOINT 12.7 TO MILEPOINT 18.41 (2020CCR) | D |  | NH | 2022 | 1150000 | 920000 |  |  |  | 230000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25; ADMIN MOD#9; ADD C PHASE FOR FY 2023 TO STIP; NEW |  |  | JEFFERSON | 5-20016 | I 264 |  | 12.7 | 18.41 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT ON I-264 BOTH DIRECTION(S) FROM MILEPOINT 12.7 TO MILEPOINT 18.41 (2020CCR) | C |  | NH | 2023 | 5000000 | 4000000 |  |  |  | 1000000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25; ADMIN MOD#9; ADD C PHASE FOR FY 2024 TO STIP; NEW |  |  | JEFFERSON | 5-20016 | I 264 |  | 12.7 | 18.41 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT ON I-264 BOTH DIRECTION(S) FROM MILEPOINT 12.7 TO MILEPOINT 18.41 (2020CCR) | C |  | NH | 2024 | 6500000 | 5200000 |  |  |  | 1300000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25; ADMIN MOD#9; ADD PROJECT TO STIP; NEW |  |  | JEFFERSON | 5-20017 | I 264 |  | 20.7 | 22.927 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-264 BOTH DIRECTIONS FROM MP 20.7 TO MP 22.927. | D |  | NH | 2023 | 450000 | 360000 |  |  |  | 90000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25; ADMIN MOD#9; ADD PROJECT TO STIP; NEW |  |  | JEFFERSON | 5-20017 | I 264 |  | 20.7 | 22.927 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-264 BOTH DIRECTIONS FROM MP 20.7 TO MP 22.927. | C |  | NH | 2024 | 4500000 | 3600000 |  |  |  | 900000 |  |  |  |  | 0
STIP | [9 empty] | JEFFERSON | 5-20018 | I 264 |  | 0.46 | 12.7 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT ON I-264 BOTH DIRECTION(S) FROM MILEPOINT 0.46 TO MILEPOINT 12.7 | D |  | PM/NH | 2020 | 1220000 | 976000 |  |  | 244000 | [5 empty] | 0
TIP | [6 empty] | TIP AND STIP AMOUNTS ARE DIFFERENT |  |  | JEFFERSON | 5-20018 | I 264 |  | 0.46 | 12.7 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT ON I-264 BOTH DIRECTION(S) FROM MILEPOINT 0.46 TO MILEPOINT 12.7 | D |  | PM/NH | 2020 | 1220000 | 1220000 |  |  | 0 | [5 empty] | 0
|  |  |  | ADMINISTRATIVE MODIFICATION | 2018.036 | 2019-03-12 | TIP FY 18-21; ADMIN MOD#27; UPDATE FUND AMOUNTS; MOD |  |  | JEFFERSON | 5-20018 | I 264 |  | 0.46 | 12.7 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT ON I-264 BOTH DIRECTION(S) FROM MILEPOINT 0.46 TO MILEPOINT 12.7 | D |  | PM/NH | 2020 | 1200000 | 1200000 | 1200000 |  | 0 | [5 empty] | 0
STIP | [9 empty] | JEFFERSON | 5-20018 | I 264 |  | 0.46 | 12.7 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT ON I-264 BOTH DIRECTION(S) FROM MILEPOINT 0.46 TO MILEPOINT 12.7 | C |  | PM/NH | 2020 | 12200000 | 9760000 |  |  | 2440000 | [5 empty] | 0
TIP | [6 empty] | TIP AND STIP AMOUNTS ARE DIFFERENT |  |  | JEFFERSON | 5-20018 | I 264 |  | 0.46 | 12.7 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT ON I-264 BOTH DIRECTION(S) FROM MILEPOINT 0.46 TO MILEPOINT 12.7 | C |  | PM/NH | 2020 | 12200000 | 12200000 |  |  | 0 | [5 empty] | 0
STIP | YES | [8 empty] | JEFFERSON | 5-20019 | I 265 |  | 15.66 | 18.8 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT ON I-265 BOTH DIRECTION(S) FROM MILEPOINT 15.66 TO MILEPOINT 18.8 | D |  | PM/NH | 2022 | 325000 | 260000 |  |  | 65000 | [5 empty] | 0
STIP | YES | [8 empty] | JEFFERSON | 5-20019 | I 265 |  | 15.66 | 18.8 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT ON I-265 BOTH DIRECTION(S) FROM MILEPOINT 15.66 TO MILEPOINT 18.8 | C |  | PM/NH | 2022 | 3250000 | 2600000 |  |  | 650000 | [5 empty] | 0
STIP | [9 empty] | JEFFERSON | 5-20020 | I 265 |  | 18.8 | 23.364 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT ON I-265 BOTH DIRECTION(S) FROM MILEPOINT 18.8 TO MILEPOINT 23.364 | D |  | PM/NH | 2019 | 460000 | 368000 |  |  | 92000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; UPDATE FISCAL YEAR; MOD |  |  | JEFFERSON | 5-20020 | I 265 |  | 18.8 | 23.364 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT ON I-265 BOTH DIRECTION(S) FROM MILEPOINT 18.8 TO MILEPOINT 23.364 | D |  | PM/NH | 2021 | 460000 | 368000 |  |  | 92000 | [5 empty] | 0
TIP | [7 empty] | NHPPIM | 2652026 | JEFFERSON | 5-20020 | I 265 |  | 18.8 | 23.364 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT ON I-265 BOTH DIRECTION(S) FROM MILEPOINT 18.8 TO MILEPOINT 23.364 | C |  | PM/NH | 2019 | 4600000 | 4600000 | [5 empty] | OBLIGATED | 300000 | 3223140 | 3523140 | 2020 | 1ST QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; UPDATE FISCAL YEAR AND FUND AMOUNTS; MOD |  |  | JEFFERSON | 5-20020 | I 265 |  | 18.8 | 23.364 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT ON I-265 BOTH DIRECTION(S) FROM MILEPOINT 18.8 TO MILEPOINT 23.364 | C |  | PM/NH | 2021 | 4600000 | 3680000 |  |  | 920000 | [5 empty] | 0
STIP | YES | [8 empty] | JEFFERSON | 5-20021 | I 265 |  | 23.364 | 26.6 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-265 BOTH DIRECTION(S) FROM MILEPOINT 23.364 TO MILEPOINT 26.6 | D |  | PM/NH | 2022 | 350000 | 280000 |  |  | 70000 | [5 empty] | 0
STIP | YES | [8 empty] | JEFFERSON | 5-20021 | I 265 |  | 23.364 | 26.6 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-265 BOTH DIRECTION(S) FROM MILEPOINT 23.364 TO MILEPOINT 26.6 | C |  | PM/NH | 2022 | 3500000 | 2800000 |  |  | 700000 | [5 empty] | 0
STIP | YES | [5 empty] | Not in TIP |  |  | JEFFERSON | 5-20022 | KY 841 |  | 0 | 10.25 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | D |  | PM/STP | 2022 | 725000 | 580000 |  |  | 145000 | [5 empty] | 0
STIP | YES | [5 empty] | Not in TIP |  |  | JEFFERSON | 5-20022 | KY 841 |  | 0 | 10.25 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | C |  | PM/STP | 2022 | 7250000 | 5800000 |  |  | 1450000 | [5 empty] | 0
STIP | [9 empty] | JEFFERSON | 5-20023 | KY 864 |  | 7.111 | 11.438 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | D |  | PM/STP | 2019 | 325000 | 260000 |  |  | 65000 | [5 empty] | 0
TIP | [6 empty] | TIP AND STIP AMOUNTS ARE DIFFERENT |  |  | JEFFERSON | 5-20023 | KY 864 |  | 7.111 | 11.438 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | D |  | PM/STP | 2019 | 325000 | 325000 |  |  | 0 | [5 empty] | 0
STIP | [6 empty] | NOT IN TIP |  |  | JEFFERSON | 5-20023 | KY 864 |  | 7.111 | 11.438 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | C |  | PM/STP | 2019 | 3250000 | 2600000 |  |  | 650000 | [5 empty] | 0
STIP | [9 empty] | JEFFERSON | 5-20024 | KY 913 |  | 2.384 | 3.072 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | D |  | PM/STP | 2021 | 50000 | 40000 |  |  | 10000 | [5 empty] | 0
TIP | [6 empty] | TIP AND STIP AMOUNTS ARE DIFFERENT |  |  | JEFFERSON | 5-20024 | KY 913 |  | 2.384 | 3.072 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | D |  | PM/STP | 2021 | 50000 | 50000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; UPDATE FISCAL YEAR AND FUND TYPE; MOD |  |  | JEFFERSON | 5-20024 | KY 913 |  | 2.384 | 3.072 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | D |  | NHPP | 2022 | 50000 | 40000 |  |  | 10000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; UPDATE FISCAL YEAR & FUND AMOUNTS; MOD |  |  | JEFFERSON | 5-20024 | KY 913 |  | 2.384 | 3.072 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | D |  | NHPP | 2021 | 250000 | 200000 |  |  | 50000 | [5 empty] | 0
STIP | [9 empty] | JEFFERSON | 5-20024 | KY 913 |  | 2.384 | 3.072 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | C |  | PM/STP | 2021 | 500000 | 400000 |  |  | 100000 | [5 empty] | 0
TIP | [6 empty] | TIP AND STIP AMOUNTS ARE DIFFERENT |  |  | JEFFERSON | 5-20024 | KY 913 |  | 2.384 | 3.072 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | C |  | PM/STP | 2021 | 500000 | 500000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; UPDATE FISCAL YEAR AND FUND TYPE; MOD |  |  | JEFFERSON | 5-20024 | KY 913 |  | 2.384 | 3.072 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | C |  | NHPP | 2022 | 500000 | 400000 |  |  | 100000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; UPDATE FISCAL YEAR; MOD |  |  | JEFFERSON | 5-20024 | KY 913 |  | 2.384 | 3.072 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | C |  | NHPP | 2021 | 500000 | 400000 |  |  | 100000 | [5 empty] | 0
STIP | [9 empty] | JEFFERSON | 5-20025 | KY 1020 |  | 2.669 | 3.661 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | D |  | PM/STP | 2021 | 75000 | 60000 |  |  | 15000 | [5 empty] | 0
TIP | [6 empty] | TIP AND STIP AMOUNTS ARE DIFFERENT |  |  | JEFFERSON | 5-20025 | KY 1020 |  | 2.669 | 3.661 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | D |  | STP/ST | 2021 | 50000 | 50000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; UPDATE FUND AMOUNTS; MOD |  |  | JEFFERSON | 5-20025 | KY 1020 |  | 2.669 | 3.661 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | D |  | STP/ST | 2021 | 250000 | 200000 |  |  | 50000 | [5 empty] | 0
STIP | [9 empty] | JEFFERSON | 5-20025 | KY 1020 |  | 2.669 | 3.661 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | C |  | PM/STP | 2021 | 750000 | 600000 |  |  | 150000 | [5 empty] | 0
TIP | [6 empty] | TIP AND STIP AMOUNTS ARE DIFFERENT |  |  | JEFFERSON | 5-20025 | KY 1020 |  | 2.669 | 3.661 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | C |  | STP/ST | 2021 | 500000 | 500000 | [8 empty] | 0
STIP | [9 empty] | JEFFERSON | 5-20026 | KY 1065 |  | 2.504 | 5.25 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | D |  | PM/STP | 2019 | 200000 | 160000 |  |  | 40000 | [5 empty] | 0
TIP | [6 empty] | TIP AND STIP AMOUNTS ARE DIFFERENT |  |  | JEFFERSON | 5-20026 | KY 1065 |  | 2.504 | 5.25 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | D |  | STP/ST | 2019 | 200000 | 200000 | [8 empty] | 0
STIP | [9 empty] | JEFFERSON | 5-20026 | KY 1065 |  | 2.504 | 5.25 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | C |  | PM/STP | 2019 | 2000000 | 1600000 |  |  | 400000 | [5 empty] | 0
TIP | [6 empty] | TIP AND STIP AMOUNTS ARE DIFFERENT | STP | 873018 | JEFFERSON | 5-20026 | KY 1065 |  | 2.504 | 5.25 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | C |  | STP/ST | 2019 | 2000000 | 2000000 | [5 empty] | OBLIGATED | 2729600 |  | 2729600 | 2020 | 1ST QUARTER
STIP | [9 empty] | JEFFERSON | 5-20027 | KY 1932 |  | 3.21 | 3.8 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | D |  | PM/STP | 2021 | 50000 | 40000 |  |  | 10000 | [5 empty] | 0
TIP | [6 empty] | TIP AND STIP AMOUNTS ARE DIFFERENT |  |  | JEFFERSON | 5-20027 | KY 1932 |  | 3.21 | 3.8 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | D |  | STP/ST | 2021 | 50000 | 50000 | [8 empty] | 0
STIP | [9 empty] | JEFFERSON | 5-20027 | KY 1932 |  | 3.21 | 3.8 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | C |  | PM/STP | 2021 | 500000 | 400000 |  |  | 100000 | [5 empty] | 0
TIP | [6 empty] | TIP AND STIP AMOUNTS ARE DIFFERENT |  |  | JEFFERSON | 5-20027 | KY 1932 |  | 3.21 | 3.8 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | C |  | STP/ST | 2021 | 500000 | 500000 | [8 empty] | 0
STIP | [9 empty] | JEFFERSON | 5-20028 | KY 1934 |  | 0 | 4.444 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | D |  | PM/STP | 2021 | 325000 | 260000 |  |  | 65000 | [5 empty] | 0
TIP | [6 empty] | TIP AND STIP AMOUNTS ARE DIFFERENT |  |  | JEFFERSON | 5-20028 | KY 1934 |  | 0 | 4.444 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | D |  | STP/ST | 2021 | 325000 | 325000 | [8 empty] | 0
STIP | [9 empty] | JEFFERSON | 5-20028 | KY 1934 |  | 0 | 4.444 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | C |  | PM/STP | 2021 | 3250000 | 2600000 |  |  | 650000 | [5 empty] | 0
TIP | [6 empty] | TIP AND STIP AMOUNTS ARE DIFFERENT |  |  | JEFFERSON | 5-20028 | KY 1934 |  | 0 | 4.444 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | C |  | STP/ST | 2021 | 3250000 | 3250000 | [8 empty] | 0
STIP | YES | [5 empty] | NOT IN TIP |  |  | JEFFERSON | 5-20029 | KY 1934 |  | 4.444 | 9.742 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | D |  | PM/STP | 2022 | 375000 | 300000 |  |  | 75000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; UPDATE FUND TYPE; MOD |  |  | JEFFERSON | 5-20029 | KY 1934 |  | 4.444 | 9.742 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | D |  | NHPP | 2022 | 375000 | 300000 |  |  | 75000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; UDPATE FISCAL YEAR; MOD |  |  | JEFFERSON | 5-20029 | KY 1934 |  | 4.444 | 9.742 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | D |  | NHPP | 2021 | 375000 | 300000 |  |  | 75000 | [5 empty] | 0
STIP | YES | [5 empty] | NOT IN TIP |  |  | JEFFERSON | 5-20029 | KY 1934 |  | 4.444 | 9.742 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | C |  | PM/STP | 2022 | 3750000 | 3000000 |  |  | 750000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; UPDATE FUND TYPE; MOD |  |  | JEFFERSON | 5-20029 | KY 1934 |  | 4.444 | 9.742 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | C |  | NHPP | 2022 | 3750000 | 3000000 |  |  | 750000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; UDPATE FISCAL YEAR; MOD |  |  | JEFFERSON | 5-20029 | KY 1934 |  | 4.444 | 9.742 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | C |  | NHPP | 2021 | 3750000 | 3000000 |  |  | 750000 | [5 empty] | 0
STIP | YES | [5 empty] | NOT IN TIP |  |  | JEFFERSON | 5-20030 | KY 2048 |  | 0 | 1.13 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | D |  | PM/STP | 2022 | 100000 | 80000 |  |  | 20000 | [5 empty] | 0
STIP | YES | [5 empty] | NOT IN TIP |  |  | JEFFERSON | 5-20030 | KY 2048 |  | 0 | 1.13 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | C |  | PM/STP | 2022 | 1000000 | 800000 |  |  | 200000 | [5 empty] | 0
STIP | [9 empty] | JEFFERSON | 5-20031 | KY 2052 |  | 0 | 4.205 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | D |  | PM/STP | 2021 | 300000 | 240000 |  |  | 60000 | [5 empty] | 0
TIP | [6 empty] | TIP AND STIP AMOUNTS ARE DIFFERENT |  |  | JEFFERSON | 5-20031 | KY 2052 |  | 0 | 4.205 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | D |  | STP/ST | 2021 | 300000 | 300000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; UPDATE FISCAL YEAR; MOD |  |  | JEFFERSON | 5-20031 | KY 2052 |  | 0 | 4.205 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | D |  | STP/ST | 2022 | 300000 | 240000 |  |  | 60000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#9; UPDATE FISCAL YEAR; MOD |  |  | JEFFERSON | 5-20031 | KY 2052 |  | 0 | 4.205 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | D |  | STP/ST | 2021 | 300000 | 240000 |  |  | 60000 | [5 empty] | 0
STIP | [9 empty] | JEFFERSON | 5-20031 | KY 2052 |  | 0 | 4.205 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | C |  | PM/STP | 2021 | 3000000 | 2400000 |  |  | 600000 | [5 empty] | 0
TIP | [6 empty] | TIP AND STIP AMOUNTS ARE DIFFERENT |  |  | JEFFERSON | 5-20031 | KY 2052 |  | 0 | 4.205 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | C |  | STP/ST | 2021 | 3000000 | 3000000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; UPDATE FISCAL YEAR; MOD |  |  | JEFFERSON | 5-20031 | KY 2052 |  | 0 | 4.205 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | C |  | STP/ST | 2022 | 3000000 | 2400000 |  |  | 600000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#9; UPDATE FISCAL YEAR; MOD |  |  | JEFFERSON | 5-20031 | KY 2052 |  | 0 | 4.205 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | C |  | STP/ST | 2021 | 3000000 | 2400000 |  |  | 600000 | [5 empty] | 0
STIP | [9 empty] | JEFFERSON | 5-20032 | US 31W |  | 14.51 | 14.96 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | D |  | PM/NH | 2020 | 75000 | 60000 |  |  | 15000 | [5 empty] | 0
TIP | [6 empty] | TIP AND STIP AMOUNTS ARE DIFFERENT |  |  | JEFFERSON | 5-20032 | US 31W |  | 14.51 | 14.96 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | D |  | STP/ST | 2020 | 75000 | 75000 |  |  | 0 | [5 empty] | 0
TIP | [7 empty] | NHPP | 0311045 | JEFFERSON | 5-20032 | US 31W |  | 14.51 | 14.96 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | C |  | PM/NH | 2020 | 750000 | 750000 |  |  | 0 |  |  | OBLIGATED | 100000 | 958000 | 1058000 | 2019 | 4TH QUARTER
STIP | YES | [5 empty] | NOT IN TIP |  |  | JEFFERSON | 5-20039 | US 31W | 7.25 | 0 | 7.25 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION ON US-31W FROM MILEPOINT 0.00 TO MILEPOINT 7.25 | C |  | PM/NH | 2022 | 965000 | 772000 |  |  | 193000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.318 | 2021-07-07 | TIP FY 20-25, AMENDMENT#3; ADD PROJECT TO STIP; NEW |  |  | JEFFERSON | 5-20061 | I 65 |  | 131.24 | 135.672 | RELIABILITY | AM-PAVEMENT (PRI)(P) | Address Pavement needs on I-65 between MP 131.24 and MP 135.672 and to replace bridge over Hill Street at MP 133.873; replace bridge over Brook Street at MP 134.753, and to replace bridge over Jacob and Broadway at MP 135.273. | D |  | NHPP | 2021 | 2000000 | 1800000 |  |  | 200000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.318 | 2021-07-07 | TIP FY 20-25, AMENDMENT#3; ADD PROJECT TO STIP; NEW |  |  | JEFFERSON | 5-20061 | I 65 |  | 131.24 | 135.672 | RELIABILITY | AM-PAVEMENT (PRI)(P) | Address Pavement needs on I-65 between MP 131.24 and MP 135.672 and to replace bridge over Hill Street at MP 133.873; replace bridge over Brook Street at MP 134.753, and to replace bridge over Jacob and Broadway at MP 135.273. | C |  | NHPP | 2023 | 54000000 | 48600000 |  |  | 5400000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; ADD D PHASE TO STIP; NEW |  |  | JEFFERSON | 5-80001 | US 60 |  | 11.093 | 11.684 | RELIABILITY | MAJOR WIDENING(O) | WIDEN US-60 TO 6 LANES FROM OLD SHELBYVILLE RD. TO NORTH ENGLISH STATION RD.(18CCN) (2020CCR) | D |  | NHPP | 2021 | 1260000 | 1008000 |  |  | 252000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; ADD R PHASE TO STIP; NEW |  |  | JEFFERSON | 5-80001 | US 60 |  | 11.093 | 11.684 | RELIABILITY | MAJOR WIDENING(O) | WIDEN US-60 TO 6 LANES FROM OLD SHELBYVILLE RD. TO NORTH ENGLISH STATION RD.(18CCN) (2020CCR) | R |  | NHPP | 2022 | 550000 | 440000 |  |  | 110000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; ADD U PHASE TO STIP; NEW |  |  | JEFFERSON | 5-80001 | US 60 |  | 11.093 | 11.684 | RELIABILITY | MAJOR WIDENING(O) | WIDEN US-60 TO 6 LANES FROM OLD SHELBYVILLE RD. TO NORTH ENGLISH STATION RD.(18CCN) (2020CCR) | U |  | NHPP | 2023 | 720000 | 576000 |  |  | 144000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; ADD C PHASE TO STIP; NEW |  |  | JEFFERSON | 5-80001 | US 60 |  | 11.093 | 11.684 | RELIABILITY | MAJOR WIDENING(O) | WIDEN US-60 TO 6 LANES FROM OLD SHELBYVILLE RD. TO NORTH ENGLISH STATION RD.(18CCN) (2020CCR) | C |  | NHPP | 2024 | 15000000 | 12000000 |  |  | 3000000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; ADD PROJECT TO STIP; NEW |  |  | JEFFERSON | 5-80005 | I 71 |  | 6.8 | 7 | SAFETY | SAFETY (P) | IMPROVE THE INTERCHANGE OF I 71 AND KY 329. (18CCN) (2020CCR) | D |  | STP | 2021 | 370000 | 296000 |  |  | 74000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; ADD PROJECT TO STIP; NEW |  |  | JEFFERSON | 5-80005 | I 71 |  | 6.8 | 7 | SAFETY | SAFETY (P) | IMPROVE THE INTERCHANGE OF I 71 AND KY 329. (18CCN) (2020CCR) | R |  | STP | 2021 | 150000 | 120000 |  |  | 30000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; ADD PROJECT TO STIP; NEW |  |  | JEFFERSON | 5-80005 | I 71 |  | 6.8 | 7 | SAFETY | SAFETY (P) | IMPROVE THE INTERCHANGE OF I 71 AND KY 329. (18CCN) (2020CCR) | U |  | STP | 2022 | 340000 | 272000 |  |  | 68000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; ADD PROJECT TO STIP; NEW |  |  | JEFFERSON | 5-80005 | I 71 |  | 6.8 | 7 | SAFETY | SAFETY (P) | IMPROVE THE INTERCHANGE OF I 71 AND KY 329. (18CCN) (2020CCR) | C |  | STP | 2023 | 3400000 | 2720000 |  |  | 680000 | [5 empty] | 0
STIP | [6 empty] | NOT IN TIP |  |  | JEFFERSON | 5-80053 | US 31E | 1.242 | 16.325 | 17.567 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT EAST MARKET (US-31E) FROM FIRST ST TO JOHNSON ST TO IMPROVE PEDESTRIAN SAFETY AND ENHANCE ECONOMIC DEVELOPMENT.(18CCN) | C |  | STP | 2019 | 5000000 | 5000000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | JEFFERSON | 5-80053.1 | US 31E | 1.242 | 16.325 | 17.567 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT EAST MARKET (US-31E) FROM FIRST ST TO JOHNSON ST TO IMPROVE PEDESTRIAN SAFETY AND ENHANCE ECONOMIC DEVELOPMENT.(18CCN) | C |  | STP | 2020 | 5000000 | 5000000 |  |  | 0 | [5 empty] | 0
TIP | [6 empty] | TIP AND STIP AMOUNTS ARE DIFFERENT |  |  | Jefferson | 5-80053.1 | US 31E | 1.242 | 16.325 | 17.567 | RELIABILITY | RECONSTRUCTION(O) | Streetscape enhancements to improve pedestrian/bicycle amenities along East Market Street from Brook Street to Johnson Street and along the following intersecting streets from Nanny Goat Alley to Billy Goat Strut Alley: Brook St., Floyd St., Preston St., Jackson St., Hancock St., Clay St., Shelby St., Campbell St., Wenzel St., Baxter Ave. and Johnson St. Enhancements include the addition of landscape medians in two separate blocks to serve as a gateway to the neighborhood and repurposing one of the existing east-bound drive lanes to provide a dedicated separate bike facility. | C |  | STP-ST | 2020 | 6250000 | 5000000 |  |  |  | 1250000 |  |  |  |  | 0
TIP | [6 empty] | ADDITIONAL FUNDING NOT IN STIP |  |  | Jefferson | 5-80053.1 | US 31E | 1.242 | 16.325 | 17.567 | RELIABILITY | RECONSTRUCTION(O) | Streetscape enhancements to improve pedestrian/bicycle amenities along East Market Street from Brook Street to Johnson Street and along the following intersecting streets from Nanny Goat Alley to Billy Goat Strut Alley: Brook St., Floyd St., Preston St., Jackson St., Hancock St., Clay St., Shelby St., Campbell St., Wenzel St., Baxter Ave. and Johnson St. Enhancements include the addition of landscape medians in two separate blocks to serve as a gateway to the neighborhood and repurposing one of the existing east-bound drive lanes to provide a dedicated separate bike facility. | C |  | STP-ST | 2019 | 6250000 | 5000000 |  |  |  | 1250000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.226 | 2020-08-28 | TIP FY 20-25, ADMIN MOD#7; UPDATE FUND TYPE & FUND AMOUNT; MOD |  |  | Jefferson | 5-80053.1 |  |  |  |  | RELIABILITY | RECONSTRUCTION(O) | Streetscape enhancements to improve pedestrian/bicycle amenities along East Market Street from Brook Street to Johnson Street and along the following intersecting streets from Nanny Goat Alley to Billy Goat Strut Alley: Brook St., Floyd St., Preston St., Jackson St., Hancock St., Clay St., Shelby St., Campbell St., Wenzel St., Baxter Ave. and Johnson St. Enhancements include the addition of landscape medians in two separate blocks to serve as a gateway to the neighborhood and repurposing one of the existing east-bound drive lanes to provide a dedicated separate bike facility. | C |  | STBG | 2021 | 9000000 | 7200000 |  |  |  | 1800000 |  |  |  |  | 0
TIP | [6 empty] | NOT IN STIP |  |  | Jefferson |  | Bus Stop and Access Improvements | [5 empty] | Improvements of the existing or new public transit bus stops and their surroundings, including pedestrian facilities, ADA access and passenger amenities (shelters, benches, trash receptacles). | C |  | SLO | 2021 | 312500 | 250000 |  |  |  | 62500 |  |  |  |  | 0
TIP | [6 empty] | NOT IN STIP |  |  | Jefferson |  | Bus Stop and Access Improvements | [5 empty] | Improvements of the existing or new public transit bus stops and their surroundings, including pedestrian facilities, ADA access and passenger amenities (shelters, benches, trash receptacles). | C |  | SLO | 2019 | 312500 | 250000 |  |  |  | 62500 |  |  |  |  | 0
TIP | [6 empty] | NOT IN STIP |  |  | Jefferson |  | Bus Stop and Access Improvements | [5 empty] | Improvements of the existing or new public transit bus stops and their surroundings, including pedestrian facilities, ADA access and passenger amenities (shelters, benches, trash receptacles). | C |  | SLO | 2018 | 312500 | 250000 |  |  |  | 62500 |  |  |  |  | 0
TIP | [6 empty] | NOT IN STIP |  |  | Jefferson |  | Bus Stop and Access Improvements | [5 empty] | Improvements of the existing or new public transit bus stops and their surroundings, including pedestrian facilities, ADA access and passenger amenities (shelters, benches, trash receptacles). | C |  | SLO | 2020 | 312500 | 250000 |  |  |  | 62500 |  |  |  |  | 0
TIP | [6 empty] | NOT IN STIP |  |  | Jefferson |  | Stony Brook Drive Sidewalk Connector | [5 empty] | Install new ADA compliant 5' sidewalk along Stony Brook Drive from Stara Way to Kirby Lane. Project length is 0.284 miles. | R |  | SLO | 2020 | 27000 | 22000 |  |  |  | 5000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; UPDATE FISCAL YEAR & FUND AMOUNTS; MOD |  |  | Jefferson |  | Stony Brook Drive Sidewalk Connector | [5 empty] | Install new ADA compliant 5' sidewalk along Stony Brook Drive from Stara Way to Kirby Lane. Project length is 0.284 miles. | R |  | SLO | 2021 | 27500 | 22000 |  |  |  | 5500 |  |  |  |  | 0
TIP | [6 empty] | NOT IN STIP |  |  | Jefferson |  | Stony Brook Drive Sidewalk Connector | [5 empty] | Install new ADA compliant 5' sidewalk along Stony Brook Drive from Stara Way to Kirby Lane. Project length is 0.284 miles. | D |  | SLO | 2019 | 54000 | 44000 |  |  |  | 10000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.031 | 2019-03-01 | TIP FY 18-21; ADMIN MOD#21 (ORIGINALLY ADDED TO STIP FY 17-20 ON STIP MOD 2016.225) ADD C PHASE TO STIP; CORRECT KIDPA ID# TO 2549; NEW |  |  | Jefferson |  | Stony Brook Drive Sidewalk Connector | [5 empty] | Install new ADA compliant 5' sidewalk along Stony Brook Drive from Stara Way to Kirby Lane. Project length is 0.284 miles. | C |  | SLO | 2022 | 297000 | 242000 |  |  |  | 55000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; UPDATE FUND AMOUNTS; MOD |  |  | Jefferson |  | Stony Brook Drive Sidewalk Connector | [5 empty] | Install new ADA compliant 5' sidewalk along Stony Brook Drive from Stara Way to Kirby Lane. Project length is 0.284 miles. | C |  | SLO | 2022 | 370000 | 300000 |  |  |  | 70000 |  |  |  |  | 0
TIP | [6 empty] | NOT IN STIP |  |  | Jefferson |  | Ruckriegel Parkway Sidewalk Improvement | [5 empty] | Construct the missing gaps of sidewalk and ADA ramps along Ruckriegel Parkway between Taylorsville Road and Billtown Road. | C |  | SLO | 2019 | 47250 | 37800 |  |  |  | 9450 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.057 | 2019-04-26 | TIP FY 18-21, ADMIN MOD#29; UPDATE FUND AMOUNTS; MOD |  |  | Jefferson | 5-198 | Ruckriegel Parkway Sidewalk Improvement | [5 empty] | Construct the missing gaps of sidewalk and ADA ramps along Ruckriegel Parkway between Taylorsville Road and Billtown Road. | C |  | SLO | 2019 | 391510 | 319008 |  |  |  | 72502 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; UPDATE FISCAL YEAR FROM 2019 TO 2020; MOD |  |  | Jefferson | 5-198 | Ruckriegel Parkway Sidewalk Improvement | [5 empty] | Construct the missing gaps of sidewalk and ADA ramps along Ruckriegel Parkway between Taylorsville Road and Billtown Road. | C |  | STP | 2020 | 391510 | 319008 |  |  |  | 72502 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.186 | 2020-05-06 | TIP FY 20-25, ADMIN MOD#2; UPDATE FUND AMOUNTS; MOD |  |  | Jefferson | 5-198 | Ruckriegel Parkway Sidewalk Improvement | [5 empty] | Construct the missing gaps of sidewalk and ADA ramps along Ruckriegel Parkway between Taylorsville Road and Billtown Road. | C |  | STP | 2020 | 661262 | 529010 |  |  |  | 132252 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.194 | 2020-05-29 | TIP FY 20-25, ADMIN MOD#3; UPDATE FUND AMOUNTS; MOD |  |  | Jefferson | 5-198 | Ruckriegel Parkway Sidewalk Improvement | [5 empty] | Construct the missing gaps of sidewalk and ADA ramps along Ruckriegel Parkway between Taylorsville Road and Billtown Road. | C |  | STP | 2020 | 661260 | 529008 |  |  |  | 132252 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; UPDATE FISCAL YEAR; MOD |  |  | Jefferson | 5-198 | Ruckriegel Parkway Sidewalk Improvement | [5 empty] | Construct the missing gaps of sidewalk and ADA ramps along Ruckriegel Parkway between Taylorsville Road and Billtown Road. | C |  | STP | 2022 | 661260 | 529008 |  |  |  | 132252 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.271 | 2021-01-12 | TIP FY 20-25, AMEND#2; ADD PROJECT TO STIP; NEW |  |  | Jefferson | 5-3709 | Olmsted Parkways Multi-Use Path System Section 1 |  |  |  | RELIABILITY | CONGESTION MITIGTN(O) | Construction of a 2.0 mile shared use path system along Southwestern and Algonquin Parkway between West Broadway and 41st Street. | C |  | STP | 2021 | 2750000 | 2200000 |  |  | 550000 | [5 empty] | 0
TIP | [9 empty] | Jefferson | 5-3709 | Olmsted Parkways Multi-Use Path System Section 2 |  |  |  | RELIABILITY | CONGESTION MITIGTN(O) | Construction of a 1.0 mile shared use path system along Algonquin Parkway between 41st Street and Beech Street. | U |  | SLO | 2021 | 91520 | 73216 |  |  |  | 18304 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; UPDATE FISCAL YEAR; MOD |  |  | Jefferson | 5-3709 | Olmsted Parkways Multi-Use Path System Section 2 |  |  |  | RELIABILITY | CONGESTION MITIGTN(O) | Construction of a 1.0 mile shared use path system along Algonquin Parkway between 41st Street and Beech Street. | U |  | SLO | 2025 | 91520 | 73216 |  |  | 18304 | [5 empty] | 0
TIP | [9 empty] | Jefferson | 5-3709 | Olmsted Parkways Multi-Use Path System Section 2 |  |  |  | RELIABILITY | CONGESTION MITIGTN(O) | Construction of a 1.0 mile shared use path system along Algonquin Parkway between 41st Street and Beech Street. | R |  | SLO | 2020 | 924355 | 739484 |  |  |  | 184871 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; UPDATE FISCAL YEAR; MOD |  |  | Jefferson | 5-3709 | Olmsted Parkways Multi-Use Path System Section 2 |  |  |  | RELIABILITY | CONGESTION MITIGTN(O) | Construction of a 1.0 mile shared use path system along Algonquin Parkway between 41st Street and Beech Street. | R |  | SLO | 2025 | 924355 | 739484 |  |  | 184871 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; ADD C PHASE; NEW |  |  | Jefferson | 5-3709 | Olmsted Parkways Multi-Use Path System Section 2 |  |  |  | RELIABILITY | CONGESTION MITIGTN(O) | Construction of a 1.0 mile shared use path system along Algonquin Parkway between 41st Street and Beech Street. | C |  | SLO | 2025 | 3750000 | 3000000 |  |  | 750000 | [5 empty] | 0
TIP | [9 empty] | Jefferson | 5-3709 | Olmsted Parkways Multi-Use Path System Section 3 |  |  |  | RELIABILITY | CONGESTION MITIGTN(O) | Construction of a 0.30 mile shared use path system along Algonquin Parkway between Beech Street and Cypress Street. | U |  | SLO | 2021 | 42533 | 34026 |  |  |  | 8507 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; UPDATE FISCAL YEAR & CORRECT FUND AMOUNTS; MOD |  |  | Jefferson | 5-3709 | Olmsted Parkways Multi-Use Path System Section 3 |  |  |  | RELIABILITY | CONGESTION MITIGTN(O) | Construction of a 0.30 mile shared use path system along Algonquin Parkway between Beech Street and Cypress Street. | U |  | SLO | 2025 | 42532 | 34026 |  |  |  | 8506 |  |  |  |  | 0
TIP | [9 empty] | Jefferson | 5-3709 | Olmsted Parkways Multi-Use Path System Section 3 |  |  |  | RELIABILITY | CONGESTION MITIGTN(O) | Construction of a 0.30 mile shared use path system along Algonquin Parkway between Beech Street and Cypress Street. | R |  | SLO | 2020 | 385463 | 308370 |  |  |  | 77093 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; UPDATE FISCAL YEAR; MOD |  |  | Jefferson | 5-3709 | Olmsted Parkways Multi-Use Path System Section 3 |  |  |  | RELIABILITY | CONGESTION MITIGTN(O) | Construction of a 0.30 mile shared use path system along Algonquin Parkway between Beech Street and Cypress Street. | R |  | SLO | 2025 | 385463 | 308370 |  |  |  | 77093 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; ADD C PHASE TO STIP; NEW |  |  | Jefferson | 5-3709 | Olmsted Parkways Multi-Use Path System Section 3 |  |  |  | RELIABILITY | CONGESTION MITIGTN(O) | Construction of a 0.30 mile shared use path system along Algonquin Parkway between Beech Street and Cypress Street. | C |  | SLO | 2025 | 2000000 | 1600000 |  |  | 400000 | [5 empty] | 0
TIP | [9 empty] | Jefferson | 5-3709 | Olmsted Parkways Multi-Use Path System Section 4 | [5 empty] | Construction of a 1.00 mile shared use path system along Algonquin Parkway between Cypress Street and 16th Street. | R |  | SLO | 2020 | 689992 | 551994 |  |  |  | 137998 |  |  |  |  | 0
TIP | [9 empty] | Jefferson | 5-3709 | Olmsted Parkways Multi-Use Path System Section 4 | [5 empty] | Construction of a 1.00 mile shared use path system along Algonquin Parkway between Cypress Street and 16th Street. | U |  | SLO | 2020 | 68658 | 54926 |  |  |  | 13732 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.01 | 2018-12-27 | TIP FY 18-21, ADMIN MOD#25; KIPDA ID#1273; ADD C PHASE TO STIP; NEW |  |  | Jefferson | 5-3709 | Olmsted Parkways Multi-Use Path System Section 4 | [5 empty] | Construction of a 1.00 mile shared use path system along Algonquin Parkway between Cypress Street and 16th Street. | C |  | SLO | 2021 | 2542629 | 2034103 |  |  |  | 508526 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.051 | 2019-04-18 | TIP FY 18-21, ADMIN MOD#28; KIPDA ID#2625; UPDATE FUND AMOUNTS; MOD |  |  | Jefferson | 5-3709 | Olmsted Parkways Multi-Use Path System Section 4 | [5 empty] | Construction of a 1.00 mile shared use path system along Algonquin Parkway between Cypress Street and 16th Street. | C |  | SLO | 2021 | 2505493 | 1996967 |  |  |  | 508526 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.051 | 2019-04-18 | TIP FY 18-21, ADMIN MOD#28; KIPDA ID#2625; ADD D PHASE TO STIP; NEW |  |  | Jefferson | 5-3709 | Olmsted Parkways Multi-Use Path System Section 4 | [5 empty] | Construction of a 1.00 mile shared use path system along Algonquin Parkway between Cypress Street and 16th Street. | D |  | SLO | 2019 | 45576 | 37136 |  |  |  | 8440 |  |  |  |  | 0
TIP | [6 empty] | NOT IN STIP |  |  | Jefferson | 5-3709 | Olmsted Parkways Multi-Use Path System Section 5 | [5 empty] | Construction of a 1.25 mile shared use path system along Algonquin Parkway between 16th Street to Winkler Avenue. | C |  | SLO | 2021 | 3598931 | 2879145 |  |  |  | 719786 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.051 | 2019-04-18 | TIP FY 18-21, ADMIN MOD#28; KIPDA ID#2626; UPDATE FUND AMOUNTS; MOD |  |  | Jefferson | 5-3709 | Olmsted Parkways Multi-Use Path System Section 5 | [5 empty] | Construction of a 1.25 mile shared use path system along Algonquin Parkway between 16th Street to Winkler Avenue. | C |  | SLO | 2021 | 3550312 | 2830526 |  |  |  | 719786 |  |  |  |  | 0
TIP | [6 empty] | NOT IN STIP |  |  | Jefferson | 5-3709 | Olmsted Parkways Multi-Use Path System Section 5 | [5 empty] | Construction of a 1.25 mile shared use path system along Algonquin Parkway between 16th Street to Winkler Avenue. | R |  | SLO | 2020 | 876264 | 701011 |  |  |  | 175253 |  |  |  |  | 0
TIP | [6 empty] | NOT IN STIP |  |  | Jefferson | 5-3709 | Olmsted Parkways Multi-Use Path System Section 5 | [5 empty] | Construction of a 1.25 mile shared use path system along Algonquin Parkway between 16th Street to Winkler Avenue. | U |  | SLO | 2020 | 82188 | 65750 |  |  |  | 16438 |  |  |  |  | 0
TIP | [6 empty] | NOT IN STIP |  |  | Jefferson | 5-3709 | Olmsted Parkways Multi-Use Path System Section 6 | [5 empty] | Construction of a 1.40 mile shared use path system along Southern Parkway between South 3rd Street and Woodlawn Avenue. | D |  | SLO | 2019 | 457318 | 365854 |  |  |  | 91464 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.051 | 2019-04-18 | TIP FY 18-21, ADMIN MOD#28; KIPDA ID#2627; UPDATE FUND AMOUNTS; MOD |  |  | Jefferson | 5-3709 | Olmsted Parkways Multi-Use Path System Section 6 | [5 empty] | Construction of a 1.40 mile shared use path system along Southern Parkway between South 3rd Street and Woodlawn Avenue. | D |  | SLO | 2019 | 493899 | 402435 |  |  |  | 91464 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; UPDATE FISCAL YEAR FROM 2019 TO 2020; MOD |  |  | Jefferson | 5-3709 | Olmsted Parkways Multi-Use Path System Section 6 | [5 empty] | Construction of a 1.40 mile shared use path system along Southern Parkway between South 3rd Street and Woodlawn Avenue. | D |  | STP | 2020 | 493899 | 402435 |  |  |  | 91464 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.299 | 2021-04-26 | TIP FY 20-25, ADMIN MOD#16; UPDATE FY & FUND AMOUNTS; MOD |  |  | Jefferson | 5-3709 | Olmsted Parkways Multi-Use Path System Section 6 | [5 empty] | Construction of a 1.40 mile shared use path system along Southern Parkway between South 3rd Street and Woodlawn Avenue. | D |  | STP | 2021 | 162500 | 130000 |  |  | 32500 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.299 | 2021-04-26 | TIP FY 20-25, ADMIN MOD#16; ADD FISCAL YEAR 2022 FOR THE D PHASE; MOD |  |  | Jefferson | 5-3709 | Olmsted Parkways Multi-Use Path System Section 6 | [5 empty] | Construction of a 1.40 mile shared use path system along Southern Parkway between South 3rd Street and Woodlawn Avenue. | D |  | STP | 2022 | 503044 | 402435 |  |  | 100609 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; UPDATE FISCAL YEAR & FUND AMOUNTS; MOD |  |  | Jefferson | 5-3709 | Olmsted Parkways Multi-Use Path System Section 6 | [5 empty] | Construction of a 1.40 mile shared use path system along Southern Parkway between South 3rd Street and Woodlawn Avenue. | D |  | STP |  | 503044 | 402435 |  |  |  | 100609 |  |  |  |  | 0
TIP | [6 empty] | NOT IN STIP |  |  | Jefferson | 5-3709 | Olmsted Parkways Multi-Use Path System Section 6 | [5 empty] | Construction of a 1.40 mile shared use path system along Southern Parkway between South 3rd Street and Woodlawn Avenue. | C |  | SLO | 2020 | 1100541 | 880433 |  |  |  | 220108 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.051 | 2019-04-18 | TIP FY 18-21, ADMIN MOD#28; KIPDA ID#2627; UPDATE FUND AMOUNTS; MOD |  |  | Jefferson | 5-3709 | Olmsted Parkways Multi-Use Path System Section 6 | [5 empty] | Construction of a 1.40 mile shared use path system along Southern Parkway between South 3rd Street and Woodlawn Avenue. | C |  | SLO | 2020 | 1063960 | 843852 |  |  |  | 220108 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; UPDATE FISCAL YEAR FROM 2020 TO 2022; MOD |  |  | Jefferson | 5-3709 | Olmsted Parkways Multi-Use Path System Section 6 | [5 empty] | Construction of a 1.40 mile shared use path system along Southern Parkway between South 3rd Street and Woodlawn Avenue. | C |  | STP | 2022 | 1063960 | 843852 |  |  |  | 220108 |  |  |  |  | 0
TIP | [6 empty] | NOT IN STIP |  |  | Jefferson | 5-3709 | Olmsted Parkways Multi-Use Path System Section 7 | [5 empty] | Construction of a 1.10 mile shared use path system along Southern Parkway between Woodlawn Avenue and New Cut Road. | D |  | SLO | 2019 | 359322 | 287458 |  |  |  | 71864 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.051 | 2019-04-18 | TIP FY 18-21, ADMIN MOD#28; KIPDA ID#2628; UPDATE FUND AMOUNTS; MOD |  |  | Jefferson | 5-3709 | Olmsted Parkways Multi-Use Path System Section 7 | [5 empty] | Construction of a 1.10 mile shared use path system along Southern Parkway between Woodlawn Avenue and New Cut Road. | D |  | SLO | 2019 | 388059 | 316195 |  |  |  | 71864 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; UPDATE FISCAL YEAR FROM 2019 TO 2020; MOD |  |  | Jefferson | 5-3709 | Olmsted Parkways Multi-Use Path System Section 7 | [5 empty] | Construction of a 1.10 mile shared use path system along Southern Parkway between Woodlawn Avenue and New Cut Road. | D |  | STP | 2020 | 388059 | 316195 |  |  |  | 71864 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; UPDATE FISCAL YEAR & FUND AMOUNTS; MOD |  |  | Jefferson | 5-3709 | Olmsted Parkways Multi-Use Path System Section 7 | [5 empty] | Construction of a 1.10 mile shared use path system along Southern Parkway between Woodlawn Avenue and New Cut Road. | D |  | STP | 2022 | 395244 | 316195 |  |  |  | 79049 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.299 | 2021-04-26 | TIP FY 20-25, ADMIN MOD#16, ADD FY 2021 TO D PHASE; MOD |  |  | Jefferson | 5-3709 | Olmsted Parkways Multi-Use Path System Section 7 | [5 empty] | Construction of a 1.10 mile shared use path system along Southern Parkway between Woodlawn Avenue and New Cut Road. | D |  | STP | 2021 | 125000 | 100000 |  |  | 25000
TIP | [6 empty] | NOT IN STIP |  |  | Jefferson | 5-3709 | Olmsted Parkways Multi-Use Path System Section 7 | [5 empty] | Construction of a 1.10 mile shared use path system along Southern Parkway between Woodlawn Avenue and New Cut Road. | C |  | SLO | 2020 | 1400688 | 1120550 |  |  |  | 280138 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.051 | 2019-04-18 | TIP FY 18-21, ADMIN MOD#28; KIPDA ID#2628; UPDATE FUND AMOUNTS; MOD |  |  | Jefferson | 5-3709 | Olmsted Parkways Multi-Use Path System Section 7 | [5 empty] | Construction of a 1.10 mile shared use path system along Southern Parkway between Woodlawn Avenue and New Cut Road. | C |  | SLO | 2020 | 1371951 | 1091813 |  |  |  | 280138 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; UPDATE FISCAL YEAR FROM 2020 TO 2022; MOD |  |  | Jefferson | 5-3709 | Olmsted Parkways Multi-Use Path System Section 7 | [5 empty] | Construction of a 1.10 mile shared use path system along Southern Parkway between Woodlawn Avenue and New Cut Road. | C |  | STP | 2022 | 1371951 | 1091813 |  |  |  | 280138 |  |  |  |  | 0
TIP | [6 empty] | NOT IN STIP |  |  | Jefferson | 5-3709 | Olmsted Parkways Multi-Use Path System Section 8 | [5 empty] | Construction of a 2.50 mile road diet system along Southern Parkway between South 3rd Street and New Cut Road. | D |  | SLO | 2019 | 105425 | 84340 |  |  |  | 21085 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.051 | 2019-04-18 | TIP FY 18-21, ADMIN MOD#28; KIPDA ID#2629; UPDATE FUND AMOUNTS; MOD |  |  | Jefferson | 5-3709 | Olmsted Parkways Multi-Use Path System Section 8 | [5 empty] | Construction of a 2.50 mile road diet system along Southern Parkway between South 3rd Street and New Cut Road. | D |  | SLO | 2019 | 140204 | 119119 |  |  |  | 21085 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; UPDATE FISCAL YEAR FROM 2019 TO 2020; MOD |  |  | Jefferson | 5-3709 | Olmsted Parkways Multi-Use Path System Section 8 | [5 empty] | Construction of a 2.50 mile road diet system along Southern Parkway between South 3rd Street and New Cut Road. | D |  | STP | 2020 | 140204 | 119119 |  |  |  | 21085 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; UPDATE FISCAL YEAR & FUND AMOUNTS; MOD |  |  | Jefferson | 5-3709 | Olmsted Parkways Multi-Use Path System Section 8 | [5 empty] | Construction of a 2.50 mile road diet system along Southern Parkway between South 3rd Street and New Cut Road. | D |  | STP | 2022 | 268018 | 119119 |  |  |  | 148899 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.299 | 2021-04-26 | TIP FY 20-25, ADMIN MOD#16; UPDATE FUND AMOUNTS; MOD |  |  | Jefferson | 5-3709 | Olmsted Parkways Multi-Use Path System Section 8 | [5 empty] | Construction of a 2.50 mile road diet system along Southern Parkway between South 3rd Street and New Cut Road. | D |  | STP | 2022 | 395244 | 316195 |  |  | 79049 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.299 | 2021-04-26 | TIP FY 20-25, ADMIN MOD#16; ADD FY 2021 TO D PHASE; MOD |  |  | Jefferson | 5-3709 | Olmsted Parkways Multi-Use Path System Section 8 | [5 empty] | Construction of a 2.50 mile road diet system along Southern Parkway between South 3rd Street and New Cut Road. | D |  | STP | 2021 | 175000 | 140000 |  |  | 35000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; ADD C PHASE TO STIP; NEW |  |  | Jefferson | 5-3709 | Olmsted Parkways Multi-Use Path System Section 8 | [5 empty] | Construction of a 2.50 mile road diet system along Southern Parkway between South 3rd Street and New Cut Road. | C |  | STP | 2025 | 5625000 | 4500000 |  |  |  | 1125000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.299 | 2021-04-26 | TIP FY 20-25, ADMIN MOD#16; UPDATE FISCAL YEAR & FUND AMOUNT; MOD |  |  | Jefferson | 5-3709 | Olmsted Parkways Multi-Use Path System Section 8 | [5 empty] | Construction of a 2.50 mile road diet system along Southern Parkway between South 3rd Street and New Cut Road. | C |  | STP | 2022 | 1371951 | 1091813 |  |  | 280138 | [5 empty] | 0
TIP | [6 empty] | NOT IN STIP |  |  | Jefferson | 5-3709 | Olmsted Parkways Multi-Use Path System Section 9 | [5 empty] | Construction of a 3.55 mile road diet system along Algonquin Parkway between 41st Street and Winkler Avenue. | D |  | SLO | 2019 | 173014 | 138411 |  |  |  | 34603 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.051 | 2019-04-18 | TIP FY 18-21, ADMIN MOD#28; KIPDA ID#2630; UPDATE FUND AMOUNTS; MOD |  |  | Jefferson | 5-3709 | Olmsted Parkways Multi-Use Path System Section 9 | [5 empty] | Construction of a 3.55 mile road diet system along Algonquin Parkway between 41st Street and Winkler Avenue. | D |  | SLO | 2019 | 186854 | 152251 |  |  |  | 34603 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; UPDATE FISCAL YEAR FROM 2019 TO 2020; MOD |  |  | Jefferson | 5-3709 | Olmsted Parkways Multi-Use Path System Section 9 | [5 empty] | Construction of a 3.55 mile road diet system along Algonquin Parkway between 41st Street and Winkler Avenue. | D |  | STP | 2020 | 186854 | 152251 |  |  |  | 34603 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25; ADMIN MOD#10; UDPATE FISCAL YEAR & FUND AMOUNTS; MOD |  |  | Jefferson | 5-3709 | Olmsted Parkways Multi-Use Path System Section 9 | [5 empty] | Construction of a 3.55 mile road diet system along Algonquin Parkway between 41st Street and Winkler Avenue. | D |  | STP | 2025 | 190314 | 152251 |  |  |  | 38063 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25; ADMIN MOD#10; ADD C PHASE TO STIP; NEW |  |  | Jefferson | 5-3709 | Olmsted Parkways Multi-Use Path System Section 9 | [5 empty] | Construction of a 3.55 mile road diet system along Algonquin Parkway between 41st Street and Winkler Avenue. | C |  | STP | 2025 | 2500000 | 2000000 |  |  |  | 500000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.057 | 2019-04-26 | TIP FY 18-21, ADMIN MOD#29; KIPDA ID 2104; ADD PROJECT TO STIP; NEW |  |  | Jefferson |  | Hill Street Sidewalk Rehabilitation | [5 empty] | Rehabilitation of sidewalks along Hill Street between 6th Street and 7th Street. | C |  | SLO | 2019 | 91875 | 75000 |  |  |  | 16875 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.117 | 2019-08-09 | TIP FY 18-21, ADMIN MOD#34; UPDATE FUND TYPE FROM TAP TO SLO FUNDS; MOD |  |  | Jefferson | 5-3221 | Bliss Avenue | [5 empty] | Construct sidewalk on Bliss Ave. from Shelbyville Road to Wetherby Avenue, to include ADA improvements and drainage improvements. | C |  | SLO | 2019 | 180157 | 147401 |  |  |  | 49134 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; UPDATE FISCAL YEAR FROM 2019 TO 2020; MOD |  |  | Jefferson | 5-3221 | Bliss Avenue | [5 empty] | Construct sidewalk on Bliss Ave. from Shelbyville Road to Wetherby Avenue, to include ADA improvements and drainage improvements. | C |  | STP | 2020 | 180157 | 147401 |  |  |  | 49134 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.117 | 2019-08-09 | TIP FY 18-21, ADMIN MOD#34; UPDATE FUND TYPE FROM TAP TO SLO FUNDS; MOD |  |  | Jefferson | 5-3222 | Wetherby Avenue | [5 empty] | Construct sidewalk on Wetherby Ave. from North Madison Avenue to Evergreen Road, to include ADA improvements and drainage improvements. | C |  | SLO | 2019 | 473580 | 387475 |  |  |  | 86105 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; UPDATE FISCAL YEAR FROM 2019 TO 2020; MOD |  |  | Jefferson | 5-3222 | Wetherby Avenue | [5 empty] | Construct sidewalk on Wetherby Ave. from North Madison Avenue to Evergreen Road, to include ADA improvements and drainage improvements. | C |  | STP | 2020 | 473580 | 387475 |  |  |  | 86105 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.117 | 2019-08-09 | TIP FY 18-21, ADMIN MOD#34; UPDATE FUND TYPE FROM TAP TO SLO FUNDS; NEW |  |  | JEFFERSON | 5-3219 | Patti Lane Sidewalk Safety Improvement Project | [5 empty] | Construct sidewalks along Patti Lane, a urban collector, to connect three area schools and a high density residential neighborhood to a major arterial roadway (Taylorsville Road) and the public transit system along with a commercial cluster of uses. The project also includes curb and gutter, drainage related improvements and access management to adjoining businesses to reduce conflict with pedestrians and motorist. | C |  | SLO | 2019 | 705430 | 564344 |  |  |  | 141086 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; UPDATE FISCAL YEAR FROM 2019 TO 2020; MOD |  |  | JEFFERSON | 5-3219 | Patti Lane Sidewalk Safety Improvement Project | [5 empty] | Construct sidewalks along Patti Lane, a urban collector, to connect three area schools and a high density residential neighborhood to a major arterial roadway (Taylorsville Road) and the public transit system along with a commercial cluster of uses. The project also includes curb and gutter, drainage related improvements and access management to adjoining businesses to reduce conflict with pedestrians and motorist. | C |  | STP | 2020 | 705430 | 564344 |  |  |  | 141086 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.186 | 2020-05-06 | TIP FY 20-25, ADMIN MOD#2; UPDATE PROJECT DESCRIPTION AND FUND TYPE FROM SLO TO TAP FUNDS; MOD |  |  | JEFFERSON | 5-3219 | Patti Lane Sidewalk Safety Improvement Project | [5 empty] | Construct safety and acess improvements to Patti Lane. Construct sidewalks along both sides of Patti Lane from Taylorsville Road to Glenawyn Circle and "sharrow" bicycle markings that will designate this corridor as a bike route. The project will also construct new curb and gutter and associated drainage improvements to accommodate the sidewalks and the new access management design. The project also includes adding street lights and reconfiguring all the existing curb cuts and create managable commercial entrances for each business. | C | [13 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; UPDATE FISCAL YEAR AND FUND AMOUNTS; MOD |  |  | JEFFERSON | 5-3219 | Patti Lane Sidewalk Safety Improvement Project | [5 empty] | Construct safety and acess improvements to Patti Lane. Construct sidewalks along both sides of Patti Lane from Taylorsville Road to Glenawyn Circle and "sharrow" bicycle markings that will designate this corridor as a bike route. The project will also construct new curb and gutter and associated drainage improvements to accommodate the sidewalks and the new access management design. The project also includes adding street lights and reconfiguring all the existing curb cuts and create managable commercial entrances for each business. | C |  | STP | 2022 | 930430 | 744344 |  |  | 186086 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.226 | 2020-08-28 | TIP FY 20-25, ADMIN MOD#7; ADD PROJECT TO STIP; NEW |  |  | JEFFERSON |  | Hikes Lane Rehabilitation | [5 empty] | Restoration and rehabilitation of Hikes Lane from Newburg Road to Taylorsville Road. | C |  | STBG | 2021 | 4250000 | 3400000 |  |  |  | 850000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.271 | 2021-01-12 | TIP FY 20-25, AMEND#2; ADD PROJECT TO STIP; NEW |  |  | JEFFERSON | TBD | Baxter/Bardstown Premium Transportation Corridor Project | [5 empty] | The Baxter/Bardstown Premium Transportation Corridor Project is a design-build project that will: 1) streamline transit service on a key corridor by adding traffic signal bus prioritization, new bus stops, and increasing bus service frequency; 2) bring intelligent signal upgrades, which will include upgraded traffic signals and communication equipment to support premium transit and overall mobility; 3) incorporate complete streets roadway improvements by including bicycle and pedestrian facilities, intersection safety improvements, access management strategies for surrounding land uses and new streetscape design elements. | C |  | STP | 2021 | 2750000 | 2200000 |  |  | 550000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.271 | 2021-01-12 | TIP FY 20-25, AMEND#2; ADD PROJECT TO STIP; NEW |  |  | JEFFERSON | TBD | Galene Drive/Sprowl Road Collector Extension | [5 empty] | Improve capacity along Galene Drive from Maple Road to College Drive and improve mobility between Galene Drive and Watterson Trail. Potential improvements include realigning Galene Drive and Sprowl Drive, extending Sprowl Road across Taylorsville Road to Bluebird Lane and Shelby Street, widening Galene Drive, Sprowl Road and Shelby Street, curb and gutter, sidewalk and bicycle facilities turning movements and signalization. | P |  | STP | 2021 | 375000 | 300000 |  |  | 75000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.271 | 2021-01-12 | TIP FY 20-25, AMEND#2; ADD PROJECT TO STIP; NEW |  |  | JEFFERSON | TBD | [6 empty] | Within the Louisville Central Business District (CBD), the street lights are owned and maintained by Louisville Metro Government. This project is for the rehabilitation including updating to LED lighting or replacement of these street lights. Many of the street lights within the CBD are nearing the end of their useful life and require replacement. This project will identify those street lights requiring replacement and updating to current standards. |  |  |  |  | 1250000 | 1250000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.116 | 2019-08-09 | TIP FY 17-20; ADMIN MOD#20, ADD PROJECT TO STIP; NEW |  |  | JESSAMINE | 7-414 | KY 1980 |  | 0 | 3.205 | SAFETY | SAFETY(P) | IMPROVE ROADWAY GEOMETRICS, TYPICAL SECTION, AND ROADWAY HAZARDS ON KY 1980 (BRANNON RD) FROM US 68 (HARRODSBURG RD) TO US 27 (NICHOLASVILLE RD)(12CCR)(18CCN) | R |  | SLX | 2020 | 2000000 | 2000000 |  |  |  | 0 |  |  |  |  | 0
STIP | [7 empty] | HSIP | 2681032 | JESSAMINE | 7-915 | US 68 | 0.7 | 4.1 | 4.8 | SAFETY | SAFETY(P) | IMPROVE INTERSECTION OF KY-29 NORTH OF WILMORE.(16CCR)(18CCR) | U |  | STP | 2019 | 650000 | 650000 |  |  | 0 |  |  | OBLIGATED |  | 640000 | 640000 | 2019 | 3RD QUARTER
STIP | [9 empty] | JESSAMINE | 7-915 | US 68 | 0.7 | 4.1 | 4.8 | SAFETY | SAFETY(P) | IMPROVE INTERSECTION OF KY-29 NORTH OF WILMORE.(16CCR)(18CCR) | C |  | STP | 2020 | 1080000 | 1080000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.209 | 2020-07-15 | TIP FY 17-20, ADMIN MOD#32; UPDATE FUND AMOUNT; MOD |  |  | JESSAMINE | 7-915 | US 68 | 0.7 | 4.1 | 4.8 | SAFETY | SAFETY(P) | IMPROVE INTERSECTION OF KY-29 NORTH OF WILMORE.(16CCR)(18CCR) | C |  | SLX | 2020 | 1681000 | 1401000 |  |  | 280000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.284 | 2021-03-09 | TIP FY 21-24, ADMIN MOD#3; ADD PROJECT TO STIP; NEW |  |  | JESSAMINE | 7-959 | KY 169 |  | 13.1 | 13.6 | RELIABILITY | SAFETY-HAZARD ELIM(P) | Installation of a Microsurface Treatment on KY 169 from MP 13.10 to MP 13.60 in Jessamine County, KY. | C |  | SAF | 2021 | 30000 | 24000 |  |  | 6000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.284 | 2021-03-09 | TIP FY 21-24, ADMIN MOD#3; ADD PROJECT TO STIP; NEW |  |  | JESSAMINE | 7-960 | KY 1981 |  | 4.6 | 6.13 | RELIABILITY | SAFETY-HAZARD ELIM(P) | Improve pavement friction on KY 1981 from MP 4.6 to MP 6.13 in Jessamine County, KY. | C |  | SAF | 2021 | 200000 | 160000 |  |  | 40000 | [5 empty] | 0
STIP | [9 empty] | JESSAMINE | 7-1136 | KY 39 | 0.036 | 3.74 | 3.776 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER HICKMAN CREEK AT BLACK BRIDGE ON KY 39 1.3 MI N OF KY 1268. (057B00002N)(EBRP) | D |  | BR/STP | 2019 | 350000 | 217000 |  |  | 133000 | [5 empty] | 0
STIP | [9 empty] | JESSAMINE | 7-1136 | KY 39 | 0.036 | 3.74 | 3.776 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER HICKMAN CREEK AT BLACK BRIDGE ON KY 39 1.3 MI N OF KY 1268. (057B00002N)(EBRP) | C |  | BR/STP | 2020 | 1365000 | 846300 |  |  | 518700 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.112 | 2019-08-08 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030163 | JESSAMINE | 7-1136 | KY 39 | 0.036 | 3.74 | 3.776 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER HICKMAN CREEK AT BLACK BRIDGE ON KY 39 1.3 MI N OF KY 1268. (057B00002N)(EBRP) | C |  | BR/STP | 2020 | 2139000 | 2139000 |  |  | 0 |  |  | OBLIGATED |  | 1943565 | 1943565 | 2019 | 4TH QUARTER
STIP | [9 empty] | JESSAMINE | 7-1144 | CR 1238 |  | 0.868 | 0.892 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON CR-1238 (0.88) OVER NS SYSTEM. 057R00605N | D |  | BR/STP | 2019 | 260000 | 161200 |  |  | 98800 | [5 empty] | 0
STIP | [9 empty] | JESSAMINE | 7-1144 | CR 1238 |  | 0.868 | 0.892 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON CR-1238 (0.88) OVER NS SYSTEM. 057R00605N | C |  | BR/STP | 2020 | 805000 | 499100 |  |  | 305900 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.268 | 2020-12-23 | TIP FY 21-24, ADMIN MOD#1; ADD C PHASE TO STIP; NEW NOTE: D, R & U PHASE ARE TAP FUNDS |  |  | JESSAMINE | 7-3235 | KY 39 |  | 8.43 | 9.36 | RELIABILITY | TRANSP ENHANCEMENT(P) | CONSTRUCT SHARED USE PATH ALONG W MAPLE (KY 39) TO THE EASTERN BYPASS TRAIL AND MILES ROAD INTERSECTION IN NICHOLASVILLE (2018BOP). | C |  | SLX | 2022 | 2200000 | 1760000 |  |  |  | 440000 |  |  |  |  | 0
STIP | [9 empty] | JESSAMINE | 7-8851 | KY 169 | 0.046 | 10.807 | 10.853 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF RAILROAD BRIDGE ON KY 169 (NORTH 3RD STREET) BETWEEN MEADOWLARK LANE & ILHARDT AVENUE. (057R00603N)(14CCN)(16CCR)(SD) | C |  | BR/STP | 2020 | 1500000 | 930000 |  |  | 570000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.187 | 2020-05-11 | TIP FY 17-20, ADMIN MOD#29; UPDATE FUND AMOUNTS; MOD |  |  | JESSAMINE | 7-8851 | KY 169 | 0.046 | 10.807 | 10.853 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF RAILROAD BRIDGE ON KY 169 (NORTH 3RD STREET) BETWEEN MEADOWLARK LANE & ILHARDT AVENUE. (057R00603N)(14CCN)(16CCR)(SD) | C |  | BR/STP | 2020 | 1685000 | 1648000 |  |  |  | 37000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.202 | 2020-07-01 | TIP FY 17-20, ADMIN MOD #30; ADD C PHASE TO STIP; NEW |  |  | JESSAMINE | 7-9012.9 | US 27 CS 1257 |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | CONSTRUCT OFFSET LEFT TURN LANES ALONG US 27, UPGRADE THE TRAFFIC SIGNAL TO INCLUDE REFLECTIVE BACKPLATES AND IMPROVE THE STRIPING ALONG EDGEWOOD DR NEAR THE INTERSECTION OF US 27 & EDGEWOOD DRIVE. | C |  | SAF | 2020 | 130000 | 117000 |  |  | 13000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.112 | 2019-08-08 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW. LEXINGTON MPO TIP FY 17-20, CHAPTER 4 GROUPED PROJECTS, PG 18. | HSIP | 5191013 | JESSAMINE | 7-9014 | KY 169 |  | 12.363 | 16.555 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 169 FROM MP 12.363 TO MP 16.555 IN JESSAMINE COUNTY. (2018BOP) | D |  | SAF | 2019 | 350000 | 350000 |  |  | 0 |  |  | OBLIGATED |  | 350000 | 350000 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.323 | 2021-08-02 | TIP FY 21-24, ADMIN MOD#6; ADD R PHASE TO STIP; NEW | HSIP | 5191013 | JESSAMINE | 7-9014 | KY 169 |  | 11.978 | 16.555 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 169 FROM MP 11.978 TO MP 16.555 IN JESSAMINE COUNTY. (2018BOP) | R |  | SAF | 2021 | 150000 | 135000 |  |  | 15000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.323 | 2021-08-02 | TIP FY 21-24, ADMIN MOD#6; ADD U PHASE TO STIP; NEW | HSIP | 5191013 | JESSAMINE | 7-9014 | KY 169 |  | 11.978 | 16.555 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 169 FROM MP 11.978 TO MP 16.555 IN JESSAMINE COUNTY. (2018BOP) | U |  | SAF | 2021 | 100000 | 90000 |  |  | 10000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.323 | 2021-08-02 | TIP FY 21-24, ADMIN MOD#6; ADD C PHASE TO STIP; NEW | HSIP | 5191013 | JESSAMINE | 7-9014 | KY 169 |  | 11.978 | 16.555 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 169 FROM MP 11.978 TO MP 16.555 IN JESSAMINE COUNTY. (2018BOP) | C |  | SAF | 2022 | 2400000 | 2160000 |  |  | 240000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.163 | 2020-01-27 | TIP FY 17-20; ADMIN MOD#25; ADD PROJECT TO STIP; NEW |  |  | JESSAMINE | 7-9006.5 | US 27 |  | 6.402 | 6.452 | SAFETY | SAFETY-HAZARD ELIM(P) | REBUILD THE TRAFFIC SIGNAL AND CONSTRUCT PEDESTRIAN IMPROVEMENTS AT THE INTERSECTION OF US 27 & W MAXWELL ST. (2018BOP) | C |  | SAF | 2020 | 185000 | 185000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | JESSAMINE | 7-10011 | KY 1268 |  | 4.162 | 4.188 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 1268 BRIDGE OVER HICKMAN CREEK. (057B00022N) | D |  | BR/STP | 2019 | 308000 | 190960 |  |  | 117040 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030199 | JESSAMINE | 7-10011 | KY 1268 |  | 4.162 | 4.188 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 1268 BRIDGE OVER HICKMAN CREEK. (057B00022N) | C |  | BR/STP | 2020 | 1232000 | 763840 |  |  | 468160 |  |  | OBLIGATED |  | 990965 | 990965 | 2019 | 4TH QUARTER
STIP | [9 empty] | JOHNSON | 12-134.02 | KY 172 |  | 9.132 | 9.232 | RELIABILITY | RECONSTRUCTION(O) | FEDERAL HIGHWAY FUNDS DEDICATED TO RECONSTRUCT STONE COAL ROAD IN JOHNSON COUNTY. ("KYD" FUNDS NOT AVAILABLE FOR ADDITIONAL AMOUNT NEEDED TO COVER COST) | C |  | KYD | 2019 | 203005 | 203005 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.306 | 2021-06-16 | ADD D PHASE TO STIP; NEW |  |  | JOHNSON | 12-194 | KY 40 |  | 9.375 | 9.575 | SAFETY | SAFETY(P) | ADDRESS GEOMETRIC AND SAFETY ISSUES AND FUTURE CONGESTION MITIGATION ON KY 40 FROM 0.10 MILE WEST OF TEAYS BR. ROAD TO 0.10 MILE EAST OF TEAYS BR. ROAD.(12CCR) (2020CCN) | D |  | SPP | 2021 | 500100 | 100 |  |  | 500000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.015 | 2019-01-25 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 9010357 | JOHNSON, LAWRENCE, PIKE | 12-9012 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | PRELIMINARY DESIGN AND STUDY TO DETERMINE LOW COST IMPROVEMENTS AT VARIOUS INTERSECTIONS WITHIN DISTRICT 12. (2018BOP) | D |  | SAF | 2019 | 200000 | 200000 |  |  | 0 |  |  | OBLIGATED | 200000 |  | 200000 | 2019 | 2ND QUARTER
STIP |  | No | [7 empty] | KENTON | 6-17.05 | I 75 |  | 191.277 | 191.777 | ASSET MANAGEMENT | AM-BRIDGE (P) | KY 143 HPP EARMARK "ADDRESS DEFICIENCIES OF BRENT SPENCE BRIDGE, KENTON COUNTY, KENTUCKY". (2005HPP-KY143)(SEE 6-17.04 FOR ADDITIONAL 2005HPP FUNDING)(SD) | C |  | HPP | 2019 | 1439840 | 1439840 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.253 | 2020-10-26 | TIP FY 21-24, AMEND#2; UPDATE FISCAL YEAR AND FUND AMOUNTS; MOD |  |  | KENTON | 6-17.05 | I 75 |  | 191.277 | 191.777 | ASSET MANAGEMENT | AM-BRIDGE (P) | KY 143 HPP EARMARK "ADDRESS DEFICIENCIES OF BRENT SPENCE BRIDGE, KENTON COUNTY, KENTUCKY". (2005HPP-KY143)(SEE 6-17.04 FOR ADDITIONAL 2005HPP FUNDING)(SD) | C |  | NH | 2021 | 15000000 | 12000000 |  |  | 3000000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.253 | 2020-10-26 | TIP FY 21-24, AMEND#2; UPDATE FISCAL YEAR AND FUND AMOUNTS; MOD |  |  | KENTON | 6-17.05 | I 75 |  | 191.277 | 191.777 | ASSET MANAGEMENT | AM-BRIDGE (P) | KY 143 HPP EARMARK "ADDRESS DEFICIENCIES OF BRENT SPENCE BRIDGE, KENTON COUNTY, KENTUCKY". (2005HPP-KY143)(SEE 6-17.04 FOR ADDITIONAL 2005HPP FUNDING)(SD) | C |  | NH | 2022 | 15000000 | 12000000 |  |  | 3000000 | [5 empty] | 0
STIP |  | No | [7 empty] | KENTON | 6-17.09 | I 75 |  | 191.277 | 191.777 | ASSET MANAGEMENT | AM-BRIDGE (P) | BRENT SPENCE BRIDGE PROJECT (ADDITIONAL PROJECT FUNDS FOR MAINTENANCE, REPAIR AND PAINTING). (10CCR)(12CCR)(SD) | C |  | BR/NH | 2019 | 30000000 | 18600000 |  |  | 11400000 | [5 empty] | 0
STIP | YES | No | [7 empty] | KENTON | 6-17.09 | I 75 |  |  |  | ASSET MANAGEMENT | AM-BRIDGE (P) | BRENT SPENCE BRIDGE PROJECT (SPECIAL FINANCING MECHANISM KY SHARE) | C |  | NH | 2023 | 1355000000 | 1355000000 |  |  | 0 |  | YES |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; ADD PROJECT TO STIP; NEW |  |  | KENTON | 6-162.10 | KY 1303 |  | 0 | 1.1 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE SAFETY AND REDUCE CONGESTION ON KY-1303 FROM KY-536 TO BEECHGROVE ELEMENTARY (PRIORITY SECTION 4). DESIGN PHASE UNDER PARENT NO. 6-162.01. (2012BOP)(16CCR)(18CCR) | R |  | STBG | 2022 | 3660000 | 2928000 |  |  | 732000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; ADD PROJECT TO STIP; NEW |  |  | KENTON | 6-162.10 | KY 1303 |  | 0 | 1.1 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE SAFETY AND REDUCE CONGESTION ON KY-1303 FROM KY-536 TO BEECHGROVE ELEMENTARY (PRIORITY SECTION 4). DESIGN PHASE UNDER PARENT NO. 6-162.01. (2012BOP)(16CCR)(18CCR) | U |  | STBG | 2023 | 4110000 | 3288000 |  |  | 822000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; ADD PROJECT TO STIP; NEW |  |  | KENTON | 6-162.10 | KY 1303 |  | 0 | 1.1 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE SAFETY AND REDUCE CONGESTION ON KY-1303 FROM KY-536 TO BEECHGROVE ELEMENTARY (PRIORITY SECTION 4). DESIGN PHASE UNDER PARENT NO. 6-162.01. (2012BOP)(16CCR)(18CCR) | C |  | STBG | 2024 | 11560000 | 9248000 |  |  | 2312000 | [5 empty] | 0
STIP |  | No | [7 empty] | KENTON | 6-162.2 | KY 536 | 1.061 | 0 | 1.061 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE SAFETY AND REDUCE CONGESTION ON KY-536 FROM THE WEST END OF THE NS RAILROAD BRIDGE (B91) TO KY-1303 (PRIORITY SECTION 1). DESIGN PHASE UNDER PARENT NO. 6-162.01. (16CCN)(18CCR) | U |  | STP | 2019 | 1000000 | 1000000 |  |  | 0 | [5 empty] | 0
STIP |  | No | [7 empty] | KENTON | 6-162.2 | KY 536 | 1.061 | 0 | 1.061 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE SAFETY AND REDUCE CONGESTION ON KY-536 FROM THE WEST END OF THE NS RAILROAD BRIDGE (B91) TO KY-1303 (PRIORITY SECTION 1). DESIGN PHASE UNDER PARENT NO. 6-162.01. (16CCN)(18CCR) | C |  | STP | 2020 | 5410000 | 5410000 |  |  | 0 | [5 empty] | 0
|  |  |  | AMENDMENT | 2018.003 | 2019-07-25 | TIP FY 20-23; UPDATE FUND AMOUNT; MOD |  |  | KENTON | 6-162.20 | KY 536 | 1.061 | 0 | 1.061 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE SAFETY AND REDUCE CONGESTION ON KY-536 FROM THE WEST END OF THE NS RAILROAD BRIDGE (B91) TO KY-1303 (PRIORITY SECTION 1). DESIGN PHASE UNDER PARENT NO. 6-162.01. (16CCN)(18CCR) | C |  | STP | 2020 | 10820000 | 10820000 |  |  | 0 | [5 empty] | 0
STIP | YES | No | [7 empty] | KENTON | 6-162.21 | KY 536 | 1.061 | 0 | 1.061 | RELIABILITY | PREFINANCD CONVRSN(O) | IMPROVE SAFETY AND REDUCE CONGESTION ON KY-536 FROM THE WEST END OF THE NS RAILROAD BRIDGE (B91) TO KY-1303 (PRIORITY SECTION 1). DESIGN PHASE UNDER PARENT NO. 6-162.01.(16CCN)(18CCR) | C |  | STP | 2021 | 5410000 | 4328000 |  |  | 1082000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.253 | 2020-10-26 | TIP FY 21-24, AMEND#2; ADD R PHASE TO STIP; NEW |  |  | KENTON | 6-162.3 | KY 536 |  | 1.061 | 2.542 | RELIABILITY | AIR QUALITY(P) | IMPROVE SAFETY AND REDUCE CONGESTION ON KY-536 FROM KY 1303 TO WILLIAMSWOOD ROAD/CALVARY DRIVE (PRIORITY SECTION 2). DESIGN PHASE UNDER PARENT NO. 6-162.01. (2012BOP)(18CCN) (2020CCR) | R |  | STP | 2021 | 3500000 | 2800000 |  |  | 700000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.253 | 2020-10-26 | TIP FY 21-24, AMEND#2; ADD U PHASE TO STIP; NEW |  |  | KENTON | 6-162.3 | KY 536 |  | 1.061 | 2.542 | RELIABILITY | AIR QUALITY(P) | IMPROVE SAFETY AND REDUCE CONGESTION ON KY-536 FROM KY 1303 TO WILLIAMSWOOD ROAD/CALVARY DRIVE (PRIORITY SECTION 2). DESIGN PHASE UNDER PARENT NO. 6-162.01. (2012BOP)(18CCN) (2020CCR) | U |  | STP | 2021 | 1950000 | 1560000 |  |  | 390000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.253 | 2020-10-26 | TIP FY 21-24, AMEND#2; ADD C PHASE TO STIP; NEW |  |  | KENTON | 6-162.3 | KY 536 |  | 1.061 | 2.542 | RELIABILITY | AIR QUALITY(P) | IMPROVE SAFETY AND REDUCE CONGESTION ON KY-536 FROM KY 1303 TO WILLIAMSWOOD ROAD/CALVARY DRIVE (PRIORITY SECTION 2). DESIGN PHASE UNDER PARENT NO. 6-162.01. (2012BOP)(18CCN) (2020CCR) | C |  | STP | 2023 | 16230000 | 12984000 |  |  | 3246000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.253 | 2020-10-26 | TIP FY 21-24, AMEND#2; ADD R PHASE TO STIP; NEW |  |  | KENTON | 6-162.4 | KY 536 |  | 2.542 | 4.476 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE SAFETY AND REDUCE CONGESTION ON KY-536 FROM WILLIAMSWOOD ROAD/CALVARY DRIVE TO KY-17 (PRIORITY SECTION 3). DESIGN PHASE UNDER PARENT NO. 6-162.01. (2012BOP)(18CCR) (2020CCR) | R |  | STP | 2022 | 13980000 | 11184000 |  |  | 2796000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.253 | 2020-10-26 | TIP FY 21-24, AMEND#2; ADD U PHASE TO STIP; NEW |  |  | KENTON | 6-162.4 | KY 536 |  | 2.542 | 4.476 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE SAFETY AND REDUCE CONGESTION ON KY-536 FROM WILLIAMSWOOD ROAD/CALVARY DRIVE TO KY-17 (PRIORITY SECTION 3). DESIGN PHASE UNDER PARENT NO. 6-162.01. (2012BOP)(18CCR) (2020CCR) | U |  | STP | 2023 | 1760000 | 1408000 |  |  | 352000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.253 | 2020-10-26 | TIP FY 21-24, AMEND#2; ADD C PHASE TO STIP; NEW |  |  | KENTON | 6-162.4 | KY 536 |  | 2.542 | 4.476 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE SAFETY AND REDUCE CONGESTION ON KY-536 FROM WILLIAMSWOOD ROAD/CALVARY DRIVE TO KY-17 (PRIORITY SECTION 3). DESIGN PHASE UNDER PARENT NO. 6-162.01. (2012BOP)(18CCR) (2020CCR) | C |  | STP | 2024 | 23790000 | 19032000 |  |  | 4758000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.287 | 2021-03-12 | TIP FY 21-24, AMEND#4; ADD D PHASE TO STIP; NEW |  |  | KENTON | 6-178 | CS 5075 |  | 0 | 0.711 | RELIABILITY | MATCHED FED FUNDS(O) | Bridge over Norfolk Southern RR Bridge replacement and new sidewalk on New Buffington Road | D |  | SNK | 2021 | 137500 | 110000 |  |  | 2500 | 25000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.287 | 2021-03-12 | TIP FY 21-24, AMEND#4; ADD R PHASE TO STIP; NEW |  |  | KENTON | 6-178 | CS 5075 |  | 0 | 0.711 | RELIABILITY | MATCHED FED FUNDS(O) | Bridge over Norfolk Southern RR Bridge replacement and new sidewalk on New Buffington Road | R |  | SNK | 2023 | 50000 | 40000 |  |  |  | 10000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.287 | 2021-03-12 | TIP FY 21-24, AMEND#4; ADD U PHASE TO STIP; NEW |  |  | KENTON | 6-178 | CS 5075 |  | 0 | 0.711 | RELIABILITY | MATCHED FED FUNDS(O) | Bridge over Norfolk Southern RR Bridge replacement and new sidewalk on New Buffington Road | U |  | SNK | 2023 | 50000 | 40000 |  |  |  | 10000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.287 | 2021-03-12 | TIP FY 21-24, AMEND#4; ADD C PHASE TO STIP; NEW |  |  | KENTON | 6-178 | CS 5075 |  | 0 | 0.711 | RELIABILITY | MATCHED FED FUNDS(O) | Bridge over Norfolk Southern RR Bridge replacement and new sidewalk on New Buffington Road | C |  | SNK | 2024 | 602500 | 482000 |  |  |  | 120500 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.287 | 2021-03-12 | TIP FY 21-24, AMEND#4; ADD D PHASE TO STIP; NEW |  |  | KENTON | 6-179 | CS 5079 |  | 0.963 | 1.62 | RELIABILITY | MATCHED FED FUNDS(O) | Resurfacing and correct drainage issues and replace existing multi-use path along Garvey Avenue from Florence Court to past Comanche Trail. | D |  | SNK | 2022 | 21250 | 17000 |  |  | 1250 | 3000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.287 | 2021-03-12 | TIP FY 21-24, AMEND#4; ADD C PHASE TO STIP; NEW |  |  | KENTON | 6-179 | CS 5079 |  | 0.963 | 1.62 | RELIABILITY | MATCHED FED FUNDS(O) | Resurfacing and correct drainage issues and replace existing multi-use path along Garvey Avenue from Florence Court to past Comanche Trail. | C |  | SNK | 2023 | 278750 | 223000 |  |  |  | 55750 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; ADD D PHASE TO STIP; NEW |  |  | KENTON | 6-419 | CR 1316 | 0.275 | 0 | 0.275 | RELIABILITY | MATCHED FED FUNDS(O) | PHASE I MULTI-USE PATH ALONG BROMLEY CRESCENT SPRINGS RD FROM ANDERSON ROAD TO AMSTERDAM ROAD. (2012BOP) | D |  | SNK | 2021 | 1040000 | 832000 |  |  |  | 208000 |  |  |  |  | 0
STIP | YES | No | [7 empty] | KENTON | 6-419 | CR 1316 | 0.275 | 0 | 0.275 | RELIABILITY | MATCHED FED FUNDS(O) | PHASE I MULTI-USE PATH ALONG BROMLEY CRESCENT SPRINGS RD FROM ANDERSON ROAD TO AMSTERDAM ROAD. (2012BOP) | R |  | SNK | 2019 | 400000 | 320000 |  |  |  | 80000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; UPDATE FISCAL YEAR & FUND AMOUNTS; MOD |  |  | KENTON | 6-419 | CR 1316 | 0.275 | 0 | 0.275 | RELIABILITY | MATCHED FED FUNDS(O) | PHASE I MULTI-USE PATH ALONG BROMLEY CRESCENT SPRINGS RD FROM ANDERSON ROAD TO AMSTERDAM ROAD. (2012BOP) | R |  | SNK | 2021 | 1080000 | 864000 |  |  |  | 216000 |  |  |  |  | 0
STIP | YES | No | [5 empty] | STPM | 3002258 | KENTON | 6-419 | CR 1316 | 0.275 | 0 | 0.275 | RELIABILITY | MATCHED FED FUNDS(O) | PHASE I MULTI-USE PATH ALONG BROMLEY CRESCENT SPRINGS RD FROM ANDERSON ROAD TO AMSTERDAM ROAD. (2012BOP) | U |  | SNK | 2019 | 800000 | 640000 |  |  |  | 160000 |  | OBLIGATED | 172800 |  | 172800 | 2019 | 4TH QUARTER | Kenton County
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; UPDATE FISCAL YEAR & FUND AMOUNTS; MOD |  |  | KENTON | 6-419 | CR 1316 | 0.275 | 0 | 0.275 | RELIABILITY | MATCHED FED FUNDS(O) | PHASE I MULTI-USE PATH ALONG BROMLEY CRESCENT SPRINGS RD FROM ANDERSON ROAD TO AMSTERDAM ROAD. (2012BOP) | U |  | SNK | 2021 | 60000 | 48000 |  |  |  | 12000 |  |  |  |  | 0
STIP | YES | No | [7 empty] | KENTON | 6-419 | CR 1316 | 0.275 | 0 | 0.275 | RELIABILITY | MATCHED FED FUNDS(O) | PHASE I MULTI-USE PATH ALONG BROMLEY CRESCENT SPRINGS RD FROM ANDERSON ROAD TO AMSTERDAM ROAD. (2012BOP) | C |  | SNK | 2019 | 4045000 | 3236000 |  |  |  | 809000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.149 | 2019-11-15 | TIP FY 20-23; ADMIN MOD#4; UPDATE FUND AMOUNTS & FISCAL YEAR FROM 2019 TO 2020; MOD |  |  | KENTON | 6-419 | CR 1316 | 0.275 | 0 | 0.275 | RELIABILITY | MATCHED FED FUNDS(O) | PHASE I MULTI-USE PATH ALONG BROMLEY CRESCENT SPRINGS RD FROM ANDERSON ROAD TO AMSTERDAM ROAD. (2012BOP) | C |  | SNK | 2020 | 5056000 | 4044800 |  |  |  | 1011200
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; UPDATE FISCAL YEAR & FUND AMOUNTS; MOD |  |  | KENTON | 6-419 | CR 1316 | 0.275 | 0 | 0.275 | RELIABILITY | MATCHED FED FUNDS(O) | PHASE I MULTI-USE PATH ALONG BROMLEY CRESCENT SPRINGS RD FROM ANDERSON ROAD TO AMSTERDAM ROAD. (2012BOP) | C |  | SNK & STBG | 2021 | 7280360 | 5824288 |  |  |  | 1456072 |  |  |  |  | 0
STIP | YES | No | [7 empty] | KENTON | 6-419.01 | CS 3806 |  | 0.275 | 0.741 | RELIABILITY | MATCHED FED FUNDS(O) | PHASE 2 BROMLEY CRESCENT SPRINGS ROAD BETWEEN THE TWO SEGMENTS OF AMSTERDAM ROAD. RECONSTRUCT BROMLEY CRESCENT SPRINGS ROAD AND IMPROVE INTERSECTION WITH ST. JOHNS ROAD. | D |  | SNK | 2019 | 269600 | 215680 |  |  |  | 53920 |  |  |  |  | 0
STIP | YES | No | [7 empty] | KENTON | 6-419.01 | CS 3806 |  | 0.275 | 0.741 | RELIABILITY | MATCHED FED FUNDS(O) | PHASE 2 BROMLEY CRESCENT SPRINGS ROAD BETWEEN THE TWO SEGMENTS OF AMSTERDAM ROAD. RECONSTRUCT BROMLEY CRESCENT SPRINGS ROAD AND IMPROVE INTERSECTION WITH ST. JOHNS ROAD. | R |  | SNK | 2019 | 504000 | 403200 |  |  |  | 100800 |  |  |  |  | 0
STIP | YES | No | [7 empty] | KENTON | 6-419.01 | CS 3806 |  | 0.275 | 0.741 | RELIABILITY | MATCHED FED FUNDS(O) | PHASE 2 BROMLEY CRESCENT SPRINGS ROAD BETWEEN THE TWO SEGMENTS OF AMSTERDAM ROAD. RECONSTRUCT BROMLEY CRESCENT SPRINGS ROAD AND IMPROVE INTERSECTION WITH ST. JOHNS ROAD. | U |  | SNK | 2019 | 560000 | 448000 |  |  |  | 112000 |  |  |  |  | 0
STIP | YES | No | [7 empty] | KENTON | 6-419.01 | CS 3806 |  | 0.275 | 0.741 | RELIABILITY | MATCHED FED FUNDS(O) | PHASE 2 BROMLEY CRESCENT SPRINGS ROAD BETWEEN THE TWO SEGMENTS OF AMSTERDAM ROAD. RECONSTRUCT BROMLEY CRESCENT SPRINGS ROAD AND IMPROVE INTERSECTION WITH ST. JOHNS ROAD. | C |  | SNK | 2020 | 276000 | 220800 |  |  |  | 55200 |  |  |  |  | 0
STIP | YES | No | [7 empty] | KENTON | 6-428.1 | CS 4128 |  | 2.19 | 3.11 | RELIABILITY | RESURFACING(P) | RESURFACE & STABILIZE DUDLEY ROAD FROM WINDING TRAILS TO THOMAS MORE PARKWAY (PHASE 1). (2014BOPC)(MOA WITH CITY OF EDGEWOOD). | C |  | SNK | 2019 | 1044000 | 835200 |  |  |  | 208800 |  |  |  |  | 0
STIP | YES | No | [7 empty] | KENTON | 6-428.2 | CS 4128 |  | 1.46 | 2.19 | RELIABILITY | RESURFACING(P) | RESURFACE & STABILIZE DUDLEY ROAD FROM THOMAS MORE PARKWAY TO CATHERINE DRIVE (PHASE 2). (2014BOPC)(MOA WITH CITY OF EDGEWOOD). | C |  | SNK | 2019 | 924000 | 739200 |  |  |  | 184800 |  |  |  |  | 0
STIP | YES | No | [7 empty] | KENTON | 6-428.3 | CS 4128 |  | 0.879 | 1.459 | RELIABILITY | RESURFACING(P) | DUDLEY ROAD PHASE 3. ROADWAY RESURFACING AND STABILIZATION. CONSTRUCT CONSISTENT 11' TRAVEL LANE IN EACH DIRECTION FROM CATHERINE DRIVE TO THE SUMMIT HILLS COUNTRY CLUB ENTRANCE. | D |  | SNK | 2019 | 178000 | 142400 |  |  |  | 35600 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.049 | 2019-04-16 | TIP FY 18-21; ADMIN MOD#17; UPDATE FUND AMOUNTS & FISCAL YEAR; INCLUDES MERGED FUNDS FROM ITEM 6-428.40; UPDATE PROJECT DESCRIPTION & TERMINI; MOD | STPM | 3002282 | KENTON | 6-428.3 | CS 4128 |  | 0.879 | 1.459 | RELIABILITY | RESURFACING(P) | DUDLEY ROAD PHASE 3 & 4. ROADWAY RESURFACING AND STABILIZATION. CONSTRUCT CONSISTENT 11' TRAVEL LANE IN EACH DIRECTION FROM CATHERINE DRIVE TO DIXIE HIGHWAY. | D |  | SNK | 2020 | 788333 | 489000 |  |  |  | 299333 |  | OBLIGATED | 493900 |  | 493900 | 2019 | 3RD QUARTER | CITY OF EDGEWOOD
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.069 | 2019-05-13 | TIP FY 18-21; ADMIN MOD#18; UPDATE FISCAL YEAR FROM FY20 TO FY19; MOD (SEE NOTE BELOW) | STPM | 3002282 | KENTON | 6-428.3 | CS 4128 |  | 0.879 | 1.459 | RELIABILITY | RESURFACING(P) | DUDLEY ROAD PHASE 3 & 4. ROADWAY RESURFACING AND STABILIZATION. CONSTRUCT CONSISTENT 11' TRAVEL LANE IN EACH DIRECTION FROM CATHERINE DRIVE TO DIXIE HIGHWAY. | D |  | SNK | 2019 | 788333 | 489000 |  |  |  | 299333 |  |  |  |  | 0 |  |  | CITY OF EDGEWOOD
[7 empty] | THE DESIGN OF PHASES 3 & 4 UNDER 6.428.30 IS FUNDED AS 60/40 AND 6-428.30 IS NOW PROGRAMMED UNDER 3002337. WITHDRAW $449,000 Z230 FUNDS AND $44,900 FUNDS AND MOVE TO 3002337. | STPM | 3002337 | KENTON | 6-428.3 | CS 4128 |  | 0.879 | 1.459 | RELIABILITY | RESURFACING(P) | DUDLEY ROAD PHASE 3 & 4. ROADWAY RESURFACING AND STABILIZATION. CONSTRUCT CONSISTENT 11' TRAVEL LANE IN EACH DIRECTION FROM CATHERINE DRIVE TO DIXIE HIGHWAY. | D |  | SNK | 2019 | 793233 | 493900 | [5 empty] | OBLIGATED | 493900 |  | 493900 | 2019 | 3RD QUARTER | CITY OF EDGEWOOD
STIP | YES | No | [7 empty] | KENTON | 6-428.3 | CS 4128 |  | 0.879 | 1.459 | RELIABILITY | RESURFACING(P) | DUDLEY ROAD PHASE 3. ROADWAY RESURFACING AND STABILIZATION. CONSTRUCT CONSISTENT 11' TRAVEL LANE IN EACH DIRECTION FROM CATHERINE DRIVE TO THE SUMMIT HILLS COUNTRY CLUB ENTRANCE. | C |  | SNK | 2019 | 1080000 | 864000 |  |  |  | 216000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.049 | 2019-04-16 | TIP FY 18-21; ADMIN MOD#17; UPDATE FUND AMOUNTS & FISCAL YEAR; INCLUDES MERGED FUNDS FROM ITEM 6-428.40; UPDATE PROJECT DESCRIPTION & TERMINI; MOD |  |  | KENTON | 6-428.3 | CS 4128 |  | 0.879 | 1.459 | RELIABILITY | RESURFACING(P) | DUDLEY ROAD PHASE 3 & 4. ROADWAY RESURFACING AND STABILIZATION. CONSTRUCT CONSISTENT 11' TRAVEL LANE IN EACH DIRECTION FROM CATHERINE DRIVE TO DIXIE HIGHWAY. | C |  | SNK | 2021 | 4528000 | 2716800 |  |  |  | 1811200 |  |  |  |  | 0
STIP | YES | No | [7 empty] | KENTON | 6-428.4 | CS 4128 |  | 0 | 0.879 | RELIABILITY | RESURFACING(P) | DUDLEY ROAD PHASE 4. ROADWAY RESURFACING AND STABILIZATION. CONSTRUCT CONSISTENT 11' TRAVEL LANE IN EACH DIRECTION FROM SUMMIT HILLS COUNTRY CLUB ENTRANCE TO DIXIE HIGHWAY. | D |  | SNK | 2019 | 271000 | 216800 |  |  |  | 54200 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.049 | 2019-04-16 | TIP FY 18-21; ADMIN MOD#17; UPDATE FUND AMOUNTS & FISCAL YEAR; INCLUDES MERGED FUNDS FROM ITEM 6-428.40; UPDATE PROJECT DESCRIPTION & TERMINI; MOD |  |  | KENTON | 6-428.4 | CS 4128 |  | 0 | 0.879 | RELIABILITY | RESURFACING(P) | DUDLEY ROAD PHASE 4. ROADWAY RESURFACING AND STABILIZATION. CONSTRUCT CONSISTENT 11' TRAVEL LANE IN EACH DIRECTION FROM SUMMIT HILLS COUNTRY CLUB ENTRANCE TO DIXIE HIGHWAY. | D |  | SNK | [11 empty] | 0
STIP | YES | No | [7 empty] | KENTON | 6-428.4 | CS 4128 |  | 0 | 0.879 | RELIABILITY | RESURFACING(P) | DUDLEY ROAD PHASE 4. ROADWAY RESURFACING AND STABILIZATION. CONSTRUCT CONSISTENT 11' TRAVEL LANE IN EACH DIRECTION FROM SUMMIT HILLS COUNTRY CLUB ENTRANCE TO DIXIE HIGHWAY. | C |  | SNK | 2020 | 1636800 | 1309440 |  |  |  | 327360 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.049 | 2019-04-16 | TIP FY 18-21; ADMIN MOD#17; UPDATE FUND AMOUNTS & FISCAL YEAR; INCLUDES MERGED FUNDS FROM ITEM 6-428.40; UPDATE PROJECT DESCRIPTION & TERMINI; MOD |  |  | KENTON | 6-428.4 | CS 4128 |  | 0 | 0.879 | RELIABILITY | RESURFACING(P) | DUDLEY ROAD PHASE 4. ROADWAY RESURFACING AND STABILIZATION. CONSTRUCT CONSISTENT 11' TRAVEL LANE IN EACH DIRECTION FROM SUMMIT HILLS COUNTRY CLUB ENTRANCE TO DIXIE HIGHWAY. | C |  | SNK | [11 empty] | 0
STIP | YES | No | [7 empty] | KENTON | 6-432 | US 25 | 0.24 | 9.34 | 9.58 | SAFETY | SAFETY(P) | CONSTRUCT LEFT TURN LANE ON NB APPROACH AT THE INTERSECTION OF US 25 AND BEECHWOOD RD JUST S OF I-75. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) (2014BOP) | C |  | SNK | 2019 | 1600000 | 1280000 |  |  |  | 320000 |  |  |  |  | 0
STIP | YES | No | [5 empty] | STPM | 3002296 | KENTON | 6-435 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | LUDLOW RIVERFRONT COMMONS TRAIL- CONSTRUCT A ONE-MILE MULTI-USE PATH ALONG THE OHIO RIVER FROM HOOPER STREET TO ASH STREET IN THE CITY OF LUDLOW (2016BOP). | D |  | SNK | 2019 | 5000 | 4000 |  |  |  | 1000 |  |  |  |  | 0
STIP | YES | No | [7 empty] | KENTON | 6-435 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | LUDLOW RIVERFRONT COMMONS TRAIL- CONSTRUCT A ONE-MILE MULTI-USE PATH ALONG THE OHIO RIVER FROM HOOPER STREET TO ASH STREET IN THE CITY OF LUDLOW (2016BOP). | C |  | SNK | 2019 | 240133 | 192106.4 |  |  |  | 48026.6 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.166 | 2020-02-20 | TIP FY 20-23; ADMIN MOD#6; ADD R PHASE TO STIP; NEW |  |  | KENTON | 6-435 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | LUDLOW RIVERFRONT COMMONS TRAIL- CONSTRUCT A ONE-MILE MULTI-USE PATH ALONG THE OHIO RIVER FROM HOOPER STREET TO ASH STREET IN THE CITY OF LUDLOW (2016BOP). | R |  | SNK | 2020 | 56000 | 44800 |  |  |  | 11200 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.149 | 2019-11-15 | TIP FY 20-23; ADMIN MOD#4; UPDATE FUND AMOUNT & FISCAL YEAR FROM 2019 TO 2020; MOD |  |  | KENTON | 6-435 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | LUDLOW RIVERFRONT COMMONS TRAIL- CONSTRUCT A ONE-MILE MULTI-USE PATH ALONG THE OHIO RIVER FROM HOOPER STREET TO ASH STREET IN THE CITY OF LUDLOW (2016BOP). | C |  | SNK | 2020 | 300166 | 240133 |  |  |  | 60033 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.166 | 2020-02-20 | TIP FY 20-23; ADMIN MOD#6; UPDATE FUND AMOUNTS; MOD |  |  | KENTON | 6-435 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | LUDLOW RIVERFRONT COMMONS TRAIL- CONSTRUCT A ONE-MILE MULTI-USE PATH ALONG THE OHIO RIVER FROM HOOPER STREET TO ASH STREET IN THE CITY OF LUDLOW (2016BOP). | C |  | SNK | 2020 | 294493 | 219346 |  |  |  | 75147 |  |  |  |  | 0
STIP | YES | No | [5 empty] | STPM | 3002338 | KENTON | 6-437 | CS 6142 |  | 0 | 0.527 | SAFETY | SAFETY(P) | IMPROVE SAFETY, TRAFFIC FLOW AND DRAINAGE ISSUES ALONG BUTTERMILK PIKE (CS 6142) FROM ROGERS ROAD TO COLLINS ROAD IN THE CITY OF VILLA HILLS. A DISTANCE OF 0.527 MILES (2016BOP). | C |  | SNK | 2019 | 313857 | 251085.6 |  |  |  | 62771.4 |  | OBLIGATED | 345243 |  | 345243 | 2019 | 4TH QUARTER | CITY OF VILLA HILLS
STIP | YES | No | [5 empty] | STPM | 3002302 | KENTON | 6-438 | CS 9004 |  | 0.285 | 0.652 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT AMSTERDAM ROAD FROM GENERAL DRIVE TO REDWOOD DRIVE WITH CURB, GUTTER, STORM SEWERS AND SIDEWALK (2016BOP). | R |  | SNK | 2019 | 56000 | 44800 |  |  |  | 11200 |  | OBLIGATED | 40000 |  | 40000 | 2019 | 3RD QUARTER | City of Fort Wright
STIP | YES | No | [7 empty] | KENTON | 6-438 | CS 9004 |  | 0.285 | 0.652 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT AMSTERDAM ROAD FROM GENERAL DRIVE TO REDWOOD DRIVE WITH CURB, GUTTER, STORM SEWERS AND SIDEWALK (2016BOP). | U |  | SNK | 2019 | 32000 | 25600 |  |  |  | 6400 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.149 | 2019-11-15 | TIP FY 20-23; ADMIN MOD#4; UPDATE FUND AMOUNT & FISCAL YEAR FROM 2019 TO 2020; MOD |  |  | KENTON | 6-438 | CS 9004 |  | 0.285 | 0.652 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT AMSTERDAM ROAD FROM GENERAL DRIVE TO REDWOOD DRIVE WITH CURB, GUTTER, STORM SEWERS AND SIDEWALK (2016BOP). | U |  | SNK | 2020 | 40000 | 32000 |  |  |  | 8000 |  |  |  |  | 0
STIP | YES | No | [7 empty] | KENTON | 6-438 | CS 9004 |  | 0.285 | 0.652 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT AMSTERDAM ROAD FROM GENERAL DRIVE TO REDWOOD DRIVE WITH CURB, GUTTER, STORM SEWERS AND SIDEWALK (2016BOP). | C |  | SNK | 2019 | 2080000 | 1664000 |  |  |  | 416000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.149 | 2019-11-15 | TIP FY 20-23; ADMIN MOD#4; UPDATE FUND AMOUNT & FISCAL YEAR FROM 2019 TO 2020; MOD | STPM | 3002302 | KENTON | 6-438 | CS 9004 |  | 0.285 | 0.652 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT AMSTERDAM ROAD FROM GENERAL DRIVE TO REDWOOD DRIVE WITH CURB, GUTTER, STORM SEWERS AND SIDEWALK (2016BOP). | C |  | SNK | 2020 | 2600000 | 2080000 |  |  |  | 520000 |  | OBLIGATED | 2112000 |  | 2112000 | 2020 | 2ND QUARTER | CITY OF FORT WRIGHT
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.158 | 2020-01-14 | TIP FY 20-23; ADMIN MOD#5; UPDATE FUND AMOUNTS; MOD | STPM | 3002302 | KENTON | 6-438 | CS 9004 |  | 0.285 | 0.652 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT AMSTERDAM ROAD FROM GENERAL DRIVE TO REDWOOD DRIVE WITH CURB, GUTTER, STORM SEWERS AND SIDEWALK (2016BOP). | C |  | SNK | 2020 | 2640000 | 2112000 |  |  |  | 528000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.178 | 2020-04-14 | TIP FY 20-23; ADMIN MOD#8; UPDATE FUND AMOUNTS; MOD | STPM | 3002302 | KENTON | 6-438 | CS 9004 |  | 0.285 | 0.652 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT AMSTERDAM ROAD FROM GENERAL DRIVE TO REDWOOD DRIVE WITH CURB, GUTTER, STORM SEWERS AND SIDEWALK (2016BOP). | C |  | SNK | 2020 | 2860000 | 2288000 |  |  |  | 572000 |  |  |  |  | 0
STIP | YES | No | [5 empty] | STP | 8156012 | KENTON | 6-449 | KY 17 | 0.5 | 18.15 | 18.65 | RELIABILITY | CONGESTION MITIGTN(O) | IMPROVE SAFETY AND REDUCE CONGESTION ON KY-17 AT THE I-275 INTERCHANGE. (18CCR) | D |  | STP | 2019 | 450000 | 450000 |  |  | 0 |  |  | OBLIGATED |  | 450000 | 450000 | 2019 | 2ND QUARTER
STIP | YES | No | [7 empty] | KENTON | 6-449 | KY 17 | 0.5 | 18.15 | 18.65 | RELIABILITY | CONGESTION MITIGTN(O) | IMPROVE SAFETY AND REDUCE CONGESTION ON KY-17 AT THE I-275 INTERCHANGE. (18CCR) | R |  | STP | 2020 | 200000 | 200000 |  |  | 0 | [5 empty] | 0
STIP | YES | No | [7 empty] | KENTON | 6-449 | KY 17 | 0.5 | 18.15 | 18.65 | RELIABILITY | CONGESTION MITIGTN(O) | IMPROVE SAFETY AND REDUCE CONGESTION ON KY-17 AT THE I-275 INTERCHANGE. (18CCR) | U |  | STP | 2020 | 350000 | 350000 |  |  | 0 | [5 empty] | 0
STIP |  | No | [5 empty] | STP | 8122028 | KENTON | 6-450 | KY 1303 | 1.238 | 5.01 | 6.248 | RELIABILITY | CONGESTION MITIGTN(O) | IMPROVE SAFETY AND REDUCE CONGESTION ALONG KY-1303 (TURKEYFOOT RD) FROM DUDLEY RD TO US-25 (DIXIE HWY). (18CCR) | D |  | STP | 2019 | 1500000 | 1500000 |  |  | 0 |  |  | OBLIGATED |  | 1500000 | 1500000 | 2019 | 3RD QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.253 | 2020-10-26 | TIP FY 21-24, AMEND#2; UPDATE FISCAL YEAR AND FUND AMOUNTS; MOD |  |  | KENTON | 6-450 | KY 1303 | 1.238 | 5.01 | 6.248 | RELIABILITY | CONGESTION MITIGTN(O) | IMPROVE SAFETY AND REDUCE CONGESTION ALONG KY-1303 (TURKEYFOOT RD) FROM DUDLEY RD TO US-25 (DIXIE HWY). (18CCR) | D |  | STP | 2021 | 4375000 | 3500000 |  |  | 875000 | [5 empty] | 0
STIP |  | No | [7 empty] | KENTON | 6-450 | KY 1303 | 1.238 | 5.01 | 6.248 | RELIABILITY | CONGESTION MITIGTN(O) | IMPROVE SAFETY AND REDUCE CONGESTION ALONG KY-1303 (TURKEYFOOT RD) FROM DUDLEY RD TO US-25 (DIXIE HWY). (18CCR) | R |  | STP | 2019 | 2000000 | 2000000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.253 | 2020-10-26 | TIP FY 21-24, AMEND#2; UPDATE FISCAL YEAR AND FUND AMOUNTS; MOD |  |  | KENTON | 6-450 | KY 1303 | 1.238 | 5.01 | 6.248 | RELIABILITY | CONGESTION MITIGTN(O) | IMPROVE SAFETY AND REDUCE CONGESTION ALONG KY-1303 (TURKEYFOOT RD) FROM DUDLEY RD TO US-25 (DIXIE HWY). (18CCR) | R |  | STP | 2022 | 4600000 | 3680000 |  |  | 920000 | [5 empty] | 0
STIP |  | No | [7 empty] | KENTON | 6-450 | KY 1303 | 1.238 | 5.01 | 6.248 | RELIABILITY | CONGESTION MITIGTN(O) | IMPROVE SAFETY AND REDUCE CONGESTION ALONG KY-1303 (TURKEYFOOT RD) FROM DUDLEY RD TO US-25 (DIXIE HWY). (18CCR) | U |  | STP | 2020 | 1000000 | 1000000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.253 | 2020-10-26 | TIP FY 21-24, AMEND#2; UPDATE FISCAL YEAR AND FUND AMOUNTS; MOD |  |  | KENTON | 6-450 | KY 1303 | 1.238 | 5.01 | 6.248 | RELIABILITY | CONGESTION MITIGTN(O) | IMPROVE SAFETY AND REDUCE CONGESTION ALONG KY-1303 (TURKEYFOOT RD) FROM DUDLEY RD TO US-25 (DIXIE HWY). (18CCR) | U |  | STP | 2023 | 3250000 | 2600000 |  |  | 650000 | [5 empty] | 0
STIP | YES | No | [5 empty] | STPM | 3002335 | KENTON | 6-454 | CS 1560 |  | 0 | 0.612 | RELIABILITY | RESURFACING(P) | ADELA AVENUE. CURB-LINE MILLING, ASPHALT RESURFACING, REPLACE SIDEWALK/CURBING AND NEW SIDEWALK AS NEEDED FROM KY 1072 (SLEEPY HOLLOW ROAD/DEVERILL STREET) TO KY 8 (ELM STREET). | D |  | SNK | 2019 | 35000 | 28000 |  |  |  | 7000 |  | OBLIGATED | 40000 |  | 40000 | 2019 | 3RD QUARTER | CITY OF LUDLOW
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.128 | 2019-09-13 | TIP FY 20-23, ADMIN MOD#2; UPDATE FUND AMOUNT; MOD | STPM | 3002335 | KENTON | 6-454 | CS 1560 |  | 0 | 0.612 | RELIABILITY | RESURFACING(P) | ADELA AVENUE. CURB-LINE MILLING, ASPHALT RESURFACING, REPLACE SIDEWALK/CURBING AND NEW SIDEWALK AS NEEDED FROM KY 1072 (SLEEPY HOLLOW ROAD/DEVERILL STREET) TO KY 8 (ELM STREET). | D |  | SNK | 2019 | 61969 | 50575 |  |  |  | 11394 |  | OBLIGATED | 50575 |  | 50575 | 2019 | 3RD QUARTER | CITY OF LUDLOW
STIP | YES | No | [7 empty] | KENTON | 6-454 | CS 1560 |  | 0 | 0.612 | RELIABILITY | RESURFACING(P) | ADELA AVENUE. CURB-LINE MILLING, ASPHALT RESURFACING, REPLACE SIDEWALK/CURBING AND NEW SIDEWALK AS NEEDED FROM KY 1072 (SLEEPY HOLLOW ROAD/DEVERILL STREET) TO KY 8 (ELM STREET). | R |  | SNK | 2019 | 20000 | 16000 |  |  |  | 4000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.128 | 2019-09-13 | TIP FY 20-23, ADMIN MOD#2; UPDATE FISCAL YEAR & FUND AMOUNT; MOD | STPM | 3002335 | KENTON | 6-454 | CS 1560 |  | 0 | 0.612 | RELIABILITY | RESURFACING(P) | ADELA AVENUE. CURB-LINE MILLING, ASPHALT RESURFACING, REPLACE SIDEWALK/CURBING AND NEW SIDEWALK AS NEEDED FROM KY 1072 (SLEEPY HOLLOW ROAD/DEVERILL STREET) TO KY 8 (ELM STREET). | R |  | SNK | 2020 | 11781 | 9425 |  |  |  | 2356 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.166 | 2020-02-20 | TIP FY 20-23, ADMIN MOD#6; ROW FUNDS NOT NEEDED-MOVE FUNDS TO C PHASE; MOD | STPM | 3002335 | KENTON | 6-454 | CS 1560 |  | 0 | 0.612 | RELIABILITY | RESURFACING(P) | ADELA AVENUE. CURB-LINE MILLING, ASPHALT RESURFACING, REPLACE SIDEWALK/CURBING AND NEW SIDEWALK AS NEEDED FROM KY 1072 (SLEEPY HOLLOW ROAD/DEVERILL STREET) TO KY 8 (ELM STREET). | R |  | SNK | 2020 | 0 | 0 |  |  |  | 0 |  |  |  |  | 0
STIP | YES | No | [7 empty] | KENTON | 6-454 | CS 1560 |  | 0 | 0.612 | RELIABILITY | RESURFACING(P) | ADELA AVENUE. CURB-LINE MILLING, ASPHALT RESURFACING, REPLACE SIDEWALK/CURBING AND NEW SIDEWALK AS NEEDED FROM KY 1072 (SLEEPY HOLLOW ROAD/DEVERILL STREET) TO KY 8 (ELM STREET). | C |  | SNK | 2019 | 200000 | 160000 |  |  |  | 40000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.128 | 2019-09-13 | TIP FY 20-23, ADMIN MOD#2; UPDATE FISCAL YEAR & FUND AMOUNT; MOD | STPM | 3002335 | KENTON | 6-454 | CS 1560 |  | 0 | 0.612 | RELIABILITY | RESURFACING(P) | ADELA AVENUE. CURB-LINE MILLING, ASPHALT RESURFACING, REPLACE SIDEWALK/CURBING AND NEW SIDEWALK AS NEEDED FROM KY 1072 (SLEEPY HOLLOW ROAD/DEVERILL STREET) TO KY 8 (ELM STREET). | C |  | SNK | 2020 | 250000 | 200000 |  |  |  | 50000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.166 | 2020-02-20 | TIP FY 20-23, ADMIN MOD#6; ROW FUNDS NOT NEEDED-MOVE FUNDS TO C PHASE; MOD | STPM | 3002335 | KENTON | 6-454 | CS 1560 |  | 0 | 0.612 | RELIABILITY | RESURFACING(P) | ADELA AVENUE. CURB-LINE MILLING, ASPHALT RESURFACING, REPLACE SIDEWALK/CURBING AND NEW SIDEWALK AS NEEDED FROM KY 1072 (SLEEPY HOLLOW ROAD/DEVERILL STREET) TO KY 8 (ELM STREET). | C |  | SNK | 2020 | 261781 | 209425 |  |  |  | 52356 |  |  |  |  | 0
STIP | YES | No | [7 empty] | KENTON | 6-455 | CS 1045 |  | 1.3 | 2.33 | RELIABILITY | DRAINAGE IMPROVE(P) | CODY ROAD. REPLACE CULVERT FOR BANKLICK CREEK. MILL AND OVERLAY WITH NEW ASPHALT FROM BANKLICK CREEK TO INDEPENDENCE STATION ROAD. | D |  | SNK | 2019 | 57000 | 45600 |  |  |  | 11400 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.149 | 2019-11-15 | TIP FY 20-23; ADMIN MOD#4; SPLIT ITEM NO. 6-455 INTO 2 PROJECTS (6-455.00 & 6-455.10) AND UPDATE FUND AMOUNTS; MOD |  | 3002343 | KENTON | 6-455 | CS 1045 |  | 1.3 | 2.33 | RELIABILITY | DRAINAGE IMPROVE(P) | CODY ROAD. REPLACE CULVERT FOR BANKLICK CREEK. MILL AND OVERLAY WITH NEW ASPHALT FROM BANKLICK CREEK TO INDEPENDENCE STATION ROAD. | D |  | SNK | 2019 | 24150 | 19320 |  |  |  | 4830 |  | OBLIGATED | 23320 |  | 23320 | 2020 | 1ST QUARTER | CITY OF INDEPENDENCE
STIP | YES | No | [7 empty] | KENTON | 6-455 | CS 1045 |  | 1.3 | 2.33 | RELIABILITY | DRAINAGE IMPROVE(P) | CODY ROAD. REPLACE CULVERT FOR BANKLICK CREEK. MILL AND OVERLAY WITH NEW ASPHALT FROM BANKLICK CREEK TO INDEPENDENCE STATION ROAD. | U |  | SNK | 2019 | 120000 | 96000 |  |  |  | 24000 |  |  |  |  | 0
STIP | YES | No | [7 empty] | KENTON | 6-455 | CS 1045 |  | 1.3 | 2.33 | RELIABILITY | DRAINAGE IMPROVE(P) | CODY ROAD. REPLACE CULVERT FOR BANKLICK CREEK. MILL AND OVERLAY WITH NEW ASPHALT FROM BANKLICK CREEK TO INDEPENDENCE STATION ROAD. | C |  | SNK | 2019 | 346000 | 276800 |  |  |  | 69200 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.149 | 2019-11-15 | TIP FY 20-23; ADMIN MOD#4; SPLIT ITEM NO. 6-455 INTO 2 PROJECTS (6-455.00 & 6-455.10) AND UPDATE FUND AMOUNTS & FISCAL YEAR FROM 2019 TO 2020; MOD |  |  | KENTON | 6-455 | CS 1045 |  | 1.3 | 2.33 | RELIABILITY | DRAINAGE IMPROVE(P) | CODY ROAD. REPLACE CULVERT FOR BANKLICK CREEK. MILL AND OVERLAY WITH NEW ASPHALT FROM BANKLICK CREEK TO INDEPENDENCE STATION ROAD. | C |  | SNK | 2020 | 400000 | 320000 |  |  |  | 80000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.149 | 2019-11-15 | TIP FY 20-23; ADMIN MOD#4; SPLIT ITEM NO. 6-455 INTO 2 PROJECTS (6-455.00 & 6-455.10) AND UPDATE FUND AMOUNTS; NEW |  | 3002344 | KENTON | 6-455.1 | CS 1045 |  | 1.3 | 2.33 | RELIABILITY | DRAINAGE IMPROVE(P) | CODY ROAD. REPLACE CULVERT FOR BANKLICK CREEK. MILL AND OVERLAY WITH NEW ASPHALT FROM BANKLICK CREEK TO INDEPENDENCE STATION ROAD. | D |  | SNK | 2020 | 46000 | 36800 |  |  |  | 9200 |  | OBLIGATED | 40800 |  | 40800 | 2020 | 1ST QUARTER | CITY OF INDEPENDENCE
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.149 | 2019-11-15 | TIP FY 20-23; ADMIN MOD#4; SPLIT ITEM NO. 6-455 INTO 2 PROJECTS (6-455.00 & 6-455.10) AND UPDATE FUND AMOUNTS; NEW |  |  | KENTON | 6-455.1 | CS 1045 |  | 1.3 | 2.33 | RELIABILITY | DRAINAGE IMPROVE(P) | CODY ROAD. REPLACE CULVERT FOR BANKLICK CREEK. MILL AND OVERLAY WITH NEW ASPHALT FROM BANKLICK CREEK TO INDEPENDENCE STATION ROAD. | C |  | SNK | 2021 | 183580 | 146880 |  |  |  | 36700 |  |  |  |  | 0
STIP | YES | No | [5 empty] | STPM | 3002339 | KENTON | 6-456 | CS 2103 |  | 0.841 | 1.074 | RELIABILITY | TRANSP ENHANCEMENT(P) | MADISON AVENUE. UNDERGROUND UTILITIES, STREET TREES, MAST ARM POLES, STREETLIGHTS, RESURFACING, SIGNAL IMPROVEMENTS FROM 11TH STREET TO 8TH STREET.(18CCN) | D |  | SNK | 2019 | 280000 | 224000 |  |  |  | 56000 |  | OBLIGATED |  | 315000 | 315000 | 2019 | 4TH QUARTER | CITY OF COVINGTON
STIP | YES | No | [7 empty] | KENTON | 6-456 | CS 2103 |  | 0.841 | 1.074 | RELIABILITY | TRANSP ENHANCEMENT(P) | MADISON AVENUE. UNDERGROUND UTILITIES, STREET TREES, MAST ARM POLES, STREETLIGHTS, RESURFACING, SIGNAL IMPROVEMENTS FROM 11TH STREET TO 8TH STREET.(18CCN) | U |  | SNK | 2019 | 240000 | 192000 |  |  |  | 48000 |  |  |  |  | 0
STIP | YES | No | [7 empty] | KENTON | 6-456 | CS 2103 |  | 0.841 | 1.074 | RELIABILITY | TRANSP ENHANCEMENT(P) | MADISON AVENUE. UNDERGROUND UTILITIES, STREET TREES, MAST ARM POLES, STREETLIGHTS, RESURFACING, SIGNAL IMPROVEMENTS FROM 11TH STREET TO 8TH STREET.(18CCN) | C |  | SNK | 2019 | 1650000 | 1320000 |  |  |  | 330000 |  |  |  |  | 0
STIP | YES | No | [5 empty] | STPM | 3002340 | KENTON | 6-457 | CS 2217 |  | 0.033 | 0.12 | RELIABILITY | TRANSP ENHANCEMENT(P) | 7TH STREET. SIDEWALK REPLACEMENT, UNDERGROUND UTILITIES, STREET TREES, MAST ARM TRAFFIC SIGNALS, LIGHTING, RESURFACING FROM WASHINGTON STREET TO GREENUP STREET. | D |  | SNK | 2019 | 280000 | 224000 |  |  |  | 56000 |  | OBLIGATED |  | 315000 | 315000 | 2019 | 4TH QUARTER | CITY OF COVINGTON
STIP | YES | No | [7 empty] | KENTON | 6-457 | CS 2217 |  | 0.033 | 0.12 | RELIABILITY | TRANSP ENHANCEMENT(P) | 7TH STREET. SIDEWALK REPLACEMENT, UNDERGROUND UTILITIES, STREET TREES, MAST ARM TRAFFIC SIGNALS, LIGHTING, RESURFACING FROM WASHINGTON STREET TO GREENUP STREET. | U |  | SNK | 2019 | 240000 | 192000 |  |  |  | 48000 |  |  |  |  | 0
STIP | YES | No | [7 empty] | KENTON | 6-457 | CS 2217 |  | 0.033 | 0.12 | RELIABILITY | TRANSP ENHANCEMENT(P) | 7TH STREET. SIDEWALK REPLACEMENT, UNDERGROUND UTILITIES, STREET TREES, MAST ARM TRAFFIC SIGNALS, LIGHTING, RESURFACING FROM WASHINGTON STREET TO GREENUP STREET. | C |  | SNK | 2019 | 2450000 | 1960000 |  |  |  | 490000 |  |  |  |  | 0
|  |  |  | AMENDMENT | 2018.003 | 2019-07-26 | TIP FY 20-23; ADD PROJECT TO STIP; NEW |  |  | KENTON | 6-461 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | WEST COVINGTON RIVERFRONT COMMONS SHARED USE PATH (2018BOP) | D |  | SNK | 2020 | 128700 | 95560 |  |  | 10000 | 23140 |  |  |  |  | 0
|  |  |  | AMENDMENT | 2018.003 | 2019-07-26 | TIP FY 20-23; ADD PROJECT TO STIP; NEW |  |  | KENTON | 6-461 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | WEST COVINGTON RIVERFRONT COMMONS SHARED USE PATH (2018BOP) | R |  | SNK | 2021 | 10000 | 8000 |  |  |  | 2000 |  |  |  |  | 0
|  |  |  | AMENDMENT | 2018.003 | 2019-07-26 | TIP FY 20-23; ADD PROJECT TO STIP; NEW |  |  | KENTON | 6-461 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | WEST COVINGTON RIVERFRONT COMMONS SHARED USE PATH (2018BOP) | C |  | SNK | 2022 | 751213 | 600970 |  |  |  | 150243 |  |  |  |  | 0
|  |  |  | AMENDMENT | 2018.003 | 2019-07-26 | TIP FY 20-23; ADD PROJECT TO STIP; NEW |  |  | KENTON | 6-463 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | TAYLOR MILL SIDEWALK PROJECT PHASE III (2018BOP) | D |  | SNK | 2021 | 234570 | 173456 |  |  | 19000 | 42114 |  |  |  |  | 0
|  |  |  | AMENDMENT | 2018.003 | 2019-07-26 | TIP FY 20-23; ADD PROJECT TO STIP; NEW |  |  | KENTON | 6-463 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | TAYLOR MILL SIDEWALK PROJECT PHASE III (2018BOP) | R |  | SNK | 2022 | 41000 | 32800 |  |  |  | 8200 |  |  |  |  | 0
|  |  |  | AMENDMENT | 2018.003 | 2019-07-26 | TIP FY 20-23; ADD PROJECT TO STIP; NEW |  |  | KENTON | 6-463 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | TAYLOR MILL SIDEWALK PROJECT PHASE III (2018BOP) | C |  | SNK | 2023 | 776460 | 621168 |  |  |  | 155292 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.286 | 2021-03-12 | TIP FY 21-24; ADMIN MOD#8; ADD PROJECT TO STIP; NEW |  |  | KENTON | 6-900 | KY 1501 |  | 0.3 | 1 | RELIABILITY | SAFETY-HAZARD ELIM(P) | Installation of a Microsurface Treatment on KY 1501 from MP 0.3 to MP 1.0 in Kenton County, KY. | C |  | SAF | 2021 | 50000 | 45000 |  |  | 5000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.174 | 2020-03-17 | TIP FY 20-23; ADD PROJECT TO STIP; NEW |  |  | KENTON | 6-941 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALLATION OF HIGH FRICTION SURFACE TREATMENT ON KY 536 FROM MP 8.000 TO MP 8.300 IN KENTON COUNTY, KY. (2018BOP) | C |  | SAF | 2020 | 50000 | 45000 |  |  | 5000 | [5 empty] | 0
STIP |  | No | [7 empty] | KENTON | 6-1070 | CS 2097 | 0.079 | 0.144 | 0.223 | ASSET MANAGEMENT | AM-BRIDGE (P) | WEST 15TH STREET; ADDRESS DEFICIENCIES OF BRIDGE AND APPROACHES OVER CSX RR IN COVINGTON. (059C00029N)(12CCR)(SD) | R |  | BR/STP | 2019 | 830000 | 514600 |  |  | 315400 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.149 | 2019-11-15 | TIP FY 20-23; ADMIN MOD#4; UPDATE FISCAL YEAR FROM 2019 TO 2020; MOD |  |  | KENTON | 6-1070 | CS 2097 | 0.079 | 0.144 | 0.223 | ASSET MANAGEMENT | AM-BRIDGE (P) | WEST 15TH STREET; ADDRESS DEFICIENCIES OF BRIDGE AND APPROACHES OVER CSX RR IN COVINGTON. (059C00029N)(12CCR)(SD) | R |  | BR/STP | 2020 | 830000 | 514600 |  |  | 315400 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; UPDATE FISCAL YEAR & FUND AMOUNTS; MOD |  |  | KENTON | 6-1070 | CS 2097 | 0.079 | 0.144 | 0.223 | ASSET MANAGEMENT | AM-BRIDGE (P) | WEST 15TH STREET; ADDRESS DEFICIENCIES OF BRIDGE AND APPROACHES OVER CSX RR IN COVINGTON. (059C00029N)(12CCR)(SD) | R |  | BR/STP | 2021 | 100000 | 80000 |  |  | 20000 | [5 empty] | 0
STIP |  | No | [7 empty] | KENTON | 6-1070 | CS 2097 | 0.079 | 0.144 | 0.223 | ASSET MANAGEMENT | AM-BRIDGE (P) | WEST 15TH STREET; ADDRESS DEFICIENCIES OF BRIDGE AND APPROACHES OVER CSX RR IN COVINGTON. (059C00029N)(12CCR)(SD) | U |  | BR/STP | 2019 | 550000 | 341000 |  |  | 209000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.149 | 2019-11-15 | TIP FY 20-23; ADMIN MOD#4; UPDATE FISCAL YEAR FROM 2019 TO 2020; MOD |  |  | KENTON | 6-1070 | CS 2097 | 0.079 | 0.144 | 0.223 | ASSET MANAGEMENT | AM-BRIDGE (P) | WEST 15TH STREET; ADDRESS DEFICIENCIES OF BRIDGE AND APPROACHES OVER CSX RR IN COVINGTON. (059C00029N)(12CCR)(SD) | U |  | BR/STP | 2020 | 550000 | 341000 |  |  | 209000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; UPDATE FISCAL YEAR & FUND AMOUNTS; MOD |  |  | KENTON | 6-1070 | CS 2097 | 0.079 | 0.144 | 0.223 | ASSET MANAGEMENT | AM-BRIDGE (P) | WEST 15TH STREET; ADDRESS DEFICIENCIES OF BRIDGE AND APPROACHES OVER CSX RR IN COVINGTON. (059C00029N)(12CCR)(SD) | U |  | BR/STP | 2021 | 150000 | 120000 |  |  | 30000 | [5 empty] | 0
STIP |  | No | [7 empty] | KENTON | 6-1070 | CS 2097 | 0.079 | 0.144 | 0.223 | ASSET MANAGEMENT | AM-BRIDGE (P) | WEST 15TH STREET; ADDRESS DEFICIENCIES OF BRIDGE AND APPROACHES OVER CSX RR IN COVINGTON. (059C00029N)(12CCR)(SD) | C |  | BR/STP | 2019 | 2110000 | 1308200 |  |  | 801800 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.149 | 2019-11-15 | TIP FY 20-23; ADMIN MOD#4; UPDATE FISCAL YEAR FROM 2019 TO 2020; MOD |  |  | KENTON | 6-1070 | CS 2097 | 0.079 | 0.144 | 0.223 | ASSET MANAGEMENT | AM-BRIDGE (P) | WEST 15TH STREET; ADDRESS DEFICIENCIES OF BRIDGE AND APPROACHES OVER CSX RR IN COVINGTON. (059C00029N)(12CCR)(SD) | C |  | BR/STP | 2020 | 2110000 | 1308200 |  |  | 801800 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; UPDATE FISCAL YEAR & FUND AMOUNTS; MOD |  |  | KENTON | 6-1070 | CS 2097 | 0.079 | 0.144 | 0.223 | ASSET MANAGEMENT | AM-BRIDGE (P) | WEST 15TH STREET; ADDRESS DEFICIENCIES OF BRIDGE AND APPROACHES OVER CSX RR IN COVINGTON. (059C00029N)(12CCR)(SD) | C |  | BR/STP | 2021 | 2000000 | 1600000 |  |  | 400000 | [5 empty] | 0
STIP |  | No | [7 empty] | KENTON | 6-1075 | KY 1120 | 0.1 | 0.59 | 0.65 | ASSET MANAGEMENT | AM-BRIDGE (P) | EVALUATE BRIDGE ON KY-1120 (MP 0.621) OVER CSX RAILROAD; 11TH ST E OF RUSSELL ST; 059B00083N | C |  | BR/NH | 2019 | 520000 | 322400 |  |  | 197600 | [5 empty] | 0
STIP | YES | Yes | OKI MPO requires the federal funding splits before proceeding to incorporate this project into the OKI TIP. Program Management just confirmed BR/NH funds for this project will use only STP-State Funds per Ivan - TMH 2/15/19. | [6 empty] | KENTON | 6-1086 | KY 8 | 0.062 | 7.6 | 7.662 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER LICKING RIVER ON WEST 4TH STREET (KY 8) IN COVINGTON/NEWPORT AT KENTON/CAMPBELL CO LN. (059B00037N) *CAMPBELL CO MPS ARE 0.0-0.19 | D |  | BR/NH | 2021 | 3900000 | 2418000 |  |  | 1482000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; UPDATE FUND AMOUNTS; MOD |  |  | KENTON | 6-1086 | KY 8 | 0.062 | 7.6 | 7.662 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER LICKING RIVER ON WEST 4TH STREET (KY 8) IN COVINGTON/NEWPORT AT KENTON/CAMPBELL CO LN. (059B00037N) *CAMPBELL CO MPS ARE 0.0-0.19 | D |  | BR/NH | 2021 | 4390000 | 3512000 |  |  | 878000 | [5 empty] | 0
STIP | YES | Yes | OKI MPO requires the federal funding splits before proceeding to incorporate this project into the OKI TIP. Program Management just confirmed BR/NH funds for this project will use only STP-State Funds per Ivan - TMH 2/15/19. | [6 empty] | KENTON | 6-1086 | KY 8 | 0.062 | 7.6 | 7.662 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER LICKING RIVER ON WEST 4TH STREET (KY 8) IN COVINGTON/NEWPORT AT KENTON/CAMPBELL CO LN. (059B00037N) *CAMPBELL CO MPS ARE 0.0-0.19 | R |  | BR/NH | 2022 | 2440000 | 1512800 |  |  | 927200 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; UPDATE FISCAL YEAR & FUND AMOUNTS; MOD |  |  | KENTON | 6-1086 | KY 8 | 0.062 | 7.6 | 7.662 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER LICKING RIVER ON WEST 4TH STREET (KY 8) IN COVINGTON/NEWPORT AT KENTON/CAMPBELL CO LN. (059B00037N) *CAMPBELL CO MPS ARE 0.0-0.19 | R |  | BR/NH | 2023 | 2690000 | 2152000 |  |  | 538000 | [5 empty] | 0
STIP | YES | Yes | OKI MPO requires the federal funding splits before proceeding to incorporate this project into the OKI TIP. Program Management just confirmed BR/NH funds for this project will use only STP-State Funds per Ivan - TMH 2/15/19. | [6 empty] | KENTON | 6-1086 | KY 8 | 0.062 | 7.6 | 7.662 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER LICKING RIVER ON WEST 4TH STREET (KY 8) IN COVINGTON/NEWPORT AT KENTON/CAMPBELL CO LN. (059B00037N) *CAMPBELL CO MPS ARE 0.0-0.19 | U |  | BR/NH | 2022 | 1170000 | 725400 |  |  | 444600 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; UPDATE FISCAL YEAR & FUND AMOUNTS; MOD |  |  | KENTON | 6-1086 | KY 8 | 0.062 | 7.6 | 7.662 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER LICKING RIVER ON WEST 4TH STREET (KY 8) IN COVINGTON/NEWPORT AT KENTON/CAMPBELL CO LN. (059B00037N) *CAMPBELL CO MPS ARE 0.0-0.19 | U |  | BR/NH | 2024 | 1270000 | 1016000 |  |  | 254000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; ADD C PHASE TO STIP; NEW |  |  | KENTON | 6-1086 | KY 8 | 0.062 | 7.6 | 7.662 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER LICKING RIVER ON WEST 4TH STREET (KY 8) IN COVINGTON/NEWPORT AT KENTON/CAMPBELL CO LN. (059B00037N) *CAMPBELL CO MPS ARE 0.0-0.19 | C |  | BR/NH | FUTURE DATE | 37500000 | 30000000 |  |  | 7500000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; ADD C PHASE TO STIP; NEW |  |  | KENTON | 6-4306 | KY 17 |  | 5.73 | 5.79 | SAFETY | SAF-GUARDRAIL(P) | INSTALL GUARDRAIL ON KY-17 IN KENTON COUNTY | C |  | STBG | 2021 | 12000 | 9600 |  |  | 2400 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; ADD C PHASE TO STIP; NEW |  |  | KENTON | 6-4313 | KY 3716 |  | 2.25 | 2.3 | SAFETY | SAF-GUARDRAIL(P) | INSTALL GUARDRAIL ON KY-3716 IN KENTON COUNTY | C |  | STBG | 2024 | 11000 | 8800 |  |  | 2200 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; ADD C PHASE TO STIP; NEW |  |  | KENTON | 6-4319 | KY 177 |  | 15.97 | 15.99 | SAFETY | SAF-GUARDRAIL(P) | INSTALL GUARDRAIL ON KY-177 IN KENTON COUNTY | C |  | STBG | 2021 | 5000 | 4000 |  |  | 1000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.245 | 2020-10-09 | TIP FY 21-24, ADMIN MOD#4; ADD PROJECT TO STIP; NEW |  |  | KENTON | 6-4904 | KY 1120 |  | 1 | 1.1 | ASSET MANAGEMENT | AM-BRIDGE (P) | KY 1120 GIRL SCOUT BRIDGE | D |  | NH | 2021 | 50000 | 40000 |  |  | 10000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.245 | 2020-10-09 | TIP FY 21-24, ADMIN MOD#4; ADD PROJECT TO STIP; NEW |  |  | KENTON | 6-4904 | KY 1120 |  | 1 | 1.1 | ASSET MANAGEMENT | AM-BRIDGE (P) | KY 1120 GIRL SCOUT BRIDGE | C |  | NH | 2022 | 179204 | 143363 |  |  | 35841 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.272 | 2021-01-14 | TIP FY 21-24, ADMIN MOD#6; ADD PROJECT TO STIP; NEW |  |  | KENTON | 6-8307.1 | KY 1501 |  | 0 | 1.032 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE HANDS PIKE (KY-1501) FROM KY-17 TO CRYSTAL LAKE DRIVE.(12CCR)(14CCR)(16CCR) | C |  | STP | 2021 | 6408000 | 6408000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.253 | 2020-10-26 | TIP FY 21-24, AMEND#2; ADD D PHASE TO STIP; NEW |  |  | KENTON | 6-8951 | US 25 |  | 8.583 | 8.667 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE EXISTING ALIGNMENT WITH BUTTERMILK PIKE, ORPHANAGE ROAD, AND US 25. FT. MITCHELL WILL PAY $50,000 TOWARD DESIGN. (16CCN)(18CCN) (2020CCR) | D |  | STP | 2021 | 570000 | 456000 |  |  | 114000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.253 | 2020-10-26 | TIP FY 21-24, AMEND#2; ADD R PHASE TO STIP; NEW |  |  | KENTON | 6-8951 | US 25 |  | 8.583 | 8.667 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE EXISTING ALIGNMENT WITH BUTTERMILK PIKE, ORPHANAGE ROAD, AND US 25. FT. MITCHELL WILL PAY $50,000 TOWARD DESIGN. (16CCN)(18CCN) (2020CCR) | R |  | STP | 2022 | 5000000 | 4000000 |  |  | 1000000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.253 | 2020-10-26 | TIP FY 21-24, AMEND#2; ADD U PHASE TO STIP; NEW |  |  | KENTON | 6-8951 | US 25 |  | 8.583 | 8.667 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE EXISTING ALIGNMENT WITH BUTTERMILK PIKE, ORPHANAGE ROAD, AND US 25. FT. MITCHELL WILL PAY $50,000 TOWARD DESIGN. (16CCN)(18CCN) (2020CCR) | U |  | STP | 2024 | 2340000 | 1872000 |  |  | 468000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.253 | 2020-10-26 | TIP FY 21-24, AMEND#2; ADD C PHASE TO STIP; NEW |  |  | KENTON | 6-8951 | US 25 |  | 8.583 | 8.667 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE EXISTING ALIGNMENT WITH BUTTERMILK PIKE, ORPHANAGE ROAD, AND US 25. FT. MITCHELL WILL PAY $50,000 TOWARD DESIGN. (16CCN)(18CCN) (2020CCR) | C |  | STP | FUTURE DATE | 6250000 | 5000000 |  |  | 1250000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.006 | 2018-12-18 | TIP FY 18-21; AMENDMENT#12; ADDING PROJECT TO STIP; NEW |  |  | KENTON | 6-9014.01 | KY 17 |  | 4.3 | 8.1 | SAFETY | SAFETY-HAZARD ELIM(P) | SLOPE LAYBACK TO IMPROVE SIGHT DISTANCE ALONG KY 17, REALIGNMENT OF THE INTERSECTION OF KY 17 & KY 2042, AND UPDATED SIGNING. (2016BOP) | D |  | SAF | 2018 | 275000 | 275000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.006 | 2018-12-18 | TIP FY 18-21; AMENDMENT#12; ADDING PROJECT TO STIP; NEW | HSIP | 5217017 | KENTON | 6-9014.01 | KY 17 |  | 4.3 | 8.1 | SAFETY | SAFETY-HAZARD ELIM(P) | SLOPE LAYBACK TO IMPROVE SIGHT DISTANCE ALONG KY 17, REALIGNMENT OF THE INTERSECTION OF KY 17 & KY 2042, AND UPDATED SIGNING. (2016BOP) | R |  | SAF | 2019 | 140000 | 140000 |  |  | 0 |  |  | OBLIGATED | 140000 |  | 140000 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.006 | 2018-12-18 | TIP FY 18-21; AMENDMENT#12; ADDING PROJECT TO STIP; NEW | HSIP | 5217017 | KENTON | 6-9014.01 | KY 17 |  | 4.3 | 8.1 | SAFETY | SAFETY-HAZARD ELIM(P) | SLOPE LAYBACK TO IMPROVE SIGHT DISTANCE ALONG KY 17, REALIGNMENT OF THE INTERSECTION OF KY 17 & KY 2042, AND UPDATED SIGNING. (2016BOP) | U |  | SAF | 2019 | 45000 | 45000 |  |  | 0 |  |  | OBLIGATED | 45000 |  | 45000 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.006 | 2018-12-18 | TIP FY 18-21; AMENDMENT#12; ADDING PROJECT TO STIP; NEW |  |  | KENTON | 6-9014.01 | KY 17 |  | 4.3 | 8.1 | SAFETY | SAFETY-HAZARD ELIM(P) | SLOPE LAYBACK TO IMPROVE SIGHT DISTANCE ALONG KY 17, REALIGNMENT OF THE INTERSECTION OF KY 17 & KY 2042, AND UPDATED SIGNING. (2016BOP) | C |  | SAF | 2020 | 750000 | 750000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.149 | 2019-11-15 | TIP FY 20-23; ADMIN MOD#4; ADD R PHASE TO STIP; NEW | HSIP | 8202005 | KENTON | 6-9016 | KY 1829 |  | 1.2 | 2.25 | SAFETY | SAFETY-HAZARD ELIM(P) | CORRECT DROP OFFS, IMPROVE DITCHING, REMOVE TREES IN CLEAR ZONE AND INSTALL HFS FROM MP 1.2 TO MP 2.25 ON KY 1829 IN KENTON COUNTY. (2016BOP) | R |  | SAF | 2020 | 10000 | 10000 |  |  | 0 |  |  | OBLIGATED | 10000 |  | 10000 | 2020 | 1ST QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.149 | 2019-11-15 | TIP FY 20-23; ADMIN MOD#4; ADD U PHASE TO STIP; NEW | HSIP | 8202005 | KENTON | 6-9016 | KY 1829 |  | 1.2 | 2.25 | SAFETY | SAFETY-HAZARD ELIM(P) | CORRECT DROP OFFS, IMPROVE DITCHING, REMOVE TREES IN CLEAR ZONE AND INSTALL HFS FROM MP 1.2 TO MP 2.25 ON KY 1829 IN KENTON COUNTY. (2016BOP) | U |  | SAF | 2020 | 30000 | 30000 |  |  | 0 |  |  | OBLIGATED | 30000 |  | 30000 | 2020 | 1ST QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.149 | 2019-11-15 | TIP FY 20-23; ADMIN MOD#4; ADD C PHASE TO STIP; NEW |  |  | KENTON | 6-9016 | KY 1829 |  | 1.2 | 2.25 | SAFETY | SAFETY-HAZARD ELIM(P) | CORRECT DROP OFFS, IMPROVE DITCHING, REMOVE TREES IN CLEAR ZONE AND INSTALL HFS FROM MP 1.2 TO MP 2.25 ON KY 1829 IN KENTON COUNTY. (2016BOP) | C |  | SAF | 2020 | 380000 | 380000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; UPDATE FISCAL YEAR; MOD |  |  | KENTON | 6-9016 | KY 1829 |  | 1.2 | 2.25 | SAFETY | SAFETY-HAZARD ELIM(P) | CORRECT DROP OFFS, IMPROVE DITCHING, REMOVE TREES IN CLEAR ZONE AND INSTALL HFS FROM MP 1.2 TO MP 2.25 ON KY 1829 IN KENTON COUNTY. (2016BOP) | C |  | SAF | 2021 | 380000 | 380000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.069 | 2019-05-13 | TIP FY 18-21; ADMIN MOD#18; ADD PROJECT TO STIP; NEW | HSIP | 8122029 | KENTON | 6-9017.2 | KY 1303 |  | 4.737 | 4.937 | SAFETY | SAFETY-HAZARD ELIM(P) | UPDATE THE TRAFFIC SIGNAL TO INCLUDE REFLECTIVE BACKPLATES, DOUBLE RED SIGNAL HEADS, AND SUPPLEMENTAL SIGNAL HEADS, AND UPDATE THE STRIPING AT THE INTERSECTION OF KY 1303 & DUDLEY RD (2018BOP) | C |  | SAF | 2019 | 50000 | 50000 |  |  | 0 |  |  | OBLIGATED |  | 30000 | 30000 | 2019 | 3RD QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.069 | 2019-05-13 | TIP FY 18-21; ADMIN MOD#18; ADD PROJECT TO STIP; NEW | HSIP | 8122030 | KENTON | 6-9017.4 | KY 1303 |  | 3.8 | 4.05 | SAFETY | SAFETY-HAZARD ELIM(P) | UPDATE THE TRAFFIC SIGNAL TO INCLUDE REFLECTIVE BACKPLATES AND DOUBLE RED SIGNAL HEADS, AND UPDATE THE STRIPING AT THE INTERSECTION OF KY 1303 & KY 236 (2018BOP) | C |  | SAF | 2019 | 50000 | 50000 |  |  | 0 |  |  | OBLIGATED |  | 29000 | 29000 | 2019 | 3RD QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.069 | 2019-05-13 | TIP FY 18-21; ADMIN MOD#18; ADD PROJECT TO STIP; NEW | HSIP | 5220001 | KENTON | 6-9018 | KY 177 |  | 6.15 | 11.823 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 177 FROM MP 6.150 TO MP 11.823 IN KENTON COUNTY. (2016BOP) | C |  | SAF | 2019 | 982000 | 982000 |  |  | 0 |  |  | OBLIGATED | 1257000 |  | 1257000 | 2019 | 3RD QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.286 | 2021-03-12 | TIP FY 21-24; ADMIN MOD#8; ADD PROJECT TO STIP; NEW |  |  | KENTON | 6-9018.01 | KY 177 |  | 9.05 | 9.3 | SAFETY | SAFETY-HAZARD ELIM(P) | IMPROVEMENTS AT THE INTERSECTION OF KY 177 AND KY 536. (2018BOP) | R |  | SAF | 2021 | 10000 | 8000 |  |  | 2000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.286 | 2021-03-12 | TIP FY 21-24; ADMIN MOD#8; ADD PROJECT TO STIP; NEW |  |  | KENTON | 6-9018.01 | KY 177 |  | 9.05 | 9.3 | SAFETY | SAFETY-HAZARD ELIM(P) | IMPROVEMENTS AT THE INTERSECTION OF KY 177 AND KY 536. (2018BOP) | C |  | SAF | 2022 | 200000 | 160000 |  |  | 40000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.084 | 2019-06-19 | TIP FY 18-21; ADMIN MOD#19; ADD U PHASE TO STIP; NEW |  |  | KENTON | 6-9020 | KY 1486 |  | 2.8 | 3.2 | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALL HIGH FRICTION SURFACE AND UPDATE SIGNAGE. (2018BOP) | U |  | SAF | 2019 | 11111 | 10000 |  |  | 1111 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.084 | 2019-06-19 | TIP FY 18-21; ADMIN MOD#19; ADD C PHASE TO STIP; NEW |  |  | KENTON | 6-9020 | KY 1486 |  | 2.8 | 3.2 | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALL HIGH FRICTION SURFACE AND UPDATE SIGNAGE. (2018BOP) | C |  | SAF | 2019 | 158123 | 158123 | [8 empty] | 0
STIP |  | No | [7 empty] | KENTON | 6-10005 | KY 17 |  | 23.949 | 24.321 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES ON JOHN A. ROEBLING BRIDGE OVER OHIO RIVER. (059B00048N)(BSBP) | C |  | BR/NH | 2019 | 1200000 | 744000 |  |  | 456000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.215 | 2020-08-05 | TIP FY 21-24, ADMIN MOD#2; UPDATE FISCAL YEAR AND FUND AMOUNT; MOD |  |  | KENTON | 6-10005 | KY 17 |  | 23.949 | 24.321 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES ON JOHN A. ROEBLING BRIDGE OVER OHIO RIVER. (059B00048N)(BSBP) | C |  | BR/NH | 2021 | 11250000 | 9000000 |  |  | 2250000 | [5 empty] | 0
STIP |  | No | [7 empty] | KENTON | 6-10006 | US 25 |  | 13.587 | 13.976 | ASSET MANAGEMENT | AM-BRIDGE (P) | JOINT REPLACEMENT AND PREVENTIVE MAINTENANCE ON CLAY WADE BAILEY BRIDGE OVER THE OHIO RIVER. JOINT PROJECT WITH OHIO. (059B00049N) | C |  | BR/STP | 2019 | 350000 | 217000 |  |  | 133000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; UPDATE FISCAL YEAR & FUND AMOUNT; MOD |  |  | KENTON | 6-10006 | US 25 |  | 13.587 | 13.976 | ASSET MANAGEMENT | AM-BRIDGE (P) | JOINT REPLACEMENT AND PREVENTIVE MAINTENANCE ON CLAY WADE BAILEY BRIDGE OVER THE OHIO RIVER. JOINT PROJECT WITH OHIO. (059B00049N) | C |  | BR/STP | 2021 | 1000000 | 800000 |  |  | 200000 | [5 empty] | 0
STIP |  | No | [7 empty] | KENTON | 6-10011 | KY 177 |  | 7.319 | 7.349 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 177 BRIDGE OVER BOWMAN CREEK. (059B00011N) | D |  | BR/STP | 2019 | 420000 | 260400 |  |  | 159600 | [5 empty] | 0
STIP |  | No | [5 empty] | STPBRO | 5220002 | KENTON | 6-10011 | KY 177 |  | 7.319 | 7.349 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 177 BRIDGE OVER BOWMAN CREEK. (059B00011N) | C |  | BR/STP | 2020 | 2695000 | 1670900 |  |  | 1024100 |  |  | OBLIGATED | 309460 |  | 309460 | 2019 | 2ND QUARTER
STIP |  | No | [7 empty] | KENTON | 6-10012 | KY 2045 |  | 0.397 | 0.403 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 2045 BRIDGE OVER BRUSHY CREEK. (059B00025N) | D |  | BR/STP | 2019 | 350000 | 217000 |  |  | 133000 | [5 empty] | 0
STIP |  | No | [5 empty] | STPBRZ |  | KENTON | 6-10012 | KY 2045 |  | 0.397 | 0.403 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 2045 BRIDGE OVER BRUSHY CREEK. (059B00025N) | C |  | BR/STP | 2020 | 3605000 | 2235100 |  |  | 1369900 |  |  | OBLIGATED |  | 790855 | 790855 | 2019 | 3RD QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.272 | 2021-01-14 | TIP FY 21-24, ADMIN MOD#6; ADD PROJECT TO STIP; NEW NOTE: FEDERAL EMERGENCY RELIEF PROJECT |  |  | KENTON | 6-10025 | I 75 |  | 191.4 | 191.64 | ASSET MANAGEMENT | AM-BRIDGE (P) | EMERGENCY REPAIRS TO THE I-75/I-71 BRENT SPENCE BRIDGE OVER THE OHIO RIVER BETWEEN COVINGTON, KENTUCKY AND CINCINNATI, OHIO. | D |  | ER | 2021 | 3000000 | 3000000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.272 | 2021-01-14 | TIP FY 21-24, ADMIN MOD#6; ADD PROJECT TO STIP; NEW NOTE: FEDERAL EMERGENCY RELIEF PROJECT |  |  | KENTON | 6-10025 | I 75 |  | 191.4 | 191.64 | ASSET MANAGEMENT | AM-BRIDGE (P) | EMERGENCY REPAIRS TO THE I-75/I-71 BRENT SPENCE BRIDGE OVER THE OHIO RIVER BETWEEN COVINGTON, KENTUCKY AND CINCINNATI, OHIO. | C |  | ER | 2021 | 27000000 | 27000000 |  |  | 0 | [5 empty] | 0
[10 empty] | KENTON | 6-10025 | I 75 |  | 191.4 | 191.64 | ASSET MANAGEMENT | AM-BRIDGE (P) | EMERGENCY REPAIRS TO THE I-75/I-71 BRENT SPENCE BRIDGE OVER THE OHIO RIVER BETWEEN COVINGTON, KENTUCKY AND CINCINNATI, OHIO. | C |  | NH | 2021 | 456080 | 364864 |  |  | 91216 | [5 empty] | 0
STIP | YES | No | [7 empty] | KENTON | 6-20030 | I 75 |  | 166.263 | 169.439 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-075 CARDINAL DIRECTION(S) FROM MILEPOINT 166.263 TO MILEPOINT 169.439 | D |  | PM/NH | 2021 | 390000 | 312000 |  |  | 78000 | [5 empty] | 0
STIP | YES | No | [7 empty] | KENTON | 6-20030 | I 75 |  | 166.263 | 169.439 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-075 CARDINAL DIRECTION(S) FROM MILEPOINT 166.263 TO MILEPOINT 169.439 | C |  | PM/NH | 2021 | 3900000 | 3120000 |  |  | 780000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; ADD PROJECT TO STIP; NEW |  |  | KENTON | 6-20031 | I 75 |  | 166.263 | 169.439 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-075 NON-CARDINAL DIRECTION(S) FROM MILEPOINT 166.263 TO MILEPOINT 169.439 | D |  | PM/NH | 2022 | 390000 | 312000 |  |  | 78000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; ADD PROJECT TO STIP; NEW |  |  | KENTON | 6-20031 | I 75 |  | 166.263 | 169.439 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-075 NON-CARDINAL DIRECTION(S) FROM MILEPOINT 166.263 TO MILEPOINT 169.439 | C |  | PM/NH | 2023 | 1900000 | 1520000 |  |  | 380000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; ADD PROJECT TO STIP; NEW |  |  | KENTON | 6-20031 | I 75 |  | 166.263 | 169.439 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-075 NON-CARDINAL DIRECTION(S) FROM MILEPOINT 166.263 TO MILEPOINT 169.439 | C |  | PM/NH | 2024 | 2000000 | 1600000 |  |  | 400000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.118 | 2019-08-19 | ADD PROJECT TO STIP; NEW. TIP FY 20-23, CHAPTER 7 - GROUPED PROJECTS, PAGE 7-5. | NHPPIM | 0758105 | KENTON | 6-20032 | I 75 |  | 186.95 | 190.7 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT ON I-075 BOTH DIRECTION(S) FROM MILEPOINT 186.95 TO MILEPOINT 190.721 | C |  | PM/NH | 2019 | 4000000 | 4000000 |  |  | 0 |  |  | OBLIGATED | 4180550 |  | 4180550 | 2019 | 4TH QUARTER
STIP |  | No | [7 empty] | KENTON | 6-20033 | I 75 |  | 190.7 | 191.22 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-075 NON-CARDINAL DIRECTION(S) FROM MILEPOINT 190.68 TO MILEPOINT 191.22 | D |  | PM/NH | 2019 | 30000 | 24000 |  |  | 6000 | [5 empty] | 0
STIP |  | No | [7 empty] | KENTON | 6-20034 | I 75 |  | 190.721 | 191.777 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-075 CARDINAL DIRECTION(S) FROM MILEPOINT 190.721 TO MILEPOINT 191.777 | D |  | PM/NH | 2022 | 100000 | 80000 |  |  | 20000 | [5 empty] | 0
STIP |  | No | [7 empty] | KENTON | 6-20034 | I 75 |  | 190.721 | 191.777 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-075 CARDINAL DIRECTION(S) FROM MILEPOINT 190.721 TO MILEPOINT 191.777 | C |  | PM/NH | 2022 | 1000000 | 800000 |  |  | 200000 | [5 empty] | 0
STIP | Yes | No | [7 empty] | KENTON | 6-20035 | I 275 |  | 0 | 1.582 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION ON PCC PAVEMENT ON I-275 BOTH DIRECTION(S) FROM MILEPOINT 0 TO MILEPOINT 1.582 (1.05 NON-CARDINAL) | D |  | PM/NH | 2019 | 1420000 | 1136000 |  |  | 284000 | [5 empty] | 0
STIP | Yes | No | [5 empty] | NHPP | 2759136 | KENTON | 6-20035 | I 275 |  | 0 | 1.582 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION ON PCC PAVEMENT ON I-275 BOTH DIRECTION(S) FROM MILEPOINT 0 TO MILEPOINT 1.582 (1.05 NON-CARDINAL) | C |  | PM/NH | 2019 | 14200000 | 11360000 |  |  | 2840000 |  |  | OBLIGATED |  | 28764000 | 28764000 | 2019 | 3RD QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.047 | 2019-04-11 | TIP FY18-21, AMENDMENT#16; UPDATE FUND AMOUNTS; MOD | NHPP | 2759136 | KENTON | 6-20035 | I 275 |  | 0 | 1.582 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION ON PCC PAVEMENT ON I-275 BOTH DIRECTION(S) FROM MILEPOINT 0 TO MILEPOINT 1.582 (1.05 NON-CARDINAL) | C |  | PM/NH | 2019 | 29000000 | 23200000 | 5800000 | 17400000 | 5800000 |  |  | OBLIGATED | 34471030 |  | 34471030 | 2019 | 3RD QUARTER
STIP | YES | No | [7 empty] | KENTON | 6-20036 | I 275 |  | 1.054 | 1.582 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT ON I-275 NON-CARDINAL DIRECTION(S) FROM MILEPOINT 1.054 TO MILEPOINT 1.582 | D |  | PM/NH | 2021 | 40000 | 32000 |  |  | 8000 | [5 empty] | 0
STIP | YES | No | [7 empty] | KENTON | 6-20036 | I 275 |  | 1.054 | 1.582 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT ON I-275 NON-CARDINAL DIRECTION(S) FROM MILEPOINT 1.054 TO MILEPOINT 1.582 | C |  | PM/NH | 2021 | 400000 | 320000 |  |  | 80000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 9/22/20 | TIP FY 21-24, ADMIN MOD#3; ADD PROJECT TO STIP; NEW |  |  | KENTON | 6-20037 | I 275 |  | 77.759 | 82.475 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT ON I-275 BOTH DIRECTION(S) FROM MILEPOINT 77.759 TO MILEPOINT 79.796 (2020CCR) | D |  | PM/NH | 2023 | 725000 | 580000 |  |  | 145000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 9/22/20 | TIP FY 21-24, ADMIN MOD#3; ADD PROJECT TO STIP; NEW |  |  | KENTON | 6-20037 | I 275 |  | 77.759 | 82.475 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT ON I-275 BOTH DIRECTION(S) FROM MILEPOINT 77.759 TO MILEPOINT 79.796 (2020CCR) | C |  | PM/NH | 2024 | 3250000 | 2600000 |  |  | 650000 | [5 empty] | 0
STIP | YES | No | [7 empty] | KENTON | 6-20039 | I 275 |  | 82.475 | 83.78 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION ON PCC PAVEMENT ON I-275 BOTH DIRECTION(S) FROM MILEPOINT 82.475 TO MILEPOINT 83.78 | D |  | PM/NH | 2019 | 200000 | 160000 |  |  | 40000 | [5 empty] | 0
STIP | YES | No | [7 empty] | KENTON | 6-20039 | I 275 |  | 82.475 | 83.78 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION ON PCC PAVEMENT ON I-275 BOTH DIRECTION(S) FROM MILEPOINT 82.475 TO MILEPOINT 83.78 | C |  | PM/NH | 2019 | 2000000 | 1600000 |  |  | 400000 | [5 empty] | 0
STIP | YES | No | [7 empty] | KENTON | 6-20040 | KY 16 |  | 13.9 | 14.9 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | D |  | PM/NH | 2021 | 400000 | 320000 |  |  | 80000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; UPDATE FISCAL YEAR; MOD |  |  | KENTON | 6-20040 | KY 16 |  | 13.9 | 14.9 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | D |  | PM/NH | 2024 | 400000 | 320000 |  |  | 80000 | [5 empty] | 0
STIP | YES | No | [7 empty] | KENTON | 6-20040 | KY 16 |  | 13.9 | 14.9 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | C |  | PM/NH | 2021 | 4000000 | 3200000 |  |  | 800000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; UPDATE FISCAL YEAR; MOD |  |  | KENTON | 6-20040 | KY 16 |  | 13.9 | 14.9 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | C |  | PM/NH | FUTURE DATE | 4000000 | 3200000 |  |  | 800000 | [5 empty] | 0
STIP | YES | No | [7 empty] | KENTON | 6-20041 | KY 16 |  | 14.9 | 15.69 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | D |  | PM/NH | 2021 | 75000 | 60000 |  |  | 15000 | [5 empty] | 0
STIP | YES | No | [7 empty] | KENTON | 6-20041 | KY 16 |  | 14.9 | 15.69 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | C |  | PM/NH | 2021 | 750000 | 600000 |  |  | 150000 | [5 empty] | 0
STIP | YES | No | [7 empty] | KENTON | 6-20042 | KY 16 |  | 15.69 | 16.15 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT | D |  | PM/NH | 2021 | 50000 | 40000 |  |  | 10000 | [5 empty] | 0
STIP | YES | No | [7 empty] | KENTON | 6-20042 | KY 16 |  | 15.69 | 16.15 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT | C |  | PM/NH | 2021 | 500000 | 400000 |  |  | 100000 | [5 empty] | 0
STIP | YES | No | [7 empty] | KENTON | 6-20043 | KY 17 |  | 16.2 | 18.4 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT | D |  | PM/STP | 2021 | 880000 | 704000 |  |  | 176000 | [5 empty] | 0
STIP | YES | No | [7 empty] | KENTON | 6-20043 | KY 17 |  | 16.2 | 18.4 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT | C |  | PM/STP | 2021 | 8800000 | 7040000 |  |  | 1760000 | [5 empty] | 0
STIP | YES | No | [7 empty] | KENTON | 6-20044 | KY 236 |  | 2.131 | 2.622 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | D |  | PM/STP | 2021 | 30000 | 24000 |  |  | 6000 | [5 empty] | 0
STIP | YES | No | [7 empty] | KENTON | 6-20044 | KY 236 |  | 2.131 | 2.622 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | C |  | PM/STP | 2021 | 300000 | 240000 |  |  | 60000 | [5 empty] | 0
STIP | YES | No | [7 empty] | KENTON | 6-20045 | KY 1072 |  | 2.489 | 2.83 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | D |  | PM/STP | 2021 | 20000 | 16000 |  |  | 4000 | [5 empty] | 0
STIP | YES | No | [7 empty] | KENTON | 6-20045 | KY 1072 |  | 2.489 | 2.83 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | C |  | PM/STP | 2021 | 200000 | 160000 |  |  | 40000 | [5 empty] | 0
STIP | YES | No | [7 empty] | KENTON | 6-20046 | US 25 |  | 8.65 | 10.85 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT | D |  | PM/STP | 2021 | 325000 | 260000 |  |  | 65000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; UPDATE FISCAL YEAR & FUND AMOUNTS; MOD |  |  | KENTON | 6-20046 | US 25 |  | 8.65 | 10.85 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT | D |  | PM/STP | 2024 | 125000 | 100000 |  |  | 25000 | [5 empty] | 0
STIP | YES | No | [7 empty] | KENTON | 6-20046 | US 25 |  | 8.65 | 10.85 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT | C |  | PM/STP | 2021 | 3250000 | 2600000 |  |  | 650000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; UPDATE FISCAL YEAR & FUND AMOUNTS; MOD |  |  | KENTON | 6-20046 | US 25 |  | 8.65 | 10.85 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT | C |  | PM/STP | 2024 | 1250000 | 1000000 |  |  | 250000 | [5 empty] | 0
STIP | YES | Yes | OKI MPO requires the federal funding splits before proceeding to incorporate this project into the OKI TIP. Program Management just confirmed PM/STP federal funds for this project will use federal STP-State with an 80/20 -Fed/State split per Ivan - TMH 2/15/19. | [6 empty] | KENTON | 6-20051 | KY 177 | 6.82 | 9.17 | 15.99 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION ON KY-177 FROM MILEPOINT 9.17 TO MILEPOINT 15.99 | C |  | PM/STP | 2022 | 893000 | 714400 |  |  | 178600 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.237 | 2020-09-22 | TIP FY 21-24, ADMIN MOD#3; |  |  | KENTON | 6-20051 | KY 177 |  | 9.17 | 15.99 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION ON KY-177 FROM MILEPOINT 9.17 TO MILEPOINT 15.99 | C |  | PM/STP | 2022 | 893000 | 714400 |  |  | 178600 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 1203405 | KNOTT | 12-1116 | CR 1008 |  | 0 | 0.04 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON ROCKLICK BRANCH (CR 1008) OVER RIGHT FORK BEAVER CREEK AT JUNCTION WITH SOUTH HIGHWAY 7 (060C00006N). | C |  | BR/STP | 2019 | 420000 | 260400 |  |  | 159600 |  |  | OBLIGATED | 300000 | 1074262 | 1374262 | 2019 | 4TH QUARTER
STIP | [9 empty] | KNOTT | 12-1124 | CS 1016 | 0.012 | 0.018 | 0.03 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER RIGHT FORK TROUBLESOME CREEK ON FIELDWOOD DRIVE (CS1016) IN HINDMAN (060C00060N) | D |  | BR/STP | 2019 | 210000 | 130200 |  |  | 79800 | [5 empty] | 0
STIP | [9 empty] | KNOTT | 12-1124 | CS 1016 | 0.012 | 0.018 | 0.03 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER RIGHT FORK TROUBLESOME CREEK ON FIELDWOOD DRIVE (CS1016) IN HINDMAN (060C00060N) | C |  | BR/STP | 2020 | 455000 | 282100 |  |  | 172900 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 1203398 | KNOTT | 12-8904 | KY 3209 |  | 0.312 | 0.328 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER BALLS FORK ON KY 3209. (16CCN) 060B00053N | C |  | BR/STP | 2019 | 700000 | 434000 |  |  | 266000 |  |  | OBLIGATED | 140000 | 485600 | 625600 | 2020 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.152 | 2020-01-06 | ADD R PHASE TO STIP; NEW | STPBRZ | 1203398 | KNOTT | 12-8904 | KY 3209 |  | 0.312 | 0.328 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER BALLS FORK ON KY 3209. (16CCN) 060B00053N | R |  | BR/STP | 2020 | 31500 | 25200 | [5 empty] | OBLIGATED | 25200 |  | 25200 | 2020 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.3 | 2021-05-28 | ADD C PHASE TO STIP; PARENT NO. 12-9004.00; NEW |  |  | KNOTT | 12-9004.7 | KY 15 |  | 3.902 | 3.952 | SAFETY | SAFETY-HAZARD ELIM(P) | RECONFIGURE THE EXISTING BEACON FROM A DIAGONAL SPAN TO A BOX SPAN AND INSTALL NEW HEADS WITH REFLECTIVE BACKPLATES AT THE INTERSECTION OF KY 15 & KY 160. (2018BOP) | C |  | SAF | 2021 | 102000 | 102000 | [8 empty] | 0
STIP | [9 empty] | KNOTT | 12-10001 | KY 1098 |  | 0.032 | 0.044 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-1098 BRIDGE OVER LAUREL FK OF QUICKSAND C. (060B00035N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [9 empty] | KNOTT | 12-10001 | KY 1098 |  | 0.032 | 0.044 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-1098 BRIDGE OVER LAUREL FK OF QUICKSAND C. (060B00035N) | C |  | BR/STP | 2020 | 680000 | 421600 |  |  | 258400 | [5 empty] | 0
STIP | [9 empty] | KNOTT | 12-10002 | CR 1130 |  | 0.015 | 0.021 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF COLLINS BRANCH RD BRIDGE OVER CARR FORK. (060C00029N) | D |  | BR/STP | 2019 | 157500 | 97650 |  |  | 59850 | [5 empty] | 0
STIP | [9 empty] | KNOTT | 12-10002 | CR 1130 |  | 0.015 | 0.021 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF COLLINS BRANCH RD BRIDGE OVER CARR FORK. (060C00029N) | C |  | BR/STP | 2020 | 398650 | 247163 |  |  | 151487 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.075 | 2019-05-28 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030120 | KNOTT | 12-10002 | CR 1130 |  | 0.015 | 0.021 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF COLLINS BRANCH RD BRIDGE OVER CARR FORK. (060C00029N) | C |  | STP | 2020 | 485013 | 485013 |  |  | 0 |  |  | OBLIGATED |  | 651508.4 | 651508.4 | 2019 | 3RD QUARTER
STIP | [9 empty] | KNOTT | 12-10015 | CR 1565 |  | 0.028 | 0.034 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF FRANKIE JANE DR BRIDGE OVER CANEY CREEK. (060C00071N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [9 empty] | KNOTT | 12-10015 | CR 1565 |  | 0.028 | 0.034 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF FRANKIE JANE DR BRIDGE OVER CANEY CREEK. (060C00071N) | C |  | BR/STP | 2020 | 337890 | 209491.8 |  |  | 128398.2 | [5 empty] | 0
STIP | [7 empty] | NHPP | 0251046 | KNOX | 11-188 | US 25E | 1.976 | 24.221 | 26.197 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE SAFETY AND ACCESS MANAGEMENT, AND REDUCE CONGESTION ON US-25E FROM CORBIN BYPASS TO KNOX/LAUREL COUNTY LINE.(12CCR) | C |  | NH | 2020 | 2300000 | 2300000 |  |  | 0 |  |  | OBLIGATED | 184000 |  | 184000 | 2020 | 2ND QUARTER
STIP | [9 empty] | KNOX | 11-188.01 | US 25E | 1.976 | 24.221 | 26.197 | RELIABILITY | PREFINANCD CONVRSN(O) | IMPROVE SAFETY AND ACCESS MANAGEMENT, AND REDUCE CONGESTION ON US-25E FROM CORBIN BYPASS TO KNOX/LAUREL COUNTY LINE.(12CCR) | C |  | NH | 2021 | 6920000 | 5536000 |  |  | 1384000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.291 | 2021-04-23 | ADD C PHASE TO STIP; PARENT NO. 99-911.09; NEW |  |  | KNOX | 11-977 | KY 3438 |  | 0.505 | 1.548 | SAFETY | SAFETY-HAZARD ELIM(P) | GUARDRAIL INSTALLATION ON KY 3438 FROM MP 0.505 TO MP 1.548 IN KNOX COUNTY. (2018BOP) | C |  | SAF | 2021 | 86000 | 86000 | [8 empty] | 0
STIP | [9 empty] | KNOX | 11-1102 | CR 1325 | 0.004 | 0.191 | 0.195 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON OLD HWY 25 (CR 1325) JUST WEST OF US 25E. 061C00063N | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030048 | KNOX | 11-1102 | CR 1325 | 0.004 | 0.191 | 0.195 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON OLD HWY 25 (CR 1325) JUST WEST OF US 25E. 061C00063N | C |  | BR/STP | 2020 | 350000 | 217000 |  |  | 133000 |  |  | OBLIGATED |  | 440100 | 440100 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.015 | 2019-01-25 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 9010356 | KNOX, LAUREL, WHITLEY | 11-9015 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | PRELIMINARY DESIGN AND STUDY TO DETERMINE LOW COST IMPROVEMENTS AT VARIOUS INTERSECTIONS WITHIN DISTRICT 11. (2018BOP) | D |  | SAF | 2019 | 200000 | 200000 |  |  | 0 |  |  | OBLIGATED | 200000 |  | 200000 | 2019 | 2ND QUARTER
STIP | [9 empty] | KNOX | 11-10021 | CR 1353 |  | 0.396 | 0.406 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF SPIDER CREEK RD BRIDGE OVER EAST FORK LYNN CAMP CREEK. (061C00048N) | D |  | BR/STP | 2019 | 192500 | 119350 |  |  | 73150 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030116 | KNOX | 11-10021 | CR 1353 |  | 0.396 | 0.406 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF SPIDER CREEK RD BRIDGE OVER EAST FORK LYNN CAMP CREEK. (061C00048N) | C |  | BR/STP | 2020 | 469000 | 290780 |  |  | 178220 |  |  | OBLIGATED |  | 567840 | 567840 | 2019 | 3RD QUARTER
STIP | [9 empty] | KNOX | 11-10022 | CR 1162 |  | 0.032 | 0.036 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF DETHERAGE CEMETERY BRIDGE OVER BRUSH CREEK. (061C00056N) | D |  | BR/STP | 2019 | 157500 | 97650 |  |  | 59850 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030053 | KNOX | 11-10022 | CR 1162 |  | 0.032 | 0.036 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF DETHERAGE CEMETERY BRIDGE OVER BRUSH CREEK. (061C00056N) | C |  | BR/STP | 2020 | 367500 | 227850 |  |  | 139650 |  |  | OBLIGATED |  | 355230 | 355230 | 2019 | 2ND QUARTER
STIP | [9 empty] | KNOX | 11-10023 | CR 1065 |  | 0.038 | 0.05 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BURTON BRANCH RD BRIDGE OVER BURTON BRANCH. (061C00086N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [9 empty] | KNOX | 11-10023 | CR 1065 |  | 0.038 | 0.05 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BURTON BRANCH RD BRIDGE OVER BURTON BRANCH. (061C00086N) | C |  | BR/STP | 2020 | 360000 | 223200 |  |  | 136800 | [5 empty] | 0
STIP | [9 empty] | KNOX | 11-20007 | KY 6 |  | 13.714 | 14.212 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT | D |  | PM/STP | 2020 | 30000 | 24000 |  |  | 6000 | [5 empty] | 0
STIP | [9 empty] | KNOX | 11-20007 | KY 6 |  | 13.714 | 14.212 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT | C |  | PM/STP | 2020 | 300000 | 240000 |  |  | 60000 | [5 empty] | 0
STIP | [9 empty] | KNOX | 11-20008 | US 25E |  | 9.438 | 11.554 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT | D |  | PM/NH | 2019 | 125000 | 100000 |  |  | 25000 | [5 empty] | 0
STIP | [9 empty] | KNOX | 11-20008 | US 25E |  | 9.438 | 11.554 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT | C |  | PM/NH | 2019 | 1250000 | 1000000 |  |  | 250000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.306 | 2021-06-16 | ADD D PHASE TO STIP; NEW |  |  | KNOX | 11-80155 | KY 1487 |  | 0.369 | 1.176 |  | SAFETY (P) | IMPROVE SAFETY, ADDRESS GEOMETRIC DEFICIENCIES AND PROVIDE FLOOD MITIGATION ON KY 1487 (MANCHESTER STREET) FROM JUDGE STREET TO US 25E (2020CCN) | D |  | SPP | 2021 | 500100 | 100 |  |  | 500000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.152 | 2020-01-06 | ADD R PHASE TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 9010424 | LARUE | 4-989 | KY 470 |  | 5.18 | 6.8 | SAFETY | SAFETY-HAZARD ELIM(P) | FLATTEN SLOPES, WIDEN CURVES, UPGRADE GUARDRAIL END TREATMENTS, AND EXTEND CULVERT. (2018BOP) | R |  | SAF | 2020 | 10000 | 10000 |  |  | 0 |  |  | OBLIGATED | 9000 |  | 9000 | 2020 | 1ST QUARTER
[8 empty] | HSIP | 9010342 | LARUE | 4-989 | KY 470 |  | 5.18 | 6.8 | SAFETY | SAFETY-HAZARD ELIM(P) | FLATTEN SLOPES, WIDEN CURVES, UPGRADE GUARDRAIL END TREATMENTS, AND EXTEND CULVERT. (2018BOP) | U |  | SAF | 2019 | [7 empty] | OBLIGATED | 10000 |  | 10000 | 2019 | 1ST QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.039 | 2019-03-19 | ADDING C PHASE TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 9010342 | LARUE | 4-989 | KY 470 |  | 5.18 | 6.8 | SAFETY | SAFETY-HAZARD ELIM(P) | FLATTEN SLOPES, WIDEN CURVES, UPGRADE GUARDRAIL END TREATMENTS, AND EXTEND CULVERT. (2018BOP) | C |  | SAF | 2019 | 586000 | 586000 | [5 empty] | OBLIGATED | 711101 |  | 711101 | 2019 | 3RD QUARTER
STIP | [9 empty] | LARUE | 4-8911 | KY 84 | 9.033 | 0 | 9.033 | RELIABILITY | SPOT IMPROVEMENTS(O) | SPOT IMPROVEMENTS ON KY 84 FROM HODGENVILLE TO I-65. (16CCN)(18CCN) | D |  | PM/STP | 2020 | 50000 | 40000 |  |  | 10000 | [5 empty] | 0
STIP | [9 empty] | LARUE | 4-8911 | KY 84 | 9.033 | 0 | 9.033 | RELIABILITY | SPOT IMPROVEMENTS(O) | SPOT IMPROVEMENTS ON KY 84 FROM HODGENVILLE TO I-65. (16CCN)(18CCN) | C |  | PM/STP | 2020 | 450000 | 360000 |  |  | 90000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.257 | 2020-11-16 | INCREASE FUND AMOUNT BASED ON NEW ESTIMATE & CHANGE FISCAL YEAR TO FY 2021; MOD |  |  | LARUE | 4-8911 | KY 84 | 9.033 | 0 | 9.033 | RELIABILITY | SPOT IMPROVEMENTS(O) | SPOT IMPROVEMENTS ON KY 84 FROM HODGENVILLE TO I-65. (16CCN)(18CCN) | C |  | PM/STP | 2021 | 3690500 | 3690500 | [8 empty] | 0
STIP | [9 empty] | LARUE | 4-10002 | KY 61 |  | 4.045 | 4.057 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-61 BRIDGE OVER SOUTH FORK BRANCH. (062B00008N) | D |  | BR/STP | 2019 | 87500 | 54250 |  |  | 33250 | [5 empty] | 0
STIP | [9 empty] | LARUE | 4-10002 | KY 61 |  | 4.045 | 4.057 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-61 BRIDGE OVER SOUTH FORK BRANCH. (062B00008N) | C |  | BR/STP | 2020 | 605500 | 375410 |  |  | 230090 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.306 | 2021-06-16 | ADD D PHASE TO STIP; NEW |  |  | LARUE | 4-80154 | KY 210 |  | 6.994 | 16.613 |  | SAFETY (P) | ADDRESS SAFETY BY IMPROVING EXISTING ALIGNMENT IN SPOTS AND ADD PASSING LANES ALONG KY 210 FROM CAMPBELLSVILLE TO HODGENVILLE. MILEPOINTS 0-14.148 AND 6.994-16.613 AND 0-0.750 IN TAYLOR, LARUE, AND GREEN. (2020CCN) | D |  | SPP | 2021 | 2000100 | 100 |  |  | 2000000 | [5 empty] | 0
STIP | [9 empty] | LAUREL | 11-9.1 | I 75 | 4.3 | 28.9 | 33.2 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE I-75 FROM US-25E TO THE LITTLE LAUREL RIVER (16CCR) | R |  | NH | 2019 | 70000 | 70000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | LAUREL | 11-9.1 | I 75 | 4.3 | 28.9 | 33.2 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE I-75 FROM US-25E TO THE LITTLE LAUREL RIVER (16CCR) | U |  | NH | 2019 | 50000 | 50000 |  |  | 0 | [5 empty] | 0
STIP | [7 empty] | NHPPIM | 752100 | LAUREL | 11-9.1 | I 75 | 4.3 | 28.9 | 33.2 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE I-75 FROM US-25E TO THE LITTLE LAUREL RIVER (16CCR) | C |  | NH | 2020 | 10000000 | 10000000 |  |  | 0 |  |  | OBLIGATED | 38354800 | 20549000 | 58903800 | 2019 | 2ND QUARTER
STIP | [9 empty] | LAUREL | 11-9.14 | I 75 | 4.3 | 28.85 | 33.162 | RELIABILITY | PREFINANCD CONVRSN(O) | IMPROVE I-75 FROM US-25E TO THE LITTLE LAUREL RIVER (16CCR) | C |  | NH | 2021 | 20000000 | 16000000 |  |  | 4000000 | [5 empty] | 0
STIP | [9 empty] | LAUREL | 11-9.15 | I 75 | 4.3 | 28.85 | 33.162 | RELIABILITY | PREFINANCD CONVRSN(O) | IMPROVE I-75 FROM US-25E TO THE LITTLE LAUREL RIVER (16CCR) | C |  | NH | 2022 | 18500000 | 14800000 |  |  | 3700000 | [5 empty] | 0
STIP | [9 empty] | LAUREL | 11-11 | I 75 | 7.296 | 40.704 | 48 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE I-75 FROM KY 80 AT LONDON TO SOUTH OF THE KY-909 UNDERPASS. | C |  | NH | 2022 | 20750000 | 16600000 |  |  | 4150000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.126 | 2019-09-20 | INCREASE FUNDS BASED ON NEW ESTIMATE AND UPDATE FISCAL YEAR. THIS PROJECT IS IN THE 2018 HIGHWAY PLAN UNDER ITEM 11-11.00, 11-11.02 AND 11-11.03. THESE PROJECTS TOTALED $62,250,000. WE NEED ADDITIONAL FUNDS THEREFORE WE ARE REQUESTING $70,000,000; MOD | NHPPIM | 0752059 | LAUREL | 11-11 | I 75 | 7.296 | 40.704 | 48 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE I-75 FROM KY 80 AT LONDON TO SOUTH OF THE KY-909 UNDERPASS. | C |  | NH | 2020 | 70000000 | 70000000 |  |  | 0 |  |  | OBLIGATED | 10408121 | 63774560 | 74182681 | 2019 | 4TH QUARTER
STIP | [9 empty] | LAUREL | 11-147 | US 25 | 1.505 | 9 | 10.505 | RELIABILITY | MAJOR WIDENING(O) | REDUCE CONGESTION ON US-25 FROM KY-1006 TO KY-2069; IMPROVE CONNECTIVITY FROM US-25 NEAR KY-2069 TO KY-229; IMPROVE KY-229 FROM THE NEW CONNECTOR NORTH TO KY-192; AND IMPROVE ACCESS TO THE SCHOOL FROM KY-192 BYPASS. (06CCR)(10CCR)(12CCR)(14CCR) | C |  | STP | 2022 | 10000000 | 8000000 |  |  | 2000000 | [5 empty] | 0
STIP | [9 empty] | LAUREL | 11-185 | US 25E | 2.024 | 0 | 2.024 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE SAFETY, IMPROVE ACCESS MANAGEMENT, AND REDUCE CONGESTION ON US-25E FROM THE KNOX/LAUREL COUNTY LINE TO KY-770 (12CCR)(16CCR) | C |  | NH | 2020 | 4580000 | 4580000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | LAUREL | 11-185.01 | US 25E | 2.024 | 0 | 2.024 | RELIABILITY | PREFINANCD CONVRSN(O) | IMPROVE SAFETY, IMPROVE ACCESS MANAGEMENT, AND REDUCE CONGESTION ON US-25E FROM THE KNOX/LAUREL COUNTY LINE TO KY-770 (12CCR)(16CCR) | C |  | NH | 2021 | 6860000 | 5488000 |  |  | 1372000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.126 | 2019-09-20 | ADD R PHASE TO STIP; NEW | NHPP | 0804021 | LAUREL | 11-187 | KY 192 | 2.07 | 18.35 | 20.42 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE SAFETY, ACCESS MANAGEMENT, AND FREIGHT MOBILITY; AND REDUCE CONGESTION ON KY-192 NEAR KY-1006 TO US-25 IN LONDON. (12CCR)(LET W/ 11-8514.10) | R |  | NH | 2019 | 3500000 | 3500000 |  |  | 0 |  |  | OBLIGATED | 3500000 |  | 3500000 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.126 | 2019-09-20 | ADD U PHASE TO STIP; NEW | NHPP | 0804021 | LAUREL | 11-187 | KY 192 | 2.07 | 18.35 | 20.42 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE SAFETY, ACCESS MANAGEMENT, AND FREIGHT MOBILITY; AND REDUCE CONGESTION ON KY-192 NEAR KY-1006 TO US-25 IN LONDON. (12CCR)(LET W/ 11-8514.10) | U |  | NH | 2019 | 1645000 | 1645000 |  |  | 0 |  |  | OBLIGATED | 1554218 |  | 1554218 | 2019 | 4TH QUARTER
STIP | [9 empty] | LAUREL | 11-187 | KY 192 | 2.07 | 18.35 | 20.42 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE SAFETY, ACCESS MANAGEMENT, AND FREIGHT MOBILITY; AND REDUCE CONGESTION ON KY-192 NEAR KY-1006 TO US-25 IN LONDON. (12CCR) | C |  | NH | 2022 | 6000000 | 4800000 |  |  | 1200000 | [5 empty] | 0
STIP | [9 empty] | LAUREL | 11-365 | HR 9006 | 2.788 | 1.089 | 3.877 | RELIABILITY | MAJOR WIDENING(O) | REDUCE CONGESTION ON THE HAL ROGERS PARKWAY FROM RELOCATED KY-30 TO KY-192. (18CCR) | D |  | NH | 2021 | 1870000 | 1496000 |  |  | 374000 | [5 empty] | 0
STIP | [9 empty] | LAUREL | 11-365 | HR 9006 | 2.788 | 1.089 | 3.877 | RELIABILITY | MAJOR WIDENING(O) | REDUCE CONGESTION ON THE HAL ROGERS PARKWAY FROM RELOCATED KY-30 TO KY-192. (18CCR) | R |  | NH | 2022 | 2080000 | 1664000 |  |  | 416000 | [5 empty] | 0
STIP | [9 empty] | LAUREL | 11-365 | HR 9006 | 2.788 | 1.089 | 3.877 | RELIABILITY | MAJOR WIDENING(O) | REDUCE CONGESTION ON THE HAL ROGERS PARKWAY FROM RELOCATED KY-30 TO KY-192. (18CCR) | U |  | NH | 2022 | 1250000 | 1000000 |  |  | 250000 | [5 empty] | 0
STIP | [9 empty] | LAUREL | 11-1094 | CR 1341 |  | 1.071 | 1.111 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON DOG BRANCH SCHOOL RD (CR 1341) OVER SINKING CREEK 0.56 MILE NW OF SINKING CREEK RD (FD 781) 063C00025N | C |  | BR/STP | 2020 | 770000 | 477400 |  |  | 292600 | [5 empty] | 0
STIP | [9 empty] | LAUREL | 11-1105.01 | I 75 |  | 30.55 | 30.65 | ASSET MANAGEMENT | AM-BRIDGE (P) | REHAB BRIDGE ON I-75 AT MILEPOST 30.5 OVER LAUREL RIVER (SR 34.1) (B00043R AND B00043L)(SD) | C |  | BR/NH | 2019 | 2800000 | 1736000 |  |  | 1064000 | [5 empty] | 0
STIP | [9 empty] | LAUREL | 11-8515 | US 25 |  | 0 | 10.475 | RELIABILITY | DESIGN ENGINEERING(O) | IMPROVE CONNECTIVITY BETWEEN CORBIN AND LONDON FROM KY-1006 TO US-25E. (08CCN) | P |  | STP | 2020 | 500000 | 500000 |  |  | 0 | [5 empty] | 0
STIP | [7 empty] | STP | 5203020 | LAUREL | 11-8515 | US 25 |  | 0 | 10.475 | RELIABILITY | DESIGN ENGINEERING(O) | IMPROVE CONNECTIVITY BETWEEN CORBIN AND LONDON FROM KY-1006 TO US-25E. (08CCN) | D |  | STP | 2022 | 3000000 | 2400000 |  |  | 600000 |  |  | OBLIGATED | 1400000 | 500000 | 1900000 | 2019 | 2ND QUARTER
STIP | [9 empty] | LAUREL | 11-8909 | HR 9006 | 2.716 | 7.877 | 10.593 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE THE HAL ROGERS PARKWAY TO INTERSTATE STANDARDS FROM 4.0 MI EAST OF KY 192 TO LAUREL/CLAY CO. LINE. (I-75 TO HAZARD) (16CCN)(18CCR) | D |  | NH | 2021 | 1000000 | 800000 |  |  | 200000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.274 | 2021-02-04 | ADD D PHASE TO STIP; NEW |  |  | LAUREL | 11-8953 | CR 1414 |  | 0.4 | 0.416 | ASSET MANAGEMENT | AM-BRIDGE (P) | REPLACE BRIDGE (063C00044N) ON MT ZION CHURCH ROAD (CR 1414). (16CCN) (2020CCR) | D |  | STP | 2021 | 300000 | 300000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.126 | 2019-09-20 | ADD PROJECT TO STIP; PARENT NO. 11-9008.00; NEW | HSIP | 9010408 | LAUREL | 11-9008.5 | KY 192 |  | 17.55 | 17.85 | SAFETY | SAFETY-HAZARD ELIM(P) | WIDEN KY 192 AND EXTEND THE EXISTING 3-LANE SECTION FURTHER SOUTH, INSTALL MEDIAN ACCESS CONTROL, AND UPDATE THE STRIPING AND SIGNING AT THE INTERSECTION OF KY 192 & THOMPSON POYNTER RD. (2018BOP) | C |  | SAF | 2019 | 325000 | 325000 |  |  | 0 |  |  | OBLIGATED |  | 438385 | 438385 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.139 | 2019-10-25 | ADD R PHASE TO STIP; PARENT NO. 99-911.06; NEW |  |  | LAUREL | 11-9009 | KY 490 |  | 3.012 | 8.202 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ALONG KY 490 BETWEEN MP 3.012 AND MP 8.202 IN LAUREL COUNTY, KY. (2016BOP) | R |  | SAF | 2020 | 55000 | 55000 |  |  | 0 |  |  | OBLIGATED | 55000 |  | 55000 | 2020 | 1ST QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.139 | 2019-10-25 | ADD U PHASE TO STIP; PARENT NO. 99-911.06; NEW |  |  | LAUREL | 11-9009 | KY 490 |  | 3.012 | 8.202 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ALONG KY 490 BETWEEN MP 3.012 AND MP 8.202 IN LAUREL COUNTY, KY. (2016BOP) | U |  | SAF | 2020 | 75000 | 75000 |  |  | 0 |  |  | OBLIGATED | 75000 |  | 75000 | 2020 | 1ST QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.276 | 2021-02-12 | ADD C PHASE TO STIP; PARENT NO. 99-911.06; NEW |  |  | LAUREL | 11-9009 | KY 490 |  | 2.95 | 8.202 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ALONG KY 490 BETWEEN MP 2.950 AND MP 8.202 IN LAUREL COUNTY, KY. (2016BOP) | C |  | SAF | 2021 | 2773100 | 2773100 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.029 | 2019-02-21 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 0803211 | LAUREL | 11-9014 | KY 80 |  | 7.1 | 7.9 | SAFETY | SAFETY-HAZARD ELIM(P) | CONSTRUCTION OF A J-TURN AT THE INTERSECTION OF KY 80 AND KY 1535. (2018BOP) | C |  | SAF | 2019 | 935000 | 935000 |  |  | 0 |  |  | OBLIGATED | 1312507 |  | 1312507 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.053 | 2019-04-25 | ADD D PHASE TO STIP; PARENT NO. 99-911.08; NEW |  |  | LAUREL, BELL, HARLAN | 11-9016 | KY 229 KY 2070 KY 38 |  | 7.573 .656 0.00 | 7.773 .856 .1 | SAFETY | SAFETY-HAZARD ELIM(P) | PRELIMINARY DESIGN AND STUDY OF MINI-ROUNDABOUTS AT VARIOUS INTERSECTIONS IN DISTRICT 11. (2018BOP) | D |  | SAF | 2019 | 350000 | 350000 |  |  | 0 |  |  | OBLIGATED |  | 350000 | 350000 | 2019 | 3RD QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.3 | 2021-05-28 | ADD R PHASE TO STIP; PARENT NO. 11-9016; NEW |  |  | LAUREL | 11-9016.1 | KY 229 |  | 7.512 | 7.832 | SAFETY | SAFETY-HAZARD ELIM(P) | CONSTRUCT A MINI ROUNDABOUT AT THE INTERSECTION OF KY 229 & KY 1189. (2020BOP) | R |  | SAF | 2021 | 55000 | 55000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.3 | 2021-05-28 | ADD U PHASE TO STIP; PARENT NO. 11-9016; NEW |  |  | LAUREL | 11-9016.1 | KY 229 |  | 7.512 | 7.832 | SAFETY | SAFETY-HAZARD ELIM(P) | CONSTRUCT A MINI ROUNDABOUT AT THE INTERSECTION OF KY 229 & KY 1189. (2020BOP) | U |  | SAF | 2021 | 50000 | 50000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.175 | 2020-04-09 | ADD D PHASE TO STIP; PARENT NO. 99-911.09; NEW |  |  | LAUREL | 11-9018 | KY 363 |  | 0 | 2.214 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 363 FROM MP 0.000 TO MP 2.214 IN LAUREL COUNTY, KY. (2018BOP) | D |  | SAF | 2020 | 200000 | 200000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | LAUREL | 11-10024 | KY 1223 |  | 1.241 | 1.245 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-1223 BRIDGE OVER HORSE CREEK. (063B00007N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [9 empty] | LAUREL | 11-10024 | KY 1223 |  | 1.241 | 1.245 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-1223 BRIDGE OVER HORSE CREEK. (063B00007N) | C |  | BR/STP | 2020 | 378000 | 234360 |  |  | 143640 | [5 empty] | 0
STIP | [9 empty] | LAUREL | 11-10025 | KY 80 |  | 17.706 | 17.71 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-80 BRIDGE OVER LICK FORK CREEK. (063B00013N) | D |  | BR/STP | 2019 | 210000 | 130200 |  |  | 79800 | [5 empty] | 0
STIP | [9 empty] | LAUREL | 11-10025 | KY 80 |  | 17.706 | 17.71 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-80 BRIDGE OVER LICK FORK CREEK. (063B00013N) | C |  | BR/STP | 2020 | 525000 | 325500 |  |  | 199500 | [5 empty] | 0
STIP | [9 empty] | LAUREL | 11-10026 | KY 80 |  | 22.228 | 22.236 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-80 BRIDGE OVER HOOPPOLE CREEK. (063B00017N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030074 | LAUREL | 11-10026 | KY 80 |  | 22.228 | 22.236 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-80 BRIDGE OVER HOOPPOLE CREEK. (063B00017N) | C |  | BR/STP | 2020 | 507500 | 314650 |  |  | 192850 |  |  | OBLIGATED |  | 403300 | 403300 | 2019 | 3RD QUARTER
STIP | [9 empty] | LAUREL | 11-10042 | KY 490 |  | 11.502 | 11.509 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 490 BRIDGE OVER ROCKCASTLE RIVER. (063B00004N) | D |  | BR/STP | 2019 | 245000 | 151900 |  |  | 93100 | [5 empty] | 0
STIP | [9 empty] | LAUREL | 11-10042 | KY 490 |  | 11.502 | 11.509 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 490 BRIDGE OVER ROCKCASTLE RIVER. (063B00004N) | C |  | BR/STP | 2020 | 2492000 | 1545040 |  |  | 946960 | [5 empty] | 0
STIP | [9 empty] | LAUREL | 11-10043 | KY 638 |  | 7.792 | 7.814 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 638 BRIDGE OVER BIG RACCOON CREEK. (063B00061N) | D |  | BR/STP | 2019 | 192500 | 119350 |  |  | 73150 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030097 | LAUREL | 11-10043 | KY 638 |  | 7.792 | 7.814 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 638 BRIDGE OVER BIG RACCOON CREEK. (063B00061N) | C |  | BR/STP | 2020 | 829500 | 514290 |  |  | 315210 |  |  | OBLIGATED |  | 749535 | 749535 | 2019 | 3RD QUARTER
STIP | [9 empty] | LAUREL | 11-20009 | HR 9006 |  | 0 | 3.877 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF HAL ROGERS DANIEL BOONE PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 0 TO MILEPOINT 3.877 | D |  | PM/NH | 2019 | 310000 | 248000 |  |  | 62000 | [5 empty] | 0
STIP | [7 empty] | NHPP | 0804020 | LAUREL | 11-20009 | HR 9006 |  | 0 | 3.877 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF HAL ROGERS DANIEL BOONE PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 0 TO MILEPOINT 3.877 | C |  | PM/NH | 2019 | 3100000 | 2480000 |  |  | 620000 |  |  | OBLIGATED | 2584296 |  | 2584296 | 2019 | 2ND QUARTER
STIP | [9 empty] | LAUREL | 11-20011 | I 75 |  | 32.485 | 32.9 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION ON PCC PAVEMENT ON I-075 CARDINAL DIRECTION(S) FROM MILEPOINT 32.485 TO MILEPOINT 32.9 | D |  | PM/NH | 2019 | 120000 | 96000 |  |  | 24000 | [5 empty] | 0
STIP | [9 empty] | LAUREL | 11-20011 | I 75 |  | 32.485 | 32.9 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION ON PCC PAVEMENT ON I-075 CARDINAL DIRECTION(S) FROM MILEPOINT 32.485 TO MILEPOINT 32.9 | C |  | PM/NH | 2019 | 1200000 | 960000 |  |  | 240000 | [5 empty] | 0
STIP | [9 empty] | LAUREL | 11-20013 | I 75 |  | 50.524 | 50.714 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-075 BOTH DIRECTION(S) FROM MILEPOINT 50.524 (49.87 NON-CARDINAL) TO MILEPOINT 50.714 | D |  | PM/NH | 2019 | 100000 | 80000 |  |  | 20000 | [5 empty] | 0
STIP | [7 empty] | NHPPIM | 0752101 | LAUREL | 11-20013 | I 75 |  | 50.524 | 50.714 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-075 BOTH DIRECTION(S) FROM MILEPOINT 50.524 (49.87 NON-CARDINAL) TO MILEPOINT 50.714 | C |  | PM/NH | 2019 | 1000000 | 800000 |  |  | 200000 |  |  | OBLIGATED | 722427 | 180323 | 902750 | 2019 | 3RD QUARTER
STIP | [9 empty] | LAUREL | 11-20023 | KY 490 | 6.14 | 0 | 6.14 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION ON KY-490 FROM MILEPOINT 0.00 TO MILEPOINT 6.14 | C |  | PM/STP | 2022 | 924000 | 739200 |  |  | 184800 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.229 | 2020-09-14 | ADD C PHASE TO STIP; PARENT NO. 99-224.14; NEW |  |  | LAUREL | 11-20033 | KY 490 KY 80 |  | 0 4.445 & 11.00 | 2.95 10.47 & 15.21 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | RESURFACING ON KY 490 (MP 0.00-2.95) AND KY 80 (MP 4.445-10.47 AND MP 11.00-15.21) IN LAUREL COUNTY, KY. | C |  | PM | 2020 | 4226958 | 4226958 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.039 | 2019-03-19 | ADDING PROJECT TO STIP; PARENT NO. 99-911.06; NEW | HSIP | 9010340 | LAWRENCE | 12-957 | KY 2565 |  | 3.2 | 3.35 | SAFETY | SAFETY-HAZARD ELIM(P) | REALIGNMENT OF KY 2565 BETWEEN MP 3.2 AND MP 3.35 (DEAD MAN CURVE) IN LAWRENCE COUNTY. (2016BOP)(D,R,U PHASES UNDER ITEM NO.12-193) | C |  | SAF | 2019 | 647000 | 647000 |  |  | 0 |  |  | OBLIGATED | 1142877 |  | 1142877 | 2019 | 3RD QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.25 | 2020-10-22 | ADD C PHASE TO STIP; PARENT NO. 12-9004.00; NEW |  |  | LAWRENCE | 12-9004.1 | US 23 |  | 18.35 | 18.65 | SAFETY | SAFETY-HAZARD ELIM(P) | CONSTRUCT AN ACCELERATION LANE ALONG NB US 23 JUST NORTH OF THE INTERSECTION OF US 23 & KY 3. (2018BOP) | C |  | SAF | 2021 | 161000 | 161000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | LAWRENCE | 12-10003 | CR 1234 |  | 0.04 | 0.052 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF MAXIE BRANCH RD BRIDGE OVER RT FORK-BLAINE CREEK. (064C00076N) | D |  | BR/STP | 2019 | 140000 | 86800 |  |  | 53200 | [5 empty] | 0
STIP | [9 empty] | LAWRENCE | 12-10003 | CR 1234 |  | 0.04 | 0.052 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF MAXIE BRANCH RD BRIDGE OVER RT FORK-BLAINE CREEK. (064C00076N) | C |  | BR/STP | 2020 | 478000 | 296360 |  |  | 181640 | [5 empty] | 0
STIP | [9 empty] | LAWRENCE | 12-10016 | KY 644 |  | 1.468 | 1.558 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 644 BRIDGE OVER LEVISA FORK OF BIG SANDY. (064B00038N) | D |  | BR/STP | 2019 | 560000 | 347200 |  |  | 212800 | [5 empty] | 0
STIP | [9 empty] | LAWRENCE | 12-10016 | KY 644 |  | 1.468 | 1.558 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 644 BRIDGE OVER LEVISA FORK OF BIG SANDY. (064B00038N) | C |  | BR/STP | 2020 | 2880500 | 1785910 |  |  | 1094590 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.229 | 2020-09-14 | ADD C PHASE TO STIP; PARENT NO. 99-224.14; NEW |  |  | LAWRENCE | 12-20008 | KY 32 |  | 7.184 | 14.368 | RELIABILITY | AM-PAVEMENT(PRI)(P) | RESURFACING OF KY 32 (MP 7.184-14.368) IN LAWRENCE COUNTY, KY. | C |  | STP | 2020 | 944346 | 944346 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.263 | 2020-12-11 | ADD C PHASE TO STIP; PARENT NO. 10-292.00; NEW |  |  | LEE OWSLEY | 10-292.10 | KY 11 |  | 0 | 1.082 | RELIABILITY | RECONSTRUCTION(O) | I-75 TO MOUNTAIN PARKWAY; RECONSTRUCT KY-11 FROM KY-30 AT LEVI IN OWSLEY COUNTY TO 0.5 MILE SOUTH OF KY-587 IN LEE COUNTY. START AT KY-30 AT LEVI IN OWSLEY MOVING NORTH. (06CCR)(10CCR)(14CCR)(18CCN) (2020CCR) | C |  | STP | 2021 | 20600000 | 20600000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.265 | 2020-12-23 | UPDATE PROJECT DESCRIPTION; MOD |  |  | LEE OWSLEY | 10-292.10 | KY 11 |  | 0 | 1.082 | RELIABILITY | RECONSTRUCTION(O) | I-75 TO MOUNTAIN PARKWAY; RECONSTRUCT KY-11 FROM KY-30 AT LEVI IN OWSLEY COUNTY TO KY-587 INTERSECTION IN LEE COUNTY. START AT KY-30 AT LEVI IN OWSLEY MOVING NORTH. (06CCR)(10CCR)(14CCR)(18CCN) (2020CCR) | C |  | STP | 2021 | 20600000 | 20600000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.269 | 2021-01-22 | INCREASE FUND AMOUNT BASED ON NEW ESTIMATE; MOD |  |  | LEE OWSLEY | 10-292.10 | KY 11 |  | 0 | 1.082 | RELIABILITY | RECONSTRUCTION(O) | I-75 TO MOUNTAIN PARKWAY; RECONSTRUCT KY-11 FROM KY-30 AT LEVI IN OWSLEY COUNTY TO KY-587 INTERSECTION IN LEE COUNTY. START AT KY-30 AT LEVI IN OWSLEY MOVING NORTH. (06CCR)(10CCR)(14CCR)(18CCN) (2020CCR) | C |  | STP | 2021 | 26472000 | 26472000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | LEE | 10-10013 | CR 1124 |  | 0 | 0.013 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF GOOSE CREEK RD BRIDGE OVER CSX RAILROAD. (065R00604N) | D |  | BR/STP | 2019 | 245000 | 151900 |  |  | 93100 | [5 empty] | 0
STIP | [9 empty] | LEE | 10-10013 | CR 1124 |  | 0 | 0.013 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF GOOSE CREEK RD BRIDGE OVER CSX RAILROAD. (065R00604N) | C |  | BR/STP | 2020 | 770000 | 477400 |  |  | 292600 | [5 empty] | 0
STIP | [7 empty] | STPBRO | 4211046 | LESLIE | 11-1078 | US 421 | 0.1 | 15.137 | 15.177 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE AND APPROACHES ON US-421 OVER STINNET CREEK 0.028 MILE SOUTH OF KY-406 NEAR STINNETT(10CCR)(066B00008N) | C |  | BR/STP | 2019 | 2128000 | 1319360 |  |  | 808640 |  |  | OBLIGATED |  | 2470160 | 2470160 | 2019 | 2ND QUARTER
STIP | [9 empty] | LESLIE | 11-1095 | US 421 | 0.014 | 18.423 | 18.437 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER MUNCY CREEK ON US 421 0.5 MILE SOUTH OF TAYLOR MORGAN ROAD (CR 1090).(066B00006N) | C |  | BR/STP | 2020 | 612500 | 379750 |  |  | 232750 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.21 | 2020-07-31 | ADD R PHASE TO STIP; NEW |  |  | LESLIE | 11-1095 | US 421 | 0.014 | 18.423 | 18.437 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER MUNCY CREEK ON US 421 0.5 MILE SOUTH OF TAYLOR MORGAN ROAD (CR 1090).(066B00006N) | R |  | BR/STP | 2020 | 31900 | 31900 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.21 | 2020-07-31 | ADD U PHASE TO STIP; NEW |  |  | LESLIE | 11-1095 | US 421 | 0.014 | 18.423 | 18.437 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER MUNCY CREEK ON US 421 0.5 MILE SOUTH OF TAYLOR MORGAN ROAD (CR 1090).(066B00006N) | U |  | BR/STP | 2020 | 90000 | 90000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | LESLIE | 11-1100 | CR 1528 | 0.012 | 0 | 0.012 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER WOLF CREEK ON COON CREEK ROAD (CR 1528) AT JCT WITH KY 3427 (066C00039N) (EBRP) | D |  | BR/STP | 2019 | 123000 | 76260 |  |  | 46740 | [5 empty] | 0
STIP | [9 empty] | LESLIE | 11-1100 | CR 1528 | 0.012 | 0 | 0.012 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER WOLF CREEK ON COON CREEK ROAD (CR 1528) AT JCT WITH KY 3427 (066C00039N) (EBRP) | C |  | BR/STP | 2020 | 445000 | 275900 |  |  | 169100 | [5 empty] | 0
STIP | [9 empty] | LESLIE | 11-1104 | CR 1219 | 0.012 | 0.016 | 0.028 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON MILE BRANCH RD (CR 1219) (MP 0.022) OVER BEECH FORK. 066C00048N | D |  | BR/STP | 2019 | 245000 | 151900 |  |  | 93100 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030118 | LESLIE | 11-1104 | CR 1219 | 0.012 | 0.016 | 0.028 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON MILE BRANCH RD (CR 1219) (MP 0.022) OVER BEECH FORK. 066C00048N | C |  | BR/STP | 2020 | 613000 | 380060 |  |  | 232940 |  |  | OBLIGATED |  | 682341.2 | 682341.2 | 2019 | 3RD QUARTER
STIP | [9 empty] | LESLIE | 11-1106 | CR 1207 |  | 0.022 | 0.034 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON WILLIAMS BRANCH RD (CR-1207) (0.028) OVER MIDDLE FORK KENTUCKY RIVER. 066C00020N | D |  | BR/STP | 2019 | 245000 | 151900 |  |  | 93100 | [5 empty] | 0
STIP | [9 empty] | LESLIE | 11-1106 | CR 1207 |  | 0.022 | 0.034 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON WILLIAMS BRANCH RD (CR-1207) (0.028) OVER MIDDLE FORK KENTUCKY RIVER. 066C00020N | C |  | BR/STP | 2020 | 560000 | 347200 |  |  | 212800 | [5 empty] | 0
STIP | [9 empty] | LESLIE | 11-10027 | KY 1780 |  | 14.276 | 14.288 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-1780 BRIDGE OVER BEECH FORK. (066B00027N) | D |  | BR/STP | 2019 | 210000 | 130200 |  |  | 79800 | [5 empty] | 0
STIP | [9 empty] | LESLIE | 11-10027 | KY 1780 |  | 14.276 | 14.288 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-1780 BRIDGE OVER BEECH FORK. (066B00027N) | C |  | BR/STP | 2020 | 857500 | 531650 |  |  | 325850 | [5 empty] | 0
STIP | [9 empty] | LESLIE | 11-10028 | KY 699 |  | 8.134 | 8.138 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-699 BRIDGE OVER MAGGARDS BRANCH. (066B00031N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [9 empty] | LESLIE | 11-10028 | KY 699 |  | 8.134 | 8.138 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-699 BRIDGE OVER MAGGARDS BRANCH. (066B00031N) | C |  | BR/STP | 2020 | 525000 | 325500 |  |  | 199500 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.03 | 2019-03-01 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD |  |  | LESLIE | 11-10028 | KY 699 |  | 8.134 | 8.138 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-699 BRIDGE OVER MAGGARDS BRANCH. (066B00031N) | C |  | STP | 2019 | 535536 | 535536 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.075 | 2019-05-28 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030070 | LESLIE | 11-10028 | KY 699 |  | 8.134 | 8.138 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-699 BRIDGE OVER MAGGARDS BRANCH. (066B00031N) | C |  | STP | 2020 | 745596 | 745596 |  |  | 0 |  |  | OBLIGATED |  | 921644.6 | 921644.6 | 2019 | 3RD QUARTER
STIP | [9 empty] | LESLIE | 11-10029 | KY 2431 |  | 0.008 | 0.062 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-2431 BRIDGE OVER MIDDLE FORK OF KY RIVER. (066B00039N) | D |  | BR/STP | 2021 | 300000 | 186000 |  |  | 114000 | [5 empty] | 0
STIP | [9 empty] | LESLIE | 11-10029 | KY 2431 |  | 0.008 | 0.062 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-2431 BRIDGE OVER MIDDLE FORK OF KY RIVER. (066B00039N) | R |  | BR/STP | 2022 | 75000 | 46500 |  |  | 28500 | [5 empty] | 0
STIP | [9 empty] | LESLIE | 11-10029 | KY 2431 |  | 0.008 | 0.062 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-2431 BRIDGE OVER MIDDLE FORK OF KY RIVER. (066B00039N) | U |  | BR/STP | 2022 | 180000 | 111600 |  |  | 68400 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.118 | 2019-08-19 | ADD PROJECT TO STIP; NEW | STPBRZ | 9030171 | LESLIE | 11-10029 | KY 2431 |  | 0.008 | 0.062 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-2431 BRIDGE OVER MIDDLE FORK OF KY RIVER. (066B00039N) | C |  | STP | 2020 | 1898894 | 1898894 |  |  | 0 |  |  | OBLIGATED |  | 949034.6 | 949034.6 | 2019 | 4TH QUARTER
STIP | [9 empty] | LESLIE | 11-10030 | CR 1006 |  | 0.006 | 0.016 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF CR-1006 BRIDGE OVER RACCOON CREEK. (066C00002N) | D |  | BR/STP | 2019 | 192500 | 119350 |  |  | 73150 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030054 | LESLIE | 11-10030 | CR 1006 |  | 0.006 | 0.016 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF CR-1006 BRIDGE OVER RACCOON CREEK. (066C00002N) | C |  | BR/STP | 2020 | 451500 | 279930 |  |  | 171570 |  |  | OBLIGATED |  | 445700 | 445700 | 2019 | 2ND QUARTER
STIP | [9 empty] | LESLIE | 11-10031 | CR 1271 |  | 0.056 | 0.066 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF CR-1271 BRIDGE OVER MIDDLE FK KENTUCKY RVR. (066C00023N) | D |  | BR/STP | 2019 | 210000 | 130200 |  |  | 79800 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030090 | LESLIE | 11-10031 | CR 1271 |  | 0.056 | 0.066 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF CR-1271 BRIDGE OVER MIDDLE FK KENTUCKY RVR. (066C00023N) | C |  | BR/STP | 2020 | 525000 | 325500 |  |  | 199500 |  |  | OBLIGATED |  | 372585 | 372585 | 2019 | 3RD QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.139 | 2019-10-25 | ADD PROJECT TO STIP; NEW | STPBRZ | 9030257 | LESLIE | 11-10049 | CR 406 |  | 0.013 |  | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES ON VIOLET LANE (CR 406) OVER STINNETT CREEK. (066C00093N) | C |  | STP | 2020 | 1050000 | 1050000 |  |  | 0 |  |  | OBLIGATED | 60000 | 820325 | 880325 | 2020 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.139 | 2019-10-25 | ADD PROJECT TO STIP; NEW |  |  | LESLIE | 11-10051 | CR 1210 |  | 0.065 |  | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES ON CR-1210 OVER MIDDLE FORK. (066C00090N) | C |  | STP | 2020 | 485000 | 485000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.155 | 2020-01-22 | ADD PROJECT TO STIP; NEW | STPBRZ | 9030255 | LESLIE | 11-10093 | CR 1385 |  | 0.011 |  | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES ON CR 1385 OVER ROCKHOUSE CREEK. (066C00067N) | C |  | STP | 2020 | 477250 | 477250 |  |  | 0 |  |  | OBLIGATED | 40000 | 437250 | 477250 | 2020 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.118 | 2019-08-19 | ADD PROJECT TO STIP; NEW | STPBRZ | 9030159 | LESLIE | 11-10104 | CR 1271 |  | 0.016 |  | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES ON CR-1271 OVER MIDDLE FORK. (066C00079N) | C |  | STP | 2020 | 720911 | 720911 |  |  | 0 |  |  | OBLIGATED |  | 649950 | 649950 | 2019 | 4TH QUARTER
STIP | [9 empty] | LETCHER | 12-199.1 | US 119 |  | 17.005 | 19.038 | RELIABILITY | RECONSTRUCTION(O) |  | R |  | NH | 2021 | 1300000 | 1040000 |  |  | 260000 | [5 empty] | 0
STIP | [9 empty] | LETCHER | 12-199.1 | US 119 |  | 17.005 | 19.038 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE US-119 FROM NORTH OF KY-15 TO BRASS DRIVE (SOUTH).(16CCN)(18CCR) | U |  | NH | 2021 | 1200000 | 960000 |  |  | 240000 | [5 empty] | 0
STIP | [9 empty] | LETCHER | 12-199.15 | US 119 |  | 17.964 | 18.826 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE US-119 FROM KY 2034/COUGAR DRIVE TO BRASS DRIVE (SOUTH).(16CCN)(SEE 12-199.10 FOR D, R, U)(18CCR) | C |  | NH | 2021 | 6000000 | 4800000 |  |  | 1200000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.095 | 2019-07-02 | ADD PROJECT TO STIP; PARENT NO. 911.08; NEW | HSIP | 5335020 | LETCHER | 12-965 | KY 931 |  | 0.679 | 5.505 | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALL GUARDRAIL ALONG KY 931 FROM LARRY'S ROAD (MP 0.679) TO PACK DRIVE (MP 5.505). (2018BOP) | C |  | SAF | 2019 | 425000 | 425000 |  |  | 0 |  |  | OBLIGATED | 478354 |  | 478354 | 2019 | 4TH QUARTER
STIP | [9 empty] | LETCHER | 12-1113 | KY 2034C | 0.04 | 0.006 | 0.046 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON KY 2034C OVER N FORK KY RIVER 0.02 E OF US 119 067B00121N | C |  | BR/STP | 2019 | 973000 | 603260 |  |  | 369740 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.126 | 2019-09-20 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 1203408 | LETCHER | 12-1113 | KY 2034C | 0.04 | 0.006 | 0.046 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON KY 2034C OVER N FORK KY RIVER 0.02 E OF US 119 067B00121N | C |  | STP | 2019 | 1355000 | 1355000 |  |  | 0 |  |  | OBLIGATED |  | 1353000 | 1353000 | 2019 | 4TH QUARTER
STIP | [9 empty] | LETCHER | 12-1120 | KY 3404 | 0.012 | 0.782 | 0.794 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER POOR FORK OF CUMBERLAND RIVER ON KY 3404 100 FT SOUTH OF US 119. (067B00114N) | C |  | BR/STP | 2020 | 420000 | 260400 |  |  | 159600 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.126 | 2019-09-20 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 1203397 | LETCHER | 12-1120 | KY 3404 | 0.012 | 0.782 | 0.794 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER POOR FORK OF CUMBERLAND RIVER ON KY 3404 100 FT SOUTH OF US 119. (067B00114N) | C |  | STP | 2019 | 815000 | 815000 |  |  | 0 |  |  | OBLIGATED |  | 1159269 | 1159269 | 2019 | 4TH QUARTER
STIP | [9 empty] | LETCHER | 12-1125 | CR 1226 | 0.008 | 0.006 | 0.014 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON HAMPTON BRANCH (CR 1226) (MP 0.01) OVER COWAN CREEK. 067C00021N | C |  | BR/STP | 2020 | 385000 | 238700 |  |  | 146300 | [5 empty] | 0
STIP | [9 empty] | LETCHER | 12-1126 | CR 1225 |  | 0.03 | 0.038 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON CR-1225 (0.034) OVER COWAN CREEK. 067C00020N | D |  | BR/STP | 2019 | 420000 | 260400 |  |  | 159600 | [5 empty] | 0
STIP | [9 empty] | LETCHER | 12-1126 | CR 1225 |  | 0.03 | 0.038 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON CR-1225 (0.034) OVER COWAN CREEK. 067C00020N | C |  | BR/STP | 2020 | 385000 | 238700 |  |  | 146300 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.075 | 2019-05-28 | INCREASE FUNDS BAESD ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030122 | LETCHER | 12-1126 | CR 1225 |  | 0.03 | 0.038 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON CR-1225 (0.034) OVER COWAN CREEK. 067C00020N | C |  | STP | 2020 | 429000 | 429000 |  |  | 0 |  |  | OBLIGATED |  | 778414.4 | 778414.4 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.3 | 2021-05-28 | ADD D PHASE TO STIP; NEW |  |  | LETCHER | 12-8702 | KY 805 |  | 9.176 | 9.247 | RELIABILITY | CONGESTION MITIGTN(O) | IMPROVE THE EXISTING ROADWAY TO MEET CURRENT STANDARDS AND IMPROVE CONGESTION INTO AND OUT OF JENKINS BETWEEN MP 9.176 AND MP 9.247. | D |  | STP | 2021 | 220000 | 220000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.291 | 2021-04-23 | ADD C PHASE TO STIP; PARENT NO. 99-911.08; NEW |  |  | LETCHER | 12-9011 | US 23 |  | 0 | 1.5 | SAFETY | SAFETY-HAZARD ELIM(P) | IMPROVE PAVEMENT FRICTION ON US 23 BETWEEN US 119 AND THE VIRGINIA STATE LINE BY MILLING AND OVERLAYING A 1.5" SURFACE COURSE USING A POLISH RESISTANT ASPHALT MIX IN BOTH DIRECTIONS OF TRAVEL. (2018BOP) | C |  | SAF | 2021 | 519000 | 519000 | [8 empty] | 0
STIP | [9 empty] | LETCHER | 12-10004 | KY 805 |  | 2.989 | 2.997 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-805 BRIDGE OVER POTTERS FORK. (067B00022N) | D |  | BR/STP | 2019 | 210000 | 130200 |  |  | 79800 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030146 | LETCHER | 12-10004 | KY 805 |  | 2.989 | 2.997 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-805 BRIDGE OVER POTTERS FORK. (067B00022N) | C |  | BR/STP | 2020 | 616840 | 382440.8 |  |  | 234399.2 |  |  | OBLIGATED |  | 511998 | 511998 | 2019 | 3RD QUARTER
STIP | [9 empty] | LETCHER | 12-10005 | KY 2034 |  | 2.369 | 2.375 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-2034 BRIDGE OVER CRAFTS COLLY CREEK. (067B00069N) | D |  | BR/STP | 2019 | 140000 | 86800 |  |  | 53200 | [5 empty] | 0
STIP | [9 empty] | LETCHER | 12-10005 | KY 2034 |  | 2.369 | 2.375 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-2034 BRIDGE OVER CRAFTS COLLY CREEK. (067B00069N) | C |  | BR/STP | 2020 | 406105 | 251785.1 |  |  | 154319.9 | [5 empty] | 0
STIP | [9 empty] | LETCHER | 12-10006 | CR 1433 |  | 0.005 | 0.015 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF CORNFIELD DR BRIDGE OVER BOONE FORK. (067C00004N) | D |  | BR/STP | 2019 | 140000 | 86800 |  |  | 53200 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030076 | LETCHER | 12-10006 | CR 1433 |  | 0.005 | 0.015 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF CORNFIELD DR BRIDGE OVER BOONE FORK. (067C00004N) | C |  | BR/STP | 2020 | 427840 | 265260.8 |  |  | 162579.2 |  |  | OBLIGATED |  | 308010 | 308010 | 2019 | 3RD QUARTER
STIP | [9 empty] | LETCHER | 12-10007 | CR 1386 |  | 0.003 | 0.025 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF TURKEY CRK BRIDGE OVER TURKEY CREEK. (067C00050N)(SD) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [9 empty] | LETCHER | 12-10007 | CR 1386 |  | 0.003 | 0.025 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF TURKEY CRK BRIDGE OVER TURKEY CREEK. (067C00050N)(SD) | C |  | BR/STP | 2020 | 697000 | 432140 |  |  | 264860 | [5 empty] | 0
STIP | [9 empty] | LETCHER | 12-10017 | KY 7 |  | 2.602 | 2.68 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 7 BRIDGE OVER CSX RR & N FK KY RIVER. (067B00038N) | D |  | BR/STP | 2019 | 525000 | 325500 |  |  | 199500 | [5 empty] | 0
STIP | [9 empty] | LETCHER | 12-10017 | KY 7 |  | 2.602 | 2.68 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 7 BRIDGE OVER CSX RR & N FK KY RIVER. (067B00038N) | C |  | BR/STP | 2020 | 4900000 | 3038000 |  |  | 1862000 | [5 empty] | 0
STIP | [9 empty] | LETCHER | 12-10018 | KY 343 |  | 0.458 | 0.464 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 343 BRIDGE OVER WRIGHT FORK. (067B00078N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [9 empty] | LETCHER | 12-10018 | KY 343 |  | 0.458 | 0.464 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 343 BRIDGE OVER WRIGHT FORK. (067B00078N) | C |  | BR/STP | 2020 | 378560 | 234707.2 |  |  | 143852.8 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.075 | 2019-05-28 | INCREASE FUNDS BAESD ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030121 | LETCHER | 12-10018 | KY 343 |  | 0.458 | 0.464 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 343 BRIDGE OVER WRIGHT FORK. (067B00078N) | C |  | STP | 2020 | 638000 | 638000 |  |  | 0 |  |  | OBLIGATED |  | 917660 | 917660 | 2019 | 3RD QUARTER
STIP | [9 empty] | LETCHER | 12-10019 | CS 3000 |  | 0.03 | 0.038 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF E POTTER RD BRIDGE OVER YONTS FORK. (067C00007N) | D |  | BR/STP | 2019 | 157500 | 97650 |  |  | 59850 | [5 empty] | 0
STIP | [9 empty] | LETCHER | 12-10019 | CS 3000 |  | 0.03 | 0.038 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF E POTTER RD BRIDGE OVER YONTS FORK. (067C00007N) | C |  | BR/STP | 2020 | 372400 | 230888 |  |  | 141512 | [5 empty] | 0
STIP | [9 empty] | LETCHER | 12-10020 | CR 1149 |  | 0.049 | 0.061 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF HOLBROOK TOWN BRIDGE OVER N.FK.KENTUCKY RVR. (067C00017N) | D |  | BR/STP | 2019 | 210000 | 130200 |  |  | 79800 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030055 | LETCHER | 12-10020 | CR 1149 |  | 0.049 | 0.061 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF HOLBROOK TOWN BRIDGE OVER N.FK.KENTUCKY RVR. (067C00017N) | C |  | BR/STP | 2020 | 516810 | 320422.2 |  |  | 196387.8 |  |  | OBLIGATED |  | 510357 | 510357 | 2019 | 3RD QUARTER
STIP | [9 empty] | LETCHER | 12-10021 | CR 1799 |  | 0.006 | 0.012 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF PARADISE LN BRIDGE OVER KINGDOM COME CREEK. (067C00051N) | D |  | BR/STP | 2019 | 140000 | 86800 |  |  | 53200 | [5 empty] | 0
STIP | [9 empty] | LETCHER | 12-10021 | CR 1799 |  | 0.006 | 0.012 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF PARADISE LN BRIDGE OVER KINGDOM COME CREEK. (067C00051N) | C |  | BR/STP | 2020 | 269500 | 167090 |  |  | 102410 | [5 empty] | 0
STIP | [9 empty] | LETCHER | 12-10022 | CR 1737 |  | 0.02 | 0.034 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF ORCHARD RD BRIDGE OVER NORTH FORK KY RIVER. (067C00065N) | D |  | BR/STP | 2019 | 210000 | 130200 |  |  | 79800 | [5 empty] | 0
STIP | [9 empty] | LETCHER | 12-10022 | CR 1737 |  | 0.02 | 0.034 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF ORCHARD RD BRIDGE OVER NORTH FORK KY RIVER. (067C00065N) | C |  | BR/STP | 2020 | 655900 | 406658 |  |  | 249242 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.123 | 2019-09-06 | ADD PROJECT TO STIP; PARENT NO. 99-65.16 AND 99-65.17; NEW | STPBRZ | 9030203 | LETCHER | 12-10039 | CS 1072 |  | 0.034 |  | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES ON CAUDILL TOWN RD (CS 1072) OVER SANDLICK CREEK. (067C00031N) | C |  | BR | 2020 | 191000 | 191000 |  |  | 0 |  |  | OBLIGATED |  | 415231.28 | 415231.28 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.279 | 2021-03-05 | ADD C PHASE TO STIP; PARENT NO. 99-65.17; NEW |  |  | LETCHER | 12-10116 | CR 1716 |  |  |  | ASSET MANAGEMENT | AM-BRIDGE (P) | BRIDGE REPAIRS ON HANCOCK DR (CR-1716) OVER NORTH FORK KY RIVER. (067C00091N)(2018BOP) | C |  | STP | 2021 | 822250 | 822250 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | LETCHER | 12-20005 | US 119 | 5.63 | 17 | 22.63 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION ON US-119 FROM MILEPOINT 17.00 TO MILEPOINT 22.63 | C |  | PM/NH | 2022 | 1477000 | 1181600 |  |  | 295400 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.229 | 2020-09-14 | ADD C PHASE TO STIP; PARENT NO. 99-224.14; NEW |  |  | LETCHER | 12-20009 | KY 7 |  | 11.65 13.43 19.531 | 13.426 14.04 23.335 | RELIABILITY | AM-PAVEMENT (PRI)(P) | RESURFACING OF KY 7 (MP 11.65-13.426)(MP 13.43-14.04)(MP 19.531-23.335) IN LETCHER COUNTY, KY. | C |  | PM | 2020 | 1937762 | 1937762 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.229 | 2020-09-14 | ADD D PHASE TO STIP; NEW |  |  | LEWIS | 9-231 | KY 59 |  | 18.1 | 23.19 | RELIABILITY | NEW ROUTE(O) | NEW ROUTE FROM VANCEBURG TO KY-59 FROM POLLITT LANE IN VANCEBURG (ALT. 5B1-2 PER PLANNING STUDY). (2020CCR) | D |  | STP | 2020 | 4000000 | 4000000 |  |  | 0 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 903210 | LEWIS | 9-1090 | KY 1068 | 0.02 | 1.74 | 1.76 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER LAUREL FORK ON KY 1068 30 FT S OF DEEP HOLE BRANCH ROAD (CR 1125).(068B00057N)(16CCR)(SD) | R |  | BR/STP | 2019 | 75000 | 46500 |  |  | 28500 |  |  | OBLIGATED | 52000 |  | 52000 | 2019 | 2ND QUARTER
STIP | [7 empty] | STPBRZ | 903210 | LEWIS | 9-1090 | KY 1068 | 0.02 | 1.74 | 1.76 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER LAUREL FORK ON KY 1068 30 FT S OF DEEP HOLE BRANCH ROAD (CR 1125).(068B00057N)(16CCR)(SD) | U |  | BR/STP | 2019 | 75000 | 46500 |  |  | 28500 |  |  | OBLIGATED | 45000 |  | 45000 | 2019 | 2ND QUARTER
STIP | [7 empty] | STPBRZ | 903210 | LEWIS | 9-1090 | KY 1068 | 0.02 | 1.74 | 1.76 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER LAUREL FORK ON KY 1068 30 FT S OF DEEP HOLE BRANCH ROAD (CR 1125).(068B00057N)(16CCR)(SD) | C |  | BR/STP | 2019 | 900000 | 558000 |  |  | 342000 |  |  | OBLIGATED |  | 1316 | 1316 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.126 | 2019-09-20 | INCREASE FUNDS BASED ON NEW ESTIMATE; MOD |  |  | LEWIS | 9-1090 | KY 1068 | 0.02 | 1.74 | 1.76 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER LAUREL FORK ON KY 1068 30 FT S OF DEEP HOLE BRANCH ROAD (CR 1125).(068B00057N)(16CCR)(SD) | C |  | STP | 2019 | 1264425 | 1264425 |  |  | 0 | [5 empty] | 0
STIP | [7 empty] | STPBRO | 5234011 | LEWIS | 9-8507 | KY 57 |  | 0 | 0.031 | ASSET MANAGEMENT | AM-BRIDGE (P) | CONSTRUCT A NEW BRIDGE CROSSING THE NORTH FORK OF THE LICKING RIVER AT THE LEWIS-FLEMING COUNTY LINE. (08CCN): (068B00027N) | C |  | BR/STP | 2019 | 3640000 | 2256800 |  |  | 1383200 |  |  | OBLIGATED |  | 1316104.85 | 1316104.85 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.119 | 2019-08-23 | ADD PROJECT TO STIP; PARENT NO. 9-9007.00; NEW | HSIP | 9010383 | LEWIS | 9-9007.2 | KY 9 |  | 7.9 | 8.2 | SAFETY | SAFETY-HAZARD ELIM(P) | CONSTRUCT A RIGHT TURN SLIP LANE AND RECONSTRUCT THE FLASHING BEACON AT THE INTERSECTION OF KY 9 & KY 10 EAST OF VANCEBURG. (2018BOP) | C |  | SAF | 2019 | 430000 | 430000 |  |  | 0 |  |  | OBLIGATED |  | 430000 | 430000 | 2019 | 4TH QUARTER
STIP | [9 empty] | LEWIS | 9-10010 | KY 344 |  | 18.474 | 18.488 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-344 BRIDGE OVER GRASSY BRANCH. (068B00015N) | D |  | BR/STP | 2019 | 350000 | 217000 |  |  | 133000 | [5 empty] | 0
STIP | [9 empty] | LEWIS | 9-10010 | KY 344 |  | 18.474 | 18.488 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-344 BRIDGE OVER GRASSY BRANCH. (068B00015N) | C |  | BR/STP | 2020 | 1540000 | 954800 |  |  | 585200 | [5 empty] | 0
STIP | [9 empty] | LEWIS | 9-10023 | KY 1021 |  | 3.648 | 3.654 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 1021 BRIDGE OVER BRIERY CREEK. (068B00075N) | D |  | BR/STP | 2019 | 315000 | 195300 |  |  | 119700 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030128 | LEWIS | 9-10023 | KY 1021 |  | 3.648 | 3.654 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 1021 BRIDGE OVER BRIERY CREEK. (068B00075N) | C |  | BR/STP | 2020 | 857500 | 531650 |  |  | 325850 |  |  | OBLIGATED |  | 304640 | 304640 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.118 | 2019-08-19 | ADD C PHASE TO STIP; NEW | STPBRZ | 9030172 | LEWIS | 9-10028 | CR 1206 |  | 5.727 |  | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES ON BRIERY CREEK ROAD (CR 1206) OVER INDIAN CREEK. (068C00073N) | C |  | STP | 2020 | 754789 | 754789 |  |  | 0 |  |  | OBLIGATED |  | 425201 | 425201 | 2019 | 4TH QUARTER
STIP | [9 empty] | LEWIS | 9-20010 | KY 9 |  | 21.027 | 25.532 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION | D |  | PM/NH | 2021 | 210000 | 168000 |  |  | 42000 | [5 empty] | 0
STIP | [9 empty] | LEWIS | 9-20010 | KY 9 |  | 21.027 | 25.532 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION | C |  | PM/NH | 2021 | 2100000 | 1680000 |  |  | 420000 | [5 empty] | 0
STIP | [9 empty] | LEWIS | 9-20017 | KY 9 | 5.26 | 15.77 | 21.03 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION ON KY-9 FROM MILEPOINT 15.77 TO MILEPOINT 21.03 | C |  | PM/STP | 2022 | 1070000 | 856000 |  |  | 214000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.229 | 2020-09-14 | ADD C PHASE TO STIP; PARENT NO. 99-224.14; NEW |  |  | LEWIS | 9-20023 | KY 8 KY 57 |  | 24.016 0.5 | 32.26 5.129 | RELIABILITY | AM-PAVEMENT (PRI)(P) | RESURFACING OF KY 8 (MP 24.016-32.36) AND KY 57 (MP 0.5-5.129) IN LEWIS COUNTY, KY. | C |  | STP | 2020 | 471111 | 471111 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | LINCOLN | 8-167 | US 27 | 4.712 | 11.169 | 15.881 | RELIABILITY | RECONSTRUCTION(O) | US-27 CORRIDOR FROM SOMERSET TO LEXINGTON. IMPROVE SAFETY AND REDUCE CONGESTION ON US-27 FROM KY-1247 TO EDUCATION WAY. | R |  | NH | 2022 | 4720000 | 3776000 |  |  | 944000 | [5 empty] | 0
STIP | [9 empty] | LINCOLN | 8-167 | US 27 | 4.712 | 11.169 | 15.881 | RELIABILITY | RECONSTRUCTION(O) | US-27 CORRIDOR FROM SOMERSET TO LEXINGTON. IMPROVE SAFETY AND REDUCE CONGESTION ON US-27 FROM KY-1247 TO EDUCATION WAY. | U |  | NH | 2022 | 3000000 | 2400000 |  |  | 600000 | [5 empty] | 0
STIP | [9 empty] | LINCOLN | 8-196 | US 27 | 0.7 | 18.155 | 18.865 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE US-27 FROM KY-590 TO BELL STREET IN STANFORD. (INCLUDES NEW GOSHEN CUT-OFF ROAD)(2005HPP-KY115)(18CCR) | R |  | NH | 2019 | 1400000 | 1400000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.004 | 2018-12-13 | ADD FUNDS TO R/W PHASE; MOD | HPP | 0271084 | LINCOLN | 8-196 | US 27 | 0.7 | 18.155 | 18.865 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE US-27 FROM KY-590 TO BELL STREET IN STANFORD. (INCLUDES NEW GOSHEN CUT-OFF ROAD)(2005HPP-KY115)(18CCR) | R |  | NH | 2019 | 3800000 | 3800000 |  |  | 0 |  |  | OBLIGATED | 3723650 |  | 3723650 | 2019 | 4TH QUARTER
STIP | [7 empty] | HPP | 0271084 | LINCOLN | 8-196 | US 27 | 0.7 | 18.155 | 18.865 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE US-27 FROM KY-590 TO BELL STREET IN STANFORD. (INCLUDES NEW GOSHEN CUT-OFF ROAD)(2005HPP-KY115)(18CCR) | U |  | NH | 2019 | 1100000 | 1100000 |  |  | 0 |  |  | OBLIGATED |  | 1280000 | 1280000 | 2019 | 4TH QUARTER
STIP | [9 empty] | LINCOLN | 8-196 | US 27 | 0.7 | 18.155 | 18.865 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE US-27 FROM KY-590 TO BELL STREET IN STANFORD. (INCLUDES NEW GOSHEN CUT-OFF ROAD)(2005HPP-KY115)(18CCR) | C |  | NH | 2020 | 3250000 | 3250000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | LINCOLN | 8-196.01 | US 27 | 0.7 | 18.2 | 18.9 | RELIABILITY | PREFINANCD CONVRSN(O) | IMPROVE US-27 FROM KY-590 TO BELL STREET IN STANFORD. (INCLUDES NEW GOSHEN CUT-OFF ROAD)(2005HPP-KY115)(18CCR) | C |  | NH | 2021 | 3250000 | 2600000 |  |  | 650000 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 0803175 | LINCOLN | 8-1055 | KY 1247 | 0.04 | 17.67 | 17.71 | ASSET MANAGEMENT | AM-BRIDGE (P) | REPLACE BRIDGE ON KY 1247 OVER ST. ASAPH CREEK 0.044 S OF KY 78(SR 45.4) 069B00055N | C |  | BR/STP | 2019 | 567000 | 351540 |  |  | 215460 |  |  | OBLIGATED |  | 774500 | 774500 | 2019 | 2ND QUARTER
STIP | [9 empty] | LINCOLN | 8-1066 | CR 1043 |  | 0.635 | 0.651 | ASSET MANAGEMENT | AM-BRIDGE (P) | REPLACE BRIDGE ON CR-1043 (0.643) OVER LOGAN CREEK. (SR=20.2) 069C00008N | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [9 empty] | LINCOLN | 8-1066 | CR 1043 |  | 0.635 | 0.651 | ASSET MANAGEMENT | AM-BRIDGE (P) | REPLACE BRIDGE ON CR-1043 (0.643) OVER LOGAN CREEK. (SR=20.2) 069C00008N | C |  | BR/STP | 2020 | 497000 | 308140 |  |  | 188860 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.269 | 2021-01-22 | ADD PROJECT TO STIP; NEW |  |  | LINCOLN | 8-4315 | KY 1781 |  | 2.93 | 3.13 | SAFETY | SAF GUARDRAIL(P) | INSTALL GUARDRAIL ON KY-1781 IN LINCOLN COUNTY (2020CCR) | C |  | STP | 2021 | 55000 | 55000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.269 | 2021-01-22 | ADD PROJECT TO STIP; NEW |  |  | LINCOLN | 8-4318 | KY 1194 |  | 5 | 5.17 | SAFETY | SAF GUARDRAIL(P) | INSTALL GUARDRAIL ON KY-1194 IN LINCOLN COUNTY (2020CCR) | C |  | STP | 2021 | 40000 | 40000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.119 | 2019-08-23 | ADD PROJECT TO STIP; PARENT NO. 8-9008.00; NEW | HSIP | 1501120 | LINCOLN | 8-9008.1 | US 150 |  | 5 | 5.3 | SAFETY | SAFETY-HAZARD ELIM(P) | CONSTRUCT POSITIVE OFFSET LEFT TURN LANES AND UPDATE THE SIGNING AND STRIPING AT THE INTERSECTION OF US 150 & SPRING VALLEY DR. (2018BOP) | C |  | SAF | 2019 | 331000 | 331000 |  |  | 0 |  |  | OBLIGATED |  | 331000 | 331000 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.111 | 2019-08-02 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 5180029 | LINCOLN | 8-9014 | KY 78 |  | 2.909 | 12.168 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 78 FROM MP 2.909 TO MP 12.168 IN LINCOLN COUNTY. (2018BOP) | D |  | SAF | 2019 | 350000 | 350000 |  |  | 0 |  |  | OBLIGATED |  | 350000 | 350000 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.306 | 2021-06-16 | ADD D PHASE TO STIP; NEW |  |  | LINCOLN | 8-80000 | US 127 |  | 9.6 | 9.74 | RELIABILITY | NEW INTERCHANGE(O) | NEW TURNING LANE AT ARCADIA VIEW DRIVE(18CCN) (2020CCR) | D |  | SPP | 2021 | 110100 | 100 |  |  | 110000 | [5 empty] | 0
STIP | [9 empty] | LIVINGSTON | 1-330 | US 60 | 3.3 | 0.891 | 4.2 | RELIABILITY | RELOCATION(O) | PADUCAH-HENDERSON; RELOCATE US-60 FROM EAST OF THE TENNESSEE RIVER BRIDGE TO EAST OF RUDD-SPEES ROAD (00CCR)(12CCR)(14CCR) | R |  | NH | 2021 | 1580000 | 1264000 |  |  | 316000 | [5 empty] | 0
STIP | [9 empty] | LIVINGSTON | 1-330 | US 60 | 3.3 | 0.891 | 4.2 | RELIABILITY | RELOCATION(O) | PADUCAH-HENDERSON; RELOCATE US-60 FROM EAST OF THE TENNESSEE RIVER BRIDGE TO EAST OF RUDD-SPEES ROAD (00CCR)(12CCR)(14CCR) | U |  | NH | 2021 | 1560000 | 1248000 |  |  | 312000 | [5 empty] | 0
STIP | [9 empty] | LIVINGSTON | 1-1142 | US 60 | 0.344 | 12.524 | 12.868 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON US 60 OVER THE CUMBERLAND RIVER 0.27 MILE N OF KY 70 070B00017N. | C |  | BR/STP | 2019 | 16000000 | 9920000 |  |  | 6080000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.161 | 2020-02-21 | INCREASE FUNDS BASED ON NEW ESTIMATE; MOD | STPBRZ | 0601196 | LIVINGSTON | 1-1142 | US 60 | 0.344 | 12.524 | 12.868 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON US 60 OVER THE CUMBERLAND RIVER 0.27 MILE N OF KY 70 070B00017N. | C |  | BR/STP | 2020 | 62315000 | 62315000 |  |  | 0 |  |  | OBLIGATED | 21000000 | 28852000 | 49852000 | 2020 | 2ND QUARTER
STIP | [9 empty] | LIVINGSTON | 1-1142.01 | US 60 | 0.344 | 12.524 | 12.868 | ASSET MANAGEMENT | PREFINANCD CONVRSN(O) | ADDRESS DEFICIENCIES OF BRIDGE ON US 60 OVER THE CUMBERLAND RIVER 0.27 MILE N OF KY 70 (SR 32.7) 070B00017N (ADDITIONAL FUNDING FOR C PHASE) | C |  | BR/STP | 2020 | 16000000 | 9920000 |  |  | 6080000 | [5 empty] | 0
STIP | [9 empty] | LIVINGSTON | 1-20030 | KY 453 | 4.57 | 0 | 4.57 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION ON KY-453 FROM MILEPOINT 0.00 TO MILEPOINT 4.57 | C |  | PM/STP | 2022 | 879000 | 703200 |  |  | 175800 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.229 | 2020-09-14 | ADD C PHASE TO STIP; PARENT NO. 99-224.14; NEW |  |  | LIVINGSTON | 1-20035 | KY 453 US 62 |  | 0 1.05 | 8.282 2.815 | RELIABILITY | AM-PAVEMENT (PRI)(P) | RESURFACING OF KY 453 (MP 0.00-8.282) AND US 62 (1.05-2.815) IN LIVINGSTON COUNTY, KY. | C |  | STP | 2020 | 2174780 | 2174780 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.008 | 2018-12-26 | ADDING PROJECT TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 0801112 | LOGAN | 3-9017 | US 68 |  | 26.2 | 26.8 | SAFETY | SAFETY-HAZARD ELIM(P) | CONSTRUCTION OF A J-TURN AT THE INTERSECTION OF US 68 AND KY 73. (2018BOP) | D |  | SAF | 2019 | 100000 | 100000 |  |  | 0 |  |  | OBLIGATED | 954491 |  | 954491 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.075 | 2019-05-28 | ADD C PHASE TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 0801112 | LOGAN | 3-9017 | US 68 |  | 26.2 | 26.8 | SAFETY | SAFETY-HAZARD ELIM(P) | CONSTRUCTION OF A J-TURN AT THE INTERSECTION OF US 68 AND KY 73. (2018BOP) | C |  | SAF | 2019 | 1150000 | 1150000 |  |  | 0 |  |  | OBLIGATED | 295509 |  | 295509 | 2019 | 3RD QUARTER
STIP | [9 empty] | LOGAN | 3-10010 | US 79 |  | 4.35 | 4.85 | ASSET MANAGEMENT | AM-BRIDGE (P) | IMPROVE SAFETY AND BRIDGE CONDITION ON WHIPPORWILL CREEK BRIDGE NEAR KY-1151. BRIDGE ID 071B00025 (SD) | D |  | BR/NH | 2019 | 250000 | 155000 |  |  | 95000 | [5 empty] | 0
STIP | [9 empty] | LOGAN | 3-10010 | US 79 |  | 4.35 | 4.85 | ASSET MANAGEMENT | AM-BRIDGE (P) | IMPROVE SAFETY AND BRIDGE CONDITION ON WHIPPORWILL CREEK BRIDGE NEAR KY-1151. BRIDGE ID 071B00025 (SD) | C |  | BR/NH | 2020 | 1715000 | 1063300 |  |  | 651700 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.311 | 2021-07-21 | ADD R PHASE TO STIP; NEW |  |  | LOGAN | 3-10010 | US 79 |  | 4.35 | 4.85 | ASSET MANAGEMENT | AM-BRIDGE (P) | REPLACE BRIDGE ON US 79 TO WIDEN TO 4 LANES FOR FREIGHT MOVEMENT AND IMPROVE SAFETY. BRIDGE ID (071B00025N)(BRIDGE OVER WHIPPOORWILL CREEK) AT MP 4.65 (2020CCR). | R |  | STPBRZ | 2021 | 80000 | 80000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | LOGAN | 3-80050 | US 79 |  | 0 | 10.713 | RELIABILITY | MINOR WIDENING(O) | WIDEN US-79 TO 3 LANES FROM TODD COUNTY LINE TO INTERSECTION WITH RUSSELLVILLE BYPASS.(18CCN) | D |  | STP | 2021 | 4300000 | 3440000 |  |  | 860000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.274 | 2021-02-04 | UPDATE PROJECT DESCRIPTION AND FUND TYPE; MOD |  |  | LOGAN | 3-80050 | US 79 |  | 0 | 10.713 | RELIABILITY | MINOR WIDENING(O) | WIDEN US 79 TO FOUR LANES FROM 0.47 MILES SOUTH OF KY 1309/US 79 INTERSECTION IN TODD COUNTY TO INTERSECTION WITH RUSSELLVILLE BYPASS IN LOGAN COUNTY. | D |  | NHPP | 2021 | 4300000 | 3440000 |  |  | 860000 | [5 empty] | 0
STIP | [9 empty] | LOGAN | 3-80050 | US 79 |  | 0 | 10.713 | RELIABILITY | MINOR WIDENING(O) | WIDEN US-79 TO 3 LANES FROM TODD COUNTY LINE TO INTERSECTION WITH RUSSELLVILLE BYPASS.(18CCN) | R |  | STP | 2022 | 6500000 | 5200000 |  |  | 1300000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.274 | 2021-02-04 | UPDATE PROJECT DESCRIPTION AND FUND TYPE; MOD |  |  | LOGAN | 3-80050 | US 79 |  | 0 | 10.713 | RELIABILITY | MINOR WIDENING(O) | WIDEN US 79 TO FOUR LANES FROM 0.47 MILES SOUTH OF KY 1309/US 79 INTERSECTION IN TODD COUNTY TO INTERSECTION WITH RUSSELLVILLE BYPASS IN LOGAN COUNTY. | R |  | NHPP | 2021 | 6500000 | 5200000 |  |  | 1300000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.232 | 2020-09-17 | ADD D PHASE TO STIP; NEW |  |  | LOGAN | 3-80100 | US 79 |  |  |  | ASSET MANAGEMENT | BRIDGE REPLACEMENT(P) | REPLACE AND WIDEN BRIDGES ON US-79 AT MP 2.921 IN LOGAN COUNTY, AND MP 7.613 IN TODD COUNTY. (INCLUDES ITEM NO. 3-80102) (2020CCN) | D |  | NH | 2021 | 700000 | 560000 |  |  | 140000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.232 | 2020-09-17 | ADD R PHASE TO STIP; NEW |  |  | LOGAN | 3-80100 | US 79 |  |  |  | ASSET MANAGEMENT | BRIDGE REPLACEMENT(P) | REPLACE AND WIDEN BRIDGES ON US-79 AT MP 2.921 IN LOGAN COUNTY, AND MP 7.613 IN TODD COUNTY. (INCLUDES ITEM NO. 3-80102) (2020CCN) | R |  | NH | 2021 | 1000000 | 800000 |  |  | 200000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.232 | 2020-09-17 | ADD U PHASE TO STIP; NEW NOTE: THE BUILD GRANT WILL BE USED ON THIS PHASE |  |  | LOGAN | 3-80100 | US 79 |  |  |  | ASSET MANAGEMENT | BRIDGE REPLACEMENT(P) | REPLACE AND WIDEN BRIDGES ON US-79 AT MP 2.921 IN LOGAN COUNTY, AND MP 7.613 IN TODD COUNTY. (INCLUDES ITEM NO. 3-80102) (2020CCN) | U |  |  | 2021 | 2450000 | 1960000 |  |  | 490000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.232 | 2020-09-17 | ADD C PHASE TO STIP; NEW NOTE: THE BUILD GRANT WILL BE USED ON THIS PHASE |  |  | LOGAN | 3-80100 | US 79 |  |  |  | ASSET MANAGEMENT | BRIDGE REPLACEMENT(P) | REPLACE AND WIDEN BRIDGES ON US-79 AT MP 2.921 IN LOGAN COUNTY, AND MP 7.613 IN TODD COUNTY. (INCLUDES ITEM NO. 3-80102) (2020CCN) | C |  |  | 2022 | 14430000 | 11544000 |  |  | 2286000 | 600000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.306 | 2021-06-16 | ADD D PHASE TO STIP; NEW |  |  | LOGAN | 3-80101 | US 79 |  | 5.935 | 5.951 |  | BRIDGE REPLACEMENT(P) | REPLACE AND WIDEN TO 4 LANES BRIDGE ON US-79 AT MP 5.950 (BRIDGE OVER DRY FORK) (2020CCN) | D |  | SPP | 2021 | 300100 | 100 |  |  | 300000 | [5 empty] | 0
STIP | [9 empty] | LYON | 1-187.5 | US 641 | 4.25 | 0 | 4.548 | RELIABILITY | RELOCATION(O) | RELOCATE US-641 FROM US-62 NEAR EDDYVILLE TO SOUTH OF THE LYON/CALDWELL COUNTY LINE. | D |  | NH | 2019 | 2500000 | 2500000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | LYON | 1-187.5 | US 641 | 4.25 | 0 | 4.548 | RELIABILITY | RELOCATION(O) | RELOCATE US-641 FROM US-62 NEAR EDDYVILLE TO SOUTH OF THE LYON/CALDWELL COUNTY LINE. | R |  | NH | 2020 | 2000000 | 2000000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | LYON | 1-187.5 | US 641 | 4.25 | 0 | 4.548 | RELIABILITY | RELOCATION(O) | RELOCATE US-641 FROM US-62 NEAR EDDYVILLE TO SOUTH OF THE LYON/CALDWELL COUNTY LINE. | U |  | NH | 2020 | 500000 | 500000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | LYON | 1-187.5 | US 641 | 4.25 | 0 | 4.548 | RELIABILITY | RELOCATION(O) | RELOCATE US-641 FROM US-62 NEAR EDDYVILLE TO SOUTH OF THE LYON/CALDWELL COUNTY LINE. | C |  | NH | 2022 | 6000000 | 4800000 |  |  | 1200000 | [5 empty] | 0
STIP | [9 empty] | LYON | 1-187.51 | US 641 | 4.25 | 0 | 4.548 | RELIABILITY | PREFINANCD CONVRSN(O) | RELOCATE US-641 FROM US-62 NEAR EDDYVILLE TO SOUTH OF THE LYON/CALDWELL COUNTY LINE. | R |  | NH | 2021 | 2000000 | 1600000 |  |  | 400000 | [5 empty] | 0
STIP | [9 empty] | LYON | 1-187.51 | US 641 | 4.25 | 0 | 4.548 | RELIABILITY | PREFINANCD CONVRSN(O) | RELOCATE US-641 FROM US-62 NEAR EDDYVILLE TO SOUTH OF THE LYON/CALDWELL COUNTY LINE. | U |  | NH | 2021 | 500000 | 400000 |  |  | 100000 | [5 empty] | 0
STIP | [9 empty] | LYON | 1-187.6 | US 641 | 4.5 | 4.548 | 5.715 | RELIABILITY | RELOCATION(O) | RELOCATE US-641 FROM SOUTH OF THE LYON/CALDWELL COUNTY LINE TO FREDONIA, 4.5 MILES. | D |  | NH | 2019 | 1800000 | 1800000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | LYON | 1-187.6 | US 641 | 4.5 | 4.548 | 5.715 | RELIABILITY | RELOCATION(O) | RELOCATE US-641 FROM SOUTH OF THE LYON/CALDWELL COUNTY LINE TO FREDONIA, 4.5 MILES. | R |  | NH | 2020 | 2000000 | 2000000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | LYON | 1-187.6 | US 641 | 4.5 | 4.548 | 5.715 | RELIABILITY | RELOCATION(O) | RELOCATE US-641 FROM SOUTH OF THE LYON/CALDWELL COUNTY LINE TO FREDONIA, 4.5 MILES. | U |  | NH | 2020 | 800000 | 800000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | LYON | 1-187.6 | US 641 | 4.5 | 4.548 | 5.715 | RELIABILITY | RELOCATION(O) | RELOCATE US-641 FROM SOUTH OF THE LYON/CALDWELL COUNTY LINE TO FREDONIA, 4.5 MILES. | C |  | STP | 2022 | 7500000 | 6000000 |  |  | 1500000 | [5 empty] | 0
STIP | [9 empty] | LYON | 1-187.61 | US 641 | 4.5 | 4.548 | 5.715 | RELIABILITY | PREFINANCD CONVRSN(O) | RELOCATE US-641 FROM SOUTH OF THE LYON/CALDWELL COUNTY LINE TO FREDONIA, 4.5 MILES. | R |  | NH | 2021 | 2000000 | 1600000 |  |  | 400000 | [5 empty] | 0
STIP | [9 empty] | LYON | 1-187.61 | US 641 | 4.5 | 4.548 | 5.715 | RELIABILITY | PREFINANCD CONVRSN(O) | RELOCATE US-641 FROM SOUTH OF THE LYON/CALDWELL COUNTY LINE TO FREDONIA, 4.5 MILES. | U |  | NH | 2021 | 800000 | 640000 |  |  | 160000 | [5 empty] | 0
STIP | [9 empty] | LYON | 1-20009 | I 24 |  | 45.133 | 51.886 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-024 CARDINAL DIRECTION(S) FROM MILEPOINT 45.133 TO MILEPOINT 51.886 | D |  | PM/STP | 2020 | 270000 | 216000 |  |  | 54000 | [5 empty] | 0
STIP | [8 empty] | 0242076 | LYON | 1-20009 | I 24 |  | 45.133 | 51.886 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-024 CARDINAL DIRECTION(S) FROM MILEPOINT 45.133 TO MILEPOINT 51.886 | C |  | PM/STP | 2020 | 2700000 | 2160000 |  |  | 540000 |  |  | OBLIGATED | 170000 | 928900 | 1098900 | 2020 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.126 | 2019-09-20 | ADD PROJECT TO STIP. THIS PROJECT IS IN THE 2018 HIGHWAY PLAN FOR FOR FISCAL YEAR 2024 AND $4,400,000. WE ARE UPDATING THE FISCAL YEAR AND FUND AMOUNT; NEW |  |  | LYON | 1-20011 | I 24 |  | 51.89 | 54.862 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT ON I-024 BOTH DIRECTION(S) FROM MILEPOINT 51.89 (51.0 NON-CARDINAL) TO MILEPOINT 54.862 (LET W/ 2-20000, 1-20020, 1-20022) | C |  | NH | 2020 | 7350000 | 7350000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.252 | 2020-10-26 | ADD U PHASE TO STIP; NEW |  |  | MADISON | 7-235 | KY 52 |  | 1.17 | 8.015 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE KY-52 FROM WALLACE MILL ROAD TO INTERSTATE 75 AT THE DUNCANNON ROAD INTERCHANGE. (02CCR)(12CCN)(14CCR) (DESIGN/BUILD)(16CCR)(18CCR) (2020CCR) | U |  | STP | 2021 | 4080000 | 4080000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | MADISON | 7-236 | KY 595 |  | 2.565 | 2.665 | RELIABILITY | SCOPING STUDY(O) | COMPREHENSIVE TRAFFIC STUDY FOR INTERSECTION OF MAIN STREET AND BEREA COLLEGE CAMPUS, BEREA. (2005HPP-KY112)(MOA WITH BEREA). (16CCR)(LET BY CITY) | C |  | HPP | 2019 | 266952 | 266952 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | MADISON | 7-251.01 | US 25 | 3.5 | 11.903 | 15.442 | RELIABILITY | MAJOR WIDENING(O) | WIDEN US-25 FROM US-421 NORTH TO KY-876. STATE TO PROVIDE DESIGN AND PLANS, AND FUNDS FOR THIS PROJECT ARE REQUESTED TO BE PAID TO THE MADISON COUNTY FISCAL COURT, WHICH SHALL COORDINATE THE PROJECT. (2005HPP-KY110)(06CCR) | C |  | HPP | 2019 | 719921 | 719921 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.078 | 2019-06-10 | ADD PROJECT TO STIP; PARENT NO. 99-66.14; NEW | AID | 6000153 | MADISON | 7-443 | US 25 KY 876 |  | 15.4 6.4 | 20.5 9.95 | RELIABILITY | SIGNAL SYS IMPROVE(P) | DEPLOYMENT OF DEDICATED SHORT RANGE COMMUNICATION (DSRC) DEVICES AND AUTOMATED TRAFFIC SIGNAL PERFORMANCE MEASURES (ATSPM) ON US 25 (MP 15.4-20.5) AND KY 876 (MP 6.4-9.95) IN MADISON COUNTY, KY. | N |  | AID | 2019 | 625000 | 500000 |  |  | 125000 |  |  | OBLIGATED | 500000 |  | 500000 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.161 | 2020-02-21 | ADD PROJECT TO STIP; PARENT NO. 99-911.09; NEW |  |  | MADISON | 7-957 | KY 52 |  | 3.97 | 4.477 | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALLATION OF HIGH FRICTION SURFACE TREATMENT ON KY 52 FROM MP 3.970 TO MP 4.477 IN MADISON COUNTY, KY (2018BOP) | C |  | SAF | 2020 | 175000 | 175000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | MADISON | 7-1130 | US 421 | 0.04 | 2.443 | 2.483 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON BATTLEFIELD MEMORIAL HWY (US 421) OVER COWBELL CREEK AT JCT WITH HIGHWAY 21 E (KY 21)076B00021 | C |  | BR/STP | 2019 | 625000 | 387500 |  |  | 237500 | [5 empty] | 0
STIP | [7 empty] | BRZ | 0703348 | MADISON | 7-1131 | CR 1158 |  | 0.252 | 0.292 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON OLD HAYS FORK LN (CR 1158) OVER BRANCH OF HAYS FORK 0.2 MILE SE OF BATTLEFIELD MEMORIAL HWY (US 421) 076C00023N | C |  | BR/STP | 2019 | 336000 | 208320 |  |  | 127680 |  |  | OBLIGATED | 292480 | 0 | 292480 | 2019 | 3RD QUARTER
STIP | [9 empty] | MADISON | 7-1137 | KY 3376 | 0.02 | 0.279 | 0.299 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER TERRILL BRANCH ROAD ON KY 3376 IN BEREA 200 FT N OF PEACHTREE DRIVE (CS 2072).(076B00085N) | D |  | BR/STP | 2019 | 210000 | 130200 |  |  | 79800 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030034 | MADISON | 7-1137 | KY 3376 | 0.02 | 0.279 | 0.299 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER TERRILL BRANCH ROAD ON KY 3376 IN BEREA 200 FT N OF PEACHTREE DRIVE (CS 2072).(076B00085N) | C |  | BR/STP | 2020 | 857500 | 531650 |  |  | 325850 |  |  | OBLIGATED |  | 463225 | 463225 | 2019 | 2ND QUARTER
STIP | [9 empty] | MADISON | 7-1142 | CR 1017 |  | 3.397 | 3.413 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON CR-1017 (3.405) OVER MUDDY CREEK. 076C00004N (SD) | D |  | BR/STP | 2019 | 190000 | 117800 |  |  | 72200 | [5 empty] | 0
STIP | [9 empty] | MADISON | 7-1142 | CR 1017 |  | 3.397 | 3.413 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON CR-1017 (3.405) OVER MUDDY CREEK. 076C00004N (SD) | C |  | BR/STP | 2020 | 420000 | 260400 |  |  | 159600 | [5 empty] | 0
STIP | [9 empty] | MADISON | 7-1143 | CR 1044 |  | 0.003 | 0.011 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON CR-1044 (0.007) OVER BR OF MUDDY CREEK. 076C00066N | D |  | BR/STP | 2019 | 210000 | 130200 |  |  | 79800 | [5 empty] | 0
STIP | [9 empty] | MADISON | 7-1143 | CR 1044 |  | 0.003 | 0.011 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON CR-1044 (0.007) OVER BR OF MUDDY CREEK. 076C00066N | C |  | BR/STP | 2020 | 455000 | 282100 |  |  | 172900 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.075 | 2019-05-28 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD |  |  | MADISON | 7-1143 | CR 1044 |  | 0.003 | 0.011 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON CR-1044 (0.007) OVER BR OF MUDDY CREEK. 076C00066N | C |  | STP | 2020 | 680000 | 680000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.112 | 2019-08-08 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030135 | MADISON | 7-1143 | CR 1044 |  | 0.003 | 0.011 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON CR-1044 (0.007) OVER BR OF MUDDY CREEK. 076C00066N | C |  | STP | 2020 | 784875 | 784875 |  |  | 0 |  |  | OBLIGATED |  | 725870 | 725870 | 2019 | 4TH QUARTER
STIP | [7 empty] | STP | 6271016 | MADISON | 7-8403 | KY 627 | 0.12 | 0.073 | 0.193 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE SAFETY AND REDUCE CONGESTION AT THE KY-627 BRIDGE OVER I-75. (INCLUDES 7-8400) (B40)(08CCN)(10CCR)(14CCR)(16CCR)(18CCR) | C |  | NH | 2019 | 5000000 | 5000000 |  |  | 0 |  |  | OBLIGATED | 14000000 | 4043050 | 18043050 | 2019 | 2ND QUARTER
STIP | [9 empty] | MADISON | 7-8403.01 | KY 627 | 0.12 | 0.073 | 0.193 | RELIABILITY | PREFINANCD CONVRSN(O) | IMPROVE SAFETY AND REDUCE CONGESTION AT THE KY-627 BRIDGE OVER I-75. (INCLUDES 7-8400) (B40)(08CCN)(10CCR)(14CCR)(16CCR)(18CCR) | C |  | NH | 2019 | 5000000 | 5000000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.087 | 2019-06-21 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 4213013 | MADISON | 7-9013 | US 25 |  | 15.946 | 18 | SAFETY | SAFETY-HAZARD ELIM(P) | INTERSECTION AND CORRIDOR IMPROVEMENTS TO REDUCE CONFLICT POINTS AND ENHANCE SAFETY & OPERATIONS ALONG THE RICHMOND BYPASS BETWEEN MP 15.946 TO 18.000. (2018BOP) | D |  | SAF | 2019 | 550000 | 550000 |  |  | 0 |  |  | OBLIGATED |  | 550000 | 550000 | 2019 | 3RD QUARTER
STIP | [9 empty] | MADISON | 7-10001 | KY 1984 |  | 2.029 | 2.041 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-1984 BRIDGE OVER TATES CREEK. (076B00071N) | D |  | BR/STP | 2019 | 210000 | 130200 |  |  | 79800 | [5 empty] | 0
STIP | [9 empty] | MADISON | 7-10001 | KY 1984 |  | 2.029 | 2.041 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-1984 BRIDGE OVER TATES CREEK. (076B00071N) | C |  | BR/STP | 2020 | 665000 | 412300 |  |  | 252700 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.123 | 2019-09-06 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD |  |  | MADISON | 7-10001 | KY 1984 |  | 2.029 | 2.041 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-1984 BRIDGE OVER TATES CREEK. (076B00071N) | C |  | BR | 2020 | 1100000 | 1100000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | MADISON | 7-10002 | CR 1056 |  | 1.775 | 1.789 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF PEACOCK ROAD BRIDGE OVER E. FK. OTTER CREEK. (076C00011N) | D |  | BR/STP | 2019 | 210000 | 130200 |  |  | 79800 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030035 | MADISON | 7-10002 | CR 1056 |  | 1.775 | 1.789 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF PEACOCK ROAD BRIDGE OVER E. FK. OTTER CREEK. (076C00011N) | C |  | BR/STP | 2020 | 665000 | 412300 |  |  | 252700 |  |  | OBLIGATED |  | 514385 | 514385 | 2019 | 2ND QUARTER
STIP | [9 empty] | MADISON | 7-20017 | I 75 |  | 73.408 | 83.4 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-075 BOTH DIRECTION(S) FROM MILEPOINT 73.408 TO MILEPOINT 83.4 | D |  | PM/NH | 2021 | 1200000 | 960000 |  |  | 240000 | [5 empty] | 0
STIP | [9 empty] | MADISON | 7-20017 | I 75 |  | 73.408 | 83.4 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-075 BOTH DIRECTION(S) FROM MILEPOINT 73.408 TO MILEPOINT 83.4 | C |  | PM/NH | 2021 | 12000000 | 9600000 |  |  | 2400000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.229 | 2020-09-14 | ADD C PHASE TO STIP; PARENT NO. 99-224.14; NEW |  |  | MADISON | 7-20037 | KY 0876 |  | 7.508 | 9.959 | RELIABILITY | AM-PAVEMENT (INT)(P) | RESURFACING OF 076-KY-0876 -000 FROM MP7.508 TO9.959. (2020CCR) | C |  | NH | 2020 | 1149941 | 1149941 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.279 | 2021-03-05 | ADD C PHASE TO STIP; PARENT NO. 99-224.14; NEW |  |  | MADISON | 7-20043 | US 25 |  | 2.86 | 4.58 | RELIABILITY | AM-PAVEMENT (INT)(P) | Resurface US 25 from MP 2.86 to MP 4.58 in Madison County, KY. | C |  | STP | 2021 | 441139 | 441139 |  |  | 0 | [5 empty] | 0
STIP | [7 empty] | NHPP | 0061076 | MAGOFFIN | 10-126.4 | KY 9009 | 4.6 | 65 | 69.6 | RELIABILITY | MAJOR WIDENING(O) | MOUNTAIN PARKWAY CORRIDOR: WIDEN THE MOUNTAIN PARKWAY TO 4 LANES FROM 0.3MI W OF KY 3047 (65.0) TO 0.7 MI W OF MIDDLE FORK LICKING RIVER BRIDGE (69.6). (2012BOP)(14CCR)(16CCR) | C |  | NH | 2019 | 15000000 | 15000000 |  |  | 0 |  |  | OBLIGATED | 11735314 | 57572624 | 69307938 | 2019 | 4TH QUARTER
STIP | [9 empty] | MAGOFFIN | 10-126.41 | KY 9009 | 4.6 | 65 | 69.6 | RELIABILITY | PREFINANCD CONVRSN(O) | MOUNTAIN PARKWAY CORRIDOR: WIDEN THE MOUNTAIN PARKWAY TO 4 LANES FROM 0.3MI W OF KY 3047 (65.0) TO 0.7 MI W OF MIDDLE FORK LICKING RIVER BRIDGE (69.6). (2012BOP)(14CCR)(16CCN) | C |  | NH | 2020 | 10000000 | 10000000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | MAGOFFIN | 10-126.42 | KY 9009 | 4.6 | 65 | 69.6 | RELIABILITY | PREFINANCD CONVRSN(O) | MOUNTAIN PARKWAY CORRIDOR: WIDEN THE MOUNTAIN PARKWAY TO 4 LANES FROM 0.3MI W OF KY 3047 (65.0) TO 0.7 MI W OF MIDDLE FORK LICKING RIVER BRIDGE (69.6). (2012BOP)(14CCR)(16CCN) | C |  | NH | 2021 | 30000000 | 24000000 |  |  | 6000000 | [5 empty] | 0
STIP | [9 empty] | MAGOFFIN | 10-126.43 | KY 9009 | 4.6 | 65 | 69.6 | RELIABILITY | PREFINANCD CONVRSN(O) | MOUNTAIN PARKWAY CORRIDOR: WIDEN THE MOUNTAIN PARKWAY TO 4 LANES FROM 0.3MI W OF KY 3047 (65.0) TO 0.7 MI W OF MIDDLE FORK LICKING RIVER BRIDGE (69.6). (2012BOP)(14CCR)(16CCN) | C |  | NH | 2022 | 25000000 | 20000000 |  |  | 5000000 | [5 empty] | 0
[8 empty] | STPBRO | 5353004 | MAGOFFIN | 10-1098 | KY 2019 |  | 2.898 | 2.938 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 2019 OVER LICK CREEK 0.055 MILE S OF KY 3334 (SR 31.9) 077B00062N | R |  | STP | 2019 | [7 empty] | OBLIGATED | 188674.96 |  | 188674.96 | 2019 | 1ST QUARTER
STIP | [9 empty] | MAGOFFIN | 10-8901 | US 460 | 0.7 | 10 | 10.7 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE US-460 IN MAGOFFIN COUNTY AT IVY POINT HILL WEST OF SALYERSVILLE. (16CCN) | R |  | STP | 2022 | 1660000 | 1328000 |  |  | 332000 | [5 empty] | 0
STIP | [9 empty] | MAGOFFIN | 10-8901 | US 460 | 0.7 | 10 | 10.7 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE US-460 IN MAGOFFIN COUNTY AT IVY POINT HILL WEST OF SALYERSVILLE. (16CCN) | U |  | STP | 2022 | 220000 | 176000 |  |  | 44000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.152 | 2020-01-06 | ADD R PHASE TO STIP; PARENT NO. 10-9011.00 | HSIP | 5338010 | MAGOFFIN | 10-9011.1 | KY 7 |  | 18.9 | 19.28 | SAFETY | SAFETY-HAZARD ELIM(P) | MINOR WIDENING, SIGNING, STRIPING, AND SUPERELEVATION IMPROVEMENTS AT THE INTERSECTION OF KY 7 & KY 867. (2018BOP) | R |  | SAF | 2020 | 20000 | 20000 |  |  | 0 |  |  | OBLIGATED | 18000 |  | 18000 | 2020 | 1ST QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.152 | 2020-01-06 | ADD U PHASE TO STIP; PARENT NO. 10-9011.00 | HSIP | 5338010 | MAGOFFIN | 10-9011.1 | KY 7 |  | 18.9 | 19.28 | SAFETY | SAFETY-HAZARD ELIM(P) | MINOR WIDENING, SIGNING, STRIPING, AND SUPERELEVATION IMPROVEMENTS AT THE INTERSECTION OF KY 7 & KY 867. (2018BOP) | U |  | SAF | 2020 | 50000 | 50000 |  |  | 0 |  |  | OBLIGATED | 45000 |  | 45000 | 2020 | 1ST QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.197 | 2020-07-01 | ADD C PHASE TO STIP; PARENT NO. 10-9011.00; NEW |  |  | MAGOFFIN | 10-9011.1 | KY 7 |  | 18.9 | 19.28 | SAFETY | SAFETY-HAZARD ELIM(P) | MINOR WIDENING, SIGNING, STRIPING, AND SUPERELEVATION IMPROVEMENTS AT THE INTERSECTION OF KY 7 & KY 867. (2018BOP) | C |  | SAF | 2020 | 470000 | 470000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | MAGOFFIN | 10-10002 | KY 1635 |  | 5.613 | 5.621 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-1635 BRIDGE OVER OAKLEY CREEK. (077B00029N) | D |  | BR/STP | 2019 | 140000 | 86800 |  |  | 53200 | [5 empty] | 0
STIP | [9 empty] | MAGOFFIN | 10-10002 | KY 1635 |  | 5.613 | 5.621 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-1635 BRIDGE OVER OAKLEY CREEK. (077B00029N) | C |  | BR/STP | 2020 | 595000 | 368900 |  |  | 226100 | [5 empty] | 0
STIP | [9 empty] | MAGOFFIN | 10-10003 | KY 30 |  | 10.91 | 10.944 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-30 BRIDGE OVER LICKING RIVER. (077B00059N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [7 empty] | STP | 9030011 | MAGOFFIN | 10-10003 | KY 30 |  | 10.91 | 10.944 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-30 BRIDGE OVER LICKING RIVER. (077B00059N) | C |  | BR/STP | 2020 | 945000 | 585900 |  |  | 359100 |  |  | OBLIGATED | 894280 |  | 894280 | 2019 | 2ND QUARTER
STIP | [9 empty] | MAGOFFIN | 10-10014 | KY 3049 |  | 0.005 | 0.009 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 3049 BRIDGE OVER JOHNSON CREEK. (077B00069N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030086 | MAGOFFIN | 10-10014 | KY 3049 |  | 0.005 | 0.009 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 3049 BRIDGE OVER JOHNSON CREEK. (077B00069N) | C |  | BR/STP | 2020 | 402500 | 249550 |  |  | 152950 |  |  | OBLIGATED |  | 506895 | 506895 | 2019 | 3RD QUARTER
STIP | [9 empty] | MAGOFFIN | 10-10015 | CR 1032 |  | 0.022 | 0.026 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF WHITE BRANCH BRIDGE OVER STATE ROAD FORK. (077C00036N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030149 | MAGOFFIN | 10-10015 | CR 1032 |  | 0.022 | 0.026 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF WHITE BRANCH BRIDGE OVER STATE ROAD FORK. (077C00036N) | C |  | BR/STP | 2020 | 437500 | 271250 |  |  | 166250 |  |  | OBLIGATED |  | 450755 | 450755 | 2019 | 3RD QUARTER
STIP | [9 empty] | MAGOFFIN | 10-20000 | KY 9009 |  | 63.123 | 69.98 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF BERT T. COMBS MOUNTAIN PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 63.123 TO MILEPOINT 69.98 | D |  | PM/STP | 2020 | 400000 | 320000 |  |  | 80000 | [5 empty] | 0
STIP | [9 empty] | MAGOFFIN | 10-20000 | KY 9009 |  | 63.123 | 69.98 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF BERT T. COMBS MOUNTAIN PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 63.123 TO MILEPOINT 69.98 | C |  | PM/STP | 2020 | 4000000 | 3200000 |  |  | 800000 | [5 empty] | 0
STIP | [9 empty] | MAGOFFIN | 10-20013 | US 460 | 5.8 | 14.57 | 20.37 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION ON US-460 FROM MILEPOINT 14.57 TO MILEPOINT 20.37 | C |  | PM/NH | 2022 | 1485000 | 1188000 |  |  | 297000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.25 | 2020-10-22 | ADD D PHASE TO STIP; NEW |  |  | MARION | 4-8802 | KY 49 |  | 20.9 | 21.83 | RELIABILITY | SPOT IMPROVEMENTS(O) | SPOT IMPROVEMENTS ON KY-49 (MP 20.900 TO MP 21.830) AS PER THE KY-49 PLANNING STUDY. (14CCN)(18CCN) (2020CCR) | D |  | STP | 2021 | 200000 | 200000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.25 | 2020-10-22 | ADD R PHASE TO STIP; NEW |  |  | MARION | 4-8802 | KY 49 |  | 20.9 | 21.83 | RELIABILITY | SPOT IMPROVEMENTS(O) | SPOT IMPROVEMENTS ON KY-49 (MP 20.900 TO MP 21.830) AS PER THE KY-49 PLANNING STUDY. (14CCN)(18CCN) (2020CCR) | R |  | STP | 2021 | 405000 | 405000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.25 | 2020-10-22 | ADD U PHASE TO STIP; NEW |  |  | MARION | 4-8802 | KY 49 |  | 20.9 | 21.83 | RELIABILITY | SPOT IMPROVEMENTS(O) | SPOT IMPROVEMENTS ON KY-49 (MP 20.900 TO MP 21.830) AS PER THE KY-49 PLANNING STUDY. (14CCN)(18CCN) (2020CCR) | U |  | STP | 2021 | 250000 | 250000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.263 | 2020-12-11 | ADD C PHASE TO STIP; NEW |  |  | MARION | 4-8802 | KY 49 |  | 20.9 | 21.83 | RELIABILITY | SPOT IMPROVEMENTS(O) | SPOT IMPROVEMENTS ON KY-49 (MP 20.900 TO MP 21.830) AS PER THE KY-49 PLANNING STUDY. (14CCN)(18CCN) (2020CCR) | C |  | STP | 2021 | 4050000 | 4050000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | MARION | 4-8914 | KY 84 |  | 13.176 | 13.192 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON KY 84 OVER HARDINS CREEK. (16CCN)(078B00025N) | D |  | BR/STP | 2019 | 94500 | 58590 |  |  | 35910 | [5 empty] | 0
STIP | [9 empty] | MARION | 4-8914 | KY 84 |  | 13.176 | 13.192 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON KY 84 OVER HARDINS CREEK. (16CCN)(078B00025N) | C |  | BR/STP | 2019 | 616000 | 381920 |  |  | 234080 | [5 empty] | 0
STIP | [9 empty] | MARION | 4-8916 | KY 55 |  | 1.866 | 4.669 | RELIABILITY | RECONSTRUCTION(O) | HEARTLAND PARKWAY: IMPROVE MOBILITY FROM THE LEBANON BYPASS TO BOOKER ROAD (CR 1214) NEAR SPRINGFIELD. (16CCN) | R |  | NH | 2019 | 350000 | 350000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | MARION | 4-8916 | KY 55 |  | 1.866 | 4.669 | RELIABILITY | RECONSTRUCTION(O) | HEARTLAND PARKWAY: IMPROVE MOBILITY FROM THE LEBANON BYPASS TO BOOKER ROAD (CR 1214) NEAR SPRINGFIELD. (16CCN) | U |  | NH | 2019 | 350000 | 350000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | MARION | 4-8916 | KY 55 |  | 1.866 | 4.669 | RELIABILITY | RECONSTRUCTION(O) | HEARTLAND PARKWAY: IMPROVE MOBILITY FROM THE LEBANON BYPASS TO BOOKER ROAD (CR 1214) NEAR SPRINGFIELD. (16CCN) | C |  | NH | 2022 | 5000000 | 4000000 |  |  | 1000000 | [5 empty] | 0
STIP | [9 empty] | MARION | 4-10003 | CR 1127 |  | 0.149 | 0.155 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF WHITE OAK CRK RD BRIDGE OVER WHITE OAK CREEK. (078C00035N) | D |  | BR/STP | 2019 | 98000 | 60760 |  |  | 37240 | [5 empty] | 0
STIP | [9 empty] | MARION | 4-10003 | CR 1127 |  | 0.149 | 0.155 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF WHITE OAK CRK RD BRIDGE OVER WHITE OAK CREEK. (078C00035N) | C |  | BR/STP | 2020 | 217000 | 134540 |  |  | 82460 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.229 | 2020-09-14 | ADD C PHASE TO STIP; PARENT NO. 99-224.14; NEW |  |  | MARION | 4-20036 | KY 49 KY 208 KY 527 |  | 16.403 0 11.969 | 17.4 6.054 15.6 | RELIABILITY | AM-PAVEMENT(PRI)(P) | RESURFACING KY 49 FROM MP 16.403 TO 17.4; KY 208 FROM MP 0 TO 6.054; AND KY 527 FROM MP 11.969 TO 15.6 IN MARION COUNTY. | C |  | STP | 2020 | 1083798 | 1083798 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.274 | 2021-02-04 | ADD D PHASE TO STIP; NEW |  |  | MARION | 4-80152 | US 68 |  | 12.2 | 12.8 |  | CONGESTION MITIGTN(O) | REDUCE CONGESTION AT MAJOR INTERSECTION IN FRONT OF NEW SCHOOL MP 12.2 TO 12.8 (2020CCN) | D |  | STP | 2021 | 500000 | 500000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.3 | 2021-05-28 | ADD D PHASE TO STIP; NEW |  |  | MARION | 4-80153 | KY 2154 |  | 0 | 0 | NEW ROUTES | NEW ROUTE(O) | NEW BYPASS FROM KY 2154 TO BRADSFORDVILLE HWY (2020CCN) | D |  | STP | 2021 | 1000000 | 1000000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | MARSHALL | 1-398 | US 62 |  | 7.2 | 8.497 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE ACCESS AND REDUCE CONGESTION ON US-62 FROM KY-95 TO THE EXISTING FOUR-LANE HIGHWAY AT LONE VALLEY RD NEAR I-24 INTERCHANGE AND FUTURE I-69 CONNECTION. | D |  | STP | 2021 | 750000 | 600000 |  |  | 150000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.177 | 2020-04-24 | ADD C PHASE TO STIP; PARENT NO. 99-911.06; NEW |  |  | MARSHALL | 1-9009 | US 62 |  | 0 | 7.2 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ALONG US 62 BETWEEN MP 0.000 AND MP 7.200 IN MARSHALL COUNTY, KY. (2016BOP) | C |  | SAF | 2020 | 1979000 | 1979000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.126 | 2019-09-20 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 6411038 | MARSHALL | 1-9016 | US 641 |  | 0.9 | 1.55 | SAFETY | SAFETY-HAZARD ELIM(P) | CONSTRUCTION OF AN RCUT AT THE INTERSECTION OF US 641 AND KY 402 (2018BOP) | D |  | SAF | 2019 | 175000 | 175000 |  |  | 0 |  |  | OBLIGATED |  | 175000 | 175000 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.21 | 2020-07-31 | ADD C PHASE TO STIP;PARENT NO. 99-911.08; NEW |  |  | MARSHALL | 1-9016 | US 641 |  | 0.9 | 1.55 | SAFETY | SAFETY-HAZARD ELIM(P) | CONSTRUCTION OF AN RCUT AT THE INTERSECTION OF US 641 AND KY 402 (2018BOP) | C |  | SAF | 2020 | 1250000 | 1250000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.175 | 2020-04-09 | ADD D PHASE TO STIP; PARENT NO. 99-911.09; NEW |  |  | MARSHALL | 1-9019 | US 68 |  | 14 | 22.25 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON US 68 FROM MP 14.00 TO MP 22.25 IN MARSHALL COUNTY, KY. (2018BOP) | D |  | SAF | 2020 | 150000 | 150000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | MARSHALL | 1-10003 | KY 1949 |  | 7.319 | 7.329 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-1949 BRIDGE OVER SMITH CREEK. (079B00110N) | D |  | BR/STP | 2019 | 250000 | 155000 |  |  | 95000 | [5 empty] | 0
STIP | [9 empty] | MARSHALL | 1-10003 | KY 1949 |  | 7.319 | 7.329 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-1949 BRIDGE OVER SMITH CREEK. (079B00110N) | C |  | BR/STP | 2021 | 455000 | 282100 |  |  | 172900 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.075 | 2019-05-28 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030131 | MARSHALL | 1-10003 | KY 1949 |  | 7.319 | 7.329 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-1949 BRIDGE OVER SMITH CREEK. (079B00110N) | C |  | STP | 2020 | 685000 | 685000 |  |  | 0 |  |  | OBLIGATED | 493175 |  | 493175 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.123 | 2019-09-06 | ADD PROJECT TO STIP; PARENT NO. 99-65.16 AND 99-65.17; NEW |  |  | MARSHALL | 1-10028 | KY 1824 |  | 1.65 | 1.658 | ASSET MANAGEMENT | AM-BRIDGE (P) | KY-1824 OVER PEGGY ANN CREEK (079B00029N) | C |  | BR | 2020 | 415000 | 415000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.274 | 2021-02-04 | ADD C PHASE TO STIP; PARENT NO. 99-1074.08; NEW |  |  | MARSHALL | 1-10167 | KY 408 |  | 8.94 | 8.95 | ASSET MANAGEMENT | AM-BRIDGE (P) | REPLACE BRIDGE ON EGNERS FERRY RD (KY-408) LOCATED 1.1 MI EAST OF US-641 AT MP 8.94. 079B00018N | C |  | STP | 2021 | 1000000 | 1000000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.274 | 2021-02-04 | ADD C PHASE TO STIP; PARENT NO. 99-1074.08; NEW |  |  | MARSHALL | 1-10168 | KY 408 |  | 9.72 | 9.87 | ASSET MANAGEMENT | AM-BRIDGE (P) | REPLACE BRIDGE ON EGNERS FERRY RD (KY-408) LOCATED 1.5 MI EAST OF US-641 AT MP 9.79. 079B00020N | C |  | STP | 2021 | 6500000 | 6500000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | MARSHALL | 1-20016 | US 641 |  | 7.981 | 8.824 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT | D |  | PM/STP | 2019 | 75000 | 60000 |  |  | 15000 | [5 empty] | 0
STIP | [7 empty] | NHPP | 6411037 | MARSHALL | 1-20016 | US 641 |  | 7.981 | 8.824 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT | C |  | PM/STP | 2019 | 750000 | 600000 |  |  | 150000 |  |  | OBLIGATED |  | 752000 | 752000 | 2019 | 3RD QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.119 | 2019-08-23 | COST INCREASE BASED ON ENGINEERING ESTIMATE; MOD | NHPP | 6411037 | MARSHALL | 1-20016 | US 641 |  | 7.981 | 8.824 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT | C |  | NH | 2019 | 2940000 | 2940000 |  |  | 0 |  |  | OBLIGATED | 2940000 |  | 2940000 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.043 | 2019-03-29 | ADD U PHASE TO STIP; NEW |  |  | MARSHALL | 1-20016 | US 641 |  | 7.981 | 8.824 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT | U |  | PM/STP | 2019 | 940000 | 752000 |  |  | 188000 | [5 empty] | 0
STIP | [9 empty] | MARTIN | 12-1092 | CR 1324 |  | 0 | 0.028 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE AND APPROACHES ON PR-1015 OVER ROCKCASTLE CREEK (C26) 275 FEET WEST JCT. KY-3 JUST SOUTH OF CROOKED RUN ROAD. (080C00026N) | C |  | BR/STP | 2019 | 60000 | 37200 |  |  | 22800 | [5 empty] | 0
STIP | [9 empty] | MARTIN | 12-10023 | CR 1120 |  | 0.091 | 0.101 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF WILLIS DIALS RD BRIDGE OVER PIGEONROOST FORK. (080C00053N) | D |  | BR/STP | 2019 | 157500 | 97650 |  |  | 59850 | [5 empty] | 0
STIP | [9 empty] | MARTIN | 12-10023 | CR 1120 |  | 0.091 | 0.101 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF WILLIS DIALS RD BRIDGE OVER PIGEONROOST FORK. (080C00053N) | C |  | BR/STP | 2020 | 467880 | 290085.6 |  |  | 177794.4 | [5 empty] | 0
STIP | [9 empty] | MARTIN | 12-20006 | KY 645 | 6.11 | 0 | 6.11 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION ON KY-645 FROM MILEPOINT 0.00 TO MILEPOINT 6.11 | C |  | PM/STP | 2022 | 2015000 | 1612000 |  |  | 403000 | [5 empty] | 0
STIP | [9 empty] | MASON | 9-1095 | US 68 | 0.4 | 16.8 | 17.2 | ASSET MANAGEMENT | AM-BRIDGE (P) | REPAIR BRIDGE ON US 68 OVER LAWRENCE CREEK 0.13 MI SW OF KY 3056. (081B00067N)(16CCR) | C |  | BR/NH | 2019 | 1400000 | 868000 |  |  | 532000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.091 | 2019-06-28 | ADD ADDITIONAL FUNDS TO C PHASE; MOD | STPBRO | 5462028 | MASON | 9-1095 | US 68 | 0.4 | 16.8 | 17.2 | ASSET MANAGEMENT | AM-BRIDGE (P) | REPAIR BRIDGE ON US 68 OVER LAWRENCE CREEK 0.13 MI SW OF KY 3056. (081B00067N)(16CCR) | C |  | BR/NH | 2019 | 7350000 | 7350000 |  |  | 0 |  |  | OBLIGATED |  | 13476090 | 13476090 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.3 | 2021-05-28 | ADD C PHASE TO STIP; NEW |  |  | MASON | 9-4300 | KY 1167 |  |  |  | SAFETY | GUARDRAIL REPLCMNT(P) | GUARDRAIL PROJECT ALONG DRY CREEK ROAD (KY 1167) FROM KY 519 (MP 0.000) EXTENDING 2 MILES EAST OF KY 519 (MP 2.000) (2006BOPC). | C |  | STP | 2021 | 55000 | 55000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.3 | 2021-05-28 | ADD C PHASE TO STIP; NEW |  |  | MASON | 9-4304 | KY 10 |  | 0.3 | 0.6 | SAFETY | SAF GUARDRAIL(P) | INSTALL GUARDRAIL ON KY-10 IN MASON COUNTY | C |  | STP | 2021 | 33000 | 33000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.3 | 2021-05-28 | ADD C PHASE TO STIP; NEW |  |  | MASON | 9-4333 | KY 10 |  | 12 | 12.4 | SAFETY | SAF GUARDRAIL(P) | INSTALL GUARDRAIL ON KY-10 IN MASON COUNTY | C |  | STP | 2021 | 66000 | 66000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.3 | 2021-05-28 | ADD C PHASE TO STIP; NEW |  |  | MASON | 9-4336 | US 62 |  | 3 | 3.52 | SAFETY | SAF GUARDRAIL(P) | INSTALL GUARDRAIL ON US-62 IN MASON COUNTY | C |  | STP | 2021 | 122100 | 122100 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | MASON | 9-8906 | KY 3056 |  | 3.679 | 3.685 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON KY 3056 OVER SOUTH FORK LAWRENCE CREEK. (16CCN)(081B00020N) | C |  | BR/STP | 2020 | 1120000 | 694400 |  |  | 425600 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.021 | 2019-02-04 | ADD R PHASE TO STIP; NEW |  |  | MASON | 9-8906 | KY 3056 |  | 3.679 | 3.685 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON KY 3056 OVER SOUTH FORK LAWRENCE CREEK. (16CCN)(081B00020N) | R |  | STP | 2019 | 33350 | 33350 |  |  | 0 |  |  | OBLIGATED | 33350 |  | 33350 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.021 | 2019-02-04 | ADD U PHASE TO STIP; NEW |  |  | MASON | 9-8906 | KY 3056 |  | 3.679 | 3.685 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON KY 3056 OVER SOUTH FORK LAWRENCE CREEK. (16CCN)(081B00020N) | U |  | STP | 2019 | 50000 | 50000 |  |  | 0 |  |  | OBLIGATED | 50000 |  | 50000 | 2019 | 2ND QUARTER
STIP | [9 empty] | MASON | 9-8910 | CR 1124 |  | 0.007 | 0.029 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF THE BRIDGE ON DAVIS LANE. (16CCN)(081C00022N) | C |  | BR/STP | 2020 | 875000 | 542500 |  |  | 332500 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.103 | 2019-07-29 | UPDATE FUNDING AMOUNT; MOD | STPBRZ | 0903208 | MASON | 9-8910 | CR 1124 |  | 0.007 | 0.029 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF THE BRIDGE ON DAVIS LANE. (16CCN)(081C00022N) | C |  | BR/STP | 2019 | 1050000 | 1050000 |  |  | 0 |  |  | OBLIGATED | 1043050 | 305907 | 1348957 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.013 | 2019-01-10 | ADD R PHASE TO STIP; NEW | STPBRZ | 0903208 | MASON | 9-8910 | CR 1124 |  | 0.007 | 0.029 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF THE BRIDGE ON DAVIS LANE. (16CCN)(081C00022N) | R |  | BR/STP | 2019 | 51500 | 51500 |  |  | 0 |  |  | OBLIGATED | 51500 |  | 51500 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.013 | 2019-01-10 | ADD U PHASE TO STIP; NEW | STPBRZ | 0903208 | MASON | 9-8910 | CR 1124 |  | 0.007 | 0.029 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF THE BRIDGE ON DAVIS LANE. (16CCN)(081C00022N) | U |  | BR/STP | 2019 | 15000 | 15000 |  |  | 0 |  |  | OBLIGATED | 15000 |  | 15000 | 2019 | 2ND QUARTER
STIP | [9 empty] | MASON | 9-8911 | CR 1019 |  | 0.189 | 0.197 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF THE BRIDGE ON KENNEDY CREEK ROAD. (16CCN)(081C00009N) | C |  | BR/STP | 2020 | 560000 | 347200 |  |  | 212800 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.263 | 2020-12-11 | ADD U PHASE TO STIP; NEW |  |  | MASON | 9-8911 | CR 1019 |  | 0.189 | 0.197 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF THE BRIDGE ON KENNEDY CREEK ROAD. (16CCN)(081C00009N) | U |  | BR/STP | 2021 | 75000 | 75000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.263 | 2020-12-11 | ADD R PHASE TO STIP; NEW |  |  | MASON | 9-8911 | CR 1019 |  | 0.189 | 0.197 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF THE BRIDGE ON KENNEDY CREEK ROAD. (16CCN)(081C00009N) | R |  | BR/STP | 2021 | 126000 | 126000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | MASON | 9-8916 | CR 1122 |  | 1.576 | 1.594 | ASSET MANAGEMENT | AM-BRIDGE (P) | REPAIR BRIDGE (081C00018N) ON DIXIE PIKE. (16CCN)(SD) | C |  | BR/STP | 2019 | 60000 | 37200 |  |  | 22800 | [5 empty] | 0
STIP | [9 empty] | MASON | 9-10013 | US 68 |  | 18.045 | 18.457 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES ON WILLIAM HARSHA BRIDGE OVER THE OHIO RIVER. JOINT PROJECT WITH OHIO. (081B00069N)(BSBP)(SD) | D |  | BR/NH | 2019 | 100000 | 62000 |  |  | 38000 | [5 empty] | 0
STIP | [9 empty] | MASON | 9-10013 | US 68 |  | 18.045 | 18.457 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES ON WILLIAM HARSHA BRIDGE OVER THE OHIO RIVER. JOINT PROJECT WITH OHIO. (081B00069N)(BSBP)(SD) | C |  | BR/NH | 2020 | 2800000 | 1736000 |  |  | 1064000 | [5 empty] | 0
STIP | [9 empty] | MASON | 9-20011 | US 68 |  | 0 | 10.3 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT | D |  | PM/NH | 2020 | 825000 | 660000 |  |  | 165000 | [5 empty] | 0
STIP | [9 empty] | MASON | 9-20011 | US 68 |  | 0 | 10.3 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT | C |  | PM/NH | 2020 | 8250000 | 6600000 |  |  | 1650000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.229 | 2020-09-14 | ADD C PHASE TO STIP; PARENT NO. 99-224.14; NEW |  |  | MASON | 9-20024 | KY 8 KY 2516 US 62 |  | 8.908 0 0 | 11.035 1.16 3.528 | RELIABILITY | AM-PAVEMENT (PRI)(P) | RESURFACING OF KY 8 FROM MP 8.908 TO 11.035; KY 2516 FROM MP 0 TO 1.16; AND US 62 FROM MP0 TO 3.528 IN MASON COUNTY. | C |  | STP | 2020 | 723209 | 723209 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | MCCRACKEN | 1-2 | I 24 | 1 | 0 | 1.067 | ASSET MANAGEMENT | AM-BRIDGE (P) | I-24 BRIDGE OVER THE OHIO RIVER @ PADUCAH (B100); JOINT PROJECT WITH ILLINOIS TO MITIGATE SCOUR (073B00100N)(BSBP)(SD) | C |  | BR/NH | 2020 | 260000 | 161200 |  |  | 98800 | [5 empty] | 0
STIP | [9 empty] | MCCRACKEN | 1-115.1 | US 60 | 1.6 | 0.4 | 1.968 | RELIABILITY | MAJOR WIDENING(O) | PADUCAH-WICKLIFFE RD: IMPROVE US-60 FROM BETHEL CHURCH ROAD TO KY-1154 (MARTIN MARIETTA) (04CCR) (TO BE LET WITH 1-115.00).(10CCR)(12CCR)(18CCR) | R |  | NH | 2019 | 1320000 | 1320000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.311 | 2021-07-21 | INCREASE FUNDS BASED ON NEW ESTIMATE; MOD |  |  | MCCRACKEN | 1-115.1 | US 60 | 1.6 | 0.4 | 1.968 | RELIABILITY | MAJOR WIDENING(O) | PADUCAH-WICKLIFFE RD: IMPROVE US-60 FROM BETHEL CHURCH ROAD TO KY-1154 (MARTIN MARIETTA) (04CCR) (TO BE LET WITH 1-115.00).(10CCR)(12CCR)(18CCR) | R |  | NH | 2021 | 2790000 | 2790000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | MCCRACKEN | 1-115.1 | US 60 | 1.6 | 0.4 | 1.968 | RELIABILITY | MAJOR WIDENING(O) | PADUCAH-WICKLIFFE RD: IMPROVE US-60 FROM BETHEL CHURCH ROAD TO KY-1154 (MARTIN MARIETTA) (04CCR) (TO BE LET WITH 1-115.00).(10CCR)(12CCR)(18CCR) | U |  | NH | 2022 | 2710000 | 2168000 |  |  | 542000 | [5 empty] | 0
STIP | [9 empty] | MCCRACKEN | 1-115.11 | US 60 | 1.6 | 0.4 | 1.968 | RELIABILITY | PREFINANCD CONVRSN(O) | PADUCAH-WICKLIFFE RD: IMPROVE US-60 FROM BETHEL CHURCH ROAD TO KY-1154 (MARTIN MARIETTA) (04CCR) (TO BE LET WITH 1-115.00).(10CCR)(12CCR)(18CCR) | R |  | NH | 2019 | 1320000 | 1320000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.257 | 2020-11-16 | ADD C PHASE TO STIP; NEW |  |  | MCCRACKEN | 1-152 | US 62 |  | 7.851 | 8.808 | RELIABILITY | MAJOR WIDENING(O) | MAJOR WIDENING OF US-62 FROM KY-998 TO PADUCAH INFORMATION AGE PARK. (12CCR) | C |  | STP | 2021 | 10087000 | 10087000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.263 | 2020-12-11 | ADD R PHASE TO STIP; PARENT NO. 1-153.00; NEW |  |  | MCCRACKEN | 1-153.10 | KY 1286 |  | 3.623 | 5 | RELIABILITY | RECONSTRUCTION(O) | Improve KY 1286 from US 45(MP 3.623) to US 62(MP 5.000)(Priority Section 1). | R |  | STP | 2021 | 3053000 | 3053000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.269 | 2021-01-22 | ADD U PHASE TO STIP; PARENT NO. 1-153.00; NEW |  |  | MCCRACKEN | 1-153.10 | KY 1286 |  | 3.623 | 5 | RELIABILITY | RECONSTRUCTION(O) | Improve KY 1286 from US 45(MP 3.623) to US 62(MP 5.000)(Priority Section 1). | U |  | STP | 2021 | 1855000 | 1855000 |  |  | 0 | [5 empty] | 0
STIP | [7 empty] | NHPP | 0601205 | MCCRACKEN | 1-154 | US 60 | 0.407 | 10.484 | 10.891 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | CONSTRUCT A DOUBLE-CROSSOVER DIAMOND INTERCHANGE ON US-60 AT THE I-24 INTERCHANGE NEAR KENTUCKY OAKS MALL. | C |  | NH | 2019 | 3960000 | 3960000 |  |  | 0 |  |  | OBLIGATED | 10097400 |  | 10097400 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.161 | 2020-02-21 | ADD PROJECT TO STIP; PARENT NO. 99-911.09; NEW |  |  | MCCRACKEN | 1-983 | KY 1286 |  | 4.134 | 4.301 | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALLATION OF HIGH FRICTION SURFACE TREATMENT ON KY 1286 FROM MP 4.134 TO MP 4.301 IN MCCRACKEN COUNTY, KY. (2018BOP) | C |  | SAF | 2020 | 50000 | 50000 |  |  | 0 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 0103375 | MCCRACKEN | 1-1152 | KY 1954 | 0.022 | 0.768 | 0.79 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER BOTTOM DITCH ON KY 1954 0.7 MILE NORTH OF KY 348 (073B00096N) . | C |  | BR/STP | 2020 | 574000 | 355880 |  |  | 218120 |  |  | OBLIGATED |  | 482590 | 482590 | 2019 | 1ST QUARTER
STIP | [9 empty] | MCCRACKEN | 1-1154 | KY 994 | 0.038 | 2.27 | 2.308 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER BRANCH OF BOTTOM DITCH ON KY 994 0.8 MI NW OF KY 348 (073B00015N)(EBRP) | D |  | BR/STP | 2019 | 168000 | 104160 |  |  | 63840 | [5 empty] | 0
STIP | [9 empty] | MCCRACKEN | 1-1154 | KY 994 | 0.038 | 2.27 | 2.308 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER BRANCH OF BOTTOM DITCH ON KY 994 0.8 MI NW OF KY 348 (073B00015N)(EBRP) | C |  | BR/STP | 2020 | 791000 | 490420 |  |  | 300580 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.021 | 2019-02-04 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030012 | MCCRACKEN | 1-1154 | KY 994 | 0.038 | 2.27 | 2.308 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER BRANCH OF BOTTOM DITCH ON KY 994 0.8 MI NW OF KY 348 (073B00015N)(EBRP) | C |  | STP | 2019 | 809000 | 809000 |  |  | 0 |  |  | OBLIGATED |  | 607882 | 607882 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.087 | 2019-06-21 | ADD PROJECT TO STIP; PARENT NO. 1-9008.00; NEW | HSIP | 9010378 | MCCRACKEN | 1-9008.3 | US 60 |  | 12.35 | 12.65 | SAFETY | SAFETY-HAZARD ELIM(P) | UPDATE THE TRAFFIC SIGNAL TO INCLUDE YELLOW ARROW, REFLECTIVE BACKPLATES, DOUBLE RED SIGNAL HEADS, AND GREEN EXTENSION LOOPS AND CLOSURE OF AN ENTRANCE NEAR THE INTERSECTION OF US 60 & KY 731. (2018BOP) | C |  | SAF | 2019 | 67000 | 67000 |  |  | 0 |  |  | OBLIGATED |  | 50000 | 50000 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.087 | 2019-06-21 | ADD PROJECT TO STIP; PARENT NO. 1-9008.00; NEW | HSIP | 9010379 | MCCRACKEN | 1-9008.4 | US 45 US 60 |  | 1.953 1.823 | 2.114 1.898 | SAFETY | SAFETY-HAZARD ELIM(P) | UPDATE THE TRAFFIC SIGNAL TO INCLUDE DOUBLE RED SIGNAL HEADS AND REFLECTIVE BACKPLATES, CONSTRUCT CURB BUMP OUTS, AND UPDATE THE SIGNING AND STRIPING NEAR THE INTERSECTION OF US 45X & US 60X. (2018BOP) | C |  | SAF | 2019 | 104000 | 104000 |  |  | 0 |  |  | OBLIGATED |  | 92000 | 92000 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.087 | 2019-06-21 | ADD PROJECT TO STIP; PARENT NO. 1-9008.00; NEW | HSIP | 9010380 | MCCRACKEN | 1-9008.5 | US 60 CS 1320 |  | 13.402 .36 | 13.575 .45 | SAFETY | SAFETY-HAZARD ELIM(P) | SIGNING AND STRIPING IMPROVEMENTS NEAR THE INTERSECTION OF US 60 & S 27TH ST. (2018BOP) | C |  | SAF | 2019 | 12000 | 12000 |  |  | 0 |  |  | OBLIGATED |  | 45000 | 45000 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.087 | 2019-06-21 | ADD PROJECT TO STIP; PARENT NO. 1-9008.00; NEW | HSIP | 9010381 | MCCRACKEN | 1-9008.6 | US 60 |  | 11.68 | 11.98 | SAFETY | SAFETY-HAZARD ELIM(P) | REBUILD THE TRAFFIC SIGNAL AND UPDATE THE STRIPING AT THE INTERSECTION OF US 60 & ALLEN LN. (2018BOP) | C |  | SAF | 2019 | 156000 | 156000 |  |  | 0 |  |  | OBLIGATED |  | 138000 | 138000 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.103 | 2019-07-29 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 1681013 | MCCRACKEN MARSHALL | 1-9014 | US 68 |  | 1.55 0 | 2.677 14 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON US 68 FROM MP 1.550 TO MP 2.677 IN MCCRACKEN COUNTY AND FROM MP 0.000 TO MP 14.000 IN MARSHALL COUNTY. (2018BOP) | D |  | SAF | 2019 | 550000 | 550000 |  |  | 0 |  |  | OBLIGATED |  | 550000 | 550000 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.103 | 2019-07-29 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 0451009 | MCCRACKEN | 1-9015 | US 45 |  | 2.2 | 3 | SAFETY | SAFETY-HAZARD ELIM(P) | CONSTRUCTION OF AN RCUT AT THE INTERSECTION OF US 45 AND KY 1288 IN MCCRACKEN COUNTY, KY. (2018BOP) | D |  | SAF | 2019 | 175000 | 175000 |  |  | 0 |  |  | OBLIGATED |  | 175000 | 175000 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.177 | 2020-04-24 | ADD C PHASE TO STIP; PARENT NO. 99-911.08; NEW |  |  | MCCRACKEN | 1-9015 | US 45 |  | 2.2 | 3 | SAFETY | SAFETY-HAZARD ELIM(P) | CONSTRUCTION OF AN RCUT AT THE INTERSECTION OF US 45 AND KY 1288 IN MCCRACKEN COUNTY, KY. (2018BOP) | C |  | SAF | 2020 | 1045000 | 1045000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.126 | 2019-09-20 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 0601209 | MCCRACKEN | 1-9017 | US 60 |  | 3.1 | 4.2 | SAFETY | SAFETY-HAZARD ELIM(P) | INTERSECTION AND CORRIDOR IMPROVEMENTS TO REDUCE CONFLICT POINTS AND ENHANCE SAFETY ALONG US 231 FROM MP 3.0-6.6. (2018BOP) | D |  | SAF | 2019 | 350000 | 350000 |  |  | 0 |  |  | OBLIGATED |  | 350000 | 350000 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.218 | 2020-08-28 | ADD C PHASE TO STIP; PARENT NO. 99-911.08; NEW |  |  | MCCRACKEN | 1-9017 | US 60 |  | 3.1 | 4.2 | SAFETY | SAFETY-HAZARD ELIM(P) | INTERSECTION AND CORRIDOR IMPROVEMENTS TO REDUCE CONFLICT POINTS AND ENHANCE SAFETY ALONG US 231 FROM MP 3.0-6.6. (2018BOP) | C |  | SAF | 2020 | 2357000 | 2357000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.175 | 2020-04-09 | ADD D PHASE TO STIP; PARENT NO. 99-911.09; NEW |  |  | MCCRACKEN | 1-9018 | I 24 |  | 4.45 | 4.8 | SAFETY | SAFETY-HAZARD ELIM(P) | CONSTRUCT AN ACCELERATION LANE ALONG I-24 FOR THE EASTBOUND ON RAMP AT EXIT 4. (2018BOP) | D |  | SAF | 2020 | 50000 | 50000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.175 | 2020-04-09 | ADD C PHASE TO STIP; PARENT NO. 99-911.09; NEW |  |  | MCCRACKEN | 1-9018 | I 24 |  | 4.45 | 4.8 | SAFETY | SAFETY-HAZARD ELIM(P) | CONSTRUCT AN ACCELERATION LANE ALONG I-24 FOR THE EASTBOUND ON RAMP AT EXIT 4. (2018BOP) | C |  | SAF | 2020 | 500000 | 500000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.276 | 2021-02-12 | INCREASE FUNDS BASED ON NEW ESTIMATE; MOD |  |  | MCCRACKEN | 1-9018 | I 24 |  | 4.45 | 4.8 | SAFETY | SAFETY-HAZARD ELIM(P) | CONSTRUCT AN ACCELERATION LANE ALONG I-24 FOR THE EASTBOUND ON RAMP AT EXIT 4. (2018BOP) | C |  | SAF | 2021 | 814110 | 814110 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | MCCRACKEN | 1-10006 | I 24 |  | 0 | 1 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES ON I-24 BRIDGE OVER OHIO RIVER. JOINT PROJECT WITH ILLINOIS. (073B00100N)(BSBP)(SD) | C |  | BR/NH | 2020 | 2000000 | 1240000 |  |  | 760000 | [5 empty] | 0
STIP | [9 empty] | MCCRACKEN | 1-10007 | I 24 |  | 0 | 1 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES WITH BRIDGE LIGHTING ON I-24 BRIDGE OVER THE OHIO RIVER. JOINT PROJECT WITH ILLINOIS. (073B000100N)(BSBP)(SD) | C |  | BR/NH | 2019 | 375000 | 232500 |  |  | 142500 | [5 empty] | 0
STIP | [9 empty] | MCCRACKEN | 1-10012 | KY 339 |  | 5.387 | 5.403 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 339 BRIDGE OVER MASSAC CREEK. (073B00058N) | D |  | BR/STP | 2019 | 210000 | 130200 |  |  | 79800 | [5 empty] | 0
STIP | [9 empty] | MCCRACKEN | 1-10012 | KY 339 |  | 5.387 | 5.403 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 339 BRIDGE OVER MASSAC CREEK. (073B00058N) | C |  | BR/STP | 2020 | 892500 | 553350 |  |  | 339150 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.017 | 2019-01-23 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030079 | MCCRACKEN | 1-10012 | KY 339 |  | 5.387 | 5.403 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 339 BRIDGE OVER MASSAC CREEK. (073B00058N) | C |  | STP | 2020 | 1056000 | 1056000 |  |  | 0 |  |  | OBLIGATED |  | 894435 | 894435 | 2019 | 3RD QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.123 | 2019-09-06 | ADD PROJECT TO STIP; PARENT NO. 99-65.16 AND 99-65.17; NEW | STPBRZ | 9030185 | MCCRACKEN | 1-10029 | KY 1565 |  | 2.89 | 2.894 | ASSET MANAGEMENT | AM-BRIDGE (P) | KY-1565 OVER BRANCH OF MASSAC CREEK (073B00006N) | C |  | BR | 2020 | 281500 | 281500 |  |  | 0 |  |  | OBLIGATED |  | 287840 | 287840 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.123 | 2019-09-06 | ADD PROJECT TO STIP; PARENT NO. 99-65.16 AND 99-65.17; NEW | STPBRZ | 9030186 | MCCRACKEN | 1-10030 | KY 725 |  | 8.263 | 8.267 | ASSET MANAGEMENT | AM-BRIDGE (P) | KY-725 OVER NEWTONS CREEK (073B00066N) | C |  | BR | 2020 | 319400 | 319400 |  |  | 0 |  |  | OBLIGATED |  | 287840 | 287840 | 2019 | 4TH QUARTER
STIP | [9 empty] | MCCRACKEN | 1-20019 | US 45 |  | 10.33 | 10.806 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT | D |  | PM/NH | 2019 | 100000 | 80000 |  |  | 20000 | [5 empty] | 0
STIP | [7 empty] | STP | 3015028 | MCCRACKEN | 1-20019 | US 45 |  | 10.33 | 10.806 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT | C |  | PM/NH | 2019 | 1000000 | 800000 |  |  | 200000 |  |  | OBLIGATED | 1502548 |  | 1502548 | 2019 | 4TH QUARTER
STIP | [9 empty] | MCCRACKEN | 1-20031 | US 60 | 5.48 | 2.22 | 7.7 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION ON US-60 FROM MILEPOINT 2.22 TO MILEPOINT 7.70 | C |  | PM/NH | 2022 | 853000 | 682400 |  |  | 170600 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.3 | 2021-05-28 | ADD C PHASE TO STIP; PARENT NO. 99-369.10; NEW |  |  | MCCRACKEN | 1-20037 | US 45X |  | 2.039 | 2.946 | RELIABILITY | AM-PAVEMENT (PRI)(P) | Resurface US 45X from MP 2.039-2.946 and US 60X from MP 0.900-2.166 in McCracken County, KY. | C |  | NHPP | 2021 | 1699500 | 1699500 |  |  | 0 | [5 empty] | 0
STIP | [7 empty] | STP | 5147022 | MCCREARY | 8-261.3 | KY 92 | 4.566 | 20.335 | 24.835 | RELIABILITY | RELOCATION(O) | IMPROVE KY-92 FROM WEST OF KY-592 TO EAST OF THE WHITLEY/MCCREARY COUNTY LINE (SECTION 2).(2014BOP)(SAME AS 11-184.20) | C |  | STP | 2019 | 8000000 | 8000000 |  |  | 0 |  |  | OBLIGATED | 17000000 | 6156206 | 23156206 | 2019 | 1ST QUARTER
STIP | [9 empty] | MCCREARY | 8-261.31 | KY 92 | 4.566 | 20.335 | 24.835 | RELIABILITY | PREFINANCD CONVRSN(O) | IMPROVE KY-92 FROM WEST OF KY-592 TO EAST OF THE WHITLEY/MCCREARY COUNTY LINE (SECTION 2).(2014BOP)(SAME AS 11-184.20) | C |  | STP | 2020 | 7000000 | 7000000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | MCCREARY | 8-261.32 | KY 92 |  | 20.335 | 24.835 | RELIABILITY | PREFINANCD CONVRSN(O) | IMPROVE KY-92 FROM WEST OF KY-592 TO EAST OF THE WHITLEY/MCCREARY COUNTY LINE (SECTION 2).(2014BOP)(SAME AS 11-184.20) | C |  | STP | 2021 | 9000000 | 7200000 |  |  | 1800000 | [5 empty] | 0
STIP | [9 empty] | MCCREARY | 8-1065 | CR 1239 | 0.04 | 0.25 | 0.29 | RELIABILITY | AM-BRIDGE (P) | BRIDGE OVER ROCK CREEK ON OLD FIDELITY-BELL FARM ROAD (CR 1239) 0.25 MI W OF ROCK CREEK ROAD (CR 1236) (074C00008N)(SR=22) | D |  | BR/STP | 2019 | 196000 | 121520 |  |  | 74480 | [5 empty] | 0
STIP | [9 empty] | MCCREARY | 8-1065 | CR 1239 | 0.04 | 0.25 | 0.29 | RELIABILITY | AM-BRIDGE (P) | BRIDGE OVER ROCK CREEK ON OLD FIDELITY-BELL FARM ROAD (CR 1239) 0.25 MI W OF ROCK CREEK ROAD (CR 1236) (074C00008N)(SR=22) | C |  | BR/STP | 2020 | 448000 | 277760 |  |  | 170240 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.119 | 2019-08-23 | ADD PROJECT TO STIP; PARENT NO. 8-9008.00; NEW | HSIP | 0271095 | MCCREARY | 8-9008.3 | US 27 KY 478 |  | 8.97 .106 | 9.22 .216 | SAFETY | SAFETY-HAZARD ELIM(P) | CONSTRUCTION OF RIGHT TURN LANES ALONG NB US 27 AND BOTH KY 478 APPROACHES, TRAFFIC SIGNAL ENHANCEMENTS AND STRIPING IMPROVEMENTS AT THE INTERSECTION OF US 27 & KY 478. (2018BOP) | C |  | SAF | 2019 | 99000 | 99000 |  |  | 0 |  |  | OBLIGATED |  | 110000 | 110000 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.119 | 2019-08-23 | ADD PROJECT TO STIP; PARENT NO. 8-9008.00; NEW | HSIP | 0271097 | MCCREARY | 8-9008.6 | US 27 |  | 7.709 | 7.809 | SAFETY | SAFETY-HAZARD ELIM(P) | SIGNAL ENHANCEMENTS AT THE INTERSECTION OF US 27 & KY 92. (2018BOP) | C |  | SAF | 2019 | 54000 | 54000 |  |  | 0 |  |  | OBLIGATED |  | 57500 | 57500 | 2019 | 4TH QUARTER
STIP | [9 empty] | MCCREARY | 8-10002 | KY 1044 |  | 4.385 | 4.399 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-1044 BRIDGE OVER MARSH CREEK. (074B00023N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030160 | MCCREARY | 8-10002 | KY 1044 |  | 4.385 | 4.399 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-1044 BRIDGE OVER MARSH CREEK. (074B00023N) | C |  | BR/STP | 2020 | 451500 | 279930 |  |  | 171570 |  |  | OBLIGATED |  | 575294 | 575294 | 2019 | 4TH QUARTER
STIP | [9 empty] | MCCREARY | 8-10003 | KY 700 |  | 14.059 | 14.091 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-700 BRIDGE OVER INDIAN CREEK. (074B00026N) | D |  | BR/STP | 2019 | 210000 | 130200 |  |  | 79800 | [5 empty] | 0
STIP | [9 empty] | MCCREARY | 8-10003 | KY 700 |  | 14.059 | 14.091 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-700 BRIDGE OVER INDIAN CREEK. (074B00026N) | C |  | BR/STP | 2020 | 1155000 | 716100 |  |  | 438900 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.03 | 2019-03-01 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030063 | MCCREARY | 8-10003 | KY 700 |  | 14.059 | 14.091 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-700 BRIDGE OVER INDIAN CREEK. (074B00026N) | C |  | STP | 2019 | 1446732 | 1446732 |  |  | 0 |  |  | OBLIGATED |  | 1656793.8 | 1656793.8 | 2019 | 2ND QUARTER
STIP | [9 empty] | MCCREARY | 8-10004 | KY 478 |  | 8.388 | 8.404 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-478 BRIDGE OVER MARSH CREEK. (074B00027N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [9 empty] | MCCREARY | 8-10004 | KY 478 |  | 8.388 | 8.404 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-478 BRIDGE OVER MARSH CREEK. (074B00027N) | C |  | BR/STP | 2020 | 521500 | 323330 |  |  | 198170 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.03 | 2019-03-01 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030064 | MCCREARY | 8-10004 | KY 478 |  | 8.388 | 8.404 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-478 BRIDGE OVER MARSH CREEK. (074B00027N) | C |  | STP | 2019 | 586437 | 586437 |  |  | 0 |  |  | OBLIGATED |  | 596773 | 596773 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.306 | 2021-06-16 | ADD D PHASE TO STIP; NEW |  |  | MCCREARY | 8-80101 | US 27 |  | 11.43 | 11.9 |  | SAFETY (P) | IMPROVE SAFETY BY CONSTRUCTING TURN LANES INTO COMMUNITY PARK AND WHITLEY CITY ELEMENTARY (2020CCN) | D |  | SPP | 2021 | 811100 | 100 |  |  | 811000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.067 | 2019-05-13 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 4311044 | MCLEAN | 2-918 | US 431 |  | 0 | 9.262 | SAFETY | SAFETY-HAZARD ELIM(P) | REPLACEMENT OF TARGETED GUARDRAIL END TREATMENTS ON US 431 FROM MP 0.000 TO MP 9.262 (2018BOP). | C |  | SAF | 2019 | 385000 | 385000 |  |  | 0 |  |  | OBLIGATED | 376500 |  | 376500 | 2019 | 3RD QUARTER
STIP | [7 empty] | STPBRZ | 4311037 | MCLEAN | 2-1078 | US 431 | 0.142 | 0 | 0.071 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF OVERFLOW STRUCTURE ON US-431 AT THE MUHLENBERG-MCLEAN CO LINE B00056N. | C |  | BR/STP | 2019 | 2500000 | 1550000 |  |  | 950000 |  |  | OBLIGATED | 2401502 |  | 2401502 | 2019 | 3RD QUARTER
STIP | [9 empty] | MCLEAN | 2-1090 | KY 2385 | 0.08 | 3.5 | 3.58 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER BRANCH OF POND DRAIN CREEK ON KY 2385 0.9 MI SW OF KY 81 (075B00066N) | D |  | BR/STP | 2019 | 308000 | 190960 |  |  | 117040 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.254 | 2020-11-06 | ADD D PHASE TO STIP; PARENT NO. 99-400.07; NEW |  |  | MCLEAN | 2-4902 | KY 81 |  | 11.4 | 11.7 | SAFETY | LIGHTING (P) | UPGRADE NAVIGATIONAL LIGHTING ON THE KY 81 CALHOUN BRIDGE (075B00076N) OVER GREEN RIVER IN MCLEAN COUNTY, KY. | D |  | STP | 2021 | 50000 | 50000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.254 | 2020-11-06 | ADD C PHASE TO STIP; PARENT NO. 99-400.07; NEW |  |  | MCLEAN | 2-4902 | KY 81 |  | 11.4 | 11.7 | SAFETY | LIGHTING (P) | UPGRADE NAVIGATIONAL LIGHTING ON THE KY 81 CALHOUN BRIDGE (075B00076N) OVER GREEN RIVER IN MCLEAN COUNTY, KY. | C |  | STP | 2021 | 160000 | 160000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.254 | 2020-11-06 | ADD D PHASE TO STIP; PARENT NO. 99-400.07; NEW |  |  | MCLEAN | 2-4903 | US 431 |  | 5.1 | 5.3 | SAFETY | LIGHTING (P) | UPGRADE NAVIGATIONAL LIGHTING ON US 431 LIVERMORE BRIDGE (075B00018N) OVER GREEN RIVER IN MCLEAN COUNTY, KY. | D |  | STP | 2021 | 50000 | 50000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.254 | 2020-11-06 | ADD C PHASE TO STIP; PARENT NO. 99-400.07; NEW |  |  | MCLEAN | 2-4903 | US 431 |  | 5.1 | 5.3 | SAFETY | LIGHTING (P) | UPGRADE NAVIGATIONAL LIGHTING ON US 431 LIVERMORE BRIDGE (075B00018N) OVER GREEN RIVER IN MCLEAN COUNTY, KY. | C |  | STP | 2021 | 232000 | 232000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.254 | 2020-11-06 | ADD D PHASE TO STIP; PARENT NO. 99-400.07; NEW |  |  | MCLEAN | 2-4904 | KY 85 |  | 12.2 | 12.4 | SAFETY | LIGHTING (P) | UPGRADE NAVIGATIONAL LIGHTING ON KY 85 ISLAND BRIDE (075B00065N) IN MCLEAN COUNTY, KY. | D |  | STP | 2021 | 50000 | 50000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.254 | 2020-11-06 | ADD C PHASE TO STIP; PARENT NO. 99-400.07; NEW |  |  | MCLEAN | 2-4904 | KY 85 |  | 12.2 | 12.4 | SAFETY | LIGHTING (P) | UPGRADE NAVIGATIONAL LIGHTING ON KY 85 ISLAND BRIDE (075B00065N) IN MCLEAN COUNTY, KY. | C |  | STP | 2021 | 167000 | 167000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.112 | 2019-08-08 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW. OWENSBORO-DAVIESS COUNTY MPO TIP FY 19-24, GROUPED PROJECTS, TABLE 1, PG 8. | HSIP | 5055015 | MCLEAN DAVIESS | 2-9013 | KY 81 KY 81 |  | 17.839 0 | 18.087 8.673 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 81 FROM MP 17.839 TO MP 18.087 IN MCLEAN COUNTY AND FROM MP 0.000 TO MP 8.673 IN DAVIESS COUNTY. (2018BOP) | D |  | SAF | 2019 | 350000 | 350000 |  |  | 0 |  |  | OBLIGATED |  | 350000 | 350000 | 2019 | 4TH QUARTER
STIP | [9 empty] | MCLEAN | 2-10007 | US 431 |  | 0.743 | 0.837 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF US-431 BRIDGE OVER DRAIN TO CYPRESS CREEK. (075B00019N) | D |  | BR/STP | 2019 | 280000 | 173600 |  |  | 106400 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030150 | MCLEAN | 2-10007 | US 431 |  | 0.743 | 0.837 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF US-431 BRIDGE OVER DRAIN TO CYPRESS CREEK. (075B00019N) | C |  | BR/STP | 2020 | 3010000 | 1866200 |  |  | 1143800 |  |  | OBLIGATED |  | 1835550 | 1835550 | 2019 | 4TH QUARTER
STIP | [9 empty] | MCLEAN | 2-10008 | KY 81 |  | 5.655 | 5.661 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-81 BRIDGE OVER SLOUGH. (075B00026N) | D |  | BR/STP | 2019 | 245000 | 151900 |  |  | 93100 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030014 | MCLEAN | 2-10008 | KY 81 |  | 5.655 | 5.661 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-81 BRIDGE OVER SLOUGH. (075B00026N) | C |  | BR/STP | 2020 | 892500 | 553350 |  |  | 339150 |  |  | OBLIGATED |  | 209220 | 209220 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.229 | 2020-09-14 | ADD C PHASE TO STIP; PARENT NO. 99-224.14; NEW |  |  | MCLEAN | 2-20053 | KY 136 |  | 18.981 | 22.62 | RELIABILITY | AM-PAVEMENT(PRI)(P) | RESURFACING OF KY 136 FROM MP 18.981 TO 22.62 IN MCLEAN COUNTY. | C |  | STP | 2020 | 333126 | 333126 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.279 | 2021-03-05 | RADCLIFF/ETOWN MPO AREA, TIP FY 18-22, GROUPED PROEJCTS, TABLE 4, PG 14; NEW |  |  | MEADE | 4-944 | KY 144 |  | 13.4 | 13.7 | RELIABILITY | SAFETY-HAZARD ELIM(P) | Installation of High Friction Surface Treatment on KY 144 from MP 13.4 to MP 13.7 in Meade County, KY. | C |  | SAF | 2021 | 102000 | 102000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | MEADE | 4-1088 | KY 823 | 0.01 | 0.54 | 0.55 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF CULVERT OVER UNNAMED STREAM ON KY 823 0.5 MILE WEST OF KY 2734.(082B00008N) | D |  | BR/STP | 2019 | 105000 | 65100 |  |  | 39900 | [5 empty] | 0
STIP | [9 empty] | MEADE | 4-1088 | KY 823 | 0.01 | 0.54 | 0.55 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF CULVERT OVER UNNAMED STREAM ON KY 823 0.5 MILE WEST OF KY 2734.(082B00008N) | C |  | BR/STP | 2020 | 560000 | 347200 |  |  | 212800 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.279 | 2021-03-05 | RADCLIFF/ETOWN MPO AREA, TIP FY 18-22, GROUPED PROEJCTS, TABLE 4, PG 14; NEW |  |  | MEADE | 4-20039 | KY 144 |  | 18.4 | 22.66 | RELIABILITY | AM-PAVEMENT(PRI)(P) | Resurface KY 144 from MP 18.40 to MP 22.66 in Meade County, KY. | C |  | STP | 2021 | 320165 | 320165 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | MENIFEE | 10-372 | KY 1274 |  | 6.5 | 8 | RELIABILITY | FOREST HIGHWAY(P) | ROCKFALL/SLOPE IMPROVEMENTS ALONG KY 1274 NORTH OF THE LONG BOW BOAT RAMP IN MENIFEE COUNTY. (2016BOP) | R |  | FH | 2019 | 100000 | 100000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | MENIFEE | 10-372 | KY 1274 |  | 6.5 | 8 | RELIABILITY | FOREST HIGHWAY(P) | ROCKFALL/SLOPE IMPROVEMENTS ALONG KY 1274 NORTH OF THE LONG BOW BOAT RAMP IN MENIFEE COUNTY. (2016BOP) | U |  | FH | 2019 | 100000 | 100000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | MENIFEE | 10-372 | KY 1274 |  | 6.5 | 8 | RELIABILITY | FOREST HIGHWAY(P) | ROCKFALL/SLOPE IMPROVEMENTS ALONG KY 1274 NORTH OF THE LONG BOW BOAT RAMP IN MENIFEE COUNTY. (2016BOP) | C |  | FH | 2019 | 2625000 | 2625000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | MENIFEE | 10-373 | KY 1274 |  | 13.28 | 13.378 | RELIABILITY | FOREST HIGHWAY(P) | ROCKFALL/SLOPE IMPROVEMENTS ALONG KY 1274 SOUTH OF THE MENIFEE/ROWAN COUNTY LINE. (2016BOP) | R |  | FH | 2019 | 250000 | 250000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | MENIFEE | 10-373 | KY 1274 |  | 13.28 | 13.378 | RELIABILITY | FOREST HIGHWAY(P) | ROCKFALL/SLOPE IMPROVEMENTS ALONG KY 1274 SOUTH OF THE MENIFEE/ROWAN COUNTY LINE. (2016BOP) | U |  | FH | 2019 | 250000 | 250000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | MENIFEE | 10-373 | KY 1274 |  | 13.28 | 13.378 | RELIABILITY | FOREST HIGHWAY(P) | ROCKFALL/SLOPE IMPROVEMENTS ALONG KY 1274 SOUTH OF THE MENIFEE/ROWAN COUNTY LINE. (2016BOP) | C |  | FH | 2019 | 4010000 | 4010000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.148 | 2019-12-03 | ADD PROJECT TO STIP; NEW |  |  | MENIFEE | 10-8802 | US 460 |  | 6.2 | 8.5 | SAFETY | SAFETY(P) | IMPROVE SAFETY AND GEOMETRICS ON US-460 FROM THE END OF ROTHWELL HILL IMPROVEMENTS TO THE BRIDGE OVER BEAVER CREEK. (14CCN)(16CCR)(18CCR) | C |  | STP | 2024 | 13530000 | 10824000 |  |  | 2706000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.254 | 2020-11-06 | UPDATE FISCAL YEAR FROM 2024 TO 2022; MOD |  |  | MENIFEE | 10-8802 | US 460 |  | 6.2 | 8.5 | SAFETY | SAFETY(P) | IMPROVE SAFETY AND GEOMETRICS ON US-460 FROM THE END OF ROTHWELL HILL IMPROVEMENTS TO THE BRIDGE OVER BEAVER CREEK. (14CCN)(16CCR)(18CCR) | C |  | STP | 2022 | 13530000 | 10824000 |  |  | 2706000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.311 | 2021-07-21 | INCREASE FUNDS BASED ON NEW ESTIMATE; MOD |  |  | MENIFEE | 10-8802 | US 460 |  | 6.2 | 8.5 | SAFETY | SAFETY(P) | IMPROVE SAFETY AND GEOMETRICS ON US-460 FROM THE END OF ROTHWELL HILL IMPROVEMENTS TO THE BRIDGE OVER BEAVER CREEK. (14CCN)(16CCR)(18CCR) | C |  | STP | 2021 | 14861000 | 14861000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | MERCER | 7-10003 | KY 1941 |  | 3.515 | 3.531 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-1941 BRIDGE OVER CHAPLIN RIVER. (084B00030N) | D |  | BR/STP | 2019 | 300000 | 186000 |  |  | 114000 | [5 empty] | 0
STIP | [9 empty] | MERCER | 7-10003 | KY 1941 |  | 3.515 | 3.531 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-1941 BRIDGE OVER CHAPLIN RIVER. (084B00030N) | C |  | BR/STP | 2020 | 682000 | 422840 |  |  | 259160 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.112 | 2019-08-08 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030164 | MERCER | 7-10003 | KY 1941 |  | 3.515 | 3.531 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-1941 BRIDGE OVER CHAPLIN RIVER. (084B00030N) | C |  | BR/STP | 2020 | 1653125 | 1653125 |  |  | 0 |  |  | OBLIGATED |  | 1058355.8 | 1058355.8 | 2019 | 4TH QUARTER
STIP | [9 empty] | MERCER | 7-10004 | CR 1322 |  | 0.247 | 0.255 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF STRATTON RD BRIDGE OVER BRUSH CREEK. (084C00029N) | D |  | BR/STP | 2019 | 192500 | 119350 |  |  | 73150 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030036 | MERCER | 7-10004 | CR 1322 |  | 0.247 | 0.255 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF STRATTON RD BRIDGE OVER BRUSH CREEK. (084C00029N) | C |  | BR/STP | 2020 | 595000 | 368900 |  |  | 226100 |  |  | OBLIGATED |  | 426215 | 426215 | 2019 | 2ND QUARTER
STIP | [9 empty] | METCALFE | 3-1087 | KY 496 | 0.02 | 11.201 | 11.221 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER OIL WELL BRANCH ON KY 496 0.5 MILE SE OF KY 533.(085B00025N) EBRP)(SD) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [9 empty] | METCALFE | 3-1087 | KY 496 | 0.02 | 11.201 | 11.221 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER OIL WELL BRANCH ON KY 496 0.5 MILE SE OF KY 533.(085B00025N) EBRP)(SD) | C |  | BR/STP | 2020 | 287000 | 177940 |  |  | 109060 | [5 empty] | 0
STIP | [9 empty] | METCALFE | 3-8706 | US 68 | 2.191 | 17.635 | 20.016 | RELIABILITY | SPOT IMPROVEMENTS(O) | SPOT IMPROVEMENTS ON US-68 FROM THE CUMBERLAND PARKWAY TO THE GREEN/METCALFE COUNTY LINE.(12CCN)(16CCN)(18CCN) | R |  | STP | 2021 | 775000 | 620000 |  |  | 155000 | [5 empty] | 0
STIP | [9 empty] | METCALFE | 3-8706 | US 68 | 2.191 | 17.635 | 20.016 | RELIABILITY | SPOT IMPROVEMENTS(O) | SPOT IMPROVEMENTS ON US-68 FROM THE CUMBERLAND PARKWAY TO THE GREEN/METCALFE COUNTY LINE.(12CCN)(16CCN)(18CCN) | U |  | STP | 2022 | 970000 | 776000 |  |  | 194000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.306 | 2021-06-16 | ADD D PHASE TO STIP; NEW |  |  | METCALFE | 3-8859 | KY 163 |  | 9.777 | 11.22 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT KY 163 AS A NEW ROUTE ON WEST SIDE OF EDMONTON FROM KY 163 AT GARY BELL RD (MP 10.0) S OF EDMONTON CROSSING US 68 (STOCKTON ST) 2000 FT WEST OF THE COURTHOUSE SQ, TO US 68 (GREENSBURG ST) AT I-CHNG WITH NUNN PKWY (MP 9.8).(14CCN)(16CCR)(18CCN) (2020CCR) | D |  | SPP | 2021 | 1090100 | 100 |  |  | 1090000 | [5 empty] | 0
STIP | [9 empty] | METCALFE | 3-10005 | KY 1243 |  | 7.493 | 7.497 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-1243 BRIDGE OVER KNOB LICK SPRINGS. (085B00034N) | D |  | BR/STP | 2019 | 157500 | 97650 |  |  | 59850 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030105 | METCALFE | 3-10005 | KY 1243 |  | 7.493 | 7.497 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-1243 BRIDGE OVER KNOB LICK SPRINGS. (085B00034N) | C |  | BR/STP | 2020 | 262500 | 162750 |  |  | 99750 |  |  | OBLIGATED |  | 267300 | 267300 | 2019 | 3RD QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.075 | 2019-05-28 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD |  |  | METCALFE | 3-10005 | KY 1243 |  | 7.493 | 7.497 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-1243 BRIDGE OVER KNOB LICK SPRINGS. (085B00034N) | C |  | STP | 2020 | 274140 | 274140 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | METCALFE | 3-10006 | CR 1108 |  | 0.181 | 0.209 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF MOSBY RIDGE RD BRIDGE OVER E FORK LITTLE BARREN RVR. (085C00005N) | D |  | BR/STP | 2019 | 210000 | 130200 |  |  | 79800 | [5 empty] | 0
STIP | [9 empty] | METCALFE | 3-10006 | CR 1108 |  | 0.181 | 0.209 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF MOSBY RIDGE RD BRIDGE OVER E FORK LITTLE BARREN RVR. (085C00005N) | C |  | BR/STP | 2020 | 896000 | 555520 |  |  | 340480 | [5 empty] | 0
STIP | [9 empty] | METCALFE | 3-20013 | LN 9008 |  | 22.357 | 36.16 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF LOUIE B. NUNN CUMBERLAND PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 22.357 TO MILEPOINT 36.16 | D |  | PM/NH | 2021 | 1100000 | 880000 |  |  | 220000 | [5 empty] | 0
STIP | [9 empty] | METCALFE | 3-20013 | LN 9008 |  | 22.357 | 36.16 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF LOUIE B. NUNN CUMBERLAND PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 22.357 TO MILEPOINT 36.16 | C |  | PM/NH | 2021 | 11000000 | 8800000 |  |  | 2200000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.229 | 2020-09-14 | ADD C PHASE TO STIP; PARENT NO. 99-224.14; NEW |  |  | METCALFE | 3-20034 | KY 90 |  | 6.945 9.27 | 9.27 11.661 | RELIABILITY | AM-PAVEMENT(PRI)(P) | RESURFACING OF KY 90 FROM MP 6.945 TO 9.27 AND FROM MP 9.27 TO 11.661 IN METCALFE COUNTY. | C |  | STP | 2020 | 1154038 | 1154038 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | MONROE | 3-7020.17 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | CONSTRUCT NEW ROUTE FOR THE EAST TOMPKINSVILLE BYPASS "SURFACING ONLY". (98CCN)(02CCR) (2002BOPC)(DESIGN "STP" FUNDING SHALL BE SUPPLEMENTAL TO THE AUTHORIZED AMOUNT ALREADY EXPENDED ON THIS PROJECT). (08CCR)(10CCR)(18CCR) | C |  | STP | 2019 | 730000 | 730000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | MONROE | 3-7020.18 |  |  |  |  | RELIABILITY | PREFINANCD CONVRSN(O) | CONSTRUCT NEW ROUTE FOR THE EAST TOMPKINSVILLE BYPASS "SURFACING ONLY". (98CCN)(02CCR) (2002BOPC)(DESIGN "STP" FUNDING SHALL BE SUPPLEMENTAL TO THE AUTHORIZED AMOUNT ALREADY EXPENDED ON THIS PROJECT). (08CCR)(10CCR)(18CCR) | C |  | STP | 2020 | 6580000 | 6580000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.026 | 2019-02-15 | ADDING PROJECT TO STIP; NEW | FBP | 6000149 | MONROE | N/A |  |  |  |  | RELIABILITY | FERRY BOAT | RESURFACING TURKEY NECK BEND (KY 214) FROM KY 100, EXTENDING TO THE CUMBERLAND RIVER FERRY APPROACH. | C |  | FBP | 2019 | 13372 | 13372 |  |  | 0 |  |  | OBLIGATED | 13372.25 |  | 13372.25 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.067 | 2019-05-13 | ADDING PROJECT TO STIP; NEW | FBP | 6000169 | MONROE | 3-161 |  |  |  |  | RELIABILITY | FERRY OPERATION (P) | MONROE COUNTY FERRY INSPECTION AND PRESERVATION. | C |  | FBP | 2019 | 90000 | 90000 |  |  | 0 |  |  | OBLIGATED | 90000 |  | 90000 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.097 | 2019-07-08 | ADDING PROJECT TO STIP; NEW | FBP | 6000164 | MONROE | 3-160 |  |  |  |  | RELIABILITY | FERRY OPERATION (P) | PURCHASE/CONSTRUCTION OF TWO NEW TUGBOATS FOR USE AT TURKEY NECK BEND FERRY. | C |  | FBP | 2019 | 355000 | 355000 |  |  | 0 |  |  | OBLIGATED | 267804 | 87196 | 355000 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.216 | 2020-08-17 | ADD C PHASE TO STIP; NEW | FBP |  | MONROE | N/A |  |  |  |  | RELIABILITY | FERRY OPERATION (P) | MONROE COUNTY FERRY LANDING REHABILITATION. | C |  | FBP | 2020 | 14697 | 11757.6 |  |  | 2939.4 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.306 | 2021-06-16 | ADD D PHASE TO STIP; NEW |  |  | MONROE | 3-8954 | KY 63 |  | 10.5 | 10.6 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT INTERSECTION OF KY 63 AND POPLAR LOG CHURCH ROAD (2020CCN) | D |  | SPP | 2021 | 250100 | 100 |  |  | 250000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.21 | 2020-07-31 | ADD D PHASE TO STIP; NEW |  |  | MONROE | 3-80003 | KY 100 |  | 14.7 | 14.9 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-100 BETWEEN MP 14.7 AND 14.9 (18CCN). | D |  | STP | 2020 | 280000 | 280000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | MONTGOMERY | 7-240.01 | KY 1991 | 1.768 | 0 | 1.768 | RELIABILITY | MAJOR WIDENING(O) | WIDEN KY 1991 FROM MAYSVILLE ROAD TO MIDLAND TRAIL INDUSTRIAL PARK, MONTGOMERY COUNTY (SEE 7-8501.00 FOR "SPB" FUNDS)(2005HPP-KY129) | C |  | HPP | 2019 | 559899 | 559899 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.252 | 2020-10-26 | ADD D PHASE TO STIP; NEW |  |  | MONTGOMERY | 7-8810 | US 60 |  | 2.007 | 4.311 | RELIABILITY | MAJOR WIDENING(O) | WIDEN EXISTING PAVEMENT & IMPROVE VERTICAL & HORIZONTAL CURVES FROM EXISTING MT STERLING BYPASS (KY 686) TO 500' W OF BENTBROOK SUBDIVISION. ADD FULL WIDTH SHOULDERS & A CENTER TURNING LANE IN CONGESTION AREAS FROM MP 2.2 TO 4.311.(14CCN)(16CCR)(18CCN) (2020CCR) | D |  | STP | 2021 | 650000 | 650000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.111 | 2019-08-02 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 5303010 | MONTGOMERY | 7-9016 | KY 213 |  | 0.675 | 5.322 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 213 FROM MP 0.675 TO MP 5.322 IN MONTGOMERY COUNTY. (2018BOP) | D |  | SAF | 2019 | 350000 | 350000 |  |  | 0 |  |  | OBLIGATED |  | 350000 | 350000 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.123 | 2019-09-06 | ADD PROJECT TO STIP; PARENT NO. 99-65.16 AND 99-65.17; NEW | STPBRZ | 9030201 | MONTGOMERY | 7-10018 | KY 1991 |  | 1.029 | 1.035 | ASSET MANAGEMENT | AM-BRIDGE (P) | KY-1991 OVER HINKSTON CR. (087B00035N) | C |  | BR | 2020 | 250000 | 250000 |  |  | 0 |  |  | OBLIGATED |  | 376050 | 376050 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.123 | 2019-09-06 | ADD PROJECT TO STIP; PARENT NO. 99-65.16 AND 99-65.17; NEW | STPBRZ | 9030202 | MONTGOMERY | 7-10019 | KY 713 |  | 6.567 | 6.571 | ASSET MANAGEMENT | AM-BRIDGE (P) | EAST LOCUST STREET OVER HINKSTON CREEK (087B00042N) | C |  | BR | 2020 | 250000 | 250000 |  |  | 0 |  |  | OBLIGATED |  | 331915 | 331915 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.203 | 2020-07-15 | ADD D PHASE TO STIP; NEW |  |  | MORGAN | 10-157 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | PROVIDE ACCESS ROAD TO TRAINING FACILITY IN WEST LIBERTY. (2020CCR) | D |  | STP | 2020 | 200000 | 200000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | MORGAN | 10-1111 | US 460 | 0.05 | 25.74 | 25.79 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER WHITE OAK CREEK ON US 460 0.5 MILE NW OF KY 1000. (088B00021N) | D |  | BR/STP | 2019 | 224000 | 138880 |  |  | 85120 | [5 empty] | 0
STIP | [9 empty] | MORGAN | 10-1111 | US 460 | 0.05 | 25.74 | 25.79 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER WHITE OAK CREEK ON US 460 0.5 MILE NW OF KY 1000. (088B00021N) | C |  | BR/STP | 2020 | 1239000 | 768180 |  |  | 470820 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.075 | 2019-05-28 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD |  |  | MORGAN | 10-1111 | US 460 | 0.05 | 25.74 | 25.79 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER WHITE OAK CREEK ON US 460 0.5 MILE NW OF KY 1000. (088B00021N) | C |  | STP | 2020 | 1284000 | 1284000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.118 | 2019-08-19 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030166 | MORGAN | 10-1111 | US 460 | 0.05 | 25.74 | 25.79 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER WHITE OAK CREEK ON US 460 0.5 MILE NW OF KY 1000. (088B00021N) | C |  | STP | 2020 | 1915524 | 1915524 |  |  | 0 |  |  | OBLIGATED |  | 977169.8 | 977169.8 | 2019 | 4TH QUARTER
STIP | [9 empty] | MORGAN | 10-8902 | KY 191 | 0.04 | 7.813 | 7.853 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON KY 191 OVER CANEY CREEK .5 MILES WEST OF KY 1162. (16CCN)(SD) | D |  | BR/STP | 2019 | 182000 | 112840 |  |  | 69160 | [5 empty] | 0
STIP | [9 empty] | MORGAN | 10-8902 | KY 191 | 0.04 | 7.813 | 7.853 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON KY 191 OVER CANEY CREEK .5 MILES WEST OF KY 1162. (16CCN)(SD) | C |  | BR/STP | 2020 | 756000 | 468720 |  |  | 287280 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.175 | 2020-04-09 | ADD D PHASE TO STIP; PARENT NO.99-911.09; NEW |  |  | MORGAN | 10-9016 | US 460 |  | 6.26 | 10.26 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON US 460 FROM MP 6.260 TO MP 10.260 IN MORGAN COUNTY, KY. (2018BOP) | D |  | SAF | 2020 | 250000 | 250000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | MORGAN | 10-10016 | US 460 |  | 27.809 | 27.815 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF US 460 BRIDGE OVER BIG SPRING BRANCH. (088B00022N) | D |  | BR/NH | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [9 empty] | MORGAN | 10-10016 | US 460 |  | 27.809 | 27.815 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF US 460 BRIDGE OVER BIG SPRING BRANCH. (088B00022N) | C |  | BR/NH | 2020 | 472500 | 292950 |  |  | 179550 | [5 empty] | 0
STIP | [9 empty] | MORGAN | 10-20001 | KY 9009 |  | 57.72 | 63.08 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF BERT T. COMBS MOUNTAIN PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 57.72 TO MILEPOINT 63.08 | D |  | PM/STP | 2019 | 210000 | 168000 |  |  | 42000 | [5 empty] | 0
STIP | [9 empty] | MORGAN | 10-20001 | KY 9009 |  | 57.72 | 63.08 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF BERT T. COMBS MOUNTAIN PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 57.72 TO MILEPOINT 63.08 | C |  | PM/STP | 2019 | 2100000 | 1680000 |  |  | 420000 | [5 empty] | 0
STIP | [9 empty] | MORGAN | 10-20014 | KY 7 | 4.25 | 3.9 | 8.14 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION ON KY-7 FROM MILEPOINT 3.90 TO MILEPOINT 8.14 | C |  | PM/STP | 2022 | 1207000 | 965600 |  |  | 241400 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.229 | 2020-09-14 | ADD C PHASE TO STIP; PARENT NO. 99-224.14; NEW |  |  | MORGAN | 10-20026 | US 460 KY 7 |  | 4.838, 18.99 3.34 | 6.438, 28.565 8.14 | RELIABILITY | AM-PAVEMENT (PRI)(P) | RESURFACING OF US 460 FROM MP 4.838 TO 6.438, US 460 FROM MP 18.99 TO 28.565, KY 7 FROM MP 3.34 TO 8.14 IN MORGAN COUNTY. | C |  | STP | 2020 | 2195513 | 2195513 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.075 | 2019-05-28 | ADD C PHASE TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 4311043 | MUHLENBERG | 2-914 | US 431 |  | 0 | 28.313 | SAFETY | SAFETY-HAZARD ELIM(P) | REPLACEMENT OF TARGETED GUARDRAIL END TREATMENTS ON US 431 FROM MP 0.000 TO MP 28.390 (2018BOP). | C |  | SAF | 2019 | 660000 | 660000 |  |  | 0 |  |  | OBLIGATED | 755810 |  | 755810 | 2019 | 3RD QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.177 | 2020-04-24 | ADD C PHASE TO STIP; PARENT NO. 99-911.08; NEW |  |  | MUHLENBERG | 2-993 | KY 171 |  | 12.1 | 1224 | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALL GUARDRAIL ALONG KY 171 (WEIR STREET) IN GREENVILLE FROM MP 12.100 TO 12.240. (2018BOP) | C |  | SAF | 2020 | 94050 | 94050 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.218 | 2020-08-28 | ADD D PHASE TO STIP; NEW |  |  | MUHLENBERG | 2-8802 | KY 181 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | WIDEN KY 181 BY FOUR FEET ON EACH SIDE FROM INTERSECTION 601 TO WENDELL FORD CENTER (14CCCN)(18CCN). | D |  | STP | 2020 | 380000 | 380000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.306 | 2021-06-16 | ADD D PHASE TO STIP; NEW |  |  | MUHLENBERG | 2-8803 | KY 2533 |  | 0 | 2.023 | RELIABILITY | RECONSTRUCTION(O) | STRAIGHTEN DEAN ROAD INTERSECTION OF 189 BYPASS TO KY 181 NORTH NEAR THE INTERSECTION WITH THE WKY PARKWAY, WENDELL FORD NATIONAL GUARD CENTER, AND JOB CORP. (14CCN)(18CCN) (2020CCR) | D |  | SPP | 2021 | 780100 | 100 |  |  | 780000 | [5 empty] | 0
STIP | [9 empty] | MUHLENBERG | 2-10009 | CR 1141 |  | 2.415 | 2.433 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF UNION RIDGE RD BRIDGE OVER ROCKY CREEK. (089C00004N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [9 empty] | MUHLENBERG | 2-10009 | CR 1141 |  | 2.415 | 2.433 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF UNION RIDGE RD BRIDGE OVER ROCKY CREEK. (089C00004N) | C |  | BR/STP | 2020 | 647500 | 401450 |  |  | 246050 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.306 | 2021-06-16 | ADD D PHASE TO STIP; NEW |  |  | MUHLENBERG | 2-80100 | KY 246 |  | 0 | 0.04 |  | SAFETY (P) | ADDRESS SAFETY AND MOBILITY ISSUES AT KY 246 INTERSECTION WITH KY 176 (2020CCN) | D |  | SPP | 2021 | 150100 | 100 |  |  | 150000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.306 | 2021-06-16 | ADD D PHASE TO STIP; NEW |  |  | MUHLENBERG | 2-80101 | KY 81 |  | 7.025 | 7.381 |  | SAFETY (P) | ADDRESS SAFETY AND MOBILITY ISSUES AT THE INTERSECTION OF KY 81 AND KY 181 (2020CCN) | D |  | SPP | 2021 | 100100 | 100 |  |  | 100000 | [5 empty] | 0
STIP | [9 empty] | NELSON | 4-396.1 | US 150 | 5.474 | 1.952 | 7.426 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE SAFETY, MOBILITY, AND GEOMETRICS ON US-150 FROM THE BLUEGRASS PARKWAY TO THE NELSON/WASHINGTON COUNTY LINE. (2016BOP)(18CCR) | D |  | STP | 2020 | 600000 | 600000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | NELSON | 4-396.12 | US 150 |  | 2.266 | 7.653 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE SAFETY, MOBILITY, AND GEOMETRICS ON US-150 FROM THE BLUEGRASS PARKWAY TO THE NELSON/WASHINGTON COUNTY LINE. (18CCN) | D |  | STP | 2021 | 600000 | 480000 |  |  | 120000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.175 | 2020-04-09 | INSTALLATION OF HIGH FRICTION SURFACE ON KY 55 FROM MP 5.3 TO MP 5.6 IN NELSON COUNTY, KY. (2018BOP) |  |  | NELSON | 4-991 | KY 55 |  | 5.3 | 5.6 | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALLATION OF HIGH FRICTION SURFACE ON KY 55 FROM MP 5.3 TO MP 5.6 IN NELSON COUNTY, KY. (2018BOP) | D |  | SAF | 2020 | 59000 | 59000 |  |  | 0 | [5 empty] | 0
STIP | [7 empty] | STPBRO | 5038104 | NELSON | 4-1078 | US 62 | 0.1 | 27.278 | 27.318 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGES ON US 62 (HINKLE CREEK) AND KY 48 IN BLOOMFIELD 090B00096N (SR 28.2) 090B00095N (12CCR) | C |  | BR/STP | 2019 | 1260000 | 781200 |  |  | 478800 |  |  | OBLIGATED | 150000 | 1484840 | 1634840 | 2020 | 1ST QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.152 | 2020-01-06 | INCREASE FUND AMOUNT BASED ON NEW ESTIMATE; MOD | STPBRO | 5038104 | NELSON | 4-1078 | US 62 | 0.1 | 27.278 | 27.318 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGES ON US 62 (HINKLE CREEK) AND KY 48 IN BLOOMFIELD 090B00096N (SR 28.2) 090B00095N (12CCR) | C |  | BR/STP | 2020 | 1800000 | 1800000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.026 | 2019-02-15 | ADD R PHASE TO STIP; NEW | STPBRO | 5038104 | NELSON | 4-1078 | US 62 | 0.1 | 27.278 | 27.318 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGES ON US 62 (HINKLE CREEK) AND KY 48 IN BLOOMFIELD 090B00096N (SR 28.2) 090B00095N (12CCR) | R |  | STP | 2019 | 147000 | 147000 |  |  | 0 |  |  | OBLIGATED | 147000 |  | 147000 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.026 | 2019-02-15 | ADD U PHASE TO STIP; NEW | STPBRO | 5038104 | NELSON | 4-1078 | US 62 | 0.1 | 27.278 | 27.318 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGES ON US 62 (HINKLE CREEK) AND KY 48 IN BLOOMFIELD 090B00096N (SR 28.2) 090B00095N (12CCR) | U |  | STP | 2019 | 415000 | 415000 |  |  | 0 |  |  | OBLIGATED | 415000 |  | 415000 | 2019 | 2ND QUARTER
STIP | [9 empty] | NELSON | 4-1089 | KY 509 | 0.018 | 3.61 | 3.628 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER FROMAN CREEK ON KY 509 0.9 MI W OF US 31E (090B00068N) | D |  | BR/STP | 2019 | 105000 | 65100 |  |  | 39900 | [5 empty] | 0
STIP | [9 empty] | NELSON | 4-1089 | KY 509 | 0.018 | 3.61 | 3.628 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER FROMAN CREEK ON KY 509 0.9 MI W OF US 31E (090B00068N) | C |  | BR/STP | 2020 | 756000 | 468720 |  |  | 287280 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.021 | 2019-02-04 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030022 | NELSON | 4-1089 | KY 509 | 0.018 | 3.61 | 3.628 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER FROMAN CREEK ON KY 509 0.9 MI W OF US 31E (090B00068N) | C |  | STP | 2019 | 967000 | 967000 |  |  | 0 |  |  | OBLIGATED |  | 794185 | 794185 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.233 | 2020-09-21 | ADD C PHASE TO STIP; PARENT NO. 4-8309; NEW |  |  | NELSON | 4-8309.1 | US 150 |  | 1.697 | 2.285 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE US-150 FROM WEST OF KY-245 THROUGH THE BLUEGRASS PARKWAY INTERCHANGE TO EAST OF LESLIE BALLARD LN (CR 1110). (06CCN)(2006BOPC)(12CCR)(14CCR)(16CCR)(18CCR) (2020CCR) | C |  | STP | 2020 | 9663500 | 9663500 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.254 | 2020-11-06 | ADD D PHASE TO STIP; NEW |  |  | NELSON | 4-8809 | US 62 KY 245 |  |  |  | RELIABILITY | NEW ROUTE(O) | NEW ROUTE BETWEEN US 62 AND KY 245 WEST OF BARDSTOWN (2020CCN) | D |  | STP | 2021 | 1000000 | 1000000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-01-25 | ADD PROJECT TO STIP; PARENT NO. 99-911.06; NEW | HSIP | 9010361 | NELSON | 4-9006.5 | KY 245 |  | 4.96 | 5.34 | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALL OVERHEAD ADVANCE WARNING FLASHERS AND UPGRADE THE SIGNAL BY INSTALLING DUAL RED HEADS AND REFLECTIVE BACKPLATES AT THE INTERSECTION OF KY 245 & KY 1430. (2018BOP) | C |  | SAF | 2019 | 135000 | 135000 |  |  | 0 |  |  | OBLIGATED | 135000 |  | 135000 | 2019 | 2ND QUARTER
STIP | [9 empty] | NELSON | 4-10004 | KY 52 |  | 12.591 | 12.621 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-52 BRIDGE OVER MONKS CREEK. (090B00033N) | D |  | BR/STP | 2019 | 105000 | 65100 |  |  | 39900 | [5 empty] | 0
STIP | [9 empty] | NELSON | 4-10004 | KY 52 |  | 12.591 | 12.621 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-52 BRIDGE OVER MONKS CREEK. (090B00033N) | C |  | BR/STP | 2020 | 1015000 | 629300 |  |  | 385700 | [5 empty] | 0
STIP | [9 empty] | NELSON | 4-10005 | CS 4003 |  | 0.43 | 0.444 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF DEPOT ST BRIDGE OVER SIMPSON CREEK. (090C00045N) | D |  | BR/STP | 2019 | 98000 | 60760 |  |  | 37240 | [5 empty] | 0
STIP | [9 empty] | NELSON | 4-10005 | CS 4003 |  | 0.43 | 0.444 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF DEPOT ST BRIDGE OVER SIMPSON CREEK. (090C00045N) | C |  | BR/STP | 2020 | 406000 | 251720 |  |  | 154280 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.021 | 2019-02-04 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030024 | NELSON | 4-10005 | CS 4003 |  | 0.43 | 0.444 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF DEPOT ST BRIDGE OVER SIMPSON CREEK. (090C00045N) | C |  | STP | 2019 | 498000 | 498000 |  |  | 0 |  |  | OBLIGATED |  | 480182 | 480182 | 2019 | 2ND QUARTER
STIP | [9 empty] | NELSON | 4-10014 | CR 1128 |  | 0.027 | 0.033 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF POTTERSHOP LOOP BRIDGE OVER ROWAN CREEK. (090C00021N) | D |  | BR/STP | 2019 | 91000 | 56420 |  |  | 34580 | [5 empty] | 0
STIP | [9 empty] | NELSON | 4-10014 | CR 1128 |  | 0.027 | 0.033 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF POTTERSHOP LOOP BRIDGE OVER ROWAN CREEK. (090C00021N) | C |  | BR/STP | 2020 | 227500 | 141050 |  |  | 86450 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.021 | 2019-02-04 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030023 | NELSON | 4-10014 | CR 1128 |  | 0.027 | 0.033 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF POTTERSHOP LOOP BRIDGE OVER ROWAN CREEK. (090C00021N) | C |  | STP | 2019 | 530000 | 530000 |  |  | 0 |  |  | OBLIGATED |  | 443141.6 | 443141.6 | 2019 | 2ND QUARTER
STIP | [9 empty] | NELSON | 4-20022 | BG 9002 |  | 24.24 | 35.15 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF MARTHA LAYNE COLLINS BLUEGRASS PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 24.24 TO MILEPOINT 35.15 | D |  | PM/NH | 2022 | 875000 | 700000 |  |  | 175000 | [5 empty] | 0
STIP | [9 empty] | NELSON | 4-20022 | BG 9002 |  | 24.24 | 35.15 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF MARTHA LAYNE COLLINS BLUEGRASS PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 24.24 TO MILEPOINT 35.15 | C |  | PM/NH | 2022 | 8750000 | 7000000 |  |  | 1750000 | [5 empty] | 0
STIP | [9 empty] | NELSON | 4-20023 | BG 9002 |  | 8.837 | 10.172 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF MARTHA LAYNE COLLINS BLUEGRASS PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 8.837 TO MILEPOINT 10.172 | D |  | PM/NH | 2019 | 110000 | 88000 |  |  | 22000 | [5 empty] | 0
STIP | [9 empty] | NELSON | 4-20023 | BG 9002 |  | 8.837 | 10.172 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF MARTHA LAYNE COLLINS BLUEGRASS PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 8.837 TO MILEPOINT 10.172 | C |  | PM/NH | 2019 | 1100000 | 880000 |  |  | 220000 | [5 empty] | 0
STIP | [9 empty] | NELSON | 4-20030 | KY 49 | 4.52 | 0 | 4.52 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION ON KY-49 FROM MILEPOINT 0.00 TO MILEPOINT 4.52 | C |  | PM/STP | 2022 | 484000 | 387200 |  |  | 96800 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.263 | 2020-12-11 | ADD D PHASE TO STIP; NEW |  |  | NELSON | 4-80050 | US 62 |  | 14.24 | 14.274 | RELIABILITY | CONGESTION MITIGTN(O) | INTERSECTION IMPROVEMENTS AT US 62 AND US 31E. (18CCN) (2020CCR) | D |  | STP | 2021 | 300000 | 300000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.321 | 2021-08-17 | ADD R PHASE TO STIP; NEW |  |  | NELSON | 4-80050 | US 62 |  | 14.24 | 14.274 | RELIABILITY | CONGESTION MITIGTN(O) | INTERSECTION IMPROVEMENTS AT US 62 AND US 31E. (18CCN) (2020CCR) | R |  | STP | 2021 | 140000 | 140000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.321 | 2021-08-17 | ADD U PHASE TO STIP; NEW |  |  | NELSON | 4-80050 | US 62 |  | 14.24 | 14.274 | RELIABILITY | CONGESTION MITIGTN(O) | INTERSECTION IMPROVEMENTS AT US 62 AND US 31E. (18CCN) (2020CCR) | U |  | STP | 2021 | 195000 | 195000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | NICHOLAS | 9-8951 | CR 1010 |  | 2.387 | 2.414 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON ABNER'S MILL ROAD (CR 1010) 2.4 MILES NORTH OF KY 32. (16CCN)(18CCN) | C |  | BR/STP | 2021 | 100000 | 62000 |  |  | 38000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.111 | 2019-08-02 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW | HSIP |  | NICHOLAS BATH | 9-9013 | KY 36 |  | 4.5 0 | 12.807 .89 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 36 FROM MP 4.5 TO MP 12.807 IN NICHOLAS COUNTY AND MP 0.000 TO MP 0.890 IN BATH COUNTY. (2018BOP) | D |  | SAF | 2019 | 350000 | 350000 |  |  | 0 |  |  | OBLIGATED |  | 350000 | 350000 | 2019 | 4TH QUARTER
STIP | [9 empty] | NICHOLAS | 9-10011 | KY 36 |  | 2.96 | 2.972 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-36 BRIDGE OVER BRUSHY FORK. (091B00018N) | D |  | BR/STP | 2019 | 525000 | 325500 |  |  | 199500 | [5 empty] | 0
STIP | [9 empty] | NICHOLAS | 9-10011 | KY 36 |  | 2.96 | 2.972 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-36 BRIDGE OVER BRUSHY FORK. (091B00018N) | C |  | BR/STP | 2020 | 1610000 | 998200 |  |  | 611800 | [5 empty] | 0
STIP | [9 empty] | NICHOLAS | 9-10012 | CS 1096 |  | 0.075 | 0.085 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF DORSEY AVE BRIDGE OVER BRUSH FORK. (091C00029N) | D |  | BR/STP | 2019 | 280000 | 173600 |  |  | 106400 | [5 empty] | 0
STIP | [9 empty] | NICHOLAS | 9-10012 | CS 1096 |  | 0.075 | 0.085 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF DORSEY AVE BRIDGE OVER BRUSH FORK. (091C00029N) | C |  | BR/STP | 2020 | 595000 | 368900 |  |  | 226100 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.229 | 2020-09-14 | ADD C PHASE TO STIP; PARENT NO. 99-224.14; NEW |  |  | NICHOLAS | 9-20025 | KY 36 |  | 4.583 | 12.807 | RELIABILITY | AM-PAVEMENT(PRI)(P) | RESURFACING OF KY 36 FROM MP 4.583 TO 12.807 IN NICHOLAS COUNTY. | C |  | STP | 2020 | 683248 | 683248 |  |  | 0 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 5038116 | OHIO | 2-1083 | US 62 | 0.04 | 11.892 | 11.932 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON US 62 OVER BRANCH OF THREE LICK FORK 0.23 MILE E OF GREEN MEADOWS DR (CS 6068)092B00032 (SD) | C |  | BR/STP | 2019 | 1148000 | 711760 |  |  | 436240 |  |  | OBLIGATED | 200000 | 922017 | 1122017 | 2019 | 4TH QUARTER
STIP | [9 empty] | OHIO | 2-1091 | US 62 | 0.074 | 12 | 12.074 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER THREELICK FORK ON US 62 0.4 MILE E OF GREEN MEADOWS DRIVE (CS 6068) IN BEAVER DAM. (092B00033N) | D |  | BR/STP | 2019 | 308000 | 190960 |  |  | 117040 | [5 empty] | 0
STIP | [9 empty] | OHIO | 2-1091 | US 62 | 0.074 | 12 | 12.074 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER THREELICK FORK ON US 62 0.4 MILE E OF GREEN MEADOWS DRIVE (CS 6068) IN BEAVER DAM. (092B00033N) | C |  | BR/STP | 2020 | 1029000 | 637980 |  |  | 391020 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.118 | 2019-08-19 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030169 | OHIO | 2-1091 | US 62 | 0.074 | 12 | 12.074 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER THREELICK FORK ON US 62 0.4 MILE E OF GREEN MEADOWS DRIVE (CS 6068) IN BEAVER DAM. (092B00033N) | C |  | STP | 2020 | 1690399 | 1690399 |  |  | 0 |  |  | OBLIGATED |  | 1177245.6 | 1177245.6 | 2019 | 4TH QUARTER
STIP | [9 empty] | OHIO | 2-2092.2 | WN 9007 |  | 49.7 | 50.1 | RELIABILITY | I-CHANGE RECONST(O) | I-65 SPUR CORRIDOR; RECONSTRUCT THE EXISTING NATCHER PARKWAY/KY-69 INTERCHANGE (EXIT 50) IN OHIO COUNTY. (2016BOP) | C |  | NH | 2021 | 8700000 | 6960000 |  |  | 1740000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.276 | 2021-02-12 | INCREASE FUNDS BASED ON NEW ESTIMATE; MOD |  |  | OHIO | 2-2092.2 | WN 9007 |  | 49.7 | 50.1 | RELIABILITY | I-CHANGE RECONST(O) | I-65 SPUR CORRIDOR; RECONSTRUCT THE EXISTING NATCHER PARKWAY/KY-69 INTERCHANGE (EXIT 50) IN OHIO COUNTY. (2016BOP) | C |  | NHPP | 2021 | 8508500 | 8508500 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.306 | 2021-06-16 | ADD D PHASE TO STIP; NEW |  |  | OHIO | 2-8951 | KY 54 |  | 7.047 | 7.995 | RELIABILITY | MINOR WIDENING(O) | IMPROVE SAFETY ON KY 54 BY UPGRADING MP 7.0 TO MP 8.0 TO THREE LANES INCLUDING CURB AND GUTTER AND ADDRESSING TWO SHARP TURNS. (16CCN)(18CCN) (2020CCR) | D |  | SPP | 2021 | 750100 | 100 |  |  | 750000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.175 | 2020-04-09 | ADD D PHASE TO STIP; PARENT NO. 99-911.09; NEW |  |  | OHIO | 2-9015 | KY 69 |  | 16.835 | 24.031 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 69 FROM MP 16.835 TO MP 24.031 IN OHIO COUNTY, KY. (2018BOP) | D |  | SAF | 2020 | 150000 | 150000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | OHIO | 2-10010 | KY 85 |  | 9.614 | 9.627 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-85 BRIDGE OVER BR OF W FK LEWIS CREEK. (092B00053N) | D |  | BR/STP | 2019 | 210000 | 130200 |  |  | 79800 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030101 | OHIO | 2-10010 | KY 85 |  | 9.614 | 9.627 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-85 BRIDGE OVER BR OF W FK LEWIS CREEK. (092B00053N) | C |  | BR/STP | 2020 | 962500 | 596750 |  |  | 365750 |  |  | OBLIGATED | 654989 | 131396 | 786385 | 2019 | 4TH QUARTER
STIP | [9 empty] | OHIO | 2-10011 | CR 1003 |  | 1.331 | 1.338 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF WEST HALLS CREEK R BRIDGE OVER BRANCH OF HALLS CREEK. (092C00001N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030015 | OHIO | 2-10011 | CR 1003 |  | 1.331 | 1.338 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF WEST HALLS CREEK R BRIDGE OVER BRANCH OF HALLS CREEK. (092C00001N) | C |  | BR/STP | 2020 | 630000 | 390600 |  |  | 239400 |  |  | OBLIGATED |  | 333140 | 333140 | 2019 | 2ND QUARTER
STIP | [9 empty] | OHIO | 2-10012 | CR 1067 |  | 2.377 | 2.386 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF SUNNYDALE RD BRIDGE OVER BRANCH OF ROUGH RIVER. (092C00020N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030061 | OHIO | 2-10012 | CR 1067 |  | 2.377 | 2.386 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF SUNNYDALE RD BRIDGE OVER BRANCH OF ROUGH RIVER. (092C00020N) | C |  | BR/STP | 2020 | 630000 | 390600 |  |  | 239400 |  |  | OBLIGATED |  | 220994 | 220994 | 2019 | 3RD QUARTER
STIP | [9 empty] | OHIO | 2-10013 | CR 1036 |  | 2.88 | 2.892 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF RAILROAD BED RD BRIDGE OVER WFK ADAMS CREEK. (092C00067N) | D |  | BR/STP | 2019 | 210000 | 130200 |  |  | 79800 | [5 empty] | 0
STIP | [7 empty] | STP | 9030005 | OHIO | 2-10013 | CR 1036 |  | 2.88 | 2.892 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF RAILROAD BED RD BRIDGE OVER WFK ADAMS CREEK. (092C00067N) | C |  | BR/STP | 2020 | 735000 | 455700 |  |  | 279300 |  |  | OBLIGATED | 535800 |  | 535800 | 2019 | 2ND QUARTER
STIP | [9 empty] | OHIO | 2-10014 | CR 1414 |  | 4.907 | 4.92 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF JOHNSON SCHOOL RD BRIDGE OVER BARASS DITCH. (092C00080N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [9 empty] | OHIO | 2-10014 | CR 1414 |  | 4.907 | 4.92 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF JOHNSON SCHOOL RD BRIDGE OVER BARASS DITCH. (092C00080N) | C |  | BR/STP | 2020 | 647500 | 401450 |  |  | 246050 | [5 empty] | 0
STIP | [9 empty] | OHIO | 2-10015 | CR 1083 |  | 0.007 | 0.012 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF ROCK CREEK LN BRIDGE OVER BR-S.FK PANTHER CK. (092C00097N) | D |  | BR/STP | 2019 | 210000 | 130200 |  |  | 79800 | [5 empty] | 0
STIP | [9 empty] | OHIO | 2-10015 | CR 1083 |  | 0.007 | 0.012 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF ROCK CREEK LN BRIDGE OVER BR-S.FK PANTHER CK. (092C00097N) | C |  | BR/STP | 2020 | 840000 | 520800 |  |  | 319200 | [5 empty] | 0
STIP | [9 empty] | OHIO | 2-10016 | CR 1510 |  | 0.256 | 0.269 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF QUARTERHORSE LN BRIDGE OVER N FK PANTHER CREEK. (092C00133N) | D |  | BR/STP | 2019 | 245000 | 151900 |  |  | 93100 | [5 empty] | 0
STIP | [9 empty] | OHIO | 2-10016 | CR 1510 |  | 0.256 | 0.269 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF QUARTERHORSE LN BRIDGE OVER N FK PANTHER CREEK. (092C00133N) | C |  | BR/STP | 2020 | 892500 | 553350 |  |  | 339150 | [5 empty] | 0
STIP | [9 empty] | OHIO | 2-20038 | US 62 |  | 19.797 | 25.95 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT | D |  | PM/STP | 2022 | 500000 | 400000 |  |  | 100000 | [5 empty] | 0
STIP | [9 empty] | OHIO | 2-20038 | US 62 |  | 19.797 | 25.95 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT | C |  | PM/STP | 2022 | 5000000 | 4000000 |  |  | 1000000 | [5 empty] | 0
STIP | [9 empty] | OHIO | 2-20039 | WK 9001 |  | 65.68 | 83.3 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF WENDELL H. FORD WESTERN KY PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 65.68 TO MILEPOINT 83.3 | C |  | PM/NH | 2020 | 16596000 | 13276800 |  |  | 3319200 | [5 empty] | 0
STIP | [9 empty] | OHIO | 2-20040 | WK 9001 |  | 83.3 | 87.544 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF WENDELL H. FORD WESTERN KY PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 83.3 TO MILEPOINT 87.544 | C |  | PM/NH | 2020 | 4282000 | 3425600 |  |  | 856400 | [5 empty] | 0
STIP | [9 empty] | OHIO | 2-20041 | WN 9007 |  | 49.8 | 59.86 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF WILLIAM H. NATCHER PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 49.8 TO MILEPOINT 59.86 (61.553 NON-CARDINAL) | C |  | PM/NH | 2020 | 11064000 | 8851200 |  |  | 2212800 | [5 empty] | 0
STIP | [9 empty] | OHIO | 2-20049 | KY 136 | 9.6 | 0 | 9.6 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION ON KY-136 FROM MILEPOINT 0.00 TO MILEPOINT 9.60 | C |  | PM/STP | 2022 | 1177000 | 941600 |  |  | 235400 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.229 | 2020-09-14 | ADD C PHASE TO STIP; PARENT NO. 99-224.14; NEW |  |  | OHIO | 2-20054 | KY 69 |  | 19.91 | 25.535 | RELIABILITY | AM-PAVEMENT (PRI)(P) | RESURFACING OF KY 69 FROM MP 19.91 TO 25.535 IN OHIO COUNTY. | C |  | STP | 2020 | 666292 | 666292 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.271 | 2021-01-12 | TIP FY 20-25, AMEND#2; ADD PROJECT TO STIP; NEW |  |  | OLDHAM | 5-234 | KY 393 |  | 5.13 | 5.868 | RELIABILITY | MAJOR WIDENING(O) | KY-393 RECONSTRUCT FROM 140FEET SOUTH OF RAILROAD CROSSING (CSX) EXTENDING NORTHWEST TOWARDS KY 146 ENDING AT STATION 12+00 (DESIGN UNDER 5-230.00). (CONSTRUCTION SEQ.#2) (2020CCN) | C |  | STP | 2021 | 12468000 | 9976000 |  |  | 2492000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; ADD PROJECT TO STIP; NEW |  |  | OLDHAM | 5-367.2 | Old Henry Road |  |  |  | NEW ROUTES | NEW ROUTE(O) | EXTENSION OF OLD HENRY ROAD EAST TO ASH AVENUE (KY362). (12CCR)(18CCN) (2020CCR) | C |  | STP | 2021 | 12000000 | 9600000 |  |  | 2400000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; ADD PROJECT TO STIP; NEW |  |  | OLDHAM | 5-367.2 | Old Henry Road |  |  |  | NEW ROUTES | NEW ROUTE(O) | EXTENSION OF OLD HENRY ROAD EAST TO ASH AVENUE (KY362). (12CCR)(18CCN) (2020CCR) | C |  | STP | 2023 | 6000000 | 4800000 |  |  | 1200000 | [5 empty] | 0
TIP | [6 empty] | NOT IN STIP |  |  | Oldham | 5-410 | Oldham County Bicycle & Pedestrian Trail | [5 empty] | Construct a non-motorized corridor from LaGrange to Jefferson County line along the Buckner Connector, the new 393 alignment to Wendell Moore Park and/or along KY 146 at the new pedestrian bridge over I-71. | D |  | SLO | 2021 | 625000 | 500000 |  |  |  | 125000 |  |  |  |  | 0
STIP | [6 empty] | NOT IN TIP |  |  | OLDHAM | 5-410.01 | CR 1203 |  | 0 | 3.391 | SAFETY | BIKE/PED FACIL(O) | OLDHAM COUNTY BICYCLE & PEDESTRIAN TRAIL - OLD LAGRANGE RD. CONSTRUCT A BICYCLE AND PEDESTRIAN TRAIL ALONG OLD LAGRANGE ROAD FROM KY 146 TO THE INTERSECTION WITH KY 329 BYPASS. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). (14CCR)(18CCR) | D |  | SLO | 2019 | 250000 | 200000 |  |  |  | 50000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; UPDATE FISCAL YEAR FROM 2019 TO 2020; MOD |  |  | OLDHAM | 5-410.01 | CR 1203 |  | 0 | 3.391 | SAFETY | BIKE/PED FACIL(O) | OLDHAM COUNTY BICYCLE & PEDESTRIAN TRAIL - OLD LAGRANGE ROAD IMPROVEMENTS. CONSTRUCT A BICYCLE AND PEDESTRIAN TRAIL SECTION ALONG OLD LAGRANGE ROAD FROM NORTH CAMDEN LANE TO THE KY 329 BYPASS AND ON TO THE INTERSECTION WITH KY 146 IN CRESTWOOD. | D |  | STP | 2020 | 250000 | 200000 |  |  |  | 50000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.309 | 2021-06-10 | TIP FY 20-25, ADMIN MOD#17; UPDATE FUND AMOUNTS; MOD |  |  | OLDHAM | 5-410.01 | CR 1203 |  | 0 | 3.391 | SAFETY | BIKE/PED FACIL(O) | OLDHAM COUNTY BICYCLE & PEDESTRIAN TRAIL - OLD LAGRANGE ROAD IMPROVEMENTS. CONSTRUCT A BICYCLE AND PEDESTRIAN TRAIL SECTION ALONG OLD LAGRANGE ROAD FROM NORTH CAMDEN LANE TO THE KY 329 BYPASS AND ON TO THE INTERSECTION WITH KY 146 IN CRESTWOOD. | D
STIP | [6 empty] | NOT IN TIP |  |  | OLDHAM | 5-410.01 | CR 1203 |  | 0 | 3.391 | SAFETY | BIKE/PED FACIL(O) | OLDHAM COUNTY BICYCLE & PEDESTRIAN TRAIL - OLD LAGRANGE RD. CONSTRUCT A BICYCLE AND PEDESTRIAN TRAIL ALONG OLD LAGRANGE ROAD FROM KY 146 TO THE INTERSECTION WITH KY 329 BYPASS. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). (14CCR)(18CCR) | R |  | SLO | 2020 | 500000 | 400000 |  |  |  | 100000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; UPDATE FISCAL YEAR FROM 2020 TO 2022; MOD |  |  | OLDHAM | 5-410.01 | CR 1203 |  | 0 | 3.391 | SAFETY | BIKE/PED FACIL(O) | OLDHAM COUNTY BICYCLE & PEDESTRIAN TRAIL - OLD LAGRANGE ROAD IMPROVEMENTS. CONSTRUCT A BICYCLE AND PEDESTRIAN TRAIL SECTION ALONG OLD LAGRANGE ROAD FROM NORTH CAMDEN LANE TO THE KY 329 BYPASS AND ON TO THE INTERSECTION WITH KY 146 IN CRESTWOOD. | R |  | STP | 2022 | 500000 | 400000 |  |  |  | 100000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.309 | 2021-06-10 | TIP FY 20-25, ADMIN MOD#17; UPDATE FUND AMOUNTS; MOD |  |  | OLDHAM | 5-410.01 | CR 1203 |  | 0 | 3.391 | SAFETY | BIKE/PED FACIL(O) | OLDHAM COUNTY BICYCLE & PEDESTRIAN TRAIL - OLD LAGRANGE ROAD IMPROVEMENTS. CONSTRUCT A BICYCLE AND PEDESTRIAN TRAIL SECTION ALONG OLD LAGRANGE ROAD FROM NORTH CAMDEN LANE TO THE KY 329 BYPASS AND ON TO THE INTERSECTION WITH KY 146 IN CRESTWOOD. | R |  | STP | 2022 | 195603 | 159676 |  |  | 35927 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.309 | 2021-06-10 | TIP FY 20-25, ADMIN MOD#17; ADD CRRSAA FUNDS TO THE R/W PHASE; MOD |  |  | OLDHAM | 5-410.01 | CR 1203 |  | 0 | 3.391 | SAFETY | BIKE/PED FACIL(O) | OLDHAM COUNTY BICYCLE & PEDESTRIAN TRAIL - OLD LAGRANGE ROAD IMPROVEMENTS. CONSTRUCT A BICYCLE AND PEDESTRIAN TRAIL SECTION ALONG OLD LAGRANGE ROAD FROM NORTH CAMDEN LANE TO THE KY 329 BYPASS AND ON TO THE INTERSECTION WITH KY 146 IN CRESTWOOD. | R |  |  | 2022 | 340324 | 340324 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.107 | 2019-07-26 | TIP FY 18-21, ADMIN MOD#33; ADD U PHASE TO STIP; NEW |  |  | OLDHAM | 5-410.01 | CR 1203 |  | 0 | 3.391 | SAFETY | BIKE/PED FACIL(O) | OLDHAM COUNTY BICYCLE & PEDESTRIAN TRAIL - OLD LAGRANGE ROAD IMPROVEMENTS. CONSTRUCT A BICYCLE AND PEDESTRIAN TRAIL SECTION ALONG OLD LAGRANGE ROAD FROM NORTH CAMDEN LANE TO THE KY 329 BYPASS AND ON TO THE INTERSECTION WITH KY 146 IN CRESTWOOD. | U |  | SLO | 2021 | 937500 | 750000 |  |  | 187500 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; UPDATE FISCAL YEAR FROM 2021 TO 2023; MOD |  |  | OLDHAM | 5-410.01 | CR 1203 |  | 0 | 3.391 | SAFETY | BIKE/PED FACIL(O) | OLDHAM COUNTY BICYCLE & PEDESTRIAN TRAIL - OLD LAGRANGE ROAD IMPROVEMENTS. CONSTRUCT A BICYCLE AND PEDESTRIAN TRAIL SECTION ALONG OLD LAGRANGE ROAD FROM NORTH CAMDEN LANE TO THE KY 329 BYPASS AND ON TO THE INTERSECTION WITH KY 146 IN CRESTWOOD. | U |  | STP | 2023 | 937500 | 750000 |  |  | 187500 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.309 | 2021-06-10 | TIP FY 20-25, ADMIN MOD#17; ADD C PHASE TO STIP; NEW |  |  | OLDHAM | 5-410.01 | CR 1203 |  | 0 | 3.391 | SAFETY | BIKE/PED FACIL(O) | OLDHAM COUNTY BICYCLE & PEDESTRIAN TRAIL - OLD LAGRANGE ROAD IMPROVEMENTS. CONSTRUCT A BICYCLE AND PEDESTRIAN TRAIL SECTION ALONG OLD LAGRANGE ROAD FROM NORTH CAMDEN LANE TO THE KY 329 BYPASS AND ON TO THE INTERSECTION WITH KY 146 IN CRESTWOOD. | C |  | STP | 2024 | 625000 | 500000 |  |  | 125000
STIP | [9 empty] | OLDHAM | 5-434 | CR 1002 | 0.75 | 0 | 0.747 | SAFETY | SAFETY(P) | CONSTRUCT A 4-LANE UNINTERRUPTED RAIL UNDERPASS WEST OF LAGRANGE. (LOCAL MATCH)(ALL WORK BY OLDHAM COUNTY) (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). (14CCR) | C |  | SLO | 2019 | 10000000 | 8000000 |  |  |  | 2000000 |  |  |  |  | 0
TIP | [9 empty] | Oldham | 5-434 | CR 1002 | 0.75 | 0 | 0.747 | SAFETY | SAFETY(P) | Construct a 4 lane uninterrupted rail underpass west of LaGrange. | C |  | SLO | 2019 | 10100000 | 10100000 |  |  |  | 0 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.051 | 2019-04-18 | TIP FY 18-21, ADMIN MOD#28; UPDATE FUND AMOUNTS; MOD |  |  | Oldham | 5-434 | CR 1002 | 0.75 | 0 | 0.747 | SAFETY | SAFETY(P) | Construct a 4 lane uninterrupted rail underpass west of LaGrange. | C |  | SLO | 2019 | 10000000 | 10000000 |  |  |  | 0 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; UPDATE FISCAL YEAR FROM 2019 TO 2022; MOD |  |  | Oldham | 5-434 | CR 1002 | 0.75 | 0 | 0.747 | SAFETY | SAFETY(P) | Construct a 4 lane uninterrupted rail underpass west of LaGrange. | C |  | SLO | 2022 | 10000000 | 10000000 |  |  |  | 0 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; UPDATE FISCAL YEAR & FUND AMOUNTS; MOD |  |  | Oldham | 5-434 | CR 1002 | 0.75 | 0 | 0.747 | SAFETY | SAFETY(P) | Construct a 4 lane uninterrupted rail underpass west of LaGrange. | C |  | SLO | 2023 | 12500000 | 10000000 |  |  |  | 2500000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.051 | 2019-04-18 | TIP FY 18-21, ADMIN MOD#28; ADD D PHASE; NEW |  |  | Oldham | 5-434 | CR 1002 | 0.75 | 0 | 0.747 | SAFETY | SAFETY(P) | Construct a 4 lane uninterrupted rail underpass west of LaGrange. | D |  | SLO | 2019 | 100000 | 100000 |  |  |  | 0 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.186 | 2020-05-06 | TIP FY 20-25, ADMIN MOD#2; ADD R PHASE TO STIP; NEW |  |  | Oldham | 5-434 | CR 1002 | 0.75 | 0 | 0.747 | SAFETY | SAFETY(P) | Construct a 4 lane uninterrupted rail underpass west of LaGrange. | R |  | SLO | 2020 | 4868750 | 3895000 |  |  |  | 973750 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; ADD U PHASE TO STIP; NEW |  |  | Oldham | 5-434 | CR 1002 | 0.75 | 0 | 0.747 | SAFETY | SAFETY(P) | Construct a 4 lane uninterrupted rail underpass west of LaGrange. | U |  | SLO | 2021 | 4868750 | 3895000 |  |  |  | 973750 |  |  |  |  | 0
STIP | [9 empty] | OLDHAM | 5-440.1 | KY 1793 | 0.286 | 1.542 | 1.828 | SAFETY | SAFETY(P) | CONSTRUCT SIDEWALKS ON KY 1793 FROM RIDGEVIEW DRIVE TO SETTLERS POINT TRAIL.(FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C |  | SLO | 2019 | 100000 | 80000 |  |  |  | 20000 |  |  |  |  | 0
TIP | [9 empty] | OLDHAM | 5-440.1 | KY 1793 | 0.286 | 1.542 | 1.828 | SAFETY | SAFETY(P) | Construct sidewalks on KY 1793 from Ridgeview Drive to Settlers Point Trail. | C |  | SLO | 2019 | 125000 | 100000 |  |  |  | 25000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.051 | 2019-04-18 | TIP FY 18-21, ADMIN MOD#28; CHANGE DESCRIPTION; MOD |  |  | OLDHAM | 5-440.1 | KY 1793 | 0.286 | 1.542 | 1.828 | SAFETY | SAFETY(P) | Construct sidewalks on KY 1793 from Ridgeview Drive to Ridgetop Drive. | C |  | SLO | 2019 | 125000 | 100000 |  |  |  | 25000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.117 | 2019-08-09 | TIP FY 18-21, ADMIN MOD#34; UPDATE FUND TYPE FROM SLO TO TAP FUNDS; MOD |  |  | OLDHAM | 5-440.1 | KY 1793 | 0.286 | 1.542 | 1.828 | SAFETY | SAFETY(P) | Construct sidewalks on KY 1793 from Ridgeview Drive to Ridgetop Drive. | C
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.122 | 2019-08-26 | TIP FY 18-21, ADMIN MOD#35; UPDATE FUND TYPE FROM TAP TO SLO FUNDS; MOD |  |  | OLDHAM | 5-440.1 | KY 1793 | 0.286 | 1.542 | 1.828 | SAFETY | SAFETY(P) | Construct sidewalks on KY 1793 from Ridgeview Drive to Ridgetop Drive. | C |  | SLO | 2019 | 125000 | 100000 |  |  |  | 25000 |  | OBLIGATED | 70720 |  | 70720 | 2019 | 4TH QUARTER | OLDHAM COUNTY
STIP | [9 empty] | OLDHAM | 5-441.01 | US 42 | 0.9 | 0 | 0.942 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT US 42 AND WIDEN FROM 2 LANES TO 3 LANES (3RD LANE WILL BE A CENTER TURN LANE) FROM JEFFERSON/OLDHAM COUNTY LINE TO RIDGEMOOR DRIVE. PROJECT WILL INCLUDE THE CONSIDERATION OF IMPROVEMENTS TO THE HAYFIELD WAY INTERSECTION. (2004BOPC) | C |  | SLO | 2019 | 5320000 | 4256000 |  |  |  | 1064000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.107 | 2019-07-26 | TIP FY 18-21, ADMIN MOD#33; UPDATE FUND AMOUNT; MOD |  |  | OLDHAM | 5-441.01 | US 42 | 0.9 | 0 | 0.942 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT US 42 AND WIDEN FROM 2 LANES TO 3 LANES (3RD LANE WILL BE A CENTER TURN LANE) FROM JEFFERSON/OLDHAM COUNTY LINE TO RIDGEMOOR DRIVE. PROJECT WILL INCLUDE THE CONSIDERATION OF IMPROVEMENTS TO THE HAYFIELD WAY INTERSECTION. (2004BOPC) | C |  | SLO | 2019 | 5020000 | 5020000 |  |  |  | 0 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; UPDATE FISCAL YEAR FROM 2019 TO 2020; MOD |  |  | OLDHAM | 5-441.01 | US 42 | 0.9 | 0 | 0.942 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT US 42 AND WIDEN FROM 2 LANES TO 3 LANES (3RD LANE WILL BE A CENTER TURN LANE) FROM JEFFERSON/OLDHAM COUNTY LINE TO RIDGEMOOR DRIVE. PROJECT WILL INCLUDE THE CONSIDERATION OF IMPROVEMENTS TO THE HAYFIELD WAY INTERSECTION. (2004BOPC) | C |  | STP | 2020 | 5020000 | 5020000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; UPDATE FISCAL YEAR; MOD |  |  | OLDHAM | 5-441.01 | US 42 | 0.9 | 0 | 0.942 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT US 42 AND WIDEN FROM 2 LANES TO 3 LANES (3RD LANE WILL BE A CENTER TURN LANE) FROM JEFFERSON/OLDHAM COUNTY LINE TO RIDGEMOOR DRIVE. PROJECT WILL INCLUDE THE CONSIDERATION OF IMPROVEMENTS TO THE HAYFIELD WAY INTERSECTION. (2004BOPC) | C |  | STP | 2021 | 5020000 | 5020000 | [8 empty] | 0
TIP | [7 empty] | STPM | 5138059 | Oldham | 5-441.01 | US 42 | 0.9 | 0 | 0.942 | RELIABILITY | RECONSTRUCTION(O) | Reconstruct US 42 and widen from 2 lanes to 3 lanes (3rd lane will be a center turn lane) from Jefferson/Oldham County line to Ridgemoor Drive. Project will include the consideration of improvements to the Hayfield Way intersection. | D |  | SLO | 2018 | 51000 | 51000 |  |  |  | 0 |  | OBLIGATED | 51000 |  | 51000 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.23 | 2020-09-14 | TIP FY 20-25, AMENDMENT#1; UPDATE FY TO 2020; MOD |  |  | Oldham | 5-441.01 | US 42 | 0.9 | 0 | 0.942 | RELIABILITY | RECONSTRUCTION(O) | Reconstruct US 42 and widen from 2 lanes to 3 lanes (3rd lane will be a center turn lane) from Jefferson/Oldham County line to Ridgemoor Drive. Project will include the consideration of improvements to the Hayfield Way intersection. | D |  | STP | 2020 | 51000 | 51000 | [8 empty] | 51000
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.107 | 2019-07-26 | TIP FY 18-21, ADMIN MOD#33; ADD U PHASE TO STIP; NEW |  |  | Oldham | 5-441.01 | US 42 | 0.9 | 0 | 0.942 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT US 42 AND WIDEN FROM 2 LANES TO 3 LANES (3RD LANE WILL BE A CENTER TURN LANE) FROM JEFFERSON/OLDHAM COUNTY LINE TO RIDGEMOOR DRIVE. PROJECT WILL INCLUDE THE CONSIDERATION OF IMPROVEMENTS TO THE HAYFIELD WAY INTERSECTION. (2004BOPC) | U |  | SLO | 2019 | 300000 | 300000 |  |  |  | 0 |  | OBLIGATED |  | 300000 | 300000 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.23 | 2020-09-14 | TIP FY 20-25, AMENDMENT#1; UPDATE FY TO 2020; MOD |  |  | Oldham | 5-441.01 | US 42 | 0.9 | 0 | 0.942 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT US 42 AND WIDEN FROM 2 LANES TO 3 LANES (3RD LANE WILL BE A CENTER TURN LANE) FROM JEFFERSON/OLDHAM COUNTY LINE TO RIDGEMOOR DRIVE. PROJECT WILL INCLUDE THE CONSIDERATION OF IMPROVEMENTS TO THE HAYFIELD WAY INTERSECTION. (2004BOPC) | U |  | STP | 2020 | 300000 | 300000 | [8 empty] | 0
TIP | [6 empty] | NOT IN STIP |  |  | Oldham | 5-449 | KY 22 / KY 329 | [5 empty] | Intersection improvement at KY 22 and KY 329 in Crestwood. | C |  | SLO | 2019 | 129285 | 129285 |  |  |  | 0 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.165 | 2020-02-03 | TIP FY 18-21, ADMIN MOD#42; REMOVE FY 2019 CONSTRUCTION PHASE AND ASSOCIATED FUNDS; PROJECT COMPLETED AS OF DEC. 2019; MOD |  |  | Oldham | 5-449 | KY 22 / KY 329 | [5 empty] | Intersection improvement at KY 22 and KY 329 in Crestwood. | C
TIP | [6 empty] | NOT IN STIP |  |  | Oldham | 5-449 | KY 22 / KY 329 | [5 empty] | Intersection improvement at KY 22 and KY 329 in Crestwood. | C |  | SLO | 2018 | 170715 | 170715 |  |  |  | 0 |  |  |  |  | 0
STIP | [9 empty] | OLDHAM | 5-468.1 | CS 2102 | 0.041 | 0 | 0.041 | RELIABILITY | CONGESTION MITIGTN(O) | CONSTRUCTION OF A PARK AND RIDE FACILITY INCLUDING A PARKING LOT, SHELTER, PLAYGROUND, BIKE LOCKERS, WALKWAYS, AND A 1000' ACCESS ROAD LOCATED ON APPLE PATCH WAY OFF OF KY-329 NEAR I-71 EXIT 14 IN CRESTWOOD.(2010BOPC)(ADDITIONAL FUNDING)(14CCN) | C |  | SLO | 2019 | 1174800 | 939840 |  |  |  | 234960 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; UPDATE FUND AMOUNTS & FISCAL YEAR FROM 2019 TO 2020; MOD |  |  | OLDHAM | 5-468.1 | CS 2102 | 0.041 | 0 | 0.041 | RELIABILITY | CONGESTION MITIGTN(O) | CONSTRUCTION OF A PARK AND RIDE FACILITY INCLUDING A PARKING LOT, SHELTER, PLAYGROUND, BIKE LOCKERS, WALKWAYS, AND A 1000' ACCESS ROAD LOCATED ON APPLE PATCH WAY OFF OF KY-329 NEAR I-71 EXIT 14 IN CRESTWOOD.(2010BOPC)(ADDITIONAL FUNDING)(14CCN) | C |  | STP | 2020 | 1308483 | 1073523 |  |  |  | 234960 |  |  |  |  | 0
STIP | YES | [6 empty] | NHPP | 0711119 | OLDHAM | 5-483.1 | I 71 | 3.9 | 14.1 | 18 | RELIABILITY | MAJOR WIDENING(O) | WIDEN I-71 FROM FOUR TO SIX LANES FROM KY-329 (MP 14.1) TO KY-393 (MP 18.0). (16CCN) | D |  | NH | 2019 | 3500000 | 3500000 |  |  | 0 |  |  | OBLIGATED |  | 3500000 | 3500000 | 2019 | 3RD QUARTER
STIP | YES | [5 empty] | NOT IN TIP |  |  | OLDHAM | 5-483.1 | I 71 | 3.9 | 14.1 | 18 | RELIABILITY | MAJOR WIDENING(O) | WIDEN I-71 FROM FOUR TO SIX LANES FROM KY-329 (MP 14.1) TO KY-393 (MP 18.0). (16CCN) | R |  | NH | 2022 | 1900000 | 1520000 |  |  | 380000 | [5 empty] | 0
STIP | YES | [5 empty] | NOT IN TIP |  |  | OLDHAM | 5-483.1 | I 71 | 3.9 | 14.1 | 18 | RELIABILITY | MAJOR WIDENING(O) | WIDEN I-71 FROM FOUR TO SIX LANES FROM KY-329 (MP 14.1) TO KY-393 (MP 18.0). (16CCN) | U |  | NH | 2022 | 1700000 | 1360000 |  |  | 340000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.271 | 2021-01-12 | TIP FY 20-25, AMEND#2; ADD PROJECT TO STIP; NEW |  |  | OLDHAM | 5-483.2 | I 71 |  | 18 | 22.4 | RELIABILITY | MAJOR WIDENING(O) | WIDEN I-71 FROM FOUR TO SIX LANES FROM KY-393 (MP 18.0) TO KY-53 (MP 22.4). (16CCN) | D |  | NH | 2023 | 5500000 | 4400000 |  |  | 1100000 | [5 empty] | 0
STIP | YES | [8 empty] | OLDHAM | 5-483.3 | I 71 |  | 20 | 21 | RELIABILITY | NEW INTERCHANGE(O) | CONSTRUCT NEW I-71 INTERCHANGE BETWEEN KY-393 AND KY-53 TO RELIEVE CONGESTION IN LAGRANGE. | D |  | NH | 2019 | 1500000 | 1500000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.093 | 2019-06-28 | TIP FY 18-21; ADMIN MOD#32; UPDATE FUNDING AMOUNT; MOD |  |  | OLDHAM | 5-483.3 | I 71 |  | 20 | 21 | RELIABILITY | NEW INTERCHANGE(O) | CONSTRUCT NEW I-71 INTERCHANGE BETWEEN KY-393 AND KY-53 TO RELIEVE CONGESTION IN LAGRANGE. | D |  | NH | 2019 | 2000000 | 2000000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.201 | 2020-07-01 | TIP FY 20-25, ADMIN MOD#4; UPDATE FISCAL YEAR AND FUND AMOUNT; MOD |  |  | OLDHAM | 5-483.3 | I 71 |  | 20 | 21 | RELIABILITY | NEW INTERCHANGE(O) | CONSTRUCT NEW I-71 INTERCHANGE BETWEEN KY-393 AND KY-53 TO RELIEVE CONGESTION IN LAGRANGE. | D |  | NH | 2020 | 2500000 | 2000000 |  |  |  | 500000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.213 | 2020-07-24 | TIP FY 20-25, ADMIN MOD#5; UPDATE THE FUND TYPE; MOD |  |  | OLDHAM | 5-483.3 | I 71 |  | 20 | 21 | RELIABILITY | NEW INTERCHANGE(O) | CONSTRUCT NEW I-71 INTERCHANGE BETWEEN KY-393 AND KY-53 TO RELIEVE CONGESTION IN LAGRANGE. | D |  | NHPP | 2020 | 2500000 | 2000000 |  |  |  | 500000 |  |  |  |  | 0
STIP | YES | [8 empty] | OLDHAM | 5-483.3 | I 71 |  | 20 | 21 | RELIABILITY | NEW INTERCHANGE(O) | CONSTRUCT NEW I-71 INTERCHANGE BETWEEN KY-393 AND KY-53 TO RELIEVE CONGESTION IN LAGRANGE. | R |  | NH | 2019 | 3000000 | 3000000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; UDPATE FISCAL YEAR; MOD |  |  | OLDHAM | 5-483.3 | I 71 |  | 20 | 21 | RELIABILITY | NEW INTERCHANGE(O) | CONSTRUCT NEW I-71 INTERCHANGE BETWEEN KY-393 AND KY-53 TO RELIEVE CONGESTION IN LAGRANGE. | R |  | NHS | 2020 | 3000000 | 3000000 | [8 empty] | 0
STIP | YES | [8 empty] | OLDHAM | 5-483.3 | I 71 |  | 20 | 21 | RELIABILITY | NEW INTERCHANGE(O) | CONSTRUCT NEW I-71 INTERCHANGE BETWEEN KY-393 AND KY-53 TO RELIEVE CONGESTION IN LAGRANGE. | U |  | NH | 2019 | 1900000 | 1900000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; UDPATE FISCAL YEAR; MOD |  |  | OLDHAM | 5-483.3 | I 71 |  | 20 | 21 | RELIABILITY | NEW INTERCHANGE(O) | CONSTRUCT NEW I-71 INTERCHANGE BETWEEN KY-393 AND KY-53 TO RELIEVE CONGESTION IN LAGRANGE. | U |  | NHPP | 2020 | 1900000 | 1900000 | [8 empty] | 0
STIP | YES | [8 empty] | OLDHAM | 5-483.3 | I 71 |  | 20 | 21 | RELIABILITY | NEW INTERCHANGE(O) | CONSTRUCT NEW I-71 INTERCHANGE BETWEEN KY-393 AND KY-53 TO RELIEVE CONGESTION IN LAGRANGE. | C |  | NH | 2020 | 6000000 | 6000000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; UDPATE FISCAL YEAR & FUND AMOUNTS; MOD |  |  | OLDHAM | 5-483.3 | I 71 |  | 20 | 21 | RELIABILITY | NEW INTERCHANGE(O) | CONSTRUCT NEW I-71 INTERCHANGE BETWEEN KY-393 AND KY-53 TO RELIEVE CONGESTION IN LAGRANGE. | C |  | NHPP | 2020 | 12000000 | 9600000 |  |  | 2400000 | [5 empty] | 0
STIP | YES | [8 empty] | OLDHAM | 5-483.31 | I 71 |  | 20 | 21 | RELIABILITY | PREFINANCD CONVRSN(O) | CONSTRUCT NEW I-71 INTERCHANGE BETWEEN KY-393 AND KY-53 TO RELIEVE CONGESTION IN LAGRANGE. | C |  | NH | 2021 | 6000000 | 4800000 |  |  | 1200000 | [5 empty] | 0
STIP | [9 empty] | OLDHAM | 5-494 | CR 1209 |  | 1.43 | 1.44 | SAFETY | SAFETY-HAZARD ELIM(P) | OLD FLOYDSBURG ROAD SAFETY IMPROVEMENTS: REPLACE NARROW ONE-LANE CULVERT CROSSING; CLEAR TREES AND VEGETATION OUT OF RIGHT-OF-WAY; ADD SHOULDER TO THE ROAD, AND ADD SIGNAGE FOR SAFETY. | C |  | SLO | 2019 | 700000 | 560000 |  |  |  | 140000 |  |  |  |  | 0
TIP | [6 empty] | TIP AND STIP AMOUNTS ARE DIFFERENT |  |  | Oldham | 5-494 | CR 1209 |  | 1.43 | 1.44 | SAFETY | SAFETY-HAZARD ELIM(P) | Replace narrow one-lane culvert crossing; clear trees and vegetation out of right-of-way; add shoulder to the road, and add signage for safety. | C |  | SLO | 2019 | 950000 | 950000 |  |  |  | 0 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.057 | 2019-04-26 | TIP FY 18-21, ADMIN MOD#29; UPDATE FUND AMOUNTS; MOD |  |  | Oldham | 5-494 | CR 1209 |  | 1.43 | 1.44 | SAFETY | SAFETY-HAZARD ELIM(P) | Replace narrow one-lane culvert crossing; clear trees and vegetation out of right-of-way; add shoulder to the road, and add signage for safety. | C |  | SLO | 2019 | 1133308 | 1133308 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; UPDATE FISCAL YEAR FROM 2019 TO 2020 & UPDATE FUND AMOUNTS; MOD |  |  | Oldham | 5-494 | CR 1209 |  | 1.43 | 1.44 | SAFETY | SAFETY-HAZARD ELIM(P) | Replace narrow one-lane culvert crossing; clear trees and vegetation out of right-of-way; add shoulder to the road, and add signage for safety. | C |  | STP | 2020 | 1288308 | 1288308 | [8 empty] | 0
STIP | [9 empty] | OLDHAM | 5-542 | KY 329 |  | 7.226 |  | RELIABILITY | RECONSTRUCTION(O) | INTERSECTION REALIGNMENT/RECONSTRUCTION AT KY 329 AND KY 329 BYPASS (2016BOP). | R |  | SLO | 2019 | 100000 | 80000 |  |  |  | 20000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.107 | 2019-07-26 | TIP FY 18-21, ADMIN MOD#33; UPDATE PROJECT DESCRIPTION | STPM | 3001499 | Oldham | 5-542 | KY 329 |  | 7.226 |  | RELIABILITY | RECONSTRUCTION(O) | The project is improvements to the area of the KY 329 and KY 329 Bypass intersection in Oldham County adjacent to the KY 329 interchange with Interstate 71. Congestion occurs during the morning and evening rush hours due to several nearby public schools as well as several roadways converging close to the intersection. Other areas of concern in the area include the 5% downgrade on KY 329 Bypass approaching Ky 329 intersection; the sight distance between KY 329 Bypass to the business on the east of the road is obscured by an existing rock and the distance between a crest vertical curve on KY 329 and the intersection with the Spring Hill Subdivision looking east 575 ft. The project is planned to include: widening or reconstruction of KY 329 to include dual left turn lanes and a signal; widening of the KY 329 Bypass to include a left turn lane onto KY 329 and right turn lane onto KY 329; and sight distance improvements on both the KY 329 Bypass and existing KY 329. | R |  | SLO | 2019 | 100000 | 80000 |  |  |  | 20000 |  | OBLIGATED | 88000 |  | 88000 | 2019 | 4TH QUARTER | OLDHAM COUNTY
STIP | [9 empty] | OLDHAM | 5-542 | KY 329 |  | 7.226 |  | RELIABILITY | RECONSTRUCTION(O) | INTERSECTION REALIGNMENT/RECONSTRUCTION AT KY 329 AND KY 329 BYPASS (2016BOP). | U |  | SLO | 2020 | 100000 | 80000 |  |  |  | 20000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.057 | 2019-04-26 | TIP FY 18-21, ADMIN MOD#29; UPDATE FUND AMOUNTS; MOD |  |  | OLDHAM | 5-542 | KY 329 |  | 7.226 |  | RELIABILITY | RECONSTRUCTION(O) | Intersection realignment/reconstruction at KY 329 and KY 329 Bypass. | U |  | SLO | 2020 | 421875 | 337500 |  |  |  | 84375 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.107 | 2019-07-26 | TIP FY 18-21, ADMIN MOD#33; UPDATE PROJECT DESCRIPTION | STPM | 3001499 | Oldham | 5-542 | KY 329 |  | 7.226 |  | RELIABILITY | RECONSTRUCTION(O) | The project is improvements to the area of the KY 329 and KY 329 Bypass intersection in Oldham County adjacent to the KY 329 interchange with Interstate 71. Congestion occurs during the morning and evening rush hours due to several nearby public schools as well as several roadways converging close to the intersection. Other areas of concern in the area include the 5% downgrade on KY 329 Bypass approaching Ky 329 intersection; the sight distance between KY 329 Bypass to the business on the east of the road is obscured by an existing rock and the distance between a crest vertical curve on KY 329 and the intersection with the Spring Hill Subdivision looking east 575 ft. The project is planned to include: widening or reconstruction of KY 329 to include dual left turn lanes and a signal; widening of the KY 329 Bypass to include a left turn lane onto KY 329 and right turn lane onto KY 329; and sight distance improvements on both the KY 329 Bypass and existing KY 329. | U |  | SLO | 2020 | 421875 | 337500 |  |  |  | 84375 |  | OBLIGATED | 276000 |  | 276000 | 2020 | 2ND QUARTER | OLDHAM COUNTY
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; | STPM | 3001499 | Oldham | 5-542 | KY 329 | [5 empty] | The project is improvements to the area of the KY 329 and KY 329 Bypass intersection in Oldham County adjacent to the KY 329 interchange with Interstate 71. Congestion occurs during the morning and evening rush hours due to several nearby public schools as well as several roadways converging close to the intersection. Other areas of concern in the area include the 5% downgrade on KY 329 Bypass approaching Ky 329 intersection; the sight distance between KY 329 Bypass to the business on the east of the road is obscured by an existing rock and the distance between a crest vertical curve on KY 329 and the intersection with the Spring Hill Subdivision looking east 575 ft. The project is planned to include: widening or reconstruction of KY 329 to include dual left turn lanes and a signal; widening of the KY 329 Bypass to include a left turn lane onto KY 329 and right turn lane onto KY 329; and sight distance improvements on both the KY 329 Bypass and existing KY 329. | U |  | SLO | 2021 | 76875 | 61500 |  |  |  | 15375 |  |  |  |  | 0
TIP | [6 empty] | NOT IN STIP |  |  | Oldham | 5-542 | KY 329 | [5 empty] | Intersection realignment/reconstruction at KY 329 and KY 329 Bypass. | D |  | SLO | 2018 | 150000 | 120000 |  |  |  | 30000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; UPDATE FISCAL YEAR FROM 2018 TO 2020 AND FUND AMOUNT; MOD |  |  | Oldham | 5-542 | KY 329 | [5 empty] | The project is improvements to the area of the KY 329 and KY 329 Bypass intersection in Oldham County adjacent to the KY 329 interchange with Interstate 71. Congestion occurs during the morning and evening rush hours due to several nearby public schools as well as several roadways converging close to the intersection. Other areas of concern in the area include the 5% downgrade on KY 329 Bypass approaching Ky 329 intersection; the sight distance between KY 329 Bypass to the business on the east of the road is obscured by an existing rock and the distance between a crest vertical curve on KY 329 and the intersection with the Spring Hill Subdivision looking east 575 ft. The project is planned to include: widening or reconstruction of KY 329 to include dual left turn lanes and a signal; widening of the KY 329 Bypass to include a left turn lane onto KY 329 and right turn lane onto KY 329; and sight distance improvements on both the KY 329 Bypass and existing KY 329. | D |  | STP | 2020 | 170000 | 140000 |  |  |  | 30000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; UPDATE FUND AMOUNTS; MOD |  |  | Oldham | 5-542 | KY 329 | [5 empty] | The project is improvements to the area of the KY 329 and KY 329 Bypass intersection in Oldham County adjacent to the KY 329 interchange with Interstate 71. Congestion occurs during the morning and evening rush hours due to several nearby public schools as well as several roadways converging close to the intersection. Other areas of concern in the area include the 5% downgrade on KY 329 Bypass approaching Ky 329 intersection; the sight distance between KY 329 Bypass to the business on the east of the road is obscured by an existing rock and the distance between a crest vertical curve on KY 329 and the intersection with the Spring Hill Subdivision looking east 575 ft. The project is planned to include: widening or reconstruction of KY 329 to include dual left turn lanes and a signal; widening of the KY 329 Bypass to include a left turn lane onto KY 329 and right turn lane onto KY 329; and sight distance improvements on both the KY 329 Bypass and existing KY 329. | D |  | STP | 2020 | 20000 | 20000 |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.107 | 2019-07-26 | TIP FY 18-21, ADMIN MOD#33; ADD C PHASE & UPDATE PROJECT DESCRIPTION |  |  | Oldham | 5-542 | KY 329 |  | 7.226 |  | RELIABILITY | RECONSTRUCTION(O) | The project is improvements to the area of the KY 329 and KY 329 Bypass intersection in Oldham County adjacent to the KY 329 interchange with Interstate 71. Congestion occurs during the morning and evening rush hours due to several nearby public schools as well as several roadways converging close to the intersection. Other areas of concern in the area include the 5% downgrade on KY 329 Bypass approaching Ky 329 intersection; the sight distance between KY 329 Bypass to the business on the east of the road is obscured by an existing rock and the distance between a crest vertical curve on KY 329 and the intersection with the Spring Hill Subdivision looking east 575 ft. The project is planned to include: widening or reconstruction of KY 329 to include dual left turn lanes and a signal; widening of the KY 329 Bypass to include a left turn lane onto KY 329 and right turn lane onto KY 329; and sight distance improvements on both the KY 329 Bypass and existing KY 329. | C |  | SLO | 2021 | 2500000 | 2000000 |  |  |  | 500000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; UPDATE FISCAL YEAR; MOD |  |  | Oldham | 5-542 |  |  |  |  | RELIABILITY | RECONSTRUCTION(O) | The project is improvements to the area of the KY 329 and KY 329 Bypass intersection in Oldham County adjacent to the KY 329 interchange with Interstate 71. Congestion occurs during the morning and evening rush hours due to several nearby public schools as well as several roadways converging close to the intersection. Other areas of concern in the area include the 5% downgrade on KY 329 Bypass approaching Ky 329 intersection; the sight distance between KY 329 Bypass to the business on the east of the road is obscured by an existing rock and the distance between a crest vertical curve on KY 329 and the intersection with the Spring Hill Subdivision looking east 575 ft. The project is planned to include: widening or reconstruction of KY 329 to include dual left turn lanes and a signal; widening of the KY 329 Bypass to include a left turn lane onto KY 329 and right turn lane onto KY 329; and sight distance improvements on both the KY 329 Bypass and existing KY 329. | C |  | SLO | 2022 | 2500000 | 2000000 |  |  |  | 500000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.271 | 2021-01-12 | TIP FY 20-25, AMEND#2; ADD PROJECT TO STIP; NEW |  |  | Oldham | 5-552 | I-71 |  | 24.727 | 28 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE SAFETY AND REDUCE CONGESTION ON I-71 FROM KY-53 TO KY-153. | D |  | NH | 2023 | 5600000 | 4480000 |  |  | 1120000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.057 | 2019-04-26 | TIP FY 18-21, ADMIN MOD#29; ADD D PHASE TO STIP; NEW |  |  | Oldham | 5-754 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | Construct new connection from Old LaGrange Road to KY 393 Project length is 0.8 miles. | D |  | SLO | 2019 | 39000 | 39000 |  |  |  | 0 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; UPDATE FISCAL YEAR FROM 2019 TO 2020; MOD | STPM | 3001442 | Oldham | 5-754 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | Construct new connection from Old LaGrange Road to KY 393 Project length is 0.8 miles. | D |  | STP | 2020 | 39000 | 39000 |  |  |  | 0 |  | OBLIGATED | 39000 |  | 39000 | 2020 | 3RD QUARTER
TIP | [9 empty] | Oldham | 5-754 | [6 empty] | Construct new connection from Old LaGrange Road to KY 393 Project length is 0.8 miles. | U |  | SLO | 2019 | 326955 | 261566 |  |  |  | 65389 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; UPDATE FISCAL YEAR FROM 2019 TO 2020; MOD |  |  | Oldham | 5-754 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | Construct new connection from Old LaGrange Road to KY 393 Project length is 0.8 miles. | U |  | STP | 2020 | 326955 | 261566 |  |  |  | 65389 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.186 | 2020-05-06 | TIP FY 20-25, ADMIN MOD#2; UPDATE PROJECT DESCRIPTION AND FUND AMOUNT; MOD |  |  | Oldham | 5-754 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | The proposed project will extend Commerce Parkway and the shared use path west 0.8 mile from KY 393 on new alignment to connect with Mattingly Road. Commerce Pkwy in Oldham County is currently a 2-lane road with a 10-foot wide shared use path along the north side, separated from the road with a grass verge. The road currently extends from KY 393 east approximately 1200 ft. north of I-71 and KY 393 interchange. Mattingly Road provides access to several industrial sites. The proposed project will provide access to I-71 from Mattingly Road that would allow traffic to avoid an at-grade railroad crossing. | U |  | SLO | 2020 | 385808 | 308646 |  |  | 77162 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; UPDATE FISCAL YEAR; MOD |  |  | Oldham | 5-754 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | The proposed project will extend Commerce Parkway and the shared use path west 0.8 mile from KY 393 on new alignment to connect with Mattingly Road. Commerce Pkwy in Oldham County is currently a 2-lane road with a 10-foot wide shared use path along the north side, separated from the road with a grass verge. The road currently extends from KY 393 east approximately 1200 ft. north of I-71 and KY 393 interchange. Mattingly Road provides access to several industrial sites. The proposed project will provide access to I-71 from Mattingly Road that would allow traffic to avoid an at-grade railroad crossing. | U |  | SLO | 2021 | 385808 | 308646 |  |  | 77162 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.309 | 2021-06-10 | TIP FY 20-25, ADMIN MOD#17; UPDATE FUND AMOUNTS; MOD |  |  | Oldham | 5-754 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | The proposed project will extend Commerce Parkway and the shared use path west 0.8 mile from KY 393 on new alignment to connect with Mattingly Road. Commerce Pkwy in Oldham County is currently a 2-lane road with a 10-foot wide shared use path along the north side, separated from the road with a grass verge. The road currently extends from KY 393 east approximately 1200 ft. north of I-71 and KY 393 interchange. Mattingly Road provides access to several industrial sites. The proposed project will provide access to I-71 from Mattingly Road that would allow traffic to avoid an at-grade railroad crossing. | U |  | SLO | 2021 | 445808 | 368646 |  |  | 77162 | [5 empty] | 0
TIP | [6 empty] | NOT IN STIP |  |  | Oldham | 5-754 | [6 empty] | Construct new connection from Old LaGrange Road to KY 393 Project length is 0.8 miles. | R |  | SLO | 2018 | 851180 | 680944 |  |  |  | 170236 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.186 | 2020-05-06 | TIP FY 20-25, ADMIN MOD#2; ADD R PHASE TO STIP; NEW |  |  | Oldham | 5-754 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | The proposed project will extend Commerce Parkway and the shared use path west 0.8 mile from KY 393 on new alignment to connect with Mattingly Road. Commerce Pkwy in Oldham County is currently a 2-lane road with a 10-foot wide shared use path along the north side, separated from the road with a grass verge. The road currently extends from KY 393 east approximately 1200 ft. north of I-71 and KY 393 interchange. Mattingly Road provides access to several industrial sites. The proposed project will provide access to I-71 from Mattingly Road that would allow traffic to avoid an at-grade railroad crossing. | R |  | SLO | 2020 | 53438 | 42750 |  |  |  | 10688 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; UPDATE FISCAL YEAR & FUND AMOUNTS; MOD |  |  | Oldham | 5-754 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | The proposed project will extend Commerce Parkway and the shared use path west 0.8 mile from KY 393 on new alignment to connect with Mattingly Road. Commerce Pkwy in Oldham County is currently a 2-lane road with a 10-foot wide shared use path along the north side, separated from the road with a grass verge. The road currently extends from KY 393 east approximately 1200 ft. north of I-71 and KY 393 interchange. Mattingly Road provides access to several industrial sites. The proposed project will provide access to I-71 from Mattingly Road that would allow traffic to avoid an at-grade railroad crossing. | R |  | SLO | 2021 | 119688 | 95750 |  |  |  | 23938 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.29 | 2021-04-01 | TIP FY 20-25, ADMIN MOD#14; UPDATE FUND AMOUNTS; MOD |  |  | Oldham | 5-754 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | The proposed project will extend Commerce Parkway and the shared use path west 0.8 mile from KY 393 on new alignment to connect with Mattingly Road. Commerce Pkwy in Oldham County is currently a 2-lane road with a 10-foot wide shared use path along the north side, separated from the road with a grass verge. The road currently extends from KY 393 east approximately 1200 ft. north of I-71 and KY 393 interchange. Mattingly Road provides access to several industrial sites. The proposed project will provide access to I-71 from Mattingly Road that would allow traffic to avoid an at-grade railroad crossing. | R |  | SLO | 2021 | 53438 | 42750 |  |  |  | 10688 |  |  |  |  | 0
STIP | [9 empty] | OLDHAM | 5-754 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | Construct new connection from Old LaGrange Road to KY 393 Project length is 0.8 miles. | C |  | SLO | 2019 | 2300000 | 1840000 |  |  |  | 460000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.114 | 2019-08-12 | TIP FY 18-21, AMENDMENT#6; CHANGE OPEN TO PUBLIC DATE FROM 2020 TO 2021; MOD |  |  | OLDHAM | 5-754 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | Construct new connection from Old LaGrange Road to KY 393 Project length is 0.8 miles. | C |  | SLO | 2021 | 2300000 | 1840000 |  |  |  | 460000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; UPDATE FISCAL YEAR FROM 2021 TO 2020; MOD |  |  | OLDHAM | 5-754 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | Construct new connection from Old LaGrange Road to KY 393 Project length is 0.8 miles. | C |  | STP | 2020 | 2300000 | 1840000 |  |  |  | 460000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; UPDATE DESCRIPTION, FISCAL YEAR & FUND AMOUNTS; MOD |  |  | Oldham | 5-754 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | The proposed project will extend Commerce Parkway and the shared use path west 0.8 mile from KY 393 on new alignment to connect with Mattingly Road. Commerce Pkwy in Oldham County is currently a 2-lane road with a 10-foot wide shared use path along the north side, separated from the road with a grass verge. The road currently extends from KY 393 east approximately 1200 ft. north of I-71 and KY 393 interchange. Mattingly Road provides access to several industrial sites. The proposed project will provide access to I-71 from Mattingly Road that would allow traffic to avoid an at-grade railroad crossing. | C |  | STP | 2021 | 2875000 | 2300000 |  |  | 575000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.29 | 2021-04-01 | TIP FY 20-25, ADMIN MOD#14; UPDATE FUND AMOUNTS; MOD |  |  | Oldham | 5-754 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | The proposed project will extend Commerce Parkway and the shared use path west 0.8 mile from KY 393 on new alignment to connect with Mattingly Road. Commerce Pkwy in Oldham County is currently a 2-lane road with a 10-foot wide shared use path along the north side, separated from the road with a grass verge. The road currently extends from KY 393 east approximately 1200 ft. north of I-71 and KY 393 interchange. Mattingly Road provides access to several industrial sites. The proposed project will provide access to I-71 from Mattingly Road that would allow traffic to avoid an at-grade railroad crossing. | C |  | STP | 2021 | 2941250 | 2353000 |  |  | 588250 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.309 | 2021-06-10 | TIP FY 20-25, ADMIN MOD#17; UPDATE FUND AMOUNTS; MOD |  |  | Oldham | 5-754 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | The proposed project will extend Commerce Parkway and the shared use path west 0.8 mile from KY 393 on new alignment to connect with Mattingly Road. Commerce Pkwy in Oldham County is currently a 2-lane road with a 10-foot wide shared use path along the north side, separated from the road with a grass verge. The road currently extends from KY 393 east approximately 1200 ft. north of I-71 and KY 393 interchange. Mattingly Road provides access to several industrial sites. The proposed project will provide access to I-71 from Mattingly Road that would allow traffic to avoid an at-grade railroad crossing. | C |  | STP | 2021 | 2178050 | 1778000 |  |  | 400050
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.309 | 2021-06-10 | TIP FY 20-25, ADMIN MOD#17; ADD CRRSAA FUNDS TO THE C PHASE; MOD |  |  | Oldham | 5-754 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | The proposed project will extend Commerce Parkway and the shared use path west 0.8 mile from KY 393 on new alignment to connect with Mattingly Road. Commerce Pkwy in Oldham County is currently a 2-lane road with a 10-foot wide shared use path along the north side, separated from the road with a grass verge. The road currently extends from KY 393 east approximately 1200 ft. north of I-71 and KY 393 interchange. Mattingly Road provides access to several industrial sites. The proposed project will provide access to I-71 from Mattingly Road that would allow traffic to avoid an at-grade railroad crossing. | C |  |  | 2021 | 575000 | 575000
STIP | [9 empty] | OLDHAM | 5-757 | CS 2030 |  | 0 | 0.45 | SAFETY | BIKE/PED FACIL(O) | CONSTRUCT 5' CONCRETE SIDEWALKS IN THE EXISTING RIGHT-OF-WAY ALONG BOTH SIDES OF SPRING HILL TRACE FROM KY 329 TO THE END OF THE EXISTING SUBDIVISION, SLIGHTLY BEYOND SPRING HILL COURT (2014BOP). | U |  | SLO | 2019 | 75000 | 60000 |  |  |  | 15000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; UPDATE FISCAL YEAR FROM 2019 TO 2020; MOD |  |  | OLDHAM | 5-757 | CS 2030 |  | 0 | 0.45 | SAFETY | BIKE/PED FACIL(O) | The project is planned to include: widening or reconstruction of KY 329 to include dual left turn lanes and a signal; widening of the KY 329 Bypass to include a left turn lane onto KY 329 and right turn lane onto KY 329; and sight distance improvements on both the KY 329 Bypass and existing KY 329. | U |  | STP | 2020 | 75000 | 60000 |  |  |  | 15000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; UPDATE FISCAL YEAR & FUND AMOUNTS; MOD |  |  | OLDHAM | 5-757 | CS 2030 |  | 0 | 0.45 | SAFETY | BIKE/PED FACIL(O) | The project is planned to include: widening or reconstruction of KY 329 to include dual left turn lanes and a signal; widening of the KY 329 Bypass to include a left turn lane onto KY 329 and right turn lane onto KY 329; and sight distance improvements on both the KY 329 Bypass and existing KY 329. | U |  | STP | 2021 | 93750 | 75000 |  |  |  | 18750 |  |  |  |  | 0
STIP | [9 empty] | OLDHAM | 5-757 | CS 2030 |  | 0 | 0.45 | SAFETY | BIKE/PED FACIL(O) | CONSTRUCT 5' CONCRETE SIDEWALKS IN THE EXISTING RIGHT-OF-WAY ALONG BOTH SIDES OF SPRING HILL TRACE FROM KY 329 TO THE END OF THE EXISTING SUBDIVISION, SLIGHTLY BEYOND SPRING HILL COURT (2014BOP). | C |  | SLO | 2019 | 445000 | 356000 |  |  |  | 89000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.15 | 2019-12-02 | TIP FY 18-21, ADMIN MOD#38; UPDATE FISCAL YEAR FROM 2019 TO 2020; MOD |  |  | OLDHAM | 5-757 | CS 2030 |  | 0 | 0.45 | SAFETY | BIKE/PED FACIL(O) | The project is planned to include: widening or reconstruction of KY 329 to include dual left turn lanes and a signal; widening of the KY 329 Bypass to include a left turn lane onto KY 329 and right turn lane onto KY 329; and sight distance improvements on both the KY 329 Bypass and existing KY 329. | C |  | STP | 2020 | 445000 | 356000 |  |  |  | 89000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.262 | 2020-11-25 | TIP FY 20-25, ADMIN MOD#10; UPDATE FISCAL YEAR & FUND AMOUNTS; MOD |  |  | OLDHAM | 5-757 | CS 2030 |  | 0 | 0.45 | SAFETY | BIKE/PED FACIL(O) | The project is planned to include: widening or reconstruction of KY 329 to include dual left turn lanes and a signal; widening of the KY 329 Bypass to include a left turn lane onto KY 329 and right turn lane onto KY 329; and sight distance improvements on both the KY 329 Bypass and existing KY 329. | C |  | STP | 2021 | 556250 | 445000 |  |  |  | 111250 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.328 | 2021-08-30 | TIP FY 20-25, ADMIN MOD#19; UPDATE FUND AMOUNTS; MOD |  |  | OLDHAM | 5-757 | CS 2030 |  | 0 | 0.45 | SAFETY | BIKE/PED FACIL(O) | The project is planned to include: widening or reconstruction of KY 329 to include dual left turn lanes and a signal; widening of the KY 329 Bypass to include a left turn lane onto KY 329 and right turn lane onto KY 329; and sight distance improvements on both the KY 329 Bypass and existing KY 329. | C |  | STP | 2021 | 650000 | 520000 |  |  |  | 130000 |  |  |  |  | 0
TIP | [6 empty] | NOT IN STIP |  |  | Oldham | 5-757 | CS 2030 |  | 0 | 0.45 | SAFETY | BIKE/PED FACIL(O) | Construct sidewalks along both sides of Spring Hill Trace within existing right-of-way from KY 329 to the existing bridge between Spring Hill subdivision and Brentwood subdivision (approximately 240’ beyond the intersection of Spring Hill Trace and Spring Hill Court). | R |  | SLO | 2018 | 228086 | 186193 |  |  |  | 41893 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; ADD PROJECT TO STIP; NEW |  |  | Oldham | 5-4306 | KY 1793 |  | 0.92 | 1.06 | SAFETY | SAF-GUARDRAIL(P) | INSTALL GUARDRAIL ON KY-1793 IN OLDHAM COUNTY | C |  | STP | 2021 | 30000 | 24000 |  |  |  | 6000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; ADD PROJECT TO STIP; NEW |  |  | Oldham | 5-4308 | KY 362 |  | 2.3 | 2.53 | SAFETY | SAF-GUARDRAIL(P) | INSTALL GUARDRAIL ON KY-362 IN OLDHAM COUNTY | C |  | STP | 2024 | 49000 | 39200 |  |  | 9800 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; ADD PROJECT TO STIP; NEW |  |  | Oldham | 5-8852 | KY 53 |  | 3.068 | 5.685 | RELIABILITY | DESIGN ENGINEERING(O) | DESIGN FOR IMPROVING KY-53 FROM ZHALE SMITH ROAD TO KY-22 (TOTAL 3.2 MILES). (14CCN)(18CCN) | D |  | STP | 2023 | 2000000 | 1600000 |  |  | 400000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; ADD R PHASE TO STIP; NEW |  |  | Oldham | 5-9012 | KY 53 |  | 10.04 | 2.65 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 53 BEGINNING AT MP 10.040 AND EXTENDING TO MP 2.65 IN OLDHAM COUNTY. (2016BOP) | R |  | SAF | 2021 | 50000 | 45000 |  |  | 5000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.246 | 2020-10-09 | TIP FY 20-25, ADMIN MOD#9; ADD U PHASE TO STIP; NEW |  |  | Oldham | 5-9012 | KY 53 |  | 10.04 | 2.65 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 53 BEGINNING AT MP 10.040 AND EXTENDING TO MP 2.65 IN OLDHAM COUNTY. (2016BOP) | U |  | SAF | 2021 | 50000 | 45000 |  |  | 5000 | [5 empty] | 0
STIP | [9 empty] | Oldham | 5-9018 | Various Intersection Improvement Projects in KYTC District 5 | [5 empty] | Preliminary design and study to determine low cost improvements at KY 53 at KY 146 intersection between mile points 6.955 to 7.115 in Oldham County. | D |  | Safety | 2019 | 200000 | 200000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.015 | 2019-01-05 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW (NOTE: OLDHAM COUNTY IS ON KIDPA ADMIN MOD#2018.020) | HSIP | 9010350 | OLDHAM, FRANKLIN, SPENCER, SHELBY | 5-9018 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | PRELIMINARY DESIGN AND STUDY TO DETERMINE LOW COST IMPROVEMENTS AT VARIOUS INTERSECTIONS WITHIN DISTRICT 5. (2018BOP) | D |  | SAF | 2019 | 200000 | 200000 | [5 empty] | OBLIGATED | 200000 |  | 200000 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.093 | 2019-06-28 | TIP FY 18-21; ADMIN MOD#32; ADD PROJECT TO STIP; NEW | HSIP | 0711125 | OLDHAM | 5-9020 | I 71 |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | STUDY SAFETY IMPROVEMENTS ALONG I-71 IN OLDHAM COUNTY FROM MILE POINT 11.315 TO MILE POINT 24.727. | D |  | SAF | 2019 | 250000 | 250000 | [5 empty] | OBLIGATED | 225000 |  | 225000 | 2020 | 2ND QUARTER
STIP | [6 empty] | NOT IN TIP |  |  | OLDHAM | 5-10012 | KY 1488 |  | 2.031 | 2.037 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 1488 BRIDGE OVER ORGAN CREEK. (093B00048N) | D |  | BR/STP | 2019 | 280000 | 173600 |  |  | 106400 | [5 empty] | 0
STIP | [6 empty] | NOT IN TIP |  |  | OLDHAM | 5-10012 | KY 1488 |  | 2.031 | 2.037 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 1488 BRIDGE OVER ORGAN CREEK. (093B00048N) | C |  | BR/STP | 2020 | 343000 | 212660 |  |  | 130340 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.057 | 2019-04-26 | TIP FY 18-21, ADMIN MOD#29; UPDATE FUND AMOUNTS; MOD |  |  | OLDHAM | 5-10012 | KY 1488 |  | 2.031 | 2.037 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 1488 BRIDGE OVER ORGAN CREEK. (093B00048N) | C |  | BR/STP | 2020 | 737000 | 456940 |  |  |  | 280060 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.226 | 2020-08-28 | TIP FY 20-25, ADMIN MOD#7, ADD D PHASE TO STIP; NEW |  |  | OLDHAM | 5-20056 | I-71 |  | 22.3 | 24.727 | ASSET MANAGEMENT | AM-PAVEMENT(INT)(P) | ADDRESS PAVEMENT CONDITIONS OF I-71 BOTH DIRECTIONS FROM MILEPOINT 22.3 TO MILEPOINT 24.727. | D |  | NHPP | 2020 | 250000 | 200000 |  |  |  | 50000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.226 | 2020-08-28 | TIP FY 20-25, ADMIN MOD#7, ADD C PHASE TO STIP; NEW |  |  | OLDHAM | 5-20056 | I-71 |  | 22.3 | 24.727 | ASSET MANAGEMENT | AM-PAVEMENT(INT)(P) | ADDRESS PAVEMENT CONDITIONS OF I-71 BOTH DIRECTIONS FROM MILEPOINT 22.3 TO MILEPOINT 24.727. | C |  | NHPP | 2021 | 2500000 | 2000000 |  |  |  | 500000 |  |  |  |  | 0
TIP | [6 empty] | NOT IN STIP |  |  | Oldham |  | Various Sidewalks in Oldham County | [5 empty] | Construct various sidewalks in Oldham County | C |  | SLO | 2020 | 125000 | 100000 |  |  |  | 25000 |  |  |  |  | 0
TIP | [6 empty] | NOT IN STIP |  |  | Oldham |  | Various Sidewalks in Oldham County | [5 empty] | Construct various sidewalks in Oldham County | C |  | SLO | 2019 | 125000 | 100000 |  |  |  | 25000 |  |  |  |  | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.051 | 2019-04-18 | TIP FY 18-21, ADMIN MOD#28; KIPDA ID#1427; REMOVE THE FY 2019 CONSTRUCTION PHASE; MOD |  |  | Oldham |  | Various Sidewalks in Oldham County | [5 empty] | Construct various sidewalks in Oldham County | C |  | SLO | 2019 | [10 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.271 | 2021-01-12 | TIP FY 20-25, AMEND#2; ADD PROJECT TO STIP; NEW |  |  | Oldham | TBD | KY 22 | [5 empty] | Improve safety and reduce congestion on KY 22 from Haunz Lane to KY 329. Includes consideration of a three lane widening and bike/ped accommodations. | P |  | STP | 2021 | 281250 | 225000 |  |  | 56250 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.271 | 2021-01-12 | TIP FY 20-25, AMEND#2; ADD PROJECT TO STIP; NEW |  |  | Oldham | TBD | Kenwood Road | [5 empty] | Construct a newurban roadway section to connect KY 146 and KY 393 Bypass in Crestwood. The proposed facility will be three-lanes with a continuous center left-turn lane, curb, gutter, a sidewalk and a potential traffic signal. Lane width will be 11 feet with a proposed posted speed of 25 MPH. | D |  | STP | 2024 | 406250 | 325000 |  |  | 81250 | [5 empty] | 0
STIP | [9 empty] | OWEN | 6-1088 | CR 1214 | 0.04 | 0.22 | 0.26 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER CEDAR CREEK ON SAWDRIDGE CREEK W ROAD (CR 1214) 0.2 MI N OF US 127 (094C00011N) | C |  | BR/STP | 2020 | 672000 | 416640 |  |  | 255360 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.3 | 2021-05-28 | ADD R PHASE TO STIP; NEW |  |  | OWEN | 6-1088 | CR 1214 | 0.04 | 0.22 | 0.26 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER CEDAR CREEK ON SAWDRIDGE CREEK W ROAD (CR 1214) 0.2 MI N OF US 127 (094C00011N) | R |  | STP | 2021 | 32000 | 32000 | [8 empty] | 0
STIP | [9 empty] | OWEN | 6-10013 | KY 3102 |  | 3.005 | 3.017 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 3102 BRIDGE OVER BRUSH CREEK. (094B00034N) | D |  | BR/STP | 2019 | 280000 | 173600 |  |  | 106400 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030111 | OWEN | 6-10013 | KY 3102 |  | 3.005 | 3.017 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 3102 BRIDGE OVER BRUSH CREEK. (094B00034N) | C |  | BR/STP | 2020 | 1942500 | 1204350 |  |  | 738150 |  |  | OBLIGATED |  | 391950 | 391950 | 2019 | 3RD QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.139 | 2019-10-25 | ADD PROJECT TO STIP; PARENT NO. 99-65.17; NEW |  |  | OWEN | 6-10052 | CR 1325 |  |  |  | ASSET MANAGEMENT | AM-BRIDGE (P) | BRIDGE REPAIRS ON BIG TWIN CREEK RD (CR-1325) OVER PUNCHEON CAMP BRANCH. (094C00019N)(2018BOP) | C |  | STP | 2020 | 290000 | 290000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.161 | 2020-02-21 | INCREASE FUNDS BASED ON NEW ESTIMATE; MOD | STPBRZ | 9030251 | OWEN | 6-10052 | CR 1325 |  |  |  | ASSET MANAGEMENT | AM-BRIDGE (P) | BRIDGE REPAIRS ON BIG TWIN CREEK RD (CR-1325) OVER PUNCHEON CAMP BRANCH. (094C00019N)(2018BOP) | C |  | STP | 2020 | 310500 | 310500 | [5 empty] | OBLIGATED | 50000 | 255325 | 305325 | 2020 | 2ND QUARTER
STIP | [9 empty] | OWEN | 6-20052 | KY 22 | 7.23 | 11.33 | 18.56 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION ON KY-22 FROM MILEPOINT 11.33 TO MILEPOINT 18.56 | C |  | PM/STP | 2022 | 947000 | 757600 |  |  | 189400 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.254 | 2020-11-06 | ADD D PHASE TO STIP; PARENT NO. 99-224.14; NEW |  |  | OWEN | 6-20059 | KY 355 |  | 6.56 | 18.923 | RELIABILITY | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION ON KY-355 FROM MP 6.56 TO MP 18.923. | D |  | STP | 2021 | 310000 | 310000 | [8 empty] | 0
STIP | [9 empty] | OWSLEY | 10-279.61 | KY 30 | 13.562 | 0 | 5.166 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE KY-30 FROM KY-847 IN OWSLEY COUNTY TO JACKSON COUNTY LINE.(LET W/ JACKSON CO. SECTION UNDER 11-278.30)(SEE 10-279.60 FOR PE & ENVIR)(AR/W)(14CCR)(16CCR)(18CCR) | C |  | STP | 2019 | 14500000 | 14500000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.101 | 2019-07-18 | UPDATE FUND AMOUNT; TOTAL CONSTRUCTION COST COMBINES THE JACKSON COUNTY SECTION OF KY 30 (ITEM NO. 11-279.61); MOD | STP | 0302025 | OWSLEY JACKSON | 10-279.61 | KY 30 | 13.562 | 0 | 5.166 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE KY-30 FROM KY-847 IN OWSLEY COUNTY TO JACKSON COUNTY LINE.(LET W/ JACKSON CO. SECTION UNDER 11-278.30)(SEE 10-279.60 FOR PE & ENVIR)(AR/W)(14CCR)(16CCR)(18CCR) | C |  | STP | 2019 | 53900000 | 53900000 |  |  | 0 |  |  | OBLIGATED | 10520440.1 | 55942475 | 66462915.1 | 2019 | 4TH QUARTER
STIP | [9 empty] | OWSLEY | 10-279.62 | KY 30 | 13.562 | 0 | 5.166 | RELIABILITY | PREFINANCD CONVRSN(P) | IMPROVE KY-30 FROM KY-847 IN OWSLEY COUNTY TO JACKSON COUNTY LINE.(LET W/ JACKSON CO. SECTION UNDER 11-278.30)(SEE 10-279.60 FOR PE & ENVIR)(AR/W)(14CCR)(16CCR)(18CCR) | C |  | STP | 2021 | 14500000 | 11600000 |  |  | 2900000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.279 | 2021-03-05 | ADD C PHASE TO STIP; NEW |  |  | PENDLETON | 6-8706 | US 27 |  | 17.9 | 19.34 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE SAFETY ON US-27 FROM BUTLER IN PENDLETON COUNTY TO SOUTH OF KY-154 IN CAMPBELL COUNTY.(12CCN)(14CCR) | C |  | STP | 2021 | 5036900 | 5036900 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | PENDLETON | 6-10004 | KY 159 |  | 4.658 | 4.68 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-159 BRIDGE OVER NORTH LITTLE KINCAID CRE. (096B00006N) | D |  | BR/STP | 2019 | 210000 | 130200 |  |  | 79800 | [5 empty] | 0
STIP | [9 empty] | PENDLETON | 6-10004 | KY 159 |  | 4.658 | 4.68 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-159 BRIDGE OVER NORTH LITTLE KINCAID CRE. (096B00006N) | C |  | BR/STP | 2020 | 490000 | 303800 |  |  | 186200 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.065 | 2019-05-06 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030112 | PENDLETON | 6-10004 | KY 159 |  | 4.658 | 4.68 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-159 BRIDGE OVER NORTH LITTLE KINCAID CRE. (096B00006N) | C |  | BR/STP | 2019 | 1538730 | 1538730 |  |  | 0 |  |  | OBLIGATED |  | 1257755 | 1257755 | 2019 | 3RD QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.123 | 2019-09-06 | ADD PROJECT TO STIP; PARENT NO. 99-65.16 AND 99-65.17; NEW |  |  | PENDLETON | 6-10014 | CR 1110 |  | 8.151 |  | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES ON MILFORD RD (CR 1110) OVER MILL CREEK. (096C00015N) | C |  | BR | 2020 | 340000 | 340000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | PERRY | 10-209 | KY 476 | 0.9 | 0 | 0.9 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE KY-476 FROM KY-15X IN WALKERTOWN TO NORTH OF WALKER CORNETT ROAD IN WABACO. | D |  | STP | 2021 | 600000 | 480000 |  |  | 120000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.306 | 2021-06-16 | ADD D PHASE TO STIP; NEW |  |  | PERRY | 10-269.20 | KY 15 |  | 16.847 | 20.135 | RELIABILITY | MAJOR WIDENING(O) | RECONSTRUCTION OF KY 15 FROM BONNYMAN TO NEAR KY 28. (14CCN) (2020CCN) | D |  | SPP | 2021 | 1500100 | 100 |  |  | 1500000 | [5 empty] | 0
STIP | [9 empty] | PERRY | 10-1113 | CR 1114 | 0.047 | 0.07 | 0.117 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER NORTH FORK KENTUCKY RIVER ON KENMONT ROAD (CR 1114) 380 FT SE OF KY 7 (097C00005N) | D |  | BR/STP | 2019 | 224000 | 138880 |  |  | 85120 | [5 empty] | 0
STIP | [9 empty] | PERRY | 10-1113 | CR 1114 | 0.047 | 0.07 | 0.117 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER NORTH FORK KENTUCKY RIVER ON KENMONT ROAD (CR 1114) 380 FT SE OF KY 7 (097C00005N) | C |  | BR/STP | 2020 | 1400000 | 868000 |  |  | 532000 | [5 empty] | 0
STIP | [9 empty] | PERRY | 10-1114 | CR 1140 | 0.009 | 0 | 0.009 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER STRAIGHT FORK ON LITTLE LEATHERWOOD CREEK ROAD (CR 1140) AT JCT WITH KY 3348 (097C00013N) | D |  | BR/STP | 2019 | 182000 | 112840 |  |  | 69160 | [5 empty] | 0
STIP | [9 empty] | PERRY | 10-1114 | CR 1140 | 0.009 | 0 | 0.009 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER STRAIGHT FORK ON LITTLE LEATHERWOOD CREEK ROAD (CR 1140) AT JCT WITH KY 3348 (097C00013N) | C |  | BR/STP | 2020 | 504000 | 312480 |  |  | 191520 | [5 empty] | 0
STIP | [9 empty] | PERRY | 10-8903 | HR 9006 | 0.2 | 54.9 | 55.1 | RELIABILITY | NEW INTERCHANGE(O) | NEW INTERCHANGE OFF OF A NEW EXIT 55 HAL ROGERS PARKWAY. (16CCN)(18CCN) | R |  | STP | 2019 | 1200000 | 1200000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | PERRY | 10-8903 | HR 9006 | 0.2 | 54.9 | 55.1 | RELIABILITY | NEW INTERCHANGE(O) | NEW INTERCHANGE OFF OF A NEW EXIT 55 HAL ROGERS PARKWAY. (16CCN)(18CCN) | U |  | STP | 2020 | 320000 | 320000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | PERRY | 10-8903 | HR 9006 | 0.2 | 54.9 | 55.1 | RELIABILITY | NEW INTERCHANGE(O) | NEW INTERCHANGE OFF OF A NEW EXIT 55 HAL ROGERS PARKWAY. (16CCN)(18CCN) | C |  | STP | 2021 | 1632000 | 1305600 |  |  | 326400 | [5 empty] | 0
STIP | [9 empty] | PERRY | 10-8906 | KY 80 | 4.6 | 0 | 4.6 | RELIABILITY | SAFETY(P) | SAFETY IMPROVEMENTS ON KY-80 FROM LESLIE COUNTY LINE TO KY-451. (16CCN) | D |  | STP | 2019 | 700000 | 700000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | PERRY | 10-8906 | KY 80 | 4.6 | 0 | 4.6 | RELIABILITY | SAFETY(P) | SAFETY IMPROVEMENTS ON KY-80 FROM LESLIE COUNTY LINE TO KY-451. (16CCN) | R |  | STP | 2020 | 350000 | 350000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.139 | 2019-10-25 | INCREASE FUNDING COSTS FOR R PHASE; MOD | STP | 5271045 | PERRY | 10-8906 | KY 80 | 4.6 | 0 | 4.6 | RELIABILITY | SAFETY(P) | SAFETY IMPROVEMENTS ON KY-80 FROM LESLIE COUNTY LINE TO KY-451. (16CCN) | R |  | STP | 2020 | 815000 | 815000 |  |  | 0 |  |  | OBLIGATED | 550000 |  | 550000 | 2020 | 3RD QUARTER
STIP | [9 empty] | PERRY | 10-8906 | KY 80 | 4.6 | 0 | 4.6 | RELIABILITY | SAFETY(P) | SAFETY IMPROVEMENTS ON KY-80 FROM LESLIE COUNTY LINE TO KY-451. (16CCN) | U |  | STP | 2020 | 280000 | 280000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.139 | 2019-10-25 | INCREASE FUNDING COSTS FOR U PHASE; MOD |  |  | PERRY | 10-8906 | KY 80 | 4.6 | 0 | 4.6 | RELIABILITY | SAFETY(P) | SAFETY IMPROVEMENTS ON KY-80 FROM LESLIE COUNTY LINE TO KY-451. (16CCN) | U |  | STP | 2020 | 840000 | 840000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | PERRY | 10-8906 | KY 80 | 4.6 | 0 | 4.6 | RELIABILITY | SAFETY(P) | SAFETY IMPROVEMENTS ON KY-80 FROM LESLIE COUNTY LINE TO KY-451. (16CCN) | C |  | STP | 2022 | 5400000 | 4320000 |  |  | 1080000 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 1003272 | PERRY | 10-8910 | KY 1166 | 0.04 | 0.64 | 0.648 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON KY-1166 OVER RT. FK. MACES CREEK. (16CCN) 097B00110N | C |  | BR/STP | 2020 | 938000 | 581560 |  |  | 356440 |  |  | OBLIGATED | 1290661 | 323000 | 1613661 | 2019 | 3RD QUARTER
STIP | [9 empty] | PERRY | 10-8913 | KY 1166 |  | 4.283 | 4.291 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON KY 1166 OVER MACES CREEK. (16CCN) 097B00072N (SD) | C |  | BR/STP | 2020 | 742000 | 460040 |  |  | 281960 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.103 | 2019-07-29 | UPDATE FUNDING AMOUNT; MOD | STPBRZ | 1003274 | PERRY | 10-8913 | KY 1166 |  | 4.283 | 4.291 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON KY 1166 OVER MACES CREEK. (16CCN) 097B00072N (SD) | C |  | BR/STP | 2019 | 1370000 | 1370000 |  |  | 0 |  |  | OBLIGATED | 248592.47 | 1611034.53 | 1859627 | 2019 | 4TH QUARTER
STIP | [7 empty] | STPBRO | 1003270 | PERRY | 10-8915 | CR 1150 | 0.05 | 0 | 0.05 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER LEATHERWOOD CREEK. (16CCN) 097C00021N | C |  | BR/STP | 2020 | 455000 | 282100 |  |  | 172900 |  |  | OBLIGATED | 415000 | 327270.4 | 742270.4 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.111 | 2019-08-02 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 5271046 | PERRY | 10-9015 | KY 80 |  | 0 | 7.054 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 80 FROM MP 0.000 TO MP 7.054 IN PERRY COUNTY. (2018BOP) | D |  | SAF | 2019 | 350000 | 350000 |  |  | 0 |  |  | OBLIGATED | 350000 |  | 350000 | 2019 | 4TH QUARTER
STIP | [9 empty] | PERRY | 10-10004 | CR 1115 |  | 0.32 | 0.326 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF GEORGES BRANCH RD BRIDGE OVER GEORGES BRANCH. (097C00007N) | D |  | BR/STP | 2019 | 140000 | 86800 |  |  | 53200 | [5 empty] | 0
STIP | [9 empty] | PERRY | 10-10004 | CR 1115 |  | 0.32 | 0.326 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF GEORGES BRANCH RD BRIDGE OVER GEORGES BRANCH. (097C00007N) | C |  | BR/STP | 2020 | 390000 | 241800 |  |  | 148200 | [5 empty] | 0
STIP | [9 empty] | PERRY | 10-10005 | CR 1145 |  | 0.121 | 0.127 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF OWENS BR RD BRIDGE OVER OWENS BRANCH. (097C00018N) | D |  | BR/STP | 2019 | 140000 | 86800 |  |  | 53200 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030087 | PERRY | 10-10005 | CR 1145 |  | 0.121 | 0.127 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF OWENS BR RD BRIDGE OVER OWENS BRANCH. (097C00018N) | C |  | BR/STP | 2020 | 340000 | 210800 |  |  | 129200 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.046 | 2019-04-07 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030087 | PERRY | 10-10005 | CR 1145 |  | 0.121 | 0.127 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF OWENS BR RD BRIDGE OVER OWENS BRANCH. (097C00018N) | C |  | BR/STP | 2019 | 365118 | 365118 |  |  | 0 |  |  | OBLIGATED |  | 310490 | 310490 | 2019 | 3RD QUARTER
STIP | [9 empty] | PERRY | 10-10006 | CR 1083 |  | 0.026 | 0.044 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF HALL OLD HOME PLACE BRIDGE OVER BIG CREEK. (097C00084N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [9 empty] | PERRY | 10-10006 | CR 1083 |  | 0.026 | 0.044 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF HALL OLD HOME PLACE BRIDGE OVER BIG CREEK. (097C00084N) | C |  | BR/STP | 2020 | 613000 | 380060 |  |  | 232940 | [5 empty] | 0
STIP | [9 empty] | PERRY | 10-10017 | KY 476 |  | 12.419 | 12.435 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 476 BRIDGE OVER BALL FORK. (097B00007N) | D |  | BR/STP | 2019 | 210000 | 130200 |  |  | 79800 | [5 empty] | 0
STIP | [9 empty] | PERRY | 10-10017 | KY 476 |  | 12.419 | 12.435 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 476 BRIDGE OVER BALL FORK. (097B00007N) | C |  | BR/STP | 2020 | 840000 | 520800 |  |  | 319200 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.118 | 2019-08-19 | ADD PROJECT TO STIP; NEW | STPBRZ | 9030168 | PERRY | 10-10025 | CS 2014 |  | 0.007 |  | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES ON LOWER HONEYSUCKLE (CS 2014) OVER MONTGOMERY CREEK. (097C00053N) | C |  | STP | 2020 | 210979 | 210979 |  |  | 0 |  |  | OBLIGATED |  | 238853.44 | 238853.44 | 2019 | 4TH QUARTER
STIP | [9 empty] | PERRY | 10-20003 | KY 80 |  | 7.9 | 8.4 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | D |  | PM/NH | 2019 | 100000 | 80000 |  |  | 20000 | [5 empty] | 0
STIP | [9 empty] | PERRY | 10-20003 | KY 80 |  | 7.9 | 8.4 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT | C |  | PM/NH | 2019 | 100000 | 80000 |  |  | 20000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.229 | 2020-09-14 | ADD C PHASE TO STIP; PARENT NO. 99-224.14; NEW |  |  | PERRY | 10-20027 | KY 699 KY 476 |  | .334 1.91 | 11.995 8.9 | RELIABILITY | AM-PAVEMENT (PRI)(P) | RESURFACING OF KY 699 FROM MP.334 TO 11.995 AND KY 476 FROM MP 1.91 TO 8.9 IN PERRY COUNTY. | C |  | STP | 2020 | 1668445 | 1668445 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.254 | 2020-11-06 | ADD D PHASE TO STIP; PARENT NO. 224.14; NEW |  |  | PERRY | 10-20030 | KY 15 |  | 0 | 4 | RELIABILITY | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION ON KY-15 FROM MP 0.0 TO MP 4.0. | D |  | NH | 2021 | 250000 | 250000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.291 | 2021-04-23 | ADD C PHASE TO STIP; PARENT NO. 99-224.14; NEW |  |  | PERRY | 10-20030 | KY 15 |  | 0 | 4 | RELIABILITY | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION ON KY-15 FROM MP 0.0 TO MP 4.0. | C |  | NHPP | 2021 | 1331000 | 1331000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.306 | 2021-06-16 | ADD D PHASE TO STIP; NEW |  |  | PERRY | 10-80100 | [5 empty] | NEW ROUTE(O) | NEW IMPROVED ACCESS TO WENDALL FORD AIRPORT (2020CCN) | D |  | SPP | 2021 | 1200100 | 100 |  |  | 1200000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.283 | 2021-03-22 | ADD R PHASE TO STIP; NEW |  |  | PIKE | 12-198 | KY 194 |  | 17.951 | 21 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE KY 194 FROM US 119 RAMP NEAR SMITH FARMS BOTTOM (CR 1458) TO NEAR DESKINS BRANCH CULVERT. (18CCR) (2020CCR) | R |  | STP | 2021 | 2150000 | 2150000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | PIKE | 12-263.67 | US 460 | 0.4 |  |  | RELIABILITY | RELOCATION(O) | PIKEVILLE TO VA. STATE LINE: IMPROVE US 460/KY 80 FROM DUNLEARY HOLLOW TO KY 80 AT BEAVER CREEK (SECTION 6C) BRIDGE ONLY.(14CCN)(16CCR) | C |  | NH | 2021 | 10000000 | 8000000 |  |  | 2000000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.244 | 2020-10-16 | UPDATE FUND AMOUNT BASED ON NEW ESTIMATE; MOD |  |  | PIKE | 12-263.67 | US 460 |  |  |  | RELIABILITY | RELOCATION(O) | PIKEVILLE TO VA. STATE LINE: IMPROVE US 460/KY 80 FROM DUNLEARY HOLLOW TO KY 80 AT BEAVER CREEK (SECTION 6C) BRIDGE ONLY.(14CCN)(16CCR) | C |  | NH | 2021 | 91022500 | 91022500 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | PIKE | 12-263.95 | US 460 | 0.4 |  |  | RELIABILITY | PREFINANCD CONVRSN(O) | PIKEVILLE TO VA. STATE LINE: IMPROVE US 460/KY 80 FROM DUNLEARY HOLLOW TO KY 80 AT BEAVER CREEK (SECTION 6C) BRIDGE ONLY.(14CCN)(16CCR)(ADDITIONAL FUNDING FOR C PHASE UNDER 12-263.67) | C |  | NH | 2022 | 10000000 | 8000000 |  |  | 2000000 | [5 empty] | 0
STIP | [9 empty] | PIKE | 12-346 | US 460 | 0.2 | 2.57 | 2.77 | RELIABILITY | MINOR WIDENING(O) | IMPROVE SAFETY AND REDUCE CONGESTION AT THE US-460 AND KY-1460 INTERSECTION. | D |  | NH | 2021 | 240000 | 192000 |  |  | 48000 | [5 empty] | 0
STIP | [9 empty] | PIKE | 12-346 | US 460 | 0.2 | 2.57 | 2.77 | RELIABILITY | MINOR WIDENING(O) | IMPROVE SAFETY AND REDUCE CONGESTION AT THE US-460 AND KY-1460 INTERSECTION. | R |  | NH | 2022 | 400000 | 320000 |  |  | 80000 | [5 empty] | 0
STIP | [9 empty] | PIKE | 12-346 | US 460 | 0.2 | 2.57 | 2.77 | RELIABILITY | MINOR WIDENING(O) | IMPROVE SAFETY AND REDUCE CONGESTION AT THE US-460 AND KY-1460 INTERSECTION. | U |  | NH | 2022 | 160000 | 128000 |  |  | 32000 | [5 empty] | 0
STIP | [7 empty] | STPBRO | 1203394 | PIKE | 12-1115 | KY 1441 | 0.04 | 10.279 | 10.319 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON FISHTRAP RD (KY 1441) OVER RACCOON CREEK AT INTERSECTION WITH COON CREEK (CR 1371) 098B00093N | C |  | BR/STP | 2019 | 665000 | 412300 |  |  | 252700 |  |  | OBLIGATED |  | 1700544 | 1700544 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.118 | 2019-08-19 | ADD PROJECT TO STIP; NEW |  |  | PIKE | 12-1116 | CR 1008 |  | 0 | 0.04 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON ROCKLICK BRANCH (CR 1008) OVER RIGHT FORK BEAVER CREEK AT JUNCTION WITH SOUTH HIGHWAY 7 (060C00006N). | C |  | STP | 2019 | 966000 | 966000 |  |  | 0 |  |  | OBLIGATED | 981218 | 719326 | 1700544 | 2019 | 2ND QUARTER
STIP | [7 empty] | STPBRZ | 1203413 | PIKE | 12-1122 | CR 1181 | 0.038 | 0.04 | 0.078 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER LEVISA FORK ON SOUTH RIVER ROAD CONNECTOR (CR 1181-70) AT JCT WITH US 460 NEAR VIRGINIA STATE LN (098C00088N) | C |  | BR/STP | 2019 | 980000 | 607600 |  |  | 372400 |  |  | OBLIGATED |  | 683376 | 683376 | 2019 | 3RD QUARTER
STIP | [9 empty] | PIKE | 12-1123 | CR 1801 | 0.265 | 0.005 | 0.027 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER BLACKBERRY CREEK ON BIG BLUE SPRINGS ROAD (CR 1801) AT JCT WITH KY 1056 (098C00028N) | C |  | BR/STP | 2019 | 210000 | 130200 |  |  | 79800 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.126 | 2019-09-20 | ADD PROJECT TO STIP; PARENT NO. 99-911.05; NEW | HSIP | 5361008 | PIKE | 12-9002 | KY 632 |  | 0 | 7 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 632 FROM KY 194 (MP 0.00) TO 0.037 MI EAST OF BLACKBERRY FRK (CR-1576) AT (MP 7.00) IN PIKE COUNTY. (2016BOP) | C |  | SAF | 2019 | 1768000 | 1768000 |  |  | 0 |  |  | OBLIGATED |  | 1768000 | 1768000 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.175 | 2020-04-09 | ADD D PHASE TO STIP; PARENT NO. 911.09; NEW |  |  | PIKE | 12-9014 | KY 80 |  | 0 | 1.65 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 80 FROM MP 0.000 TO MP 1.650 IN PIKE COUNTY, KY. (2018BOP) | D |  | SAF | 2020 | 200000 | 200000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.175 | 2020-04-09 | ADD D PHASE TO STIP; PARENT NO. 911.09; NEW |  |  | PIKE | 12-9015 | US 460 |  | 22.461 | 25.325 | SAFETY | SAFETY-HAZARD ELIM(P) | PEFORM LOW COST SAFETY IMPROVEMENTS ON US 460 FROM MP 22.461 TO MP 25.325 IN PIKE COUNTY, KY. (2018BOP) | D |  | SAF | 2020 | 200000 | 200000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | PIKE | 12-10008 | KY 199 |  | 8.876 | 8.882 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-199 BRIDGE OVER PINSONS CREEK. (098B00032N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [9 empty] | PIKE | 12-10008 | KY 199 |  | 8.876 | 8.882 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-199 BRIDGE OVER PINSONS CREEK. (098B00032N) | C |  | BR/STP | 2020 | 484400 | 300328 |  |  | 184072 | [5 empty] | 0
STIP | [9 empty] | PIKE | 12-10009 | KY 199 |  | 6.591 | 6.597 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-199 BRIDGE OVER POND CREEK. (098B00036N) | D |  | BR/STP | 2019 | 140000 | 86800 |  |  | 53200 | [5 empty] | 0
STIP | [9 empty] | PIKE | 12-10009 | KY 199 |  | 6.591 | 6.597 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-199 BRIDGE OVER POND CREEK. (098B00036N) | C |  | BR/STP | 2020 | 331100 | 205282 |  |  | 125818 | [5 empty] | 0
STIP | [9 empty] | PIKE | 12-10010 | KY 3419 |  | 11.321 | 11.329 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-3419 BRIDGE OVER LEFT FK BLACKBERRY CR. (098B00180N) | D |  | BR/STP | 2019 | 210000 | 130200 |  |  | 79800 | [5 empty] | 0
STIP | [9 empty] | PIKE | 12-10010 | KY 3419 |  | 11.321 | 11.329 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-3419 BRIDGE OVER LEFT FK BLACKBERRY CR. (098B00180N) | C |  | BR/STP | 2020 | 618450 | 383439 |  |  | 235011 | [5 empty] | 0
STIP | [9 empty] | PIKE | 12-10011 | CR 1517 |  | 0.083 | 0.089 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF PIGEON ROOST RD BRIDGE OVER BIG CREEK. (098C00005N) | D |  | BR/STP | 2019 | 157500 | 97650 |  |  | 59850 | [5 empty] | 0
STIP | [9 empty] | PIKE | 12-10011 | CR 1517 |  | 0.083 | 0.089 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF PIGEON ROOST RD BRIDGE OVER BIG CREEK. (098C00005N) | C |  | BR/STP | 2020 | 389200 | 241304 |  |  | 147896 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.075 | 2019-05-28 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030145 | PIKE | 12-10011 | CR 1517 |  | 0.083 | 0.089 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF PIGEON ROOST RD BRIDGE OVER BIG CREEK. (098C00005N) | C |  | STP | 2020 | 475000 | 475000 |  |  | 0 |  |  | OBLIGATED |  | 507705 | 507705 | 2019 | 3RD QUARTER
STIP | [9 empty] | PIKE | 12-10012 | CR 1545 |  | 0.004 | 0.014 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF MULLEN FRK BRIDGE OVER POND CREEK. (098C00021N) | D |  | BR/STP | 2019 | 140000 | 86800 |  |  | 53200 | [5 empty] | 0
STIP | [9 empty] | PIKE | 12-10012 | CR 1545 |  | 0.004 | 0.014 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF MULLEN FRK BRIDGE OVER POND CREEK. (098C00021N) | C |  | BR/STP | 2020 | 567280 | 351713.6 |  |  | 215566.4 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.123 | 2019-09-06 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD |  |  | PIKE | 12-10012 | CR 1545 |  | 0.004 | 0.014 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF MULLEN FRK BRIDGE OVER POND CREEK. (098C00021N) | C |  | BR | 2020 | 748000 | 748000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | PIKE | 12-10013 | CR 1906 |  | 1.424 | 1.43 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BEEFHIDE CRK BRIDGE OVER BEEFHIDE CREEK. (098C00119N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [9 empty] | PIKE | 12-10013 | CR 1906 |  | 1.424 | 1.43 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BEEFHIDE CRK BRIDGE OVER BEEFHIDE CREEK. (098C00119N) | C |  | BR/STP | 2020 | 506100 | 313782 |  |  | 192318 | [5 empty] | 0
STIP | [9 empty] | PIKE | 12-10024 | CR 1789 |  | 0.024 | 0.04 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF ELWOOD RD BRIDGE OVER SHELBY CREEK. (098C00080N) | D |  | BR/STP | 2019 | 192500 | 119350 |  |  | 73150 | [5 empty] | 0
STIP | [9 empty] | PIKE | 12-10024 | CR 1789 |  | 0.024 | 0.04 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF ELWOOD RD BRIDGE OVER SHELBY CREEK. (098C00080N) | C |  | BR/STP | 2020 | 930580 | 576959.6 |  |  | 353620.4 | [5 empty] | 0
STIP | [9 empty] | PIKE | 12-10025 | CR 1360Q4 |  | 0.049 | 0.057 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF RIGHT FORK OF BRUS BRIDGE OVER LEFT FK.BRUSHY FORK. (098C00091N) | D |  | BR/STP | 2019 | 157500 | 97650 |  |  | 59850 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030078 | PIKE | 12-10025 | CR 1360Q4 |  | 0.049 | 0.057 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF RIGHT FORK OF BRUS BRIDGE OVER LEFT FK.BRUSHY FORK. (098C00091N) | C |  | BR/STP | 2020 | 444500 | 275590 |  |  | 168910 |  |  | OBLIGATED |  | 310555 | 310555 | 2019 | 3RD QUARTER
STIP | [9 empty] | PIKE | 12-10026 | CR 1911 |  | 0.309 | 0.323 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF CANEY HWY #1 BRIDGE OVER CANEY CREEK. (098C00113N) | D |  | BR/STP | 2019 | 140000 | 86800 |  |  | 53200 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030091 | PIKE | 12-10026 | CR 1911 |  | 0.309 | 0.323 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF CANEY HWY #1 BRIDGE OVER CANEY CREEK. (098C00113N) | C |  | BR/STP | 2020 | 530250 | 328755 |  |  | 201495 |  |  | OBLIGATED |  | 633720 | 633720 | 2019 | 3RD QUARTER
STIP | [9 empty] | PIKE | 12-10027 | CR 1460 |  | 0.03 | 0.058 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF DESKINS RD BRIDGE OVER JOHNS CREEK. (098C00170N) | D |  | BR/STP | 2019 | 227500 | 141050 |  |  | 86450 | [5 empty] | 0
STIP | [9 empty] | PIKE | 12-10027 | CR 1460 |  | 0.03 | 0.058 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF DESKINS RD BRIDGE OVER JOHNS CREEK. (098C00170N) | C |  | BR/STP | 2020 | 875000 | 542500 |  |  | 332500 | [5 empty] | 0
STIP | [9 empty] | PIKE | 12-20002 | US 23 |  | 29.5 | 32.78 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT | D |  | PM/NH | 2020 | 525000 | 420000 |  |  | 105000 | [5 empty] | 0
STIP | [9 empty] | PIKE | 12-20002 | US 23 |  | 29.5 | 32.78 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT | C |  | PM/NH | 2020 | 5250000 | 4200000 |  |  | 1050000 | [5 empty] | 0
STIP | [9 empty] | PIKE | 12-20003 | US 119 |  | 10.4 | 12.4 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT | D |  | PM/NH | 2021 | 175000 | 140000 |  |  | 35000 | [5 empty] | 0
STIP | [9 empty] | PIKE | 12-20003 | US 119 |  | 10.4 | 12.4 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT | C |  | PM/NH | 2021 | 1750000 | 1400000 |  |  | 350000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.203 | 2020-07-15 | ADD D PHASE TO STIP; NEW |  |  | POWELL | 10-150 | CR 1316 |  | 0.07 | 0.57 | RELIABILITY | PAVE RECON W/ALIGN | RECONSTRUCT ROADWAY OUT OF FLOODWAY/FLOODWAY IN ORDER TO ELIMINATE MOUNTAIN PARKWAY ACCESS. (2020CCR) | D |  | STP | 2020 | 500000 | 500000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.274 | 2021-02-04 | ADD U PHASE TO STIP; NEW |  |  | POWELL | 10-150 | CR 1316 |  | 0.07 | 0.57 |  | RECONSTRUCTION(O) | RECONSTRUCT ROADWAY OUT OF FLOODWAY/FLOODWAY IN ORDER TO ELIMINATE MOUNTAIN PARKWAY ACCESS. (2020CCR) | U |  | STP | 2021 | 105000 | 105000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.274 | 2021-02-04 | ADD R PHASE TO STIP; NEW |  |  | POWELL | 10-150 | CR 1316 |  | 0.07 | 0.57 |  | RECONSTRUCTION(O) | RECONSTRUCT ROADWAY OUT OF FLOODWAY/FLOODWAY IN ORDER TO ELIMINATE MOUNTAIN PARKWAY ACCESS. (2020CCR) | R |  | STP | 2021 | 420000 | 420000 |  |  | 0 | [5 empty] | 0
[8 empty] | HSIP | 5303008 | POWELL | 10-163 | KY 213 |  | 7.595 | 11.271 | SAFETY | SAFETY(P) | IMPROVE SAFETY AND GEOMETRICS, AND REDUCE CONGESTION KY-213 FROM KY-11 TO BOTTOM OF MOUNTAIN. (12CCR)(16CCR) | R |  | SAF | 2019 | [7 empty] | OBLIGATED | 4000000 |  | 4000000 | 2019 | 1ST QUARTER
[8 empty] | HSIP | 5303008 | POWELL | 10-163 | KY 213 |  | 7.595 | 11.271 | SAFETY | SAFETY(P) | IMPROVE SAFETY AND GEOMETRICS, AND REDUCE CONGESTION KY-213 FROM KY-11 TO BOTTOM OF MOUNTAIN. (12CCR)(16CCR) | U |  | SAF | 2019 | [7 empty] | OBLIGATED | 1130000 |  | 1130000 | 2019 | 1ST QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.265 | 2020-12-23 | ADD C PHASE TO STIP; PARENT NO. 10-163.00; NEW |  |  | POWELL | 10-163.10 | KY 213 |  | 7.595 | 9 | SAFETY | SAFETY(P) | IMPROVE SAFETY AND UPGRADE GEOMETRICS, AND ADDRESS CAPACITY ISSUES FOR KY 213 FROM KY 11 TO KY 615, INCLUDES BRIDGE OVER RED RIVER. (PRIORITY SECTION 1)(R & U FUNDING SEE 10-163.00)(2018BOP) (2020CCR) | C |  | STP | 2021 | 12075000 | 12075000 | [8 empty] | 0
STIP | [9 empty] | POWELL | 10-211 | KY 2026 | 0.336 | 0 | 0.381 | RELIABILITY | RECONSTRUCTION(O) | CORRECT FLOODING ISSUES ON KY-2026 FROM KY-11 TO THE RED RIVER IN CLAY CITY. | D |  | STP | 2019 | 500000 | 500000 |  |  | 0 | [5 empty] | 0
STIP | [7 empty] | STP | 6000135 | POWELL | 10-211 | KY 2026 | 0.336 | 0 | 0.381 | RELIABILITY | RECONSTRUCTION(O) | CORRECT FLOODING ISSUES ON KY-2026 FROM KY-11 TO THE RED RIVER IN CLAY CITY. | R |  | STP | 2020 | 200000 | 200000 |  |  | 0 |  |  | OBLIGATED |  | 75000 | 75000 | 2019 | 4TH QUARTER
STIP | [7 empty] | STP | 6000135 | POWELL | 10-211 | KY 2026 | 0.336 | 0 | 0.381 | RELIABILITY | RECONSTRUCTION(O) | CORRECT FLOODING ISSUES ON KY-2026 FROM KY-11 TO THE RED RIVER IN CLAY CITY. | U |  | STP | 2020 | 150000 | 150000 |  |  | 0 |  |  | OBLIGATED |  | 150000 | 150000 | 2019 | 4TH QUARTER
STIP | [9 empty] | POWELL | 10-211 | KY 2026 | 0.336 | 0 | 0.381 | RELIABILITY | RECONSTRUCTION(O) | CORRECT FLOODING ISSUES ON KY-2026 FROM KY-11 TO THE RED RIVER IN CLAY CITY. | C |  | STP | 2021 | 1100000 | 880000 |  |  | 220000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.015 | 2019-01-25 | ADD PROJECT TO STIP; PARENT NO. 99-911.05; NEW | HSIP | 5260042 | POWELL | 10-932 | KY 15 & KY 11 |  | 3.493 20.93 | 3.6 21.05 | SAFETY | SAFETY(P) | INTERSECTION IMPROVEMENTS AT KY 15 AND KY 11 IN POWELL COUNTY LOCATED IN DISTRICT 10. (2014BOP) | C |  | SAF | 2019 | 395000 | 395000 |  |  | 0 |  |  | OBLIGATED | 395000 |  | 395000 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.218 | 2020-08-28 | ADD C PHASE TO STIP; NEW |  |  | POWELL | 10-5015 | KY 9000 |  | 35.8 | 35.9 |  | SLIDE CORRECTIONS | MOUNTAIN PARKWAY, KY 9000 EMERGENCY REPAIRS TO CORRECT SUBSIDENCE AND ENBANKMENT STABLIZATION BETWEEN MP 35.8 AND MP 35.9 NEAR TUNNEL RIDGE ROAD OVERPASS IN POWELL COUNTY, KENTUCKY. | C |  | NH | 2020 | 950000 | 760000 |  |  | 190000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.126 | 2019-09-20 | ADD PROJECT TO STIP; PARENT NO. 99-911.06; NEW | HSIP | 9010316 | POWELL | 10-9009 | KY 1057 |  | 0.824 | 4.976 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 1057 BEGINNING AT MP 0.824 AND ENDING AT MP 4.976 IN POWELL COUNTY. (2016BOP) | C |  | SAF | 2019 | 1703000 | 1703000 |  |  | 0 |  |  | OBLIGATED | 907852 | 1703000 | 2610852 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.015 | 2019-01-25 | ADD PROJECT TO STIP; PARENT NO. 99-911.06; NEW | HSIP | 5260045 | POWELL | 10-9012 | KY 11 |  | 7.45 | 14.047 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 11 FROM MP 7.450 TO MP 14.047 IN POWELL COUNTY. (2016BOP) | C |  | SAF | 2019 | 1650000 | 1650000 |  |  | 0 |  |  | OBLIGATED | 1475643 | 1000000 | 2475643 | 2019 | 2ND QUARTER
STIP | [9 empty] | POWELL | 10-10007 | KY 599 |  | 0.908 | 0.926 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-599 BRIDGE OVER CANE CREEK. (099B00069N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [9 empty] | POWELL | 10-10007 | KY 599 |  | 0.908 | 0.926 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-599 BRIDGE OVER CANE CREEK. (099B00069N) | C |  | BR/STP | 2020 | 770000 | 477400 |  |  | 292600 | [5 empty] | 0
STIP | [9 empty] | POWELL | 10-10008 | KY 2026 |  | 0.381 | 0.411 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-2026 BRIDGE OVER RED RIVER. (099B00090N) | D |  | BR/STP | 2019 | 210000 | 130200 |  |  | 79800 | [5 empty] | 0
STIP | [9 empty] | POWELL | 10-10008 | KY 2026 |  | 0.381 | 0.411 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-2026 BRIDGE OVER RED RIVER. (099B00090N) | C |  | BR/STP | 2020 | 1120000 | 694400 |  |  | 425600 | [5 empty] | 0
STIP | [9 empty] | POWELL | 10-10018 | KY 3354 |  | 4.095 | 4.103 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 3354 BRIDGE OVER CAT CREEK. (099B00081N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030147 | POWELL | 10-10018 | KY 3354 |  | 4.095 | 4.103 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 3354 BRIDGE OVER CAT CREEK. (099B00081N) | C |  | BR/STP | 2020 | 560000 | 347200 |  |  | 212800 |  |  | OBLIGATED |  | 740603.4 | 740603.4 | 2019 | 3RD QUARTER
STIP | [9 empty] | POWELL | 10-20004 | KY 9000 |  | 11.91 | 19.15 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF BERT T. COMBS MOUNTAIN PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 11.91 TO MILEPOINT 19.15 | D |  | PM/STP | 2022 | 580000 | 464000 |  |  | 116000 | [5 empty] | 0
STIP | [9 empty] | POWELL | 10-20004 | KY 9000 |  | 11.91 | 19.15 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF BERT T. COMBS MOUNTAIN PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 11.91 TO MILEPOINT 19.15 | C |  | PM/STP | 2022 | 5800000 | 4640000 |  |  | 1160000 | [5 empty] | 0
STIP | [9 empty] | POWELL | 10-20006 | KY 9000 |  | 22.307 | 27.376 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF BERT T. COMBS MOUNTAIN PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 22.307 TO MILEPOINT 27.376 | D |  | PM/NH | 2019 | 410000 | 328000 |  |  | 82000 | [5 empty] | 0
STIP | [9 empty] | POWELL | 10-20006 | KY 9000 |  | 22.307 | 27.376 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF BERT T. COMBS MOUNTAIN PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 22.307 TO MILEPOINT 27.376 | C |  | PM/NH | 2019 | 4100000 | 3280000 |  |  | 820000 | [5 empty] | 0
STIP | [9 empty] | POWELL | 10-20007 | KY 9000 |  | 27.376 | 32.788 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF BERT T. COMBS MOUNTAIN PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 27.376 TO MILEPOINT 32.788 | C |  | PM/NH | 2020 | 5416000 | 4332800 |  |  | 1083200 | [5 empty] | 0
[8 empty] | NHPP | 4611009 | PULASKI | 8-59.25 | KY 461 | 3.879 | 0 | 3.879 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE KY-461 FROM KY-80 TO BUCK CREEK BRIDGE, INCLUDING INTERCHANGE AT KY-80. (18CCR) | D |  | NH | 2019 | [7 empty] | OBLIGATED | 1000000 |  | 1000000 | 2019 | 4TH QUARTER
STIP | [7 empty] | NHPP | 4611009 | PULASKI | 8-59.25 | KY 461 | 3.879 | 0 | 3.879 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE KY-461 FROM KY-80 TO BUCK CREEK BRIDGE, INCLUDING INTERCHANGE AT KY-80. (18CCR) | R |  | NH | 2019 | 3000000 | 3000000 |  |  | 0 |  |  | OBLIGATED | 5687000 |  | 5687000 | 2019 | 4TH QUARTER
STIP | [7 empty] | NHPP | 4611009 | PULASKI | 8-59.25 | KY 461 | 3.879 | 0 | 3.879 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE KY-461 FROM KY-80 TO BUCK CREEK BRIDGE, INCLUDING INTERCHANGE AT KY-80. (18CCR) | U |  | NH | 2020 | 1500000 | 1500000 |  |  | 0 |  |  | OBLIGATED | 2742048 | 3757951.91 | 6499999.91 | 2019 | 4TH QUARTER
STIP | [7 empty] | NHPP | 4611009 | PULASKI | 8-59.25 | KY 461 | 3.879 | 0 | 3.879 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE KY-461 FROM KY-80 TO BUCK CREEK BRIDGE, INCLUDING INTERCHANGE AT KY-80. (18CCR) | C |  | NH | 2021 | 13000000 | 10400000 |  |  | 2600000 | [5 empty] | 0
STIP | [9 empty] | PULASKI | 8-59.26 | KY 461 | 3.879 | 0 | 3.879 | RELIABILITY | PREFINANCD CONVRSN(O) | IMPROVE KY-461 FROM KY-80 TO BUCK CREEK BRIDGE, INCLUDING INTERCHANGE AT KY-80. (18CCR) | R |  | NH | 2019 | 3000000 | 3000000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | PULASKI | 8-59.26 | KY 461 | 3.879 | 0 | 3.879 | RELIABILITY | PREFINANCD CONVRSN(O) | IMPROVE KY-461 FROM KY-80 TO BUCK CREEK BRIDGE, INCLUDING INTERCHANGE AT KY-80. (18CCR) | U |  | NH | 2020 | 1500000 | 1500000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.291 | 2021-04-23 | ADD C PHASE TO STIP; PARENT NO. 99-911.10; NEW |  |  | PULASKI | 8-946 | US 27 |  | 29.384 | 30.307 | RELIABILITY | SAFETY-HAZARD ELIM(P) | Construction of an RCUT at the Intersection of US 27 & KY 70. | C |  | SAF | 2021 | 1486500 | 1486500 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.269 | 2021-01-22 | ADD PROJECT TO STIP; NEW |  |  | PULASKI | 8-4324 | KY 761 |  | 4.89 | 5.21 | SAFETY | SAF GUARDRAIL(P) | INSTALL GUARDRAIL ON KY-761 IN PULASKI COUNTY | C |  | STP | 2021 | 55000 | 55000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.042 | 2019-03-25 | ADD C PHASE TO STIP; PARENT NO. 99-911.04; NEW | HSIP | 5148005 | PULASKI | 8-9003 | KY 790 |  | 0 | 5.551 | SAFETY | SAFETY(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 790 FROM WAYNE-PULASKI COUNTY LINE (MP 0.000) TO KY 90 (MP 5.551) IN PULASKI COUNTY, KY. (2014BOP) | C |  | SAF | 2019 | 1480000 | 1480000 |  |  | 0 |  |  | OBLIGATED |  | 1480000 | 1480000 | 2019 | 3RD QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.015 | 2019-01-25 | ADD PROJECT TO STIP; PARENT NO. 8-9004.00; NEW | HSIP | 0271093 | PULASKI | 8-9004.4 | US 27 |  | 10.33 | 10.43 | SAFETY | SAFETY(P) | CONSTRUCT A J-TURN AND UPDATE SIGNING AND STRIPING AT THE INTERSECTION OF US 27 AND LOST LODGE ROAD. (2016BOP) | C |  | SAF | 2019 | 155000 | 155000 |  |  | 0 |  |  | OBLIGATED |  | 237652 | 237652 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.015 | 2019-01-25 | ADD PROJECT TO STIP; PARENT NO. 8-9004.00; NEW | HSIP | 9010334 | PULASKI | 8-9004.5 | KY 1577 |  | 2.77 | 3.15 | SAFETY | SAFETY(P) | CONSTRUCT A LEFT AND RIGHT TURN LANE ALONG KY 1577, ADJUST APPROACH GRADE OF GRAND CENTRAL BLVD, REBUILD FLASHING BEACON, UPDATE SIGNING AND STRIPING, AND REMOVE TREES AT INTERSECTION OF KY 1577 AND GRAND CENTRAL BLVD. (2016BOP) | C |  | SAF | 2019 | 290000 | 290000 |  |  | 0 |  |  | OBLIGATED | 435568 |  | 435568 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.078 | 2019-06-10 | ADD R PHASE TO STIP; PARENT NO. 99-911.06; NEW | HSIP | 5181006 | PULASKI | 8-9007 | KY 39 |  | 3.535 | 12.809 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 39 BEGINNING AT MP 3.535 AND ENDING AT MP 12.809 IN PULASKI COUNTY. (2016BOP) | R |  | SAF | 2019 | 20000 | 20000 |  |  | 0 |  |  | OBLIGATED | 20000 |  | 20000 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.218 | 2020-08-28 | ADD C PHASE TO STIP; PARENT NO. 99-911.06; NEW | HSIP | 5181006 | PULASKI | 8-9007 | KY 39 |  | 3.535 | 12.809 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 39 BEGINNING AT MP 3.535 AND ENDING AT MP 12.809 IN PULASKI COUNTY. (2016BOP) | C |  | SAF | 2020 | 1555000 | 1555000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.119 | 2019-08-23 | ADD PROJECT TO STIP; PARENT NO. 8-9008.00; NEW | HSIP | 0271096 | PULASKI | 8-9008.5 | US 27 |  | 11.324 | 11.424 | SAFETY | SAFETY-HAZARD ELIM(P) | SIGNAL ENCHANCEMENTS AND INSTALL MEDIAN ACCESS CONTROL AT THE INTERSECTION OF US 27 & BOAT DOCK RD. (2018BOP) | C |  | SAF | 2019 | 76000 | 76000 |  |  | 0 |  |  | OBLIGATED |  | 76000 | 76000 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.123 | 2019-09-06 | ADD U PHASE TO STIP; PARENT NO. 99-911.06; NEW | HSIP | 5105046 | PULASKI | 8-9009 | KY 70 |  | 3.535 | 11.96 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ALONG KY 70 BETWEEN MP 3.535 AND MP 11.960 IN PULASKI COUNTY, KY. (2016BOP) | U |  | SAF | 2019 | 35000 | 35000 |  |  | 0 |  |  | OBLIGATED | 35000 |  | 35000 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.291 | 2021-04-23 | ADD C PHASE TO STIP; PARENT NO. 99-911.06; NEW | HSIP | 5105046 | PULASKI | 8-9009 | KY 70 |  | 3.535 | 11.96 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ALONG KY 70 BETWEEN MP 3.535 AND MP 11.960 IN PULASKI COUNTY, KY. (2016BOP) | C |  | SAF | 2021 | 2481220 | 2481220 | [8 empty] | 0
STIP | [9 empty] | PULASKI | 8-9010 | KY 635 | 1.286 | 6.9 | 8.186 | SAFETY | SAFETY-RR SEPARATN(P) | SAFETY PROJECT TO RECONSTRUCT KY 635 TO ELIMINATE AT GRADE RAILROAD CROSSING AND REPLACE WITH RAILROAD SEPARATION CROSSING AT SCIENCE HILL, KENTUCKY IN PULASKI COUNTY. (2016BOP) | R |  | RRS | 2020 | 1800000 | 1800000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | PULASKI | 8-9010 | KY 635 | 1.286 | 6.9 | 8.186 | SAFETY | SAFETY-RR SEPARATN(P) | SAFETY PROJECT TO RECONSTRUCT KY 635 TO ELIMINATE AT GRADE RAILROAD CROSSING AND REPLACE WITH RAILROAD SEPARATION CROSSING AT SCIENCE HILL, KENTUCKY IN PULASKI COUNTY. (2016BOP) | U |  | RRS | 2020 | 1300000 | 1300000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | PULASKI | 8-9010 | KY 635 | 1.286 | 6.9 | 8.186 | SAFETY | SAFETY-RR SEPARATN(P) | SAFETY PROJECT TO RECONSTRUCT KY 635 TO ELIMINATE AT GRADE RAILROAD CROSSING AND REPLACE WITH RAILROAD SEPARATION CROSSING AT SCIENCE HILL, KENTUCKY IN PULASKI COUNTY. (2016BOP) | C |  | RRS | 2022 | 6500000 | 5200000 |  |  | 1300000 | [5 empty] | 0
STIP | [9 empty] | PULASKI | 8-20008 | US 27 | 6.78 | 0 | 6.78 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION ON US-27 FROM MILEPOINT 0.00 TO MILEPOINT 6.78 | C |  | PM/NH | 2022 | 2708000 | 2166400 |  |  | 541600 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.306 | 2021-06-16 | ADD D PHASE TO STIP; NEW |  |  | PULASKI | 8-80104 | KY 90 |  | 0 | 3 |  | CONGESTION MITIGTN(O) | REDUCE CONGESTION AND IMPROVE SAFETY, CAPACITY AND MOBILIITY ALONG KY 90 BETWEEN WAYNE COUNTY LINE AND NEW CUMBERLAND RIVER BRIDGE (2020CCN) | D |  | SPP | 2021 | 1406100 | 100 |  |  | 1406000 | [5 empty] | 0
STIP | [9 empty] | ROBERTSON | 6-20053 | US 62 | 11 | 0 | 11 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION ON US-62 FROM MILEPOINT 0.00 TO MILEPOINT 11.00 | C |  | PM/NH | 2022 | 863000 | 690400 |  |  | 172600 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.238 | 2020-09-25 | ADD D PHASE TO STIP; NEW |  |  | ROBERTSON | 6-80151 | US 62 |  | 4.897 | 4.911 | RELIABILITY | TRANSP ENHANCEMENT(P) | WIDEN THE BRIDGE ON US 62 OVER N. BRANCH CEDAR CREEK NEAR KENTONTOWN TO IMPROVE SAFETY AND MOBILITY. (2020CCN) | D |  | STP | 2020 | 170000 | 170000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | ROCKCASTLE | 8-8952 | KY 461 |  | 7 | 9.404 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE KY-461 FROM US-150 TO THE EXISTING FOUR LANE APPROACH AT US-25.(16CCN)(18CCR) | D |  | NH | 2019 | 1200000 | 1200000 |  |  | 0 |  |  | OBLIGATED | 650491 | 549509 | 1200000 | 2020 | 2ND QUARTER
STIP | [9 empty] | ROCKCASTLE | 8-8952 | KY 461 |  | 7 | 9.404 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE KY-461 FROM US-150 TO THE EXISTING FOUR LANE APPROACH AT US-25.(16CCN)(18CCR) | R |  | NH | 2020 | 1450000 | 1450000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | ROCKCASTLE | 8-8952 | KY 461 |  | 7 | 9.404 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE KY-461 FROM US-150 TO THE EXISTING FOUR LANE APPROACH AT US-25.(16CCN)(18CCR) | U |  | NH | 2021 | 2230000 | 1784000 |  |  | 446000 | [5 empty] | 0
STIP | [9 empty] | ROCKCASTLE | 8-8952.01 | KY 461 |  | 7 | 9.404 | RELIABILITY | PREFINANCD CONVRSN(O) | IMPROVE KY-461 FROM US-150 TO THE EXISTING FOUR LANE APPROACH AT US-25.(16CCN)(18CCR) | R |  | NH | 2021 | 1450000 | 1160000 |  |  | 290000 | [5 empty] | 0
STIP | [9 empty] | ROCKCASTLE | 8-8952.01 | KY 461 |  | 7 | 9.404 | RELIABILITY | PREFINANCD CONVRSN(O) | IMPROVE KY-461 FROM US-150 TO THE EXISTING FOUR LANE APPROACH AT US-25.(16CCN)(18CCR) | U |  | NH | 2022 | 1120000 | 896000 |  |  | 224000 | [5 empty] | 0
STIP | [9 empty] | ROCKCASTLE | 8-10010 | KY 1326 |  | 3.584 | 3.588 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 1326 BRIDGE OVER LITTLE RENFRO CREEK. (102B00026N) | D |  | BR/STP | 2019 | 70000 | 43400 |  |  | 26600 | [5 empty] | 0
STIP | [9 empty] | ROCKCASTLE | 8-10010 | KY 1326 |  | 3.584 | 3.588 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 1326 BRIDGE OVER LITTLE RENFRO CREEK. (102B00026N) | C |  | BR/STP | 2020 | 210000 | 130200 |  |  | 79800 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.021 | 2019-02-04 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION;MOD | STPBRZ | 9030038 | ROCKCASTLE | 8-10010 | KY 1326 |  | 3.584 | 3.588 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 1326 BRIDGE OVER LITTLE RENFRO CREEK. (102B00026N) | C |  | STP | 2019 | 330000 | 330000 |  |  | 0 |  |  | OBLIGATED |  | 343060 | 343060 | 2019 | 2ND QUARTER
STIP | [9 empty] | ROCKCASTLE | 8-20003 | I 75 |  | 52.05 | 55.295 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-075 BOTH DIRECTION(S) FROM MILEPOINT 52.05 TO MILEPOINT 55.295 | D |  | PM/NH | 2019 | 390000 | 312000 |  |  | 78000 | [5 empty] | 0
STIP | [7 empty] | NHPPIM | 0753102 | ROCKCASTLE | 8-20003 | I 75 |  | 52.05 | 55.295 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-075 BOTH DIRECTION(S) FROM MILEPOINT 52.05 TO MILEPOINT 55.295 | C |  | PM/NH | 2019 | 3900000 | 3120000 |  |  | 780000 |  |  | OBLIGATED | 4096400 |  | 4096400 | 2019 | 3RD QUARTER
STIP | [9 empty] | ROCKCASTLE | 8-20004 | I 75 |  | 52.05 | 55.295 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-075 BOTH DIRECTION(S) FROM MILEPOINT 71.668 TO MILEPOINT 73.408 | D |  | PM/NH | 2020 | 210000 | 168000 |  |  | 42000 | [5 empty] | 0
STIP | [7 empty] | NHPPIM | 0753101 | ROCKCASTLE | 8-20004 | I 75 |  | 52.05 | 55.295 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-075 BOTH DIRECTION(S) FROM MILEPOINT 71.668 TO MILEPOINT 73.408 | C |  | PM/NH | 2020 | 2100000 | 1680000 |  |  | 420000 |  |  | OBLIGATED | 2779613 |  | 2779613 | 2019 | 3RD QUARTER
STIP | [9 empty] | ROCKCASTLE | 8-20005 | US 25 |  | 20.404 | 27.052 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION | D |  | PM/STP | 2020 | 175000 | 140000 |  |  | 35000 | [5 empty] | 0
STIP | [9 empty] | ROCKCASTLE | 8-20005 | US 25 |  | 20.404 | 27.052 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION | C |  | PM/STP | 2020 | 1750000 | 1400000 |  |  | 350000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.229 | 2020-09-14 | ADD C PHASE TO STIP; PARENT NO. 99-224.14; NEW |  |  | ROCKCASTLE | 8-20012 | KY 461 |  | 0 | 4.8 | RELIABILITY | AM-PAVEMENT (PRI)(P) | RESURFACING OF KY 461 AT MP 0.000 TO MP 4.800 IN ROCKCASTLE COUNTY. (2020CCR) | C |  | NH | 2020 | 1525915 | 1525915 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.306 | 2021-06-16 | ADD D PHASE TO STIP; NEW |  |  | ROCKCASTLE | 8-80106 | US 25 |  | 15.018 | 15.785 |  | CONGESTION MITIGTN(O) | ADDRESS SAFETY, MOBILITY, AND CONGESTION WITH ACCESS AMANGEMENT ALONG US-25 (RICHMOND ST) FROM THE US 25/US 461 INTERSECTION TO I 75 (2020CCN) | D |  | SPP | 2021 | 1100100 | 100 |  |  | 1100000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.238 | 2020-09-25 | ADD PROJECT TO STIP; NEW |  |  | ROWAN | 9-204 | KY 32 |  | 2.235 | 4.157 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE KY-32 FROM PARK HILLS DRIVE TO VIKING DRIVE NORTH. (12CCR)(18CCR) (2020CCR) | D |  | STP | 2020 | 2000000 | 1600000 |  |  | 400000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.238 | 2020-09-25 | ADD PROJECT TO STIP; NEW |  |  | ROWAN | 9-204 | KY 32 |  | 2.235 | 4.157 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE KY-32 FROM PARK HILLS DRIVE TO VIKING DRIVE NORTH. (12CCR)(18CCR) (2020CCR) | R |  | STP | 2020 | 2600000 | 2080000 |  |  | 520000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.238 | 2020-09-25 | ADD PROJECT TO STIP; NEW |  |  | ROWAN | 9-204 | KY 32 |  | 2.235 | 4.157 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE KY-32 FROM PARK HILLS DRIVE TO VIKING DRIVE NORTH. (12CCR)(18CCR) (2020CCR) | U |  | STP | 2020 | 2000000 | 1600000 |  |  | 400000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.265 | 2020-12-23 | ADD C PHASE TO STIP; PARENT NO. 99-911.10; NEW |  |  | ROWAN | 9-938 | US 60 |  | 7 | 10.152 | SAFETY | SAFETY-HAZARD ELIM(P) | Installation of 6" Striping on US 60 in Rowan County (2020BOP). | C |  | SAF | 2021 | 145000 | 145000 | [8 empty] | 0
STIP | [9 empty] | ROWAN | 9-1093 | CR 1140 | 0.01 | 0.01 | 0.02 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER BULL FORK ON HORSEMAN CEMETERY ROAD (CR 1140) AT JCT WITH BULLFORK ROAD (CR 1222) (103C00108N)(SR=32.5)(EBRP)(18CCN) | D |  | BR/STP | 2021 | 350000 | 217000 |  |  | 133000 | [5 empty] | 0
STIP | [9 empty] | ROWAN | 9-1093 | CR 1140 | 0.01 | 0.01 | 0.02 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER BULL FORK ON HORSEMAN CEMETERY ROAD (CR 1140) AT JCT WITH BULLFORK ROAD (CR 1222) (103C00108N)(SR=32.5)(EBRP)(18CCN) | R |  | BR/STP | 2022 | 50000 | 31000 |  |  | 19000 | [5 empty] | 0
STIP | [9 empty] | ROWAN | 9-1093 | CR 1140 | 0.01 | 0.01 | 0.02 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER BULL FORK ON HORSEMAN CEMETERY ROAD (CR 1140) AT JCT WITH BULLFORK ROAD (CR 1222) (103C00108N)(SR=32.5)(EBRP)(18CCN) | U |  | BR/STP | 2022 | 50000 | 31000 |  |  | 19000 | [5 empty] | 0
STIP | [9 empty] | ROWAN | 9-1093 | CR 1140 | 0.01 | 0.01 | 0.02 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER BULL FORK ON HORSEMAN CEMETERY ROAD (CR 1140) AT JCT WITH BULLFORK ROAD (CR 1222) (103C00108N)(SR=32.5)(EBRP)(18CCN) | C |  | BR/STP | 2022 | 400000 | 248000 |  |  | 152000 | [5 empty] | 0
STIP | [9 empty] | ROWAN | 9-8406 | KY 377 | 8.2 | 0 | 8.3 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE SAFETY AND CONNECTIVITY AND REDUCE CONGESTION ON KY-377 FROM KY-32 TO NORTH OF KY-799. (08CCN)(10CCR)(16CCR)(18CCR) | R |  | STP | 2020 | 2600000 | 2600000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.276 | 2021-02-12 | INCREASE FUNDS BASED ON NEW ESTIMATE; MOD |  |  | ROWAN | 9-8406 | KY 377 | 8.2 | 0 | 8.3 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE SAFETY AND CONNECTIVITY AND REDUCE CONGESTION ON KY-377 FROM KY-32 TO NORTH OF KY-799. (08CCN)(10CCR)(16CCR)(18CCR) | R |  | STP | 2021 | 4978000 | 4978000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | ROWAN | 9-8406 | KY 377 | 8.2 | 0 | 8.3 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE SAFETY AND CONNECTIVITY AND REDUCE CONGESTION ON KY-377 FROM KY-32 TO NORTH OF KY-799. (08CCN)(10CCR)(16CCR)(18CCR) | U |  | STP | 2021 | 7700000 | 6160000 |  |  | 1540000 | [5 empty] | 0
STIP | [9 empty] | ROWAN | 9-8406 | KY 377 | 8.2 | 0 | 8.3 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE SAFETY AND CONNECTIVITY AND REDUCE CONGESTION ON KY-377 FROM KY-32 TO NORTH OF KY-799. (08CCN)(10CCR)(16CCR)(18CCR) | C |  | STP | 2022 | 9100000 | 7280000 |  |  | 1820000 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 0903211 | ROWAN | 9-8914 | CR 1025 |  | 0.081 | 0.089 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON LITTLE PERRY ROAD OVER TRIPLETT CREEK.(16CCN) | C |  | BR/STP | 2020 | 822500 | 509950 |  |  | 312550 |  |  | OBLIGATED | 135000 | 486460 | 621460 | 2020 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.013 | 2019-01-10 | ADD R PHASE TO STIP; NEW | STPBRZ | 0903211 | ROWAN | 9-8914 | CR 1025 |  | 0.081 | 0.089 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON LITTLE PERRY ROAD OVER TRIPLETT CREEK.(16CCN) | R |  | BR/STP | 2019 | 58500 | 58500 |  |  | 0 |  |  | OBLIGATED | 58500 |  | 58500 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.013 | 2019-01-10 | ADD U PHASE TO STIP; NEW | STPBRZ | 0903211 | ROWAN | 9-8914 | CR 1025 |  | 0.081 | 0.089 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON LITTLE PERRY ROAD OVER TRIPLETT CREEK.(16CCN) | U |  | BR/STP | 2019 | 65000 | 65000 |  |  | 0 |  |  | OBLIGATED | 65000 |  | 65000 | 2019 | 2ND QUARTER
STIP | [9 empty] | ROWAN | 9-8915 | KY 801 |  | 15.61 | 16.978 | RELIABILITY | MAJOR WIDENING(O) | WIDEN KY 801 FROM NEAR MMRC REGIONAL PARK TO KY 158 IN FLEMING CO. (16CCN)(18CCN) | P |  | STP | 2019 | 100000 | 100000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.21 | 2020-07-31 | ADD D PHASE TO STIP; NEW |  |  | ROWAN | 9-8915 | KY 801 |  | 15.61 | 16.978 | RELIABILITY | MAJOR WIDENING(O) | WIDEN KY 801 FROM NEAR MMRC REGIONAL PARK TO KY 158 IN FLEMING CO. (16CCN)(18CCN) | D |  | STP | 2020 | 1560000 | 1560000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.029 | 2019-02-21 | ADD PROJECT TO STIP; PARENT NO. 99-911.04; NEW | HSIP | 9010335 | ROWAN | 9-9000 | KY 158 |  | 0 | 2.766 | SAFETY | SAFETY(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 158 FROM THE FLEMING/ROWAN COUNTY LINE TO KY 32. (2014BOP) | C |  | SAF | 2019 | 600000 | 600000 |  |  | 0 |  |  | OBLIGATED | 2100000 |  | 2100000 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.155 | 2020-01-22 | ADD PROJECT TO STIP; PARENT NO. 99-911.06; NEW |  |  | ROWAN | 9-9008 | US 60 |  | 10.834 | 17.112 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON US 60 FROM MP 10.834 TO MP 17.112 IN ROWAN COUNTY. (2016BOP) | C |  | SAF | 2020 | 1400000 | 1260000 |  |  | 140000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.218 | 2020-08-28 | INCREASE FUNDS BASED ON NEW ESTIMATE; MOD |  |  | ROWAN | 9-9008 | US 60 |  | 10.834 | 17.112 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON US 60 FROM MP 10.834 TO MP 17.112 IN ROWAN COUNTY. (2016BOP) | C |  | SAF | 2020 | 1850000 | 1850000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.177 | 2020-04-24 | ADD C PHASE TO STIP; PARENT NO. 9-9010; NEW |  |  | ROWAN | 9-9010.1 | KY 32 I 64 |  | 5.608 .1 | 5.788 .359 | SAFETY | SAFETY-HAZARD ELIM(P) | UPDATES TO THE SIGNAL AND STRIPING AT THE INTERSECTION OF KY 32 & THE EB I-64 OFF RAMP AT EXIT 137. (2018BOP) | C |  | SAF | 2020 | 160000 | 160000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.177 | 2020-04-24 | ADD C PHASE TO STIP; PARENT NO. 9-9010; NEW |  |  | ROWAN | 9-9010.4 | KY 32 |  | 5.358 | 5.458 | SAFETY | SAFETY-HAZARD ELIM(P) | WIDEN TURN RADIUS AND UPGRADE THE SIGNAL TO INCLUDE REFLECTIVE BACKPLATES AT THE INTERSECTION OF KY 32 & TRADEMORE DR.(2018BOP) | C |  | SAF | 2020 | 76000 | 76000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.103 | 2019-07-29 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 0646066 | ROWAN | 9-9011 | I 64 |  | 128.955 | 137.268 | SAFETY | SAFETY-HAZARD ELIM(P) | CABLE MEDIAN BARRIER ON I-64 FROM MP 128.955 TO MP 137.268 IN ROWAN COUNTY, KY. (2018BOP) | D |  | SAF | 2019 | 50000 | 50000 |  |  | 0 |  |  | OBLIGATED | 50000 |  | 50000 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.139 | 2019-10-25 | ADD C PHASE TO THE STIP; PARENT NO. 99-911.08; NEW | HSIP | 0646066 | ROWAN | 9-9011 | I 64 |  | 128.955 | 137.268 | SAFETY | SAFETY-HAZARD ELIM(P) | CABLE MEDIAN BARRIER ON I-64 FROM MP 128.955 TO MP 137.268 IN ROWAN COUNTY, KY. (2018BOP) | C |  | SAF | 2020 | 1368730 | 1368730 |  |  | 0 |  |  | OBLIGATED | 1644640 |  | 1644640 | 2020 | 1ST QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.175 | 2020-04-09 | ADD D PHASE TO STIP; PARENT NO. 99-911.09; NEW |  |  | ROWAN | 9-9014 | KY 377 |  | 8.049 | 15.339 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 377 FROM MP 8.049 TO MP 15.339 IN ROWAN COUNTY, KY. (2018BOP) | D |  | SAF | 2020 | 325000 | 325000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | ROWAN | 9-20014 | I 64 |  | 141.5 | 147.95 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-064 BOTH DIRECTION(S) FROM MILEPOINT 141.5 TO MILEPOINT 147.95 | D |  | PM/NH | 2022 | 525000 | 420000 |  |  | 105000 | [5 empty] | 0
STIP | [9 empty] | ROWAN | 9-20014 | I 64 |  | 141.5 | 147.95 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-064 BOTH DIRECTION(S) FROM MILEPOINT 141.5 TO MILEPOINT 147.95 | C |  | PM/NH | 2022 | 5250000 | 4200000 |  |  | 1050000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.314 | 2021-06-25 | ADD C PHASE TO STIP; NEW |  |  | ROWAN | KY FLAP11 | KY 1274 |  |  |  | RELIABILITY | RESURFACING(P) | PAVEMENT REHABILITATION OF 4.9 MILES OF KY 1274 (PRETTY RIDGE ROAD) IN SOUTHERN ROWAN COUNTY. | C |  | FLAP | 2021 | 1000000 | 800000 |  |  | 200000 | [5 empty] | 0
STIP | [9 empty] | RUSSELL | 8-8601.21 | US 127 | 2.52 | 0 | 2.5 | RELIABILITY | RELOCATION(O) | RELOCATE US-127 FROM EAST OF THE KY-1730 AND MANNTOWN RD INTERSECTION, AND EXTENDING NORTHERLY TO NORTH BANK OF CUMBERLAND RIVER (SEE 8-108&8-115 FOR PE/PH.2)(12CCR)(14CCR) | C |  | NH | 2019 | 9320000 | 9320000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | RUSSELL | 8-8601.23 | US 127 | 2.52 | 0 | 2.5 | RELIABILITY | PREFINANCD CONVRSN(O) | RELOCATE US-127 FROM EAST OF THE KY-1730 AND MANNTOWN RD INTERSECTION, AND EXTENDING NORTHERLY TO NORTH BANK OF CUMBERLAND RIVER (SEE 8-108&8-115 FOR PE/PH.2)(12CCR)(14CCR) | C |  | NH | 2020 | 8280000 | 8280000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | RUSSELL | 8-8601.24 | US 127 | 2.52 | 0 | 2.5 | RELIABILITY | PREFINANCD CONVRSN(O) | RELOCATE US-127 FROM EAST OF THE KY-1730 AND MANNTOWN RD INTERSECTION, AND EXTENDING NORTHERLY TO NORTH BANK OF CUMBERLAND RIVER (SEE 8-108&8-115 FOR PE/PH.2)(12CCR)(14CCR) | C |  | NH | 2021 | 8280000 | 6624000 |  |  | 1656000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.276 | 2021-02-12 | ADD C PHASE TO STIP; PARENT NO. 99-911.08; NEW |  |  | RUSSELL | 8-9012 | KY 80 |  | 3.7 | 3.8 | SAFETY | SAFETY-HAZARD ELIM(P) | IMPROVE ALIGNMENT AT THE INTERSECTION OF KY80, KY379, & KY 3017. (2018BOP) | C |  | SAF | 2021 | 250585 | 250585 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.311 | 2021-07-21 | ADD C PHASE TO STIP; NEW |  |  | RUSSELL | 8-20007 | LN 9008 |  | 62.544 | 72.087 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF LOUIE B. NUNN CUMBERLAND PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 62.544 TO MILEPOINT 72.087 (2020CCR) | C |  | NHPP | 2021 | 6694600 | 6694600 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | RUSSELL | 8-20009 | US 127 | 7.19 | 19.03 | 26.21 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION ON US-127 FROM MILEPOINT 19.03 TO MILEPOINT 26.21 | C |  | PM/NH | 2022 | 1549000 | 1239200 |  |  | 309800 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.218 | 2020-08-28 | ADD C PHASE TO STIP; PARENT NO. 99-2700.14; NEW |  |  | RUSSELL | 8-20011 | KY 80 |  | 3.96 | 7.55 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | PAVEMENT RESFURACING ON KY 80 AT MP 3.960 TO MP 7.550 IN RUSSELL COUNTY. | C |  | STP | 2020 | 600000 | 600000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | SCOTT | 7-102.5 |  |  |  |  | RELIABILITY | BYPASS(O) | GEORGETOWN NORTHWEST BYPASS: IMPROVE CONNECTIVITY AND MOBILITY NORTHWEST AROUND GEORGETOWN FROM KY-32 TO I-75. (04CCR)(2004BOPC)(SEE 7-102.01 FOR "HPP" COMPONENT)(10CCR)(12CCR)(16CCR) | C |  | STP | 2020 | 5000000 | 5000000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | SCOTT | 7-102.51 |  |  |  |  | RELIABILITY | PREFINANCD CONVRSN(O) | GEORGETOWN NORTHWEST BYPASS: IMPROVE CONNECTIVITY AND MOBILITY NORTHWEST AROUND GEORGETOWN FROM KY-32 TO I-75. (04CCR)(2004BOPC)(SEE 7-102.01 FOR "HPP" COMPONENT)(10CCR)(12CCR)(16CCR) | C |  | STP | 2021 | 10000000 | 8000000 |  |  | 2000000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.233 | 2020-09-21 | ADD P PHASE TO STIP; NEW |  |  | SCOTT | 7-119 | KY 32 |  | 22.466 | 23.003 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT KY 32/I-75 INTERCHANGE EXIT 136 (LOVE'S TRUCK STOP), REALIGNING PORTER RD WITH SADIEVILLE RD AT US25. (2020CCR) | P |  | STP | 2020 | 250000 | 250000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.161 | 2020-02-21 | ADD PROJECT TO STIP; PARENT NO. 99-911.09; NEW |  | 5196012 | SCOTT | 7-952 | US 421 |  | 0 | 0.754 | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALLATION OF STRIPING ON US 421 IN SCOTT COUNTY. (2018BOP) | C |  | SAF | 2020 | 50000 | 50000 |  |  | 0 |  |  | OBLIGATED | 50000 |  | 50000 | 2020 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.161 | 2020-02-21 | ADD PROJECT TO STIP; PARENT NO. 99-911.09; NEW |  | 5196013 | SCOTT | 7-953 | US 62 |  | 0 | 0.825 | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALLATION OF STRIPING ON US 62 IN SCOTT COUNTY. (2018BOP) | C |  | SAF | 2020 | 55000 | 55000 |  |  | 0 |  |  | OBLIGATED | 55000 |  | 55000 | 2020 | 2ND QUARTER
STIP | [9 empty] | SCOTT | 7-1139 | CR 1022 | 0.02 | 1.19 | 1.21 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER NS (CNO&TP)RR ON FIELDS ROAD (CR 1022) AT SCOTT/HARRISON CO LINE (105R00607N) (EBRP) | D |  | BR/STP | 2019 | 210000 | 130200 |  |  | 79800 | [5 empty] | 0
STIP | [9 empty] | SCOTT | 7-1139 | CR 1022 | 0.02 | 1.19 | 1.21 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER NS (CNO&TP)RR ON FIELDS ROAD (CR 1022) AT SCOTT/HARRISON CO LINE (105R00607N) (EBRP) | C |  | BR/STP | 2019 | 1120000 | 694400 |  |  | 425600 | [5 empty] | 0
[8 empty] | HSIP | 5200060 | SCOTT | 7-9010 | US 25 |  | 9.366 | 14.975 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM SAFETY IMPROVEMENTS ALONG US 25 CORRIDOR IN SCOTT COUNTY FROM SHOULDERING, DRAINAGE ENHANCEMENTS, AND ROADSIDE IMPROVEMENTS. (2018BOP) | D |  | SAF | 2019 | [7 empty] | OBLIGATED | 50000 |  | 50000 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.197 | 2020-07-01 | ADD C PHASE TO STIP; PARENT NO. 99-911.08; NEW |  |  | SCOTT | 7-9010 | US 25 |  | 9.366 | 14.975 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM SAFETY IMPROVEMENTS ALONG US 25 CORRIDOR IN SCOTT COUNTY FROM SHOULDERING, DRAINAGE ENHANCEMENTS, AND ROADSIDE IMPROVEMENTS. (2018BOP) | C |  | SAF | 2020 | 336000 | 336000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.112 | 2019-08-08 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW. LEXINGTON MPO TIP FY 17-20, CHAPTER 4 GROUPED PROJECTS, PG 18. | HSIP | 5166019 | SCOTT | 7-9018 | KY 227 |  | 0 | 5.874 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 227 FROM MP 0.000 TO MP 5.874 IN SCOTT COUNTY. (2018BOP) | D |  | SAF | 2019 | 350000 | 350000 | [5 empty] | OBLIGATED |  | 350000 | 350000 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.119 | 2019-08-23 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 4601051 | SCOTT | 7-9019 | US 62 |  | 5.943 | 7.693 | SAFETY | SAFETY-HAZARD ELIM(P) | INTERSECTION AND CORRIDOR IMPROVEMENTS TO REDUCE CONFLICT POINTS AND ENHANCE SAFETY & OPERATIONS ALONG THE GEORGETOWN BYPASS BETWEEN MP 5.943 TO 7.693. (2018BOP) | D |  | SAF | 2019 | 100000 | 100000 | [5 empty] | OBLIGATED |  | 100000 | 100000 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.155 | 2020-01-22 | ADD C PHASE TO THE STIP; PARENT NO. 99-911.08; NEW | HSIP | 4601051 | SCOTT | 7-9019 | US 62 |  | 5.943 | 7.693 | SAFETY | SAFETY-HAZARD ELIM(P) | INTERSECTION AND CORRIDOR IMPROVEMENTS TO REDUCE CONFLICT POINTS AND ENHANCE SAFETY & OPERATIONS ALONG THE GEORGETOWN BYPASS BETWEEN MP 5.943 TO 7.693. (2018BOP) | C |  | SAF | 2020 | 1116000 | 1004400 | [5 empty] | OBLIGATED | 1004400 | 100000 | 1104400 | 2020 | 2ND QUARTER
STIP | [9 empty] | SCOTT | 7-10005 | KY 620 |  | 15.923 | 15.939 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-620 BRIDGE OVER ROGERS GAP CREEK. (105B00095N) | D |  | BR/STP | 2019 | 210000 | 130200 |  |  | 79800 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030092 | SCOTT | 7-10005 | KY 620 |  | 15.923 | 15.939 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-620 BRIDGE OVER ROGERS GAP CREEK. (105B00095N) | C |  | BR/STP | 2020 | 665000 | 412300 |  |  | 252700 |  |  | OBLIGATED |  | 393060 | 393060 | 2019 | 3RD QUARTER
STIP | [9 empty] | SCOTT | 7-10006 | CS 1010 |  | 0.025 | 0.045 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF LEMONS MILL RD BRIDGE OVER NS (CNO&AMP;TP) SYSTEM. (105C00112N) | D |  | BR/STP | 2019 | 350000 | 217000 |  |  | 133000 | [5 empty] | 0
STIP | [9 empty] | SCOTT | 7-10006 | CS 1010 |  | 0.025 | 0.045 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF LEMONS MILL RD BRIDGE OVER NS (CNO&AMP;TP) SYSTEM. (105C00112N) | C |  | BR/STP | 2020 | 1295000 | 802900 |  |  | 492100 | [5 empty] | 0
STIP | [9 empty] | SCOTT | 7-10012 | KY 1689 |  | 2.219 | 2.227 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 1689 BRIDGE OVER LOCUST FORK. (105B00039N) | D |  | BR/STP | 2019 | 133000 | 82460 |  |  | 50540 | [5 empty] | 0
STIP | [9 empty] | SCOTT | 7-10012 | KY 1689 |  | 2.219 | 2.227 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 1689 BRIDGE OVER LOCUST FORK. (105B00039N) | C |  | BR/STP | 2020 | 308000 | 190960 |  |  | 117040 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.075 | 2019-05-28 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD |  |  | SCOTT | 7-10012 | KY 1689 |  | 2.219 | 2.227 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 1689 BRIDGE OVER LOCUST FORK. (105B00039N) | C |  | STP | 2020 | 941000 | 941000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.112 | 2019-08-08 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030136 | SCOTT | 7-10012 | KY 1689 |  | 2.219 | 2.227 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 1689 BRIDGE OVER LOCUST FORK. (105B00039N) | C |  | STP | 2020 | 1023500 | 1023500 |  |  | 0 |  |  | OBLIGATED |  | 931995 | 931995 | 2019 | 4TH QUARTER
STIP | [9 empty] | SCOTT | 7-10013 | CR 1020 |  | 0 | 0.021 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF HINTON RD BRIDGE OVER NS (CNO&TP) SYSTEM. (105R00605N) | D |  | BR/STP | 2019 | 238000 | 147560 |  |  | 90440 | [5 empty] | 0
STIP | [9 empty] | SCOTT | 7-10013 | CR 1020 |  | 0 | 0.021 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF HINTON RD BRIDGE OVER NS (CNO&TP) SYSTEM. (105R00605N) | C |  | BR/STP | 2020 | 511000 | 316820 |  |  | 194180 | [5 empty] | 0
STIP | [9 empty] | SCOTT | 7-20019 | I 75 |  | 120.792 | 121.117 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-075 BOTH DIRECTION(S) FROM MILEPOINT 120.792 TO MILEPOINT 121.117 | D |  | PM/NH | 2020 | 40000 | 32000 |  |  | 8000 | [5 empty] | 0
STIP | [9 empty] | SCOTT | 7-20019 | I 75 |  | 120.792 | 121.117 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-075 BOTH DIRECTION(S) FROM MILEPOINT 120.792 TO MILEPOINT 121.117 | C |  | PM/NH | 2020 | 400000 | 320000 |  |  | 80000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.229 | 2020-09-14 | ADD C PHASE TO STIP; PARENT NO. 99-224.14; NEW |  |  | SCOTT | 7-20040 | US 25 |  | 4.574 16.840 | 8.700 25.372 | RELIABILITY | AM-PAVEMENT(PRI)(P) | RESURFACING OF US 25 (MP 4.574 TO MP 8.700) AND (MP 16.840 TO MP 25.372) IN SCOTT COUNTY. (2020CCR) | C |  | STP | 2020 | 1843421 | 1843421 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.229 | 2020-09-14 | ADD C PHASE TO STIP; PARENT NO. 99-224.14; NEW |  |  | SCOTT | 7-20041 | US 62 |  | 13.310 8.583 | 18.942 11.497 | RELIABILITY | AM-PAVEMENT(PRI)(P) | RESURFACING OF US 62 (MP 13.310 TO MP 18.942) AND (MP 8.583 TO MP 11.497) IN SCOTT COUNTY. (2020CCR) | C |  | STP | 2020 | 2199944 | 2199944 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.311 | 2021-07-21 | ADD C PHASE TO STIP; PARENT NO. 99-337.15; NEW |  |  | SCOTT | 7-20042 | I 75 |  | 121.12 | 125.528 | RELIABILITY | AM-PAVEMENT(INT)(P) | ADDRESS CONDITION OF ASPHALT PAVEMENT ON I-75 BOTH DIRECTIONS FROM MILEPOINT 121.12 TO 125.528. | C |  | NHPP | 2021 | 13970000 | 13970000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.306 | 2021-06-16 | ADD D PHASE TO STIP; NEW |  |  | SCOTT | 7-80102 | KY 2906 |  | 0 | 1.118 |  | CONGESTION MITIGTN(O) | IMPROVE CAPACITY AND ACCESS ON KY 2906 FROM US 460 TO US 62 (2020CCN) | D |  | SPP | 2021 | 811100 | 100 |  |  | 811000 | [5 empty] | 0
STIP | [9 empty] | SHELBY | 5-65.4 | I 64 | 5.8 | 32.3 | 38.1 | RELIABILITY | MAJOR WIDENING(O) | WIDEN I-64 TO 6-LANES FROM 0.458 MILE EAST OF THE KY-55 INTERCHANGE TO THE KY-1790 UNDERPASS. (2006BOPC) | D |  | NH | 2019 | 2000000 | 2000000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | SHELBY | 5-65.4 | I 64 | 5.8 | 32.3 | 38.1 | RELIABILITY | MAJOR WIDENING(O) | WIDEN I-64 TO 6-LANES FROM 0.458 MILE EAST OF THE KY-55 INTERCHANGE TO THE KY-1790 UNDERPASS. (2006BOPC) | U |  | NH | 2020 | 2000000 | 2000000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | SHELBY | 5-65.4 | I 64 | 5.8 | 32.3 | 38.1 | RELIABILITY | MAJOR WIDENING(O) | WIDEN I-64 TO 6-LANES FROM 0.458 MILE EAST OF THE KY-55 INTERCHANGE TO THE KY-1790 UNDERPASS. (2006BOPC) | C |  | NH | 2022 | 19800000 | 15840000 |  |  | 3960000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.083 | 2019-06-18 | ADD PROJECT TO STIP; PARENT NO. 99-391.04; NEW |  |  | SHELBY | 5-475 | I 64 |  | 35.9 | 38.18 | SAFETY | SAFETY(P) | WIDEN I-64 TO SIX LANES FROM KY 53 IN SHELBYVILLE TO KY 1790 UNDERPASS. | D |  | STP | 2019 | 2500000 | 2500000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.279 | 2021-03-05 | ADD C PHASE TO STIP; PARENT NO. 99-911.10; NEW |  |  | SHELBY | 5-940 | KY 53 |  | 0.8 | 1.1 | RELIABILITY | SAFETY-HAZARD ELIM(P) | Installation of High Friction Surface Treatment on KY 53 from MP 0.8 to MP 1.1 in Shelby County, KY. | C |  | STP | 2021 | 60000 | 60000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | SHELBY | 5-2035.4 | I 64 | 4.37 | 43.33 | 46.303 | RELIABILITY | MAJOR WIDENING(O) | WIDEN I-64 TO 6 LANES FROM KY-395 TO KY-151. (2004BOPC)(DESIGN FUNDING COVERS 5-2035.70 SECTION ALSO) | R |  | NH | 2021 | 100000 | 80000 |  |  | 20000 | [5 empty] | 0
STIP | [9 empty] | SHELBY | 5-2035.4 | I 64 | 4.37 | 43.33 | 46.303 | RELIABILITY | MAJOR WIDENING(O) | WIDEN I-64 TO 6 LANES FROM KY-395 TO KY-151. (2004BOPC)(DESIGN FUNDING COVERS 5-2035.70 SECTION ALSO) | U |  | NH | 2021 | 100000 | 80000 |  |  | 20000 | [5 empty] | 0
STIP | [9 empty] | SHELBY | 5-8511 | KY 53 | 1.9 | 6.064 | 8.006 | RELIABILITY | RECONSTRUCTION(O) | WIDEN KY-53 TO FOUR LANES FROM I-64 TO US-60.(08CCN)(10CCN) (12CCR)(14CCR)(16CCR)(18CCR) | C |  | STP | 2019 | 3000000 | 3000000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | SHELBY | 5-8511.01 | KY 53 | 1.9 | 6.064 | 8.006 | RELIABILITY | PREFINANCD CONVRSN(O) | WIDEN KY-53 TO FOUR LANES FROM I-64 TO US-60.(08CCN)(10CCN) (12CCR)(14CCR)(16CCR)(18CCR) | C |  | STP | 2020 | 7700000 | 7700000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.279 | 2021-03-05 | ADD C PHASE TO STIP; NEW |  |  | SHELBY | 5-8713 | US 60 |  | 11.5 | 12.878 | RELIABILITY | RECONSTRUCTION(O) | CONSTRUCT A THIRD LANE ON US-60 FROM THE MASONIC HOME TO ROCKET LANE. (12CCN)(14CCR) (2020CCR) | C |  | STP | 2021 | 2960000 | 2960000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.111 | 2019-08-02 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 9010405 | SHELBY | 5-9023 | KY 1848 |  | 6.418 | 10.591 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 1848 FROM MP 6.418 TO MP 10.591 IN SHELBY COUNTY. (2018BOP) | D |  | SAF | 2019 | 350000 | 350000 |  |  | 0 |  |  | OBLIGATED |  | 350000 | 350000 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.279 | 2021-03-05 | ADD R PHASE TO STIP; PARENT NO. 99-911.08; NEW |  |  | SHELBY | 5-9023 | KY 1848 |  | 6.418 | 10.591 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 1848 FROM MP 6.418 TO MP 10.591 IN SHELBY COUNTY. (2018BOP) | R |  | SAF | 2021 | 150000 | 150000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.279 | 2021-03-05 | ADD U PHASE TO STIP; PARENT NO. 99-911.08; NEW |  |  | SHELBY | 5-9023 | KY 1848 |  | 6.418 | 10.591 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 1848 FROM MP 6.418 TO MP 10.591 IN SHELBY COUNTY. (2018BOP) | U |  | SAF | 2021 | 322000 | 322000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.279 | 2021-03-05 | ADD C PHASE TO STIP; PARENT NO. 99-911.08; NEW |  |  | SHELBY | 5-9023 | KY 1848 |  | 6.418 | 10.591 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 1848 FROM MP 6.418 TO MP 10.591 IN SHELBY COUNTY. (2018BOP) | C |  | SAF | 2021 | 1200000 | 1200000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | SHELBY | 5-10024 | CR 1007 |  | 1.394 | 1.398 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF MOODY PIKE BRIDGE OVER FOX RUN CREEK. (106C00004N) | D |  | BR/STP | 2019 | 140000 | 86800 |  |  | 53200 | [5 empty] | 0
STIP | [9 empty] | SHELBY | 5-10024 | CR 1007 |  | 1.394 | 1.398 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF MOODY PIKE BRIDGE OVER FOX RUN CREEK. (106C00004N) | C |  | BR/STP | 2020 | 217000 | 134540 |  |  | 82460 | [5 empty] | 0
STIP | [9 empty] | SHELBY | 5-10025 | CR 1009 |  | 2.738 | 2.75 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF CLORE JACKSON RD BRIDGE OVER FOX RUN CREEK. (106C00007N) | D |  | BR/STP | 2019 | 140000 | 86800 |  |  | 53200 | [5 empty] | 0
STIP | [9 empty] | SHELBY | 5-10025 | CR 1009 |  | 2.738 | 2.75 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF CLORE JACKSON RD BRIDGE OVER FOX RUN CREEK. (106C00007N) | C |  | BR/STP | 2020 | 406000 | 251720 |  |  | 154280 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.123 | 2019-09-06 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD |  |  | SHELBY | 5-10025 | CR 1009 |  | 2.738 | 2.75 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF CLORE JACKSON RD BRIDGE OVER FOX RUN CREEK. (106C00007N) | C |  | BR | 2020 | 567000 | 567000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.279 | 2021-03-05 | ADD C PHASE TO STIP; PARENT NO. 99-1074.08; NEW |  |  | SHELBY | 5-10034 | KY 636 |  | 1.121 | 1.14 | ASSET MANAGEMENT | AM-BRIDGE (P) | REPLACE BRIDGE ON KY 636 AT MP 1.13 OVER LITTLE BEECH CREEK IN SHELBY COUNTY. | C |  | STP | 2021 | 1200000 | 1200000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | SHELBY | 5-20033 | I 64 |  | 38.18 | 43.33 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-064 BOTH DIRECTION(S) FROM MILEPOINT 38.18 (38 NON-CARDINAL) TO MILEPOINT 43.33 (43.892 NON-CARDINAL) | D |  | PM/NH | 2022 | 775000 | 620000 |  |  | 155000 | [5 empty] | 0
STIP | [9 empty] | SHELBY | 5-20033 | I 64 |  | 38.18 | 43.33 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-064 BOTH DIRECTION(S) FROM MILEPOINT 38.18 (38 NON-CARDINAL) TO MILEPOINT 43.33 (43.892 NON-CARDINAL) | C |  | PM/NH | 2022 | 7750000 | 6200000 |  |  | 1550000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.327 | 2021-09-08 | INCREASE FUNDS BASED ON NEW ESTIMATE; MOD |  |  | SHELBY | 5-20033 | I 64 |  | 38.18 | 43.33 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-064 BOTH DIRECTION(S) FROM MILEPOINT 38.18 (38 NON-CARDINAL) TO MILEPOINT 43.33 (43.892 NON-CARDINAL) | C |  | NHPP | 2021 | 10816850 | 10816850
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.229 | 2020-09-14 | ADD C PHASE TO STIP; PARENT NO. 99-224.14; NEW |  |  | SHELBY | 5-20057 | US 60 |  | 0 | 8.324 | RELIABILITY | AM-PAVEMENT(PRI)(P) | RESURFACING OF US 60 (MP 0.000 TO MP 8.324) IN SHELBY COUNTY. (2020CCR) | C |  | STP | 2020 | 1558194 | 1558194 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.306 | 2021-06-16 | ADD D PHASE TO STIP; NEW |  |  | SHELBY | 5-80004 | KY 55X |  | 1.2 | 1.3 | SAFETY | SAFETY (P) | FOUR RIGHT TURNING LANES AT THE INTERSECTION OF KY 55X AND KY 43 AND TWO LEFT TURNING LANES FROM KY 55X ONTO KY 43.(18CCN) (2020CCR) | D |  | SPP | 2021 | 150100 | 100 |  |  | 150000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.103 | 2019-07-29 | ADD PROJECT TO STIP; PARENT NO. 99-369.09; NEW | STPE | 0651103 | SIMPSON | 3-67 | I 65 |  | 0.1 | 0.6 | RELIABILITY | NEW REST AREA(P) | RECONSTRUCTION OF THE EXISTING SIMPSON COUNTY I-65 WELCOME CENTER BETWEEN NORTHBOUND MILE MARKER 0.1 AND MILE MARKER 0.6. (2018BOP) | C |  | TE | 2019 | 4220000 | 4220000 |  |  | 0 |  |  | OBLIGATED | 4220000 |  | 4220000 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.042 | 2019-03-25 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 0651101 | SIMPSON | 3-968 | I 65 |  | 6.5 | 8 | SAFETY | SAFETY-HAZARD ELIM(P) | CORRECT DRAINAGE ISSUE ALONG NB I-65. (2018BOP) | C |  | SAF | 2019 | 112000 | 112000 |  |  | 0 |  |  | OBLIGATED | 112000 | 0 | 112000 | 2019 | 3RD QUARTER
STIP | [9 empty] | SIMPSON | 3-8856 | US 31W | 2.302 | 8.477 | 10.799 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE US-31W FROM KY-1008 TO KY-621. (14CCN)(16CCR) | D |  | STP | 2021 | 1000000 | 800000 |  |  | 200000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.21 | 2020-07-31 | INCREASE FUND AMOUNT FOR PROJECT; MOD |  |  | SIMPSON | 3-8856 | US 31W | 2.302 | 8.477 | 10.799 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE US-31W FROM KY-1008 TO KY-621. (14CCN)(16CCR) | D |  | STP | 2020 | 1560000 | 1560000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | SIMPSON | 3-10007 | KY 621 |  | 6.68 | 6.686 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-621 BRIDGE OVER SINKING CREEK. (107B00018N) | D |  | BR/STP | 2019 | 157500 | 97650 |  |  | 59850 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030225 | SIMPSON | 3-10007 | KY 621 |  | 6.68 | 6.686 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-621 BRIDGE OVER SINKING CREEK. (107B00018N) | C |  | BR/STP | 2020 | 332500 | 206150 |  |  | 126350 |  |  | OBLIGATED |  | 529240 | 529240 | 2020 | 1ST QUARTER
STIP | [9 empty] | SIMPSON | 3-10008 | CR 1126 |  | 1.453 | 1.459 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF PLEASANT HILL ROAD BRIDGE OVER MAYS BRANCH. (107C00011N) | D |  | BR/STP | 2019 | 157500 | 97650 |  |  | 59850 | [5 empty] | 0
STIP | [9 empty] | SIMPSON | 3-10008 | CR 1126 |  | 1.453 | 1.459 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF PLEASANT HILL ROAD BRIDGE OVER MAYS BRANCH. (107C00011N) | C |  | BR/STP | 2020 | 280000 | 173600 |  |  | 106400 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.053 | 2019-04-25 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030093 | SIMPSON | 3-10008 | CR 1126 |  | 1.453 | 1.459 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF PLEASANT HILL ROAD BRIDGE OVER MAYS BRANCH. (107C00011N) | C |  | BR/STP | 2019 | 325000 | 325000 |  |  | 0 |  |  | OBLIGATED |  | 340290 | 340290 | 2019 | 3RD QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.161 | 2020-02-21 | ADD PROJECT TO STIP; NEW |  |  | SIMPSON | 3-10018 | KY 664 |  | 4.415 |  | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES ON KY 664 OVER SULPHER CREEK. (107B00020N) | C |  | BR/STP | 2020 | 623300 | 623300 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.306 | 2021-06-16 | ADD D PHASE TO STIP; NEW |  |  | SIMPSON | 3-80106 | KY 1008 |  | 2.1 | 2.4 |  | CONGESTION MITIGTN(O) | ADD A TURN LANE AT THE INTERSECTION OF KY 1008 AND US 31W (2020CCN) | D |  | SPP | 2021 | 250100 | 100 |  |  | 250000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.075 | 2019-05-28 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 9010389 | SPENCER | 5-932 | KY 1319 |  | 1.939 | 2.05 | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALL GUARDRAIL ALONG KY 1319 FROM MP 1.939 TO MP 2.050. (2018BOP) | C |  | SAF | 2019 | 43595 | 43595 |  |  | 0 |  |  | OBLIGATED |  | 47500 | 47500 | 2019 | 3RD QUARTER
STIP | [9 empty] | SPENCER | 5-1076 | KY 1169 |  | 8.53 | 8.552 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER BUCK CREEK ON KY 1169 75 FT EAST OF YODER TIPTON ROAD (CR 1142). (108B00022N)(EBRP) | D |  | BR/STP | 2019 | 245000 | 151900 |  |  | 93100 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 0503256 | SPENCER | 5-1076 | KY 1169 |  | 8.53 | 8.552 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE OVER BUCK CREEK ON KY 1169 75 FT EAST OF YODER TIPTON ROAD (CR 1142). (108B00022N)(EBRP) | C |  | BR/STP | 2020 | 497000 | 308140 |  |  | 188860 |  |  | OBLIGATED | 685877 | 73943 | 759820 | 2019 | 2ND QUARTER
STIP | [9 empty] | SPENCER | 5-8955 | KY 44 | 0.16 | 0.28 | 0.44 | SAFETY | SAFETY(P) | IMPROVE SAFETY AND ADDRESS GEOMETRIC DEFICIENCIES ALONG KY-44 NEAR DUTCHMAN CREEK ROAD. (16CCN) | D |  | STP | 2022 | 230000 | 184000 |  |  | 46000 | [5 empty] | 0
[8 empty] | HSIP | 5177005 | SPENCER SHELBY | 5-9017 | KY 55 |  | 11.27 0 | 13.566 2.184 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 55 FROM KY 155 IN SPENCER COUNTY TO KY 148 IN SHELBY COUNTY. (2018BOP) | D |  | SAF | 2019 | [7 empty] | OBLIGATED |  | 150000 | 150000 | 2019 | 1ST QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.175 | 2020-04-09 | ADD R PHASE TO STIP; PARENT NO. 99-911.08; NEW |  |  | SPENCER SHELBY | 5-9017 | KY 55 KY 148 |  | 11.27 0 | 13.566 2.184 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 55 FROM KY 155 IN SPENCER COUNTY TO KY 148 IN SHELBY COUNTY. (2018BOP) | R |  | SAF | 2020 | 35000 | 35000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.175 | 2020-04-09 | ADD U PHASE TO STIP; PARENT NO. 99-911.08; NEW |  |  | SPENCER SHELBY | 5-9017 | KY 55 KY 148 |  | 11.27 0 | 13.566 2.184 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 55 FROM KY 155 IN SPENCER COUNTY TO KY 148 IN SHELBY COUNTY. (2018BOP) | U |  | SAF | 2020 | 50000 | 50000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.283 | 2021-03-22 | ADD C PHASE TO STIP; PARENT NO. 99-911.08; NEW |  |  | SPENCER SHELBY | 5-9017 | KY 55 KY 148 |  | 11.27 0 | 13.566 2.184 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 55 FROM KY 155 IN SPENCER COUNTY TO KY 148 IN SHELBY COUNTY. (2018BOP) | C |  | SAF | 2020 | 1749000 | 1749000 | [8 empty] | 0
STIP | [9 empty] | SPENCER | 5-10013 | KY 1169 |  | 4.639 | 4.655 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 1169 BRIDGE OVER ELK CREEK. (108B00040N) | D |  | BR/STP | 2019 | 210000 | 130200 |  |  | 79800 | [5 empty] | 0
STIP | [9 empty] | SPENCER | 5-10013 | KY 1169 |  | 4.639 | 4.655 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 1169 BRIDGE OVER ELK CREEK. (108B00040N) | C |  | BR/STP | 2020 | 490000 | 303800 |  |  | 186200 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.021 | 2019-02-04 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030027 | SPENCER | 5-10013 | KY 1169 |  | 4.639 | 4.655 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 1169 BRIDGE OVER ELK CREEK. (108B00040N) | C |  | STP | 2019 | 770000 | 770000 |  |  | 0 |  |  | OBLIGATED |  | 626470.6 | 626470.6 | 2019 | 2ND QUARTER
STIP | [9 empty] | SPENCER | 5-10014 | CR 1128 |  | 0.025 | 0.033 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF WASHBURN LANE BRIDGE OVER ELK CREEK. (108B00017N)(SD) | D |  | BR/STP | 2019 | 192500 | 119350 |  |  | 73150 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030266 | SPENCER | 5-10014 | CR 1128 |  | 0.025 | 0.033 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF WASHBURN LANE BRIDGE OVER ELK CREEK. (108B00017N)(SD) | C |  | BR/STP | 2020 | 248500 | 154070 |  |  | 94430 |  |  | OBLIGATED | 75000 | 665055 | 740055 | 2020 | 2ND QUARTER
STIP | [9 empty] | SPENCER | 5-10026 | CR 1155 |  | 0.088 | 0.112 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF FEATHERBED HOLW RD BRIDGE OVER LITTLE PLUM CREEK. (108C00019N)(18CCR) | D |  | BR/STP | 2019 | 210000 | 130200 |  |  | 79800 | [5 empty] | 0
STIP | [9 empty] | SPENCER | 5-10026 | CR 1155 |  | 0.088 | 0.112 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF FEATHERBED HOLW RD BRIDGE OVER LITTLE PLUM CREEK. (108C00019N)(18CCR) | C |  | BR/STP | 2019 | 567000 | 351540 |  |  | 215460 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.075 | 2019-05-28 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030109 | SPENCER | 5-10026 | CR 1155 |  | 0.088 | 0.112 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF FEATHERBED HOLW RD BRIDGE OVER LITTLE PLUM CREEK. (108C00019N)(18CCR) | C |  | STP | 2020 | 1141257 | 1141257 |  |  | 0 |  |  | OBLIGATED |  | 1052855 | 1052855 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.152 | 2020-01-06 | ADD PROJECT TO STIP; PARENT NO. 99-911.09; NEW |  | 9010425 | STATEWIDE | 99-925 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | PAVEMENT FRICTION STUDY AND DATA COLLECTION ON ALL INTERSTATES, PARKWAYS, STATE PRIMARY AND STATE SECONDARY ROUTES. (2018BOP) | C |  | SAF | 2020 | 3500000 | 3500000 |  |  | 0 |  |  | OBLIGATED | 3100000 |  | 3100000 | 2020 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.257 | 2020-11-16 | ADD D PHASE TO STIP; PARENT NO. 99-911.10; NEW |  |  | STATEWIDE | 99-926 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | Project Development funds for on-call Consultant services to assist with the administration of the HSIP, including Planning Studies and Preliminary Engineering | D |  | SAF | 2021 | 2500000 | 2500000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.276 | 2021-02-12 | ADD D PHASE TO STIP; PARENT NO. 99-911.10; NEW |  |  | STATEWIDE | 99-927 |  |  |  |  | RELIABILITY | SAFETY-HAZARD ELIM(P) | Project Development funds for KYTC personnel for the administration of the HSIP, including Planning Studies and Preliminary Engineering. | D |  | SAF | 2021 | 1000000 | 1000000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.123 | 2019-09-06 | ADD PROJECT TO STIP; PARENT NO. 99-65.16 AND 99-65.17; NEW | STP | 6000167 | STATEWIDE | 99-10001 |  |  |  |  | ASSET MANAGEMENT | AM-BRIDGE (P) | DESIGN-BUILD; STATEWIDE BRIDGE REPLACEMENTS ON VARIOUS BRIDGES AS PART OF THE KYTC BRIDGE ASSET MANAGEMENT PROGRAM. (2018BOP) | C |  | BR | 2020 | 91885000 | 91885000 |  |  | 0 |  |  | OBLIGATED | 15973507 | 75138427.56 | 91111934.56 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.086 | 2019-06-19 | ADD PROJECT TO STIP; NEW |  |  | STATEWIDE | N/A | [6 empty] | FY 2020 SPR PART B RESEARCH PROGRAM. | N |  |  | 2019 | 3750000 | 3750000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.196 | 2020-06-16 | ADD PROJECT TO STIP; NEW |  |  | STATEWIDE | N/A | [6 empty] | FY 2021 SPR PART B RESEARCH PROGRAM. | N |  |  | 2020 | 3000000 | 2400000 |  |  | 600000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.308 | 2021-06-08 | ADD PROJECT TO STIP; NEW |  |  | STATEWIDE | N/A | [6 empty] | FY 2022 SPR PART B RESEARCH PROGRAM. | N |  |  | 2021 | 3750000 | 3000000 |  |  | 750000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.139 | 2019-10-25 | ADD PROJECT TO STIP; PARENT NO. 99-388.10; NEW |  |  | STATEWIDE | N/A |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | 2020-2021 OHIO RIVER BRIDGES FRACTURE CRITICAL INSPECTION. | N |  | STP | 2020 | 4800000 | 4800000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.145 | 2019-11-13 | ADD PROJECT TO STIP; NEW |  |  | STATEWIDE | N/A |  |  |  |  | RELIABILITY | SIGNING(P) | RAILROAD CROSSING SIGN INSTALLATIONS AT VARIOUS LOCATIONS STATEWIDE. | U |  | RRP | 2020 | 35000 | 35000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.152 | 2020-01-06 | ADD PROJECT TO STIP; NEW |  |  | STATEWIDE | N/A |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | EVALUATION OF DURABLE PAVEMENT STRIPING MATERIALS. | N |  | SAF | 2020 | 668000 | 668000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.152 | 2020-01-06 | ADD PROJECT TO STIP; NEW | HSIP | 9010427 | STATEWIDE | N/A |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | COMMERCIAL MOTOR VEHICLE (CMV) CRASH INVESTIGATION IN KENTUCKY. | N |  | SAF | 2020 | 181500 | 181500 |  |  | 0 |  |  | OBLIGATED | 163350 |  | 163350 | 2020 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.175 | 2020-04-09 | ADD PROJECT TO STIP; NEW |  |  | STATEWIDE | N/A |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | MOBILE LIDAR DATA COLLECTION & HIGH FRICTION SURFACE EVALUATION. | N |  | SAF | 2020 | 550000 | 550000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.238 | 2020-09-25 | ADD PROJECT TO STIP; NEW |  |  | STATEWIDE | HUTE |  |  |  |  | SAFETY | SAFETY (P) | HVUT EVASION ANALYSIS & INTERAGENCY EFFORTS. | N |  | Z960 | 2020 | 395000 | 395000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | TAYLOR | 4-142.2 | KY 555 |  |  |  | RELIABILITY | NEW ROUTE(O) | HEARTLAND PARKWAY: IMPROVE MOBILITY AND CONNECTIVITY VIA NEW CAMPBELLSVILLE BYPASS FROM KY-55 SOUTH OF CAMPBELLSVILLE TO KY-70. SECTION 1. (2010BOP)(14CCR)(16CCR) | C |  | NH | 2022 | 7600000 | 6080000 |  |  | 1520000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.118 | 2019-08-19 | COSE INCREASE BASED ON NEW ENGINEERING ESTIMATE; MOD | NHPP | 6000143 | TAYLOR | 4-142.2 | KY 555 |  |  |  | RELIABILITY | NEW ROUTE(O) | HEARTLAND PARKWAY: IMPROVE MOBILITY AND CONNECTIVITY VIA NEW CAMPBELLSVILLE BYPASS FROM KY-55 SOUTH OF CAMPBELLSVILLE TO KY-70. SECTION 1. (2010BOP)(14CCR)(16CCR) | C |  | NH | 2019 | 17765000 | 17765000 |  |  | 0 |  |  | OBLIGATED | 4000000 | 14957191 | 18957191 | 2019 | 4TH QUARTER
STIP | [9 empty] | TAYLOR | 4-142.21 | KY 555 |  |  |  | RELIABILITY | PREFINANCD CONVRSN(O) | HEARTLAND PARKWAY: IMPROVE MOBILITY AND CONNECTIVITY VIA NEW CAMPBELLSVILLE BYPASS FROM KY-55 SOUTH OF CAMPBELLSVILLE TO KY-70. SECTION 1. (2010BOP)(14CCR)(16CCR)(18CCR) | C |  | NH | 2020 | 7600000 | 7600000 |  |  | 0 | [5 empty] | 0
STIP | [7 empty] | NHPP | 6000098 | TAYLOR | 4-142.3 | KY 555 |  |  |  | RELIABILITY | NEW ROUTE(O) | HEARTLAND PARKWAY: IMPROVE MOBILITY AND CONNECTIVITY VIA NEW CAMPBELLSVILLE BYPASS FROM KY-70 TO US-68 EAST OF CAMPBELLSVILLE. SECTION 2. (2010BOP)(16CCR) | U |  | NH | 2019 | 1000000 | 1000000 |  |  | 0 |  |  | OBLIGATED |  | 1000000 | 1000000 | 2019 | 3RD QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.25 | 2010-10-22 | ADD C PHASE TO STIP; PARENT NO. 4-142.10; NEW |  |  | TAYLOR | 4-142.3 | KY 555 |  |  |  | RELIABILITY | NEW ROUTE(O) | HEARTLAND PARKWAY: IMPROVE MOBILITY AND CONNECTIVITY VIA NEW CAMPBELLSVILLE BYPASS FROM KY-70 TO US-68 EAST OF CAMPBELLSVILLE. SECTION 2. (2010BOP)(16CCR) | C |  | NH | 2021 | 12600000 | 12600000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.203 | 2020-07-15 | ADD D PHASE TO STIP; NEW |  |  | TAYLOR MARION | 4-8917 | US 68 |  | 0 | 9.364 |  | MAJOR WIDENING(O) | HEARTLAND PARKWAY: ADDRESS SAFETY AND MOBILITY CONCERNS ON US 68 FROM KY 1799 (AIRPORT RD) IN TAYLOR COUNTY TO THE LEBANON BYPASS IN MARION COUNTY. (BUILD PROJECT). | D |  | NHPP | 2020 | 600000 | 600000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.203 | 2020-07-15 | ADD U PHASE TO STIP; NEW |  |  | TAYLOR MARION | 4-8917 | US 68 |  | 0 | 9.364 |  | MAJOR WIDENING(O) | HEARTLAND PARKWAY: ADDRESS SAFETY AND MOBILITY CONCERNS ON US 68 FROM KY 1799 (AIRPORT RD) IN TAYLOR COUNTY TO THE LEBANON BYPASS IN MARION COUNTY. (BUILD PROJECT). | U |  | NHPP | 2020 | 1500000 | 1500000 |  |  | 0 | [5 empty] | 0
STIP | [7 empty] | NHPP | 0551047 | TAYLOR | 4-8920 | KY 55 |  | 0 | 8.003 | RELIABILITY | RECONSTRUCTION(O) | HEARTLAND PARKWAY: IMPROVE MOBILITY ON KY-55 FROM SOUTH OF THE TAYLOR/ADAIR COUNTY LINE TO THE CAMPBELLSVILLE BYPASS. (16CCN) | R |  | NH | 2019 | 500000 | 500000 |  |  | 0 |  |  | OBLIGATED | 20000 |  | 20000 | 2019 | 2ND QUARTER
STIP | [7 empty] | NHPP | 0551047 | TAYLOR | 4-8920 | KY 55 |  | 0 | 8.003 | RELIABILITY | RECONSTRUCTION(O) | HEARTLAND PARKWAY: IMPROVE MOBILITY ON KY-55 FROM SOUTH OF THE TAYLOR/ADAIR COUNTY LINE TO THE CAMPBELLSVILLE BYPASS. (16CCN) | U |  | NH | 2019 | 1000000 | 1000000 |  |  | 0 |  |  | OBLIGATED |  | 1300000 | 1300000 | 2019 | 2ND QUARTER
STIP | [7 empty] | NHPP | 0551047 | TAYLOR | 4-8920 | KY 55 |  | 0 | 8.003 | RELIABILITY | RECONSTRUCTION(O) | HEARTLAND PARKWAY: IMPROVE MOBILITY ON KY-55 FROM SOUTH OF THE TAYLOR/ADAIR COUNTY LINE TO THE CAMPBELLSVILLE BYPASS. (16CCN) | C |  | NH | 2020 | 1000000 | 1000000 |  |  | 0 |  |  | OBLIGATED | 10136675 |  | 10136675 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.091 | 2019-06-28 | ADD ADDITIONAL FUNDS TO C PHASE AND UPDATE FISCAL YEAR; MOD |  |  | TAYLOR ADAIR | 4-8920 | KY 55 |  | 0 | 8.003 | RELIABILITY | RECONSTRUCTION(O) | HEARTLAND PARKWAY: IMPROVE MOBILITY ON KY-55 FROM SOUTH OF THE TAYLOR/ADAIR COUNTY LINE TO THE CAMPBELLSVILLE BYPASS. (16CCN) | C |  | NH | 2019 | 10308400 | 10308400 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | TAYLOR | 4-8920.01 | KY 55 |  | 0 | 8.003 | RELIABILITY | PREFINANCD CONVRSN(O) | HEARTLAND PARKWAY: IMPROVE MOBILITY ON KY-55 FROM SOUTH OF THE TAYLOR/ADAIR COUNTY LINE TO THE CAMPBELLSVILLE BYPASS. (16CCN)(18CCR) | C |  | NH | 2020 | 7000000 | 7000000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.015 | 2019-01-25 | ADD PROJECT TO STIP; PARENT NO. 99-911.06; NEW | HSIP | 9010362 | TAYLOR | 4-9006.6 | US 68 |  | 5.867 | 5.977 | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALL GREEN EXTENSION LOOP DETECTORS, UPDATE THE SIGNAL BY INSTALLING REFLECTIVE BACKPLATES, AND SIGNING UPGRADES AT THE INTERSECTION OF US 68 & KY 289. (2018BOP) | C |  | SAF | 2019 | 77000 | 77000 |  |  | 0 |  |  | OBLIGATED | 77000 |  | 77000 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.015 | 2019-01-25 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 5105048 | TAYLOR | 4-9010 | US 68 |  | 3.5 | 4.9 | SAFETY | SAFETY-HAZARD ELIM(P) | ADDING NEW TURN LANES, IMPROVING EXISTING TURN LANES, AND SIGNAL IMPROVEMENTS ALONG US 68 FROM MP 3.5 TO 4.9. (2018BOP) | C |  | SAF | 2019 | 480000 | 480000 |  |  | 0 |  |  | OBLIGATED | 655938 |  | 655938 | 2019 | 2ND QUARTER
STIP | [9 empty] | TAYLOR | 4-10006 | KY 323 |  | 8.731 | 8.737 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF WEST MAIN STREET BRIDGE OVER BUCKHORN CRK.. (109B00051N) | D |  | BR/STP | 2019 | 157500 | 97650 |  |  | 59850 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030155 | TAYLOR | 4-10006 | KY 323 |  | 8.731 | 8.737 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF WEST MAIN STREET BRIDGE OVER BUCKHORN CRK.. (109B00051N) | C |  | BR/STP | 2020 | 805000 | 499100 |  |  | 305900 |  |  | OBLIGATED |  | 878080 | 878080 | 2019 | 4TH QUARTER
STIP | [9 empty] | TAYLOR | 4-10007 | CS 1241 |  | 0.077 | 0.083 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF SOUTH JACKSON ST BRIDGE OVER BUCKHORN CREEK. (109C00028N) | D |  | BR/STP | 2019 | 105000 | 65100 |  |  | 39900 | [5 empty] | 0
STIP | [9 empty] | TAYLOR | 4-10007 | CS 1241 |  | 0.077 | 0.083 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF SOUTH JACKSON ST BRIDGE OVER BUCKHORN CREEK. (109C00028N) | C |  | BR/STP | 2020 | 367500 | 227850 |  |  | 139650 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.046 | 2019-04-07 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030081 | TAYLOR | 4-10007 | CS 1241 |  | 0.077 | 0.083 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF SOUTH JACKSON ST BRIDGE OVER BUCKHORN CREEK. (109C00028N) | C |  | BR/STP | 2019 | 460000 | 460000 |  |  | 0 |  |  | OBLIGATED |  | 512400 | 512400 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.029 | 2019-02-21 | ADD PROJECT TO STIP; PARENT NO. 9-9013.00; NEW | HSIP | 9010373 | TODD | 3-9013.2 | US 68 KY 181 |  | 8.45 12.758 | 8.95 13.326 | SAFETY | SAFETY-HAZARD ELIM(P) | CONSTRUCT OFFSET LEFT TURN LANES, UPDATE THE SIGNING & STRIPING, AND UPDATE THE SIGNAL TO INCLUDE REFLECTIVE BACKPLATES AT THE INTERSECTION OF US 68 & KY 181. (2018BOP) | C |  | SAF | 2019 | 501000 | 501000 |  |  | 0 |  |  | OBLIGATED |  | 460900 | 460900 | 2019 | 2ND QUARTER
STIP | [9 empty] | TODD | 3-10009 | CR 1333 |  | 1.471 | 1.475 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF RATTLESNAKE RD BRIDGE OVER BUCK FORK. (110C00059N) | D |  | BR/STP | 2019 | 192500 | 119350 |  |  | 73150 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030018 | TODD | 3-10009 | CR 1333 |  | 1.471 | 1.475 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF RATTLESNAKE RD BRIDGE OVER BUCK FORK. (110C00059N) | C |  | BR/STP | 2020 | 294000 | 182280 |  |  | 111720 |  |  | OBLIGATED |  | 256700 | 256700 | 2019 | 2ND QUARTER
STIP | [9 empty] | TODD | 3-10013 | CR 1233 |  | 0.028 | 0.032 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF ROGER Q MILL RD. BRIDGE OVER RED RIVER W FORK BRANCH. (110C00061N) | D |  | BR/STP | 2019 | 157500 | 97650 |  |  | 59850 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030019 | TODD | 3-10013 | CR 1233 |  | 0.028 | 0.032 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF ROGER Q MILL RD. BRIDGE OVER RED RIVER W FORK BRANCH. (110C00061N) | C |  | BR/STP | 2020 | 385000 | 238700 |  |  | 146300 |  |  | OBLIGATED |  | 257210 | 257210 | 2018 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.229 | 2020-09-14 | ADD C PHASE TO STIP; PARENT NO. 99-224.14; NEW |  |  | TODD | 3-20035 | KY 104 |  | 10.094 | 14.246 | RELIABILITY | AM-PAVEMENT(PRI)(P) | RESURFACING OF KY 104 (MP 10.094 TO MP 14.246) IN TODD COUNTY. (2020CCR) | C |  | STP | 2020 | 472967 | 472967 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.269 | 2021-01-22 | ADD R PHASE TO STIP; NEW |  |  | TODD | 3-80001 | US 79 |  | 0 | 3 | RELIABILITY | MINOR WIDENING(O) | REDUCE CONGESTION AND IMPROVE MOBILITY ON US 79 FROM MP 0 TO 3 IN GUTHRIE INCLUDING WIDENING THE BRIDGE OVER CSX RAILROAD TO 4 LANES (FOR NOVELIS). (NEEDS PBFS) (2020CCR) | R |  | NHPP | 2021 | 2000000 | 2000000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.269 | 2021-01-22 | ADD U PHASE TO STIP; NEW |  |  | TODD | 3-80001 | US 79 |  | 0 | 3 | RELIABILITY | MINOR WIDENING(O) | REDUCE CONGESTION AND IMPROVE MOBILITY ON US 79 FROM MP 0 TO 3 IN GUTHRIE INCLUDING WIDENING THE BRIDGE OVER CSX RAILROAD TO 4 LANES (FOR NOVELIS). (NEEDS PBFS) (2020CCR) | U |  | NHPP | 2021 | 4815000 | 4815000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.269 | 2021-01-22 | ADD C PHASE TO STIP; NEW |  |  | TODD | 3-80001 | US 79 |  | 0 | 3 | RELIABILITY | MINOR WIDENING(O) | REDUCE CONGESTION AND IMPROVE MOBILITY ON US 79 FROM MP 0 TO 3 IN GUTHRIE INCLUDING WIDENING THE BRIDGE OVER CSX RAILROAD TO 4 LANES (FOR NOVELIS). (NEEDS PBFS) (2020CCR) | C |  | NHPP | 2021 | 6942000 | 6942000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | TRIGG | 1-1160 | CR 1380 |  | 0.011 | 0.017 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON CR-1380 (0.014) OVER DYERS CREEK 111C00027N | D |  | BR/STP | 2019 | 140000 | 86800 |  |  | 53200 | [5 empty] | 0
STIP | [9 empty] | TRIGG | 1-1160 | CR 1380 |  | 0.011 | 0.017 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON CR-1380 (0.014) OVER DYERS CREEK 111C00027N | C |  | BR/STP | 2020 | 381500 | 236530 |  |  | 144970 | [5 empty] | 0
STIP | [9 empty] | TRIGG | 1-2039 | I 24 |  | 66.5 | 66.53 | ASSET MANAGEMENT | AM-BRIDGE (P) | OVERLAY BRIDGE DECK AND ADDRESS DEFICIENCIES OF EXPANSION JOINTS ON EASTBOUND I-24 BRIDGE OVER TRW RAILROAD EAST OF US 68 AT (MP 66.515). (111B00027R) (2012BOP)(SD) | C |  | BR/NH | 2019 | 250000 | 155000 |  |  | 95000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.263 | 2020-12-11 | ADD D PHASE TO STIP; NEW |  |  | TRIGG | 1-8951 | KY 139 |  | 17.83 | 17.98 | RELIABILITY | SIGNING(P) | REALIGN KY 124 APPROACH TO KY 139 TO IMPROVE INTERSECTION ANGLE AND SIGHT DISTANCE. (16CCN)(18CCN) (2020CCR) | D |  | STP | 2021 | 200000 | 200000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | TRIGG | 1-10005 | KY 139 |  | 13.386 | 13.422 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-139 BRIDGE OVER BURGE CREEK. (111B00012N) | D |  | BR/STP | 2019 | 280000 | 173600 |  |  | 106400 | [5 empty] | 0
STIP | [9 empty] | TRIGG | 1-10005 | KY 139 |  | 13.386 | 13.422 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-139 BRIDGE OVER BURGE CREEK. (111B00012N) | C |  | BR/STP | 2020 | 997500 | 618450 |  |  | 379050 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.283 | 2021-03-22 | ADD C PHASET TO STIP; PARENT NO. 1-20011.00; NEW |  |  | TRIGG CALDWELL | 1-20011.10 | 1 24 |  | 55.5 | 64.5 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT ON I-024 BOTH DIRECTION(S) FROM MILEPOINT 55.5 TO MILEPOINT 64.5. | C |  | NHPP | 2021 | 18315000 | 18315000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.126 | 2019-09-20 | ADD PROJECT TO STIP. THIS PROJECT IS IN THE 2018 HIGHWAY PLAN FOR FISCAL YEAR 2020 FOR $13,400,000. ONLY NEED $9,176,000; NEW |  |  | TRIGG | 1-20020 | I 24 |  | 57.389 | 69.389 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT ON I-24 CARDINAL DIRECTION(S) FROM MILEPOINT 57.39 TO MILEPOINT 69.83. (LET UNDER ITEM NUMBER 1-20011) | C |  | NH | 2020 | 9176000 | 9176000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.126 | 2019-09-20 | ADD PROJECT TO STIP. THIS PROJECT IS IN THE 2018 HIGHWAY PLAN FOR FISCAL YEAR 2020 FOR $13,400,000. ONLY NEED $9,176,000; NEW |  |  | TRIGG | 1-20022 | I 24 |  | 57.39 | 69.83 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT ON I-24 NON-CARDINAL DIRECTION(S) FROM MILEPOINT 57.389 TO MILEPOINT 69.389. (LET UNDER ITEM NUMBER 1-20011) | C |  | NH | 2020 | 9176000 | 9176000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.229 | 2020-09-14 | ADD C PHASE TO STIP; PARENT NO. 99-224.14; NEW |  |  | TRIGG | 1-20036 | KY 139 US 68X |  | 9 0 | 11.850 1.926 | RELIABILITY | AM-PAVEMENT(PRI)(P) | RESURFACING OF KY 139 (MP 9.000 TO MP 11.850) AND US 68X (MP 0.000 TO MP 1.926) IN TRIGG COUNTY. (2020CCR) | C |  | STP | 2020 | 713949 | 713949 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.175 | 2020-04-09 | ADD D PHASE TO STIP; PARENT NO. 99-911.09; NEW |  |  | TRIMBLE | 5-9025 | US 42 |  | 8.268 | 14.25 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON US 42 FROM MP 8.268 TO MP 14.520 IN TRIMBLE COUNTY, KY. (2018BOP) | D |  | SAF | 2020 | 300000 | 300000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.279 | 2021-03-05 | ADD C PHASE TO STIP; PARENT NO. 2-310.01; NEW |  |  | UNION | 2-310.21 | KY 56 |  | 2.723 | 7.182 | RELIABILITY | MINOR WIDENING(O) | ADDRESS SAFETY, CONDITION AND SERVICE CONCERN FROM KY 109 TO WEST OF KY 360 TO ESTABLISH TRUCK NETWORK CONNECTION TO SHAWNEETOWN BRIDGE.(14CCR) (SAME AS ITEM NO. 2-310.20 IN 2014 SYP) (2020CCR) | C |  | STP | 2021 | 18000000 | 18000000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.067 | 2019-05-13 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 0601206 | UNION | 2-917 | US 60 |  | 0 | 26.069 | SAFETY | SAFETY-HAZARD ELIM(P) | REPLACEMENT OF TARGETED GUARDRAIL END TREATMENTS ON US 60 FROM MP 0.000 TO MP 26.069 (2018BOP). | C |  | SAF | 2019 | 305000 | 305000 |  |  | 0 |  |  | OBLIGATED |  | 82700 | 82700 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.103 | 2019-07-29 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 0601208 | UNION | 2-926 | US 60 |  | 0 | 2.915 | SAFETY | SAFETY-HAZARD ELIM(P) | REPLACEMENT OF TARGETED GUARDRAIL END TREATMENTS ON US 60B FROM MP 0.000 TO 2.915 IN UNION COUNTY, KY. | C |  | SAF | 2019 | 190000 | 190000 |  |  | 0 |  |  | OBLIGATED |  | 193200 | 193200 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.25 | 2020-10-22 | ADD C PHASE TO STIP; PARENT NO. 99-911.06; NEW |  |  | UNION | 2-9009 | KY 130 |  | 9.584 | 15.657 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ALONG KY 130 BETWEEN MP 9.584 AND MP 15.657 IN UNION COUNTY, KY. (2016BOP) | C |  | SAF | 2021 | 1383000 | 1383000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | UNION | 2-10017 | KY 359 |  | 6.147 | 6.166 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-359 BRIDGE OVER LITTLE MASON CREEK. (113B00008N) | D |  | BR/STP | 2019 | 210000 | 130200 |  |  | 79800 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030102 | UNION | 2-10017 | KY 359 |  | 6.147 | 6.166 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-359 BRIDGE OVER LITTLE MASON CREEK. (113B00008N) | C |  | BR/STP | 2020 | 682500 | 423150 |  |  | 259350 |  |  | OBLIGATED |  | 763790 | 763790 | 2019 | 4TH QUARTER
STIP | [9 empty] | UNION | 2-10026 | KY 492 |  | 6.096 | 6.104 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 492 BRIDGE OVER WASH CREEK. (113B00054N) | D |  | BR/STP | 2019 | 70000 | 43400 |  |  | 26600 | [5 empty] | 0
STIP | [7 empty] | STP | 9030006 | UNION | 2-10026 | KY 492 |  | 6.096 | 6.104 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 492 BRIDGE OVER WASH CREEK. (113B00054N) | C |  | BR/STP | 2020 | 350000 | 217000 |  |  | 133000 |  |  | OBLIGATED | 591000 |  | 591000 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.017 | 2019-01-23 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD |  |  | UNION | 2-10026 | KY 492 |  | 6.096 | 6.104 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 492 BRIDGE OVER WASH CREEK. (113B00054N) | C |  | STP | 2020 | 648000 | 648000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.229 | 2020-09-14 | ADD C PHASE TO STIP; PARENT NO. 99-224.14; NEW |  |  | UNION | 2-20057 | KY 56 KY 1180 |  | 11.460 1.513 | 13.550 4.517 | RELIABILITY | AM-PAVEMENT(PRI)(P) | RESURFACING OF KY 56 (MP 11.460 TO MP 13.550) AND KY 1180 (MP 1.513 TO MP 4.517) IN UNION COUNTY. (2020CCR) | C |  | STP | 2020 | 829513 | 829513 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.177 | 2020-04-24 | ADD C PHASE TO STIP; PARENT NO. 99-911.08; NEW |  |  | VARIOUS | 1-911 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALLATION OF STRIPING ON VARIOUS ROUTES IN DISTRICT 1. (2018BOP) | C |  | SAF | 2020 | 830000 | 830000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.155 | 2020-01-22 | ADD PROJECT TO STIP; PARENT NO. 99-911.09; NEW | HSIP | 9010412 | VARIOUS | 1-982 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALLATION OF PAVEMENT MARKERS ON VARIOUS ROUTES IN DISTRICT 1. (HSIP)(2018BOP) | C |  | SAF | 2020 | 45000 | 45000 |  |  | 0 |  |  | OBLIGATED | 45000 |  | 45000 | 2020 | 2ND QUARTER |  | 229910.155
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.087 | 2019-06-21 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW |  |  | VARIOUS | 2-924 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALLATION OF STRIPING ON VARIOUS ROUTES IN DISTRICT 2. (2018BOP) | C |  | SAF | 2019 | 570000 | 570000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.155 | 2020-01-22 | ADD PROJECT TO STIP; PARENT NO. 99-911.09; NEW | HSIP | 9010413 | VARIOUS | 2-995 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALLATION OF PAVEMENT MARKERS ON VARIOUS ROUTES IN DISTRICT 2. (HSIP)(2018BOP) | C |  | SAF | 2019 | 68000 | 68000 |  |  | 0 |  |  | OBLIGATED | 68000 |  | 68000 | 2020 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.029 | 2019-02-21 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 9010364 | VARIOUS | 3-930 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALLATION OF PAVEMENT MARKERS ON VARIOUS ROUTES IN DISTRICT 3. (2018BOP) | C |  | SAF | 2019 | 310000 | 310000 |  |  | 0 |  |  | OBLIGATED |  | 310000 | 310000 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.087 | 2019-06-21 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW |  |  | VARIOUS | 3-931 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALLATION OF STRIPING ON VARIOUS ROUTES IN DISTRICT 3. (2018BOP) | C |  | SAF | 2019 | 940000 | 940000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.155 | 2020-01-22 | ADD PROJECT TO STIP; PARENT NO. 99-911.09; NEW | HSIP | 9010414 | VARIOUS | 3-967 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALLATION OF PAVEMENT MARKERS ON VARIOUS ROUTES IN DISTRICT 3. (HSIP)(2018BOP) | C |  | SAF | 2020 | 414000 | 414000 |  |  | 0 |  |  | OBLIGATED | 414000 |  | 414000 | 2020 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.029 | 2019-02-21 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 9010365 | VARIOUS | 4-941 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALLATION OF PAVEMENT MARKERS ON VARIOUS ROUTES IN DISTRICT 4. (2018BOP) | C |  | SAF | 2019 | 215000 | 215000 |  |  | 0 |  |  | OBLIGATED |  | 215000 | 215000 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.087 | 2019-06-21 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW |  |  | VARIOUS | 4-942 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALLATION OF STRIPING ON VARIOUS ROUTES IN DISTRICT 4. (2018BOP) | C |  | SAF | 2019 | 1125000 | 1125000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.155 | 2020-01-22 | ADD PROJECT TO STIP; PARENT NO. 99-911.09; NEW |  |  | VARIOUS | 4-990 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALLATION OF PAVEMENT MARKERS ON VARIOUS ROUTES IN DISTRICT 4. (HSIP)(2018BOP) | C |  | SAF | 2020 | 55000 | 55000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.162 | 2020-01-27 | TIP FY 18-22; ADMIN MOD#12; UPDATE FUND AMOUNT; MOD | HSIP | 9010415 | VARIOUS | 4-990 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALLATION OF PAVEMENT MARKERS ON VARIOUS ROUTES IN DISTRICT 4. (HSIP)(2018BOP) | C |  | SAF | 2020 | 165000 | 165000 |  |  | 0 |  |  | OBLIGATED | 55000 |  | 55000 | 2020 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.029 | 2019-02-21 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 9010366 | VARIOUS | 5-933 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALLATION OF PAVEMENT MARKERS ON VARIOUS ROUTES IN DISTRICT 5. (2018BOP) | C |  | SAF | 2019 | 795000 | 795000 |  |  | 0 |  |  | OBLIGATED |  | 795000 | 795000 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.087 | 2019-06-21 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW |  |  | VARIOUS | 5-935 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALLATION OF STRIPING ON VARIOUS ROUTES IN DISTRICT 5. (2018BOP) | C |  | SAF | 2019 | 900000 | 900000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.155 | 2020-01-22 | ADD PROJECT TO STIP; PARENT NO. 99-911.09; NEW | HSIP | 9010416 | VARIOUS | 5-962 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALLATION OF PAVEMENT MARKERS ON VARIOUS ROUTES IN DISTRICT 5. (HSIP)(2018BOP) | C |  | SAF | 2020 | 900000 | 900000 |  |  | 0 |  |  | OBLIGATED | 900000 |  | 900000 | 2020 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.029 | 2019-02-21 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 9010367 | VARIOUS | 6-938 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALLATION OF PAVEMENT MARKERS ON VARIOUS ROUTES IN DISTRICT 6. (2018BOP) | C |  | SAF | 2019 | 365000 | 365000 |  |  | 0 |  |  | OBLIGATED |  | 365000 | 365000 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.087 | 2019-06-21 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW |  |  | VARIOUS | 6-939 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALLATION OF STRIPING ON VARIOUS ROUTES IN DISTRICT 6. (2018BOP) | C |  | SAF | 2019 | 840000 | 840000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.155 | 2020-01-22 | ADD PROJECT TO STIP; PARENT NO. 99-911.09; NEW | HSIP | 9010417 | VARIOUS | 6-957 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALLATION OF PAVEMENT MARKERS ON VARIOUS ROUTES IN DISTRICT 6. (HSIP)(2018BOP) | C |  | SAF | 2020 | 465000 | 465000 |  |  | 0 |  |  | OBLIGATED | 465000 |  | 465000 | 2020 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.087 | 2019-06-21 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW |  |  | VARIOUS | 7-950 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALLATION OF STRIPING ON VARIOUS ROUTES IN DISTRICT 7. (2018BOP) | C |  | SAF | 2019 | 735000 | 735000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.251 | 2020-10-22 | TIP FY 17-20, ADMIN MOD#36; ADD PROJECT TO STIP; NEW |  |  | VARIOUS | 7-958 |  |  | 1.372 | 10.153 | SAFETY | SAFETY-HAZARD ELIM(P) | Trimming and/or Removal of Trees along various routes in Woodford, Fayette, Jessamine, Montgomery and Scott Counties. (2020BOP) | C |  | SAF | 2020 | 1440000 | 1296000 |  |  | 144000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.155 | 2020-01-22 | ADD PROJECT TO STIP; PARENT NO. 99-911.09; NEW | HSIP | 9010418 | VARIOUS | 7-993 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALLATION OF PAVEMENT MARKERS ON VARIOUS ROUTES IN DISTRICT 7. (HSIP)(2018BOP) | C |  | SAF | 2020 | 290000 | 290000 |  |  | 0 |  |  | OBLIGATED | 290000 |  | 290000 | 2020 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.087 | 2019-06-21 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW |  |  | VARIOUS | 8-944 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALLATION OF STRIPING ON VARIOUS ROUTES IN DISTRICT 8. (2018BOP) | C |  | SAF | 2019 | 1101000 | 1101000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.155 | 2020-01-22 | ADD PROJECT TO STIP; PARENT NO. 99-911.09; NEW | HSIP | 9010419 | VARIOUS | 8-987 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALLATION OF PAVEMENT MARKERS ON VARIOUS ROUTES IN DISTRICT 8. (HSIP)(2018BOP) | C |  | SAF | 2020 | 120000 | 120000 |  |  | 0 |  |  | OBLIGATED | 120000 |  | 120000 | 2020 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.244 | 2020-10-16 | ADD C PHASE TO STIP; PARENT NO. 99-514.01; NEW |  |  | VARIOUS | 8-10046 |  |  |  |  | RELIABILITY | AM-BRIDGE (P) | PREVENTATIVE BRIDGE MAINTENANCE CLEANING AND PAINTING ON VARIOUS BRIDGES IN DISTRICT 8. (100B00067L/R); (104B00022N); (102B00017N); (116B00001N) | C |  | STP | 2021 | 980000 | 980000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.269 | 2021-01-22 | INCREASE FUND AMOUNT BASED ON NEW ESTIMATE; MOD |  |  | VARIOUS | 8-10046 |  |  |  |  | RELIABILITY | AM-BRIDGE (P) | PREVENTATIVE BRIDGE MAINTENANCE CLEANING AND PAINTING ON VARIOUS BRIDGES IN DISTRICT 8. (100B00067L/R); (104B00022N); (102B00017N); (116B00001N) | C |  | STP | 2021 | 1200000 | 1200000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.029 | 2019-02-21 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 9010369 | VARIOUS | 9-947 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALLATION OF PAVEMENT MARKERS ON VARIOUS ROUTES IN DISTRICT 9. (2018BOP) | C |  | SAF | 2019 | 215000 | 215000 |  |  | 0 |  |  | OBLIGATED |  | 215000 | 215000 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.145 | 2019-11-13 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW |  |  | VARIOUS | 9-948 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALLATION OF STRIPING ON VARIOUS ROUTES IN DISTRICT 9. (2018BOP) | C |  | SAF | 2020 | 1163000 | 1163000 |  |  | 0 |  |  | OBLIGATED | 1243671 |  | 1243671 | 2020 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.155 | 2020-01-22 | ADD PROJECT TO STIP; PARENT NO. 99-911.09; NEW | HSIP | 9010420 | VARIOUS | 9-995 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALLATION OF PAVEMENT MARKERS ON VARIOUS ROUTES IN DISTRICT 9. (HSIP)(2018BOP) | C |  | SAF | 2020 | 110000 | 110000 |  |  | 0 |  |  | OBLIGATED | 110000 |  | 110000 | 2020 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.145 | 2019-11-13 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW |  |  | VARIOUS | 10-939 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALLATION OF STRIPING ON VARIOUS ROUTES IN DISTRICT 10. (2018BOP) | C |  | SAF | 2020 | 920000 | 920000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.155 | 2020-01-22 | ADD PROJECT TO STIP; PARENT NO. 99-911.09; NEW | HSIP | 9010421 | VARIOUS | 10-990 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALLATION OF PAVEMENT MARKERS ON VARIOUS ROUTES IN DISTRICT 10. (HSIP)(2018BOP) | C |  | SAF | 2020 | 130000 | 130000 |  |  | 0 |  |  | OBLIGATED | 130000 |  | 130000 | 2020 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.029 | 2019-02-21 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 9010370 | VARIOUS | 11-969 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALLATION OF PAVEMENT MARKERS ON VARIOUS ROUTES IN DISTRICT 11. (2018BOP) | C |  | SAF | 2019 | 225000 | 225000 |  |  | 0 |  |  | OBLIGATED |  | 255000 | 255000 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.087 | 2019-06-21 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW |  |  | VARIOUS | 11-970 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALLATION OF STRIPING ON VARIOUS ROUTES IN DISTRICT 11. (2018BOP) | C |  | SAF | 2019 | 840000 | 840000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.155 | 2020-01-22 | ADD PROJECT TO STIP; PARENT NO. 99-911.09; NEW | HSIP | 9010422 | VARIOUS | 11-976 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALLATION OF PAVEMENT MARKERS ON VARIOUS ROUTES IN DISTRICT 11. (HSIP)(2018BOP) | C |  | SAF | 2020 | 90000 | 90000 |  |  | 0 |  |  | OBLIGATED | 90000 |  | 90000 | 2020 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.029 | 2019-02-21 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 9010371 | VARIOUS | 12-967 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALLATION OF PAVEMENT MARKERS ON VARIOUS ROUTES IN DISTRICT 12. (2018BOP) | C |  | SAF | 2019 | 420000 | 420000 |  |  | 0 |  |  | OBLIGATED |  | 420000 | 420000 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.145 | 2019-11-13 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 9010402 | VARIOUS | 12-968 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALLATION OF STRIPING ON VARIOUS ROUTES IN DISTRICT 12. (2018BOP) | C |  | SAF | 2020 | 1110000 | 1110000 |  |  | 0 |  |  | OBLIGATED | 1109350 |  | 1109350 | 2020 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.155 | 2020-01-22 | ADD PROJECT TO STIP; PARENT NO. 99-911.09; NEW | HSIP | 9010423 | VARIOUS | 12-969 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALLATION OF PAVEMENT MARKERS ON VARIOUS ROUTES IN DISTRICT 12. (HSIP)(2018BOP) | C |  | SAF | 2020 | 205000 | 205000 |  |  | 0 |  |  | OBLIGATED | 205000 |  | 205000 | 2020 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.029 | 2019-02-21 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 9010363 | VARIOUS | 99-923 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALLATION OF PAVEMENT MARKERS ON VARIOUS ROUTES IN DISTRICT 1 & 2. (2018BOP) | C |  | SAF | 2019 | 375000 | 375000 |  |  | 0 |  |  | OBLIGATED |  | 375000 | 375000 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.029 | 2019-02-21 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 9010368 | VARIOUS | 99-924 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALLATION OF PAVEMENT MARKERS ON VARIOUS ROUTES IN DISTRICT 7, 8 &10. (2018BOP) | C |  | SAF | 2019 | 710000 | 710000 |  |  | 0 |  |  | OBLIGATED |  | 710000 | 710000 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.032 | 2019-03-11 | ADD PROJECT TO STIP; PARENT NO. 99-224.13; FUNDING FOR THE SOFTWARE SYSTEMS FOR THE COLLECTION OF MANDATED FEDERAL HIGHWAY ADMINISTRATION HIGHWAY PERFORMANCE MONITORING SYSTEM (HPMS). |  |  | VARIOUS | N/A | [6 empty] | THIS AUTHORIZATION PROVIDES FEDERAL FUNDING TO PURCHASE THREE (3) MANDLI COMMUNICATIONS AND ASSOCIATED SOFTWARE SYSTEMS. | N |  | STP | 2019 | 2173635 | 2173635 | 2173635 |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.216 | 2020-08-17 | ADD C PHASE TO STIP;NEW |  |  | VARIOUS | N/A |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | INTERSECTION DATABASE UPDATE. | C |  | SAF | 2020 | 115000 | 115000 |  |  | 0 | [5 empty] | 0
|  |  |  | AMENDMENT | 2018.004 | 2019-11-08 | TIP REFERENCE FY 2019-2024; RESOLUTION DATED 9/30/2019; NEW |  |  | WARREN | [22 empty] | 0
STIP |  |  | GOOD | [6 empty] | WARREN | 3-110 | KY 185 | 5.623 | 6.29 | 11.913 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE KY-185 FROM NORTH OF THE JUNCTION WITH KY-263 NEAR RICHARDSVILLE TO THE BUTLER COUNTY LINE. (02CCR)(04CCR)(06CCR)(10CCR)(14CCR)(18CCR) | C |  | STP | 2020 | 5000000 | 5000000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.242 | 2020-10-06 | TIP FY 19-24, AMEND#01; REMOVE PROJECT FROM STIP; REPLACED BY 3-110.3 & 3-110.4; MOD |  |  | WARREN | 3-110 | KY 185 | 5.623 | 6.29 | 11.913 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE KY-185 FROM NORTH OF THE JUNCTION WITH KY-263 NEAR RICHARDSVILLE TO THE BUTLER COUNTY LINE. (02CCR)(04CCR)(06CCR)(10CCR)(14CCR)(18CCR) | C
STIP |  |  | GOOD | [6 empty] | WARREN | 3-110.01 | KY 185 | 5.623 | 6.29 | 11.913 | RELIABILITY | PREFINANCD CONVRSN(P) | IMPROVE KY-185 FROM NORTH OF THE JUNCTION WITH KY-263 NEAR RICHARDSVILLE TO THE BUTLER COUNTY LINE. (02CCR)(04CCR)(06CCR)(10CCR)(14CCR)(18CCR) | C |  | STP | 2021 | 5000000 | 4000000 |  |  | 1000000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.234 | 2020-09-15 | TIP FY 19-24, ADMIN MOD#6; ADD PROJECT TO STIP; NEW |  |  | WARREN | 3-110.3 | KY 185 | 1.81 | 6.54 | 8.35 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE KY 185 FROM 0.24 MILES SOUTH OF PRUITT ROAD TO 0.16 MILES SOUTH OF KY 1320. (2018BOP) | R |  | STP | 2020 | 1550000 | 1550000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.234 | 2020-09-15 | TIP FY 19-24, ADMIN MOD#6; ADD PROJECT TO STIP; NEW |  |  | WARREN | 3-110.3 | KY 185 | 1.81 | 6.54 | 8.35 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE KY 185 FROM 0.24 MILES SOUTH OF PRUITT ROAD TO 0.16 MILES SOUTH OF KY 1320. (2018BOP) | U |  | STP | 2021 | 830000 | 830000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.234 | 2020-09-15 | TIP FY 19-24, ADMIN MOD#6; ADD PROJECT TO STIP; NEW |  |  | WARREN | 3-110.3 | KY 185 | 1.81 | 6.54 | 8.35 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE KY 185 FROM 0.24 MILES SOUTH OF PRUITT ROAD TO 0.16 MILES SOUTH OF KY 1320. (2018BOP) | C |  | STP | 2021 | 8530000 | 8530000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.242 | 2020-10-06 | TIP FY 19-24, AMEND#01; ADD U PHASE TO STIP; NEW |  |  | WARREN | 3-110.4 | KY 185 | 1 | 10.02 | 11.02 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE KY 185 FROM 0.22 MILES NORTH OF THE AUSTIN RAYMER ROAD TO 0.08 MILES SOUTH OF THE BRIDGE OVER IVY CREEK. (2018BOP) | U |  | STP | 2021 | 300000 | 300000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.242 | 2020-10-06 | TIP FY 19-24, AMEND#01; ADD C PHASE TO STIP; NEW |  |  | WARREN | 3-110.4 | KY 185 | 1 | 10.02 | 11.02 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE KY 185 FROM 0.22 MILES NORTH OF THE AUSTIN RAYMER ROAD TO 0.08 MILES SOUTH OF THE BRIDGE OVER IVY CREEK. (2018BOP) | C |  | STP | 2021 | 4665000 | 4665000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.242 | 2020-10-06 | TIP FY 19-24, AMEND#01; ADD C PHASE TO STIP; NEW |  |  | WARREN | 3-199 | US-31W | 2.6 | 4.1 | 6.7 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE US-31W FROM SOUTH OF KY-242 TO DILLARD ROAD.(12CCR) (2020CCR) | C |  | STP | 2021 | 11690000 | 11690000 |  |  | 0 | [5 empty] | 0
STIP | YES |  | GOOD | [6 empty] | WARREN | 3-199.99 | US 31W |  | 4.1 | 4.258 | SAFETY | BIKE/PED FACIL(O) | CONSTRUCT A PEDESTRIAN UNDERPASS UNDER US-31W CONNECTING BUCHANON PARK TRAIL TO CHANEY'S DAIRY BARN.(16CCN) | D |  | STP | 2022 | 50000 | 40000 |  |  | 10000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.242 | 2020-10-06 | TIP FY 19-24, AMEND#01; UPDATE FUND AMOUNT; MOD |  |  | WARREN | 3-199.99 | US 31W |  | 4.1 | 4.258 | SAFETY | BIKE/PED FACIL(O) | CONSTRUCT A PEDESTRIAN UNDERPASS UNDER US-31W CONNECTING BUCHANON PARK TRAIL TO CHANEY'S DAIRY BARN.(16CCN) | D |  | STP | 2022 | 10000 | 10000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.242 | 2020-10-06 | TIP FY 19-24, AMEND#01; ADD C PHASE TO STIP; NEW |  |  | WARREN | 3-199.99 | US 31W |  | 4.1 | 4.258 | SAFETY | BIKE/PED FACIL(O) | CONSTRUCT A PEDESTRIAN UNDERPASS UNDER US-31W CONNECTING BUCHANON PARK TRAIL TO CHANEY'S DAIRY BARN.(16CCN) | C |  | STP | 2024 | 440000 | 440000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.078 | 2019-06-10 | ADD PROJECT TO STIP; PARENT NO. 99-66.14; GROUPED PROJECT IN BOWLING GREEN-WARREN COUNTY MPO TIP FY 16-20, PG 11, TABLE 3; NEW | AID | 6000154 | WARREN | 3-325 | US 231 US 231X |  | 6.6 0 | 10.5 2.1 | RELIABILITY | SIGNAL SYS IMPROVE(P) | DEPLOYMENT OF DEDICATED SHORT RANGE COMMUNICATION (DSRC) DEVICES AND AUTOMATED TRAFFIC SIGNAL PERFORMANCE MEASURES (ATSPM) ON US 231 (MP 6.6-10.5) AND US 231X (MP 0.0-2.1) IN WARREN COUNTY, KY. | N |  | AID | 2019 | 625000 | 500000 |  |  | 125000 |  |  | OBLIGATED | 500000 |  | 500000 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.133 | 2019-09-30 | TIP FY 16-20, ADMIN MOD#2020.03; UPDATE MILEPOINTS ON PROJECT; MOD | AID | 6000154 | WARREN | 3-325 | US 231 US 231X |  | 10.5 0 | 13.1 2.1 | RELIABILITY | SIGNAL SYS IMPROVE(P) | DEPLOYMENT OF DEDICATED SHORT RANGE COMMUNICATION (DSRC) DEVICES AND AUTOMATED TRAFFIC SIGNAL PERFORMANCE MEASURES (ATSPM) ON US 231 (MP 10.5-13.1) AND US 231X (MP 0.0-2.1) IN WARREN COUNTY, KY. | N |  | AID | 2019 | 625000 | 500000 |  |  | 125000 | [5 empty] | 0
STIP |  | YES | Listed in Future Years of TIP (project breakout); Not listed in actual Federally Funded Projects table |  |  |  |  | NHPP | 0031020 | WARREN | 3-2042.11 | WN 9007 | 70.185 | 2.473 | 20.246 | ECONOMIC DEVELOPMENT | SIGNING(P) | I-65 SPUR CORRIDOR SIGNING; EXISTING NATCHER PARKWAY FROM I-65 INTERCHANGE (EXIT 2) IN WARREN CO. EXTENDING NORTH TO THE US 60 INTERCHANGE IN DAVIESS CO. TO MEET INTERSTATE STANDARDS. (2016BOP) | C |  | NH | 2019 | 2150000 | 2150000 |  |  | 0 |  |  | OBLIGATED | 1907410 |  | 1907410 | 2019 | 2ND QUARTER
STIP |  |  | GOOD | [6 empty] | WARREN | 3-2042.2 | WN 9007 |  | 9.4 | 9.6 | RELIABILITY | I-CHANGE RECONST(O) | I-65 SPUR CORRIDOR: IMPROVE THE NATCHER PARKWAY/US-231 INTERCHANGE (EXIT 9) ON THE WEST SIDE OF BOWLING GREEN. (SEE ITEM NO. 3-202 FOR DESIGN) (2016BOP) | C |  | NH | 2021 | 8200000 | 6560000 |  |  | 1640000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.2 | 2020-06-19 | TIP FY 19-24, ADMIN MOD#2; INCREASE FUND AMOUNT AND UPDATE FISCAL YEAR; MOD |  |  | WARREN | 3-2042.2 | WN 9007 |  |  |  | RELIABILITY | I-CHANGE RECONST(O) | I-65 SPUR CORRIDOR: IMPROVE THE NATCHER PARKWAY/US-231 INTERCHANGE (EXIT 9) ON THE WEST SIDE OF BOWLING GREEN. (SEE ITEM NO. 3-202 FOR DESIGN) (2016BOP) | C |  | NH | 2020 | 10005000 | 10005000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.242 | 2020-10-06 | TIP FY 19-24, AMEND#01; UPDATE FISCAL YEAR AND FUND AMOUNT; MOD |  |  | WARREN | 3-2042.2 | WN 9007 |  |  |  | RELIABILITY | I-CHANGE RECONST(O) | I-65 SPUR CORRIDOR: IMPROVE THE NATCHER PARKWAY/US-231 INTERCHANGE (EXIT 9) ON THE WEST SIDE OF BOWLING GREEN. (SEE ITEM NO. 3-202 FOR DESIGN) (2016BOP) | C |  | NH | 2021 | 8400000 | 8400000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.242 | 2020-10-06 | TIP FY 19-24, AMEND#01; ADD PROJECT TO STIP; NEW |  |  | WARREN | 3-4307 | KY 234 | 0.11 | 1.61 | 1.72 | SAFETY | SAF-GUARDRAIL(P) | INSTALL GUARDRAIL ON KY-234 IN WARREN COUNTY | C |  | STP | 2022 | 25000 | 25000 |  |  | 0 | [5 empty] | 0
STIP |  |  | GOOD | [6 empty] | WARREN | 3-8702 | US 231 | 0.998 | 9.455 | 10.453 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE US-231 FROM PASCOE BLVD. TO NORTH OF CAVE MILL ROAD. (12CCN) | U |  | NH | 2019 | 2500000 | 2500000 |  |  | 0 | [5 empty] | 0
STIP |  |  | GOOD | [6 empty] | WARREN | 3-8702 | US 231 | 0.998 | 9.455 | 10.453 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE US-231 FROM PASCOE BLVD. TO NORTH OF CAVE MILL ROAD. (12CCN) | C |  | NH | 2019 | 2600000 | 2600000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.242 | 2020-10-06 | TIP FY 19-24, AMEND#01; UPDATE FISCAL YEAR AND FUND AMOUNT; MOD |  |  | WARREN | 3-8702 | US 231 | 0.998 | 9.455 | 10.453 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE US-231 FROM PASCOE BLVD. TO NORTH OF CAVE MILL ROAD. (12CCN) | C |  | NH | 2022 | 3400000 | 3400000 |  |  | 0 | [5 empty] | 0
STIP |  | YES | Listed in Future Years of TIP (project breakout); Not listed in actual Federally Funded Projects table | [6 empty] | WARREN | 3-8702.01 | US 231 | 0.998 | 9.455 | 10.453 | RELIABILITY | PREFINANCD CONVRSN(O) | IMPROVE US-231 FROM PASCOE BLVD. TO NORTH OF CAVE MILL ROAD. (12CCN) | C |  | NH | 2021 | 870000 | 696000 |  |  | 174000 | [5 empty] | 0
[10 empty] | WARREN | 3-8707 | WN 9007 | 0.6 | 3.4 | 4 | RELIABILITY | NEW INTERCHANGE(O) | CONSTRUCT A NEW INTERCHANGE ON THE NATCHER PARKWAY AT ELROD ROAD IN BOWLING GREEN (MP 3.4 TO MP 4.0).(12CCN) | D |  | NH | 2019 | 800000 | 80000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.242 | 2020-10-06 | TIP FY 19-24, AMEND#01; ADD R PHASE TO STIP; NEW |  |  | WARREN | 3-8707 | WN 9007 | 0.6 | 3.4 | 4 | RELIABILITY | NEW INTERCHANGE(O) | CONSTRUCT A NEW INTERCHANGE ON THE NATCHER PARKWAY AT ELROD ROAD IN BOWLING GREEN (MP 3.4 TO MP 4.0).(12CCN) | R |  | NH | 2021 | 8810000 | 8810000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.242 | 2020-10-06 | TIP FY 19-24, AMEND#01; ADD U PHASE TO STIP; NEW |  |  | WARREN | 3-8707 | WN 9007 | 0.6 | 3.4 | 4 | RELIABILITY | NEW INTERCHANGE(O) | CONSTRUCT A NEW INTERCHANGE ON THE NATCHER PARKWAY AT ELROD ROAD IN BOWLING GREEN (MP 3.4 TO MP 4.0).(12CCN) | U |  | NH | 2021 | 8290000 | 8290000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.242 | 2020-10-06 | TIP FY 19-24, AMEND#01; ADD C PHASE TO STIP; NEW |  |  | WARREN | 3-8707 | WN 9007 | 0.6 | 3.4 | 4 | RELIABILITY | NEW INTERCHANGE(O) | CONSTRUCT A NEW INTERCHANGE ON THE NATCHER PARKWAY AT ELROD ROAD IN BOWLING GREEN (MP 3.4 TO MP 4.0).(12CCN) | C |  | NH | 2022 | 25290000 | 25290000 | [8 empty] | 0
[10 empty] | WARREN | 3-8857 | US 31W | 1.26 | 10.561 | 11.817 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE US-31W FROM CAMPBELL LANE (US-231) TO UNIVERSITY BOULEVARD (US-231X). (14CCN)(16CCR)(18CCR) (2020CCR) | R |  | STP | 2019 | 1750000 | 1750000 | [8 empty] | 0
[10 empty] | WARREN | 3-8857 | US 31W | 1.26 | 10.561 | 11.817 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE US-31W FROM CAMPBELL LANE (US-231) TO UNIVERSITY BOULEVARD (US-231X). (14CCN)(16CCR)(18CCR) (2020CCR) | U |  | STP | 2019 | 5800000 | 5800000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.242 | 2020-10-06 | TIP FY 19-24, AMEND#01; ADD C PHASE TO STIP; NEW |  |  | WARREN | 3-8857 | US 31W | 1.26 | 10.561 | 11.817 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE US-31W FROM CAMPBELL LANE (US-231) TO UNIVERSITY BOULEVARD (US-231X). (14CCN)(16CCR)(18CCR) (2020CCR) | C |  | STP | 2022 | 4550000 | 4550000 | [8 empty] | 0
STIP |  | YES | .01 breakout not shown in TIP; amount is included in 3-8702 C in TIP | [6 empty] | WARREN | 3-8904.1 | US 31W | 0.971 | 13.698 | 14.669 | RELIABILITY | MINOR WIDENING(O) | WIDEN US 31W FROM PARK AVENUE TO FAIRVIEW AVENUE MP 13.7-14.25. (18CCN) | D |  | STP | 2019 | 500000 | 500000 |  |  | 0 | [5 empty] | 0
STIP |  | YES | 2016-2020 TIP lists U in 2018 and C in 2019 | [6 empty] | WARREN | 3-8904.1 | US 31W | 0.971 | 13.698 | 14.669 | RELIABILITY | MINOR WIDENING(O) | WIDEN US 31W FROM PARK AVENUE TO FAIRVIEW AVENUE MP 13.7-14.25. (18CCN) | R |  | STP | 2020 | 1500000 | 1500000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.242 | 2020-10-06 | TIP FY 19-24, AMEND#01; UPDATE FISCAL YEAR; MOD |  |  | WARREN | 3-8904.1 | US 31W | 0.971 | 13.698 | 14.669 | RELIABILITY | MINOR WIDENING(O) | WIDEN US 31W FROM PARK AVENUE TO FAIRVIEW AVENUE MP 13.7-14.25. (18CCN) | R |  | STP | 2022 | 1500000 | 1500000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.27 | 2021-01-12 | TIP FY 19-24, ADMIN MOD#8; UPDATE FISCAL YEAR & FUND AMOUNT; MOD |  |  | WARREN | 3-8904.1 | US 31W | 0.971 | 13.698 | 14.669 | RELIABILITY | MINOR WIDENING(O) | WIDEN US 31W FROM PARK AVENUE TO FAIRVIEW AVENUE MP 13.7-14.25. (18CCN) | R |  | STP | 2021 | 4710000 | 4710000 | [8 empty] | 0
STIP |  | YES | TIP has C amount = $3,470,000 (see note above for 3-8702.01) | [6 empty] | WARREN | 3-8904.1 | US 31W | 0.971 | 13.698 | 14.669 | RELIABILITY | MINOR WIDENING(O) | WIDEN US 31W FROM PARK AVENUE TO FAIRVIEW AVENUE MP 13.7-14.25. (18CCN) | U |  | STP | 2020 | 1750000 | 1750000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.242 | 2020-10-06 | TIP FY 19-24, AMEND#01; UPDATE FISCAL YEAR; MOD |  |  | WARREN | 3-8904.1 | US 31W | 0.971 | 13.698 | 14.669 | RELIABILITY | MINOR WIDENING(O) | WIDEN US 31W FROM PARK AVENUE TO FAIRVIEW AVENUE MP 13.7-14.25. (18CCN) | U |  | STP | 2024 | 1750000 | 1750000 | [8 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.27 | 2021-01-12 | TIP FY 19-24, ADMIN MOD#8; UPDATE FISCAL YEAR & FUND AMOUNT; MOD |  |  | WARREN | 3-8904.1 | US 31W | 0.971 | 13.698 | 14.669 | RELIABILITY | MINOR WIDENING(O) | WIDEN US 31W FROM PARK AVENUE TO FAIRVIEW AVENUE MP 13.7-14.25. (18CCN) | U |  | STP | 2021 | 3840000 | 3840000 | [8 empty] | 0
STIP | YES | YES | Phase outside years of current TIP; phase shown in project breakout table | [6 empty] | WARREN | 3-8904.1 | US 31W | 0.971 | 13.698 | 14.669 | RELIABILITY | MINOR WIDENING(O) | WIDEN US 31W FROM PARK AVENUE TO FAIRVIEW AVENUE MP 13.7-14.25. (18CCN) | C |  | STP | 2021 | 4500000 | 3600000 |  |  | 900000 | [5 empty] | 0
STIP |  |  | GOOD | [6 empty] | WARREN | 3-8905 | US 31W | 1.586 | 20.904 | 22.49 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE MOBILITY AND REDUCE CONGESTION ON US-31W FROM US-68 TO MIZPAH. (16CCN) | D |  | STP | 2020 | 800000 | 800000 |  |  | 0 | [5 empty] | 0
STIP |  |  | GOOD | [6 empty] | WARREN | 3-8905 | US 31W | 1.586 | 20.904 | 22.49 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE MOBILITY AND REDUCE CONGESTION ON US-31W FROM US-68 TO MIZPAH. (16CCN) | R |  | STP | 2020 | 900000 | 900000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.242 | 2020-10-06 | TIP FY 19-24, AMEND#01; UPDATE FISCAL YEAR; MOD |  |  | WARREN | 3-8905 | US 31W | 1.586 | 20.904 | 22.49 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE MOBILITY AND REDUCE CONGESTION ON US-31W FROM US-68 TO MIZPAH. (16CCN) | R |  | STP | 2021 | 900000 | 900000 |  |  | 0 | [5 empty] | 0
STIP |  |  | GOOD | [6 empty] | WARREN | 3-8905 |  | 1.586 | 20.904 | 22.49 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE MOBILITY AND REDUCE CONGESTION ON US-31W FROM US-68 TO MIZPAH. (16CCN) | U |  | STP | 2020 | 400000 | 400000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.242 | 2020-10-06 | TIP FY 19-24, AMEND#01; UPDATE FISCAL YEAR AND FUND AMOUNT; MOD |  |  | WARREN | 3-8905 | US 31W | 1.586 | 20.904 | 22.49 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE MOBILITY AND REDUCE CONGESTION ON US-31W FROM US-68 TO MIZPAH. (16CCN) | U |  | STP | 2021 | 950000 | 950000 |  |  | 0 | [5 empty] | 0
STIP | YES |  | GOOD | [6 empty] | WARREN | 3-8905 | US 31W | 1.586 | 20.904 | 22.49 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE MOBILITY AND REDUCE CONGESTION ON US-31W FROM US-68 TO MIZPAH. (16CCN) | C |  | STP | 2022 | 2800000 | 2240000 |  |  | 560000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.242 | 2020-10-06 | TIP FY 19-24, AMEND#01; UPDATE FISCAL YEAR AND FUND AMOUNT; MOD |  |  | WARREN | 3-8905 | US 31W | 1.586 | 20.904 | 22.49 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE MOBILITY AND REDUCE CONGESTION ON US-31W FROM US-68 TO MIZPAH. (16CCN) | C |  | STP | 2023 | 6000000 | 6000000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.146 | 2019-11-13 | TIP FY 19-24; ADMIN MOD#1; ADD U PHASE TO STIP; NEW | HSIP | 5084025 | WARREN | 3-9012 | US 68 | 6.4 | 20.889 | 27.284 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON US 68 BEGINNING AT MP 20.889 AND ENDING AT MP 27.284 IN WARREN COUNTY. (2016BOP) | U |  | SAF | 2020 | 140000 | 140000 |  |  | 0 |  |  | OBLIGATED | 195000 |  | 195000 | 2020 | 1ST QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.146 | 2019-11-13 | TIP FY 19-24; ADMIN MOD#1; ADD C PHASE TO STIP; NEW | HSIP | 5084025 | WARREN | 3-9012 | US 68 | 6.4 | 20.889 | 27.284 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON US 68 BEGINNING AT MP 20.889 AND ENDING AT MP 27.284 IN WARREN COUNTY. (2016BOP) | C |  | SAF | 2020 | 1000000 | 1000000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.029 | 2019-02-21 | ADD PROJECT TO STIP; PARENT NO. 3-9013.00; BOWLING GREEN/WARREN CO MPO TIP 16-20, GROUP PROJECTS, TABLE 3, PG 17; NEW | HSIP | 9010374 | WARREN | 3-9013.4 | US 68 |  | 13.768 | 13.868 | SAFETY | SAFETY-HAZARD ELIM(P) | UPDATE THE SIGNAL TO INCLUDE REFLECTIVE BACKPLATES AT THE INTERSECTION OF US 68 & OLD BARREN RIVER ROAD. (2018BOP) | C |  | SAF | 2019 | 21000 | 21000 |  |  | 0 |  |  | OBLIGATED |  | 21729 | 21729 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.029 | 2019-02-21 | ADD PROJECT TO STIP; PARENT NO. 3-9013.00; BOWLING GREEN/WARREN CO MPO TIP 16-20, GROUP PROJECTS, TABLE 3, PG 17; NEW | HSIP | 9010376 | WARREN | 3-9013.6 | US 31W KY 743 |  | 23.253 0 | 23.821 .25 | SAFETY | SAFETY-HAZARD ELIM(P) | UPDATE THE SIGNING AT THE INTERSECTION OF US 31W & KY 743. (2018BOP) | C |  | SAF | 2019 | 9000 | 9000 |  |  | 0 |  |  | OBLIGATED |  | 8800 | 8800 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.22 | 2020-08-19 | TIP FY 19-24, ADMIN MOD#5; ADD PROJECT TO STIP; NEW |  |  | WARREN | 3-9015 | KY 234 |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM SAFETY IMPROVEMENTS ON KY 234 (CEMETARY RD) FROM THE WARREN/ALLEN COUNTY LINE TO CR 1175/CR 1155 IN WARREN COUNTY. WORK INCLUDES GUARD RAIL REPLACEMENT, ROAD RESURFACING, DRAINAGE AND SHOULDERING IMPROVEMENTS, SIGNAGE, TREE TRIMMING AND ENBANKMENT STABLIZATION. | C |  | SAF | 2020 | 2672000 | 2672000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.015 | 2019-01-25 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; BOWLING GREEN/WARREN CO MPO TIP 16-20, GROUP PROJECTS, TABLE 3, PG 17; NEW | HSIP | 9010348 | WARREN | 3-9018 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | PRELIMINARY DESIGN AND STUDY TO DETERMINE LOW COST IMPROVEMENTS AT INTERSECTIONS BETWEEN MILEPOINTS 10.5 TO 11.5 ALONG US 231 IN WARREN CO. (2018BOP) | D |  | SAF | 2019 | 200000 | 200000 |  |  | 0 |  |  | OBLIGATED |  | 200000 | 200000 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.066 | 2019-05-09 | TIP FY 16-20; ADMIN MOD#2019.04; ADD PROJECT TO STIP; NEW | HSIP | 2311018 | WARREN | 3-9019 | US 231 |  | 3 | 6.6 | SAFETY | SAFETY-HAZARD ELIM(P) | INTERSECTION AND CORRIDOR IMPROVEMENTS TO REDUCE CONFLICT POINT AND ENHANCE SAFETY ALONG US 231 FROM MP 3.0 TO MP 6.6. (2018BOP) | D |  | SAF | 2020 | 400000 | 400000 |  |  | 0 |  |  | OBLIGATED |  | 400000 | 400000 | 2019 | 3RD QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.255 | 2020-11-06 | TIP FY 19-24, ADMIN MOD#7; ADD C PHASE TO STIP; NEW |  |  | WARREN | 3-9019 | US 231 |  | 3 | 6.6 | SAFETY | SAFETY-HAZARD ELIM(P) | INTERSECTION AND CORRIDOR IMPROVEMENTS TO REDUCE CONFLICT POINT AND ENHANCE SAFETY ALONG US 231 FROM MP 3.0 TO MP 6.6. (2018BOP) | C |  | SAF | 2021 | 3900000 | 3900000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.066 | 2019-05-09 | TIP FY 16-20; ADMIN MOD#2019.04; ADD D PHASE TO STIP; NEW | HSIP | 0801113 | WARREN | 3-9020 | US 68 |  | 7.456 | 7.656 | SAFETY | SAFETY-HAZARD ELIM(P) | REMOVE RAISED MEDIAN AND CONSTRUCT A LEFT TURN LANE AT OLD TRAM RD AND US 68 (RUSSELLVILLE RD).(2018BOP) | D |  | SAF | 2020 | 20000 | 20000 |  |  | 0 |  |  | OBLIGATED |  | 20000 | 20000 | 2019 | 3RD QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.066 | 2019-05-09 | TIP FY 16-20; ADMIN MOD#2019.04; ADD C PHASE TO STIP; NEW | HSIP | 0801113 | WARREN | 3-9020 | US 68 |  | 7.456 | 7.656 | SAFETY | SAFETY-HAZARD ELIM(P) | REMOVE RAISED MEDIAN AND CONSTRUCT A LEFT TURN LANE AT OLD TRAM RD AND US 68 (RUSSELLVILLE RD).(2018BOP) | C |  | SAF | 2020 | 80000 | 80000 |  |  | 0 |  |  | OBLIGATED |  | 100000 | 100000 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.127 | 2019-09-10 | TIP FY 16-20; ADMIN MOD#2020.02; ADD PROJECT TO STIP; NEW | HSIP | 7415015 | WARREN | 3-9022 | US 231X |  | 1.119 | 1.839 | SAFETY | SAFETY-HAZARD ELIM(P) | OVERLAY AND RESTRIPE US 231X BETWEEN WILKINSON TRACE AND COVINGTON ST TO CONVERT FROM A 4 LANE SECTION TO A 5 LANE SECTION. (2018BOP) | C |  | SAF | 2019 | 90000 | 90000 |  |  | 0 |  |  | OBLIGATED | 114353 |  | 114353 | 2020 | 1ST QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.175 | 2020-04-09 | BOWLING GREEN/WARREN COUNTY MPO AREA TIP FY 19-24, GROUP PROJECTS, TABLE 1, PAGE 8-9; ADD D PHASE TO STIP; NEW |  |  | WARREN | 3-9024 | KY 185 |  | 8.25 | 10.05 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 185 FROM MP 8.250 TO MP 10.050 IN WARREN COUNTY, KY. (2018BOP) | D |  | SAF | 2020 | 200000 | 200000 |  |  | 0 | [5 empty] | 0
STIP |  |  | GOOD | [6 empty] | WARREN | 3-10014 | KY 2632 |  | 4.96 | 4.966 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF HAMMET HILL ROAD BRIDGE OVER SALT LICK CREEK. (114B00071N) | D |  | BR/STP | 2019 | 157500 | 97650 |  |  | 59850 | [5 empty] | 0
STIP |  |  | GOOD | [6 empty] | WARREN | 3-10014 | KY 2632 |  | 4.96 | 4.966 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF HAMMET HILL ROAD BRIDGE OVER SALT LICK CREEK. (114B00071N) | C |  | BR/STP | 2020 | 350000 | 217000 |  |  | 133000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.021 | 2019-02-04 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; WARREN COUNTY TIP MOD 2019.02 | STPBRZ | 9030020 | WARREN | 3-10014 | KY 2632 |  | 4.96 | 4.966 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF HAMMET HILL ROAD BRIDGE OVER SALT LICK CREEK. (114B00071N) | C |  | STP | 2019 | 457000 | 457000 |  |  | 0 |  |  | OBLIGATED |  | 387765 | 387765 | 2019 | 2ND QUARTER
STIP |  |  | GOOD | [6 empty] | WARREN | 3-10015 | KY 1435 | 0.36 | 9.445 | 9.481 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 1435 BRIDGE OVER GASPER RIVER. (114B00074N) | D |  | BR/STP | 2019 | 280000 | 173600 |  |  | 106400 | [5 empty] | 0
STIP |  | YES | 3-110.01 is not broken out in TIP: reference 3-110.01 + 3-110 for total amount listed in TIP ($10,000,000) | [6 empty] | WARREN | 3-10015 | KY 1435 | 0.36 | 9.445 | 9.481 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 1435 BRIDGE OVER GASPER RIVER. (114B00074N) | C |  | BR/STP | 2020 | 1172500 | 726950 |  |  | 445550 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.264 | 2020-10-06 | TIP FY 19-24, AMEND#01; UPDATE FISCAL YEAR AND FUND AMOUNT; MOD |  |  | WARREN | 3-10015 | KY 1435 | 0.36 | 9.445 | 9.481 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 1435 BRIDGE OVER GASPER RIVER. (114B00074N) | C |  | BR/STP | 2021 | 1250000 | 1250000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.214 | 2020-07-24 | TIP FY 19-24, ADMIN MOD#4; ADD D PHASE TO STIP; NEW |  |  | WARREN | 3-20016 | I 65 | 11.29 | 19.6 | 25.2 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-065 BOTH DIRECTIONS. | D |  | NH | 2020 | 1350000 | 1350000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.264 | 2020-10-06 | TIP FY 19-24, AMEND#01; UPDATE FISCAL YEAR; MOD |  |  | WARREN | 3-20016 | I 65 | 11.29 | 19.6 | 25.2 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-065 BOTH DIRECTIONS. | D |  | NH | 2021 | 1350000 | 1350000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.214 | 2020-07-24 | TIP FY 19-24, ADMIN MOD#4; ADD C PHASE TO STIP; NEW |  |  | WARREN | 3-20016 | I 65 | 11.29 | 19.6 | 25.2 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-065 BOTH DIRECTIONS. | C |  | NH | 2023 | 13500000 | 13500000 |  |  | 0 | [5 empty] | 0
STIP |  | YES | TIP Amendment 2018.02: C = $10,000,000 (see note above) | [6 empty] | WARREN | 3-20017 | I 65 |  | 35.616 | 42.89 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-065 BOTH DIRECTION(S) FROM MILEPOINT 35.616 TO MILEPOINT 42.89 | D |  | PM/NH | 2019 | 870000 | 696000 |  |  | 174000 | [5 empty] | 0
STIP |  |  | GOOD | [6 empty] | WARREN | 3-20017 | I 65 |  | 35.616 | 42.89 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-065 BOTH DIRECTION(S) FROM MILEPOINT 35.616 TO MILEPOINT 42.89 | C |  | PM/NH | 2019 | 8700000 | 6960000 |  |  | 1740000 | [5 empty] | 0
STIP |  |  | GOOD | [6 empty] | WARREN | 3-20018 | WN 9007 |  | 0 | 2.473 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF WILLIAM H. NATCHER PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 0 TO MILEPOINT 2.473 | D |  | PM/STP | 2019 | 200000 | 160000 |  |  | 40000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.264 | 2020-10-06 | TIP FY 19-24, AMEND#01; UPDATE FISCAL YEAR AND FUND TYPE; MOD |  |  | WARREN | 3-20018 | WN 9007 |  | 0 | 2.473 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF WILLIAM H. NATCHER PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 0 TO MILEPOINT 2.473 | D |  | NH | 2021 | 200000 | 160000 |  |  | 40000 | [5 empty] | 0
STIP |  |  | GOOD | [6 empty] | WARREN | 3-20018 | WN 9007 |  | 0 | 2.473 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF WILLIAM H. NATCHER PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 0 TO MILEPOINT 2.473 | C |  | PM/STP | 2020 | 2000000 | 1600000 |  |  | 400000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.264 | 2020-10-06 | TIP FY 19-24, AMEND#01; UPDATE FISCAL YEAR AND FUND TYPE; MOD |  |  | WARREN | 3-20018 | WN 9007 |  | 0 | 2.473 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF WILLIAM H. NATCHER PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 0 TO MILEPOINT 2.473 | C |  | NH | 2021 | 2000000 | 1600000 |  |  | 400000 | [5 empty] | 0
STIP |  |  | GOOD |  |  |  |  | NHPPIM | 0165005 | WARREN | 3-20019 | WN 9007 |  | 9.2 | 20.246 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF WILLIAM H. NATCHER PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 9.2 TO MILEPOINT 20.246 | C |  | PM/NH | 2020 | 11083000 | 8866400 |  |  | 2216600 |  |  | OBLIGATED | 6211137 |  | 6211137 | 2019 | 3RD QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.264 | 2020-10-06 | TIP FY 19-24, AMEND#01; ADD C PHASE TO STIP; NEW |  |  | WARREN | 3-80151 | US 31E |  | 15.6 | 15.7 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | RECONSTRUCT THE INTERSECTION OF BARDSTOWN ROAD (US 31E) AND BAXTER AVENUE (KY 1703) FOR PEDESTRIAN SAFETY | C |  | STP | 2021 | 650000 | 650000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | WASHINGTON | 4-396 | US 150 | 12.178 | 0 | 6.557 | SAFETY | RECONSTRUCTION(O) | IMPROVE US-150 FROM SPRINGFIELD TO BARDSTOWN. | D |  | STP | 2020 | 3000000 | 3000000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | WASHINGTON | 4-396.2 | US 150 | 2.074 | 0.426 | 2.5 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE SAFETY, MOBILITY, AND GEOMETRICS ALONG US-150 FROM WEST OF OLD FREDERICKTOWN-BARDSTOWN ROAD (KY-1872) THROUGH GRUNDY HOME CURVE TO MAYFIELD LN (CR-1336). (2016BOP) | D |  | STP | 2021 | 500000 | 400000 |  |  | 100000 | [5 empty] | 0
STIP | [9 empty] | WASHINGTON | 4-396.2 | US 150 | 2.074 | 0.426 | 2.5 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE SAFETY, MOBILITY, AND GEOMETRICS ALONG US-150 FROM WEST OF OLD FREDERICKTOWN-BARDSTOWN ROAD (KY-1872) THROUGH GRUNDY HOME CURVE TO MAYFIELD LN (CR-1336). (2016BOP) | R |  | STP | 2022 | 500000 | 400000 |  |  | 100000 | [5 empty] | 0
STIP | [9 empty] | WASHINGTON | 4-396.2 | US 150 | 2.074 | 0.426 | 2.5 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE SAFETY, MOBILITY, AND GEOMETRICS ALONG US-150 FROM WEST OF OLD FREDERICKTOWN-BARDSTOWN ROAD (KY-1872) THROUGH GRUNDY HOME CURVE TO MAYFIELD LN (CR-1336). (2016BOP) | U |  | STP | 2022 | 750000 | 600000 |  |  | 150000 | [5 empty] | 0
STIP | [9 empty] | WASHINGTON | 4-1094 | KY 528 |  | 1.433 | 1.441 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON KY 528 (MP 1.437) OVER ROAD RUN BRANCH.(115B00043N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030226 | WASHINGTON | 4-1094 | KY 528 |  | 1.433 | 1.441 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON KY 528 (MP 1.437) OVER ROAD RUN BRANCH.(115B00043N) | C |  | BR/STP | 2020 | 1302000 | 807240 |  |  | 494760 |  |  | OBLIGATED |  | 548800 | 548800 | 2020 | 1ST QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.218 | 2020-08-28 | ADD C PHASE TO STIP; PARENT NO. 4-8916; NEW |  |  | WASHINGTON | 4-8916.20 | KY 55 US 150X |  |  |  | RELIABILITY | RECONSTRUCTION(O) | HEARTLAND PARKWAY: ADDRESS SAFETY AND MOBILITY ON KY 55 FROM THE MARION/WASHINGTON COUNTY LINE NORTH TO US-150X IN SPRINGFIELD. (CONSTRUCTION SEGMENT 2)(2018BOP). | C |  | NH | 2021 | 5500000 | 5500000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | WASHINGTON | 4-8957 | CR 1140 |  | 0.344 | 0.354 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON TEXAS-MACKVILLE ROAD (CR 1140) AT MP 0.349 OVER LONG LICK CREEK.(115C00039) (16CCN)(SD) | C |  | BR/STP | 2020 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.015 | 2019-01-25 | ADD PROJECT TO STIP; PARENT NO. 99-911.06; NEW | HSIP | 9010359 | WASHINGTON | 4-9006.2 | KY 555 |  | 1.18 | 1.66 | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALL REFLECTIVE BACKPLATES AND UPDATE THE STRIPING AT THE INTERSECTION OF KY 555 & US 150. (2018BOP) | C |  | SAF | 2019 | 37000 | 37000 |  |  | 0 |  |  | OBLIGATED | 37000 |  | 37000 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.015 | 2019-01-25 | ADD PROJECT TO STIP; PARENT NO. 99-911.06; NEW | HSIP | 9010360 | WASHINGTON | 4-9006.3 | KY 555 |  | 0.7 | 0.98 | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALL REFLECTIVE BACKPLATES, SUPPLEMENTAL SIGNAL HEADS, AND GREEN EXTENSION LOOP DETECTORS AT THE INTERSECTION OF KY 555 & KY 528. (2018BOP) | C |  | SAF | 2019 | 48000 | 48000 |  |  | 0 |  |  | OBLIGATED | 48000 |  | 48000 | 2019 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.175 | 2020-04-09 | ADD D PHASE TO STIP; PARENT NO. 99-911.09; NEW |  |  | WASHINGTON | 4-9014 | KY 55 |  | 5.585 | 9.862 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 55 FROM MP 5.585 TO MP 9.862 IN WASHINGTON COUNTY, KY. (2018BOP) | D |  | SAF | 2020 | 250000 | 250000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | WASHINGTON | 4-10008 | KY 55 |  | 8.669 | 8.679 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-55 BRIDGE OVER SEIBERT CREEK. (115B00026N) | D |  | BR/STP | 2019 | 87500 | 54250 |  |  | 33250 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030025 | WASHINGTON | 4-10008 | KY 55 |  | 8.669 | 8.679 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-55 BRIDGE OVER SEIBERT CREEK. (115B00026N) | C |  | BR/STP | 2020 | 511000 | 316820 |  |  | 194180 |  |  | OBLIGATED |  | 454288.4 | 454288.4 | 2019 | 2ND QUARTER
STIP | [9 empty] | WASHINGTON | 4-10015 | KY 1920 |  | 0.017 | 0.025 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 1920 BRIDGE OVER DEEP CREEK. (115B00061N) | D |  | BR/STP | 2019 | 87500 | 54250 |  |  | 33250 | [5 empty] | 0
STIP | [9 empty] | WASHINGTON | 4-10015 | KY 1920 |  | 0.017 | 0.025 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 1920 BRIDGE OVER DEEP CREEK. (115B00061N) | C |  | BR/STP | 2020 | 262500 | 162750 |  |  | 99750 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.218 | 2020-08-28 | ADD C PHASE TO STIP; PARENT NO. 99-2700.14; NEW |  |  | WASHINGTON | 4-20034 | KY 555 |  | 0 | 8.28 | ASSET MANAGEMENT | AM-PAVEMENT(PRI)(P) | PAVEMENT RESFURFACING ON KY 555 FROM MP 0.000 TO MP 8.280 IN WASHINGTON COUNTY. | C |  | STP | 2020 | 1463000 | 1463000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.269 | 2021-01-22 | ADD C PHASE TO STIP; PARENT NO. 8-109.00; NEW |  |  | WAYNE | 8-109.10 | KY 90 |  | 17.691 | 19.5 | SAFETY | SAFETY(P) | IMPROVE KY-90 FROM OLD MILL SPRINGS ROAD TO THE BRIDGE AT MP 19.5. (12CCR)(16CCR)(18CCR) | C |  | STP | 2021 | 8835000 | 8835000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | WAYNE | 8-1050 | CR 1136 | 0.1 | 0.175 | 0.275 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BRIDGE ON CR-1136 (MP 0.225) OVER LITTLE SOUTH FORK RIVER; 0.25 MI SE OF JCT CR-5137; 116C00007N | C |  | BR/STP | 2019 | 455000 | 282100 |  |  | 172900 | [5 empty] | 0
STIP | [9 empty] | WAYNE | 8-10005 | CR 1016 |  | 0.216 | 0.224 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF DODSON HOLLOW RD BRIDGE OVER MEADOW CREEK. (116C00028N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [9 empty] | WAYNE | 8-10005 | CR 1016 |  | 0.216 | 0.224 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF DODSON HOLLOW RD BRIDGE OVER MEADOW CREEK. (116C00028N) | C |  | BR/STP | 2020 | 466000 | 288920 |  |  | 177080 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.075 | 2019-05-28 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030125 | WAYNE | 8-10005 | CR 1016 |  | 0.216 | 0.224 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF DODSON HOLLOW RD BRIDGE OVER MEADOW CREEK. (116C00028N) | C |  | STP | 2020 | 560000 | 560000 |  |  | 0 |  |  | OBLIGATED |  | 594675 | 594675 | 2019 | 3RD QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.306 | 2021-06-16 | ADD D PHASE TO STIP; NEW |  |  | WAYNE | 8-80005 | KY 1275 |  | 4.479 | 4.7 | SAFETY | SAFETY (P) | IMPROVE CURVE ON KY 1275 AT KY 833/ROGERS GROVE ROAD AND RESURFACE FROM KY 1275 FROM BELL LANE TO KY 833/ROGERS GROVE ROAD(18CCN) (2020CCR) | D |  | SPP | 2021 | 60100 | 100 |  |  | 60000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.306 | 2021-06-16 | ADD D PHASE TO STIP; NEW |  |  | WAYNE | 8-80105 | KY 90 |  | 12.931 | 15.617 |  | CONGESTION MITIGTN(O) | REDUCE CONGESTION AND IMPROVES SAFETY, CAPACITY AND MOBILITY OF KY 90 BETWEEN KY 90X/KY 1275 AND KY 3106 (2020CCN) | D |  | SPP | 2021 | 1568100 | 100 |  |  | 1568000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.067 | 2019-05-13 | ADD PROJECT TO STIP; PARENT NO. 911.08; NEW | HSIP | 5046013 | WEBSTER | 2-921 | US 41 |  | 0 | 6.035 | SAFETY | SAFETY-HAZARD ELIM(P) | REPLACEMENT OF TARGETED GUARDRAIL END TREATMENTS ON US 41 FROM MP 0.000 TO MP 6.035 (2018BOP). | C |  | SAF | 2019 | 465000 | 465000 |  |  | 0 |  |  | OBLIGATED | 469000 |  | 469000 | 2019 | 3RD QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.067 | 2019-05-13 | ADD PROJECT TO STIP; PARENT NO. 911.08; NEW | HSIP | 5047019 | WEBSTER | 2-922 | US 41A |  | 0 | 19.657 | SAFETY | SAFETY-HAZARD ELIM(P) | REPLACEMENT OF TARGETED GUARDRAIL END TREATMENTS ON US 41A FROM MP 0.000 TO MP 19.657 (2018BOP). | C |  | SAF | 2019 | 150000 | 150000 |  |  | 0 |  |  | OBLIGATED | 167900 |  | 167900 | 2019 | 3RD QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.229 | 2020-09-14 | ADD C PHASE TO STIP; PARENT NO. 99-911.09; NEW |  |  | WEBSTER | 2-999 | US 41 |  | 6.035 | 12.226 | SAFETY | SAFETY-HAZARD ELIM(P) | REPLACEMENT OF TARGETED GUARDRAIL END TREATMENTS ALONG US 41 IN WEBSTER COUNTY, KY. (2018BOP) | C |  | SAF | 2020 | 385000 | 385000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | WEBSTER | 2-10018 | KY 1835 |  | 0.385 | 0.406 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-1835 BRIDGE OVER SUGAR CAMP CREEK. (117B00023N) | D |  | BR/STP | 2019 | 210000 | 130200 |  |  | 79800 | [5 empty] | 0
STIP | [7 empty] | STP | 9030007 | WEBSTER | 2-10018 | KY 1835 |  | 0.385 | 0.406 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-1835 BRIDGE OVER SUGAR CAMP CREEK. (117B00023N) | C |  | BR/STP | 2020 | 665000 | 412300 |  |  | 252700 |  |  | OBLIGATED | 433440 |  | 433440 | 2019 | 2ND QUARTER
STIP | [9 empty] | WEBSTER | 2-10019 | KY 132 |  | 12.304 | 12.314 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-132 BRIDGE OVER NALL DITCH. (117B00064N) | D |  | BR/STP | 2019 | 245000 | 151900 |  |  | 93100 | [5 empty] | 0
STIP | [7 empty] | STP | 9030008 | WEBSTER | 2-10019 | KY 132 |  | 12.304 | 12.314 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-132 BRIDGE OVER NALL DITCH. (117B00064N) | C |  | BR/STP | 2020 | 1102500 | 683550 |  |  | 418950 |  |  | OBLIGATED |  | 915400 | 915400 | 2019 | 2ND QUARTER
STIP | [9 empty] | WHITLEY | 11-14.8 | I 75 | 8.65 | 20.2 | 27.943 | RELIABILITY | MAJOR WIDENING(O) | TENN. STATE LINE-LEXINGTON; WIDEN I-75 TO 8 LANES FROM MP 20.2 IN WHITLEY COUNTY TO MP 28.85, US-25E NORTH OF CORBIN. (C-COST=$87,500,000)(18CCR) | R |  | NH | 2019 | 500000 | 500000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | WHITLEY | 11-14.8 | I 75 | 8.65 | 20.2 | 27.943 | RELIABILITY | MAJOR WIDENING(O) | TENN. STATE LINE-LEXINGTON; WIDEN I-75 TO 8 LANES FROM MP 20.2 IN WHITLEY COUNTY TO MP 28.85, US-25E NORTH OF CORBIN. (C-COST=$87,500,000)(18CCR) | U |  | NH | 2019 | 500000 | 500000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | WHITLEY | 11-14.8 | I 75 | 8.65 | 20.2 | 27.943 | RELIABILITY | MAJOR WIDENING(O) | TENN. STATE LINE-LEXINGTON; WIDEN I-75 TO 8 LANES FROM MP 20.2 IN WHITLEY COUNTY TO MP 28.85, US-25E NORTH OF CORBIN. (C-COST=$87,500,000)(18CCR) | C |  | NH | 2020 | 10000000 | 10000000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | WHITLEY | 11-14.81 | I 75 | 8.65 | 20.2 | 27.943 | RELIABILITY | PREFINANCD CONVRSN(O) | TENN. STATE LINE-LEXINGTON; WIDEN I-75 TO 8 LANES FROM MP 20.2 IN WHITLEY COUNTY TO MP 28.85, US-25E NORTH OF CORBIN. (18CCR) | C |  | NH | 2021 | 25000000 | 20000000 |  |  | 5000000 | [5 empty] | 0
STIP | [9 empty] | WHITLEY | 11-14.83 | I 75 |  | 20.2 | 27.943 | RELIABILITY | PREFINANCD CONVRSN(O) | TENN. STATE LINE-LEXINGTON; WIDEN I-75 TO 8 LANES FROM MP 20.2 IN WHITLEY COUNTY TO MP 28.85, US-25E NORTH OF CORBIN(ADDITIONAL CONSTRUCTION FUNDING FOR 11-14.80)(18CCN) | C |  | NH | 2022 | 25000000 | 20000000 |  |  | 5000000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.123 | 2019-09-06 | ADD D PHASE TO STIP; PARENT NO. 11-14.80; NEW | NHPPIM | 0752102 | WHITLEY LAUREL | 11-14.9 | I 75 |  | 27.5 27.943 | 27.943 29.14 | RELIABILITY | MAJOR WIDENING(O) | WIDENING OF I-75 AND REPLACEMENT OF BRIDGE OVER LYNN CREEK FROM MP 27.5 TO 29.1. (2018BOP)(DESIGN-BUILD) | D |  | NH | 2019 | 1000000 | 1000000 |  |  | 0 |  |  | OBLIGATED |  | 1000000 | 1000000 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.123 | 2019-09-06 | ADD C PHASE TO STIP; PARENT NO. 11-14.80; NEW |  |  | WHITLEY LAUREL | 11-14.9 | I 75 |  | 27.5 27.943 | 27.943 29.14 | RELIABILITY | MAJOR WIDENING(O) | WIDENING OF I-75 AND REPLACEMENT OF BRIDGE OVER LYNN CREEK FROM MP 27.5 TO 29.1. (2018BOP)(DESIGN-BUILD) | C |  | NH | 2020 | 40000000 | 40000000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.103 | 2019-07-29 | ADD PROJECT TO STIP; PARENT NO. 99-369.09; NEW | STPE | 0751089 | WHITLEY | 11-58 | I 75 |  | 1.4 | 2 | RELIABILITY | NEW REST AREA(P) | RECONSTRUCTION OF THE EXISTING WHITLEY COUNTY I-75 WELCOME CENTER BETWEEN NORTHBOUNDN MILE MARKER 1.4 AND MILE MARKER 2.0. (2018BOP) | C |  | TE | 2019 | 3760000 | 3760000 |  |  | 0 |  |  | OBLIGATED | 4465985 |  | 4465985 | 2019 | 4TH QUARTER
STIP | [7 empty] | STP | 5147023 | WHITLEY | 11-184.1 | KY 92 | 4.172 | 0 | 4.172 | RELIABILITY | RELOCATION(O) | RECONSTRUCT KY-92 FROM 500 FT WEST OF THE WHITLEY/MCCREARY COUNTY LINE TO 1200 FT EAST OF OLD JELLICO CREEK ROAD. (SECTION 1)(14CCR) | C |  | STP | 2019 | 10000000 | 10000000 |  |  | 0 |  |  | OBLIGATED | 9000000 | 15512140 | 24512140 | 2019 | 1ST QUARTER
STIP | [9 empty] | WHITLEY | 11-184.11 | KY 92 | 4.172 | 0 | 4.172 | RELIABILITY | PREFINANCD CONVRSN(O) | RECONSTRUCT KY-92 FROM 500 FT WEST OF THE WHITLEY/MCCREARY COUNTY LINE TO 1200 FT EAST OF OLD JELLICO CREEK ROAD. (SECTION 1) (ADDITIONAL FUNDING FOR 11-184.10) | C |  | STP | 2021 | 6000000 | 4800000 |  |  | 1200000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.276 | 2021-02-12 | ADD D PHASE TO STIP; NEW |  |  | WHITLEY | 11-186 | US 25W | 2.325 | 28.1 | 30.425 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE FREIGHT MOBILITY AND REDUCE CONGESTION ON US-25W FROM KY-727 TO KY-3041. (12CCR)(16CCR) | D |  | STP | 2021 | 500000 | 500000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | WHITLEY | 11-186 | US 25W | 2.325 | 28.1 | 30.425 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE FREIGHT MOBILITY AND REDUCE CONGESTION ON US-25W FROM KY-727 TO KY-3041. (12CCR)(16CCR) | R |  | NH | 2021 | 2770000 | 2216000 |  |  | 554000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.276 | 2021-02-12 | INCREASE FUNDS BASED ON NEW ESTIMATE; MOD |  |  | WHITLEY | 11-186 | US 25W | 2.325 | 28.1 | 30.425 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE FREIGHT MOBILITY AND REDUCE CONGESTION ON US-25W FROM KY-727 TO KY-3041. (12CCR)(16CCR) | R |  | STP | 2021 | 5000000 | 5000000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | WHITLEY | 11-186 | US 25W | 2.325 | 28.1 | 30.425 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE FREIGHT MOBILITY AND REDUCE CONGESTION ON US-25W FROM KY-727 TO KY-3041. (12CCR)(16CCR) | U |  | NH | 2021 | 4160000 | 3328000 |  |  | 832000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.276 | 2021-02-12 | INCREASE FUNDS BASED ON NEW ESTIMATE; MOD |  |  | WHITLEY | 11-186 | US 25W | 2.325 | 28.1 | 30.425 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE FREIGHT MOBILITY AND REDUCE CONGESTION ON US-25W FROM KY-727 TO KY-3041. (12CCR)(16CCR) | U |  | STP | 2021 | 5000000 | 5000000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | WHITLEY | 11-186 | US 25W | 2.325 | 28.1 | 30.425 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE FREIGHT MOBILITY AND REDUCE CONGESTION ON US-25W FROM KY-727 TO KY-3041. (12CCR)(16CCR) | C |  | NH | 2022 | 3330000 | 2664000 |  |  | 666000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.276 | 2021-02-12 | INCREASE FUNDS BASED ON NEW ESTIMATE; MOD |  |  | WHITLEY | 11-186 | US 25W | 2.325 | 28.1 | 30.425 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE FREIGHT MOBILITY AND REDUCE CONGESTION ON US-25W FROM KY-727 TO KY-3041. (12CCR)(16CCR) | C |  | BUILD | 2023 | 15050000 | 15050000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.043 | 2019-03-29 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 5154031 | WHITLEY | 11-966 | KY 26 |  | 10.16 | 10.66 | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALL GUARDRAIL ALON KY 26 FROM MP 10.160 TO MP 10.660. (2018BOP) | C |  | SAF | 2019 | 138545 | 138545 |  |  | 0 |  |  | OBLIGATED | 138545 |  | 138545 | 2019 | 3RD QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.043 | 2019-03-29 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 5154030 | WHITLEY | 11-967 | KY 26 |  | 1.97 | 2.15 | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALL GUARDRAIL ALONG KY 26 FROM MP 1.970 TO 2.150. (2018BOP) | C |  | SAF | 2019 | 26208 | 26208 |  |  | 0 |  |  | OBLIGATED |  | 26207 | 26207 | 2019 | 3RD QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.043 | 2019-03-29 | ADD PROJECT TO STIP; PARENT NO. 99-911.08; NEW | HSIP | 9010337 | WHITLEY | 11-968 | KY 3421 |  | 0.784 | 0.824 | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALL GUARDRAIL ALONG KY 3421 FROM MP 0.784 TO 0.824. (2018BOP) | C |  | SAF | 2019 | 20504 | 20504 |  |  | 0 |  |  | OBLIGATED |  | 21895 | 21895 | 2019 | 3RD QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.291 | 2021-04-23 | ADD C PHASET TO STIP; PARENT NO. 99-911.09; NEW |  |  | WHITLEY | 11-978 | KY 1259 |  | 0.652 | 0.782 | SAFETY | SAFETY-HAZARD ELIM(P) | GUARDRAIL INSTALLATION ON KY 1259 FROM MP 0.652 TO MP 0.782 IN WHITLEY COUNTY. (2018BOP) | C |  | SAF | 2021 | 38500 | 38500 | [8 empty] | 0
STIP | [9 empty] | WHITLEY | 11-1105 | I 75 |  | 27.85 | 27.943 | ASSET MANAGEMENT | AM-BRIDGE (P) | REHAB BRIDGE ON I-75 AT MILEPOINT 27.9 OVER LYNN CAMP CREEK (SR 34.1) (B00063R AND B00063L)(SD) | C |  | BR/NH | 2019 | 2800000 | 1736000 |  |  | 1064000 | [5 empty] | 0
STIP | [9 empty] | WHITLEY | 11-10032 | KY 904 |  | 8.153 | 8.157 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-904 BRIDGE OVER TYES FK OF BENNETTS BR. (118B00070N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [9 empty] | WHITLEY | 11-10032 | KY 904 |  | 8.153 | 8.157 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-904 BRIDGE OVER TYES FK OF BENNETTS BR. (118B00070N) | C |  | BR/STP | 2020 | 493500 | 305970 |  |  | 187530 | [5 empty] | 0
STIP | [9 empty] | WHITLEY | 11-10033 | KY 779 |  | 2.342 | 2.346 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-779 BRIDGE OVER BROWNS CREEK. (118B00079N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [9 empty] | WHITLEY | 11-10033 | KY 779 |  | 2.342 | 2.346 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-779 BRIDGE OVER BROWNS CREEK. (118B00079N) | C |  | BR/STP | 2020 | 448000 | 277760 |  |  | 170240 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.021 | 2019-02-04 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030050 | WHITLEY | 11-10033 | KY 779 |  | 2.342 | 2.346 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-779 BRIDGE OVER BROWNS CREEK. (118B00079N) | C |  | STP | 2019 | 600000 | 600000 |  |  | 0 |  |  | OBLIGATED |  | 432720 | 432720 | 2019 | 2ND QUARTER
STIP | [9 empty] | WHITLEY | 11-10034 | KY 204 |  | 10.146 | 10.156 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-204 BRIDGE OVER YOUNGS CREEK. (118B00084N) | D |  | BR/STP | 2019 | 262500 | 162750 |  |  | 99750 | [5 empty] | 0
STIP | [9 empty] | WHITLEY | 11-10034 | KY 204 |  | 10.146 | 10.156 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-204 BRIDGE OVER YOUNGS CREEK. (118B00084N) | C |  | BR/STP | 2020 | 910000 | 564200 |  |  | 345800 | [5 empty] | 0
STIP | [9 empty] | WHITLEY | 11-10035 | KY 2996 |  | 3.548 | 3.554 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-2996 BRIDGE OVER WOLF CREEK. (118B00101N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [9 empty] | WHITLEY | 11-10035 | KY 2996 |  | 3.548 | 3.554 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-2996 BRIDGE OVER WOLF CREEK. (118B00101N) | C |  | BR/STP | 2020 | 455000 | 282100 |  |  | 172900 | [5 empty] | 0
STIP | [9 empty] | WHITLEY | 11-10036 | CR 1275 |  | 0.479 | 0.487 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BETHEL ROAD BRIDGE OVER PATTERSON CREEK. (118C00029N) | D |  | BR/STP | 2019 | 140000 | 86800 |  |  | 53200 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030049 | WHITLEY | 11-10036 | CR 1275 |  | 0.479 | 0.487 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF BETHEL ROAD BRIDGE OVER PATTERSON CREEK. (118C00029N) | C |  | BR/STP | 2020 | 315000 | 195300 |  |  | 119700 |  |  | OBLIGATED |  | 412220 | 412220 | 2019 | 2ND QUARTER
STIP | [9 empty] | WHITLEY | 11-10037 | CR 1461 |  | 0.091 | 0.097 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF RIVER ROAD BRIDGE OVER SANDERS CREEK. (118C00039N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [7 empty] | STPBRZ | 9030259 | WHITLEY | 11-10037 | CR 1461 |  | 0.091 | 0.097 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF RIVER ROAD BRIDGE OVER SANDERS CREEK. (118C00039N) | C |  | BR/STP | 2020 | 406000 | 251720 |  |  | 154280 |  |  | OBLIGATED | 20000 | 348575 | 368575 | 2020 | 2ND QUARTER
STIP | [9 empty] | WHITLEY | 11-10044 | US 25W |  | 5.045 | 5.117 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF US 25W BRIDGE OVER CLEAR FORK RVR. (118B00041N) | D |  | BR/NH | 2019 | 245000 | 151900 |  |  | 93100 | [5 empty] | 0
STIP | [9 empty] | WHITLEY | 11-10044 | US 25W |  | 5.045 | 5.117 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF US 25W BRIDGE OVER CLEAR FORK RVR. (118B00041N) | C |  | BR/NH | 2020 | 1890000 | 1171800 |  |  | 718200 | [5 empty] | 0
STIP | [9 empty] | WHITLEY | 11-10045 | US 25W |  | 6.205 | 6.277 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF US 25W BRIDGE OVER CLEAR FORK RIVER. (118B00042N) | D |  | BR/NH | 2019 | 245000 | 151900 |  |  | 93100 | [5 empty] | 0
STIP | [9 empty] | WHITLEY | 11-10045 | US 25W |  | 6.205 | 6.277 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF US 25W BRIDGE OVER CLEAR FORK RIVER. (118B00042N) | C |  | BR/NH | 2020 | 1645000 | 1019900 |  |  | 625100 | [5 empty] | 0
STIP | [9 empty] | WHITLEY | 11-20015 | I 75 |  | 0 | 11.27 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-075 BOTH DIRECTION(S) FROM MILEPOINT 0 TO MILEPOINT 11.27 | D |  | PM/NH | 2022 | 900000 | 720000 |  |  | 180000 | [5 empty] | 0
STIP | [9 empty] | WHITLEY | 11-20015 | I 75 |  | 0 | 11.27 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-075 BOTH DIRECTION(S) FROM MILEPOINT 0 TO MILEPOINT 11.27 | C |  | PM/NH | 2022 | 9000000 | 7200000 |  |  | 1800000 | [5 empty] | 0
STIP | [9 empty] | WHITLEY | 11-20018 | I 75 |  | 20.2 | 24.645 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-075 CARDINAL DIRECTION(S) FROM MILEPOINT 20.2 TO MILEPOINT 24.645 | D |  | PM/NH | 2022 | 200000 | 160000 |  |  | 40000 | [5 empty] | 0
STIP | [9 empty] | WHITLEY | 11-20018 | I 75 |  | 20.2 | 24.645 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-075 CARDINAL DIRECTION(S) FROM MILEPOINT 20.2 TO MILEPOINT 24.645 | C |  | PM/NH | 2022 | 2000000 | 1600000 |  |  | 400000 | [5 empty] | 0
STIP | [9 empty] | WHITLEY | 11-20019 | I 75 |  | 23 | 28.872 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-075 BOTH DIRECTION(S) FROM MILEPOINT 23.0 (25.26 NON-CARDINAL) TO MILEPOINT 28.872 | D |  | PM/NH | 2019 | 340000 | 272000 |  |  | 68000 | [5 empty] | 0
STIP | [9 empty] | WHITLEY | 11-20019 | I 75 |  | 23 | 28.872 | ASSET MANAGEMENT | AM-PAVEMENT (INT)(P) | ADDRESS PAVEMENT CONDITION OF I-075 BOTH DIRECTION(S) FROM MILEPOINT 23.0 (25.26 NON-CARDINAL) TO MILEPOINT 28.872 | C |  | PM/NH | 2019 | 3400000 | 2720000 |  |  | 680000 | [5 empty] | 0
STIP | [9 empty] | WHITLEY | 11-20024 | KY 26 | 7.87 | 5.46 | 13.33 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION ON KY-26 FROM MILEPOINT 5.46 TO MILEPOINT 13.33 | C |  | PM/STP | 2022 | 1313000 | 1050400 |  |  | 262600 | [5 empty] | 0
STIP | [9 empty] | WHITLEY | 11-20025 | KY 90 | 5.55 | 2.78 | 8.33 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION ON KY-90 FROM MILEPOINT 2.78 TO MILEPOINT 8.33 | C |  | PM/STP | 2022 | 926000 | 740800 |  |  | 185200 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.229 | 2020-09-14 | ADD C PHASE TO STIP; PARENT NO. 99-224.14; NEW |  |  | WHITLEY | 11-20035 | KY 26 |  | 7.400 5.400 | 13.332 7.400 | RELIABILITY | AM-PAVEMENT (PRI)(P) | RESURFACING OF KY 26 AT (MP 7.400 TO MP 13.332) AND (MP 5.400 TO MP 7.400) IN WHITLEY COUNTY. (2020CCR) | C |  | STP | 2020 | 1534289 | 1534289 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.306 | 2021-06-16 | ADD D PHASE TO STIP; NEW |  |  | WHITLEY | 11-80107 | US 25 |  | 13.3 | 14.6 |  | RECONSTRUCTION(O) | IMPROVE US 25 W FROM MP 13.3 TO MP 14.6 AT THREE POINT | D |  | SPP | 2021 | 920100 | 100 |  |  | 920000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.216 | 2020-08-17 | ADD R PHASE TO STIP; NEW |  |  | WOLFE | 10-168.2 |  |  |  |  | RELIABILITY | MAJOR WIDENING(O) | MOUNTAIN PARKWAY CORRIDOR: WIDEN THE MOUNTAIN PARKWAY TO 4 LANES FROM 0.6 MILES WEST OF THE KY 191 OVERPASS TO THE KY 1010 INTERCHANGE. (2020CCR) | R |  | NH | 2021 | 6500000 | 5200000 |  |  | 1300000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.216 | 2020-08-17 | ADD U PHASE TO STIP; NEW |  |  | WOLFE | 10-168.2 |  |  |  |  | RELIABILITY | MAJOR WIDENING(O) | MOUNTAIN PARKWAY CORRIDOR: WIDEN THE MOUNTAIN PARKWAY TO 4 LANES FROM 0.6 MILES WEST OF THE KY 191 OVERPASS TO THE KY 1010 INTERCHANGE. (2020CCR) | U |  | NH | 2022 | 2000000 | 1600000 |  |  | 400000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.216 | 2020-08-17 | ADD C PHASE TO STIP; NEW |  |  | WOLFE | 10-168.2 |  |  |  |  | RELIABILITY | MAJOR WIDENING(O) | MOUNTAIN PARKWAY CORRIDOR: WIDEN THE MOUNTAIN PARKWAY TO 4 LANES FROM 0.6 MILES WEST OF THE KY 191 OVERPASS TO THE KY 1010 INTERCHANGE. (2020CCR) | C |  | INFRA | 2022 | 28000000 | 28000000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.216 | 2020-08-17 | ADD C PHASE TO STIP; NEW |  |  | WOLFE | 10-168.2 |  |  |  |  | RELIABILITY | MAJOR WIDENING(O) | MOUNTAIN PARKWAY CORRIDOR: WIDEN THE MOUNTAIN PARKWAY TO 4 LANES FROM 0.6 MILES WEST OF THE KY 191 OVERPASS TO THE KY 1010 INTERCHANGE. (2020CCR) | C |  | NH | 2023 | 11400000 | 5700000 |  |  | 5700000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.216 | 2020-08-17 | ADD C PHASE TO STIP; NEW |  |  | WOLFE | 10-168.2 |  |  |  |  | RELIABILITY | MAJOR WIDENING(O) | MOUNTAIN PARKWAY CORRIDOR: WIDEN THE MOUNTAIN PARKWAY TO 4 LANES FROM 0.6 MILES WEST OF THE KY 191 OVERPASS TO THE KY 1010 INTERCHANGE. (2020CCR) | C |  | NH | 2024 | 11400000 | 5700000 |  |  | 5700000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.216 | 2020-08-17 | ADD R PHASE TO STIP; NEW |  |  | WOLFE | 10-168.5 |  |  |  |  | RELIABILITY | MAJOR WIDENING(O) | MOUNTAIN PARKWAY CORRIDOR: WIDEN THE MOUNTAIN PARKWAY CORRIDOR TO 4 LANES FROM THE KY 1010 INTERCHANGE TO 0.45 MILES WEST OF THE KY 205 INTERCHANGE. (PRIORITY SECTION 1). (2020CCR) | R |  | NH | 2021 | 5000000 | 4000000 |  |  | 1000000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.216 | 2020-08-17 | ADD U PHASE TO STIP; NEW |  |  | WOLFE | 10-168.5 |  |  |  |  | RELIABILITY | MAJOR WIDENING(O) | MOUNTAIN PARKWAY CORRIDOR: WIDEN THE MOUNTAIN PARKWAY CORRIDOR TO 4 LANES FROM THE KY 1010 INTERCHANGE TO 0.45 MILES WEST OF THE KY 205 INTERCHANGE. (PRIORITY SECTION 1). (2020CCR) | U |  | NH | 2022 | 1140000 | 912000 |  |  | 228000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.216 | 2020-08-17 | ADD C PHASE TO STIP; NEW |  |  | WOLFE | 10-168.5 |  |  |  |  | RELIABILITY | MAJOR WIDENING(O) | MOUNTAIN PARKWAY CORRIDOR: WIDEN THE MOUNTAIN PARKWAY CORRIDOR TO 4 LANES FROM THE KY 1010 INTERCHANGE TO 0.45 MILES WEST OF THE KY 205 INTERCHANGE. (PRIORITY SECTION 1). (2020CCR) | C |  | INFRA | 2022 | 27150000 | 27150000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.216 | 2020-08-17 | ADD C PHASE TO STIP; NEW |  |  | WOLFE | 10-168.5 |  |  |  |  | RELIABILITY | MAJOR WIDENING(O) | MOUNTAIN PARKWAY CORRIDOR: WIDEN THE MOUNTAIN PARKWAY CORRIDOR TO 4 LANES FROM THE KY 1010 INTERCHANGE TO 0.45 MILES WEST OF THE KY 205 INTERCHANGE. (PRIORITY SECTION 1). (2020CCR) | C |  | NH | 2023 | 11400000 | 5700000 |  |  | 5700000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.216 | 2020-08-17 | ADD C PHASE TO STIP; NEW |  |  | WOLFE | 10-168.5 |  |  |  |  | RELIABILITY | MAJOR WIDENING(O) | MOUNTAIN PARKWAY CORRIDOR: WIDEN THE MOUNTAIN PARKWAY CORRIDOR TO 4 LANES FROM THE KY 1010 INTERCHANGE TO 0.45 MILES WEST OF THE KY 205 INTERCHANGE. (PRIORITY SECTION 1). (2020CCR) | C |  | NH | 2024 | 11400000 | 5700000 |  |  | 5700000 | [5 empty] | 0
STIP | [9 empty] | WOLFE | 10-10009 | KY 191 |  | 9.456 | 9.47 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-191 BRIDGE OVER LACEY CREEK. (119B00001N) | D |  | BR/NH | 2019 | 150000 | 93000 |  |  | 57000 | [5 empty] | 0
STIP | [9 empty] | WOLFE | 10-10009 | KY 191 |  | 9.456 | 9.47 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-191 BRIDGE OVER LACEY CREEK. (119B00001N) | C |  | BR/NH | 2020 | 564000 | 349680 |  |  | 214320 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.03 | 2019-03-01 | INCREASE FUNDS BASED ON BRIDGE NEEDS AFTER INSPECTION; MOD | STPBRZ | 9030067 | WOLFE | 10-10009 | KY 191 |  | 9.456 | 9.47 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY-191 BRIDGE OVER LACEY CREEK. (119B00001N) | C |  | STP | 2019 | 726750 | 726750 |  |  | 0 |  |  | OBLIGATED |  | 701675 | 701675 | 2019 | 3RD QUARTER
STIP | [9 empty] | WOLFE | 10-10019 | KY 2491 |  | 4.899 | 4.905 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 2491 BRIDGE OVER SWANGO FORK. (119B00058N) | D |  | BR/STP | 2019 | 175000 | 108500 |  |  | 66500 | [5 empty] | 0
STIP | [9 empty] | WOLFE | 10-10019 | KY 2491 |  | 4.899 | 4.905 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF KY 2491 BRIDGE OVER SWANGO FORK. (119B00058N) | C |  | BR/STP | 2020 | 525000 | 325500 |  |  | 199500 | [5 empty] | 0
STIP | [9 empty] | WOLFE | 10-20009 | KY 9000 |  | 36 | 41.373 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF BERT T. COMBS MOUNTAIN PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 36 TO MILEPOINT 42.85 | D |  | PM/NH | 2021 | 550000 | 440000 |  |  | 110000 | [5 empty] | 0
STIP | [9 empty] | WOLFE | 10-20009 | KY 9000 |  | 36 | 41.373 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF BERT T. COMBS MOUNTAIN PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 36 TO MILEPOINT 42.85 | C |  | PM/NH | 2021 | 5500000 | 4400000 |  |  | 1100000 | [5 empty] | 0
STIP | [9 empty] | WOLFE | 10-20010 | KY 9009 |  | 42.853 | 46.208 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF BERT T. COMBS MOUNTAIN PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 42.853 TO MILEPOINT 46.208 | D |  | PM/STP | 2022 | 275000 | 220000 |  |  | 55000 | [5 empty] | 0
STIP | [9 empty] | WOLFE | 10-20010 | KY 9009 |  | 42.853 | 46.208 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF BERT T. COMBS MOUNTAIN PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 42.853 TO MILEPOINT 46.208 | C |  | PM/STP | 2022 | 2750000 | 2200000 |  |  | 550000 | [5 empty] | 0
STIP | [9 empty] | WOLFE | 10-20011 | KY 9009 |  | 46.208 | 55.434 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF BERT T. COMBS MOUNTAIN PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 46.208 TO MILEPOINT 55.434 | D |  | PM/STP | 2021 | 370000 | 296000 |  |  | 74000 | [5 empty] | 0
STIP | [9 empty] | WOLFE | 10-20011 | KY 9009 |  | 46.208 | 55.434 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF BERT T. COMBS MOUNTAIN PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 46.208 TO MILEPOINT 55.434 | C |  | PM/STP | 2021 | 3700000 | 2960000 |  |  | 740000 | [5 empty] | 0
STIP | [9 empty] | WOLFE | 10-20012 | KY 9009 |  | 55.434 | 57.72 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF BERT T. COMBS MOUNTAIN PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 55.434 TO MILEPOINT 57.72 | D |  | PM/STP | 2019 | 90000 | 72000 |  |  | 18000 | [5 empty] | 0
STIP | [7 empty] | NHPP | 0061079 | WOLFE | 10-20012 | KY 9009 |  | 55.434 | 57.72 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF BERT T. COMBS MOUNTAIN PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 55.434 TO MILEPOINT 57.72 | C |  | PM/STP | 2019 | 900000 | 720000 |  |  | 180000 |  |  | OBLIGATED | 5500044 |  | 5500044 | 2019 | 2ND QUARTER
STIP | [9 empty] | WOLFE | 10-20016 | KY 15S | 0.93 | 0 | 0.93 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION ON KY-15S FROM MILEPOINT 0.00 TO MILEPOINT 0.93 | C |  | PM/STP | 2022 | 896000 | 716800 |  |  | 179200 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.229 | 2020-09-14 | ADD C PHASE TO STIP; PARENT NO. 99-224.14; NEW |  |  | WOLFE | 10-20029 | KY 15 |  | 9.515 | 14.88 | RELIABILITY | AM-PAVEMENT (PRI)(P) | RESURFACING OF KY 15 (MP 9.515 TO MP 14.880) IN WOLFE COUNTY. (2020CCR) | C |  | STP | 2020 | 717486 | 717486 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.161 | 2020-02-21 | ADD PROJECT TO STIP; PARENT NO. 99-911.09; NEW |  | 5196014 | WOODFORD | 7-954 | US 62 |  | 14.4 | 16.459 | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALLATION OF STRIPING ON US 62 IN WOODFORD COUNTY. (2018BOP) | C |  | SAF | 2020 | 132000 | 132000 |  |  | 0 |  |  | OBLIGATED | 132000 |  | 132000 | 2020 | 2ND QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.161 | 2020-02-21 | ADD PROJECT TO STIP; PARENT NO. 99-911.09; NEW |  | 5196015 | WOODFORD | 7-955 | US 421 |  | 0 | 4.931 | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALLATION OF STRIPING AND CENTERLINE RUMBLE STRIPS ON US 421 IN WOODFORD COUNTY. (2018BOP) | C |  | SAF | 2020 | 356000 | 356000 |  |  | 0 |  |  | OBLIGATED | 352000 |  | 352000 | 2020 | 2ND QUARTER
STIP | [7 empty] | STPBRZ | 0703334 | WOODFORD | 7-8642 | CR 1015 | 0.023 | 2.499 | 2.522 | ASSET MANAGEMENT | AM-BRIDGE (P) | ADDRESS DEFICIENCIES OF THE WEISENBURG MILL ROAD BRIDGE AT THE WOODFORD/SCOTT COUNTY LINE. (10CCN)(120C00006N) | C |  | BR/STP | 2020 | 966000 | 598920 |  |  | 367080 |  |  | OBLIGATED | 798122 | 166578 | 964700 | 2019 | 3RD QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.053 | 2019-04-25 | ADD R PHASE TO STIP; PARENT NO. 99-911.06; NEW | HSIP | 519002 | WOODFORD | 7-9005 | KY 33 |  | 3.017 | 11.686 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 33 BEGINNING AT MP 3.017 AND ENDING AT MP 11.686 IN WOODFORD COUNTY. (2016BOP) | R |  | SAF | 2019 | 55000 | 55000 |  |  | 0 |  |  | OBLIGATED | 55000 |  | 55000 | 2019 | 3RD QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.053 | 2019-04-25 | ADD U PHASE TO STIP; PARENT NO. 99-911.06; NEW | HSIP | 519002 | WOODFORD | 7-9005 | KY 33 |  | 3.017 | 11.686 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 33 BEGINNING AT MP 3.017 AND ENDING AT MP 11.686 IN WOODFORD COUNTY. (2016BOP) | U |  | SAF | 2019 | 150000 | 150000 |  |  | 0 |  |  | OBLIGATED | 150000 |  | 150000 | 2019 | 3RD QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.229 | 2020-09-14 | ADD C PHASE TO STIP; PARENT NO. 99-911.06; NEW |  |  | WOODFORD | 7-9005 | KY 33 |  | 0 | 11.686 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 33 BEGINNING AT MP 0.000 AND ENDING AT MP 11.686 IN WOODFORD COUNTY. (2016BOP) | C |  | SAF | 2020 | 3000000 | 3000000 |  |  | 0 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.175 | 2020-04-09 | LEXINGTON MPO AREA TIP FY 17-20, GROUP PROJECTS, TABLE 6, PAGE 35; ADD D PHASE TO STIP;NEW |  |  | WOODFORD FAYETTE | 7-9020 | KY 1966 |  | 0 0 | 0.694 3.865 | SAFETY | SAFETY-HAZARD ELIM(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 1966 FROM MP 0.000 TO MP 0.694 IN WOODFORD COUNTY, AND MP 0.000 TO MP 3.865 IN FAYETTE COUNTY, KY. (2018BOP) | D |  | SAF | 2020 | 275000 | 275000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | WOODFORD | 7-20022 | BG 9002 |  | 61.95 | 70.7 | ASSET MANAGEMENT | AM-PAVEMENT (PKY)(P) | ADDRESS PAVEMENT CONDITION OF MARTHA LAYNE COLLINS BLUEGRASS PARKWAY BOTH DIRECTION(S) FROM MILEPOINT 61.95 (62.05 NON-CARDINAL) TO MILEPOINT 70.70 (70.91 NON-CARDINAL) | D |  | PM/NH | 2019 | 700000 | 560000 |  |  | 140000 | [5 empty] | 0
STIP | [9 empty] | WOODFORD | 7-20023 | US 60 |  | 7.345 | 9.305 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT | D |  | PM/NH | 2020 | 350000 | 280000 |  |  | 70000 | [5 empty] | 0
STIP | [9 empty] | WOODFORD | 7-20023 | US 60 |  | 7.345 | 9.305 | ASSET MANAGEMENT | AM-PAVEMENT (PRI)(P) | ADDRESS PAVEMENT CONDITION OF AC PAVEMENT | C |  | PM/NH | 2020 | 3500000 | 2800000 |  |  | 700000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-65.16 |  |  |  |  | ASSET MANAGEMENT | AM-BRIDGE (P) | BRIDGE REPAIRS ON VARIOUS BRIDGES FOR FY 2019. | C |  | BR/NH | 2019 | 2000000 | 1240000 |  |  | 760000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-65.17 |  |  |  |  | ASSET MANAGEMENT | AM-BRIDGE (P) | BRIDGE REPAIRS ON VARIOUS BRIDGES FOR FY 2020. | C |  | BR/NH | 2020 | 2000000 | 1240000 |  |  | 760000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-65.18 |  |  |  |  | ASSET MANAGEMENT | AM-BRIDGE (P) | BRIDGE REPAIRS ON VARIOUS BRIDGES FOR FY 2021. | C |  | BR/NH | 2021 | 30000000 | 18600000 |  |  | 11400000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-65.19 |  |  |  |  | ASSET MANAGEMENT | AM-BRIDGE (P) | BRIDGE REPAIRS ON VARIOUS BRIDGES FOR FY 2022. | C |  | BR/NH | 2022 | 30000000 | 18600000 |  |  | 11400000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-66.14 |  |  |  |  | RELIABILITY | ITS(P) | 'ITS' ACTIVITIES ON VARIOUS NHS ROUTES IN KENTUCKY FOR FY 2019. | C |  | NH | 2019 | 2000000 | 2000000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-66.15 |  |  |  |  | RELIABILITY | ITS(P) | 'ITS' ACTIVITIES ON VARIOUS NHS ROUTES IN KENTUCKY FOR FY 2020. | C |  | NH | 2020 | 2000000 | 2000000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-66.16 |  |  |  |  | RELIABILITY | ITS(P) | 'ITS' ACTIVITIES ON VARIOUS NHS ROUTES IN KENTUCKY FOR FY 2021. | C |  | NH | 2021 | 2000000 | 1600000 |  |  | 400000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-66.17 |  |  |  |  | RELIABILITY | ITS(P) | 'ITS' ACTIVITIES ON VARIOUS NHS ROUTES IN KENTUCKY FOR FY 2022. | C |  | NH | 2022 | 2000000 | 1600000 |  |  | 400000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.279 | 2021-03-05 | ADD C PHASE TO STIP; PARENT NO. 99-66.15; NEW |  |  | ZVARIOUS | 99-66.20 |  |  |  |  | RELIABILITY | ITS(P) | KYTC TECHNOLOGY MODERNIZATION UPDATES TO HARDWARE AND SOFTWARE (CRS FUNDING IS PROVIDED BY "CORONAVIRUS RESPONSE AND RELIEF SUPPLEMENTAL APPROPRIATIONS ACT 2021"). | C |  | CRS | 2021 | 1450000 | 1450000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-195.15 |  |  |  |  | RELIABILITY | TRANSP ENHANCEMENT(P) | STATEWIDE TRANSPORTATION ENHANCEMENT FOR FY 2019. (98CCR) | C |  | TE | 2019 | 13700000 | 10960000 |  |  |  | 2740000 |  |  |  |  | 0
STIP | [9 empty] | ZVARIOUS | 99-195.16 |  |  |  |  | RELIABILITY | TRANSP ENHANCEMENT(P) | STATEWIDE TRANSPORTATION ENHANCEMENT FOR FY 2020 (98CCR) | C |  | TE | 2020 | 13700000 | 10960000 |  |  |  | 2740000 |  |  |  |  | 0
STIP | [9 empty] | ZVARIOUS | 99-195.17 |  |  |  |  | RELIABILITY | TRANSP ENHANCEMENT(P) | STATEWIDE TRANSPORTATION ENHANCEMENT FOR FY 2021. | C |  | TE | 2021 | 12800000 | 10240000 |  |  |  | 2560000 |  |  |  |  | 0
STIP | [9 empty] | ZVARIOUS | 99-195.18 |  |  |  |  | RELIABILITY | TRANSP ENHANCEMENT(P) | STATEWIDE TRANSPORTATION ENHANCEMENT FOR FY 2022. | C |  | TE | 2022 | 12800000 | 10240000 |  |  |  | 2560000 |  |  |  |  | 0
STIP | [9 empty] | ZVARIOUS | 99-219.17 |  |  |  |  | RELIABILITY | CONGESTION MITIGTN(O) | NON-ATTAINMENT AREAS STATEWIDE CMAQ FUNDED PROJECTS FOR FY 2019. | C |  | CM | 2019 | 13100000 | 10480000 |  |  |  | 2620000 |  |  |  |  | 0
STIP | [9 empty] | ZVARIOUS | 99-219.18 |  |  |  |  | RELIABILITY | CONGESTION MITIGTN(O) | NON-ATTAINMENT AREAS STATEWIDE CMAQ FUNDED PROJECTS FOR FY 2020. | C |  | CM | 2020 | 13100000 | 10480000 |  |  |  | 2620000 |  |  |  |  | 0
STIP | [9 empty] | ZVARIOUS | 99-219.19 |  |  |  |  | RELIABILITY | CONGESTION MITIGTN(O) | NON-ATTAINMENT AREAS STATEWIDE CMAQ FUNDED PROJECTS FOR FY 2021. | C |  | CM | 2021 | 17800000 | 14240000 |  |  |  | 3560000 |  |  |  |  | 0
STIP | [9 empty] | ZVARIOUS | 99-219.2 |  |  |  |  | RELIABILITY | CONGESTION MITIGTN(O) | NON-ATTAINMENT AREAS STATEWIDE CMAQ FUNDED PROJECTS FOR FY 2022. | C |  | CM | 2022 | 17800000 | 14240000 |  |  |  | 3560000 |  |  |  |  | 0
STIP | [9 empty] | ZVARIOUS | 99-224.13 |  |  |  |  | RELIABILITY | AM-PAVEMENT (PRI)(P) | PAVEMENT REHAB ON STATE (NON RS) SYSTEM ROUTES IN KENTUCKY FOR FY 2019. | C |  | PM/STP | 2019 | 2000000 | 1600000 |  |  | 400000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-224.14 |  |  |  |  | RELIABILITY | AM-PAVEMENT (PRI)(P) | PAVEMENT REHAB ON STATE (NON RS) SYSTEM ROUTES IN KENTUCKY FOR FY 2021. | C |  | PM/STP | 2021 | 9000000 | 7200000 |  |  | 1800000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-327.15 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | STATEWIDE BRIDGE INSPECTION FOR FY 2019. | C |  | BR/STP | 2019 | 2600000 | 1612000 |  |  | 988000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.012 | 2019-01-08 | CHANGE STATE MATCH TO TOLL CREDITS; MOD |  |  | ZVARIOUS | 99-327.15 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | STATEWIDE BRIDGE INSPECTION FOR FY 2019. | C |  | BR/STP | 2019 | 2600000 | 2600000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-327.16 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | STATEWIDE BRIDGE INSPECTION FOR FY 2020. | C |  | BR/STP | 2020 | 2600000 | 1612000 |  |  | 988000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-327.17 |  |  |  |  | RELIABILITY | BRIDGE INSPECTION(P) | STATEWIDE BRIDGE INSPECTION FOR FY 2021. | C |  | BR/STP | 2021 | 2600000 | 1612000 |  |  | 988000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-327.18 |  |  |  |  | RELIABILITY | BRIDGE INSPECTION(P) | STATEWIDE BRIDGE INSPECTION FOR FY 2022. | C |  | BR/STP | 2022 | 2600000 | 1612000 |  |  | 988000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-333.15 |  |  |  |  | RELIABILITY | FOREST HIGHWAY(P) | STATEWIDE FEDERAL LANDS ACCESS PROGRAM FEDERAL HIGHWAY FUNDS FOR FY 2019. | C |  | FH | 2022 | 1641000 | 1312800 |  |  | 328200 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-337.14 |  |  |  |  | RELIABILITY | AM-PAVEMENT (INT)(P) | STATEWIDE I-STATE ROUTES FOR FY 2019.(14CCR) | C |  | PM/NH | 2019 | 2000000 | 1600000 |  |  | 400000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-337.15 |  |  |  |  | RELIABILITY | AM-PAVEMENT (INT)(P) | STATEWIDE I-STATE ROUTES FOR FY 2021.(14CCR) | C |  | PM/NH | 2021 | 9000000 | 7200000 |  |  | 1800000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-346.15 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | STATEWIDE OFF-SYSTEM BRIDGE INSPECTION FOR FY 2019. | C |  | BR/STP | 2019 | 1100000 | 682000 |  |  | 418000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.012 | 2019-01-08 | CHANGE STATE MATCH TO TOLL CREDITS; MOD |  |  | ZVARIOUS | 99-346.15 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | STATEWIDE OFF-SYSTEM BRIDGE INSPECTION FOR FY 2019. | C |  | BR/STP | 2019 | 1100000 | 1100000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-346.16 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | STATEWIDE OFF-SYSTEM BRIDGE INSPECTION FOR FY 2020. | C |  | BR/STP | 2020 | 1100000 | 682000 |  |  | 418000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-346.17 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | STATEWIDE OFF-SYSTEM BRIDGE INSPECTION FOR FY 2021. | C |  | BR/STP | 2021 | 1100000 | 682000 |  |  | 418000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-346.18 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | STATEWIDE OFF-SYSTEM BRIDGE INSPECTION FOR FY 2022. | C |  | BR/STP | 2022 | 1100000 | 682000 |  |  | 418000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-352.15 |  |  |  |  | SAFETY | SAFETY-RR PROTECTN(P) | RAIL PROTECTION ON VARIOUS ROUTES FOR FY 2019. | C |  | RRP | 2019 | 3600000 | 3600000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-352.16 |  |  |  |  | SAFETY | SAFETY-RR PROTECTN(P) | RAIL PROTECTION ON VARIOUS ROUTES FOR FY 2020. | C |  | RRP | 2020 | 3600000 | 3600000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-352.17 |  |  |  |  | RELIABILITY | SAFETY-RR PROTECTN(P) | RAIL PROTECTION ON VARIOUS ROUTES FOR FY 2021. | C |  | RRP | 2021 | 4400000 | 3520000 |  |  | 880000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-352.18 |  |  |  |  | RELIABILITY | SAFETY-RR PROTECTN(P) | RAIL PROTECTION ON VARIOUS ROUTES FOR FY 2022. | C |  | RRP | 2022 | 4400000 | 3520000 |  |  | 880000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-369.09 |  |  |  |  | RELIABILITY | AM-PAVEMENT (PRI)(P) | PAVEMENT REHABILITATION FOR VARIOUS NHS ROUTES IN KENTUCKY FOR FY 2019. | C |  | PM/NH | 2019 | 2000000 | 1600000 |  |  | 400000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-369.1 |  |  |  |  | RELIABILITY | AM-PAVEMENT (PRI)(P) | PAVEMENT REHABILITATION FOR VARIOUS NHS ROUTES IN KENTUCKY FOR FY 2021. | C |  | PM/NH | 2021 | 9000000 | 7200000 |  |  | 1800000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-388.09 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | OHIO RIVER BRIDGES FRACTURE CRITICAL FOR FY 2019. | C |  | BR/STP | 2019 | 1600000 | 992000 |  |  | 608000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-388.1 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | OHIO RIVER BRIDGES FRACTURE CRITICAL FOR FY 2020. | C |  | BR/STP | 2020 | 1600000 | 992000 |  |  | 608000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-388.11 |  |  |  |  | RELIABILITY | BRIDGE INSPECTION(P) | OHIO RIVER BRIDGES FRACTURE CRITICAL FOR FY 2021. | C |  | BR/STP | 2021 | 1600000 | 992000 |  |  | 608000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-388.12 |  |  |  |  | RELIABILITY | BRIDGE INSPECTION(P) | OHIO RIVER BRIDGES FRACTURE CRITICAL FOR FY 2022. | C |  | BR/STP | 2022 | 1600000 | 992000 |  |  | 608000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-391.04 |  |  |  |  | RELIABILITY | DESIGN ENGINEERING(O) | STATEWIDE STP HIGHWAY PROJECT ACTIVITIES. | D |  | STP | 2019 | 2000000 | 2000000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-391.06 |  |  |  |  | RELIABILITY | DESIGN ENGINEERING(O) | STATEWIDE HIGHWAY PROJECT DESIGN ACTIVITIES. | D |  | STP | 2021 | 1000000 | 800000 |  |  | 200000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-395.07 |  |  |  |  | RELIABILITY | AM-PAVEMENT (INT)(P) | PAVEMENT REPAIR AT INTERSECTIONS FOR VARIOUS ROADWAYS FOR FY 2019.(12CCR) | C |  | PM/STP | 2019 | 2000000 | 1600000 |  |  | 400000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-395.08 |  |  |  |  | RELIABILITY | AM-PAVEMENT (INT)(P) | PAVEMENT REPAIR AT INTERSECTIONS FOR VARIOUS ROADWAYS FOR FY 2021.(12CCR) | C |  | PM/STP | 2021 | 5000000 | 4000000 |  |  | 1000000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-510.03 |  |  |  |  | RELIABILITY | AM-BRIDGE (P) | HONORING BORDER STATES COMMITMENTS FOR EXISTING BRIDGES(CANNOT BE MOVED). | C |  | BR/STP | 2019 | 3500000 | 2170000 |  |  | 1330000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-510.05 |  |  |  |  | RELIABILITY | AM-BRIDGE (P) | HONORING BORDER STATES COMMITMENTS FOR EXISTING BRIDGES(CANNOT BE MOVED). | C |  | BR/STP | 2021 | 15000000 | 9300000 |  |  | 5700000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-510.06 |  |  |  |  | RELIABILITY | AM-BRIDGE (P) | HONORING BORDER STATES COMMITMENTS FOR EXISTING BRIDGES(CANNOT BE MOVED). | C |  | BR/STP | 2022 | 15000000 | 9300000 |  |  | 5700000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-511.03 |  |  |  |  | RELIABILITY | LANDSLIDE REPAIR(P) | STATEWIDE CORRECTIONS OF ROCK FALL OR EMBANKMENT STABILIZATION FOR FY 2019. | C |  | STP | 2019 | 2000000 | 2000000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-511.04 |  |  |  |  | RELIABILITY | LANDSLIDE REPAIR(P) | STATEWIDE CORRECTIONS OF ROCK FALL OR EMBANKMENT STABILIZATION FOR FY 2020. | C |  | STP | 2020 | 1000000 | 1000000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-511.05 |  |  |  |  | RELIABILITY | LANDSLIDE REPAIR(P) | STATEWIDE CORRECTIONS OF ROCK FALL OR EMBANKMENT STABILIZATION FOR FY 2021. | C |  | STP | 2021 | 1000000 | 800000 |  |  | 200000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-511.06 |  |  |  |  | RELIABILITY | LANDSLIDE REPAIR(P) | STATEWIDE CORRECTIONS OF ROCK FALL OR EMBANKMENT STABILIZATION FOR FY 2022. | C |  | STP | 2022 | 2000000 | 1600000 |  |  | 400000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-514 |  |  |  |  | RELIABILITY | AM-BRIDGE (P) | PREVENTATIVE MAINTENANCE FOR BRIDGE STRUCTURES FOR FY 2019. | C |  | BR/STP | 2019 | 3000000 | 1860000 |  |  | 1140000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-514.01 |  |  |  |  | RELIABILITY | AM-BRIDGE (P) | PREVENTATIVE MAINTENANCE FOR BRIDGE STRUCTURES FOR FY 2021. | C |  | BR/STP | 2021 | 10000000 | 6200000 |  |  | 3800000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-518 |  |  |  |  | RELIABILITY | LANDSLIDE REPAIR(P) | STATEWIDE CORRECTIONS OF ROCKFALL OR EMBANKMENT STABILIZATION ON NH ROUTES FOR FY 2019. | C |  | NH | 2019 | 6000000 | 4800000 |  |  | 1200000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-518.01 |  |  |  |  | RELIABILITY | LANDSLIDE REPAIR(P) | STATEWIDE CORRECTIONS OF ROCKFALL OR EMBANKMENT STABILIZATION ON NH ROUTES FOR FY 2020. | C |  | NH | 2020 | 1000000 | 800000 |  |  | 200000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-518.02 |  |  |  |  | RELIABILITY | LANDSLIDE REPAIR(P) | STATEWIDE CORRECTIONS OF ROCKFALL OR EMBANKMENT STABILIZATION ON NH ROUTES FOR FY 2021. | C |  | NH | 2021 | 6000000 | 4800000 |  |  | 1200000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-518.03 |  |  |  |  | RELIABILITY | LANDSLIDE REPAIR(P) | STATEWIDE CORRECTIONS OF ROCKFALL OR EMBANKMENT STABILIZATION ON NH ROUTES FOR FY 2022. | C |  | NH | 2022 | 7000000 | 5600000 |  |  | 1400000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-911.08 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | STATEWIDE SAFETY PROGRAM FOR FY 2019.(HSIP) | C |  | SAF | 2019 | 38500000 | 30800000 |  |  | 7700000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-911.09 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | STATEWIDE SAFETY PROGRAM FOR FY 2020. (HSIP) | C |  | SAF | 2020 | 38500000 | 30800000 |  |  | 7700000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-911.1 |  |  |  |  | RELIABILITY | SAFETY-HAZARD ELIM(P) | STATEWIDE SAFETY PROGRAM FOR FY 2021. (HSIP) | C |  | SAF | 2021 | 47500000 | 38000000 |  |  | 9500000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-911.11 |  |  |  |  | RELIABILITY | SAFETY-HAZARD ELIM(P) | STATEWIDE SAFETY PROGRAM FOR FY 2022. (HSIP) | C |  | SAF | 2022 | 47500000 | 38000000 |  |  | 9500000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-1063.15 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | STATEWIDE UNDERWATER BRIDGE INSPECTION FOR FY 2019. | C |  | BR/STP | 2019 | 500000 | 310000 |  |  | 190000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-1063.16 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | STATEWIDE UNDERWATER BRIDGE INSPECTION FOR FY 2020. | C |  | BR/STP | 2020 | 500000 | 310000 |  |  | 190000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-1063.17 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | STATEWIDE UNDERWATER BRIDGE INSPECTION FOR FY 2021. | C |  | BR/STP | 2021 | 500000 | 310000 |  |  | 190000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-1063.18 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | STATEWIDE UNDERWATER BRIDGE INSPECTION FOR FY 2022. | C |  | BR/STP | 2022 | 500000 | 310000 |  |  | 190000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-1074.07 |  |  |  |  | ASSET MANAGEMENT | AM-BRIDGE (P) | STATEWIDE BRIDGE REPLACEMENT PROGRAM FOR FY 2019. | C |  | BR/STP | 2019 | 3000000 | 1860000 |  |  | 1140000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-1074.08 |  |  |  |  | ASSET MANAGEMENT | AM-BRIDGE (P) | STATEWIDE BRIDGE REPLACEMENT PROGRAM FOR FY 2021. | C |  | BR/STP | 2021 | 18000000 | 11160000 |  |  | 6840000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-1074.09 |  |  |  |  | ASSET MANAGEMENT | AM-BRIDGE (P) | STATEWIDE BRIDGE REPLACEMENT PROGRAM FOR FY 2022. | C |  | BR/STP | 2022 | 20000000 | 12400000 |  |  | 7600000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-2700.13 |  |  |  |  | RELIABILITY | AM-PAVEMENT (PRI)(P) | PAVEMENT PREVENTATIVE MAINTENANCE PROGRAM FOR FY 2019. | C |  | PM/STP | 2019 | 2000000 | 1600000 |  |  | 400000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-2700.14 |  |  |  |  | RELIABILITY | AM-PAVEMENT (PRI)(P) | PAVEMENT PREVENTATIVE MAINTENANCE PROGRAM FOR FY 2020. | C |  | PM/STP | 2020 | 2000000 | 1600000 |  |  | 400000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-2700.15 |  |  |  |  | RELIABILITY | AM-PAVEMENT (PRI)(P) | PAVEMENT PREVENTATIVE MAINTENANCE PROGRAM FOR FY 2021. | C |  | PM/STP | 2021 | 5000000 | 4000000 |  |  | 1000000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-2700.16 |  |  |  |  | RELIABILITY | AM-PAVEMENT (PRI)(P) | PAVEMENT PREVENTATIVE MAINTENANCE PROGRAM FOR FY 2022. | C |  | PM/STP | 2022 | 5000000 | 4000000 |  |  | 1000000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-3011 |  |  |  |  | SAFETY | SAFETY(P) | AMERICANS WITH DISABILITIES ACT (ADA) TRANSITION PLAN IMPLEMENTATION PROJECTS. | C |  | STP | 2019 | 1000000 | 1000000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-3011.01 |  |  |  |  | SAFETY | SAFETY(P) | AMERICANS WITH DISABILITIES ACT (ADA) TRANSITION PLAN IMPLEMENTATION PROJECTS. | C |  | STP | 2020 | 1000000 | 1000000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-3011.02 |  |  |  |  | SAFETY | SAFETY(P) | AMERICANS WITH DISABILITIES ACT (ADA) TRANSITION PLAN IMPLEMENTATION PROJECTS. | C |  | STP | 2021 | 1000000 | 800000 |  |  | 200000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-3011.03 |  |  |  |  | SAFETY | SAFETY(P) | AMERICANS WITH DISABILITIES ACT (ADA) TRANSITION PLAN IMPLEMENTATION PROJECTS. | C |  | STP | 2022 | 1000000 | 800000 |  |  | 200000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-9050.1 |  |  |  |  | RELIABILITY | MAJOR WIDENING(O) | GARVEE BOND DEBT SERVICE FOR I-65; I-75; AND I-64 FOR FY 2019. (JM03-FD53 "IM" COMPONENT) | C |  | NH | 2019 | 44500000 | 44500000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-9068.05 | US 68 |  |  |  | RELIABILITY | AM-BRIDGE (P) | US 68/KY 80 LAKE BARKLEY AND KENTUCKY LAKE GARVEE BOND DEBT SERVICE (NH) FOR FY 2019. (079B00023N, 111B00020N) | C |  | NH | 2019 | 9100000 | 9100000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-9068.61 | US 68 |  |  |  | RELIABILITY | AM-BRIDGE (P) | US 68/KY 80 LAKE BARKLEY AND KENTUCKY LAKE GARVEE BOND DEBT SERVICE (NH) FOR FY 2020. (12CCR) | C |  | NH | 2020 | 9100000 | 9100000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-9068.65 | US 68 |  |  |  | RELIABILITY | AM-BRIDGE (P) | US 68/KY 80 LAKE BARKLEY AND KENTUCKY LAKE GARVEE BOND DEBT SERVICE (STP) FOR FY 2019. | C |  | STP | 2019 | 9100000 | 9100000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-9068.66 | US 68 |  |  |  | RELIABILITY | AM-BRIDGE (P) | US 68/KY 80 LAKE BARKLEY AND KENTUCKY LAKE GARVEE BOND DEBT SERVICE (STP) FOR FY 2020. | C |  | STP | 2020 | 9100000 | 9100000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-9068.67 | US 68 |  |  |  | RELIABILITY | AM-BRIDGE (P) | US 68/KY 80 LAKE BARKLEY AND KENTUCKY LAKE GARVEE BOND DEBT SERVICE (STP) FOR FY 2021. | C |  | STP | 2021 | 9100000 | 7280000 |  |  | 1820000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-9068.68 | US 68 |  |  |  | RELIABILITY | AM-BRIDGE (P) | US 68/KY 80 LAKE BARKLEY AND KENTUCKY LAKE GARVEE BOND DEBT SERVICE (STP) FOR FY 2022. | C |  | STP | 2022 | 9100000 | 7280000 |  |  | 1820000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-9068.69 | US 68 |  |  |  | RELIABILITY | AM-BRIDGE (P) | US 68/KY 80 LAKE BARKLEY AND KENTUCKY LAKE GARVEE BOND DEBT SERVICE (NH) FOR FY 2021. | C |  | NH | 2021 | 9100000 | 7280000 |  |  | 1820000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-9068.7 | US 68 |  |  |  | RELIABILITY | AM-BRIDGE (P) | US 68/KY 80 LAKE BARKLEY AND KENTUCKY LAKE GARVEE BOND DEBT SERVICE (NH) FOR FY 2022. | C |  | NH | 2022 | 9100000 | 7280000 |  |  | 1820000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-9659.21 |  |  |  |  | RELIABILITY | RECONSTRUCTION(O) | GARVEE BOND DEBT SERVICE FOR LOUISVILLE BRIDGES PROJECT FOR FY 2019. (JZ1-FD53 "NH" COMPONENT) | C |  | NH | 2019 | 34300000 | 34300000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-9659.23 |  |  |  |  | RELIABILITY | RECONSTRUCTION(O) | GARVEE BOND DEBT SERVICE FOR LOUISVILLE BRIDGES PROJECT FOR FY 2020. (JZ1-FD53 "NH" COMPONENT) | C |  | NH | 2020 | 62800000 | 62800000 |  |  | 0 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-9659.25 |  |  |  |  | RELIABILITY | RECONSTRUCTION(O) | GARVEE BOND DEBT SERVICE FOR LOUISVILLE BRIDGES PROJECT FOR FY 2021. (JZ1-FD53 "NH" COMPONENT) | C |  | NH | 2021 | 62800000 | 50240000 |  |  | 12560000 | [5 empty] | 0
STIP | [9 empty] | ZVARIOUS | 99-9659.27 |  |  |  |  | RELIABILITY | RECONSTRUCTION(O) | GARVEE BOND DEBT SERVICE FOR LOUISVILLE BRIDGES PROJECT FOR FY 2022. (JZ1-FD53 "NH" COMPONENT) | C |  | NH | 2022 | 62800000 | 50240000 |  |  | 12560000 | [5 empty] | 0
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.099 | 2019-07-10 | ADD PROJECT TO STIP; NEW |  |  | ZVARIOUS | [5 empty] | RELIABILITY | RECONSTRUCTION(O) | STATEWIDE RIVERPORT STUDY TO DEVELOP STRATEGIC RECOMMENDATIONS FOR FREIGHT MODAL SHIFT, NEW INFRASTRUCTURE NEEDS AND INVESTMENTS AND FINANCIAL PLAN. | P |  | SPR | 2019 | 1000000 | 1000000 |  |  | 0 |  |  | OBLIGATED | 328576 | 671424 | 1000000 | 2019 | 4TH QUARTER
STIP MOD |  |  |  | ADMINISTRATIVE MODIFICATION | 2018.321 | 2021-08-17 | ADD PROJECT TO STIP; NEW |  |  | ZVARIOUS | N/A | [6 empty] | ACQUISITION OF AX900 SEMI-PORTABLE SCALES. | N |  | STP | 2021 | 60000 | 60000 |  |  | 0 | [5 empty] | 0
0

## REGIONAL SIGNIFICANT SPP PROJ
MODIFICATION OR AMENDMENT | STIP ADMINISTRATIVE MODIFICATION OR AMENDMENT NUMBER | APPROVAL DATE | COMMENTS | COUNTY | DISTNO | ITEMNO | ITEM ID | ROUTE NO. | PREFIX1 | ROUTENO1 | SUFFIX1 | LENGTH | BMP1 | EMP1 | PRIORITY | TYPEWORK | DESCRIPTION | PHASE | FUND CODE | FISYEAR | AMOUNT | NH SYSTEM
|  |  |  | BARREN | 3 | 80002 | 3-80002 | LN 9008 | LN | 9008 |  |  | 12.8 | 13 | RELIABILITY | NEW INTERCHANGE(O) | NEW INTERCHANGE ON THE LOUIE NUNN CUMBERLAND PARKWAY AT KY-249 IN GLASGOW(18CCN) | D | SPP | 2020 | 1500000 | N
|  |  |  | BARREN | 3 | 80002 | 3-80002 | LN 9008 | LN | 9008 |  |  | 12.8 | 13 | RELIABILITY | NEW INTERCHANGE(O) | NEW INTERCHANGE ON THE LOUIE NUNN CUMBERLAND PARKWAY AT KY-249 IN GLASGOW(18CCN) | R | SPP | 2021 | 2000000 | N
|  |  |  | BARREN | 3 | 80002 | 3-80002 | LN 9008 | LN | 9008 |  |  | 12.8 | 13 | RELIABILITY | NEW INTERCHANGE(O) | NEW INTERCHANGE ON THE LOUIE NUNN CUMBERLAND PARKWAY AT KY-249 IN GLASGOW(18CCN) | U | SPP | 2022 | 750000 | N
|  |  |  | BOONE | 6 | 80003 | 6-80003 | US 42 | US | 42 |  |  | 13.802 | 14.16 | RELIABILITY | RECONSTRUCTION(O) | INCREASE CAPACITY AND REDUCE CONGESTION ON US 42 AT I 71/75(18CCN) | D | SPP | 2019 | 650000 | Y
|  |  |  | BULLITT | 5 | 150.5 | 5-150.5 | KY 44 | KY | 44 |  | 0.5 | 22.8 | 23.25 | SAFETY | RECONSTRUCTION(O) | SECTION 5 - FROM US-31EX TO US-31E BYPASS. (2008BOPC). | D | SPP | 2019 | 1000000 | N
|  |  |  | GARRARD | 7 | 196.3 | 7-196.3 | US 27 | US | 27 |  | 5.132 | 5.199 | 10.331 | RELIABILITY | RELOCATION(O) | IMPROVE US-27 FROM WEST LANCASTER BYPASS TO KY-34. (2006BOPC) (16CCN)(18CCR) | D | SPP | 2019 | 500000 | Y
|  |  |  | GARRARD | 7 | 196.3 | 7-196.3 | US 27 | US | 27 |  | 5.132 | 5.199 | 10.331 | RELIABILITY | RELOCATION(O) | IMPROVE US-27 FROM WEST LANCASTER BYPASS TO KY-34. (2006BOPC) (16CCN)(18CCR) | R | SPP | 2020 | 10000000 | Y
|  |  |  | GARRARD | 7 | 196.3 | 7-196.3 | US 27 | US | 27 |  | 5.132 | 5.199 | 10.331 | RELIABILITY | RELOCATION(O) | IMPROVE US-27 FROM WEST LANCASTER BYPASS TO KY-34. (2006BOPC) (16CCN)(18CCR) | U | SPP | 2021 | 9000000 | Y
|  |  |  | GARRARD | 7 | 196.3 | 7-196.3 | US 27 | US | 27 |  | 5.132 | 5.199 | 10.331 | RELIABILITY | RELOCATION(O) | IMPROVE US-27 FROM WEST LANCASTER BYPASS TO KY-34. (2006BOPC) (16CCN)(18CCR) | C | SPP | 2022 | 38000000 | Y
|  |  |  | GRAVES | 1 | 181.5 | 1-181.5 | KY 80 | KY | 80 |  | 2.8 |  |  | RELIABILITY | NEW ROUTE(O) | MURRAY-MAYFIELD RD; EXTEND MAYFIELD SOUTHERN BYPASS FROM KY-303 SOUTH OF MAYFIELD, NORTHWEST TO JULIAN M. CARROLL PARKWAY (PURCHASE PARKWAY). (EXTENSION OF 1-181.30)(00CCR)(12CCR)(14CCR)(18CCR) | C | SPP | 2020 | 7280000 | N
|  |  |  | GRAVES | 1 | 181.51 | 1-181.51 | KY 80 | KY | 80 |  | 2.8 |  |  | RELIABILITY | PREFINANCD CONVRSN(O) | MURRAY-MAYFIELD RD; EXTEND MAYFIELD SOUTHERN BYPASS FROM KY-303 SOUTH OF MAYFIELD, NORTHWEST TO JULIAN M. CARROLL PARKWAY (PURCHASE PARKWAY). (EXTENSION OF 1-181.30)(00CCR)(12CCR)(14CCR)(18CCR) | C | SPP | 2021 | 7280000 | N
|  |  |  | GRAYSON | 4 | 8954 | 4-8954 | KY 3155 | KY | 3155 |  |  |  |  | NEW ROUTES | NEW ROUTE(O) | EXTEND THE WILLIAM THOMASON BYWAY (KY 3155) FROM THE SOUTHERN INTERSECTION AT KY 259 WESTERLY TO KY 54. (16CCN)(18CCN) | R | SPP | 2021 | 2500000
|  |  |  | GRAYSON | 4 | 8954 | 4-8954 | KY 3155 | KY | 3155 |  |  |  |  | NEW ROUTES | NEW ROUTE(O) | EXTEND THE WILLIAM THOMASON BYWAY (KY 3155) FROM THE SOUTHERN INTERSECTION AT KY 259 WESTERLY TO KY 54. (16CCN)(18CCN) | U | SPP | 2021 | 1500000
|  |  |  | GRAYSON | 4 | 8954 | 4-8954 | KY 3155 | KY | 3155 |  |  |  |  | NEW ROUTES | NEW ROUTE(O) | EXTEND THE WILLIAM THOMASON BYWAY (KY 3155) FROM THE SOUTHERN INTERSECTION AT KY 259 WESTERLY TO KY 54. (16CCN)(18CCN) | C | SPP | 2022 | 14500000
|  |  |  | JEFFERSON | 5 | 323.01 | 5-323.01 | KY 1931 | KY | 1931 |  | 2.6 | 0.54 | 3.148 | RELIABILITY | MAJOR WIDENING(O) | WIDEN GREENWOOD ROAD FROM GREENBELT HWY TO DIXIE HWY (US-31W) (3-LANE IMPROVEMENT) FROM MP 0.54 TO MP 3.148. (98CCR)(R-04DEOB)(04CCR)(BOP2006P)(10CCR)(12CCR) | C | SPP | 2022 | 4860000 | N
|  |  |  | JEFFERSON | 5 | 8908 | 5-8908 | KY 155 | KY | 155 |  |  | 4.4 | 5.75 | RELIABILITY | MINOR WIDENING(O) | WIDEN TAYLORSVILLE ROAD TO 3 LANES FROM I-265 TO KY-148. (18CCN) | P | SPP | 2019 | 915000 | N
|  |  |  | JEFFERSON | 5 | 8908 | 5-8908 | KY 155 | KY | 155 |  |  | 4.4 | 5.75 | RELIABILITY | MINOR WIDENING(O) | WIDEN TAYLORSVILLE ROAD TO 3 LANES FROM I-265 TO KY-148. (18CCN) | D | SPP | 2020 | 1495000 | N
|  |  |  | JEFFERSON | 5 | 8908 | 5-8908 | KY 155 | KY | 155 |  |  | 4.4 | 5.75 | RELIABILITY | MINOR WIDENING(O) | WIDEN TAYLORSVILLE ROAD TO 3 LANES FROM I-265 TO KY-148. (18CCN) | R | SPP | 2022 | 1000000 | N
|  |  |  | JEFFERSON | 5 | 8908 | 5-8908 | KY 155 | KY | 155 |  |  | 4.4 | 5.75 | RELIABILITY | MINOR WIDENING(O) | WIDEN TAYLORSVILLE ROAD TO 3 LANES FROM I-265 TO KY-148. (18CCN) | U | SPP | 2022 | 500000 | N
|  |  |  | JEFFERSON | 5 | 8952 | 5-8952 | US 60 | US | 60 |  | 0.396 | 14.718 | 15.114 | RELIABILITY | MINOR WIDENING(O) | WIDEN US-60 TO THREE LANES FROM EASTWOOD CUTOFF (MP 14.7) TO ROCKCREST WAY (MP 15.1). (LOCALS WILL DO DESIGN FOR $330,000). (16CCN)(18CCR) | R | SPP | 2019 | 410000 | N
|  |  |  | JEFFERSON | 5 | 8952 | 5-8952 | US 60 | US | 60 |  | 0.396 | 14.718 | 15.114 | RELIABILITY | MINOR WIDENING(O) | WIDEN US-60 TO THREE LANES FROM EASTWOOD CUTOFF (MP 14.7) TO ROCKCREST WAY (MP 15.1). (LOCALS WILL DO DESIGN FOR $330,000). (16CCN)(18CCR) | U | SPP | 2020 | 460000 | N
|  |  |  | JEFFERSON | 5 | 8952 | 5-8952 | US 60 | US | 60 |  | 0.396 | 14.718 | 15.114 | RELIABILITY | MINOR WIDENING(O) | WIDEN US-60 TO THREE LANES FROM EASTWOOD CUTOFF (MP 14.7) TO ROCKCREST WAY (MP 15.1). (LOCALS WILL DO DESIGN FOR $330,000). (16CCN)(18CCR) | C | SPP | 2021 | 1000000 | N
|  |  |  | JEFFERSON | 5 | 80000 | 5-80000 | KY 1531 | KY | 1531 |  | 0.2 | 8.1 | 8.3 | RELIABILITY | NEW INTERCHANGE(O) | EASTWOOD FISHERSVILLE CONNECTOR TO I-64 (18CCN) | P | SPP | 2019 | 750000 | N
|  |  |  | JEFFERSON | 5 | 80001 | 5-80001 | US 60 | US | 60 |  | 0.591 | 11.093 | 11.684 | RELIABILITY | MAJOR WIDENING(O) | WIDEN US-60 TO 6 LANES FROM OLD SHELBYVILLE RD. TO NORTH ENGLISH STATION RD.(18CCN) | D | SPP | 2019 | 1255000 | Y
|  |  |  | JEFFERSON | 5 | 80001 | 5-80001 | US 60 | US | 60 |  | 0.591 | 11.093 | 11.684 | RELIABILITY | MAJOR WIDENING(O) | WIDEN US-60 TO 6 LANES FROM OLD SHELBYVILLE RD. TO NORTH ENGLISH STATION RD.(18CCN) | R | SPP | 2021 | 550000 | Y
|  |  |  | JEFFERSON | 5 | 80001 | 5-80001 | US 60 | US | 60 |  | 0.591 | 11.093 | 11.684 | RELIABILITY | MAJOR WIDENING(O) | WIDEN US-60 TO 6 LANES FROM OLD SHELBYVILLE RD. TO NORTH ENGLISH STATION RD.(18CCN) | U | SPP | 2022 | 720000 | Y
|  |  |  | JEFFERSON | 5 | 80003 | 5-80003 | [7 empty] | NEW ROUTES | NEW ROUTE(O) | EXTEND PLANTSIDE DRIVE FROM REHL ROAD TO TAYLORSVILLE ROAD(18CCN) | D | SPP | 2020 | 750000 | N
|  |  |  | JEFFERSON | 5 | 80006 | 5-80006 | KY 841 | KY | 841 |  | 0.5 | 9.1 | 9.6 | RELIABILITY | SPOT IMPROVEMENTS(O) | CONSTRUCT NEW INTERCHANGE ON KY-841 AT THE RENAISSANCE SOUTH BUSINESS PARK(18CCN) | C | SPP | 2021 | 12500000 | N
|  |  |  | KENTON | 6 | 162.3 | 6-162.3 | KY 536 | KY | 536 |  | 1.481 | 1.061 | 2.542 | RELIABILITY | AIR QUALITY(P) | IMPROVE SAFETY AND REDUCE CONGESTION ON KY-536 FROM KY 1303 TO WILLIAMSWOOD ROAD/CALVARY DRIVE (PRIORITY SECTION 2). DESIGN PHASE UNDER PARENT NO. 6-162.01. (2012BOP)(18CCN) | R | SPP | 2020 | 3000000 | N
|  |  |  | KENTON | 6 | 162.3 | 6-162.3 | KY 536 | KY | 536 |  | 1.481 | 1.061 | 2.542 | RELIABILITY | AIR QUALITY(P) | IMPROVE SAFETY AND REDUCE CONGESTION ON KY-536 FROM KY 1303 TO WILLIAMSWOOD ROAD/CALVARY DRIVE (PRIORITY SECTION 2). DESIGN PHASE UNDER PARENT NO. 6-162.01. (2012BOP)(18CCN) | U | SPP | 2020 | 1500000 | N
|  |  |  | KENTON | 6 | 162.3 | 6-162.3 | KY 536 | KY | 536 |  | 1.481 | 1.061 | 2.542 | RELIABILITY | AIR QUALITY(P) | IMPROVE SAFETY AND REDUCE CONGESTION ON KY-536 FROM KY 1303 TO WILLIAMSWOOD ROAD/CALVARY DRIVE (PRIORITY SECTION 2). DESIGN PHASE UNDER PARENT NO. 6-162.01. (2012BOP)(18CCN) | C | SPP | 2022 | 13500000 | N
|  |  |  | KENTON | 6 | 162.4 | 6-162.4 | KY 536 | KY | 536 |  | 1.934 | 2.542 | 4.476 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE SAFETY AND REDUCE CONGESTION ON KY-536 FROM WILLIAMSWOOD ROAD/CALVARY DRIVE TO KY-17 (PRIORITY SECTION 3). DESIGN PHASE UNDER PARENT NO. 6-162.01. (2012BOP)(18CCR) | R | SPP | 2022 | 12080000 | N
|  |  |  | LINCOLN | 8 | 80009 | 8-80009 | US 27 | US | 27 |  |  | 18.521 | 20.8 | RELIABILITY | MINOR WIDENING(O) | EXPAND US-27 TO FOUR LANES FROM THE WALMART IN STANFORD TO THE DIX RIVER(18CCN) | D | SPP | 2021 | 2100000 | Y
|  |  |  | LINCOLN | 8 | 80009 | 8-80009 | US 27 | US | 27 |  |  | 18.521 | 20.8 | RELIABILITY | MINOR WIDENING(O) | EXPAND US-27 TO FOUR LANES FROM THE WALMART IN STANFORD TO THE DIX RIVER(18CCN) | R | SPP | 2022 | 7500000 | Y
|  |  |  | MASON | 9 | 147.2 | 9-147.2 | US 68 | US | 68 |  | 2.7 |  |  | RELIABILITY | NEW ROUTE(O) | NEW FULLY CONTROLLED ACCESS ROUTE FROM US 68 NEAR WASHINGTON EAST TO KY 11 INCLUDING A NEW I-CHNG AT KY 11. (PRIORITY SECTION)(2004BOPC)(06CCR)(18CCN) | D | SPP | 2021 | 780000 | N
|  |  |  | MASON | 9 | 147.6 | 9-147.6 | US 68 | US | 68 |  | 2.9 |  |  | RELIABILITY | NEW ROUTE(O) | NEW FULLY CONTROLLED ACCESS ROUTE FROM KY 11 NORTHEAST TO KY 9 (AA HWY) INCLUDING NEW I-CHNG AT KY 9. (2004BOPC)(06CCR)(18CCN) | D | SPP | 2021 | 780000 | N
|  |  |  | MASON | 9 | 147.6 | 9-147.6 | US 68 | US | 68 |  | 2.9 |  |  | RELIABILITY | NEW ROUTE(O) | NEW FULLY CONTROLLED ACCESS ROUTE FROM KY 11 NORTHEAST TO KY 9 (AA HWY) INCLUDING NEW I-CHNG AT KY 9. (2004BOPC)(06CCR)(18CCN) | R | SPP | 2022 | 1580000 | N
|  |  |  | MASON | 9 | 147.6 | 9-147.6 | US 68 | US | 68 |  | 2.9 |  |  | RELIABILITY | NEW ROUTE(O) | NEW FULLY CONTROLLED ACCESS ROUTE FROM KY 11 NORTHEAST TO KY 9 (AA HWY) INCLUDING NEW I-CHNG AT KY 9. (2004BOPC)(06CCR)(18CCN) | U | SPP | 2022 | 1820000 | N
|  |  |  | OLDHAM | 5 | 367.2 | 5-367.2 |  |  |  |  | 2.2 |  |  | NEW ROUTES | NEW ROUTE(O) | EXTENSION OF OLD HENRY ROAD EAST TO ASH AVENUE (KY362). (12CCR)(18CCN) | C | SPP | 2021 | 10000000 | N
|  |  |  | OLDHAM | 5 | 367.21 | 5-367.21 | [7 empty] | RELIABILITY | PREFINANCD CONVRSN(O) | EXTENSION OF OLD HENRY ROAD EAST TO ASH AVENUE (KY362).(18CCN) | C | SPP | 2022 | 8500000 | N
|  |  |  | OLDHAM | 5 | 8852 | 5-8852 | KY 53 | KY | 53 |  | 2.617 | 3.068 | 5.685 | RELIABILITY | DESIGN ENGINEERING(O) | DESIGN FOR IMPROVING KY-53 FROM ZHALE SMITH ROAD TO KY-22 (TOTAL 3.2 MILES). (14CCN)(18CCN) | D | SPP | 2021 | 2000000
|  |  |  | OLDHAM | 5 | 80005 | 5-80005 | KY 329 | KY | 329 |  |  | 6.8 | 7 | SAFETY | SAFETY(P) | IMPROVE THE INTERCHANGE OF I 71 AND KY 329. (18CCN) | D | SPP | 2019 | 250000 | N
|  |  |  | TODD | 3 | 80001 | 3-80001 | US 79 | US | 79 |  |  | 0 | 3 | RELIABILITY | MINOR WIDENING(O) | US 79 WIDENING FROM MP 0 TO MP 3. (18CCN) | D | SPP | 2019 | 1200000 | Y
|  |  |  | TODD | 3 | 80001 | 3-80001 | US 79 | US | 79 |  |  | 0 | 3 | RELIABILITY | MINOR WIDENING(O) | US 79 WIDENING FROM MP 0 TO MP 3. (18CCN) | R | SPP | 2021 | 2000000 | Y
|  |  |  | TODD | 3 | 80001 | 3-80001 | US 79 | US | 79 |  |  | 0 | 3 | RELIABILITY | MINOR WIDENING(O) | US 79 WIDENING FROM MP 0 TO MP 3. (18CCN) | U | SPP | 2021 | 3000000 | Y
|  |  |  | TODD | 3 | 80001 | 3-80001 | US 79 | US | 79 |  |  | 0 | 3 | RELIABILITY | MINOR WIDENING(O) | US 79 WIDENING FROM MP 0 TO MP 3. (18CCN) | C | SPP | 2022 | 8000000 | Y
|  |  |  | WARREN | 3 | 199 | 3-199 | US 31W | US | 31 | W | 2.6 | 4.1 | 6.7 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE US-31W FROM SOUTH OF KY-242 TO DILLARD ROAD.(12CCR) | C | SPP | 2022 | 2880000 | N
|  |  |  | WARREN | 3 | 8857 | 3-8857 | US 31W | US | 31 | W | 1.256 | 10.561 | 11.817 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE US-31W FROM CAMPBELL LANE (US-231) TO UNIVERSITY BOULEVARD (US-231X). (14CCN)(16CCR)(18CCR) | R | SPP | 2019 | 1750000
|  |  |  | WARREN | 3 | 8857 | 3-8857 | US 31W | US | 31 | W | 1.256 | 10.561 | 11.817 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE US-31W FROM CAMPBELL LANE (US-231) TO UNIVERSITY BOULEVARD (US-231X). (14CCN)(16CCR)(18CCR) | U | SPP | 2019 | 2000000
|  |  |  | WARREN | 3 | 8857 | 3-8857 | US 31W | US | 31 | W | 1.256 | 10.561 | 11.817 | RELIABILITY | MAJOR WIDENING(O) | IMPROVE US-31W FROM CAMPBELL LANE (US-231) TO UNIVERSITY BOULEVARD (US-231X). (14CCN)(16CCR)(18CCR) | C | SPP | 2022 | 4250000