## Plans
Mountain Parkway 10-126.6
Document Changes Log
Preliminary Plans to Final Plans
| Sheet Number | Reason for change | Drawing Sheet Title | Description of Changes
Changes From Preliminary to Final
ROADWAY | R2g | Cont. Proc. Quest #4 (1) | GENERAL SUMMARY | Change Note 10 to reference General Note Sheet No. R2p
|  | Cont. Proc. Question #14 | GENERAL SUMMARY | Remove Note 18 concerning signs, walls, etc.
| R2h | Cont. Proc. Quest #4 (1) | GENERAL SUMMARY | Change Note 10 to reference General Note Sheet No. R2p
|  | Cont. Proc. Question #14 | GENERAL SUMMARY | Remove Note 18 concerning signs, walls, etc.
|  | Update | GENERAL SUMMARY | Item No. 2898 Relocate Crash Cushion Changed from 4 to 8 EACH
|  | Update | GENERAL SUMMARY | Item No. 2898 Relocate Crash Cushion (PERM) Eliminated
|  | Update | GENERAL SUMMARY | Item No. 20318ES508 Relocate Barrier Wall Changed from 1,740 to 3,500 Lin Ft.
|  | Update | GENERAL SUMMARY | Item No. 20318ES508 Relocate Barrier Wall (PERM) Eliminated
|  | Cont. Proc. Quest. #15 b) | GENERAL SUMMARY | Item No. 22664EN Water Blast Existing Stripe Eliminated
|  | Update | GENERAL SUMMARY | Items 23791EC, 24489EC, and 24530ED moved from Sheet R2i
| R2i | Cont. Proc. Quest #4 (1) | GENERAL SUMMARY | Change Note 10 to reference General Note Sheet No. R2p
|  | Cont. Proc. Question #14 | GENERAL SUMMARY | Remove Note 18 concerning signs, walls, etc.
|  | Update | GENERAL SUMMARY | Items 23791EC, 24489EC, and 24530ED moved to Sheet R2h
| R2o | Cont. Proc. Quest. #10 & #13 | GENERAL NOTES | Removed clearing and grubbing note. Added headwall removal note.
| R2p | Cont. Proc. Question #14 | GENERAL NOTES | Remove Relocate Barrier Wall and Crash Cushion Note
|  | Cont. Proc. Quest #4 (1) | GENERAL NOTES | Add Retaining Wall -KY 9009 Over KY 134 West Note
| R91 | Update | MTN PKWY MOT PH 4 STA 3060+00 to 3075+00 | Remove Notes for Concrete Barrrier Wall, Crash Cushion and Tubular Markers to Remain in Place
| R92 | Update | MTN PKWY MOT PH 4 STA 3075+00 to 3090+00 | Remove Notes for Concrete Barrrier Wall and Crash Cushion to Remain in Place
| R93 | Update | MTN PKWY MOT PH 4 STA 3210+00 to 3225+00 | Remove Notes for Concrete Barrrier Wall and Crash Cushion to Remain in Place
| R94 | Update | MTN PKWY MOT PH 4 STA 3210+00 to 3225+00 | Remove Notes for Concrete Barrrier Wall and Crash Cushion to Remain in Place
| R64 | FHWA Comment #3 | MTN PKWY MOT PH 1 STA 3090+00 to 3105+00 | Changed Arrow at 3092+00 to point to douuble yellow stripes
| R100 | FHWA Comment #4 | MOT STRIPING PLAN STA 3135+00 TO 3150+00 | Changed description from 6" double yellow stripes to 6"skipped white stripes
STRUCTURES | Drawing No. 27512
| S2 | Update | GENERAL NOTES | Removed Geotechnical Note
Drawing No. 27530
| S2 | Update | GENERAL NOTES | Removed Geotechnical Note
Drawing No. 27602
| S2 | Update | GENERAL NOTES | Removed Geotechnical Note
Drawing No. 27603
| S2 | Update | GENERAL NOTES | Removed Geotechnical Note and Existing Bridge Drawing Number
Drawing No. 27604
| S2 | Update | GENERAL NOTES | Removed Geotechnical Note and Existing Bridge Drawing Number
TRAFFIC
| T1 | Update | SIGNING QUANTITY SHEET | Bid Item No. 6407 0.125 gauge changed from 664 SF to 650 SF
| T9 | Update | MOUNTAIN PARKWAY INTER. SIGN. SHEET | Relabel prohibeted right turn signs S-21 to S-33
| T21 | Update | SHEETING SIGN DETAIL SHEET | S-2 and S-3 M3-2 changes from 24"X12" to 36"X18"
| T22 | Update | SHEETING SIGN DETAIL SHEET | S-14, S-18, S-22, S-23, S-24 shield sign changes from 48"X60" to 24"X30"
| T23 | Update | SHEETING SIGN DETAIL SHEET | S-29 shield sign changes from 48"X60" to 24"X30"

## Special Notes
Mountain Parkway 10-126.6
Contract Document Changes Log
Preliminary to Final Special Notes
| Reason for Change | Special Note Title | Description of Changes
Changes From Preliminary Plans (posted October) to Final Plan (advertised November 18)
SPECIAL NOTES | Contract Procurement Q12 | Special Note For Excess Materials Site | Erosion Control Devices and Seeding & Protection will be paid at the contract unit bid prices.
| Contract Procurement Q4(1) | Special Note for MSE Retaining Walls | Added note