## Plans
Mountain Parkway 10-126.7
Document Changes Log
Preliminary Plans to Final Plans
| Sheet Number | Reason for change | Drawing Sheet Title | Description of Changes
Changes From Preliminary to Final
ROADWAY | R2G | Update | General Summary | Bid Item 02562 Temporary Signs quantity changed. Wolfe Co. 746 sf to 734 sf Morgan Co. no change Total 924 sf to 912 sf
| R64 | Update | MOT Plan Quantities | Change temporary sign quantities. Same as above.
| R84 | Update | Phase II MOT Sheet Sta 105+59.89 to Sta. 130+00 | Removed "Exit Open" sign placard. Changed Note "…Signal Heads shall be a minimum of 53' beyond the stop bar…"
| R2F | Update | General Summary | Add Bid Item "2475 Plug Water Well Each 1". Add Bid Item "2731 Remove Structure - Parcel 26 (Well House)
| R2G | Cont.Proc. Question #16 | General Summary | Removed Bid Item 20667ED Pneumatic Backstowing
STRUCTURES | 27079 S1 | Cont.Proc. Question #5 (2) | Title Sheet | Changed Bid Item 20746ED Rock Corings from 96 lf to 276 lf. No quantity changes required for rock coring for 27081 & 27082.
| 27084 S2 | Cont.Proc. Question #4 (2) | Outlet Barrel Details | Added finished grade / original ground profile
| 27085 S3 | Cont.Proc. Question #4 (2) | Outlet Details | Added finished grade / original ground profile
| 27086 S2 & S3 | Cont.Proc. Question #4 (2) | Inlet Barrel Details | Added finished grade / original ground profile
TRAFFIC | T11 | FHWA #3 | MT PKWY Signing & Striping Plan Sta 203+00 to Sta 215+00 | Relabed the west bound direction edge line pavement stripes
| T12 | FHWA #3 | MT PKWY Signing & Striping Plan Sta 215+00 to Sta 227+00 | Relabed the west bound direction edge line pavement stripes

## Special Notes
Mountain Parkway 10-126.7
Contract Document Changes Log
Preliminary to Final Special Notes
| Reason for Change | Special Note Title | Description of Changes
Changes From Preliminary Plans (posted October) to Final Plans (advertised November 18)
SPECIAL NOTES | Update | Special Note for Maintenance of Traffic | Changed the temporary signal to pole mounted with in-ground detection loops
| Contract Procurement Q12 | Special Note For Excess Materials Site | Erosion Control Devices and Seeding & Protection will be paid at the contract unit bid prices.
| Contract Procurement Q9a | CAP Report | Changed the tree clearing restriction dates to April 1 to October 14