## Slide 1: The Cumberland Gap Tunnel Fast Track Pavement Replacement
History and Repair

## Slide 2: History Review
Original highway constructed in 1916
Replaced a 2.3 mile section of US 25E known as Massacre Mountain
NPS accredited with the first discussion of a tunnel in 1956
Following geological studies and surviving funding issues, excavation of a pilot tunnel began in 1985 with construction to follow on the NB Tunnel on June 21, 1991

## Slide 3: History Review
CGT was completed at a cost of $280M
CGT opened to traffic on October 18, 1996
Current AADT of 22,400
Total length: 4600 feet
Height: 30 feet
Width: 36 feet
Number of lanes: 4
http://cgtunnel.com

## Slide 4: What we didn’t see…

## Slide 5: What we discovered…
The Pilot Tunnel took two years to drill
Caverns as tall as 85 ft
A lake of water 30 ft deep
Springs produce approximately 450 GPM of water regardless of weather

## Slide 6: What we did…
Line each bore with a PVC membrane covered with 10” concrete
Install 15” groundwater drains isolated from the 12” roadway drains

## Slide 7: What we designed…

## Slide 8: Problem solved…

## Slide 9: A New Challenge…
2001 – CGTA requested a pavement inspection due to possible slab settlement in the SB tunnel
2002 – URETEK foam was injected into the settled areas
2005 – GPR was used to locate voids beneath the pavement

## Slide 10: A New Challenge…
What happened to the subgrade…

## Slide 11: A New Challenge…
Calcium deficient groundwater dissolved the limestone base

## Slide 12: 2007 Project Information
CID | 072280
Contract Amount | $786,098.62
County | Bell
Project Number | FD04 007 025E 000-001
Work Type | Bridge Repairs
Prime | Bluegrass Contracting Corporation

## Slide 13: 2007 Repair Area…
CGT Repair Locations |  |  |  |  |  | 
Location | Station |  | Dimensions |  |  | 
 | From | To | Length (FT) | Width (FT) | Area (SQ FT) | Area (SQ YD)
Completed in 2007 |  |  |  |  |  | 
SB | 122+17 | 123+37 | 120 | 30 | 3,600 | 400

## Slide 14: 2007 Photo…

## Slide 15: The Solution and Result…
The solution…replace the limestone with inert granite
Consisted of replacing 400 SY of pavement and subgrade
Constructed a concrete dam to control / prevent migration of the aggressive water
Resulted in approximate 6 week complete closure of the SB Bore

## Slide 16: 2012 Project Information
CID | 111052
Contract Amount | $1,523,316.10
County | Bell
Project Number | STP 0251 (028)
Work Type | Grade & Drain with PCC Pavement
Prime | Hinkle Contracting Company, LLC

## Slide 17: 2012 Repair Area…
CGT Repair Locations |  |  |  |  |  | 
Location | Station |  | Dimensions |  |  | 
 | From | To | Length (FT) | Width (FT) | Area (SQ FT) | Area (SQ YD)
Completed in 2012 |  |  |  |  |  | 
SB | 121+83 | 122+27 | 44 | 30 | 1,320 | 147
SB | 127+37 | 129+32 | 195 | 30 | 5,850 | 650
SB | 137+82 | 140+00 | 218 | 30 | 6,540 | 727
NB | 120+46 | 123+36 | 290 | 30 | 8,700 | 967
NB | 126+78 | 129+03 | 225 | 30 | 6,750 | 750
NB | 134+76 | 139+52 | 476 | 30 | 14,280 | 1,587

## Slide 18: The Result…
Consisted of replacing 4,827 SY of pavement and subgrade
Constructed concrete dams to control / prevent migration of the aggressive water
Resulted in approximately 4.5 months of alternating closures of the NB and SB Bores

## Slide 19: 2014 Project Information
CID | 141009
Contract Amount | $3,488,000.00
County | Bell
Project Number | FD04 SPP 007 025E 000-001
Work Type | JPC Pavement Repairs
Prime | MAC Construction & Excavating

## Slide 20: 2014 Repair Area…
CGT Repair Locations |  |  |  |  |  | 
Location | Station |  | Dimensions |  |  | 
 | From | To | Length (FT) | Width (FT) | Area (SQ FT) | Area (SQ YD)
Completed in 2014 |  |  |  |  |  | 
NB | 118+99 | 120+46 | 147 | 30 | 4,410 | 490
NB | 123+36 | 126+78 | 342 | 30 | 10,260 | 1,140
NB | 129+03 | 134+76 | 573 | 30 | 17,190 | 1,910
NB | 139+52 | 143+50 | 398 | 30 | 11,940 | 1,327
SB | 118+55 | 121+83 | 328 | 30 | 9,840 | 1,093
SB | 123+37 | 127+37 | 400 | 30 | 12,000 | 1,333
SB | 129+32 | 137+82 | 850 | 30 | 25,500 | 2,833
SB | 140+00 | 143+50 | 350 | 30 | 10,500 | 1,167

## Slide 21: Project Details…
Anticipated 180 days
August 19, 2014 - Fixed Completion Date for bore closures
October 1, 2014 – Overall Fixed Completion Date

## Slide 22: Project Details…
Consisted of replacing 11,293 SY of pavement and subgrade
A+B Bid to encourage fast track construction and limit disruption to traffic
Resulted in approximate 34 days of alternating closures of the NB and SB Bores

## Slide 23: 2014 Bid Amounts
Company | Total
MAC Construction | $ 3,488,000.00
Bluegrass Construction | $ 3,849,988.25
Hinkle Contracting | $ 4,284,150.66

## Slide 24: 2014 Project Days
Company | Quantity | Days | Total
Hinkle Contracting | $ 5,000.00 | 150 | $ 750,000.00
Bluegrass Construction | $ 5,000.00 | 140 | $ 700,000.00
MAC Construction | $ 5,000.00 | 30 | $ 150,000.00

## Slide 25: How fast is fast?
Notes: Everyone wants fast!

## Slide 26: 2014 Project Timeline
Project Dates | 
Letting | 01/10/14
Award | 01/14/14
Notice to Proceed | 02/19/14
Work Began | 02/21/14
Work Completed | 08/19/14

## Slide 27: Approach…
Vision
Prepare
Implement
Challenge

## Slide 28: Stockpile Material
Granite deliveries began on March 3, 2014
More than 21,000 Tons of Granite

## Slide 29: Dewatering Plan

## Slide 30: Aluminum Chloride Treatment

## Slide 31: Pre-Mark for Sawing
Notes: 6’ X 6’ sections

## Slide 32: Sawed Pavement

## Slide 33: Slab Removal

## Slide 34: Water Filled Excavation

## Slide 35: Water Pump
Notes: Diesel Trash pump (1 of 3 on site) used to remove groundwater. 790 GPM via 6” HDPE Fused Pipe.

## Slide 36: Granite Refill
Notes: 12” HDPE Pipe to daylight into existing groundwater drains.

## Slide 37: Bidwell Finishing Machine

## Slide 38: Telebelt Conveyor System

## Slide 39: Telebelt Conveyor System

## Slide 40: Poor Curing Compound Coverage

## Slide 41: Additional Work Items…
Diamond Grinding
Re-sealing Joints
Upgraded Crash Cushions
New RPM’s

## Slide 42: Project Survival…
7 Claims - $120k Administrative Settlement
High Turbidity From Groundwater
NOV Settlement