## Slide 1: Special Note for Railroad flagging “A+B” Bidding
2014 Section Engineer’s Meeting

## Slide 2: RR Flagging Background
Paid by the Contractor
  Buried in the Construction costs
RR’s had no agreement with Contractor
  Disputes were difficult
Norfolk Southern has been an exception
  We’ve always paid them directly
RR’s asked that we pay

## Slide 3: KYTC now pays for Flagging
Shifted costs from Construction to Utilities
Flagging bills paid by District Utilities Agent
Contractor’s Acceptance Form
Potential issues
  KYTC estimates flagging days
  Blank Check
    Could run up costs quickly
    No incentive to maximize flagging efficiency

## Slide 4: Example problems
District 1
  Flagging estimate very low
    Change orders ($76,950.00; $67,200.00)
  Contractor reportedly said he would have been more selective if he was paying
District 6
  Hints of problems
    Multiple projects including different RR’s
      Change Orders, questions about flagging time, etc.

## Slide 5: A + B Bidding
“A” value: contract bid amount
“B” value: flagging costs
  Number of days times set flagging daily rate
Estimated Calendar days for flagging
  Guidelines in Special Provisions for Protection of RR Interest, aka, “RR notes”
  Multiple flaggers count as multiple days
Daily Rate
  Found in Summary for KYTC Projects That Involve a Railroad, aka, “Project Summary Sheet” in proposal

## Slide 6: Additional Details
KYTC Construction keeps track of days
Change Orders may add to “B” value if justified
If under “B” value, we pay Contractor
If over “B” value, Contractor owes us

## Slide 7: What This Means For Inspector
Keep Track of Railroad Flagger’s Time
  Hours on site for each flagger
Charge Day For Each Flagger Present 5 Hours Minimum
Do Not Charge Day if Contractor Cannot Perform at Least 5 Hours of the Work That Necessitates Flagging
  Based on Weather, Seasonal, or Temperature Limitations
  Railroad will define when flagging is required and how many flaggers are required

## Slide 8: What This Means For Section Engineer
Keep Record of Flagger Calendar Days
  When flagging operations started/ended
  Which days were charged or not charged and why
Statements Will be Furnished Bi-Weekly
  Days charged for the period
  Total days charged through that date
  Number of days remaining
Contractor Has 14 Days to Protest
  Protest must be written and contain supporting evidence

## Slide 9: Payment
“B” Value May Be Increased by Change Order
  If the nature of the work requires extra flagging time
  It may not be reduced
Pay Item is Railroad Flagging
  Pay Unit is Day
If Calendar Days of Flagging < “B”
  Contractor is to be paid for remaining days (positive pay item) once Formal is received
If Calendar Days of Flagging > “B”
  Contractor is to be charged for extra days (negative pay item) until Formal is received

## Slide 10: Conclusion
Suggestions/Comments/Questions
  Still finalizing note