## Slide 1: PROJECT ADULTHOOD
ALL GROWN UP
Matt Looney
Section Engineer’s Meeting Spring 2014

## Slide 2: CHANGE ORDERS
You get to hear about this is the next presentation by BOB!

## Slide 3: MYLARS & CONSTRUCTION REVISIONS
WHEN IS A CONSTRUCTION REVISION NECESSARY
  RIGHT-OF-WAY CHANGE
  TYPICAL SECTION CHANGE
  MAJOR DESIGN FEATURE CHANGE
MYLARS No Longer Required
REVISION NEEDS TO COME WITH DRAFT CHANGE ORDER
GUIDANCE MANUAL CST-301

## Slide 4: CLAIMS
WHY CAN’T WE ALL JUST GET ALONG 

## Slide 5: CLAIMS
SPECIFICATION 105.13 & CONSTRUCTION ENGINEER RESOURCE CENTER ON WEB
IF THERE IS AN IMPASSE, ADVISE CONTRACTOR THE CLAIMS PROCESS IS AVAILABLE
RESPOND WITHIN SPECIFIED TIMEFRAME TO NOTICE OF CHANGED CONDITION
CONTRACTOR IS RESPONSIBLE FOR TRACKING WORK
  SECTION ENGINEER PROVIDES FORM TC 63-11 PER SECTION 109.04.02 E
  SECTION ENGINEER SHOULD CHECK AND SIGN EACH DAY
    THIS IS HOW THE DEPARTMENT WILL ULTIMATELY CHECK ANY SUBMITTED CLAIM
IF A FORMAL CLAIM IS SUBMITTED, IT MUST BE EVALUATED ACCORDING TO SECTION 105.13 AND GUIDANCE MANUAL CST 311

## Slide 6: VALUE ENGINEERING
CID XX-XXXX, project. A project barely buildable. Cabinet, we can build it better. We have the technology. We have the capability to build Kentucky's first bionic project. CID XX-XXXX will be that project. Better than it was before. Better, stronger, faster.

## Slide 7: VALUE ENGINEERING
SEE SPECIFICATION SECTION 111 & GUIDANCE MANUAL SECTION CST 312
ENSURE ALL INFORMATION REQUIRED BY SECTION 111.03.01 IS IN SUBMITTAL
  DETAILED DESCRIPTION OF WORK & CHANGES
  COMPLETE SET OF PLANS & CONSTRUCTION DETAILS
  DETAILED COST ESTIMATE FOR WORK PERFORMED UNDER EXISTING CONTRACT & PROPOSED CHANGE INCLUDING BREAKDOWN OF PRICING FOR LABOR, EQUIPMENT, MATERIALS, ETC.
  DETAILED COST ESTIMATE FOR NON-CONTRACT ITEMS
  DETAILED CHANGES IN FUTURE COSTS TO CABINET
  WHAT EFFECT VE WILL HAVE ON PROJECT COMPLETION DATE
DISTRICT REVIEWS VE PER SECTION 111.03.03

## Slide 8: VALUE ENGINEERING
District submits Value Engineering proposal to Central Office Construction for Review (With District Recommendation).
Director of Construction makes decision as to whether or not to accept VECP and informs Contractor by Letter.
If approved, a change order will be processed to pay Contractor.

## Slide 9: PROGRESS ESTIMATES
SHOW ME THE MONEY!!

## Slide 10: PROGRESS ESTIMATES
CHECK AND RESOLVE ANY DISCREPANCIES
SEE GUIDANCE MANUAL CST 302
MUST BE CHECKED BEFORE BEING APPROVED
CHECK FUNDING LINES FOR ANY FLAGS BEFORE APPROVING
$
$
$
$

## Slide 11: SECTION ENGINEER PUNCHLIST
ARE WE DONE YET?

## Slide 12: SECTION ENGINEER PUNCHLIST
REFER TO SPECIFICATION SECTION 105.12
DURING LIFE OF PROJECT, PROVIDE WRITTEN LIST OF CORRECTIVE WORK TO CONTRACTOR AND UPDATE AS NEEDED.
  MAKE SURE CONTRACTOR UNDERSTANDS PROJECT WILL NOT BE CALLED COMPLETE UNTIL SECTION ENGINEER’S LIST IS COMPLETE
  WHEN WEATHER OR OTHER “COMPELLING” REASONS EXIST, SECTION ENGINEER CAN CALL PROJECT COMPLETE BEFORE PUNCHLIST IS COMPLETE AND LET ITEMS CARRY OVER TO FINAL INSPECTION REPORT.
IF USED PROPERLY, THE SECTION ENGINEER PUNCHLIST SHOULD GREATLY LIMIT THE LIST OF CORRECTIVE WORK INCLUDED ON FINAL INSPECTION REPORT

## Slide 13: WORK COMPLETION NOTICE
“THIS IS THE END”

## Slide 14: WORK COMPLETION NOTICE
SPECIFICATION SECTION 105.12
Generated from PROCESS LIST in SITEMANAGER
DATES ARE AUTO-FILLED IN FROM KEY DATES
  COMPLETE KEY DATES IN SM BEFORE GENERATING REPORT
SEND COMPLETION NOTICE TO CONTRACTOR, DISTRICT TEBM FOR PD&P AND CENTRAL OFFICE LIAISON
  SEE CONSTRUCTION MEMO 02-10
REPORT INCLUDES TYPES OF INSPECTIONS NEEDED
  TYPE “YES” IN SM NEXT TO ALL TYPES OF INSPECTIONS REQUIRED

## Slide 15: QUESTIONS?
Contact Info
Matt.Looney@ky.gov
(502) 564-4780