## Slide 1: KY 11 Bridge Replacement Project
Scope of Project
Replace the Existing 2 lane Daniel Boone Drive Bridge with a 3 Lane Structure.
Objectives
Increase Bridge Radii to allow trucks better access to downtown Barbourville
Add additional lane to improved traffic flow out of Barbourville
Construct bride that will keep the Historic Heritage of Barbourville
  Daniel Boone
  Dr. Thomas Walker

## Slide 2: Proposed Plan to address Barbourville’s Historic Heritage
Aesthetic Treatment on Barrier Walls using Form Liners
  Greenstreak architectural form liners
    Pattern 330 (Ashlar Stones)
Concrete Stain and Sealer
  List of approved materials
  Sherwin Williams
    SWD DOT Bridge and Highway Concrete Sealer B97 Series
  or Pittsburg Paints
    Perma-Crete Vertical Concrete Stain
  Yellow Sand
    Federal Standard 595B Color Number 30400 (AKA Thousand Island Dressing)
Mock-up Wall
  12 feet long
  Constructed on site
  Used to experiment with stain color and application methods and to verify suitability.
Findings
  Specified Stain did not meet the Historical look that the Department and the City of Barbourville was looking for.

## Slide 3: Revised Plan to address Barbourville’s Historic Heritage
Try to find a stain that would provide a more natural stone look.
Looked at several alternatives
Scofield Systems
  Lithochrome Chemstain
    Chemical Stain that reacted with the concrete to alter the color of the concrete

## Slide 4: Revised Plan to address Barbourville’s Historic Heritage
Scofield System (Lithochrome Chemstain) provide the most natural stone appearance.
Both State and City Officials were please with the look.

## Slide 5: Challenges in Revising Plan to address Barbourville’s Historical Heritage
Scofield product was not on list of approved materials.
Had not been used on any Highway Projects in the state.
Contractor was concerned that it was much more labor intensive than the planned stain and was concerned about the hazards of handling the acid stain.
Would we use one color or try several colors.
Department was worried about how rubbing and patching would alter the color.

## Slide 6: Application
Department chose to go with a base color and use the other colors to stain individual stones an alternate color.
  4 Colors Selected
    Antique Amber
    Faded Terracotta
    Padre Brown
    Dark Walnut
Padre Brown selected as the base color and remaining 3 colors were used to add character.
Every 6th stone was stained by hand application with random pattern.
Two applications of Cureseal – W over the acid stain.

## Slide 7: Lessons Learned
Cold Weather
  Dying time
  Concrete maintained moisture longer.
  Could have contributed to hazing.
Application
  PPE Required
  High Viscosity
    Contributed to runs
Cureseal W Application.
  Airless sprayer.
Could not apply over curing compound or Masonry Coating.
Probably should have started with a lighter color base coat and have ample cure time before applying additional colors.
Form lined areas and wood form areas appeared to stain differently.

## Slide 8: Barrier Wall prior to Stain

## Slide 9: KY 11 Bridge Stained Barrier Walls

## Slide 10: Conclusion
This project won a LM Scofield’s Yearly Decorative Concrete Award.
Alternative to Colored Stains or Masonry Coatings
Acid Stain vs Stain and Masonry Coating.
  Masonry Coating - $12.00 per sf
  Planned Concrete Staining – $8.50 per sf.
  Acid Staining - $23.00 per sf.