## Slide 1
I-65 Central Corridor Project
KYTC’s 1st CM/GC Project
Thursday, September 10th

## Slide 2
What is CM/GC?
In CM/GC, the Cabinet procures a contractor based on qualifications to provide input during the Preconstruction Phase of the Project as well as to construct the Project. During the Preconstruction Phase, the Contractor provides constructability input to the Cabinet on matters such as constructability, risk, cost, and construction schedule optimization.
KYTC Contact:
Erika Drury, PE
Alternative Delivery Program Manager

## Slide 3
Construction Manager/General Contractor
(CM/GC)
Note: Image from FHWA Website

## Slide 4
Construction Manager/General Contractor
(CM/GC)
QK4
CDI
KYTC
AECOM
KIEWIT

## Slide 5
Project Overview

## Slide 6
Location Map – I-65 Central Corridor
I-65 Project Website
https://i65centralcorridor.com

## Slide 7
Location Map – I-65 Central Corridor
I-65 Project Website
https://i65centralcorridor.com

## Slide 8
Location Map – I-65 Central Corridor
I-65 Project Website
https://i65centralcorridor.com

## Slide 9
18 Bridges + Pavement Rehab
Bradley Ave
Bundle #1
Notes: 30% Plans on all 18 bridges. RFC Plans on 9 bridges.

## Slide 10
18 Bridges + Pavement Rehab
Bradley Ave
Bundle #2
Notes: 30% Plans on all bridges.

## Slide 11
Creating Opportunities from Challenges
High Traffic Volume
Complex MOT Planning/Design
Restricted Urban Corridor
Limited Existing ROW
High-cost commercial properties
High Profile Stakeholders
Historic Districts
Medical Districts
Colleges/Universities
Kentucky Expo Center / Fairgrounds
Utilities (active & abandoned)
Existing Bridge Geometrics
Complex Bridge Design
Unique Details and Special Design
“Another first on a project with many firsts”
~ Adam Ross - KYTC

## Slide 12
I-65 Central Corridor Setting | Historic Districts
Old Louisville is the 3rd largest Historical Preservation District in the U.S. given its number of restored Victorian homes.
Seminary Hall – Broadway

## Slide 13
I-65 Central Corridor Setting | Medical District

## Slide 14
I-65 Central Corridor Setting | Dense Urban Corridor

## Slide 15
Tackling the Challenges
Preconstruction Coordination

## Slide 16
Challenge | Preconstruction Coordination Meetings
Design Task Force Meetings
Weekly Design Task Force Meetings (Tues/Fri)
Weekly Risk/Estimate Coordination Meetings (GEC/ICE)
Bi-Weekly Geotech Meetings
Bi-Weekly ROW Meetings
30% / 60% / 90% Pricing Milestone Meetings
Constructability Review Meetings
Quantity/Cost Reconciliation Meetings

## Slide 17
Challenge | Preconstruction Coordination Meetings
Early Utility Coordination Meetings
Monthly Utility Meetings
Potholing/SUE
Video Inspection
    96” Combined Sewer
    108” Combined Sewer
Early Utility Relocation Packages

## Slide 18
Challenge | Preconstruction Coordination Meetings
Early CSX Coordination Meetings
CSX Bi-Weekly Meetings
Collaboration on design progression avoided challenges such as:
  Influence zone for shoring
  Replacement of pedestrian bridge

## Slide 19
Challenge | Preconstruction Coordination Meetings
Early identification of Staging Areas/ Laydown Yards / Excess Excavation
Allowed NEPA Integration
Conducted advanced HAZMAT Sampling & Soil Characterization
Coordinated for Right of Way acquisition
Improved construction productivity

## Slide 20
Tackling the Challenges
MOT Planning and Design

## Slide 21
Challenge | MOT Planning and Design
Transmodeler Regional Model
Calibration
Alternatives Analysis
  Multiple construction scenarios
Results
  Volumes, LOS, Delay, Queuing & Travel Times
Origin-Destination Analysis
  10 locations- AM/PM
  Truck O/D
  No major increase in delay for most O/D routes (<10 minutes)
Identified Mitigation Locations
Notes: Question- which first- bridge closure approach or traffic approach to see if we could close it?
Could we close it?- Transmodeler runs- ID’d where traffic would go . AM and PM peaks (3 hour window), identified/highlighted some areas/hotspots/bottleneck areas –
Mitigations -

## Slide 22
Challenge | MOT Planning and Design
Off-Site Safety/Capacity Mitigations
Temporary Ramp / Lane Closures
  Addresses Weaving concerns
Temporary Ramp Widening
  Additional Capacity
I-65 Project Website
https://i65centralcorridor.com
Notes: Question- which first- bridge closure approach or traffic approach to see if we could close it?
Could we close it?- Transmodeler runs- ID’d where traffic would go . AM and PM peaks (3 hour window), identified/highlighted some areas/hotspots/bottleneck areas –
Mitigations -

## Slide 23
Challenge | MOT Planning and Design
  SIGNED DETOUR
  Through traffic detoured to WB I-264 (Georgia Davis Powers Expressway) on west side of Louisville
    Utilize most available capacity
    Create least traffic impacts
    Downtown Access
    Surface Street Detours – Vehicular and Pedestrian
I-65 Project Website
https://i65centralcorridor.com

## Slide 24
Challenge | MOT Planning and Design
Pre-Construction Planning
Speed limit reduction to 40 mph (SHE Approval
Truck lane restrictions
Regional Variable Message and TRIMARC signing
2-Way Street Conversions
Hospital Parking Garage Access
Notes: Question- which first- bridge closure approach or traffic approach to see if we could close it?
Could we close it?- Transmodeler runs- ID’d where traffic would go . AM and PM peaks (3 hour window), identified/highlighted some areas/hotspots/bottleneck areas –
Mitigations -

## Slide 25
Challenge | MOT Planning and Design
Pre-Construction Agency Coordination
KYTC / Louisville Metro Partnership
  Coordination with Traffic Signal Controller Updates (220)
  Signal Timing Updates
  Special thanks to Brandon Shelley and Stacy Keith & Jason Yeager at Louisville Metro
Notes: Question- which first- bridge closure approach or traffic approach to see if we could close it?
Could we close it?- Transmodeler runs- ID’d where traffic would go . AM and PM peaks (3 hour window), identified/highlighted some areas/hotspots/bottleneck areas –
Mitigations -

## Slide 26
Challenge | MOT Planning and Design
Full Closure – Week 1 Adjustments
Coordination with navigational apps (WAZE, Google, Apple)
MUST BE FLEXIBLE AND AVAILABLE DURING WEEK 1

## Slide 27
Challenge | MOT Planning and Design
Can opener at 3rd Street (https://www.louisvillecanopener.live/ )

## Slide 28
Tackling the Challenges
Complex Bridge Design

## Slide 29
Challenge | Complex Bridge Design
Bridge Maintenance Project
9 Bridges Released For Construction
  3 Bridge Rehabilitations
  6 Bridge Replacements
Project Goals:
  Replace Aging Infrastructure
  Reduce Future Maintenance Needs
Innovations At Every Turn!

## Slide 30
Challenge | Complex Bridge Design
Accelerated Bridge Construction
Under bridge work
Micropiles
LWCC
Precast Deck Panels

## Slide 31
Challenge | Complex Bridge Design
CSX/Hill St./Burnett Ave.
    Railroad Vertical Clearance
    Link slab design
    Bridge Deck Reduction
Bradley Avenue
    Bridge conversion to wagon box
    Meeting KFEC’s Needs

## Slide 32
Challenge | Complex Bridge Design
    Kentucky St./Brook St.
      Complicated Geometry
      Minimal Vertical Clearance
      Redundant Steel Straddle Bents

## Slide 33
Challenge | Complex Bridge Design
Jacob St./Broadway/Gray St. & Chestnut St.
    Extreme Bridge span reduction
      33 Span to 3 Single Spans
    MSE Supported Roadway Plugs
    Substructure Reuse

## Slide 34
Challenge | Complex Bridge Design
Brook St./Muhammed Ali Blvd.
  (Hospital Curve)
    “Maintenance Nightmare”
    Complicated Geometry
    Robust FEA Model (LARSA)
    Substructure reuse and chloride mitigation
    Bridge deck reduction

## Slide 35
Tackling the Challenges
Closing the Interstate

## Slide 36
Closing the Interstate
COMMUNICATION IS KEY
Stakeholder Engagement
Media Events
Social Media
Website
Public Meetings
Digital Message Signs
Radio Advertisements
Billboards

## Slide 37
Closing the Interstate
SUCCESS FACTORS
Early railroad coordination
Advance sewer relocation
Early steel procurement
Laydown yard access
Reduced bridge deck area
Utilized precast concrete deck panels

## Slide 38
Precast Concrete Deck Panels

## Slide 39
Precast Concrete Deck Panels

## Slide 40
Closing the Interstate
CHALLENGES
Overhead Utilities
Limited Right-of-Way
Noise & Vibration
  Micropiles
  Vibration Monitoring
Detoured Interstate Traffic
  Incident Management Coordination
  Quick Clearance
Weather
Notes: Can Opener, increased train traffic, random pedestrians on the interstate

## Slide 41
Closing the Interstate
MAINTENANCE OPPORTUNITIES
Wrong Way Project
Roadway Sweeping
Drain Cleaning
Tree Trimming
Pothole & Bridge Deck Patching
Overhead Panel Sign Replacements
I-65 CC Surveying & Coring
TRIMARC Camera Repairs
Localized Repair Projects
Notes: Can Opener, increased train traffic, random pedestrians on the interstate

## Slide 42
Bradley Avenue

## Slide 43
Bradley – Deck Area Reduction
CURRENT CONCEPT
PLANNED CONCEPT

## Slide 44
Bradley – Old Bridge

## Slide 45
Bradley – Pre-Closure

## Slide 46
Bradley – New Bridge

## Slide 47
Hill Street,
CSX Railroad & Burnett Avenue

## Slide 48
Hill/CSX/Burnett – Old Bridge

## Slide 49
Hill/CSX/Burnett – Closure

## Slide 50
Hill/CSX/Burnett – Closure

## Slide 51
Kentucky & Brook Streets

## Slide 52
Kentucky/Brook – Closure

## Slide 53
Kentucky/Brook – Closure

## Slide 54
Questions?