## Slide 1
Just Double It!
Building Planning and Scoping Cost Estimates
Steve De Witte & Patrick Perry
September 4, 2025

## Slide 2
​THE KYTC MISSION
To provide a safe, efficient, environmentally sound and fiscally responsible transportation system that delivers economic opportunity and enhances the quality of life in Kentucky

## Slide 3
Agenda
Cost Estimate Background
AASHTOWare Project Estimation Update
Recent examples – What Gets Missed?
Building a Scoping Estimate Together/Framework
Next Steps/Questions
Exchange Tearful Goodbyes

## Slide 4
https://pe.app/

## Slide 5
Cost Estimate Background

## Slide 6
Cost Estimate Background

## Slide 7
Cost Estimate Background

## Slide 8
AASHTOWare Project Estimation Update

## Slide 10
Recent Examples

## Slide 11
Straight Costs

## Slide 12
Straight Costs
LESS
GOOD
GOOD

## Slide 13
Grown with CPI
LESS
GOOD
GOOD

## Slide 14
Grown with NHCCI
LESS
GOOD
GOOD

## Slide 15
Year | CPI | NHCCI
2014 | 1.00 | 1.69
2015 | 1.00 | 1.66
2016 | 1.01 | 1.66
2017 | 1.04 | 1.65
2018 | 1.06 | 1.66
2019 | 1.08 | 1.87
2020 | 1.09 | 1.92
2021 | 1.14 | 1.86
2022 | 1.24 | 2.18
2023 | 1.29 | 2.78
2024 | 1.33 | 3.12
2025 | 1.36 | 3.23
Δ | 36% | 91%

## Slide 16
Building a Scoping Estimate Together/Framework
  Scope
  Quantities
  Parametric
  Standard Contingencies
  Risk-Based Contingencies
  Time/Management Risk

## Slide 17
Not Escalation to a future year!
PDP does that:
4% YOY for D, U, C
5% YOY for R

## Slide 18
Representative Example: Rural Route in District 9
Concept:
Reconstruct 4.9 miles
11’ lanes/8’ shoulders
Small sections of curb/gutter
10’ shared use path
1 bridge
1 railroad crossing (not feasible to grade separate)
1 traffic signal
45 potential parcels, 8 potential relocations
Utilities crisscross existing route
2024 SYP:
Only P in biennium, no other phases shown
Sponsored in SHIFT 2026 by District, single boost by BTADD

## Slide 19
Easy Stuff First! What do we have bid-item quantities for?
Pavement
Excavation/Embankment
Striping
Curb & Gutter
Multi-Use Path
Guardrail & End Treatments

## Slide 20
Easy Stuff First! What do we have bid-item quantities for?
Description | Depth (in) | lb/in/sq yd | Units |  | $ per Unit | Subtotal
CL2 ASPH SURF 0.38D PG64-22 | 1.5 | 110 | 0.08 | TON | $160.00 | $13.20
CL2 ASPH BASE 1.00D PG64-22 | 9.5 | 110 | 0.44 | TON | $140.00 | $61.60
CRUSHED STONE BASE | 18 | 115 | 1.04 | TON | $40.00 | $41.40
FABRIC-GEOTEXTILE CLASS 1 | 1 | -- | 1 | SQ YD | $3.00 | $3.00
TACK COAT |  |  | 0.075 | GAL | $36.54 | $2.74
PRIME COAT |  |  | 0.4 | GAL | $32.28 | $12.91
 |  |  |  |  | SUM | $134.85
 |  |  |  | SY | USE | $140.00

## Slide 21
Easy Stuff First! What do we have bid-item quantities for?
Driving Pavement Costs |  | 
Total Length | 25,872 | LF
2 11' Lanes | 22 | LF
Area | 569,184 | SF
 | 63,243 | SY
Cost | $ 140 | 
Subtotal | $ 8,853,973 | 
Shoulder Pavement |  | 
Total Length | 25,872 | LF
2 @ 8' Wide | 16 | LF
Area | 413,952 | SF
 | 45,995 | SY
Cost | $ 140 | 
Subtotal | $ 6,439,253 | 
Total Paving | $ 15,293,227 | 

## Slide 22
Easy Stuff First! What do we have bid-item quantities for?
Other Bid Items | Qty | Units | $ per unit | Total
Clearing & Grubbing | 4.9 | mi | $250,000 | $1,225,000
Excavation | 963,425 | CY | $25 | $24,085,625
Guardrail | 13,125 | LF | $40 | $525,000
Guardrail End Treatments | 20 | EA | $4,500 | $90,000
Mill & Overlay (tie ins) | 1,617 | SY | $16 | $25,872
Pavement Striping | 25,872 | LF | $5 | $129,360
10' Shared Use Path | 28,747 | SY | $60 | $1,724,800
Curb & Gutter | 250 | LF | $60 | $15,000
 |  |  | Subtotal | $27,820,657
Bid-Item Cost: $43,113,884

## Slide 23
Next: Parametric
Structures
Drainage
Signals
MOT
Mob/Demob
Phase Costs

## Slide 24
Next: Parametric
Parametric Items | Qty | Units | $ per unit | Total
350’ long Bridge | 17,850 | SF | $400 | $7,140,000
Drainage/Erosion Control |  |  | 50% paving | $7,646,613
Maintenance of Traffic | 1 | LS | $500,000 | $500,000
Signals | 1 | EA | $1,000,000 | $1,000,000
 |  |  | Subtotal | $16,286,613

## Slide 25
Next: Parametric
Phase Costs
  Design (comes later)
  ROW $9.2M (from District)
  Utilities $12M (from District)

## Slide 26
Paving | $15,293,227
Bid Items | $27,820,657
Parametric | $16,286,613
Total | $59,400,497
Mobilization (3%) | $1,782,015
Demobilization (1.5%) | $891,007
Construction w/o Contingency | $62,073,519

## Slide 27
Next: Standard Contingencies
Blanket 25%? 30%? 50%?
What does it actually cover?
Will vary based on detail.

## Slide 28
New: Risk-based Contingencies (risks to KYTC)
How likely to occur?
The railroad is CSX
Scope Changes
Surprise Utility conflict
Geotech issues
Carter County Commissioner’s Award
Environmental Mitigation
Unknown Unknowns (30%)
  How much do you know now vs. at PL&G?

## Slide 29
New: Risk-based Contingencies (risks to KYTC)
Risk | Worst-Case Cost | Likelihood to Occur | Risk Cost
CSX Coordination |  |  | 
Flagger ($10k/day @ 365 days) | $3,650,000 | 65% | $2,372,500
Multiple Design Changes | $400,000 | 80% | $320,000
----------------------------------- |  |  | 
Scope Changes | $2,500,000 | 70% | $1,750,000
Surprise Utility Conflict | $2,500,000 | 50% | $1,250,000
Geotech Issues | $2,500,000 | 90% | $2,250,000
Carter County Commissioner Award | $1,800,000 | 75% | $1,350,000
Environmental Mitigation | $5,000,000 | 80% | $4,000,000
Unknown Unknowns (30%) | $18,622,056 | 100% | $18,622,056
 |  | Total Contingency | $31,914,556

## Slide 30
New: Risk-based Contingencies (risks to KYTC)
Risk | Worst-Case Cost | Likelihood to Occur | Risk Cost
CSX Coordination |  |  | 
Flagger ($10k/day @ 365 days) | $3,650,000 | 65% | $2,372,500
Multiple Design Changes | $400,000 | 80% | $320,000
----------------------------------- |  |  | 
Scope Changes | $2,500,000 | 70% | $1,750,000
Surprise Utility Conflict | $2,500,000 | 50% | $1,250,000
Geotech Issues | $2,500,000 | 90% | $2,250,000
Carter County Commissioner Award | $1,800,000 | 75% | $1,350,000
Environmental Mitigation | $5,000,000 | 80% | $4,000,000
Unknown Unknowns (30%) | $18,622,056 | 100% | $18,622,056
 |  | Total Contingency | $31,914,556
At this point, add to C phase. We can always go back.

## Slide 31
Are we done? No!!
We’re so not done I’m not even showing the new total.

## Slide 32
Are we done? No!!
We’re so not done I’m not even showing the new total.
(but also 15% of that number for D phase estimate is ~$14.1M)

## Slide 33
New: Time/Management Contingency (SYP risk)
We can’t even start design until (at earliest) 2026
  Which means R, U in 2028
  C in 2030
What things can hold this up?
  Rail, Utilities, ROW, Environmental
  Legislative Momentum
More likely case
    D in 2028
    R, U in 2030-2032
    C in 2034
The number we put down is going to hang around!

## Slide 34
New: Time/Management Contingency (SYP risk)
Add 10-20% per biennium, per phase
Keep in Current Year Dollars
This is a contingency, not escalation
Design (in 2028):
$14.1M + 1 biennium away (15%) = $16.2M
ROW (in 2030):
$9.2M + 2 biennia away (30%) = $12.0M
Utilities (in 2032):
$12M + 3 biennia away (45%) = $17.4M
Construction (in 2034):
$94.0M + 4 biennia away (60%) = $150.4M

## Slide 35
Phase | Cost (2025$ )
Design | $16,200,000
ROW | $12,000,000
Utilities | $17,400,000
Construction | $150,400,000
Total | $196,000,000

## Slide 36
Phase | Cost (2025$ )
Design | $16,200,000
ROW | $12,000,000
Utilities | $17,400,000
Construction | $150,400,000
Total | $196,000,000
This goes into report, PDP, SYP

## Slide 38
REVISIT ESTIMATE

## Slide 39
Next Steps/Notes
Document, Document, Document
Pushback? Throw Steve Under Bus
Use estimates w/o Time/Management Contingency for B/C calcs
Risk Factor Research

## Slide 40
https://pe.app/

## Slide 41
Patrick Perry, P.E., P.L.S.
TE Branch Manager – Roadway Design
Patrick.Perry@ky.gov
502-782-4925
Steve De Witte, P.E.
TE Branch Manager – Strategic Planning
Stephen.DeWitte@ky.gov
502-782-5056
QUESTIONS/DISCUSSION
Tearful goodbyes