## Revised Production-Hour Form
PRODUCTION-HOUR WORKSHEET (revised 7/14)
SURVEY
No. | ITEM | CREW | UNIT | AMOUNT | HRS/UNIT | HOURS
RECONNAISSANCE
1 | Control - (existing) | 1 | Mile |  |  | 0
2 | Utilities - (data gathering, identification & contact) | 1 | No. |  |  | 0
3 | Drainage - (sink holes, streams, pipes, etc.) | 1 | Mile |  |  | 0
CONTROL
4 | Horizontal | 2 | Mile |  |  | 0
5 | Vertical | 2 | Mile |  |  | 0
6 | Process data | 1 | Mile |  |  | 0
PLANIMETRIC SURVEY
7 | Planimetric location (specify complete, pickup or update) | 2 | Mile |  |  | 0
8 | Subsurface Utility Engineering, Quality Levels C & D | 1 | Mile |  |  | 0
9 | Subsurface Utility Engineering, Quality Level B | 1 | LS |  |  | 0
10 | Subsurface Utility Engineering, Quality Level A | 1 | LS |  |  | 0
11 | Process data | 1 | Mile |  |  | 0
TERRAIN SURVEY
12 | DTM data collection (Items 11-18 not required if used) | 2 | Acre |  |  | 0
13 | Verify terrain model accuracy | 2 | Mile |  |  | 0
14 | Tie-ins | 2 | No. |  |  | 0
15 | Drainage situations survey (Bridge) | 2 | No. |  |  | 0
16 | Drainage situations survey (Culvert) | 2 | No. |  |  | 0
17 | Drainage pipe section (non-situation size) | 2 | No. |  |  | 0
18 | Flood plain data | 2 | No. |  |  | 0
19 | Railroad Surveys | 2 | No. |  |  | 0
20 | Additional necessary DTM data (specify pickup or update) | 2 | Acre |  |  | 0
21 | Process data | 1 | Mile |  |  | 0
ESTABLISH PROPERTY LINES & OWNERSHIP
22 | Contact & Interview Property Owners | 1 | Parcel |  |  | 0
23 | Field tie property lines/corners | 2 | Parcel |  |  | 0
STAKING
24 | Stake centerlines, approaches, detours | 2 | Mile |  |  | 0
25 | Stake core holes - structures (unit is per structure) | 2 | No. |  |  | 0
26 | Stake core holes - roadway (unit is per core hole) | 2 | No. |  |  | 0
SURVEY MISCELLANEOUS
27 | Determine roadway elevations (Crown and EP) | 2 | Mile |  |  | 0
28 | Environmental areas | 2 | No. |  |  | 0
29 | [5 empty] | 0
SURVEY TOTAL | [5 empty] | 0
PRELIMINARY LINE AND GRADE
No. | ITEM |  | UNIT | AMOUNT | HRS/UNIT | HOURS
30 | Computer setup |  | LS |  |  | 0
31 | Prepare existing manuscripts |  | Mile |  |  | 0
32 | Establish approximate property lines and ownership |  | Parcel |  |  | 0
33 | Study and develop typical sections |  | No. |  |  | 0
34 | Study and develop horizontal alignments |  | Mile |  |  | 0
35 | Study and develop vertical alignments |  | Mile |  |  | 0
36 | Create and evaluate proposed roadway models |  | Mile |  |  | 0
37 | Design entrances |  | No. |  |  | 0
38 | Pre-size pipes (all alternates) |  | No. |  |  | 0
39 | Pre-size culverts (all alternates) |  | No. |  |  | 0
40 | Pre-size bridges (all alternates) |  | No. |  |  | 0
41a | Conduct Traffic Engineering Analysis (Basic; Highway Capacity Manual Procedures) |  | Intersection |  |  | 0
41b | Conduct Traffic Engineering Analysis (Advanced; Micro-simulation) |  | Intersection |  |  | 0
42 | Study and development of interchange |  | No. |  |  | 0
43 | Study and development of intersection |  | No. |  |  | 0
44 | Study and develop maintenance of traffic plan |  | LS |  |  | 0
45 | Plot/print copies of plans for team meeting and inspections |  | LS |  |  | 0
46 | Calculate preliminary quantities and develop cost estimates |  | Alt. |  |  | 0
47 | Revise plans and estimates |  | LS |  |  | 0
48 | Preliminary Right of Way with taking areas |  | Parcel |  |  | 0
49 | Prepare Design Executive Summary |  | LS |  |  | 0
50 | Develop/document "Avoidance Alternatives to Water Related Impacts" |  | LS |  |  | 0
PRELIMINARY LINE & GRADE MISCELLANEOUS
51 | [5 empty] | 0
52 | [5 empty] | 0
53 | [5 empty] | 0
54 | [5 empty] | 0
55 | [5 empty] | 0
PRELIMINARY LINE AND GRADE TOTAL | [5 empty] | 0
UTILITY COORDINATION
No. | ITEM | PERSONS | UNIT | AMOUNT | HRS/UNIT | HOURS
56 | Utility Coordination Meeting | 2 | No. |  |  | 0
57 | Develop Utility Relocation Layout Sheets (1"=200') |  | Mile |  |  | 0
58 | Develop Utility Relocation Plans (1"=50') |  | Mile |  |  | 0
UTILITY COORDINATION MISCELLANEOUS
59
| UTILITY COORDINATION TOTAL |  |  |  |  | 0
RIGHT OF WAY PLANS
No. | ITEM |  | UNIT | AMOUNT | HRS/UNIT | HOURS
60 | Deed research |  | Parcel |  |  | 0
61 | Establish property and ownership |  | Parcel |  |  | 0
62 | Calculate Right of Way |  | Parcel |  |  | 0
63 | Prepare legal descriptions |  | Parcel |  |  | 0
64 | Complete Right of Way summary sheet |  | Parcel |  |  | 0
65 | Generate Right of Way strip map (scale 1" = xxx') |  | Sheet |  |  | 0
66 | Prepare Right of Way Plans Submittal |  | LS |  |  | 0
67 | Right of Way revisions after Right of Way submittal |  | LS |  |  | 0
R/W PLANS MISCELLANEOUS
68 | Deed Research for Existing Alignments |  | LS |  |  | 0
69 | Deed Research for Existing Parcels |  | Parcel |  |  | 0
70 | Prepare Legal Descriptions for Right of Way transfer |  | Parcel |  |  | 0
71
72
RIGHT OF WAY PLANS TOTAL | [5 empty] | 0
FINAL PLAN PREPARATION
No. | ITEM |  | UNIT | AMOUNT | HRS/UNIT | HOURS
80 | Computer setup |  | LS |  |  | 0
81 | Update existing topography and terrain model |  | Mile |  |  | 0
82 | Refine alignments (horizontal & vertical) |  | Mile |  |  | 0
83 | Develop pavement design |  | No. |  |  | 0
84 | Finalize templates & transitions |  | No. |  |  | 0
85 | Develop final roadway model |  | Mile |  |  | 0
86 | Develop proposed design |  | Mile |  |  | 0
87 | Generate plan sheets (scale 1" = xxx') |  | Sheet |  |  | 0
88 | Generate profile sheets (scale 1" = xxx') |  | Sheet |  |  | 0
89 | Detail cross sections (scale 1" = xxx') |  | No. |  |  | 0
90 | Design entrances |  | No. |  |  | 0
91 | Revise roadway plans from soils report |  | Mile |  |  | 0
DRAINAGE
92 | Develop pipe sections (< 54") |  | No. |  |  | 0
93 | Develop drainage system map |  | Mile |  |  | 0
94 | Develop drainage situation (bridge) |  | No. |  |  | 0
95 | Develop drainage situation (culvert) |  | No. |  |  | 0
96 | Develop blue line stream channel change ( => 200') |  | No. |  |  | 0
97 | Drainage analysis (entrance pipes) |  | No. |  |  | 0
98 | Drainage analysis (A < = 200 acres) |  | No. |  |  | 0
99 | Drainage analysis (200 acres < A < 1.0 sq. mile) |  | No. |  |  | 0
100 | Drainage analysis (A = > 1.0 sq. mile) level 1 analysis |  | No. |  |  | 0
101 | Drainage analysis (A = > 1.0 sq. mile) level 2 analysis |  | No. |  |  | 0
102 | Drainage analysis (A = > 1.0 sq. mile) level 3 analysis |  | No. |  |  | 0
103 | Special drainage studies |  | No. |  |  | 0
104 | Roadway ditches and channels |  | Mile |  |  | 0
105 | Develop Erosion Control Plan |  | Mile |  |  | 0
106 | Inlet spacing calculations |  | No. |  |  | 0
107 | Storm sewers calculations |  | No. |  |  | 0
108 | Perform scour analysis |  | No. |  |  | 0
109 | Assemble preliminary and final drainage folders |  | LS |  |  | 0
110 | Prepare advanced situation folder - bridge |  | No. |  |  | 0
111 | Prepare advanced situation folder - culvert |  | No. |  |  | 0
DRAINAGE MISCELLANEOUS
112 |  |  | LS |  |  | 0
113 | [5 empty] | 0
114 | [5 empty] | 0
115 | [5 empty] | 0
FINAL PLAN PREPARATION (Continued)
No. | ITEM |  | UNIT | AMOUNT | HRS/UNIT | HOURS
116 | Prepare layout sheet |  | LS |  |  | 0
117 | Prepare typical sections |  | No. |  |  | 0
118 | Prepare Interchange geometric approval |  | No. |  |  | 0
119 | Prepare intersection geometric approval |  | No. |  |  | 0
120 | Prepare coordinate control sheet |  | Mile |  |  | 0
121 | Prepare elevation developments |  | No. |  |  | 0
122 | Prepare striping plan |  | No. |  |  | 0
123 | Calculate final quantities |  | Mile |  |  | 0
124 | Complete general summary |  | LS |  |  | 0
125 | Complete paving summary |  | LS |  |  | 0
126 | Complete drainage summary |  | LS |  |  | 0
127 | Complete pavement under-drain summary |  | LS |  |  | 0
128 | Prepare cost estimate |  | LS |  |  | 0
129 | Plot/print copies of plans |  | LS |  |  | 0
130 | Plan revisions |  | Mile |  |  | 0
131 | Prepare final construction plans submittal |  | LS |  |  | 0
MAINTENANCE OF TRAFFIC
132 | Write maintenance of traffic notes (TCP) |  | LS |  |  | 0
133 | Prepare construction phasing plans |  | Mile |  |  | 0
134 | Develop diversion plan sheets |  | Sheet |  |  | 0
135 | Develop diversion profile sheets |  | Sheet |  |  | 0
136 | Develop diversion cross sections |  | No. |  |  | 0
137 | Develop temporary drainage |  | No. |  |  | 0
FINAL PLANS MISCELLANEOUS
138 | Document available rock quantities |  | LS |  |  | 0
139 | [5 empty] | 0
140 | [5 empty] | 0
141 | [5 empty] | 0
142 | [5 empty] | 0
143 | [5 empty] | 0
FINAL PLANS TOTAL | [5 empty] | 0
MEETINGS
No. | ITEM | PERSONS | UNIT | AMOUNT | HRS/UNIT | HOURS
150 | Prelim. line and grade inspection | 2 | No. |  |  | 0
151 | Drainage inspection | 2 | No. |  |  | 0
152 | Final inspection | 2 | No. |  |  | 0
153 | Misc. project coordination meetings | 2 | No. |  |  | 0
154 | Project team meetings | 2 | No. |  |  | 0
MEETINGS MISCELLANEOUS
155 | Value Engineering Study |  | LS |  |  | 0
156 | Constructability Review |  | LS |  |  | 0
MEETINGS TOTAL | [5 empty] | 0
PUBLIC INVOLVEMENT
No. | ITEM | PERSONS | UNIT | AMOUNT | HRS/UNIT | HOURS
160 | Develop and Maintain Mailing List |  | LS |  |  | 0
161 | Prepare for Advisory Committee/Officials Meeting |  | No. |  |  | 0
162 | Attend Advisory Committee/Officials Meeting | 2 | No. |  |  | 0
163 | Prepare for Public Meetings/Hearings |  | No. |  |  | 0
164 | Attend Public Meetings/Hearings | 2 | No. |  |  | 0
165 | Prepare and Distribute Newsletter |  | No. |  |  | 0
166 | Property owner coordination |  | No. |  |  | 0
PUBLIC INVOLVEMENT MISCELLANEOUS
167 | [5 empty] | 0
168 | [5 empty] | 0
169
PUBLIC INVOLVEMENT TOTAL | [5 empty] | 0
QA/QC
No. | ITEM |  | UNIT | AMOUNT | HRS/UNIT | HOURS
180 | Plan review |  |  |  |  | 0
181 | Structure review |  |  |  |  | 0
QA/QC TOTAL | [5 empty] | 0
PRODUCTION-HOUR SUMMARY
SURVEY TOTAL | [5 empty] | 0
LINE AND GRADE TOTAL | [5 empty] | 0
UTILITY COORDINATION TOTAL | [5 empty] | 0
RIGHT OF WAY PLANS TOTAL | [5 empty] | 0
FINAL PLANS TOTAL | [5 empty] | 0
MEETINGS TOTAL | [5 empty] | 0
PUBLIC INVOLVEMENT TOTAL | [5 empty] | 0
QA/QC TOTAL | [5 empty] | 0
GRAND TOTAL | [5 empty] | 0
COUNTY
ROUTE
DESC
ITEM NO.
PROJECT TYPE
CONSULTANT
REVIEWED BY
PREPARED BY
DATE
Note on A5: A field and record search for any existing control that may be utilized, including controls established for aerial photogrammetry. Sources of any existing control need to be identified.
Note on A6: Identify all utility companies within the project corridor and maintain a valid contact list of those utility companies and their representatives. Contact utility companies, Kentucky 811, KYTC District Utilities Staff and any other sources for utility facility mapping or other information concerning the location of any utilities. Check with local governments for GIS databases and for other sources of information.
Note on A7: Identify drainage features that may require consideration in design and that are necessary to be documented on the plans.
Note on A9: Establish any new or additional horizontal coordinate control including the monumentation. All horizontal control obtained from Global Positioning Systems (GPS) shall comply with the Geometric Geodetic Accuracy Standards and Specifications for using GPS Relative Positioning Techniques published by the Federal Geodetic Control Subcommittee dated August 1, 1989. Additional control points set shall be a minimum of 24-inch rebar (#4 or larger) with a plastic or aluminum cap.
Note on A10: Establish any new or additional vertical control, including benchmarks, and including the monumentation. All vertical control obtained from Global Positioning Systems (GPS) shall comply with the Geometric Geodetic Accuracy Standards and Specifications for using GPS Relative Positioning Techniques published by the Federal Geodetic Control Subcommittee dated August 1, 1989. Additional control points set shall be a minimum of 24-inch rebar (#4 or larger) with a plastic or aluminum cap. Note: The Department, through its photogrammetry consultant, will provide horizontal and vertical controls to USC&GS markers. Intermediate controls set by the Consultant shall be tied to the controls provided by the Department. This work is only necessary if the project was not flown or if insufficient controls were established with the aerial photogrammetry. It is expected that with this item of work, any existing controls would be checked for accuracy.
Note on A11: Process data obtained from field survey and check for accuracy and closure. Preparation of survey report of coordinate controls and bench marks. Note: A complete coordinate control report including existing and new control point information, with traverse information confirming coordinate control accuracy and a bench level report shall be prepared and submitted to the KYTC Project Manager.
Note on A13: Locate and/or identify all necessary planimetric features. On projects with aerial photogrammetry available this would require only identification of planimetric features and pick-up of areas not covered by the available photogrammetry, if required. For Phase 2 design this would be for the update of the topography due to new or changed planimetric features since the original survey or aerial photogrammetry was obtained. It should be noted on the production-hour form the extent of work required, for example, complete, pick-up or update.
Note on A14: Apply reconnaissance utility data gathered to locate utility facilities on plans. Gather a survey of all visible utility facility features (i.e. poles, valves, manholes, markers, etc.) and provide them on the plans. Utilize both the reconnaissance data and field generated data to assess the approximate location of the utility facilities within the project corridor. This data shall be used to identify potential conflicts between the project and the existing facilities.
Note on A15: Identify specific locations where the road project potentially may conflict with the existing utility facilities and a more precise location of the utility is needed. Quality Level B location is valid if precision is needed to validate the conflict, confirm the facility may remain in situ, or design to avoid. The Quality Level B location shall be a non-excavation field procedure using surface locating technologies and shall provide a more precise location of the facility without providing elevations. The consultant shall denote the Quality Level B location on the plans and use this information to avoid the facility or establish a plan for relocation as appropriate
Note on A16: Identify specific locations where the exact location of the utility is needed. A Quality Level A location is valid if a precise elevation is needed to validate the conflict, confirm the facility may remain in situ, or design to avoid. For those locations, validate the Quality Level B location, confirm facility type, size, and provide elevations via vacuum excavation or other valid means. The consultant shall communicate with the utility company, providing for the utility to be present during the facility location when necessary. The consultant shall denote the Quality Level A location on the plans and use this information to avoid the facility or establish a plan for relocation as appropriate.
Note on A17: Process all necessary data to produce a planimetric map and submit electronic files to the designer.
Note on A19: Collect general terrain data for project (when general terrain data is not already available).
Note on A20: Check for accuracy of breaklines, random points, contours, etc., including terrain model obtained from aerial photogrammetry. Note: The density of points taken in the field to check the DTM will be determined at the Predesign Conference.
Note on A21: Field verification of all field data necessary for tying of project to existing features pavements etc. Include all road approaches. Entrances are not generally required and will only be performed if specifically directed by the KYTC Project Manager.
Note on A22: Obtain all necessary field data to represent situation survey for bridges, including stream profile and necessary terrain data to merge into the existing terrain model.
Note on A23: Obtain all necessary field data to represent situation survey for culverts.
Note on A24: Obtain all necessary field data to define the accuracy of the existing flow lines and inlet and outlet location and elevations of cross drains. Note: Does not include entrance pipes.
Note on A25: Collect field data necessary for flood plain analysis.
Note on A26: Obtain all necessary terrain data to represent railroad survey (top of rail, ballast, ditches, fills, cuts, RR milepost, etc.).
Note on A27: Collect other necessary data to produce an accurate digital terrain model (obscured areas, field checked areas, areas needing greater accuracy, etc.).
Note on A28: Process all pertinent data necessary to generate digital terrain models and submit electronic files to the designer.
Note on A30: Contact property owners requesting permission for access and discuss general scope of project, locations of property lines, septic system, drainage and any other pertinent information. A report is to be generated with a copy of the contact letter and all completed contact information forms from property owners, upon request. Note: The contact letter and information form is to be reviewed and approved by the KYTC Project Manager prior to contacting the property owners. The contact letter shall include the name of a person from the consultant that may be contacted in case of problems and the KYTC Project Manager.
Note on A31: Locate all monuments (rebars, pins, etc.) and other evidence of property lines (fences, tree lines, drains, etc.).
Note on A33: Accurately stake centerline at intervals determined at the Predesign Conference and process data.
Note on A34: Stake or locate all geotechnical borings required for structural design and process data. NOTE: The unit is per individual structure, NOT per hole.
Note on A35: Stake or locate all geotechnical borings required for geotechnical soil/rock analysis and process data. NOTE: The unit is per individual core hole.
Note on A37: This would be necessary on widening and overlay projects where the terrain model is developed from aerial photogrammetry and accurate pavement elevations are required and includes processing data. NOTE: Unit is per mile of individual roadway sections.
Note on A38: Locate and identify areas and feature that may be considered environmental issues and includes processing data.
Note on A44: Load and organize project data (manuscripts, mapping, ortho-rectified photographs, etc.) into computer system, the establishment and maintenance of a file management system for project data, including the storage and manipulation of all project files required for plan development.
Note on A45: Reviewing existing manuscript, if provided from aerial photogrammetry, and modifying any items that need to be corrected in order to conform to current KYTC CADD standards. Incorporate any additional topography picked up by field survey. Depict locations of all existing utility facilities. Manipulation/addition of text and notes identifying topography, planimetrics, drainage structures and utilities. Addresses shall be shown for all parcels, if requested.
Note on A46: Using field evidence and research documentation, such as plats and PVA records, establish approximate existing right of way and property lines and denote the property ownership, parcel numbers and lines on the plans.
Note on A47: Study, develop, and document all necessary typical sections (including alternatives) for the mainline and all other roadways, including creating the Inroads roadway templates for each roadway.
Note on A48: Study, develop and document the alternate horizontal alignments including approaches. Generate the necessary graphics depicting the proposed alternative, including disturbed limits, drainage structures, etc.
Note on A49: Study, develop and document the vertical alignments for each horizontal alignment including approaches and entrances.
Note on A50: Create, review, modify and finalize the proposed roadway model for each roadway and alternative, including creating the required cut/fill and decision tables to create the roadway model. Includes depiction of critical cross sections, as discussed in the Predesign Conference. Note: This would include the various iterations and adjustments required to complete an alternative due to earthwork balancing, intersection sight distance and alignment refinement.
Note on A51: Determine approximate location, grade, width and type of entrance and depict on the plans of the preliminary alternatives.
Note on A52: Determine preliminary diameter, length, and end treatment for each drainage pipe.
Note on A53: Determine preliminary size, length, and end treatment for each culvert.
Note on A54: Determine preliminary size (deck width, span arrangement, hydraulic openings, and/or clearances) for each bridge.
Note on A55: Conduct and document traffic engineering analysis for each roadway section and each major intersection, using the appropriate Highway Capacity Manual/Highway Capacity (HCM/HCS) procedures. This analysis will determine the appropriate lane configuration to meet the desired performance of the roadway. Production hours will only be based on the number of intersections for the project. Roadway lengths between intersections will be considered incidental to the overall analysis. Note: Number of roadway sections and major intersections to be analyzed, along with appropriate analysis scenarios and roadway sections will be determined and documented at the Predesign Conference.
Note on A56: Conduct and document traffic engineering analysis for each roadway section and each major intersection, using micro-simulation. This analysis will evaluate the ability of the project to operate as a comprehensive system. Production hours will be based on the number of major intersections on the project. Analysis should account for roadway lengths between intersections and minor intersections along the approaches to the major intersections. Note: Major intersections to be analyzed, along with appropriate analysis scenarios and roadway sections will be determined and documented at the Predesign Conference.
Note on A57: Study, develop and document preliminary interchange layouts including capacity analysis for weaving areas and merge/diverge. Note: The specific scope of work and methodology of analysis will be determined at the Predesign Conference.
Note on A58: Study, develop and document preliminary intersection layouts including appropriate capacity analysis, if required, for each intersection. Intersections to be studied will be identified in the Predesign Conference. Note: The specific scope of work and methodology of analysis will be determined at the Predesign Conference.
Note on A59: Study, develop and document alternative traffic control plans including construction phasing and/or detour routes.
Note on A60: Plot and/or print plans, profiles, drawing, cross sections, schematics, etc. for meetings, inspections or upon request. Note: The number of sets of prints for meetings and inspections shall be determined at the Predesign Conference.
Note on A61: Develop and document cost estimates for each alternate, including calculating preliminary quantities for each alternative. Includes development of a preliminary pavement design, to be reviewed by the KYTC Project Manager, to use in calculating preliminary pavement quantities. This should include estimating utility relocations costs as a result of the highway project and examination of those costs relative to the road construction costs.
Note on A62: Revise plans and estimates as directed from reviews and inspections. Upon completion of the Preliminary Line and Grade Inspection, the Consultant shall incorporate all significant comments into the preliminary plans and submit the revised plans and electronic files to the KYTC Project Manager.
Note on A63: Layout preliminary Right of Way and calculate approximate Right of Way taking areas from each parcel, for each alternate. Document the areas of taking for each alternate and depict the preliminary Right of Way and easements on the plans.
Note on A64: Prepare and submit Design Executive Summary, including all necessary documentation, location map, typicals, etc.
Note on A65: Prepare documentation concerning all blue line streams as denoted on topographic quad maps.
Note on A76: Hold a Utility Coordination Meeting for all utility companies identified within the project corridor by KYTC utility and design staff. The intent of this meeting is to identify critical conflicts and easement needs, discuss avoidance possibilities, consider relocation placements and costs, phasing and schedule, and identify Quality Level A or Quality Level B location needs. This meeting shall take place prior to the joint inspection but for complex projects and projects with a prevalence of utilities, it is recommended to hold at least two meetings.
Note on A77: Develop preliminary relocation layout sheets that show all existing utility facilities, locations of Quality Level A and Quality Level B subsurface utility engineering information, identified conflicts with the project, and proposed relocation alignments.
Note on A78: Develop utility relocation plans for utilities that have agreed to have KYTC’s consultant perform relocation design services. These plans shall provide a detailed horizontal and vertical alignment of the facilities to be relocated. Plan sheets, profile sheets, and cross sections shall be required. Plans shall adhere to the utility company’s standards and specifications.
Note on A85: Research of all documents necessary to determine property lines, existing easements, encumbrances and ownership including a copy of the deed with deed book and page number and available plats.
Note on A86: Using field evidence and research documentation to accurately establish property lines, existing Right of Way, existing easements, owner names, lessee names, and parcel numbers. Document on plans.
Note on A87: Calculate lines and areas of all proposed Right of Way and easement takings for each parcel. Depict all Right of Way and easements, including metes and bounds, on plans.
Note on A88: Prepare and check legal descriptions for each area of taking.
Note on A89: Complete Right of Way summary sheet including all affected parcels.
Note on A90: Prepare Right of Way strip map covering all affected parcels. Generate individual strip map sheets.
Note on A91: Generate the computer files of the Right of Way Plans, plot the original mylars, prepare electronic submittal of plans and deeds and submit plans, computer files, source deeds and proposed deed descriptions to the District Office. Detour runarounds or other maintenance of traffic plans that have impacts to the right of way or utilities shall be included in the Right of Way Plans. A set of prints of drainage and cross sections may also be required to be included in the submittal. Note: A set of prints is to be submitted to the KYTC Project Manager for review prior to submittal of Right of Way Plans, if requested.
Note on A92: Prepare R/W plan revisions as necessary. Post R/W Plan submittal and prior to the final construction plan submittal. Includes re-submittal of revised plans (mylars), 1 set of prints with changes marked in red, plats, deed descriptions and electronic files.
Note on A94: Research to see if any back source deeds exist on existing alignments which will not be reconstructed and are not included in Line 60.
Note on A95: Investigate old Investigate old recorded deeds that exist and perform actual research for each parcel necessary to determine property lines, existing easements, encumbrances and ownership including a copy of the deed with deed book and page number and available plats, if any.
Note on A96: Prepare legal deed descriptions for each parcel to be transferred to local government responsibility.
Note on A103: Load and organize electronic data files (manuscripts, centerline data, coordinates data, terrain models etc.). Note: In most cases much of this work was completed in Phase 1.
Note on A104: Using updated field data, modify and update the existing topography and terrain model.
Note on A105: Refine, adjust, and document the preferred horizontal and vertical alignments accommodating greater detail in tie-down points, approaches, detours, etc.
Note on A106: Analyze, document and submit for review and approval the proposed pavement design folder for each roadway, including pavement calculations, life cycle costs, typical sections and pavement details.
Note on A107: Finalize necessary templates and template transitions for all roadways. This includes each instance of a horizontal change in roadway edge of pavement with respect to the centerline.
Note on A108: Modify the preliminary roadway model or generate a new roadway model incorporating the proposed design into the initial roadway model, including cut/fill slopes, roadside ditches, etc. as necessary to define ditches and disturbed limits and enable the generation of cross-sections for all roadways. Note: The extent and degree of accuracy of the “final” roadway model is to correspond with the required guidelines of electronic deliverables. This effort of work is to be discussed at the Predesign Conference.
Note on A109: Design and depict on the plans (manuscript) all proposed construction details and graphics, including pavement, drainage, construction notes, etc.
Note on A110: Perform necessary work to create individual plan sheets, including dropping of sheet cells, masking, manipulation of text and notes, etc.
Note on A111: Perform necessary work to create individual profile sheets, including dropping profile, annotation of profile, drainage, ditches, notes, etc. Note: Though depiction of longitudinal storm sewers is generally performed on the profile sheets, they will be paid for as individual pipe sections under Item 92.
Note on A112: Drop cross sections onto sheet cells; add yardage quantities, details, notes, etc. Note: The majority of work required for the development of cross sections is under Item 85.
Note on A113: Determine location, grade, type of entrance, width and quantities and depict on the plans.
Note on A114: Modify the roadway model incorporating geotechnical report recommendations. Note: Length is based on expected area requiring changes due to geotechnical report, not entire project length.
Note on A116: Create and design pipe sections including quantities, notes and depicting them in the plans. Note: Includes cross drains, storm sewer, etc.
Note on A117: Create map describing the proposed drainage system and delineates drainage areas. Includes generating the individual sheets.
Note on A118: Develop and prepare drawing of alignment, profiles, sections, and plan to represent bridge situation survey.
Note on A119: Develop and prepare drawing of alignment, profiles, sections, and plan to represent culvert situation survey.
Note on A120: Develop and prepare drawing of alignment, profiles, sections, and plan to represent channel change, including stream mitigation requirements.
Note on A121: Conduct and document drainage analysis to determine frequency flows and required structure size of entrance pipes. Includes completion of forms.
Note on A122: Conduct and document drainage analysis to determine frequency flows and required structure size. Includes completion of forms.
Note on A123: Conduct and document drainage analysis to determine frequency flows and required structure size. Includes completion of forms.
Note on A124: Conduct and document drainage analysis to determine frequency flows, required structure size, location, and risk assessment. Includes completion of forms.
Note on A125: Conduct and document drainage analysis to determine frequency flows, required structure size, location, and risk assessment. Includes completion of forms.
Note on A126: Conduct and document drainage analysis to determine frequency flows, required structure size, location, and risk assessment. Includes completion of forms.
Note on A127: Conduct special drainage studies, which may include HEC-1, TR-20, TR-55, Unsteady Flow Models, FESWMS-2DH, Detention Basin Design, Energy Dissipater Design, Dynamic Culvert Design or other Hydrologic/Hydraulic design as deemed appropriate.
Note on A128: Determine hydraulic capacity (ditch size) and necessary channel lining of all ditches and channels. Includes documentation of design calculations and completion of forms. Note: Left and right sides are independent to each other and should be added for a combined total.
Note on A129: Determination of required erosion control items and depiction in the plans, including required calculations and generating the individual sheets. Includes documentation of design calculations and completion of forms. Note: Specific scope of work and level of effort is to be discussed at the Predesign Conference.
Note on A130: Conduct necessary calculations to determine structure types, and inlet spacing for the layout and design of storm sewer systems. Includes documentation of design calculations and completion of forms.
Note on A131: Conduct necessary calculations to determine pipe size, storage volumes, etc. for the layout and design of storm sewer systems. Includes documentation of design calculations and completion of forms.
Note on A132: Perform scour analysis as referenced in the FHWA HEC-18 and HEC-20 and the current Drainage Manual. Includes documentation of design calculations and completion of forms.
Note on A133: Copy, fold, bind, and assemble drainage folders.
Note on A134: Prepare required documentation, copy, fold, bind, and assemble the folder. Note: Folder contents are to conform to requirements outlined in the Drainage and Bridge Manuals.
Note on A135: Prepare required documentation, copy, fold, bind, and assemble the folder. Note: Folder contents are to conform to requirements outlined in the Drainage and Bridge Manuals.
Note on A143: Prepare layout sheet for the Construction Plans.
Note on A144: Prepare all typical sections including the proposed pavement design and other necessary details for each roadway, detour, and entrance.
Note on A145: Prepare geometric approval sheet, including all required alignments, curve data, coordinates, etc. for requesting approval of the interchange geometrics.
Note on A146: Prepare geometric approval sheet, including all required alignments, curve data, coordinates, etc., for requesting approval of the intersection geometrics.
Note on A147: Develop all coordinate control information, including proposed centerlines, event points, control points, and benchmarks with appropriate descriptions, and place into the plans in tabular form and generate individual sheets.
Note on A148: Prepare elevation development sheets including all geometric data and elevation data necessary.
Note on A149: Prepare details for striping plans as outlined in the Predesign Conference.
Note on A150: Calculate and document all quantities required for the construction of the final roadway and maintenance of traffic during construction, including permanent and temporary items.
Note on A155: Prepare and document cost estimates including bid prices for each item, using best engineering judgment, for inspections, meetings and final plan submittal.
Note on A156: Plot/print copies of plans including the necessary copies of plans for distribution at project milestones (inspections, meetings, etc.). Note: The number of sets of prints for meetings and inspections shall be determined at the Predesign Conference.
Note on A157: Complete any necessary and unexpected plan revisions that arise during the project that are beyond the control of the consultant, including revisions to plans required due to Right of Way Revisions that are not directly shown on the Right of Way Plans.
Note on A158: Generate the computer files of the final plans, plot the original mylars, prepare electronic submittal of plans and required files and submit plans, computer files and a list of General Notes to the District Office. Also includes submittal of a set of Review Plans and making any necessary changes identified by the roadway plan review.
Note on A160: Write and submit the required Traffic Control Plan, including the construction phasing for the project.
Note on A161: Prepare plans for maintenance of traffic, construction phasing and/or detours necessary for the construction of the project, including all phasing, special notes, signs, temporary pavement markings and quantities. When maintenance of traffic details have been completed, a Traffic Control Plan shall be prepared and submitted to the KYTC Project Manager to obtain the necessary approval signatures. Once approved, the notes and phasing details will be incorporated into the final construction plans.
Note on A177: Preparation and attendance by the project engineer and others, if necessary, to the preliminary line and grade inspection and preparation of the inspection report.
Note on A178: Preparation and attendance by the project engineer and drainage engineer to the drainage inspection and preparation of the inspection report.
Note on A179: Preparation and attendance by the project engineer and others, if necessary, to the final inspection and preparation of the inspection report.
Note on A180: Attendance by the project engineer and others, if necessary, to any project coordination meetings scheduled by the Project Manager and preparation of the meeting minutes.
Note on A181: Attendance by the project engineer and others if necessary, to any project team meetings scheduled by the Project Manager and preparation of the meeting minutes.
Note on A183: This item is applicable only for a project requiring a VE study or project where the KYTC project manager specifies that a VE study will be done. Attendance by the project engineer at the project briefing (normally 2 hours). Attendance by the project engineer at the VE recommendations briefing (normally 2 hours). Preparation of presentation for the project briefing. Preparation and compilation of project plans and documents for the VE team. Meeting attendance by the project engineer with KYTC project manager to review VE recommendations for further implementation.
Note on A184: This item is applicable to any project for which the KYTC project manager determines a standalone constructability meeting is warranted. The constructability review meeting is scheduled so as to facilitate the design decision making process and the development of final plans. Typical projects are those for which the project engineer anticipates a complicated maintenance of traffic plan or unusual construction work restrictions. Attendees should include the project engineer and others as necessary. Prepare meeting materials, including any constructability related details (draft phasing, maintenance of traffic, seasonal restrictions, as well as standard plan information) prior to the meeting. Write and distribute minutes after the meeting.
Note on A189: Prepare and maintain an up-to-date mailing list consisting of all potential property owners, local officials and other interested individuals.
Note on A190: Preparation and delivery of all necessary materials (project plans, photographs, exhibits, maps, handouts, etc.) to facilitate advisory committee and local officials meetings.
Note on A191: Attendance by the project engineer and others, if necessary, to the required meetings and preparation of the meeting minutes.
Note on A192: Preparation and delivery of all necessary materials (project plans, photographs, exhibits, maps, handouts, etc.) to facilitate public meetings/hearings.
Note on A193: Attendance by the project engineer and others, if necessary, to the public meeting.
Note on A194: Develop and distribute project newsletters to individuals on the project mailing list and other interested parties. Note: The specific extent of the type of newsletter to be prepared will be determined at the Predesign Conference.
Note on A195: Coordination with property owners with respect to project impacts. Note: The specific extent of property owner coordination will be determined at the Predesign Conference.
Note on A202: Note: This section is generally ONLY required with large projects that have multiple sections and consultants.
Note on A204: Review by a Senior Engineer to ensure the quality of the design and the quality of the plans.
Note on A205: Review by a Senior Engineer to ensure the quality of the design and the quality of the plans.