## FED FUNDED WITH ZVARIOUS
MODIFICATION OR AMENDMENT | STIP ADMINISTRATIVE MODIFICATION OR AMENDMENT NUMBER | APPROVAL DATE | COMMENTS | FUND PREFIX | FEDERAL PROJECT NUMBER | COUNTY | ID NUMBER | ROUTE NO. | LENGTH | BMP | EMP | PRIORITY | TYPE OF WORK | DESCRIPTION | SORTFLAG | PHASE | TYPE OF FUND | FISCAL YEAR SCHEDULE | TOTAL PHASE COST | FEDERAL PORTION | STATUS AUGUST 31, 2010 | ON NHS | IN 2010 HWP AS FY 2010 | STATUS OF FEDERAL FUNDS | CURRENT AMOUNT OF FEDERAL FUNDS OBLIGATED | CURRENT ADVANCE CONSTRUCT (AC) AMOUNT OF FEDERAL FUNDS | TOTAL PHASE COST CURRENT FEDERAL FUNDS PLUS CURRENT AC | FISCAL YEAR OF INITIAL PROGRAMMING OF FEDERAL FUNDS | FISCAL YEAR QUARTER OF INITIAL PROGRAMMING OF FEDERAL FUNDS | NAME OF LOCAL PUBLIC AGENCY
ADMINISTRATIVE MODIFICATION | 2010.179 | 2012-04-10 | ADD PROJECT TO STIP. NEW |  |  | ADAIR | 8-915 | KY 80 | 5.67 | 6.1 | 11.77 | SAFETY | SAFETY-HAZARD ELIM(P) | RECONSTRUCT SHOULDERS, INSTALL SIGNS, IMPROVE SIGHT DISTANCE AT VARIOUS LOCATIONS ON KY 80 FROM BIG CREEK BRIDGE WEST OF GRADYVILLE TO KY 61 WEST OF COLUMBIA. | 3 | C | SAF | 2012 | 1064500 | 1064500 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | ADAIR | 8-8505 | KY 206 |  | 0.75 | 0.85 | SAFETY | SAFETY-HAZARD ELIM(P) | IMPROVE SIGHT DISTANCE ON KY-206 NEAR KY 3491. (08CCN) (10CCR) | 3 | R | STP | 2011 | 50000 | 50000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.146 | 2011-11-22 | INCREASE THE FUNDING AMOUNT FOR THE R PHASE | STP | 5110002 | ADAIR | 8-8505 | KY 206 |  | 0.75 | 0.85 | SAFETY | SAFETY-HAZARD ELIM(P) | IMPROVE SIGHT DISTANCE ON KY-206 NEAR KY 3491. (08CCN) (10CCR) | 3 | R | STP | 2012 | 100000 | 100000 | ESTIMATED | N |  | OBLIGATED |  | 100000 | 100000 | 2012 | 1st QUARTER | N/A
[6 empty] | ADAIR | 8-8505 | KY 206 |  | 0.75 | 0.85 | SAFETY | SAFETY-HAZARD ELIM(P) | IMPROVE SIGHT DISTANCE ON KY-206 NEAR KY 3491. (08CCN) (10CCR) | 4 | U | STP | 2011 | 330000 | 330000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | ADAIR | 8-8505 | KY 206 |  | 0.75 | 0.85 | SAFETY | SAFETY-HAZARD ELIM(P) | IMPROVE SIGHT DISTANCE ON KY-206 NEAR KY 3491. (08CCN) (10CCR) | 5 | C | STP | 2012 | 500000 | 500000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.099 | 2011-07-14 | ADD PROJECT TO STIP. BREAKOUT FROM 99-911.00. NEW | HSIP | 9010056 | ALLEN | 3-911 | US 31E | 8.607 | 0 | 8.607 | SAFETY | SAFETY-HAZARD ELIM(P) | REPLACE GUARDRAIL END TREATMENTS ON US31E FROM THE TENNESSEE STATE LINE TO KY980 WEST OF SCOTTSVILLE. |  | C | SAF | 2011 | 42000 | 42000 |  |  |  | OBLIGATED | 42000 |  | 42000 | 2011 | 4th QUARTER | N/A
|  |  |  | BRO | 0303229 | ALLEN | 3-1071 | KY 98 | 0.1 | 1.785 | 1.885 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-98 (MP 1.835) OVER EAST FORK OF BAYS FORK C; 1.5 MI EAST OF JCT US 31E; (FUNCTIONALLY OBSOLETE, SR=49.9) 002B00023N (10CCR) | 2 | D | BRO | 2011 | 100000 | 100000 | ESTIMATED | N | 2010 | OBLIGATED | 100000 |  | 100000 | 2011 | 1st QUARTER | N/A
[6 empty] | ALLEN | 3-1071 | KY 98 | 0.1 | 1.785 | 1.885 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-98 (MP 1.835) OVER EAST FORK OF BAYS FORK C; 1.5 MI EAST OF JCT US 31E; (FUNCTIONALLY OBSOLETE, SR=49.9) 002B00023N (10CCR) | 3 | R | BRO | 2011 | 75000 | 75000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | ALLEN | 3-1071 | KY 98 | 0.1 | 1.785 | 1.885 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-98 (MP 1.835) OVER EAST FORK OF BAYS FORK C; 1.5 MI EAST OF JCT US 31E; (FUNCTIONALLY OBSOLETE, SR=49.9) 002B00023N (10CCR) | 4 | U | BRO | 2011 | 75000 | 75000 | ESTIMATED | N |  |  |  |  | 0
|  |  |  | BRO | 0303236 | ALLEN | 3-1071 | KY 98 | 0.1 | 1.785 | 1.885 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-98 (MP 1.835) OVER EAST FORK OF BAYS FORK C; 1.5 MI EAST OF JCT US 31E; (FUNCTIONALLY OBSOLETE, SR=49.9) 002B00023N (10CCR) | 5 | C | BRO | 2012 | 650000 | 650000 | ESTIMATED | N |  | OBLIGATED | 744000 |  | 744000 | 2012 | 2nd QUARTER | N/A
|  |  |  | BRZ | 0303234 | ALLEN | 3-1074 | CR 1372 | 0.1 | 1.338 | 1.438 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON CR-1372 (MP 1.388) OVER LANCASTER BRANCH; 1.4 MI SW OF JCT US 231; (STRUCTURALLY DEFICIENT, SR=32.9) 002C00025N | 2 | D | BRZ | 2012 | 140000 | 140000 | ESTIMATED | N |  | OBLIGATED | 140000 |  | 140000 | 2011 | 2nd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.215 | 2012-07-10 | ADD PROJECT TO STIP. NEW |  |  | ALLEN | 3-1080 | KY 2160 | 0.04 | 0.626 | 0.666 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 2160 OVER FLORIDA CREEK SOUTH OF INTERSECTION WITH HUNT LANE (CR 1155) (SR 40.8) 002B00048N |  | D | BRO | 2012 | 300000 | 300000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.215 | 2012-07-10 | ADD PROJECT TO STIP. NEW |  |  | ALLEN | 3-1081 | CR 1167 | 0.04 | 1.674 | 1.714 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON HADE BELL RD (CR 1167) OVER BAYS FORK 0.5 MILE N OF PARDUE RD (CR 1163)(SR 28.7)002C00012N |  | D | BRZ | 2012 | 150000 | 150000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.161 | 2012-01-31 | ADD PROJECT TO STIP. NEW |  |  | ANDERSON BOURBON BOYLE | 7-918 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | REPLACE GUARDRAIL END TREATMENTS ON VARIOUS ROUTES IN ANDERSON, BOURBON, BOYLE, CLARK, FAYETTE, JESSAMINE, MADISON, MERCER, MONTGOMERY, SCOTT, AND WOODFORD COUNTIES |  | C | SAF | 2012 | 907850 | 907850 | [6 empty] | 0
[6 empty] | ANDERSON | 7-1123 | CR 1020 | 0.1 | 1.496 | 1.596 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON CR-1020 (MP 1.546) OVER LITTLE BENSON(GREASY) CR; @FRANKLIN CO.LN.; (STRUCTURALLY DEFICIENT, SR=16.7) 003C00001N | 2 | D | BRZ | 2012 | 130000 | 130000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.177 | 2012-03-26 | ADD PROJECT TO STIP. NEW |  |  | ANDERSON |  | CR 5006 |  |  |  | SAFETY | SAFETY-RR PROTECTN(P) | ADD GATES TO EXISTING FLASHING LIGHTS AND BELL SYSTEM AT NORFOLK SOUTHERN RR CROSSING ON BOND LILLARD ROAD IN LAWRENCEBURG. (DOT# 735638F) |  | U | SAF | 2012 | 234000 | 234000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.177 | 2012-03-26 | ADD PROJECT TO STIP. NEW | RHPD | 0701051 | ANDERSON | 99-352.07 | CR 5006 | 0.05 | 0 | 0.05 | SAFETY | SAFETY-RR PROTECTN(P) | ADD GATES TO EXISTING FLASHING LIGHTS AND BELL SYSTEM AT NORFOLK SOUTHERN RR CROSSING ON BOND LILLARD ROAD IN LAWRENCEBURG. (DOT# 735638F) |  | C | SAF | 2012 | 15000 | 15000 |  |  |  | OBLIGATED | 225600 |  | 225600 | 2012 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.099 | 2011-07-14 | ADD PROJECT TO STIP. BREAKOUT FROM 99-911.00. NEW | HSIP | 9010055 | BALLARD CALLOWAY GRAVES | 1-902 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | REPLACE GUARDRAIL END TREATMENTS: BALLARD US5 1 (MP 5.1-5.2), US 60 (MP 1.8-11.6), CALLOWAY US 641 (MP 0-12), GRAVES US 45 (MP 20-21), MARSHALL US 641 (MP 0-5) US68 (MP 27-28), KY 348 (MP 6.35-6.49), KY 348 (MP 5.8-6.0), MCCRACKEN US 45 (MP 0.0-5.0) |  | C | SAF | 2011 | 890000 | 890000 |  |  |  | OBLIGATED | 890000 |  | 890000 | 2011 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.110 | 2011-08-25 | ADD PROJECT TO STIP. NEW | BRO | 3000855 | BALLARD CALLOWAY CARLISLE GRAVES MCCRACKEN MARSHALL TRIGG | 1-1139 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | INSTALL SCOUR COUNTER-MEASURES ON VARIOUS BRIDGES IN: BALLARD, CALLOWAY, GRAVES, CARLISLE, MCCRACKEN, MARSHALL AND TODD COUNTIES |  | C | BRO | 2011 | 340000 | 340000 |  |  |  | OBLIGATED | 374000 |  | 374000 | 2011 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.115 | 2011-09-01 | ADD PROJECT TO STIP. NEW | DR | 11KY001 | BALLARD CARLISLE | 1-1140 | US 51 |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | US 51 OHIO RIVER BRIDGE REPLACEMENT STUDY |  | D | KYD | 2011 | 500000 | 500000 |  |  |  | OBLIGATED | 500000 |  | 500000 | 2011 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.197 | 2012-05-30 | ADD PROJECT TO STIP. NEW |  |  | BALLARD | 1-1143 | KY 358 | 0.04 | 14.034 | 14.074 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 358 OVER CLAYTON CREEK APPR. 0.5 MILE NORTH OF KY 473 (SR 26.5) 004B00044N |  | D | BRO | 2012 | 280000 | 280000 | [6 empty] | 0
|  |  | ADDED D PHASE TO STIP FOR PHASE II DESIGN. R PHASE WAS ALREADY IN STIP (PER SIGNED PR-1). NEW | IMNH | 0652078 | BARREN | 3-13 | I 65 | 5 | 48 | 53 | RELIABILITY | MAJOR WIDENING(O) | TENN. STATE LINE-ELIZABETHTOWN; WIDEN TO 6-LANES FROM 0.6MI N OF THE KY 255 I-CHNG (B48) TO 1.0 MI S OF THE HART CO. LINE. (10CCR) | 3 | D | IM | 2011 | 1300000 | 1300000 | ESTIMATED | Y |  | OBLIGATED | 1300000 |  | 1300000 | 2011 | 1st QUARTER | N/A
[6 empty] | BARREN | 3-13 | I 65 | 5 | 48 | 53 | RELIABILITY | MAJOR WIDENING(O) | TENN. STATE LINE-ELIZABETHTOWN; WIDEN TO 6-LANES FROM 0.6MI N OF THE KY 255 I-CHNG (B48) TO 1.0 MI S OF THE HART CO. LINE. (10CCR) | 3 | R | IM | 2011 | 2000000 | 2000000 | ESTIMATED | Y |  |  |  |  | 0
|  |  | ADDED R PHASE TO STIP. C PHASE WAS ALREADY IN STIP (PER SIGNED PR-1). NEW | IMNH | 0652076 | BARREN | 3-13.1 | I 65 | 5 | 48 | 53 | RELIABILITY | MAJOR WIDENING(O) | WIDEN I-65 TO 6 LANES FROM PARK CITY EXIT (MP 48.00) TO CAVE CITY EXIT (MP 53.00). (10CCR) | 5 | R | IM | 2011 | 1200000 | 1200000 | ESTIMATED | Y |  | OBLIGATED | 1200000 |  | 1200000 | 2011 | 2nd QUARTER | N/A
|  |  | ADDED U PHASE TO STIP. C PHASE WAS ALREADY IN STIP (PER SIGNED PR-1). NEW | IMNH | 0652077 | BARREN | 3-13.1 | I 65 | 5 | 48 | 53 | RELIABILITY | MAJOR WIDENING(O) | WIDEN I-65 TO 6 LANES FROM PARK CITY EXIT (MP 48.00) TO CAVE CITY EXIT (MP 53.00). (10CCR) | 5 | U | IM | 2011 | 2000000 | 2000000 | ESTIMATED | Y |  | OBLIGATED | 2000000 |  | 2000000 | 2011 | 2nd QUARTER | N/A
[6 empty] | BARREN | 3-13.1 | I 65 | 5 | 48 | 53 | RELIABILITY | MAJOR WIDENING(O) | WIDEN I-65 TO 6 LANES FROM PARK CITY EXIT (MP 48.00) TO CAVE CITY EXIT (MP 53.00). (10CCR) | 5 | C | IM | 2012 | 13100000 | 13100000 | ESTIMATED | Y |  |  |  |  | 0
[6 empty] | BARREN | 3-13.11 | I 65 | 5 | 48 | 53 | RELIABILITY | MAJOR WIDENING(O) | WIDEN I-65 TO 6 LANES FROM PARK CITY EXIT (MP 48.00) TO CAVE CITY EXIT (MP 53.00).(10CCN) | 2 | D | NH | 2011 | 1000000 | 1000000 | ESTIMATED | Y | 2010 |  |  |  | 0
[6 empty] | BARREN | 3-13.11 | I 65 | 5 | 48 | 53 | RELIABILITY | MAJOR WIDENING(O) | WIDEN I-65 TO 6 LANES FROM PARK CITY EXIT (MP 48.00) TO CAVE CITY EXIT (MP 53.00).(10CCN) | 3 | R | NH | 2011 | 2500000 | 2500000 | ESTIMATED | Y |  |  |  |  | 0
[6 empty] | BARREN | 3-13.11 | I 65 | 5 | 48 | 53 | RELIABILITY | MAJOR WIDENING(O) | WIDEN I-65 TO 6 LANES FROM PARK CITY EXIT (MP 48.00) TO CAVE CITY EXIT (MP 53.00).(10CCN) | 4 | U | NH | 2011 | 2000000 | 2000000 | ESTIMATED | Y |  |  |  |  | 0
[6 empty] | BARREN | 3-13.11 | I 65 | 5 | 48 | 53 | RELIABILITY | MAJOR WIDENING(O) | WIDEN I-65 TO 6 LANES FROM PARK CITY EXIT (MP 48.00) TO CAVE CITY EXIT (MP 53.00).(10CCN) | 5 | C | NH | 2012 | 16000000 | 16000000 | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.116 | 2011-09-06 | INCREASE THE FUNDING AMOUNT. MOD | NHIM | 0652081 | BARREN | 3-13.11 | I 65 | 5 | 48 | 53 | RELIABILITY | MAJOR WIDENING(O) | TENN. STATE LINE-ELIZABETHTOWN; WIDEN I-65 TO 6 LANES FROM 1.1 MILE NORTH OF THE KY 255 INTERCHANGE (B48) TO 1.0 MILE SOUTH OF THE HART COUNTY LINE. | 5 | C | NH | 2011 | 25200000 | 25200000 | ESTIMATED | Y |  | OBLIGATED | 48030088 |  | 48030088 | 2011 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.116 | 2011-09-06 | ADD PROJECT TO STIP. NEW |  |  | BARREN | 3-13.12 | I 65 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | TENN. STATE LINE-ELIZABETHTOWN; WIDEN I-65 TO 6-LANES FROM 1.1 MI N OF THE KY 255 I-CHNG (B48) TO 1.0 MI S OF THE HART CO. LINE. |  | C | IM | 2011 | 16800000 | 16800000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.076 | 2011-05-09 | ADD DESIGN PHASE TO STIP USING HPP AND NH FUNDS. NEW |  |  | BARREN | 3-14 | I 65 | 5 | 53 | 53.956 | RELIABILITY | MAJOR WIDENING(O) | TENN. STATE LINE-ELIZABETHTOWN; WIDEN TO 6-LANES FROM 1.0MI S OF THE HART CO. LINE TO 0.5MI N OF THE KY 218 I-CHNG.(10CCR) | 3 | D | NH | 2011 | 1350988 | 1350988 | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.076 | 2011-05-09 | ADD DESIGN PHASE TO STIP USING HPP AND NH FUNDS. NEW |  |  | BARREN | 3-14 | I 65 | 5 | 53 | 53.956 | RELIABILITY | MAJOR WIDENING(O) | TENN. STATE LINE-ELIZABETHTOWN; WIDEN TO 6-LANES FROM 1.0MI S OF THE HART CO. LINE TO 0.5MI N OF THE KY 218 I-CHNG.(10CCR) | 3 | D | HPP | 2011 | 849012 | 849012 | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.131 | 2011-09-22 | CHANGE DESIGN PHASE FUNDING TO 100% NH. MOD | NH | 0652080 | BARREN HART | 3-14 | I 65 | 5 | 53 | 53.956 | RELIABILITY | MAJOR WIDENING(O) | TENN. STATE LINE-ELIZABETHTOWN: WIDEN I-65 TO 6-LANES FROM 1.0MI S OF THE HART CO. LINE TO 0.5MI N OF THE KY 218 I-CHNG.(10CCR) |  | D | NH | 2011 | 2200000 | 2200000 |  | Y |  | OBLIGATED |  | 2200000 | 2200000 | 2012 | 1st QUARTER | N/A
|  |  |  | NH | 0652082 | BARREN | 3-14 | I 65 | 5 | 53 | 53.956 | RELIABILITY | MAJOR WIDENING(O) | TENN. STATE LINE-ELIZABETHTOWN; WIDEN TO 6-LANES FROM 1.0MI S OF THE HART CO. LINE TO 0.4MI N OF THE KY 218 I-CHNG.(10CCR) | 3 | R | NH | 2011 | 2000000 | 2000000 | ESTIMATED | Y |  | OBLIGATED | 150000 |  | 150000 | 2012 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.192 | 2012-05-21 | ADD PHASE TO STIP. NEW | NH | 0652083 | BARREN HART | 3-14 | I 65 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | WIDEN I-65 TO 6-LANES SOUTH OF HART COUNTY LINE TO .5 MILE NORTH OF THE KY 218 INTERCHANGE |  | U | NH | 2012 | 250000 | 250000 |  | Y |  | OBLIGATED | 250000 |  | 250000 | 2012 | 3rd QUARTER | N/A
|  |  |  | IMD | 8368002 | BARREN | 3-143 | US 68 | 0.5 | 9.8 | 9.9 | SAFETY | SAFETY(P) | US 68 AT HIGHLAND GLEN INDUSTRIAL PARK, BARREN COUNTY. (2006KYD)(2006BOPC) (SEE 03-8600 FOR ADDITIONAL FUNDING). (10CCR) | 5 | C | KYD | 2011 | 172260 | 172260 | ESTIMATED | N | 2010 | OBLIGATED | 302442 |  | 302442 | 2011 | 3rd QUARTER | N/A
|  |  |  | DPR | 0037004 | BARREN | 3-185.01 | KY 70 | 5.5 | 0 | 5.246 | RELIABILITY | RECONSTRUCTION(O) | KY 70 FROM I-65 IN CAVE CITY TO THE PARK ENTRANCE AT CHAUMONT (SPECIAL FEDERAL APPROPRIATION OF PUBLIC LANDS FUNDS REQUIRED: FUNDS NOT CURRENTLY AVAILABLE FOR R, U & C).(98KYD) | 5 | C | HPP | 2011 | 403451 | 403451 | ESTIMATED | N | 2010 | OBLIGATED | 444080 |  | 444080 | 2012 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.053 | 2011-03-08 | ADD PROJECT TO STIP. BREAKOUT FROM 99-911.00. NEW | HSIP | 3311013 | BARREN | 3-906.00 | US 31E |  |  |  | RELIABILITY | RECONSTRUCTION(O) | CONSTRUCT DUAL LEFT TURN LANES ON US 31E AT TROJAN TRAIL IN GLASGOW |  | C | SAF | 2011 | 158750 | 158750 |  |  |  | OBLIGATED | 256792.8 |  | 256792.8 | 2011 | 2nd QUARTER | N/A
|  |  | THIS ITEM NUMBER IS A BREAKOUT OF ZVARIOUS NO. 99-352.06. NEW | RHPD | 3311014 | BARREN | 99-352.06 | US 31 |  |  |  | SAFETY | SAFETY-RR PROTECTN(P) | GLASGOW BYPASS (US 31) AT CSX RAILROAD CROSSING SOUTH OF WEST MAIN STREET (KY 80) IN GLASGOW. ADD GATES TO EXISTING FLASHING LIGHTS AND BELL SYSTEM. |  | C | SAF | 2011 | 290000 | 290000 |  |  |  | OBLIGATED | 262500 |  | 262500 | 2011 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.177 | 2012-03-26 | ADD PROJECT TO STIP. NEW |  |  | BARREN |  | US 68 |  |  |  | SAFETY | SAFETY-RR PROTECTN(P) | ADD GATES TO EXISTING FLASHING LIGHTS AND BELL SYSTEM AT CSX RAILROAD CROSSING ON US 68 AT WEST CORPORATE LIMITS OF GLASGOW. (DOT# 348812V) |  | U | SAF | 2012 | 225000 | 225000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.177 | 2012-03-26 | ADD PROJECT TO STIP. NEW | RHPD | 8368003 | BARREN | 99-352.07 | US 68 | 0.001 | 10.343 | 10.344 | SAFETY | SAFETY-RR PROTECTN(P) | ADD GATES TO EXISTING FLASHING LIGHTS AND BELL SYSTEM AT CSX RAILROAD CROSSING ON US 68 AT WEST CORPORATE LIMITS OF GLASGOW. (DOT# 348812V) |  | C | SAF | 2012 | 15000 | 15000 |  |  |  | OBLIGATED | 217500 |  | 217500 | 2012 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.084 | 2011-06-06 | ADD PROJECT TO STIP. BREAKOUT FROM 99-911.00. NEW |  |  | BATH | 9-905 | KY 211 | 6.949 | 0 | 6.949 | SAFETY | SAFETY-HAZARD ELIM(P) | SAFETY IMPROVEMENTS ON KY 211 FROM KY 36 TO US 60 AT SALT LICK: REMOVE AND/OR ADD GUARDRAIL, REPLACE AND/OR EXTEND CULVERT AND ENTRANCE PIPES, RESHAPE DITCHES AND SHOULDERS AND MOVE UTILITIES. |  | U | SAF | 2011 | 60000 | 60000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.084 | 2011-06-06 | ADD PROJECT TO STIP. BREAKOUT FROM 99-911.00. NEW | HSIP | 5314002 | BATH | 9-905 | KY 211 | 6.949 | 0 | 6.949 | SAFETY | SAFETY-HAZARD ELIM(P) | SAFETY IMPROVEMENTS ON KY 211 FROM KY 36 TO US 60 AT SALT LICK: REMOVE AND/OR ADD GUARDRAIL, REPLACE AND/OR EXTEND CULVERT AND ENTRANCE PIPES, RESHAPE DITCHES AND SHOULDERS AND MOVE UTILITIES. |  | C | SAF | 2011 | 850000 | 850000 |  |  |  | OBLIGATED | 850000 |  | 850000 | 2011 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.064 | 2011-04-12 | ADD PROJECT TO STIP. BREAKOUT FROM 99-911.00. NEW | HSIP | 0251025 | BELL | 11-916 | US 25E |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | REMOVE MEDIAN/CROSSOVERS AND CONSTRUCT TURN LANE ON US 25E 1.0 MILE NORTH OF HOLLYWOOD DRIVE (KY441) IN MIDDLESBORO AND IMPROVE INTERSECTION ON US 25E FROM US 119 TO KY 2015 IN PINEVILLE. |  | C | SAF | 2011 | 150000 | 150000 |  | Y |  | OBLIGATED | 177000 |  | 177000 | 2011 | 4th QUARTER | N/A
[6 empty] | BELL | 11-1063 | US 25E | 0.1 | 15.994 | 15.999 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON US-25E OVER TURKEY CREEK SLOUGH (B02). (SR=29.5): (007B00002N) | 3 | R | BRO | 2011 | 290000 | 290000 | ESTIMATED | Y | 2010 |  |  |  | 0
[6 empty] | BELL | 11-1063 | US 25E | 0.1 | 15.994 | 15.999 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON US-25E OVER TURKEY CREEK SLOUGH (B02). (SR=29.5): (007B00002N) | 4 | U | BRO | 2011 | 220000 | 220000 | ESTIMATED | Y | 2010 |  |  |  | 0
[6 empty] | BELL | 11-1063 | US 25E | 0.1 | 15.994 | 15.999 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON US-25E OVER TURKEY CREEK SLOUGH (B02). (SR=29.5): (007B00002N) | 5 | C | BRO | 2011 | 680000 | 680000 | ESTIMATED | Y |  |  |  |  | 0
|  |  |  | BRZ | 1103232 | BELL | 11-1079 | KY 2011 | 0.1 | 8.448 | 8.548 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-2011 (MP 8.498) OVER RED BIRD CREEK; .55 MI SOU. OF JCT KY 66; (NOT DEFICIENT, SR=3.5) 007B00074N | 2 | D | BRX | 2012 | 150000 | 150000 | ESTIMATED | N |  | OBLIGATED | 150000 |  | 150000 | 2011 | 1st QUARTER | N/A
|  |  |  | BRZ | 1103245 | BELL | 11-1083 | CR 1327 | 0.1 | 0 | 0.1 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON CR-1327 (MP 0.014) OVER LEFT FORK STRAIGHT CREEK; .10 MI W OF JCT KY 66; (STRUCTURALLY DEFICIENT, SR=2) 007C00048N | 2 | D | BRZ | 2012 | 250000 | 250000 | ESTIMATED | N |  | OBLIGATED | 250000 |  | 250000 | 2011 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.216 | 2012-07-25 | ADD PROJECT PHASE TO STIP. NEW |  |  | BELL | 11-1083 | CR 1327 | 0.1 | 0 | 0.1 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON CR-1327 (MP 0.014) OVER LEFT FORK STRAIGHT CREEK; .10 MI W OF JCT KY 66; (STRUCTURALLY DEFICIENT, SR=2) 007C00048N | 2 | R | BRZ | 2012 | 175000 | 175000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.216 | 2012-07-25 | ADD PROJECT PHASE TO STIP. NEW |  |  | BELL | 11-1083 | CR 1327 | 0.1 | 0 | 0.1 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON CR-1327 (MP 0.014) OVER LEFT FORK STRAIGHT CREEK; .10 MI W OF JCT KY 66; (STRUCTURALLY DEFICIENT, SR=2) 007C00048N | 2 | U | BRZ | 2012 | 200000 | 200000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.197 | 2012-05-30 | ADD PROJECT TO STIP. NEW | BRZ | 1103252 | BELL | 11-1093 | CR 1184 | 0.04 | 0.01 | 0.05 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON DAVIS OXENDINE RD (CR 1184) OVER HANCES CREEK AT JCT WITH KY 1344(SR 12.9) 007C00061N |  | D | BRZ | 2012 | 250000 | 250000 |  |  |  | OBLIGATED | 250000 |  | 250000 | 2012 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.126 | 2011-09-14 | ADD PROJECT TO STIP. BREAKOUT FROM 99-354.06. NEW | STP | 0251028 | BELL | 11-2032 | US 25E | 0.5 | 0 | 0.5 | SAFETY | SAFETY(P) | CUMBERLAND GAP TUNNEL; REPAIR ROADWAY SUBGRADE AND PAVEMENT FAILURES CAUSED BY SUBTERRANEAN DRAINAGE |  | C | STP | 2011 | 3500000 | 3500000 |  |  |  | OBLIGATED | 1534341.68 |  | 1534341.68 | 2011 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.214 | 2012-07-05 | ADD PROJECT TO STIP. NEW |  |  | BELL |  | KY 66 |  |  |  | SAFETY | SAFETY(P) | INSTALLATION OF RAILROAD WARNING DEVICES CONSISTING OF GATES AT THE CSX RR CROSSING OF KY 66 (PINE STREET) JUST NORTH OF THE CUMBERLAND RIVER BRIDGE IN PINEVILLE. (ARR DOT 344 959G) |  | U | RHPD | 2012 | 225000 | 225000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.214 | 2012-07-05 | ADD PROJECT TO STIP. NEW |  |  | BELL |  | KY 66 |  |  |  | SAFETY | SAFETY(P) | INSTALLATION OF RAILROAD WARNING DEVICES CONSISTING OF GATES AT THE CSX RR CROSSING OF KY 66 (PINE STREET) JUST NORTH OF THE CUMBERLAND RIVER BRIDGE IN PINEVILLE. (ARR DOT 344 959G) |  | C | RHPD | 2012 | 15000 | 15000 | [6 empty] | 0
[6 empty] | BOONE | 6-9 | I 275 | 0.6 | 13.275 | 13.892 | SAFETY | BRIDGE INSPECTION(P) | I-275 BRIDGE OVER THE OHIO RIVER NEAR LAWRENCEBURG, INDIANA (B52); JOINT PROJECT WITH INDIANA TO PERFORM FRACTURE CRITICAL INSPECTION. (008B00052N) | 5 | C | IM | 2011 | 20000 | 20000 | ESTIMATED | Y | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.016 | 2010-11-15 | TIP MOD #31. REVISE FUNDING AMOUNT IN THE TIP AND DESCRIPTION. MOD |  |  | BOONE | 6-9 | I 275 | 0.6 | 13.275 | 13.892 | SAFETY | BRIDGE INSPECTION(P) | ON-GOING BRIDGE INSPECTIONS--IR 275 BRIDGE OVER THE OHIO RIVER NEAR LAWRENCEBURG, INDIANA | 5 | C | IM | 2011 | 20000 | 20000 | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.170 | 2012-03-22 | TIP AMENDMENT #6. REVISE DESCRIPTION AND FY. MOD |  |  | BOONE | 6-9 | I 275 | 0.6 | 13.275 | 13.892 | SAFETY | BRIDGE INSPECTION(P) | ON-GOING INSPECTIONS--FRACTURE CRITICAL INSPECTIONS ON IR 275 BRIDGE OVER THE OHIO RIVER NEAR LAWRENCEBURG, INDIANA, CONDUCTED EVERY 2 YEARS. | 5 | C | IM | 2012 | 20000 | 20000 | ESTIMATED | Y |  |  |  |  | 0
[6 empty] | BOONE | 6-14 | I 75 | 0.1 | 177.659 | 178.345 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | RECONSTRUCT THE KY-536 (MT. ZION ROAD) INTERCHANGE. | 3 | R | IM | 2011 | 3940000 | 3940000 | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.017 | 2010-11-18 | TIP AMENDMENT #31. INCREASE FUNDING AMOUNT IN TIP. MOD |  |  | BOONE | 6-14 | I 75 | 0.1 | 177.659 | 178.345 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | RECONSTRUCT THE KY-536 (MT. ZION ROAD) INTERCHANGE. TOLL CREDITS | 3 | R | IM | 2011 | 3940000 | 3940000 | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.210 | 2012-06-27 | TIP AMENDMENT #9, FY 2012-15. CHANGE FY. MOD |  |  | BOONE | 6-14 | I 75 | 0.1 | 177.659 | 178.345 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | RECONSTRUCT THE KY-536 (MT. ZION ROAD) INTERCHANGE. TOLL CREDITS | 3 | R | IM | 2013 | 3940000 | 3940000 | ESTIMATED | Y |  |  |  |  | 0
[6 empty] | BOONE | 6-14 | I 75 | 0.1 | 177.659 | 178.345 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | RECONSTRUCT THE KY-536 (MT. ZION ROAD) INTERCHANGE. | 4 | U | IM | 2013 | 2480000 | 2480000 | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.017 | 2010-11-18 | TIP AMENDMENT #31. INCREASE FUNDING AMOUNT IN TIP. MOD |  |  | BOONE | 6-14 | I 75 | 0.1 | 177.659 | 178.345 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | RECONSTRUCT THE KY-536 (MT. ZION ROAD) INTERCHANGE. TOLL CREDITS | 3 | U | IM | 2013 | 2480000 | 2480000 | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.030 | 2011-01-27 | TIP AMENDMENT #32. CHANGE FY. MOD |  |  | BOONE | 6-14 | I 75 | 0.1 | 177.659 | 178.345 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | RECONSTRUCT THE KY-536 (MT. ZION ROAD) INTERCHANGE. TOLL CREDITS | 3 | U | IM | 2011 | 2480000 | 2480000 | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.210 | 2012-06-27 | TIP AMENDMENT #9, FY 2012-15. CHANGE FY. MOD |  |  | BOONE | 6-14 | I 75 | 0.1 | 177.659 | 178.345 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | RECONSTRUCT THE KY-536 (MT. ZION ROAD) INTERCHANGE. TOLL CREDITS | 3 | U | IM | 2013 | 2480000 | 2480000 | ESTIMATED | Y |  |  |  |  | 0
[6 empty] | BOONE | 6-14 | I 75 | 0.1 | 177.659 | 178.345 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | RECONSTRUCT THE KY-536 (MT. ZION ROAD) INTERCHANGE. | 5 | C | IM | 2014 | 8000000 | 8000000 | ESTIMATED | [5 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.017 | 2010-11-18 | TIP AMENDMENT #31. DECREASE FUNDING AMOUNT IN TIP. MOD |  |  | BOONE | 6-14 | I 75 | 0.1 | 177.659 | 178.345 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | RECONSTRUCT THE KY-536 (MT. ZION ROAD) INTERCHANGE. TOLL CREDITS | 3 | C | IM | 2014 | 8000000 | 8000000 | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.030 | 2011-01-27 | TIP AMENDMENT #32. INCREASE FUNDING AMOUNT. MOD |  |  | BOONE | 6-14 | I 75 | 0.1 | 177.659 | 178.345 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | RECONSTRUCT THE KY-536 (MT. ZION ROAD) INTERCHANGE. TOLL CREDITS |  | C | IM | 2014 | 20810000 | 20810000 |  | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.210 | 2012-06-27 | TIP AMENDMENT #9, FY 2012-15. CHANGE FY. MOD |  |  | BOONE | 6-14 | I 75 | 0.1 | 177.659 | 178.345 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | RECONSTRUCT THE KY-536 (MT. ZION ROAD) INTERCHANGE. TOLL CREDITS |  | C | IM | 2015 | 20810000 | 20810000 |  | Y |  |  |  |  | 0
[6 empty] | BOONE | 6-14.5 | I 75 | 4.8 | 175.314 | 180.106 | RELIABILITY | MAJOR WIDENING(O) | ADD AUXILIARY LANES ON I-71/75 FROM KY-338 TO US-42 (NB & SB) AS PER THE INTERCHANGE MODIFICATION REPORT (IMR).(10CCR) | 2 | D | IM | 2011 | 1500000 | 1500000 | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.030 | 2011-01-27 | OKI TIP AMENDMENT #32. ADD TO TIP. DESCRIPTION CHANGE AND MP IN STIP. MOD | IM | 0757137 | BOONE | 6-14.5 | I 75 | 2.1 | 178.039 | 180.106 | RELIABILITY | MAJOR WIDENING(O) | CONSTRUCT AUXILIARY LANES ON IR 71/75 FROM KY-536 TO US-42 PER THE INTERCHANGE MODIFICATION REPORT . MP 178.039 TO 180.106 (TOLL CREDITS) | 2 | D | IM | 2011 | 1500000 | 1500000 | ESTIMATED | Y |  | OBLIGATED | 1500000 |  | 1500000 | 2011 | 2nd QUARTER | N/A
[6 empty] | BOONE | 6-14.5 | I 75 | 4.8 | 175.314 | 180.106 | RELIABILITY | MAJOR WIDENING(O) | ADD AUXILIARY LANES ON I-71/75 FROM KY-338 TO US-42 (NB & SB) AS PER THE INTERCHANGE MODIFICATION REPORT (IMR).(10CCR) | 3 | R | IM | 2012 | 6300000 | 6300000 | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.030 | 2011-01-27 | OKI TIP AMENDMENT #32. ADD TO TIP. DESCRIPTION CHANGE , MP, AND FY IN STIP. MOD |  |  | BOONE | 6-14.5 | I 75 | 2.1 | 178.039 | 180.106 | RELIABILITY | MAJOR WIDENING(O) | CONSTRUCT AUXILIARY LANES ON IR 71/75 FROM KY-536 TO US-42 PER THE INTERCHANGE MODIFICATION REPORT . MP 178.039 TO 180.106 (TOLL CREDITS) | 2 | R | IM | 2011 | 6300000 | 6300000 | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.210 | 2012-06-27 | TIP AMENDMENT #9, FY 2012-15. CHANGE FY. MOD |  |  | BOONE | 6-14.5 | I 75 | 2.1 | 178.039 | 180.106 | RELIABILITY | MAJOR WIDENING(O) | CONSTRUCT AUXILIARY LANES ON IR 71/75 FROM KY-536 TO US-42 PER THE INTERCHANGE MODIFICATION REPORT . MP 178.039 TO 180.106 (TOLL CREDITS) | 2 | R | IM | 2013 | 6300000 | 6300000 | ESTIMATED | Y |  |  |  |  | 0
[6 empty] | BOONE | 6-14.5 | I 75 | 4.8 | 175.314 | 180.106 | RELIABILITY | MAJOR WIDENING(O) | ADD AUXILIARY LANES ON I-71/75 FROM KY-338 TO US-42 (NB & SB) AS PER THE INTERCHANGE MODIFICATION REPORT (IMR).(10CCR) | 4 | U | IM | 2012 | 800000 | 800000 | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.030 | 2011-01-27 | OKI TIP AMENDMENT #32. ADD TO TIP. DESCRIPTION CHANGE, MP, AND FY IN STIP. MOD |  |  | BOONE | 6-14.5 | I 75 | 2.1 | 178.039 | 180.106 | RELIABILITY | MAJOR WIDENING(O) | CONSTRUCT AUXILIARY LANES ON IR 71/75 FROM KY-536 TO US-42 PER THE INTERCHANGE MODIFICATION REPORT . MP 178.039 TO 180.106 (TOLL CREDITS) | 4 | U | IM | 2011 | 800000 | 800000 | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.210 | 2012-06-27 | TIP AMENDMENT #9, FY 2012-15. CHANGE FY. MOD |  |  | BOONE | 6-14.5 | I 75 | 2.1 | 178.039 | 180.106 | RELIABILITY | MAJOR WIDENING(O) | CONSTRUCT AUXILIARY LANES ON IR 71/75 FROM KY-536 TO US-42 PER THE INTERCHANGE MODIFICATION REPORT . MP 178.039 TO 180.106 (TOLL CREDITS) | 4 | U | IM | 2013 | 800000 | 800000 | ESTIMATED | Y |  |  |  |  | 0
[6 empty] | BOONE | 6-14.5 | I 75 | 4.8 | 175.314 | 180.106 | RELIABILITY | MAJOR WIDENING(O) | ADD AUXILIARY LANES ON I-71/75 FROM KY-338 TO US-42 (NB & SB) AS PER THE INTERCHANGE MODIFICATION REPORT (IMR). | 5 | C | IM | 2013 | 17600000 | 17600000 | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.030 | 2011-01-27 | OKI TIP AMENDMENT #32. ADD TO TIP. DESCRIPTION CHANGE AND MP IN STIP. MOD |  |  | BOONE | 6-14.5 | I 75 | 2.1 | 178.039 | 180.106 | RELIABILITY | MAJOR WIDENING(O) | CONSTRUCT AUXILIARY LANES ON IR 71/75 FROM KY-536 TO US-42 PER THE INTERCHANGE MODIFICATION REPORT . MP 178.039 TO 180.106 (TOLL CREDITS) |  | C | IM | 2013 | 17600000 | 17600000 |  | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.210 | 2012-06-27 | TIP AMENDMENT #9, FY 2012-15. CHANGE FY. MOD |  |  | BOONE | 6-14.5 | I 75 | 2.1 | 178.039 | 180.106 | RELIABILITY | MAJOR WIDENING(O) | CONSTRUCT AUXILIARY LANES ON IR 71/75 FROM KY-536 TO US-42 PER THE INTERCHANGE MODIFICATION REPORT . MP 178.039 TO 180.106 (TOLL CREDITS) |  | C | IM | 2016 | 17600000 | 17600000 |  | Y |  |  |  |  | 0
[6 empty] | BOONE | 6-18 | I 75 | 0.1 | 175.217 | 175.622 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | RECONSTRUCT THE KY-338 (RICHWOOD ROAD) INTERCHANGE. (FUNDING FOR IMR SHOWN UNDER 6-14.01) (10CCR) | 3 | R | IM | 2011 | 2850000 | 2850000 | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.017 | 2010-11-18 | OKI TIP AMENDMENT #31. INCREASE FUNDING AMOUNT IN TIP. MOD |  |  | BOONE | 6-18 | I 75 | 0.1 | 175.217 | 175.622 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | RECONSTRUCT THE KY-338 (RICHWOOD ROAD) INTERCHANGE. TOLL CREDITS | 3 | R | IM | 2011 | 2850000 | 2850000 | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.210 | 2012-06-27 | TIP AMENDMENT #9, FY 2012-15. CHANGE FY. MOD |  |  | BOONE | 6-18 | I 75 | 0.1 | 175.217 | 175.622 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | RECONSTRUCT THE KY-338 (RICHWOOD ROAD) INTERCHANGE. TOLL CREDITS | 3 | R | IM | 2013 | 2850000 | 2850000 | ESTIMATED | Y |  |  |  |  | 0
[6 empty] | BOONE | 6-18 | I 75 | 0.1 | 175.217 | 175.622 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | RECONSTRUCT THE KY-338 (RICHWOOD ROAD) INTERCHANGE. (FUNDING FOR IMR SHOWN UNDER 6-14.01) (10CCR) | 4 | U | IM | 2011 | 1800000 | 1800000 | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.017 | 2010-11-18 | TIP AMENDMENT #31. INCREASE FUNDING AMOUNT IN TIP. MOD |  |  | BOONE | 6-18 | I 75 | 0.1 | 175.217 | 175.622 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | RECONSTRUCT THE KY-338 (RICHWOOD ROAD) INTERCHANGE. TOLL CREDITS | 3 | U | IM | 2011 | 1800000 | 1800000 | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.210 | 2012-06-27 | TIP AMENDMENT #9, FY 2012-15. CHANGE FY. MOD |  |  | BOONE | 6-18 | I 75 | 0.1 | 175.217 | 175.622 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | RECONSTRUCT THE KY-338 (RICHWOOD ROAD) INTERCHANGE. TOLL CREDITS | 3 | U | IM | 2013 | 1800000 | 1800000 | ESTIMATED | Y |  |  |  |  | 0
[6 empty] | BOONE | 6-18 | I 75 | 0.1 | 175.217 | 175.622 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | RECONSTRUCT THE KY-338 (RICHWOOD ROAD) INTERCHANGE. (FUNDING FOR IMR SHOWN UNDER 6-14.01) (10CCR) | 5 | C | IM | 2013 | 10000000 | 10000000 | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.017 | 2010-11-18 | TIP AMENDMENT #31. DECREASE FUNDING AMOUNT IN TIP. MOD |  |  | BOONE | 6-18 | I 75 | 0.1 | 175.217 | 175.622 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | RECONSTRUCT THE KY-338 (RICHWOOD ROAD) INTERCHANGE. TOLL CREDITS | 3 | C | IM | 2013 | 10530000 | 10530000 | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.030 | 2011-01-27 | TIP AMENDMENT #32. INCREASE FUNDING AMOUNT. MOD |  |  | BOONE | 6-18 | I 75 | 0.1 | 175.217 | 175.622 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | RECONSTRUCT THE KY-338 (RICHWOOD ROAD) INTERCHANGE. TOLL CREDITS |  | C | IM | 2013 | 20250000 | 20250000 |  | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.210 | 2012-06-27 | TIP AMENDMENT #9, FY 2012-15. CHANGE FY. MOD |  |  | BOONE | 6-18 | I 75 | 0.1 | 175.217 | 175.622 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | RECONSTRUCT THE KY-338 (RICHWOOD ROAD) INTERCHANGE. TOLL CREDITS |  | C | IM | 2016 | 20250000 | 20250000 |  | Y |  |  |  |  | 0
[6 empty] | BOONE | 6-18.01 | I 75 | 0.1 | 175.314 | 175.414 | ECONOMIC DEVELOPMENT | PREFINANCD CONVRSN(O) | RECONSTRUCT THE KY-338 (RICHWOOD ROAD) INTERCHANGE. (ADDITIONAL FUNDING FOR C PHASE) (10CCN) | 5 | C | IM | 2011 | 10530000 | 10530000 | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.210 | 2012-06-27 | TIP AMENDMENT #9, FY 2012-15. CHANGE FY. MOD |  |  | BOONE | 6-18.01 | I 75 | 0.1 | 175.314 | 175.414 | ECONOMIC DEVELOPMENT | PREFINANCD CONVRSN(O) | RECONSTRUCT THE KY-338 (RICHWOOD ROAD) INTERCHANGE. (ADDITIONAL FUNDING FOR C PHASE) (10CCN) | 5 | C | IM | 2016 | 10530000 | 10530000 | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.133 | 2011-09-27 | ADD PROJECT. BREAKOUT FROM ZVARIOUS ITEM NO. 99-65.09. NEW | IM | 2759124 | BOONE | 6-76 | I 275 | 0.1 | 4.083 | 4.183 | RELIABILITY | BRIDGE REHAB(P) | PLACE DECK OVERLAY AND REPLACE JOINTS ON THE KY 212 BRIDGE OVER I-275 |  | C | IM | 2012 | 400000 | 400000 |  | Y |  | OBLIGATED | 481250 |  | 481250 | 2012 | 3rd QUARTER | N/A
|  |  |  | HPP-STP | 3002225 | BOONE | 6-193 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | CONSTRUCT SOUTH AIRFIELD RD (AKA SOUTH AIRFIELD BYPASS),BOONE COUNTY,KENTUCKY. (2005HPP-KY140)(ALL WORK BY CO. PER AGREEMENT. LOCAL FUNDS ($10.43M) AND "SNK" FUNDS ($5.0M) SHOWN UNDER 6-193.02 & 6-193.03. TOTAL PROJECT COST=$17.83 AS PER OKI TIP)(08CCR) | 5 | C | HPP | 2011 | 2084760 | 2084760 | ESTIMATED | N | 2010 | OBLIGATED | 17184760 |  | 17184760 | 2011 | 2nd QUARTER | BOONE COUNTY FISCAL COURT
ADMINISTRATIVE MODIFICATION | 2010.052 | 2011-03-08 | TIP MOD #33. INCREASE FUNDING AMOUNT AND CHANGE DESCRIPTION. MOD |  |  | BOONE | 6-193 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | NEW 4 AND 5 LANE ROADWAY FROM KY 18 TO TURFWAY ROAD | 5 | C | HPP | 2011 | 2400000 | 2400000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.052 | 2011-03-08 | TIP MOD #33. ADD PROJECT. NEW | DPR | 0181003 | BOONE | 6-193.01 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | NEW 4 AND 5 LANE ROADWAY FROM KY 18 TO TURFWAY ROAD | 5 | C | KYD | 2011 | 245000 | 245000 | ESTIMATED | N |  | OBLIGATED | 245000 |  | 245000 | 2011 | 3rd QUARTER | N/A
[6 empty] | BOONE | 6-193.02 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | CONSTRUCT SOUTH AIRFIELD ROAD (AKA SOUTH AIRFIELD BYPASS), BOONE COUNTY, KENTUCKY. (INITIAL "SNK" FUNDING FOR C PHASE; "HPP" FUNDING SHOWN UNDER 193.00)(SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP)(08CCR) | 5 | C | SNK | 2011 | 9600000 | 9600000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | BOONE | 6-193.03 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | CONSTRUCT SOUTH AIRFIELD ROAD (AKA SOUTH AIRFIELD BYPASS), BOONE COUNTY, KENTUCKY. (ADDITIONAL "SNK" FUNDING FOR C PHASE)(SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | 5 | C | SNK | 2011 | 2500000 | 2500000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | BOONE | 6-319 |  |  |  |  | RELIABILITY | BIKE/PED FACIL(O) | BOONE COUNTY GUNPOWDER CREEK TRAIL SYSTEM. FUNDING TO BE USED FOR THE PURCHASE OF APPROXIMATELY 85 ACRES OF PROPERTY ADJACENT TO GUNPOWDER CREEK AND IMPROVEMENTS. THE SITE WILL BE USED FOR FUTURE CONSTRUCTION OF A TRAIL SYSTEM. (2008BOPC) | 5 | C | KYD | 2011 | 427500 | 427500 | ESTIMATED |  | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.188 | 2012-05-17 | OKI AMENDMENT #8. ADD PROJECT TO STIP. TOLL CREDITS AS MATCH. NEW | CM | 8124015 | BOONE | 6-367 |  |  |  |  | SAFETY | SAFETY(P) | CONSTRUCT TURN LANES AT THE INTERSECTION OF US 42 AND KY 842 |  | D | CM | 2013 | 750000 | 750000 |  |  |  | OBLIGATED | 750000 |  | 750000 | 2012 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.188 | 2012-05-17 | OKI AMENDMENT #8. ADD PROJECT TO STIP. TOLL CREDITS AS MATCH. NEW |  |  | BOONE | 6-367 |  |  |  |  | SAFETY | SAFETY(P) | CONSTRUCT TURN LANES AT THE INTERSECTION OF US 42 AND KY 842 |  | R | CM | 2013 | 1750000 | 1750000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.188 | 2012-05-17 | OKI AMENDMENT #8. ADD PROJECT TO STIP. TOLL CREDITS AS MATCH. NEW |  |  | BOONE | 6-367 |  |  |  |  | SAFETY | SAFETY(P) | CONSTRUCT TURN LANES AT THE INTERSECTION OF US 42 AND KY 842 |  | U | CM | 2013 | 150000 | 150000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.188 | 2012-05-17 | OKI AMENDMENT #8. ADD PROJECT TO STIP. TOLL CREDITS AS MATCH. NEW |  |  | BOONE | 6-367 |  |  |  |  | SAFETY | SAFETY(P) | CONSTRUCT TURN LANES AT THE INTERSECTION OF US 42 AND KY 842 |  | C | CM | 2014 | 2500000 | 2500000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.028 | 2011-01-10 | THIS PROJECT IS A DUPLICATE IN THE STIP. THE PHASE IS BEING REMOVED TO SHOW THE PROJECT NOT BEING USED. SEE 6-400.06 MOD |  |  | BOONE | 6-400.03 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | NORTHERN KENTUCKY RIDESHARE PROGRAM. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) SEE 6-400.06 | 5 |  | SNK | 2011 | 50000 | 50000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.028 | 2011-01-10 | THIS PROJECT IS A DUPLICATE IN THE STIP. THE PHASE IS BEING REMOVED TO SHOW THE PROJECT NOT BEING USED. SEE 6-400.06 MOD |  |  | BOONE | 6-400.05 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | NORTHERN KENTUCKY RIDESHARE PROGRAM. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) SEE 6-400.06 | 5 |  | SNK | 2011 | 50000 | 50000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | BOONE | 6-400.06 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | NORTHERN KENTUCKY RIDESHARE PROGRAM. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | 5 | C | SNK | 2011 | 50000 | 50000 | ESTIMATED | N |  |  |  |  | 0
|  |  |  | STPM | 3002226 | BOONE | 6-400.07 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | NORTHERN KENTUCKY RIDESHARE PROGRAM. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | 5 | C | SNK | 2012 | 50000 | 50000 | ESTIMATED | N |  | OBLIGATED | 35500 |  | 35500 | 2011 | 3rd QUARTER | OKI
|  |  |  | STPM | 3002234 | BOONE | 6-400.08 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | NORTHERN KENTUCKY RIDESHARE PROGRAM. | 5 | C | SNK | 2013 | 44000 | 44000 | ESTIMATED |  |  | OBLIGATED | 59388 |  | 59388 | 2012 | 3rd QUARTER | OKI
[6 empty] | BOONE | 6-400.09 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | NORTHERN KENTUCKY RIDESHARE PROGRAM. | 5 | C | SNK | 2014 | 44000 | 44000 | ESTIMATED | [5 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.028 | 2011-01-10 | THIS PROJECT IS A DUPLICATE IN THE STIP. THE PHASE IS BEING REMOVED TO SHOW THE PROJECT NOT BEING USED. SEE 6-401.06 MOD |  |  | BOONE | 6-401.05 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | OKI REGIONAL TRANSPORTATION PLANNING. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) SEE 6-401.05 | 5 |  | SNK | 2011 | 70000 | 70000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | BOONE | 6-401.06 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | OKI REGIONAL TRANSPORTATION PLANNING. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | 5 | C | SNK | 2011 | 70000 | 70000 | ESTIMATED | N |  |  |  |  | 0
|  |  |  | STPM | 3002227 | BOONE | 6-401.07 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | OKI REGIONAL TRANSPORTATION PLANNING. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | 5 | C | SNK | 2012 | 70000 | 70000 | ESTIMATED | N |  | OBLIGATED | 53020 |  | 53020 | 2011 | 3rd QUARTER | OKI
|  |  |  | STPM | 3002237 | BOONE | 6-401.08 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | OKI REGIONAL TRANSPORTATION PLANNING. | 5 | C | SNK | 2013 | 56000 | 56000 | ESTIMATED |  |  | OBLIGATED | 53020 |  | 53020 | 2012 | 3rd QUARTER | OKI
[6 empty] | BOONE | 6-401.09 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | OKI REGIONAL TRANSPORTATION PLANNING. | 5 | C | SNK | 2014 | 56000 | 56000 | ESTIMATED | [5 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.032 | 2011-01-24 | ADD TO STIP. PROJECT IS IN OKI'S FY 2008-2011 TIP. NEW | STPM | 8200012 | BOONE | 6-405 | KY 237 |  |  |  | RELIABILITY | PAVEMENT REHAB-PRI(P) | PAVEMENT REPLACEMENT ON KY 237 SOUTH OF I-275 FROM CONNER DRIVE TO MEDICAL ARTS DRIVE. |  | D | SNK | 2011 | 100000 | 100000 |  |  |  | OBLIGATED | 100000 |  | 100000 | 2011 | 2nd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.032 | 2011-01-24 | ADD TO STIP. PROJECT IS IN OKI'S FY 2008-2011 TIP. NEW |  |  | BOONE | 6-405 | KY 237 |  |  |  | RELIABILITY | PAVEMENT REHAB-PRI(P) | PAVEMENT REPLACEMENT ON KY 237 SOUTH OF I-275 FROM CONNER DRIVE TO MEDICAL ARTS DRIVE. |  | U | SNK | 2013 | 100000 | 100000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.032 | 2011-01-24 | ADD TO STIP. PROJECT IS IN OKI'S FY 2008-2011 TIP. NEW |  |  | BOONE | 6-405 | KY 237 |  |  |  | RELIABILITY | PAVEMENT REHAB-PRI(P) | PAVEMENT REPLACEMENT ON KY 237 SOUTH OF I-275 FROM CONNER DRIVE TO MEDICAL ARTS DRIVE. |  | C | SNK | 2013 | 4750000 | 4750000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.086 | 2011-06-08 | TIP MOD #1. REVISE C PHASE ESTIMATE AND FISCAL YEAR. MOD | STPM | 8200013 | BOONE | 6-405 | KY 237 | 2.407 | 7.49 | 9.897 | RELIABILITY | PAVEMENT REHAB-PRI(P) | PAVEMENT REPLACEMENT ON KY 237 SOUTH OF I-275 FROM CONNER DRIVE TO MEDICAL ARTS DRIVE. |  | C | SNK | 2011 | 4750000 | 4750000 |  |  |  | OBLIGATED | 4145645.75 | 604354.25 | 4750000 | 2011 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.086 | 2011-06-08 | TIP MOD #1. REVISE C PHASE ESTIMATE AND FISCAL YEAR. MOD | STPM | 8200013 | BOONE | 6-405 | KY 237 | 2.407 | 7.49 | 9.897 | RELIABILITY | PAVEMENT REHAB-PRI(P) | PAVEMENT REPLACEMENT ON KY 237 SOUTH OF I-275 FROM CONNER DRIVE TO MEDICAL ARTS DRIVE. |  | C | STP | 2011 | 1250000 | 1250000 |  |  |  | OBLIGATED | 1250000 |  | 1250000 | 2011 | 3rd QUARTER | N/A
[6 empty] | BOONE | 6-906 |  |  |  |  | RELIABILITY | PLANNING-OKI(O) | REPLACEMENT FOR TANK BUSES. | 5 | C | SNK | 2011 | 1386000 | 1386000 | ESTIMATED |  | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.085 | 2011-06-08 | ADD TO STIP USING LINE ITEM IN TIP. NEW | HSIP | 9010052 | BOONE KENTON | 6-909 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | PURCHASE AND INSTALLATION OF FLOURESCENT YELLOW HORIZONTAL ALIGNMENT SIGNS TO BE PLACED ON RURAL ROADS IN BOONE AND KENTON COUNTIES. |  | C | SAF | 2011 | 60000 | 60000 |  |  |  | OBLIGATED | 60000 |  | 60000 | 2011 | 3rd QUARTER | OKI
|  |  |  | STPM STPM | 3002228 3002229 | BOONE | 6-966 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | DEDICATED FEDERAL-AID STP FUNDS EARMARKED FOR NKY URBANIZED AREA AND SUBJECT TO MPO CONTROL. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | 5 | C | SNK | 2012 | 3750000 | 3750000 | ESTIMATED |  |  | OBLIGATED | 56480 |  | 56480 | 2011 | 3rd QUARTER | OKI
|  |  |  | STPM STPM | 3002235 3002236 | BOONE | 6-966.05 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | DEDICATED FEDERAL-AID STP FUNDS EARMARKED FOR NKY URBANIZED AREA AND SUBJECT TO MPO CONTROL | 5 | C | SNK | 2013 | 3000000 | 3000000 | ESTIMATED |  |  | OBLIGATED | 93428 |  | 93428 | 2012 | 3rd QUARTER | OKI
[6 empty] | BOONE | 6-966.06 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | DEDICATED FEDERAL-AID STP FUNDS EARMARKED FOR NKY URBANIZED AREA AND SUBJECT TO MPO CONTROL | 5 | C | SNK | 2014 | 4400000 | 4400000 | ESTIMATED | [5 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.210 | 2012-06-27 | OKI TIP AMENDMENT #9 FY 2012-15. ADD PROJECT. NEW |  |  | BOONE | 6-1079 |  |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 20 OVER WOOLPER CREEK SE OF STONE CREEK LANE (PR 1300)(SR 39.7) 008B00018N |  | D | BRO | 2013 | 500000 | 500000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.210 | 2012-06-27 | OKI TIP AMENDMENT #9 FY 2012-15. ADD PROJECT. NEW |  |  | BOONE | 6-1079 |  |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 20 OVER WOOLPER CREEK SE OF STONE CREEK LANE (PR 1300)(SR 39.7) 008B00018N |  | R | BRO | 2014 | 100000 | 100000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.210 | 2012-06-27 | OKI TIP AMENDMENT #9 FY 2012-15. ADD PROJECT. NEW |  |  | BOONE | 6-1079 |  |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 20 OVER WOOLPER CREEK SE OF STONE CREEK LANE (PR 1300)(SR 39.7) 008B00018N |  | U | BRO | 2014 | 50000 | 50000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.210 | 2012-06-27 | OKI TIP AMENDMENT #9 FY 2012-15. ADD PROJECT. NEW |  |  | BOONE | 6-1079 |  |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 20 OVER WOOLPER CREEK SE OF STONE CREEK LANE (PR 1300)(SR 39.7) 008B00018N |  | C | BRO | 2015 | 750000 | 750000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.015 | 2010-11-15 | BREAKOUT PROJECT FROM ZVARIOUS 99-337.05 IN STIP AND LINE ITEM IN OKI TIP PAGE 27: VARIOUS;BOONE, CAMPBELL, AND KENTON COUNTIES; OPERATIONS PROJECTS ELIGIBLE FOR RESURFACING, RESTORATION, AND REHABILITATION. NEW | IM | 0757131 | BOONE | 6-2032 | I-75 | 13.37 | 169.439 | 182.813 | RELIABILITY | PAVEMENT REHAB-INT(P) | MILL 1.5" AND RESURFACE ON I-75 SB FROM MP 169.439 TO MP 182.813 AND ALL ADJACENT RAMPS IN BOONE COUNTY. WILL NOT INCLUDE I-71/75 INTERCHANGE RAMPS. |  | D | IM | 2011 | 5000 | 5000 |  | Y |  | OBLIGATED | 5000 |  | 5000 | 2011 | 1st QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.015 | 2010-11-15 | BREAKOUT PROJECT FROM ZVARIOUS 99-337.05 IN STIP AND LINE ITEM IN OKI TIP PAGE 27: VARIOUS;BOONE, CAMPBELL, AND KENTON COUNTIES; OPERATIONS PROJECTS ELIGIBLE FOR RESURFACING, RESTORATION, AND REHABILITATION. NEW | IM | 0757132 | BOONE | 6-2032 | I-75 | 13.37 | 169.439 | 182.813 | RELIABILITY | PAVEMENT REHAB-INT(P) | MILL 1.5" AND RESURFACE ON I-75 SB FROM MP 169.439 TO MP 182.813 AND ALL ADJACENT RAMPS IN BOONE COUNTY. WILL NOT INCLUDE I-71/75 INTERCHANGE RAMPS. |  | C | IM | 2011 | 3500000 | 3500000 |  | Y |  | OBLIGATED | 4686039.61 |  | 4686039.61 | 2011 | 2nd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.015 | 2010-11-15 | BREAKOUT PROJECT FROM ZVARIOUS 99-337.05 IN STIP AND LINE ITEM IN OKI TIP PAGE 27: VARIOUS;BOONE, CAMPBELL, AND KENTON COUNTIES; OPERATIONS PROJECTS ELIGIBLE FOR RESURFACING, RESTORATION, AND REHABILITATION. NEW | IM | 0757133 | BOONE | 6-2033 | I-75 | 6.561 | 169.439 | 176 | RELIABILITY | PAVEMENT REHAB-INT(P) | MILL 1.5" AND RESURFACE ON I-75 NB FROM MP 169.439 TO MP 176.000 AND ALL ADJACENT RAMPS IN BOONE COUNTY. WILL NOT INCLUDE I-71/75 INTERCHANGE RAMPS. |  | D | IM | 2011 | 5000 | 5000 |  | Y |  | OBLIGATED | 5000 |  | 5000 | 2011 | 1st QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.015 | 2010-11-15 | BREAKOUT PROJECT FROM ZVARIOUS 99-337.05 IN STIP AND LINE ITEM IN OKI TIP PAGE 27: VARIOUS;BOONE, CAMPBELL, AND KENTON COUNTIES; OPERATIONS PROJECTS ELIGIBLE FOR RESURFACING, RESTORATION, AND REHABILITATION. NEW | IM | 0757134 | BOONE | 6-2033 | I-75 | 6.561 | 169.439 | 176 | RELIABILITY | PAVEMENT REHAB-INT(P) | MILL 1.5" AND RESURFACE ON I-75 NB FROM MP 169.439 TO MP 176.000 AND ALL ADJACENT RAMPS IN BOONE COUNTY. WILL NOT INCLUDE I-71/75 INTERCHANGE RAMPS. |  | C | IM | 2011 | 3500000 | 3500000 |  | Y |  | OBLIGATED | 1891120.41 |  | 1891120.41 | 2011 | 2nd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.152 | 2011-12-19 | BREAKOUT PROJECT FROM ZVARIOUS 99-337.08 IN STIP AND LINE ITEM IN OKI TIP PAGE 43: OPERATIONS PROJECTS ELIGIBLE FOR RESURFACING, RESTORATION, AND REHABILITATION. NEW | IM | 0757138 | BOONE | 6-2036 | I-75 |  |  |  | RELIABILITY | PAVEMENT REHAB-INT(P) | RESURFACE I-75 FROM 0.608 MILES NORTH OF KY 338 OVERPASS EXTENDING NORTHERLY TO 0.602 MILES SOUTH OF KY 236 OVERPASS(NORTHBOUND LANES ONLY) (INCLUDING RAMPS) |  | C | IM | 2012 | 3000000 | 3000000 |  | Y |  | OBLIGATED | 3309848 |  | 3309848 | 2012 | 2nd QUARTER | N/A
[6 empty] | BOONE | 6-8000.5 | I 275 |  | 4.842 | 4.942 | ECONOMIC DEVELOPMENT | NEW INTERCHANGE(O) | CONSTRUCT AN ENTRANCE RAMP FROM KY-20 TO EASTBOUND I-275 AND WIDENING ON KY-20 AND I-275. (2004BOPC)(KYTC SHARE @ 100%) | 5 | C | NH | 2014 | 11000000 | 11000000 | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.170 | 2012-03-22 | TIP AMENDMENT #6. **DELETE** PROJECT PER TIP AMENDMENT. MOD |  |  | BOONE | 6-8000.5 | I 275 |  | 4.842 | 4.942 | ECONOMIC DEVELOPMENT | NEW INTERCHANGE(O) | CONSTRUCT AN ENTRANCE RAMP FROM KY-20 TO EASTBOUND I-275 AND WIDENING ON KY-20 AND I-275. (2004BOPC)(KYTC SHARE @ 100%) | 5 | C | NH | 2014 | 11000000 | 11000000 | ESTIMATED | Y |  |  |  |  | 0
[6 empty] | BOONE | 6-8001.25 | KY 237 | 0.85 | 5.37 | 6.262 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT AND WIDEN KY-237 FROM ROGERS LANE TO KY-18 (PRIORITY SECTION). (00CCN)(2004BOPC)(08CCR) (10CCR) | 5 | C | STP | 2011 | 18320000 | 18320000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.170 | 2012-03-22 | TIP AMENDMENT #6. REVISE FUNDING AMOUNT. MOD |  |  | BOONE | 6-8001.25 | KY 237 | 0.85 | 5.37 | 6.262 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT AND WIDEN KY-237 FROM ROGERS LANE TO KY-18 (PRIORITY SECTION). (00CCN)(2004BOPC)(08CCR) (10CCR) | 5 | C | STP | 2011 | 19800000 | 19800000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.177 | 2012-03-26 | ADD PROJECT TO STIP. NEW |  |  | BOONE | [5 empty] | SAFETY | SAFETY-RR PROTECTN(P) | ADD GATES TO EXISTING FLASHING LIGHTS AND BELL SYSTEM AT NORFOLK SOUTHERN RR CROSSING ON CHURCH STREET IN WALTON. (DOT# 720018X) |  | U | SAF | 2012 | 234000 | 234000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.177 | 2012-03-26 | ADD PROJECT TO STIP. NEW |  |  | BOONE | [5 empty] | SAFETY | SAFETY-RR PROTECTN(P) | ADD GATES TO EXISTING FLASHING LIGHTS AND BELL SYSTEM AT NORFOLK SOUTHERN RR CROSSING ON CHURCH STREET IN WALTON. (DOT# 720018X) |  | C | SAF | 2012 | 15000 | 15000 | [6 empty] | 0
|  |  |  | NH | 0681025 | BOURBON | 7-310.1 | US 68 | 6.14 | 2.36 | 8.5 | RELIABILITY | MAJOR WIDENING(O) | PARIS-MAYSVILLE ROAD; RECONSTRUCT FR PARIS BYPASS TO MILLERSBURG (SECTION 1). (08CCR) | 5 | C | NHG | 2011 | 24720000 | 24720000 | ESTIMATED | Y |  | OBLIGATED | 6065029.16 | 26966460 | 33031489.16 | 2012 | 1st QUARTER | N/A
[6 empty] | BOURBON | 7-310.2 | US 68 | 4.4 |  |  | RELIABILITY | MAJOR WIDENING(O) | PARIS-MAYSVILLE ROAD; CONSTRUCT MILLERSBURG BYPASS (SECTION 2)(08CCR) | 3 | R | NHG | 2011 | 2480000 | 2480000 | ESTIMATED | Y | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.147 | 2011-12-01 | INCREASE FUNDING. | NH | 0681024 | BOURBON | 7-310.2 | US 68 | 4.4 |  |  | RELIABILITY | MAJOR WIDENING(O) | PARIS-MAYSVILLE ROAD; CONSTRUCT MILLERSBURG BYPASS (SECTION 2)(08CCR) | 3 | R | NHG | 2012 | 3800000 | 3800000 | ESTIMATED | Y | 2010 | OBLIGATED |  | 3800000 | 3800000 | 2012 | 1st QUARTER | N/A
[6 empty] | BOURBON | 7-310.2 | US 68 | 4.4 |  |  | RELIABILITY | MAJOR WIDENING(O) | PARIS-MAYSVILLE ROAD; CONSTRUCT MILLERSBURG BYPASS (SECTION 2)(08CCR) | 4 | U | NHG | 2011 | 2400000 | 2400000 | ESTIMATED | Y | 2010 |  |  |  | 0
[6 empty] | BOURBON | 7-310.2 | US 68 | 4.4 |  |  | RELIABILITY | MAJOR WIDENING(O) | PARIS-MAYSVILLE ROAD; CONSTRUCT MILLERSBURG BYPASS (SECTION 2)(08CCR) | 5 | C | NH | 2012 | 18500000 | 18500000 | ESTIMATED | Y |  |  |  |  | 0
[6 empty] | BOURBON | 7-310.2 | US 68 | 4.4 |  |  | RELIABILITY | PREFINANCD CONVRSN(O) | PARIS-MAYSVILLE ROAD; CONSTRUCT MILLERSBURG BYPASS (SECTION 2)(08CCR) | 5 | C | NH | 2013 | 12970000 | 12970000 | ESTIMATED | Y |  |  |  |  | 0
|  |  |  | BRZ | 0703300 | BOURBON | 7-1119 | CR 1308 | 0.1 | 1.64 | 1.657 | SAFETY | BRIDGE REPLACEMENT(P) | TOWNSEND VALLEY ROAD; REPLACE BRIDGE AND APPROACHES OVER TOWNSEND CREEK (C42) 1.6 MILES WEST OF JCT. US-27. (SR=32.0): (009C00042N) | 2 | D | BRZ | 2011 | 90000 | 90000 | ESTIMATED | N |  | OBLIGATED | 90000 |  | 90000 | 2011 | 2nd QUARTER | N/A
[6 empty] | BOURBON | 7-1119 | CR 1308 | 0.1 | 1.64 | 1.657 | SAFETY | BRIDGE REPLACEMENT(P) | TOWNSEND VALLEY ROAD; REPLACE BRIDGE AND APPROACHES OVER TOWNSEND CREEK (C42) 1.6 MILES WEST OF JCT. US-27. (SR=32.0): (009C00042N) | 3 | R | BRZ | 2012 | 135000 | 135000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | BOURBON | 7-1119 | CR 1308 | 0.1 | 1.64 | 1.657 | SAFETY | BRIDGE REPLACEMENT(P) | TOWNSEND VALLEY ROAD; REPLACE BRIDGE AND APPROACHES OVER TOWNSEND CREEK (C42) 1.6 MILES WEST OF JCT. US-27. (SR=32.0): (009C00042N) | 4 | U | BRZ | 2012 | 115000 | 115000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | BOURBON | 7-1119 | CR 1308 | 0.1 | 1.64 | 1.657 | RELIABILITY | BRIDGE REPLACEMENT(P) | TOWNSEND VALLEY ROAD; REPLACE BRIDGE AND APPROACHES OVER TOWNSEND CREEK (C42) 1.6 MILES WEST OF JCT. US-27. (SR=32.0) | 5 | C | BRZ | 2014 | 450000 | 450000 | ESTIMATED | N |  |  |  |  | 0
|  |  |  | BRZ | 0703307 | BOURBON | 7-1124 | CR 1308 | 0.1 | 3.538 | 3.638 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON CR-1308 (MP 3.588) OVER TOWNSEND CREEK; .9 MI E OF JCT KY 353; (STRUCTURALLY DEFICIENT, SR=33.2) 009C00043N | 2 | D | BRZ | 2012 | 150000 | 150000 | ESTIMATED | N |  | OBLIGATED | 305000 |  | 305000 | 2012 | 3rd QUARTER | N/A
[6 empty] | BOYD | 9-191.03 |  |  |  |  | RELIABILITY | TRANSP ENHANCEMENT(P) | ASHLAND RIVERFRONT DEVELOPMENT PROJECT IN ASHLAND. (2005HPP-KY152) | 5 | C | HPP | 2011 | 85000 | 85000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.171 | 2012-03-13 | ADD PROJECT TO STIP. BREAKOUT FROM 99-911.01. NEW | HSIP | 5244014 | BOYD | 9-908 | KY 5 | 6.8 | 0 | 6.8 | SAFETY | SAFETY-HAZARD ELIM(P) | REPLACE/EXTEND CULVERTS, REPLACE GUARDRAIL, TRIM BRUSH AND LIMBS, REMOVE TREES AND STUMPS ON KY 5 FROM US 60 AT PRINCESS TO SUMMITT ROAD (KY 716) |  | C | SAF | 2012 | 780000 | 780000 |  |  |  | OBLIGATED | 1305552.45 |  | 1305552.45 | 2012 | 3rd QUARTER | N/A
[6 empty] | BOYD | 9-993 | US 60 | 0.4 | 10.2 | 10.6 | SAFETY | SAFETY-HAZARD ELIM(P) | US60 @ HIGHLAND AVE, CONSTRUCT LEFT TURN LANES, INSTALL TRAFFIC SIGNAL, & REALIGN INTERSECTION (B/C=2.6) (D-CONSLT, C-CONTRACTOR) (2002BOP) | 5 | C | HES | 2013 | 420000 | 420000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.057 | 2011-03-23 | TIP AMENDMENT NO. 2. NO CHANGE TO STIP. REVISING THE TIP TO MATCH THE INFORMATION IN THE STIP. |  |  | BOYD | 9-993 | US 60 | 0.4 | 10.2 | 10.6 | SAFETY | SAFETY-HAZARD ELIM(P) | US60 @ HIGHLAND AVE, CONSTRUCT LEFT TURN LANES, INSTALL TRAFFIC SIGNAL, & REALIGN INTERSECTION (B/C=2.6) (D-CONSLT, C-CONTRACTOR) (2002BOP) | 5 | C | HES | 2013 | 420000 | 420000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.020 | 2010-11-23 | TIP MOD FY 11-02. ADD PROJECT TO STIP. NEW | BRZ | 0903169 | BOYD | 9-1050 | KY 752 | 0.1 | 5.076 | 5.176 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES AT DURBIN CREEK, 0.8 MILES WEST OF NEW US-23 |  | C | BRX | 2011 | 840000 | 840000 |  | N |  | OBLIGATED | 511089 |  | 511089 | 2010 | 2nd QUARTER | N/A
[6 empty] | BOYD | 9-1054 | KY 168 | 0.1 | 2.657 | 2.664 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER KEYS CREEK (B14) 2.5 MI NW OF JCT. US-23. (SR=35.1): (010B00014N) | 3 | R | BRO | 2011 | 210000 | 210000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.020 | 2010-11-23 | TIP MOD FY 11-02. CHANGE YEAR IN TIP FROM 2008 TO 2011. CHANGE MP IN STIP. MOD | BRO | 8074009 | BOYD | 9-1054 | KY 168 | 0.1 | 2.65 | 2.75 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER KEYS CREEK 2.51 MI NW OF JCT. US-23. (MATCH/OTHER = TOLL CREDITS) | 3 | R | BRO | 2011 | 210000 | 210000 | ESTIMATED | N | 2010 | OBLIGATED | 210000 |  | 210000 | 2012 | 4th QUARTER | N/A
[6 empty] | BOYD | 9-1054 | KY 168 | 0.1 | 2.657 | 2.664 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER KEYS CREEK (B14) 2.5 MI NW OF JCT. US-23. (SR=35.1): (010B00014N) | 4 | U | BRO | 2011 | 130000 | 130000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.020 | 2010-11-23 | TIP MOD FY 11-02. CHANGE YEAR IN TIP FROM 2008 TO 2011. CHANGE MP IN STIP. MOD |  |  | BOYD | 9-1054 | KY 168 | 0.1 | 2.65 | 2.75 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER KEYS CREEK 2.51 MI NW OF JCT. US-23. (MATCH/OTHER = TOLL CREDITS) | 3 | U | BRO | 2011 | 130000 | 130000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | BOYD | 9-1054 | KY 168 | 0.1 | 2.657 | 2.664 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER KEYS CREEK (B14) 2.5 MI NW OF JCT. US-23. (SR=35.1): (010B00014N) | 5 | C | BRO | 2011 | 680000 | 680000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.020 | 2010-11-23 | TIP MOD FY 11-02. CHANGE YEAR IN TIP FROM 2010 TO 2012. CHANGE MP IN STIP. MOD |  |  | BOYD | 9-1054 | KY 168 | 0.1 | 2.65 | 2.75 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER KEYS CREEK 2.51 MI NW OF JCT. US-23. (MATCH/OTHER = TOLL CREDITS) | 3 | C | BRO | 2012 | 680000 | 680000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | BOYD | 9-8605 | I 64 | 10.695 | 180.812 | 191.507 | RELIABILITY | PAVEMENT REHAB-INT(P) | REHAB AND PROVIDE PAVEMENT IMPROVEMENTS ALONG I-64. (10CCN) | 5 | C | IM | 2011 | 5000000 | 5000000 | ESTIMATED | Y | 2010 |  |  |  | 0
[6 empty] | BOYLE | 7-242 | US 68 |  | 6.4 | 6.418 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE US 68 AND US 150 BRIDGE OVER CHAPLIN RIVER, PERRYVILLE. (2005HPP-KY134) (EARMARK DOES NOT COVER TOTAL CONSTRUCTION COST OF $600,000): (011B00042N) | 5 | C | HPP | 2011 | 364940 | 364940 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.214 | 2012-07-05 | ADD PROJECT TO STIP. NEW |  |  | BOYLE | 7-1133 | CR 1226 | 0.04 | 0.004 | 0.044 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON CURTIS RD (CR 1226) OVER N ROLLING FORK AT JCT WITH KY 37(SR 19.2) 011C00042N |  | D | BRZ | 2012 | 300000 | 300000 | [6 empty] | 0
[6 empty] | BRACKEN | 6-1068 | CR 1023 | 0.1 | 0.476 | 0.488 | SAFETY | BRIDGE REPLACEMENT(P) | LONG STRETCH ROAD; REPLACE BRIDGE AND APPROACHES OVER TURTLE CREEK 400 FEET NORTH OF KY-8 (C03). (SR=17.7): (012C00003N)(10CCR) | 2 | D | BRZ | 2011 | 125000 | 125000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.060 | 2011-03-29 | INCREASE FUNDING AMOUNT FROM 125,000 TO 164,000. MOD | BRZ | 0603226 | BRACKEN | 6-1068 | CR 1023 | 0.1 | 0.476 | 0.488 | SAFETY | BRIDGE REPLACEMENT(P) | LONG STRETCH ROAD; REPLACE BRIDGE AND APPROACHES OVER TURTLE CREEK 400 FEET NORTH OF KY-8 (C03). (SR=17.7): | 2 | D | BRZ | 2011 | 164000 | 164000 | ESTIMATED | N |  | OBLIGATED | 164000 |  | 164000 | 2011 | 3rd QUARTER | N/A
[6 empty] | BRACKEN | 6-1068 | CR 1023 | 0.1 | 0.476 | 0.488 | SAFETY | BRIDGE REPLACEMENT(P) | LONG STRETCH ROAD; REPLACE BRIDGE AND APPROACHES OVER TURTLE CREEK 400 FEET NORTH OF KY-8 (C03). (SR=17.7): (012C00003N)(10CCR) | 3 | R | BRZ | 2011 | 25000 | 25000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | BRACKEN | 6-1068 | CR 1023 | 0.1 | 0.476 | 0.488 | SAFETY | BRIDGE REPLACEMENT(P) | LONG STRETCH ROAD; REPLACE BRIDGE AND APPROACHES OVER TURTLE CREEK 400 FEET NORTH OF KY-8 (C03). (SR=17.7): (012C00003N)(10CCR) | 4 | U | BRZ | 2012 | 5000 | 5000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | BRACKEN | 6-1068 | CR 1023 | 0.1 | 0.476 | 0.488 | SAFETY | BRIDGE REPLACEMENT(P) | LONG STRETCH ROAD; REPLACE BRIDGE AND APPROACHES OVER TURTLE CREEK 400 FEET NORTH OF KY-8 (C03). (SR=17.7): (012C00003N)(10CCR) | 5 | C | BRZ | 2012 | 175000 | 175000 | ESTIMATED | N |  |  |  |  | 0
|  |  |  | BRO | 5390003 | BRACKEN | 6-1074 | KY 8 | 0.1 | 4.171 | 4.271 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-8 (MP 4.221) OVER SNAG CREEK; 1 MI W OF JCT KY 1109; (STRUCTURALLY DEFICIENT, SR=48.3) 012B00005N | 2 | D | BRO | 2012 | 320000 | 320000 | ESTIMATED | N |  | OBLIGATED | 320000 |  | 320000 | 2011 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.115 | 2011-09-01 | ADD PROJECT. FY 2011 FBD PROGRAM FUNDS. NEW |  |  | BRACKEN | [7 empty] | AUGUSTA FERRY - DIESEL POWERED GENERATOR IMPROVEMENTS |  | N | KYD | 2011 | 12000 | 12000 | [6 empty] | 0
|  |  |  | NH | 0151070 | BREATHITT | 10-270.67 | KY 15 | 0.43 |  |  | RELIABILITY | SURFACE(O) | JACKSON-CAMPTON (SURFACING): FROM KY-15 AT JACKSON TO A POINT 0.43 MI N OF KY 15. (TO BE LET WITH 10-270.77) | 5 | C | NH | 2011 | 6190000 | 6190000 | ESTIMATED | Y | 2010 | OBLIGATED | 6190000 |  | 6190000 | 2011 | 4th QUARTER | N/A
|  |  |  | NH | 0151071 | BREATHITT | 10-270.77 | KY 15 | 1.7 |  |  | RELIABILITY | SURFACE(O) | JACKSON-CAMPTON (SURFACING): FROM 0.43 MI N OF KY 15 AT JACKSON TO 0.31 MI S OF STILL HOUSE HOLLOW. (TO BE LET WITH 10-270.67) | 5 | C | NH | 2011 | 4730000 | 4730000 | ESTIMATED | Y | 2010 | OBLIGATED | 7681259.3 |  | 7681259.3 | 2011 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.035 | 2011-01-28 | ADD PROJECT. BREAKOUT FROM 99-354.06. NEW | HSIP | 0151068 | BREATHITT | 10-910 | KY 15 | 19 | 7 | 26 | SAFETY | SAFETY-HAZARD ELIM(P) | UPGRADE GUARDRAIL TURN-DOWN END TREATMENTS ON KY 15 FROM KY 476 AT LOST CREEK TO KY 205 NORTH OF JACKSON |  | C | SAF | 2011 | 150000 | 150000 |  |  |  | OBLIGATED | 150000 |  | 150000 | 2011 | 2nd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.164 | 2012-02-09 | ADD PROJECT. BREAKOUT FROM 99-911.01. NEW | HSIP | 5263015 | BREATHITT | 10-914 | KY 30 | 1.523 | 7.511 | 9.034 | SAFETY | SAFETY | MILL AND INLAY WITH POLISH RESISTANT STONE ON KY 30 FROM SHOULDERBLADE CULVERT 1.6MI EAST OF KY 2469 TO 0.1MI EAST OF RIGHT FORK HADDIX FORK ROAD 1.1MI WEST OF KY 397 |  | C | SAF | 2012 | 225000 | 225000 |  |  |  | OBLIGATED | 225000 |  | 225000 | 2012 | 2nd QUARTER | N/A
|  |  |  | BRZ | 1003201 | BREATHITT | 10-1089 | KY 3193 | 0.1 | 3.984 | 4.084 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-3193 (MP 4.034) OVER NORTH FORK OF KENTUCKY RIVER; ON CR 5318 .4 MILE SOUTHWEST OF KY 15 (STRUCTURALLY DEFICIENT, SR=35.3) 013B00044N | 2 | D | BRX | 2012 | 350000 | 350000 | ESTIMATED | N |  | OBLIGATED | 350000 |  | 350000 | 2011 | 2nd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.072 | 2011-04-28 | ADD PROJECT TO STIP. BREAKOUT FROM 99-1074.03 NEW | BRZ | 1003202 | BREATHITT | 10-1094 | CR 1387 | 0.1 | 0.015 | 0.115 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON ROBINSON ROAD (CR 1387 AT MP 0.065) OVER NORTH FORK KENTUCKY RIVER LOCATED NEAR QUICKSAND, KENTUCKY APPROXIMATELY 300 FEET SOUTH OF THE JUNCTION OF KY 1812. (013C00039N) (SR=4) |  | D | BRZ | 2011 | 275000 | 275000 |  |  |  | OBLIGATED | 275000 |  | 275000 | 2011 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.215 | 2012-07-10 | ADD PROJECT TO STIP. NEW |  |  | BREATHITT | 10-1094 | CR 1387 | 0.1 | 0.015 | 0.115 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON ROBINSON ROAD (CR 1387 AT MP 0.065) OVER NORTH FORK KENTUCKY RIVER LOCATED NEAR QUICKSAND, KENTUCKY APPROXIMATELY 300 FEET SOUTH OF THE JUNCTION OF KY 1812. (013C00039N) (SR=4) (2010BOP). |  | R | BRZ | 2012 | 150000 | 150000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.215 | 2012-07-10 | ADD PROJECT TO STIP. NEW |  |  | BREATHITT | 10-1094 | CR 1387 | 0.1 | 0.015 | 0.115 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON ROBINSON ROAD (CR 1387 AT MP 0.065) OVER NORTH FORK KENTUCKY RIVER LOCATED NEAR QUICKSAND, KENTUCKY APPROXIMATELY 300 FEET SOUTH OF THE JUNCTION OF KY 1812. (013C00039N) (SR=4) (2010BOP). |  | U | BRZ | 2012 | 80000 | 80000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.191 | 2012-05-16 | ADD PROJECT TO STIP. NEW | BRO | 5263016 | BREATHITT | 10-1096 | KY 30 | 0.153 | 4.853 | 5.006 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 30 OVER THE MIDDLE FORK OF KENTUCKY RIVER (013B00017N). | D | D | BRO | 2012 | 350000 | 350000 |  |  |  | OBLIGATED | 350000 |  | 350000 | 2012 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.211 | 2012-06-28 | ADD PROJECT TO STIP. NEW |  |  | BREATHITT | 10-1105 | CR 1165 | 0.048 | 0.092 | 0.14 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON MARIE ROBERTS ROAD (CR 1165) OVER TROUBLESOME CREEK 0.1 MILE SW OF KY 15(SR 27.1) 013C00011N |  | D | BRZ | 2012 | 275000 | 275000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.062 | 2011-04-07 | ADD PROJECT. BREAKOUT FROM 99-911.00. NEW | HSIP | 0051032 | BRECKINRIDGE | 4-908 | KY 259 | 8.83 | 13.076 | 21.94 | SAFETY | SAFETY-HAZARD ELIM(P) | REMOVE HEADWALLS, EXTEND PIPES, AND FLATTEN SLOPES AT VARIOUS LOCATIONS ON KY 259 FROM KY 2779 TO KY 144 AND FILL IN A DEEP DITCH, INSTALL A DBI AND EXTEND PIPE AT AL SMITH ROAD. |  | C | SAF | 2011 | 100000 | 100000 |  |  |  | OBLIGATED | 100100 |  | 100100 | 2011 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.197 | 2012-05-30 | ADD PROJECT TO STIP. NEW |  |  | BRECKINRIDGE | 4-1081 | CR 1330 | 0.04 | 0.229 | 0.269 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON FALLS OF ROUGH SPUR ROAD (CR 1330) OVER HARRIS FORK 0.24 MILE S OF ROCKVALE-DEMPSTER RD (CR 1636)(SR 21) 014C00018N |  | D | BRZ | 2012 | 150000 | 150000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.174 | 2012-03-26 | TIP MOD #15. KIPDA ID 1493. ADD PHASE TO STIP. NEW | STPM | 3001431 | BULLITT | 5-293 | KY 1494 |  |  |  | RELIABILITY | MINOR WIDENING(O) | WIDEN TRAVEL LANES (NO ADDITIONAL TRAVEL LANES) ON KY 1494 IN BULLITT COUNTY, AND RELOCATE ROAD FROM 2000' WEST OF KY 61 TO KY 61 | C | D | SLO | 2012 | 100000 | 100000 |  |  |  | OBLIGATED | 100000 |  | 100000 | 2012 | 3rd QUARTER | YES??
ADMINISTRATIVE MODIFICATION | 2010.074 | 2011-05-05 | TIP MOD #5. KIPDA ID 1493. ADD TO STIP. NEW |  |  | BULLITT | 5-293 | KY 1494 |  |  |  | RELIABILITY | MINOR WIDENING(O) | WIDEN TRAVEL LANES (NO ADDITIONAL TRAVEL LANES) ON KY 1494 IN BULLITT COUNTY, AND RELOCATE ROAD FROM 2000' WEST OF KY 61 TO KY 61 | C | C | SLO | 2012 | 1500000 | 1500000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.148 | 2011-12-01 | TIP MOD #12. KIPDA ID 1493. INCREASE C PHASE FUNDING AMOUNT. MOD |  |  | BULLITT | 5-293 | KY 1494 |  |  |  | RELIABILITY | MINOR WIDENING(O) | WIDEN TRAVEL LANES (NO ADDITIONAL TRAVEL LANES) ON KY 1494 IN BULLITT COUNTY, AND RELOCATE ROAD FROM 2000' WEST OF KY 61 TO KY 61 |  | C | SLO | 2012 | 2660000 | 2660000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.174 | 2012-03-26 | TIP MOD #15. KIPDA ID 1493. REDUCE C PHASE FUNDING. MOD |  |  | BULLITT | 5-293 | KY 1494 |  |  |  | RELIABILITY | MINOR WIDENING(O) | WIDEN TRAVEL LANES (NO ADDITIONAL TRAVEL LANES) ON KY 1494 IN BULLITT COUNTY, AND RELOCATE ROAD FROM 2000' WEST OF KY 61 TO KY 61 | C | C | SLO | 2012 | 2560000 | 2560000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.074 | 2011-05-05 | TIP MOD #5. KIPDA ID 1229. ADD TO STIP. NEW |  |  | BULLITT OLDHAM JEFFERSON | 5-440 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | VARIOUS SIDEWALKS ON STATE ROUTES IN KENTUCKY: INSTALLATION OF SIDEWALKS TO FIX GAPS IN PEDESTRIAN NETWORK ON VARIOUS STATE MAINTAINED ROADS IN OLDHAM, JEFFERSON, AND BULLITT COUNTIES |  | C | SLO | 2011 | 110323 | 110323 |  | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.148 | 2011-12-01 | TIP MOD #12. KIPDA ID 1229. MOVE FY TO FY 2012. MOD |  |  | BULLITT OLDHAM JEFFERSON | 5-440 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | VARIOUS SIDEWALKS ON STATE ROUTES IN KENTUCKY: INSTALLATION OF SIDEWALKS TO FIX GAPS IN PEDESTRIAN NETWORK ON VARIOUS STATE MAINTAINED ROADS IN OLDHAM, JEFFERSON, AND BULLITT COUNTIES |  | C | SLO | 2012 | 210323 | 210323 |  | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.174 | 2012-03-26 | TIP MOD #15. KIPDA ID 1229. REDUCE C PHASE AND PUT THE DIFFERENCE IN 5-440.03. MOD |  |  | JEFFERSON BULLITT OLDHAM | 5-440 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | VARIOUS SIDEWALKS ON STATE ROUTES IN KENTUCKY: INSTALLATION OF SIDEWALKS TO FIX GAPS IN PEDESTRIAN NETWORK ON VARIOUS STATE MAINTAINED ROADS IN OLDHAM, JEFFERSON, AND BULLITT COUNTIES |  | C | SLO | 2012 | 25323 | 25323 |  | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.174 | 2012-03-26 | TIP MOD #15. PART OF KIPDA ID 1229. ADD PROJECT TO STIP. NEW | STPM | 5118037 | BULLITT | 5-440.03 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | KY 44 ADA SIDEWALK UPDATES: REPLACE APPROX. 2200 LINEAR FEET OF SIDEWALK, 500 LINEAR FEET OF ENTRANCE PAVEMENT, 11 HANDICAP ACCESSIBLE RAMPS AT VARIOUS LOCATIONS ALONG KY-44 BETWEEN I-65 & REESOR AVENUE IN SHEPHERDSVILLE. MINOR DRAINAGE IMPROVEMENTS. |  | D | SLO | 2012 | 15000 | 15000 |  |  |  | OBLIGATED | 15000 |  | 15000 | 2012 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.174 | 2012-03-26 | TIP MOD #15. PART OF KIPDA ID 1229. ADD PROJECT TO STIP. NEW |  |  | BULLITT | 5-440.03 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | KY 44 ADA SIDEWALK UPDATES: REPLACE APPROX. 2200 LINEAR FEET OF SIDEWALK, 500 LINEAR FEET OF ENTRANCE PAVEMENT, 11 HANDICAP ACCESSIBLE RAMPS AT VARIOUS LOCATIONS ALONG KY-44 BETWEEN I-65 & REESOR AVENUE IN SHEPHERDSVILLE. MINOR DRAINAGE IMPROVEMENTS. |  | C | SLO | 2012 | 170000 | 170000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.212 | 2012-06-29 | TIP MOD #18. KIPDA ID 1993. MODIFY DESCRIPTION. MOD |  |  | BULLITT | 5-440.03 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | UPGRADE TO CURRENT ADA STANDARDS APPROXIMATELY 2200 LINEAR FEET OF EXISTING SIDEWALK, 500 LINEAR FEET OF ENTRANCE PAVEMENT, AND 11 HANDICAP ACCESSIBLE RAMPS AT VARIOUS LOCATIONS ALONG KY-44 FROM THE WESTERN CITY LIMIT (APPROX MP 10.3) TO SALTWELL ROAD (MP 11.8) IN SHEPHERDSVILLE, KY IN BULLITT COUNTY. PROJECT WILL INCLUDE MINOR DRAINAGE IMPROVEMENTS. |  | C | SLO | 2012 | 170000 | 170000 | [6 empty] | 0
|  |  | THIS PROJECT IS USING MPO DEDICATED FUNDS. SEE JEFFERSON CO ITEM NO. 5-965.15. NEW | STPM | 1501102 | BULLITT | 5-471 | US 31 |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | CONSTRUCTION OF SIDEWALKS ON MAIN ST (US-31EX/BARDSTOWN ROAD) FROM OLD MILL RD (KY-44) TO SNAPP ST IN MOUNT WASHINGTON |  | C | SLO | 2011 | 198000 | 198000 |  |  |  | OBLIGATED | 198000 |  | 198000 | 2011 | 1st QUARTER | CITY OF MOUNT WASHINGTON
ADMINISTRATIVE MODIFICATION | 2010.169 | 2012-02-27 | TIP MOD #14, KIPDA ID 1725. ADD PROJECT - ADDITIONAL FUNDING FOR PROJECT. NEW |  |  | BULLITT |  | US 31EX |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | MT. WASHINGTON SIDEWALKS: CONSTRUCTION OF SIDEWALKS ON US 31EX (BARDSTOWN ROAD) IN MOUNT WASHINGTON |  | C | SLO | 2012 | 120000 | 96000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.174 | 2012-03-26 | TIP MOD #15, ADD PROJECT AS PART OF KIPDA ID 1633, VARIOUS SAFETY PROJECTS. NEW | HSIP | 0655107 | BULLITT/ JEFFERSON | 5-998 | I-65 |  | 116.9 | 123.6 | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALL CABLE BARRIER ON I-65 FROM KY 44 AT SHEPHERDSVILLE TO THE JEFFERSON COUNTY LINE. |  | C | SAF | 2012 | 1400000 | 1400000 |  |  |  | OBLIGATED | 979000 |  | 979000 | 2012 | 2nd QUARTER | N/A
|  |  |  | BRO | 5116025 | BULLITT | 5-1056 | KY 61 | 0.1 | 7.559 | 7.659 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-61 (MP 7.609) OVER BARLEY CREEK; .10 MI NORTH OF JCT KY 251; (STRUCTURALLY DEFICIENT, SR=49) 015B00013N | 2 | D | BRO | 2012 | 120000 | 120000 | ESTIMATED | N |  | OBLIGATED | 200000 |  | 200000 | 2011 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.031 AND 2010.034- DUPLICATE | 2011-01-18 | TIP MOD #1. KIPDA ID #1883, PART OF KIPDA ID #1633. ADD PROJECT TO TIP AND STIP. NEW |  |  | BULLITT | 5-2805 | I-65 |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | HSIP SAFETY PROJECT IN BULLITT COUNTY TO INSTALL MEDIAN CABLE BARRIER ON I-65 FROM ROLLING FORK RIVER TO CROOKED CREEK CULVERT. |  | D | SAF | 2011 | 50000 | 50000 |  | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.031 AND 2010.034- DUPLICATE | 2011-01-18 | TIP MOD #1. KIPDA ID #1883, PART OF KIPDA ID #1633. ADD PROJECT TO TIP AND STIP. NEW | HSIP | 0655106 | BULLITT | 5-2805 | I-65 |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | HSIP SAFETY PROJECT IN BULLITT COUNTY TO INSTALL MEDIAN CABLE BARRIER ON I-65 FROM ROLLING FORK RIVER TO CROOKED CREEK CULVERT. |  | C | SAF | 2011 | 930000 | 930000 |  | N |  | OBLIGATED | 788350 |  | 788350 | 2011 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.034 | 2011-01-28 | PART OF KIPDA ID #173. KIPDA MOD #2-REVISED. ADD PROJECT TO STIP. NEW |  |  | BULLITT | 5-2807 | I-65 |  |  |  | RELIABILITY | PAVEMENT REHAB-INT(P) | PAVEMENT REHABILITATION AT I-65 EXIT 116 OF THE I-65/KY 480 INTERCHANGE IN BULLITT COUNTY ON EACH OF THE FOUR I-65 RAMPS BEGINNING AT MP 115.00 AND ENDING AT MP 116.00. |  | D | IM | 2011 | 50000 | 50000 |  | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.034 | 2011-01-28 | PART OF KIPDA ID #173. KIPDA MOD #2-REVISED. ADD PROJECT TO STIP. NEW | IM | 0655105 | BULLITT | 5-2807 | I-65 |  |  |  | RELIABILITY | PAVEMENT REHAB-INT(P) | PAVEMENT REHABILITATION AT I-65 EXIT 116 OF THE I-65/KY 480 INTERCHANGE IN BULLITT COUNTY ON EACH OF THE FOUR I-65 RAMPS BEGINNING AT MP 115.00 AND ENDING AT MP 116.00. |  | C | IM | 2011 | 1000000 | 1000000 |  | Y |  | OBLIGATED | 1040600 |  | 1040600 | 2011 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.163 | 2012-02-13 | TIP AMENDMENT #3. KIPDA ID 1790. ADD D PHASE TO STIP. NEW. |  |  | BULLITT | 5-8509 | KY 245 | 1.6 |  |  | RELIABILITY | MAJOR WIDENING(O) | MAJOR WIDENING OF KY-245 FROM 2 TO 4 LANES FROM THE I-65/KY 245 INTERCHANGE TO CLERMONT. PROJECT LENGTH IS 1.6 MILES. | 5 | D | STP | 2012 | 2350000 | 2350000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.163 | 2012-02-13 | TIP AMENDMENT #3. KIPDA ID 1790. ADD R PHASE TO STIP. NEW. |  |  | BULLITT | 5-8509 | KY 245 | 1.6 |  |  | RELIABILITY | MAJOR WIDENING(O) | MAJOR WIDENING OF KY-245 FROM 2 TO 4 LANES FROM THE I-65/KY 245 INTERCHANGE TO CLERMONT. PROJECT LENGTH IS 1.6 MILES. | 5 | R | STP | 2012 | 500000 | 500000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | BULLITT | 5-8509 | KY 245 |  | 4.2 | 6.297 | RELIABILITY | MINOR WIDENING(O) | WIDEN KY-245 FROM BURNHEIM FOREST TO THE COMMUNITY COLLEGE. (08CCN)(10CCR) | 5 | C | STP | 2012 | 4000000 | 4000000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.163 | 2012-02-13 | TIP AMENDMENT #3. KIPDA ID 1790. CHANGE DESCRIPTION. MOD |  |  | BULLITT | 5-8509 | KY 245 | 1.6 |  |  | RELIABILITY | MAJOR WIDENING(O) | MAJOR WIDENING OF KY-245 FROM 2 TO 4 LANES FROM THE I-65/KY 245 INTERCHANGE TO CLERMONT. PROJECT LENGTH IS 1.6 MILES. | 5 | C | STP | 2012 | 4000000 | 4000000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.212 | 2012-06-29 | TIP MOD 18. ADD PROJECT. NEW |  |  | BULLITT |  | KY 44 | [5 empty] | CONSTRUCT SIDEWALK ON THE NORTH SIDE OF KY 44 FROM MT. WASHINGTON ELEMENTARY SCHOOL TO FISHER LANE. |  | D | SLO | 2012 | 70000 | 56000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.212 | 2012-06-29 | TIP MOD 18. ADD PROJECT. NEW |  |  | BULLITT |  | KY 44 | [5 empty] | CONSTRUCT SIDEWALK ON THE NORTH SIDE OF KY 44 FROM MT. WASHINGTON ELEMENTARY SCHOOL TO FISHER LANE. |  | R | SLO | 2013 | 75000 | 60000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.212 | 2012-06-29 | TIP MOD 18. ADD PROJECT. NEW |  |  | BULLITT |  | KY 44 | [5 empty] | CONSTRUCT SIDEWALK ON THE NORTH SIDE OF KY 44 FROM MT. WASHINGTON ELEMENTARY SCHOOL TO FISHER LANE. |  | U | SLO | 2013 | 75000 | 60000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.212 | 2012-06-29 | TIP MOD 18. ADD PROJECT. NEW |  |  | BULLITT |  | KY 44 | [5 empty] | CONSTRUCT SIDEWALK ON THE NORTH SIDE OF KY 44 FROM MT. WASHINGTON ELEMENTARY SCHOOL TO FISHER LANE. |  | C | SLO | 2014 | 275000 | 220000 | [6 empty] | 0
[6 empty] | BUTLER | 3-115 | US 231 | 1.7 | 8.947 | 10.683 | RELIABILITY | MAJOR WIDENING(O) | CONSTRUCT 5-LANE CURB AND GUTTER ALONG US-231 FROM THE NATCHER PARKWAY TO BELL STREET IN DOWNTOWN MORGANTOWN. (04CCR)(06CCR) | 3 | R | STP | 2013 | 3630000 | 3630000 | PENDING | [5 empty] | 0
[6 empty] | BUTLER | 3-115 | US 231 | 1.7 | 8.947 | 10.683 | RELIABILITY | MAJOR WIDENING(O) | CONSTRUCT 5-LANE CURB AND GUTTER ALONG US-231 FROM THE NATCHER PARKWAY TO BELL STREET IN DOWNTOWN MORGANTOWN. (04CCR)(06CCR) | 4 | U | STP | 2013 | 2200000 | 2200000 | PENDING | [5 empty] | 0
|  |  |  | ARRA | 3000809 | BUTLER | 3-157 | KY 269 |  | 1.544 | 1.644 | RELIABILITY | FERRY OPERATION(P) | REEDS FERRY BARGE REPLACEMENT - CONSTRUCT NEW FERRY BOAT. | 5 | C | FS | 2011 | 300000 | 300000 | ESTIMATED |  | 2010 | OBLIGATED | 300000 |  | 300000 | 2010 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.161 | 2012-01-31 | ADD PROJECT TO STIP. NEW | HSIP | 9010069 | BUTLER LOGAN TODD | 3-912 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | REPLACE GUARDRAIL END TREATMENTS ON VARIOUS ROUTES: BUTLER KY-106, BUTLER KY-70, BUTLER KY-79, LOGAN KY-100, LOGAN US-68X, TODD KY-106, TODD KY-181, TODD US-68X |  | C | SAF | 2012 | 162000 | 162000 |  |  |  | OBLIGATED | 61300 |  | 61300 | 2012 | 3rd QUARTER | N/A
|  |  |  | BRZ | 0303233 | BUTLER | 3-1072 | KY 340 | 0.1 | 7.07 | 7.17 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-340 (MP 7.120) OVER BR OF E PRONG INDIAN CAM; 1.0 MI NORTH OF JCT KY 79; (STRUCTURALLY DEFICIENT, SR=44.3) 016B00041N | 2 | D | BRX | 2012 | 120000 | 120000 | ESTIMATED | N |  | OBLIGATED | 120000 |  | 120000 | 2011 | 2nd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.215 | 2012-07-10 | ADD PROJECT TO STIP. NEW |  |  | BUTLER | 3-1076 | KY 403 | 0.04 | 6.094 | 6.134 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 403 OVER UNNAMED STREAM SE OF COOL SPRINGS ROAD (CR 1142)(SR 4.1) 016B00067N |  | D | BRO | 2012 | 300000 | 300000 | [6 empty] | 0
[6 empty] | BUTLER | 3-8503 | US 231 |  | 11.336 | 11.52 | SAFETY | SAFETY-HAZARD ELIM(P) | CONSTRUCT TURN LANES IN BOTH DIRECTIONS AND INSTALL PROPER LIGHTING AT THE INTERSECTION OF US-231/KY-70 ON TO BOAT FACTORY ROAD. (08CCN)(10CCR) | 3 | R | STP | 2011 | 650000 | 650000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | BUTLER | 3-8503 | US 231 |  | 11.336 | 11.52 | SAFETY | SAFETY-HAZARD ELIM(P) | CONSTRUCT TURN LANES IN BOTH DIRECTIONS AND INSTALL PROPER LIGHTING AT THE INTERSECTION OF US-231/KY-70 ON TO BOAT FACTORY ROAD. (08CCN)(10CCR) | 4 | U | STP | 2011 | 650000 | 650000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | BUTLER | 3-8503 | US 231 |  | 11.336 | 11.52 | SAFETY | SAFETY-HAZARD ELIM(P) | CONSTRUCT TURN LANES IN BOTH DIRECTIONS AND INSTALL PROPER LIGHTING AT THE INTERSECTION OF US-231/KY-70 ON TO BOAT FACTORY ROAD. (08CCN)(10CCR) | 5 | C | STP | 2011 | 1000000 | 1000000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.215 | 2012-07-10 | ADD PROJECT TO STIP. NEW |  |  | CALDWELL | 2-193 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | SOUTHERN CONNECTOR FROM KY 139 TO KY 91, CALDWELL COUNTY. (TO BE LET WITH 2-153.00)(2005HPP-KY162) | 5 | D | HPP | 2012 | 890000 | 890000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | CALDWELL | 2-193 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | SOUTHERN CONNECTOR FROM KY 139 TO KY 91, CALDWELL COUNTY. (TO BE LET WITH 2-153.00)(2005HPP-KY162) | 5 | C | HPP | 2011 | 899900 | 899900 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | CALDWELL | 2-901 | US 641 | 0.1 | 3.15 | 3.3 | SAFETY | SAFETY-HAZARD ELIM(P) | MODIFY HORIZONTAL AND VERTICAL ALIGNMENT ON US-641 0.1MI NORTH JCT. KY-902 AT FREDONIA. (2004BOPC) | 3 | R | HES | 2011 | 60000 | 60000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | CALDWELL | 2-901 | US 641 | 0.1 | 3.15 | 3.3 | SAFETY | SAFETY-HAZARD ELIM(P) | MODIFY HORIZONTAL AND VERTICAL ALIGNMENT ON US-641 0.1MI NORTH JCT. KY-902 AT FREDONIA. (2004BOPC) | 4 | U | HES | 2011 | 50000 | 50000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | CALDWELL | 2-901 | US 641 | 0.1 | 3.15 | 3.3 | SAFETY | SAFETY-HAZARD ELIM(P) | MODIFY HORIZONTAL AND VERTICAL ALIGNMENT ON US-641 0.1MI NORTH JCT. KY-902 AT FREDONIA. (2004BOPC) | 5 | C | HES | 2011 | 300000 | 300000 | ESTIMATED | N |  |  |  |  | 0
|  |  |  | BRO | 5033004 | CALDWELL | 2-1063 | KY 139 | 0.1 | 19.856 | 20.305 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE 3 BRIDGES AND APPROACHES ON KY-139 NORTH OF KY-70 OVER FORK OF DONALDSON CREEK (B04)(B05) AND OVER DONALDSON CREEK (B06). (SR = 25.5, 25.5 & 24.1 RESPECTIVELY): (017B00004N) | 5 | C | BRO | 2011 | 3200000 | 3200000 | ESTIMATED | N |  | OBLIGATED | 3587640 |  | 3587640 | 2011 | 2nd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.058 | 2011-03-22 | ADD PROJECT TO STIP FROM ITEM NO. 1-8502.00 IN THE STIP. NEW | STP | 3008011 | CALLOWAY | 1-120 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | CITY OF MURRAY BUSINESS LOOP FROM GLENDALE TO INDUSTRIAL ROAD. | 3 | R | STP | 2011 | 1110000 | 1110000 | ESTIMATED | N |  | OBLIGATED | 1110000 |  | 1110000 | 2011 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.058 | 2011-03-22 | ADD PROJECT TO STIP FROM ITEM NO. 1-8502.00 IN THE STIP. NEW | STP | 3008012 | CALLOWAY | 1-120 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | CITY OF MURRAY BUSINESS LOOP FROM GLENDALE TO INDUSTRIAL ROAD. | 3 | U | STP | 2011 | 1690000 | 1690000 | ESTIMATED | N |  | OBLIGATED | 1690000 |  | 1690000 | 2011 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.211 | 2012-06-28 | ADD PROJECT TO STIP. NEW |  |  | CALLOWAY | 1-900 | KY 1327 | 0.4 | 0.4 | 0.8 | SAFETY | SAFETY(P) | CONSTRUCT TURN LANE ON KY 1327 AT CALLOWAY COUNTY SCHOOLS AND MSU AG EXPO CENTER.(12CCR) |  | D | STP | 2012 | 280000 | 280000 | [6 empty] | 0
[6 empty] | CALLOWAY | 1-1061 | KY 1536 | 0.1 | 0.299 | 0.309 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY 1536 OVER EAST FORK CLAYTON CREEK (B108) 0.3 MILE SOUTH OF KY 280. (SR=27.7)(08CCR) | 3 | R | BRX | 2013 | 500000 | 500000 | ESTIMATED | [5 empty] | 0
[6 empty] | CALLOWAY | 1-1061 | KY 1536 | 0.1 | 0.299 | 0.309 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY 1536 OVER EAST FORK CLAYTON CREEK (B108) 0.3 MILE SOUTH OF KY 280. (SR=27.7)(08CCR) | 4 | U | BRX | 2013 | 400000 | 400000 | ESTIMATED | [5 empty] | 0
|  |  |  | BRZ | 0103300 | CALLOWAY | 1-1132 | KY 893 | 0.1 | 22.865 | 22.965 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-893 (MP 22.915) OVER MCCULLOUGH FORK; 4.0 MI EAST OF JCT US 641; (STRUCTURALLY DEFICIENT, SR=11.9) 018B00080N | 2 | D | BRX | 2012 | 120000 | 120000 | ESTIMATED | N |  | OBLIGATED | 120000 |  | 120000 | 2012 | 2nd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.216 | 2012-07-25 | ADD AN ADDITIONAL 60,000 TO D PHASE. MOD |  |  | CALLOWAY | 1-1132 | KY 893 | 0.1 | 22.865 | 22.965 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-893 (MP 22.915) OVER MCCULLOUGH FORK; 4.0 MI EAST OF JCT US 641; (STRUCTURALLY DEFICIENT, SR=11.9) 018B00080N | 2 | D | BRX | 2012 | 180000 | 180000 | ESTIMATED | N |  |  |  |  | 0
|  |  |  | BRZ | 0103295 | CALLOWAY | 1-1136 | CR 1464 | 0.1 | 0.088 | 0.188 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON CR-1464 (MP 0.138) OVER BRANCH- CANEY CREEK; .15 MI N OF JCT CR 5412; (STRUCTURALLY DEFICIENT, SR=37.9) 018C00107N | 2 | D | BRZ | 2012 | 200000 | 200000 | ESTIMATED | N |  | OBLIGATED | 200000 |  | 200000 | 2011 | 3rd QUARTER
ADMINISTRATIVE MODIFICATION | 2010.215 | 2012-07-10 | ADD PROJECT TO STIP. NEW |  |  | CALLOWAY | 1-1149 | CR 1411 | 0.04 | 1.027 | 1.067 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON CARLTON RD (CR 1411) OVER W FORK ROCKHOUSE CREEK 0.1 MILE W OF COLLINS RD (CR 1505)(SR 37.3)018C00110N |  | D | BRZ | 2012 | 200000 | 200000 | [6 empty] | 0
[6 empty] | CALLOWAY | 1-8502 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | CITY OF MURRAY BUSINESS LOOP FROM GLENDALE TO INDUSTRIAL ROAD. (08CCN)(10CCR) | 3 | R | STP | 2011 | 1110000 | 1110000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | CALLOWAY | 1-8502 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | CITY OF MURRAY BUSINESS LOOP FROM GLENDALE TO INDUSTRIAL ROAD. (08CCN)(10CCR) | 4 | U | STP | 2011 | 1690000 | 1690000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | CAMPBELL | 6-183 | I 471 |  | 0 | 5.016 | RELIABILITY | RECONSTRUCTION(O) | STUDY AND REHABILITATE THE I-471 CORRIDOR, CAMPBELL COUNTY, KENTUCKY. (SEE ALSO 6-8104.00)(2005HPP-KY120) | 5 | C | HPP | 2011 | 1439839 | 1439839 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.032 | 2011-01-24 | ADD TO STIP. PROJECT IS IN OKI'S FY 2008-2011 TIP. NEW | STPM | 0273015 | CAMPBELL | 6-403 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | CONSTRUCT UNDERGROUND GARAGE AND MULTIMODAL FACILITY AT NEWPORT. BLOCK BOUNDED BY EAST 4TH, EAST 5TH, MONMOUTH AND YORK STREETS. |  | D | SNK | 2011 | 396000 | 396000 |  |  |  | OBLIGATED | 396000 |  | 396000 | 2011 | 2nd QUARTER | CITY OF NEWPORT
ADMINISTRATIVE MODIFICATION | 2010.032 | 2011-01-24 | ADD TO STIP. PROJECT IS IN OKI'S FY 2008-2011 TIP. NEW |  |  | CAMPBELL | 6-403 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | CONSTRUCT UNDERGROUND GARAGE AND MULTIMODAL FACILITY AT NEWPORT. BLOCK BOUNDED BY EAST 4TH, EAST 5TH, MONMOUTH AND YORK STREETS. |  | C | SNK | 2013 | 935759 | 935759 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.032 | 2011-01-24 | ADD TO STIP. PROJECT IS IN OKI'S FY 2008-2011 TIP. NEW | STPM | 8177001 | CAMPBELL | 6-406 |  |  |  |  | RELIABILITY | RECONSTRUCTION(O) | SIGHT DISTANCE AND DRAINAGE IMPROVEMENTS ON CAROTHERS ROAD BETWEEN NEWPORT SHOPPING CENTER AND PAVILION PARKWAY |  | D | SNK | 2011 | 152000 | 152000 |  |  |  | OBLIGATED | 152000 |  | 152000 | 2011 | 2nd QUARTER | CITY OF NEWPORT
ADMINISTRATIVE MODIFICATION | 2010.032 | 2011-01-24 | ADD TO STIP. PROJECT IS IN OKI'S FY 2008-2011 TIP. NEW |  |  | CAMPBELL | 6-406 |  |  |  |  | RELIABILITY | RECONSTRUCTION(O) | SIGHT DISTANCE AND DRAINAGE IMPROVEMENTS ON CAROTHERS ROAD BETWEEN NEWPORT SHOPPING CENTER AND PAVILION PARKWAY |  | C | SNK | 2012 | 1416000 | 1416000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.068 | 2011-04-27 | TIP AMENDMENT #35. ADD TO STIP. NEW |  |  | CAMPBELL | 6-407 | KY 9 | 0.15 | 21.82 | 21.97 | SAFETY | SAFETY(P) | KY 9 RAILROAD UNDERPASS: RECONSTRUCT THE RAILROAD UNDERPASS ON KY 9 AT MP 21.8 |  | D | KYD | 2011 | 344520 | 344520 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.068 | 2011-04-27 | TIP AMENDMENT #35. ADD TO STIP. NEW |  |  | CAMPBELL | 6-407 | KY 9 | 0.15 | 21.82 | 21.97 | SAFETY | SAFETY(P) | KY 9 RAILROAD UNDERPASS: RECONSTRUCT THE RAILROAD UNDERPASS ON KY 9 AT MP 21.8 |  | R | STP | 2012 | 100000 | 100000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.068 | 2011-04-27 | TIP AMENDMENT #35. ADD TO STIP. NEW |  |  | CAMPBELL | 6-407 | KY 9 | 0.15 | 21.82 | 21.97 | SAFETY | SAFETY(P) | KY 9 RAILROAD UNDERPASS: RECONSTRUCT THE RAILROAD UNDERPASS ON KY 9 AT MP 21.8 |  | U | STP | 2012 | 275000 | 275000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.068 | 2011-04-27 | TIP AMENDMENT #35. ADD TO STIP. NEW |  |  | CAMPBELL | 6-407 | KY 9 | 0.15 | 21.82 | 21.97 | SAFETY | SAFETY(P) | KY 9 RAILROAD UNDERPASS: RECONSTRUCT THE RAILROAD UNDERPASS ON KY 9 AT MP 21.8 |  | C | STP | 2012 | 1100000 | 1100000 | [6 empty] | 0
[6 empty] | CAMPBELL | 6-1072 | KY 1996 | 0.1 | 0.209 | 0.309 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-1996 (MP 0.259) OVER STEVENS BRANCH; .75 MI WEST OF JCT KY 10; (STRUCTURALLY DEFICIENT, SR=19.9) 019B00013N | 2 | D | BRX | 2012 | 120000 | 120000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.030 | 2011-01-27 | OKI TIP AMENDMENT #32. ADD TO TIP. CHANGE FY IN STIP. MOD |  |  | CAMPBELL | 6-1072 | KY 1996 | 0.1 | 0.209 | 0.309 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-1996 (MP 0.259) OVER STEVENS BRANCH; .75 MI WEST OF JCT KY 10; (STRUCTURALLY DEFICIENT, SR=19.9) 019B00013N | 2 | D | BRX | 2011 | 120000 | 120000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.065 | 2011-04-13 | OKI TIP MOD #34. CHANGE FUNDING AMOUNT. MOD | BRZ | 0603225 | CAMPBELL | 6-1072 | KY 1996 | 0.1 | 0.209 | 0.309 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-1996 (MP 0.259) OVER STEVENS BRANCH; .75 MI WEST OF JCT KY 10; (STRUCTURALLY DEFICIENT, SR=19.9) 019B00013N | 2 | D | BRX | 2011 | 150000 | 150000 | ESTIMATED | N |  | OBLIGATED | 150000 |  | 150000 | 2011 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.170 | 2012-03-22 | TIP AMENDMENT #6. ADD CONSTRUCTION PHASE. NEW |  |  | CAMPBELL | 6-1072 | KY 1996 | 0.1 | 0.209 | 0.309 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-1996 (MP 0.259) OVER STEVENS BRANCH; .75 MI WEST OF JCT KY 10; (STRUCTURALLY DEFICIENT, SR=19.9) 019B00013N | 2 | C | BRX | 2015 | 300000 | 300000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | CAMPBELL | 6-1076 | CS 1193 | 0.1 | 0.733 | 0.833 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON CS-1193 (MP 0.783) OVER TAYLOR CREEK; 1.0 MI N. JCT KY 1120; (STRUCTURALLY DEFICIENT, SR=31.7) 019C00063N | 2 | D | BRZ | 2012 | 140000 | 140000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.030 | 2011-01-27 | OKI TIP AMENDMENT #32. ADD TO TIP. CHANGE FY IN STIP. MOD | BRZ | 0603224 | CAMPBELL | 6-1076 | CS 1193 | 0.1 | 0.733 | 0.833 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON CS-1193 OVER TAYLOR CREEK; 1.0 MILES NORTH OF JCT KY 1120; (STRUCTURALLY DEFICIENT, SR=31.7) 019C00063N | 2 | D | BRZ | 2011 | 140000 | 140000 | ESTIMATED | N |  | OBLIGATED | 140000 |  | 140000 | 2011 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.170 | 2012-03-22 | TIP AMENDMENT #6. ADD CONSTRUCTION PHASE. NEW |  |  | CAMPBELL | 6-1076 | CS 1193 | 0.1 | 0.733 | 0.833 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON CS-1193 OVER TAYLOR CREEK; 1.0 MILES NORTH OF JCT KY 1120; (STRUCTURALLY DEFICIENT, SR=31.7) 019C00063N | 2 | C | BRZ | 2015 | 1130000 | 1130000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.210 | 2012-06-27 | OKI TIP AMENDMENT #9 FY 2012-15. ADD PROJECT. NEW |  |  | CAMPBELL | 6-1077 | KY 10 |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 10 OVER TWELVE MILE CREEK SE OF KY 1997 (SR 15.1) 019B00006N |  | D | BRO | 2013 | 500000 | 500000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.210 | 2012-06-27 | OKI TIP AMENDMENT #9 FY 2012-15. ADD PROJECT. NEW |  |  | CAMPBELL | 6-1077 | KY 10 |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 10 OVER TWELVE MILE CREEK SE OF KY 1997 (SR 15.1) 019B00006N |  | R | BRO | 2015 | 150000 | 150000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.210 | 2012-06-27 | OKI TIP AMENDMENT #9 FY 2012-15. ADD PROJECT. NEW |  |  | CAMPBELL | 6-1077 | KY 10 |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 10 OVER TWELVE MILE CREEK SE OF KY 1997 (SR 15.1) 019B00006N |  | U | BRO | 2015 | 50000 | 50000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.210 | 2012-06-27 | OKI TIP AMENDMENT #9 FY 2012-15. ADD PROJECT. NEW |  |  | CAMPBELL | 6-1078 | KY 2921 |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 2921 OVER BR OF TWELVE MILE CREEK 0.2 MILE NW OF WASHINGTON TRACE ROAD (CR 1006)(SR 24.3) 019B00061N |  | D | BRO | 2013 | 250000 | 250000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.210 | 2012-06-27 | OKI TIP AMENDMENT #9 FY 2012-15. ADD PROJECT. NEW |  |  | CAMPBELL | 6-1078 | KY 2921 |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 2921 OVER BR OF TWELVE MILE CREEK 0.2 MILE NW OF WASHINGTON TRACE ROAD (CR 1006)(SR 24.3) 019B00061N |  | R | BRO | 2014 | 75000 | 75000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.210 | 2012-06-27 | OKI TIP AMENDMENT #9 FY 2012-15. ADD PROJECT. NEW |  |  | CAMPBELL | 6-1078 | KY 2921 |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 2921 OVER BR OF TWELVE MILE CREEK 0.2 MILE NW OF WASHINGTON TRACE ROAD (CR 1006)(SR 24.3) 019B00061N |  | U | BRO | 2014 | 50000 | 50000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.030 | 2011-01-27 | OKI TIP AMENDMENT #32. ADD PROJECT TO STIP. NEW |  |  | CAMPBELL | 6-2020 | I 275 | 1.84 | 73.55 | 75.39 | RELIABILITY | PAVEMENT REHAB-INT(P) | STRUCTURAL OVERLAY ON IR 275 FROM MP 73.55 TO MP 75.39 (TOLL CREDITS) |  | C | IM | 2011 | 2000000 | 2000000 |  | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.055 | 2011-03-17 | OKI TIP AMENDMENT #34. INCREASE FUNDING AMOUNT FOR C PHASE. MOD | IM | 2759122 | CAMPBELL | 6-2020 | I 275 | 1.84 | 73.55 | 75.39 | RELIABILITY | PAVEMENT REHAB-INT(P) | STRUCTURAL OVERLAY ON IR 275 FROM MP 73.55 TO MP 75.39 (TOLL CREDITS) |  | C | IM | 2011 | 20000000 | 20000000 |  | Y |  | OBLIGATED | 24057282 |  | 24057282 | 2011 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.123 | 2011-09-16 | OKI TIP AMENDMENT #3. ADD PROJECT TO STIP. NEW |  |  | CAMPBELL | 6-2021 | I-471 | 5.72 | 0 | 5.72 | RELIABILITY | PAVEMENT REHAB-INT(P) | PAVEMENT REHABILITATION ON I-471 FROM MP 0.0 (US 27) TO MP 5.72 (OHIO STATE LINE). |  | C | IM | 2011 | 45625000 | 45625000 |  | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.123 | 2011-09-16 | OKI TIP AMENDMENT #3. ADD PROJECT TO STIP. NEW | IM | 4714034 | CAMPBELL | 6-2021 | I-471 | 5.72 | 0 | 5.72 | RELIABILITY | PAVEMENT REHAB-INT(P) | PAVEMENT REHABILITATION ON I-471 FROM MP 0.0 (US 27) TO MP 5.72 (OHIO STATE LINE). |  | C | IMD | 2011 | 3375000 | 3375000 |  | Y |  | OBLIGATED | 13880760 | 49338712 | 63219472 | 2011 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.030 | 2011-01-27 | OKI TIP AMENDMENT #32. ADD PROJECT TO STIP. NEW |  |  | CAMPBELL | 6-2026 | I 275 | 1.637 | 75.386 | 77.023 | RELIABILITY | PAVEMENT REHAB-INT(P) | STRUCTURAL OVERLAY ON IR 275 FROM MP 75.386 TO MP 77.023 (TOLL CREDITS) |  | C | IM | 2011 | 9500000 | 9500000 |  | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.055 | 2011-03-17 | OKI TIP AMENDMENT #34. INCREASE FUNDING AMOUNT FOR C PHASE. MOD | IM | 2759123 | CAMPBELL | 6-2026 | I 275 | 1.637 | 75.386 | 77.023 | RELIABILITY | PAVEMENT REHAB-INT(P) | STRUCTURAL OVERLAY ON IR 275 FROM MP 75.386 TO MP 77.023 (TOLL CREDITS) |  | C | IM | 2011 | 11100000 | 11100000 |  | Y |  | OBLIGATED | 14281423 |  | 14281423 | 2011 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.030 | 2011-01-27 | OKI TIP AMENDMENT #32. ADD PROJECT TO STIP. NEW |  |  | CAMPBELL | 6-2800.30 | I 275 | 1.5 | 75.5 | 77 | SAFETY | SAFETY(P) | INSTALL MEDIAN CABLE GUARDRAIL ON IR 275 FROM MP 75.5 TO MP 77 (TOLL CREDITS) |  | D | IM | 2011 | 30000 | 30000 |  | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.030 | 2011-01-27 | OKI TIP AMENDMENT #32. ADD PROJECT TO STIP. NEW |  |  | CAMPBELL | 6-2800.30 | I 275 | 1.5 | 75.5 | 77 | SAFETY | SAFETY(P) | INSTALL MEDIAN CABLE GUARDRAIL ON IR 275 FROM MP 75.5 TO MP 77 (TOLL CREDITS) |  | C | IM | 2011 | 380000 | 380000 |  | Y |  |  |  |  | 0
[6 empty] | CAMPBELL | 6-8101.02 | KY 9 |  |  |  | RELIABILITY | NEW ROUTE(O) | KY 9 EXTENSION, CAMPBELL COUNTY. (2006KYD)(SEE 6-8101.01 FOR "SP" COMPONENT) | 5 | C | KYD | 2012 | 344520 | 344520 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.017 | 2010-11-18 | OKI TIP AMENDMENT #31. ADD DESIGN PHASE. NEW |  |  | CAMPBELL | 6-8105.01 | I 275 |  |  |  | RELIABILITY | NEW ROUTE(O) | TRANSPORTATION IMPROVEMENTS TO AA-IR 275 CONNECTOR, TOLL CREDITS | 5 | D | HPP | 2011 | 400000 | 400000 | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.017 | 2010-11-18 | OKI TIP AMENDMENT #31. ADD RIGHT-OF-WAY PHASE. NEW |  |  | CAMPBELL | 6-8105.01 | I 275 |  |  |  | RELIABILITY | NEW ROUTE(O) | TRANSPORTATION IMPROVEMENTS TO AA-IR 275 CONNECTOR, TOLL CREDITS | 5 | R | HPP | 2011 | 2000000 | 2000000 | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.017 | 2010-11-18 | OKI TIP AMENDMENT #31. ADD UTILITY PHASE. NEW |  |  | CAMPBELL | 6-8105.01 | I 275 |  |  |  | RELIABILITY | NEW ROUTE(O) | TRANSPORTATION IMPROVEMENTS TO AA-IR 275 CONNECTOR, TOLL CREDITS | 5 | U | HPP | 2011 | 1000000 | 1000000 | ESTIMATED | Y |  |  |  |  | 0
[6 empty] | CAMPBELL | 6-8105.01 | I 275 |  |  |  | RELIABILITY | NEW ROUTE(O) | TRANSPORTATION IMPROVEMENTS TO AA-I-275 CONNECTOR, CAMPBELL COUNTY. (2005HPP-KY155)(SEE 6-8105.00 FOR "KYD" COMPONENT)(06CCR)(10CCR) | 5 | C | HPP | 2011 | 5399401 | 5399401 | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.017 | 2010-11-18 | OKI TIP AMENDMENT #31. CHANGE FUNDING AMOUNT IN TIP. MOD |  |  | CAMPBELL | 6-8105.01 | I 275 |  |  |  | RELIABILITY | NEW ROUTE(O) | TRANSPORTATION IMPROVEMENTS TO AA-IR 275 CONNECTOR, TOLL CREDITS | 5 | C | HPP | 2011 | 5399401 | 5399401 | ESTIMATED | Y |  |  |  |  | 0
[6 empty] | CAMPBELL | 6-8105.02 | I 275 |  |  |  | RELIABILITY | NEW ROUTE(O) | TRANSPORTATION IMPROVEMENTS TO AA-I-275 CONNECTOR, CAMPBELL COUNTY. (2005HPP-KY166)(SEE 6-8105.00 FOR "KYD" COMPONENT) | 5 | C | HPP | 2011 | 7249112 | 7249112 | ESTIMATED | Y | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.016 | 2010-11-15 | OKI TIP MOD #31. REVISE FUNDING AMOUNT IN THE TIP AND DESCRIPTION. MOD |  |  | CAMPBELL | 6-8105.02 | I 275 |  |  |  | RELIABILITY | NEW ROUTE(O) | TRANSPORTATION IMPROVEMENTS TO AA-IR 275 CONNECTOR. TOLL CREDITS | 5 | C | HPP | 2011 | 7249112 | 7249112 | ESTIMATED | Y |  |  |  |  | 0
[6 empty] | CAMPBELL | 6-8105.03 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | CONSTRUCT NEW TECHNOLOGY TRIANGLE ACCESS ROAD, CAMPBELL COUNTY, KENTUCKY. (2005HPP-KY126)(2006BOPC).(10CCR) | 5 | C | HPP | 2011 | 1439839 | 1439839 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.016 | 2010-11-15 | OKI TIP MOD #31. REVISE FUNDING AMOUNT IN THE TIP AND DESCRIPTION. MOD |  |  | CAMPBELL | 6-8105.03 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | CONSTRUCT NEW TECHNOLOGY TRIANGLE ACCESS ROAD. TOLL CREDITS | 5 | C | HPP | 2011 | 1439839 | 1439839 | ESTIMATED | N |  |  |  |  | 0
|  |  |  | STPS | 0601164 | CARROLL | 6-990 | KY 47 | 0.2 | 0 | 0.1 | SAFETY | SAFETY-HAZARD ELIM(P) | KY 47 FROM MP 0.0 TO MP 0.1 @ KY 36 & KY 467, RECONSTRUCT RR CROSSING & IMPROVE SIGHT DISTANCE (B/C=2.5) (D-DISTRICT,C-CONTRACTOR) (2002BOP) | 3 | R | HES | 2011 | 160000 | 160000 | ESTIMATED | N | 2010 | OBLIGATED | 75000 |  | 75000 | 2011 | 3rd QUARTER | N/A
|  |  |  | STPS | 0601165 | CARROLL | 6-990 | KY 47 | 0.2 | 0 | 0.1 | SAFETY | SAFETY-HAZARD ELIM(P) | KY 47 FROM MP 0.0 TO MP 0.1 @ KY 36 & KY 467, RECONSTRUCT RR CROSSING & IMPROVE SIGHT DISTANCE (B/C=2.5) (D-DISTRICT,C-CONTRACTOR) (2002BOP) | 4 | U | HES | 2011 | 110000 | 110000 | ESTIMATED | N | 2010 | OBLIGATED | 470000 |  | 470000 | 2011 | 3rd QUARTER | N/A
[6 empty] | CARROLL | 6-990 | KY 47 | 0.2 | 0 | 0.1 | SAFETY | SAFETY-HAZARD ELIM(P) | KY 47 FROM MP 0.0 TO MP 0.1 @ KY 36 & KY 467, RECONSTRUCT RR CROSSING & IMPROVE SIGHT DISTANCE (B/C=2.5) (D-DISTRICT,C-CONTRACTOR) (2002BOP) | 5 | C | HES | 2011 | 280000 | 280000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.110 | 2011-08-25 | ADD PROJECT TO STIP. NEW | IM | 0712070 | CARROLL | 6-2035 | I-71 | 0.303 | 39.343 | 39.39 | RELIABILITY | BRIDGE REHAB(P) | REPAIR TWIN BRIDGES ON I-71 AT MILL CREEK AND MILL CREEK ROAD: JOINT REPLACEMENT/ELIMINATION, OVERLAY, BARRIER WALL RETROFIT, PIER CAP PATCHING AND OTHER ITEMS. (2011BOP) |  | C | IM | 2011 | 1500000 | 1500000 |  |  |  | OBLIGATED | 1243000 |  | 1243000 | 2012 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.070 | 2011-04-25 | ADD PROJECT TO STIP. BREAKOUT FROM 99-911.00. NEW | HSIP | 5211093 | CARTER | 9-904 | US 60 | 4.4 | 19.15 | 23.55 | SAFETY | SAFETY-HAZARD ELIM(P) | SHOULDER IMPROVEMENTS ON US 60 FROM WEST OF KY 6228 TO POWERS STREET IN GRAYSON: PAVE 4' OF EXISTING ROCK SHOULDERS, REPLACE GUARDRAIL END TREATMENTS AND EXTEND A BOX CULVERT. |  | C | SAF | 2011 | 798000 | 798000 |  |  |  | OBLIGATED | 1128642 |  | 1128642 | 2011 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.099 | 2011-07-14 | ADD PROJECT TO STIP. BREAKOUT FROM 99-911.00. NEW | HSIP | 9010059 | CARTER FLEMING NICHOLAS | 9-907 | US 68 |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | REPLACE GUARDRAIL END TREATMENTS ON VARIOUS ROUTES: CARTER US 60 (MP 19.15-25.50), FLEMING US 68 (MP 0.00-5.423), NICHOLAS US 68 (MP 0.00-12.132), ROBERTSON US 68 (MP 0.00-1.357). |  | C | SAF | 2011 | 1096000 | 1096000 |  |  |  | OBLIGATED | 834000 |  | 834000 | 2011 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.214 | 2012-07-05 | ADD PROJECT TO STIP. NEW |  |  | CARTER | 9-911 | KY 1947 | 3.398 | 0 | 3.398 | SAFETY | SAFETY-HAZARD ELIM(P) | SHOULDER IMPROVEMENTS, DRAINAGE STRUCTURE REPLACEMENT, AND DITCHING AND SHOULDERING ON KY 1947 FROM US 60 WEST OF GRAYSON, EAST TO KY 7 NORTH OF GRAYSON. |  | C | SAF | 2012 | 290000 | 290000 | [6 empty] | 0
[6 empty] | CARTER | 9-1072 | US 60 | 0.1 | 26.262 | 26.362 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON US-60 (MP 26.312) OVER UPPER STINSON CREEK; 1.5 MI E OF E-JCT KY 1; (STRUCTURALLY DEFICIENT, SR=29.6) 022B00064N | 2 | D | BRO | 2011 | 210000 | 210000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.012 | 2010-11-05 | CHANGE FUNDING AMOUNT. MOD | BRO | 5211091 | CARTER | 9-1072 | US 60 | 0.1 | 26.262 | 26.362 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON US-60 (MP 26.312) OVER UPPER STINSON CREEK; 1.5 MI E OF E-JCT KY 1; (STRUCTURALLY DEFICIENT, SR=29.6) 022B00064N | 2 | D | BRO | 2011 | 260000 | 260000 | ESTIMATED | N |  | OBLIGATED | 260000 |  | 260000 | 2011 | 1st QUARTER | N/A
[6 empty] | CARTER | 9-1072 | US 60 | 0.1 | 26.262 | 26.362 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON US-60 (MP 26.312) OVER UPPER STINSON CREEK; 1.5 MI E OF E-JCT KY 1; (STRUCTURALLY DEFICIENT, SR=29.6) 022B00064N | 3 | R | BRO | 2012 | 200000 | 200000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | CARTER | 9-1072 | US 60 | 0.1 | 26.262 | 26.362 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON US-60 (MP 26.312) OVER UPPER STINSON CREEK; 1.5 MI E OF E-JCT KY 1; (STRUCTURALLY DEFICIENT, SR=29.6) 022B00064N | 4 | U | BRO | 2012 | 100000 | 100000 | ESTIMATED | N |  |  |  |  | 0
|  |  |  | BRO | 5211092 | CARTER | 9-1075 | US 60 | 0.1 | 4.061 | 4.161 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON US-60 (MP 4.111) OVER TYGARTS CREEK; .75 MI E OF JCT KY 1662; (STRUCTURALLY DEFICIENT, SR=47) 022B00037N | 2 | D | BRO | 2012 | 150000 | 150000 | ESTIMATED | N |  | OBLIGATED | 150000 |  | 150000 | 2011 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.214 | 2012-07-05 | ADD PROJECT TO STIP. NEW |  |  | CARTER | 9-1080 | US 60 | 0.04 | 3.659 | 3.699 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON US 60 OVER REEVES BRANCH 0.05 MILE W OF REEVES BRANCH ROAD(CR 1352)(SR 39.4) 022B00038 |  | D | BRO | 2012 | 450000 | 450000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.214 | 2012-07-05 | ADD PROJECT TO STIP. NEW |  |  | CARTER | 9-1081 | KY 474 | 0.04 | 5.062 | 5.102 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 474 OVER SMITH CREEK IN CARTER AT INTERSECTION OF KY 474 AND NUNN ROAD(CR 1507)(SR 40.1) 022B00123N |  | D | BRO | 2012 | 450000 | 450000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.214 | 2012-07-05 | ADD PROJECT TO STIP. NEW |  |  | CARTER | 9-1083 | KY 2 | 0.4 | 8.734 | 8.774 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 2 OVER JORDA FORK AT INTERSECTION OF KY 2 & JORDAN FORK ROAD(CR 1445)(SR40.2) 022B00072N |  | D | BRO | 2012 | 650000 | 650000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.039 | 2011-02-07 | ADD PROJECT TO STIP. BREAKOUT FROM 99-65.08. NEW | IM | 0647048 | CARTER | 9-2020 | I 64 | 1 | 168 | 169 | RELIABILITY | BRIDGE REHAB(P) | REPLACE EXPANSION JOINTS, PATCH AND PLACE CONCRETE OVERLAY ON US 60 BRIDGE OVER I-64 2.5 MILES WEST OF KY 7 AT GRAYSON. |  | C | IM | 2011 | 265000 | 265000 |  | Y |  | OBLIGATED | 413778.5 |  | 413778.5 | 2011 | 2nd QUARTER | N/A
[6 empty] | CHRISTIAN | 2-100.2 | US 41A |  | 13.19 | 13.668 | RELIABILITY | NEW ROUTE(O) | E.T. BREATHITT (PENNYRILE) PARKWAY EXTENSION SECTION 1A; RECONSTRUCT US-41A FROM CLINIC DRIVE (INCLUDING CLINIC DR RECONSTRUCTION) TO NORTH ENTRANCE OF THE MALL. (2004BOPC)(CONSTRUCT SEQUENCE 3) | 5 | C | NH | 2012 | 8660000 | 8660000 | ESTIMATED | Y |  |  |  |  | 0
[6 empty] | CHRISTIAN | 2-156 | KY 115 | 0.1 | 1.2 | 1.3 | SAFETY | SAFETY(P) | RECONSTRUCT THE KY 115/KY 911 INTERSECTION IN OAK GROVE.(03KYDN)(04KYD-KY074)(05KYD) ("KYD" FUNDS NOT AVAILABLE FOR TOTAL CONSTRUCTION COST OF 2.7 MILLION)(10CCR) | 5 | C | STP | 2012 | 3000000 | 3000000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | CHRISTIAN | 2-174.01 | CR 1150 | 1.1 | 0 | 0.884 | RELIABILITY | RECONSTRUCTION(O) | FORT CAMPBELL COLE ROAD WIDENING, KENTUCKY. (ADDITIONAL AMOUNT NEEDED TO SUPPLEMENT "KYD" FUNDS TO COVER COST)(10CCR) | 5 | C | STP | 2011 | 3000000 | 3000000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.075 | 2011-05-09 | TIP AMENDMENT #4. INCREASE FUNDING AMOUNT. MOD | PLHD STP | 8910004 8910004 | CHRISTIAN | 2-174.01 | CR 1150 | 1.1 | 0 | 0.884 | RELIABILITY | RECONSTRUCTION(O) | FORT CAMPBELL COLE ROAD WIDENING, KENTUCKY. (ADDITIONAL AMOUNT NEEDED TO SUPPLEMENT "KYD" FUNDS TO COVER COST)(10CCR) | 5 | C | STP | 2011 | 5550000 | 5550000 | ESTIMATED | N |  | OBLIGATED | 5500000 |  | 5500000 | 2011 | 3rd QUARTER | N/A
[6 empty] | CHRISTIAN | 2-203 | KY 107 |  | 16.9 | 17 | RELIABILITY | CONGESTION MITIGTN(O) | INTERSECTION IMPROVEMENT AT KY-107 AND KOFFMAN DRIVE JUST SOUTH OF COUNTRY CLUB LANE IN HOPKINSVILLE. (2006BOPC) | 3 | R | CM | 2011 | 240000 | 240000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | CHRISTIAN | 2-203 | KY 107 |  | 16.9 | 17 | RELIABILITY | CONGESTION MITIGTN(O) | INTERSECTION IMPROVEMENT AT KY-107 AND KOFFMAN DRIVE JUST SOUTH OF COUNTRY CLUB LANE IN HOPKINSVILLE. (2006BOPC) | 4 | U | CM | 2011 | 550000 | 550000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | CHRISTIAN | 2-203 | KY 107 |  | 16.9 | 17 | RELIABILITY | CONGESTION MITIGTN(O) | INTERSECTION IMPROVEMENT AT KY-107 AND KOFFMAN DRIVE JUST SOUTH OF COUNTRY CLUB LANE IN HOPKINSVILLE. (2006BOPC) | 5 | C | CM | 2011 | 650000 | 650000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | CHRISTIAN | 2-213 | I 24 | 0.1 | 85.183 | 85.902 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | MODIFY I-24/US-41A INTERCHANGE @ FORT CAMPBELL (PE & ENV SHOWN UNDER 2-311.00) | 3 | R | IM | 2011 | 450000 | 450000 | ESTIMATED | Y | 2010 |  |  |  | 0
[6 empty] | CHRISTIAN | 2-213 | I 24 | 0.1 | 85.183 | 85.902 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | MODIFY I-24/US-41A INTERCHANGE @ FORT CAMPBELL (PE & ENV SHOWN UNDER 2-311.00) | 4 | U | IM | 2011 | 170000 | 170000 | ESTIMATED | Y | 2010 |  |  |  | 0
|  |  |  | IM | 0243050 | CHRISTIAN | 2-213 | I 24 | 0.1 | 85.183 | 85.902 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | MODIFY I-24/US-41A INTERCHANGE @ FORT CAMPBELL (PE & ENV SHOWN UNDER 2-311.00) | 5 | C | IM | 2011 | 1630000 | 1630000 | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.077 | 2011-05-17 | TIP AMENDMENT #5. INCREASE C PHASE. MOD | IM | 0243050 | CHRISTIAN | 2-213 | I 24 | 0.1 | 85.183 | 85.902 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | MODIFY I-24/US-41A INTERCHANGE @ FORT CAMPBELL (PE & ENV SHOWN UNDER 2-311.00) | 5 | C | IM | 2011 | 2700000 | 2700000 | ESTIMATED | Y |  | OBLIGATED | 2771681.5 |  | 2771681.5 | 2011 | 3rd QUARTER | N/A
[6 empty] | CHRISTIAN | 2-8505 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | EXTEND LOVERS LANE AND MAKE SAFETY IMPROVEMENTS. (08CCN)(10CCR) | 5 | C | STP | 2011 | 3300000 | 3300000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.037 | 2011-02-15 | TIP AMENDMENT #1. ADDING GROUPED PROJECTS PAGE. THIS ITEM NUMBER IS A BREAKOUT OF ZVARIOUS NO. 99-352.06. NEW | RHPD | 3017022 | CHRISTIAN | 99-352.06 | CS 1512 |  |  |  | SAFETY | SAFETY-RR PROTECTN(P) | 1ST STREET (CS 1512) AT CSX RAILROAD CROSSING IN HOPKINSVILLE. ADD GATES TO EXISTING FLASHING LIGHTS AND BELL SYSTEM. |  | C | RHPD | 2011 | 290000 | 290000 |  |  |  | OBLIGATED | 262500 |  | 262500 | 2011 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.050 | 2011-03-08 | ADD PROJECT TO STIP. BREAKOUT FROM 99-337.06. NEW | IM | 0645075 | CLARK | 7-6.02 | I-64 |  |  |  | RELIABILITY | REST AREA REHAB(P) | I-64 EASTBOUND REST AREA IMPROVEMENTS |  | D | IM | 2011 | 37500 | 37500 |  | Y |  | OBLIGATED | 37500 |  | 37500 | 2011 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.050 | 2011-03-08 | ADD PROJECT TO STIP. BREAKOUT FROM 99-337.06. NEW |  |  | CLARK | 7-6.02 | I-64 |  |  |  | RELIABILITY | REST AREA REHAB(P) | I-64 EASTBOUND REST AREA IMPROVEMENTS |  | C | IM | 2011 | 375000 | 375000 |  | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.133 | 2011-09-27 | ADD PROJECT TO STIP. BREAKOUT FROM 99-65.09. NEW |  |  | CLARK | 7-88.00 | I-64 | 0.1 | 101.685 | 101.785 | RELIABILITY | BRIDGE REHAB(P) | PLACE LATEX OVERLAY AND REPLACE JOINTS ON THE US 60 BRIDGE OVER I-64 WEST OF THE MONTGOMERY COUNTY LINE. |  | C | IM | 2012 | 275000 | 275000 |  | Y |  |  |  |  | 0
[6 empty] | CLARK | 7-1121 | KY 974 | 0.1 | 10.874 | 10.974 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-974 (MP 10.924) OVER DRY FORK; .05 MI E-CR 1124 @ALLNSVL; (STRUCTURALLY DEFICIENT, SR=23.1) 025B00090N | 2 | D | BRX | 2012 | 140000 | 140000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.076 | 2011-05-09 | INCREASE D PHASE FUNDING AMOUNT. MOD | BRZ | 0703303 | CLARK | 7-1121 | KY 974 | 0.1 | 10.874 | 10.974 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-974 (MP 10.924) OVER DRY FORK; .05 MI E-CR 1124 @ALLNSVL; (STRUCTURALLY DEFICIENT, SR=23.1) 025B00090N | 2 | D | BRZ | 2012 | 230000 | 230000 | ESTIMATED | N |  | OBLIGATED | 230000 |  | 230000 | 2011 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.110 | 2011-08-25 | ADD DESIGN PHASE TO STIP. NEW | IM | 0645079 | CLARK/ MONTGOMERY | 7-2032 | I-64 | 10.5 | 101.6 | 112.1 | RELIABILITY | PAVEMENT REHAB-INT(P) | MILL AND RESURFACE EAST AND WESTBOUND DIRECTIONS FROM MP 101.60 TO 112.10 IN CLARK AND MONTGOMERY COUNTIES. |  | D | IM | 2011 | 300000 | 300000 |  |  |  | OBLIGATED |  | 300000 | 300000 | 2012 | 1st QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.106 | 2011-08-23 | ADD PROJECT TO STIP. NEW | IM | 0645080 | CLARK/ MONTGOMERY | 7-2032 | I-64 | 10.5 | 101.6 | 112.1 | RELIABILITY | PAVEMENT REHAB-INT(P) | MILL AND RESURFACE EAST AND WESTBOUND DIRECTIONS FROM MP 101.60 TO 112.10 IN CLARK AND MONTGOMERY COUNTIES. |  | C | IM | 2011 | 7753000 | 7753000 |  |  |  | OBLIGATED | 8966095.68 |  | 8966095.68 | 2011 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.134 | 2011-09-28 | ADD R AND U PHASES TO STIP. | HPP | 0145004 | CLARK | 7-8101.01 | KY 974 |  |  |  | RELIABILITY | NEW INTERCHANGE(O) | CONSTRUCT KIDVILLE ROAD (KY 974) INTERCHANGE AT THE MOUNTAIN PARKWAY, CLARK COUNTY. |  | R | NH | 2012 | 736000 | 736000 |  |  |  | OBLIGATED |  | 736000 | 736000 | 2012 | 1st QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.134 | 2011-09-28 | ADD R AND U PHASES TO STIP. | NH | 9000004 | CLARK | 7-8101.01 | KY 974 |  |  |  | RELIABILITY | NEW INTERCHANGE(O) | CONSTRUCT KIDVILLE ROAD (KY 974) INTERCHANGE AT THE MOUNTAIN PARKWAY, CLARK COUNTY. |  | U | NH | 2012 | 200000 | 200000 |  |  |  | OBLIGATED |  | 200000 | 200000 | 2012 | 1st QUARTER | N/A
[6 empty] | CLARK | 7-8101.01 | KY 9000 | 0.1 | 10.531 | 10.631 | RELIABILITY | NEW INTERCHANGE(O) | CONSTRUCT KIDVILLE ROAD (KY 974) INTERCHANGE AT THE MOUNTAIN PARKWAY, CLARK COUNTY. (2005HPP-KY145)(SEE 7-8101.02 FOR SUPPLEMENTAL FUNDING COMPONENTS) | 5 | C | HPP | 2011 | 563863 | 563863 | ESTIMATED | Y | 2010 |  |  |  | 0
[6 empty] | CLARK | 7-8101.02 | KY 9000 | 0.1 | 10.531 | 10.631 | RELIABILITY | NEW INTERCHANGE(O) | INTERCHANGE AT MOUNTAIN PARKWAY AND KY-974 (KIDDVILLE RD). (04CCN)(SEE 7-8101.01 FOR 2005HPP COMPONENT)(08CCR) | 3 | R | NHG | 2011 | 530000 | 530000 | ESTIMATED |  | 2010 |  |  |  | 0
[6 empty] | CLARK | 7-8101.02 | KY 9000 | 0.1 | 10.531 | 10.631 | RELIABILITY | NEW INTERCHANGE(O) | INTERCHANGE AT MOUNTAIN PARKWAY AND KY-974 (KIDDVILLE RD). (04CCN)(SEE 7-8101.01 FOR 2005HPP COMPONENT)(08CCR)(10CCR) | 5 | C | NHG | 2011 | 11140000 | 11140000 | ESTIMATED | Y |  |  |  |  | 0
|  |  |  | NH | 0645074 | CLARK | 7-8506.01 | I 64 |  | 95.1 | 97.675 | RELIABILITY | MAJOR WIDENING(O) | PREPARE FEASIBILITY STUDY TO EVALUATE THE EXISTING I-64/MOUNTAIN PARKWAY (KY9000) INTERCHANGE AND DETERMINE ANY NECESSARY UPGRADES OR RECONSTRUCTION TO ACCOMMODATE THE EXISTING AND FUTURE TRAFFIC MOVEMENTS.(10CCR) | 2 | D | NH | 2011 | 2500000 | 2500000 | ESTIMATED | N | 2010 | OBLIGATED | 2500000 |  | 2500000 | 2011 | 1st QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.064 | 2011-04-12 | ADD PROJECT TO STIP. BREAKOUT FROM 99-911.00. NEW | HSIP | 4211022 | CLAY | 11-915 | US 421 | 0.19 | 16.92 | 17.11 | SAFETY | SAFETY-HAZARD ELIM(P) | INTERSECTION IMPROVEMENTS ON US 421 AT KY 80 0.2 MILE NORTHWEST OF KY 3481 IN MANCHESTER. |  | C | SAF | 2011 | 110000 | 110000 |  |  |  | OBLIGATED | 110000 |  | 110000 | 2011 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.199 | 2012-06-04 | ADD PROJECT TO STIP. BREAKOUT FROM 99-911.01. NEW | HSIP | 5272007 | CLAY | 11-923 | KY 11 | 0.476 | 4.129 | 4.605 | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALL GUARDRAIL ALONG KY 11 FROM .002 MILE NORTH OF COY VALENTINE ROAD TO 0.374 MILE SOUTH OF BUNDRY ROAD. |  | C | SAF | 2012 | 45000 | 45000 |  |  |  | OBLIGATED | 45000 |  | 45000 | 2012 | 3rd QUARTER | N/A
|  |  |  | BRZ | 1103199 | CLAY | 11-1069 | CR 1113A | 0.1 | 0.013 | 0.031 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON CR-1113A OVER BIG CREEK (C63). (SR=4.0)(PROJECT FUNDING CONTINGENT UPON BRIDGE POSTING COMPLIANCE) | 2 | D | BRZ | 2013 | 240000 | 240000 | PENDING |  |  | OBLIGATED | 245000 |  | 245000 | 2011 | 4th QUARTER | N/A
[6 empty] | CLAY | 11-1069 | CR 1113A | 0.1 | 0.013 | 0.031 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON CR-1113A OVER BIG CREEK (C63). (SR=4.0)(PROJECT FUNDING CONTINGENT UPON BRIDGE POSTING COMPLIANCE): (026C00063N)(10CCR) | 3 | R | BRZ | 2011 | 270000 | 270000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | CLAY | 11-1069 | CR 1113A | 0.1 | 0.013 | 0.031 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON CR-1113A OVER BIG CREEK (C63). (SR=4.0)(PROJECT FUNDING CONTINGENT UPON BRIDGE POSTING COMPLIANCE): (026C00063N)(10CCR) | 4 | U | BRZ | 2011 | 210000 | 210000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | CLAY | 11-1069 | CR 1113A | 0.1 | 0.013 | 0.031 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON CR-1113A OVER BIG CREEK (C63). (SR=4.0)(PROJECT FUNDING CONTINGENT UPON BRIDGE POSTING COMPLIANCE): (026C00063N)(10CCR) | 5 | C | BRZ | 2012 | 850000 | 850000 | ESTIMATED | N |  |  |  |  | 0
|  |  |  | NCPD | 3000873 | CLAY | 11-8002.01 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | ACCESS FROM THE HAL ROGERS PARKWAY TO THE NEW CLAY COUNTY INDUSTRIAL PARK. (GRADE, DRAIN & INC. SURFACE) (01KYD)(02KYD)(03KYD)(2006BOPP) ("KYD" FUNDS NOT AVAILABLE FOR TOTAL CONSTRUCTION COST OF 20 MILLION)(10CCN) | 5 | C | KYD | 2011 | 4500000 | 4500000 | ESTIMATED | N | 2010 | OBLIGATED | 23306594 |  | 23306594 | 2011 | 1st QUARTER | N/A
[6 empty] | CLAY | 11-8002.03 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | ACCESS FROM THE HAL ROGERS PARKWAY TO THE NEW CLAY COUNTY INDUSTRIAL PARK.(10CCR) | 5 | C | STP | 2011 | 15900000 | 15900000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | CLINTON | 8-260.03 | US 127 | 4.3 |  |  | RELIABILITY | BYPASS(O) | US-127 ALBANY BYPASS, GRADE, DRAIN AND SURFACING SECTION. SEE 8-260.15 FOR BRIDGE AND CULVERT SECTION . (02CCR)(04CCR)(08CCR)(10CCN) | 5 | C | STP | 2011 | 20800000 | 20800000 | REESTIMATED | Y | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.116 | 2011-09-06 | INCREASE FUNDING. MOD | HPSTP | 0139003 | CLINTON | 8-260.03 | US 127 | 4.3 |  |  | RELIABILITY | BYPASS(O) | US-127 ALBANY BYPASS, GRADE, DRAIN AND SURFACING SECTION. | 5 | C | STP | 2011 | 21500000 | 21500000 | REESTIMATED | Y | 2010 | OBLIGATED | 10700000 | 10800000 | 21500000 | 2011 | 4th QUARTER | N/A
[6 empty] | CLINTON | 8-260.1 | US 127 | 4.1 |  |  | RELIABILITY | RELOCATION(O) | RECONSTRUCT US-127 FROM THE TENN STATE LINE TO ALBANY BYPASS. (98KYD)(02CCR) (PE & ENV. UNDER 8-260.00)(04CCR)(08CCR)(10CCR) | 5 | C | NH | 2012 | 6550000 | 6550000 | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.121 | 2011-09-07 | INCREASE FUNDING. AMOUNT. MOD | NH | 1271105 | CLINTON | 8-260.1 | US 127 | 4.1 |  |  | RELIABILITY | RELOCATION(O) | RECONSTRUCT US-127 FROM THE TENN STATE LINE TO ALBANY BYPASS. (98KYD)(02CCR) (PE & ENV. UNDER 8-260.00)(04CCR)(08CCR)(10CCR) | 5 | C | NH | 2011 | 15750000 | 15750000 | ESTIMATED | Y |  | OBLIGATED | 9800930.45 | 0 | 9800930.45 | 2011 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.062 | 2011-04-07 | ADD PROJECT. BREAKOUT FROM 99-911.00. NEW | HSIP | 1271103 | CLINTON | 8-910 | US 127 | 0.15 | 4.25 | 4.4 | SAFETY | SAFETY-HAZARD ELIM(P) | REMOVE EMBANKMENT TO IMPROVE SIGHT DISTANCE ON US 127 0.14 MI NORTH OF KY 696 SOUTHEAST OF ALBANY. |  | U | SAF | 2011 | 20000 | 20000 |  |  |  | OBLIGATED | 20000 |  | 20000 | 2011 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.062 | 2011-04-07 | ADD PROJECT. BREAKOUT FROM 99-911.00. NEW | HSIP | 1271104 | CLINTON | 8-910 | US 127 | 0.15 | 4.25 | 4.4 | SAFETY | SAFETY-HAZARD ELIM(P) | REMOVE EMBANKMENT TO IMPROVE SIGHT DISTANCE ON US 127 0.14 MI NORTH OF KY 696 SOUTHEAST OF ALBANY. |  | C | SAF | 2011 | 55873 | 55873 |  |  |  | OBLIGATED | 98977.5 |  | 98977.5 | 2011 | 3rd QUARTER | N/A
|  |  |  | ARRA | 3000807 | CRITTENDEN | 1-138 | KY 91 |  | 11.162 | 11.262 | RELIABILITY | FERRY OPERATION(P) | CAVE IN ROCK FERRY LANDING IMPROVEMENT PROJECT - CONSTRUCTION AND REHABILITATION OF FERRY LANDING TO REDUCE SERVICE DELAYS | 5 | C | FS | 2011 | 90000 | 90000 | ESTIMATED | N | 2010 | OBLIGATED | 90000 |  | 90000 | 2010 | 4th QUARTER | N/A
[6 empty] | DAVIESS | 2-167 | KY 56 | 0.1 | 13.966 | 14.105 | RELIABILITY | CONGESTION MITIGTN(O) | CONSTRUCT A ROUND-ABOUT AT THE INTERSECTION OF KY-56/KY-81 AND WORTHINGTON ROAD WEST OF OWENSBORO. (2004BOPC) | 3 | R | CM | 2011 | 320000 | 320000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.003 | 2010-10-05 | TIP MOD #11: MODIFY THE R PHASE FUNDING AMOUNT IN THE TIP TO MATCH THE STIP AMOUNT AND CHANGE TIP FY TO 2011 AND DESCRIPTION. MOD | CM | 3023025 | DAVIESS | 2-167 | KY 56 | 0.1 | 13.966 | 14.105 | RELIABILITY | CONGESTION MITIGTN(O) | KY 81/KY 56/WORTHINGTON RD ROUNDABOUT: RECONSTRUCT THE INTERSECTION TO A ROUNDABOUT CONFIGURATION AND RELOCATE WORTHINGTON ROAD TO FORM A FOUR LEGGED ROUNDABOUT. | 3 | R | CM | 2011 | 320000 | 320000 | ESTIMATED | N |  | OBLIGATED | 320000 |  | 320000 | 2011 | 1st QUARTER | N/A
[6 empty] | DAVIESS | 2-167 | KY 56 | 0.1 | 13.966 | 14.105 | RELIABILITY | CONGESTION MITIGTN(O) | CONSTRUCT A ROUND-ABOUT AT THE INTERSECTION OF KY-56/KY-81 AND WORTHINGTON ROAD WEST OF OWENSBORO. (2004BOPC) | 4 | U | CM | 2011 | 420000 | 420000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.003 | 2010-10-05 | TIP MOD #11: MODIFY THE U PHASE FUNDING AMOUNT IN THE TIP TO MATCH THE STIP AMOUNT AND CHANGE TIP FY TO 2011 AND DESCRIPTION. MOD |  |  | DAVIESS | 2-167 | KY 56 | 0.1 | 13.966 | 14.105 | RELIABILITY | CONGESTION MITIGTN(O) | KY 81/KY 56/WORTHINGTON RD ROUNDABOUT: RECONSTRUCT THE INTERSECTION TO A ROUNDABOUT CONFIGURATION AND RELOCATE WORTHINGTON ROAD TO FORM A FOUR LEGGED ROUNDABOUT. | 3 | U | CM | 2011 | 420000 | 420000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | DAVIESS | 2-167 | KY 56 | 0.1 | 13.966 | 14.105 | RELIABILITY | CONGESTION MITIGTN(O) | CONSTRUCT A ROUND-ABOUT AT THE INTERSECTION OF KY-56/KY-81 AND WORTHINGTON ROAD WEST OF OWENSBORO. (2004BOPC) | 5 | C | CM | 2011 | 1950000 | 1950000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.003 | 2010-10-05 | TIP MOD #11: MODIFY THE C PHASE FUNDING AMOUNT IN THE TIP TO MATCH THE STIP AMOUNT AND CHANGE TIP FY TO 2011 AND DESCRIPTION. MOD |  |  | DAVIESS | 2-167 | KY 56 | 0.1 | 13.966 | 14.105 | RELIABILITY | CONGESTION MITIGTN(O) | KY 81/KY 56/WORTHINGTON RD ROUNDABOUT: RECONSTRUCT THE INTERSECTION TO A ROUNDABOUT CONFIGURATION AND RELOCATE WORTHINGTON ROAD TO FORM A FOUR LEGGED ROUNDABOUT. | 3 | C | CM | 2011 | 1950000 | 1950000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | DAVIESS | 2-224 | KY 2155 |  | 3.585 | 4.427 | RELIABILITY | BRIDGE REHAB(P) | DAVIESS COUNTY GROVER CARY BRIDGE OVER THE OHIO RIVER. (KY-010) | 5 | C | KYD | 2011 | 1540600 | 1540600 | ESTIMATED |  | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.069 | 2011-04-21 | TIP MOD #12. INCREASE THE FUNDING AMOUNT FOR C PHASE. MOD | KBD | 0101039 | DAVIESS | 2-224 | KY 2155 |  | 3.585 | 4.427 | RELIABILITY | BRIDGE REHAB(P) | DAVIESS COUNTY GROVER CARY BRIDGE OVER THE OHIO RIVER. (KY-010) | 5 | C | KYD | 2011 | 3000000 | 3000000 | ESTIMATED |  | 2010 | OBLIGATED | 1725000 |  | 1725000 | 2011 | 3rd QUARTER | N/A
|  |  |  | STP | 0604011 | DAVIESS | 2-287.1 | US 60 | 2.7 |  |  | RELIABILITY | RELOCATION(O) | RELOCATE US-60 BYPASS EAST OF OWENSBORO (EAST COUNTY CORRIDOR): FROM THE US-60B/KY-54 INTERCHANGE, EXTENDING EAST TO REID ROAD. (98KYD) (2004BOPC)(10CCR) | 5 | C | STP | 2011 | 15000000 | 15000000 | ESTIMATED | Y |  | OBLIGATED | 10886855.39 | 31654192.61 | 42541048 | 2011 | 3rd QUARTER | N/A
[6 empty] | DAVIESS | 2-287.1 | US 60 | 2.7 |  |  | RELIABILITY | PREFINANCD CONVRSN(O) | RELOCATE US-60 BYPASS EAST OF OWENSBORO (EAST COUNTY CORRIDOR): FROM THE US-60B/KY-54 INTERCHANGE, EXTENDING EAST TO REID ROAD. (98KYD) (2004BOPC)(10CCR) | 5 | C | STP | 2012 | 10000000 | 10000000 | ESTIMATED | Y |  |  |  |  | 0
[6 empty] | DAVIESS | 2-287.1 | US 60 | 2.7 |  |  | RELIABILITY | PREFINANCD CONVRSN(O) | RELOCATE US-60 BYPASS EAST OF OWENSBORO (EAST COUNTY CORRIDOR): FROM THE US-60B/KY-54 INTERCHANGE, EXTENDING EAST TO REID ROAD. (98KYD) (2004BOPC)(10CCR) | 5 | C | STP | 2013 | 9620000 | 9620000 | ESTIMATED | Y |  |  |  |  | 0
AMENDMENT | 2010.003 | 2011-06-09 | ADDING PROJECT TO STIP PER THE MPO's RESOLUTION DATED MARCH 2011 FOR THE NEW APPROVED TIP FOR FY 2011-2016. | STP | 0604013 | DAVIESS | 2-287.20 | KY 54 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCTION OF THE KY 54/US 60 BYPASS INTERCHANGE IN OWENSBORO. |  | D | STP | 2012 | 200000 | 200000 |  | Y |  |  |  |  | 0
AMENDMENT | 2010.003 | 2011-06-09 | ADDING PROJECT TO STIP PER THE MPO's RESOLUTION DATED MARCH 2011 FOR THE NEW APPROVED TIP FOR FY 2011-2016. | STP | 1541014 | DAVIESS | 2-287.21 | KY 54 |  | 2.397 | 2.469 | RELIABILITY | RECONSTRUCTION(O) | CONSTRUCT AN EASTBOUND RIGHT TURN LANE ON KY 54 AT US 60 BYPASS IN OWENSBORO |  | C | STP | 2012 | 200000 | 200000 |  | Y |  | OBLIGATED | 200000 |  | 200000 | 2012 | 2nd QUARTER | N/A
[6 empty] | DAVIESS | 2-287.52 | US 60 | 2.2 |  |  | RELIABILITY | RELOCATION(O) | TRANSPORTATION IMPROVEMENTS TO US 60 OWENSBORO, DAVIESS COUNTY. (2005HPP-KY167)(SEE 2-287.51 FOR "FS" COMPONENT) | 5 | C | HPP | 2011 | 1812278 | 1812278 | ESTIMATED | Y | 2010 |  |  |  | 0
|  |  |  | BRZ | 0203300 | DAVIESS | 2-1065 | KY 279 | 0.1 | 2.37 | 2.41 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-279 OVER BRANCH OF PANTHER CREEK (B120). (SR=49.5): (030B00120N) | 5 | C | BRX | 2011 | 630000 | 630000 | ESTIMATED | N |  | OBLIGATED | 720000 |  | 720000 | 2011 | 1st QUARTER | N/A
[6 empty] | DAVIESS | 2-1066 | CR 1060 | 0.1 | 1.893 | 1.911 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON CR-1060 OVER BLACKFORD CREEK (C18). (SR=19.9)(08CCR): (030C00018N) | 3 | R | BRZ | 2011 | 110000 | 110000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | DAVIESS | 2-1066 | CR 1060 | 0.1 | 1.893 | 1.911 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON CR-1060 OVER BLACKFORD CREEK (C18). (SR=19.9)(08CCR): (030C00018N) | 4 | U | BRZ | 2011 | 110000 | 110000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | DAVIESS | 2-1066 | CR 1060 | 0.1 | 1.893 | 1.911 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON CR-1060 OVER BLACKFORD CREEK (C18). (SR=19.9)(08CCR): (030C00018N) | 5 | C | BRZ | 2011 | 1060000 | 1060000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | DAVIESS | 2-1075 | PR 1212 | 0.1 | 0.675 | 0.775 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON PR-1212 (MP 0.725) OVER TRIB-PANTHER CK; .4 MI E KY 279; (STRUCTURALLY DEFICIENT, SR=16.8) 030C00168N | 2 | D | BRZ | 2012 | 130000 | 130000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.061 | 2011-03-30 | BREAKOUT THE DESIGN PHASE FROM THE CONSTRUCTION PHASE THAT IS IN THE STIP. NEW | HPP | 0118001 | EDMONSON | 3-149 | KY 70 | 0.36 | 10.401 | 10.761 | RELIABILITY | SPOT IMPROVEMENTS(O) | RECONSTRUCT KY-70/KY-259 FROM 0.36 MILE NORTH GREEN RIVER BRIDGE AT BROWNSVILLE TO 0.42 MILE NORTH OF THE KY-70/KY-259 INTERSECTION. (2005HPP-KY118) (10CCR) | 5 | D | HPP | 2011 | 100000 | 100000 | ESTIMATED | N | 2010 | OBLIGATED | 100000 |  | 100000 | 2011 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.215 | 2012-07-10 | ADD PHASE TO STIP. NEW |  |  | EDMONSON | 3-149 | KY 70/ KY 259 |  |  |  | RELIABILITY | SPOT IMPROVEMENTS(O) | RECONSTRUCT KY-70/KY-259 FROM 0.36 MILE NORTH GREEN RIVER BRIDGE AT BROWNSVILLE TO 0.42 MILE NORTH OF THE KY-70/KY-259 INTERSECTION. (2005HPP-KY118) (10CCR) | 5 | R | HPP | 2012 | 130000 | 130000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.216 | 2012-07-25 | INCREASE R PHASE TO 200,000. MOD |  |  | EDMONSON | 3-149 | KY 70/ KY 259 |  |  |  | RELIABILITY | SPOT IMPROVEMENTS(O) | RECONSTRUCT KY-70/KY-259 FROM 0.36 MILE NORTH GREEN RIVER BRIDGE AT BROWNSVILLE TO 0.42 MILE NORTH OF THE KY-70/KY-259 INTERSECTION. (2005HPP-KY118) (10CCR) | 5 | R | HPP | 2012 | 200000 | 200000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.215 | 2012-07-10 | ADD PHASE TO STIP. NEW |  |  | EDMONSON | 3-149 | KY 70/ KY 259 |  |  |  | RELIABILITY | SPOT IMPROVEMENTS(O) | RECONSTRUCT KY-70/KY-259 FROM 0.36 MILE NORTH GREEN RIVER BRIDGE AT BROWNSVILLE TO 0.42 MILE NORTH OF THE KY-70/KY-259 INTERSECTION. (2005HPP-KY118) (10CCR) | 5 | U | HPP | 2012 | 220000 | 220000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | EDMONSON | 3-149 | KY 70 | 0.36 | 10.401 | 10.761 | RELIABILITY | SPOT IMPROVEMENTS(O) | RECONSTRUCT KY-70/KY-259 FROM 0.36 MILE NORTH GREEN RIVER BRIDGE AT BROWNSVILLE TO 0.42 MILE NORTH OF THE KY-70/KY-259 INTERSECTION. (2005HPP-KY118) (10CCR) | 5 | C | HPP | 2011 | 1079880 | 1079880 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | EDMONSON | 3-8508 | I 65 |  | 43.75 | 45.935 | RELIABILITY | MAJOR WIDENING(O) | TENN STATE LINE-ELIZABETHTOWN; WIDEN TO 6-LANES FROM KY-1339 TO 0.6 MILES NORTH OF THE KY-255 I-CHANGE (B48). (SUPPLEMENTAL "STP" FUNDING FOR 03-12 PROJECT). (08CCN)(10CCN) | 5 | C | STP | 2011 | 6483000 | 6483000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | EDMONSON | 3-8509 | I 65 |  | 43.789 | 45.935 | RELIABILITY | MAJOR WIDENING(O) | TENN STATE LINE-ELIZABETHTOWN; WIDEN TO 6-LANES FROM KY-1339 TO 0.6 MILES NORTH OF THE KY-255 I-CHANGE (B48). (SUPPLEMENTAL "NHG" FUNDING FOR 3-12 PROJECT). (08CCN)(10CCN) | 5 | C | NHG | 2011 | 23817000 | 23817000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | ELLIOTT | 9-126.51 | KY 7 | 5.2 | 13.47 | 18.48 | RELIABILITY | RECONSTRUCTION(O) | SANDY HOOK - I-64; RECONSTRUCT KY-7 FROM 0.4 MI NORTH OF KY-706 TO THE CARTER COUNTY LINE. (2004BOPC)(08CCR) | 5 | C | STP | 2011 | 27500000 | 27500000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.214 | 2012-07-05 | ADD PROJECT TO STIP. NEW |  |  | ELLIOTT | 9-228 | KY 7 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT KY 7 FROM SOUTH CITY LIMITS OF SANDY HOOK TOWARD WRIGLEY (TO KY 711 AT WRIGLEY). (12CCR) |  | P | STP | 2012 | 1000000 | 1000000 | [6 empty] | 0
[6 empty] | ELLIOTT | 9-1077 | CR 1122 | 0.1 | 0.029 | 0.129 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON CR-1122 (MP 0.079) OVER LICK FK NEWCOMBE CREEK; .05 MI S OF JCT KY 32; (STRUCTURALLY DEFICIENT, SR=2) 032C00006N | 2 | D | BRZ | 2012 | 120000 | 120000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | ESTILL | 10-363.21 | KY 89 | 1.7 | 12.881 | 14.578 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT KY 89 FROM IRVINE BYPASS TO 2000 FEET NORTH OF ESTILL COUNTY HIGH SCHOOL, ESTILL COUNTY (PRIORITY SECTION). (2005HPP-KY117)(SEE 10-363.20 FOR "SPB" COMPONENT) | 5 | C | HPP | 2011 | 539940 | 539940 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.157 | 2012-01-19 | ADD PROJECT TO STIP. NEW | HSIP | 9010072 | ESTILL | 10-913 | KY 499 | 1.721 | 6.02 | 7.741 | SAFETY | SAFETY | EXTEND CULVERTS, INSTALL SIGNING, AND RESHAPE DITCHES ON KY 499 FROM KY 3328 TO KY 52. |  | C | SAF | 2012 | 335000 | 335000 |  |  |  | OBLIGATED | 395340.1 |  | 395340.1 | 2012 | 2nd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.045 | 2011-03-02 | TIP AMENDMENT #1. ADD D PHASE. NEW | NH | 2682011 | FAYETTE | 7-113 | KY 4 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | NEW CIRCLE ROAD IMPROVEMENTS BETWEEN VERSAILLES RD AND GEORGETOWN RD; LENGTH 4.1 MI | 3 | D | NH | 2011 | 2000000 | 2000000 | REESTIMATED | Y |  | OBLIGATED | 1000000 |  | 1000000 | 2011 | 3rd QUARTER | N/A
[6 empty] | FAYETTE | 7-113 | KY 4 | 1.28 | 8.731 | 10.015 | RELIABILITY | MAJOR WIDENING(O) | NEW CIRCLE ROAD REHAB AND WIDENING FROM VERSAILLES ROAD TO NEAR GEORGETOWN ROAD.(10CCN) | 3 | R | NH | 2013 | 15230000 | 15230000 | REESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.045 | 2011-03-02 | TIP AMENDMENT #1. REDUCE R PHASE TO 2,000,000 AND FY TO 2013. MOD |  |  | FAYETTE | 7-113 | KY 4 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | NEW CIRCLE ROAD IMPROVEMENTS BETWEEN VERSAILLES RD AND GEORGETOWN RD; LENGTH 4.1 MI | 3 | R | NH | 2013 | 2000000 | 2000000 | REESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.045 | 2011-03-02 | TIP AMENDMENT #1. REMOVE U AND C PHASES FROM TIP AND STIP. U PHASE WAS 5,200,000. C PHASE IS IN REG SIGNIFICANT SECTION IN STIP. MOD |  |  | FAYETTE | 7-113 | KY 4 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | NEW CIRCLE ROAD REHAB AND WIDENING FROM VERSAILLES ROAD TO NEAR GEORGETOWN ROAD.(10CCN) | 4 | U | NH | 2013 |  |  | REESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.045 | 2011-03-02 | TIP AMENDMENT #1. REVISED R PHASE IN TIP TO MATCH THE STIP. MOD | NH | 2681024 | FAYETTE | 7-144.01 | US 68 | 1.4 | 2.882 | 3.296 | RELIABILITY | MAJOR WIDENING(O) | WIDEN HARRODSBURG ROAD AT NEW CIRCLE ROAD FROM CORPORATE DRIVE TO ALEXANDRIA DRIVE BY INCREASING CAPACITY UNDER THE NCR BRIDGES AND INTERSECTION IMPROVEMENTS. (06CCR) | 3 | R | NH | 2011 | 110000 | 110000 | ESTIMATED | N | 2010 | OBLIGATED | 465000 |  | 465000 | 2010 | 4th QUARTER | N/A
|  |  |  | NH | 2681025 | FAYETTE | 7-144.01 | US 68 | 1.4 | 2.882 | 3.296 | RELIABILITY | MAJOR WIDENING(O) | WIDEN HARRODSBURG ROAD AT NEW CIRCLE ROAD FROM CORPORATE DRIVE TO ALEXANDRIA DRIVE BY INCREASING CAPACITY UNDER THE NCR BRIDGES AND INTERSECTION IMPROVEMENTS. (06CCR) | 4 | U | NH | 2011 | 840000 | 840000 | ESTIMATED | N | 2010 | OBLIGATED | 840000 |  | 840000 | 2011 | 1st QUARTER | N/A
[6 empty] | FAYETTE | 7-144.01 | US 68 | 1.4 | 2.882 | 3.296 | RELIABILITY | MAJOR WIDENING(O) | WIDEN HARRODSBURG ROAD AT NEW CIRCLE ROAD FROM CORPORATE DRIVE TO ALEXANDRIA DRIVE BY INCREASING CAPACITY UNDER THE NCR BRIDGES AND INTERSECTION IMPROVEMENTS. (06CCR) | 5 | C | NH | 2011 | 2170000 | 2170000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.071 | 2011-04-26 | TIP MOD #16. INCREASE C PHASE FUNDING AMOUNT AND CHANGE DESCRIPTION. MOD | NH | 2681026 | FAYETTE | 7-144.01 | US 68 | 1.4 | 2.882 | 3.296 | RELIABILITY | MAJOR WIDENING(O) | HARRODSBURG ROAD AT NEW CIRCLE ROAD FROM CORPORATE DRIVE TO ALEXANDRIA DRIVE . INCREASE CAPACITY BY CONSTRUCTING A DOUBLE CROSS-OVER DIAMOND INTERCHANGE AND INTERSECTION IMPROVEMENTS | 5 | C | NH | 2011 | 5700000 | 5700000 | ESTIMATED | N |  | OBLIGATED | 6740110 |  | 6740110 | 2011 | 2nd QUARTER | N/A
[6 empty] | FAYETTE | 7-220 | US 25 | 1 | 8.4 | 9.55 | SAFETY | BIKE/PED FACIL(O) | RICHMOND ROAD MULTIUSE PATH IN LEXINGTON BETWEEN EAGLE CREEK DRIVE AND JACOBSON PARK. (LOCAL MATCH) (ALL WORK BY LFUCG) (SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | 5 | C | SLX | 2011 | 638000 | 638000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.045 | 2011-03-02 | TIP AMENDMENT #1. CHANGED FISCAL YEAR TO 2012, CHANGED DESCRIPTION AND AMOUNT. MOD |  |  | FAYETTE | 7-220 | US 25 | 1 | 8.4 | 9.55 | SAFETY | BIKE/PED FACIL(O) | RICHMOND ROAD MULTIUSE PATH IN LEXINGTON BETWEEN EAGLE CREEK DRIVE AND COYS LANE | 5 | C | SLX | 2012 | 690000 | 552000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | FAYETTE | 7-223 | US 421 | 1.5 | 2.296 | 3.842 | RELIABILITY | MAJOR WIDENING(O) | LEESTOWN ROAD; WIDEN TO 4 LANES FROM EXISTING 4-LANE NEAR NEW CIRCLE ROAD TO MASTERSON PARK (LFUCG T.I.P.). (SEE 7-223.02 FOR "SLX" COMPONENT)(08CCR) (10CCR) | 5 | C | STP | 2011 | 14070000 | 14070000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.045 | 2011-03-02 | TIP AMENDMENT #1. CHANGED C PHASE IN TIP TO MATCH THE STIP FOR C PHASE. MOD |  |  | FAYETTE | 7-223 | US 421 | 1.5 | 2.296 | 3.842 | RELIABILITY | MAJOR WIDENING(O) | LEESTOWN ROAD; WIDEN TO 4 LANES FROM EXISTING 4-LANE NEAR NEW CIRCLE ROAD TO MASTERSON PARK (LFUCG T.I.P.). (SEE 7-223.02 FOR "SLX" COMPONENT)(08CCR) (10CCR) | 5 | C | STP | 2011 | 14070000 | 14070000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | FAYETTE | 7-223.02 | US 421 | 1.5 | 2.296 | 3.842 | RELIABILITY | MAJOR WIDENING(O) | LEESTOWN ROAD; WIDEN TO 4 LANES FROM EXISTING 4-LANE NEAR NEW CIRCLE ROAD TO MASTERSON PARK. (ADDITIONAL "SLX" FUNDING FOR C PHASE)(SEE 7-223.00 FOR "STP" COMPONENT) (SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | 5 | C | SLX | 2011 | 4856384 | 4856384 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.045 | 2011-03-02 | TIP AMENDMENT #1. CHANGED FISCAL YEAR TO 2011, CHANGED DESCRIPTION AND AMOUNT. MOD |  |  | FAYETTE | 7-223.02 | US 421 | 1.5 | 2.296 | 3.842 | RELIABILITY | MAJOR WIDENING(O) | LEESTOWN ROAD; WIDEN TO 4 LANES FROM EXISTING 4-LANE TO MASTERSON PARK. | 5 | C | SLX | 2011 | 4856384 | 3885000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.183 | 2012-04-30 | TIP MOD #25. ADD PROJECT TO COVER INCREASED DESIGN COST. NEW | STPM | 8552003 | FAYETTE | 7-224.50 | CS-4174 | 1.7 |  |  | RELIABILITY | MINOR WIDENING(O) | CLAYS MILL ROAD; WIDEN FROM NEW CIRCLE ROAD TO TWAIN RIDGE DRIVE (SECTION 2) |  | D | SLX | 2012 | 75000 | 75000 |  | N |  | OBLIGATED | 516600 |  | 516600 | 2012 | 3RD QUARTER | LFUCG
[6 empty] | FAYETTE | 7-224.51 | CS 4174 |  | 2.684 | 3.593 | RELIABILITY | MINOR WIDENING(O) | CLAYS MILL ROAD (SECTION 2A); WIDEN FROM KEITHSHIRE WAY TO HIGBEE MILL ROAD. (LOCAL MATCH) (ALL WORK BY LFUCG)(PRIORITY SECTION) (SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | 5 | C | SLX | 2011 | 4759040 | 4759040 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.005 | 2010-10-06 | TIP MOD #11: CLAYS MILL ROAD SECTION 2A - SHIFT CONSTRUCTION FUNDING TO FY 2011. MOD | STPM | 8552006 | FAYETTE | 7-224.51 | CS 4174 | 0.9 | 2.684 | 3.593 | RELIABILITY | MINOR WIDENING(O) | CLAYS MILL ROAD; WIDEN FROM KEITHSHIRE WAY TO HIGBEE MILL ROAD. SECTION 2A | 5 | C | SLX | 2011 | 4160000 | 3328000 | ESTIMATED | N |  | OBLIGATED | 4160000 |  | 4160000 | 2010 | 4th QUARTER | LEXINGTON-FAYETTE URBAN COUNTY GOVERNMENT
ADMINISTRATIVE MODIFICATION | 2010.045 | 2011-03-02 | TIP AMENDMENT #1. INCREASE FUNDING TO 4,200,000. MOD |  |  | FAYETTE | 7-224.51 | CS 4174 | 0.9 | 2.684 | 3.593 | RELIABILITY | MINOR WIDENING(O) | CLAYS MILL ROAD; WIDEN FROM KEITHSHIRE WAY TO HIGBEE MILL ROAD. SECTION 2A | 5 | C | SLX | 2011 | 4200000 | 3360000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.183 | 2012-04-30 | TIP MOD #25. ADD $250,000 ADDITIONAL SLX FUNDS TO COVER CONSTRUCTION CHANGE ORDERS. MOD |  |  | FAYETTE | 7-224.51 | CS 4174 | 0.9 | 2.684 | 3.593 | RELIABILITY | MINOR WIDENING(O) | CLAYS MILL ROAD; WIDEN FROM KEITHSHIRE WAY TO HIGBEE MILL ROAD. SECTION 2A | 5 | C | SLX | 2011 | 4450000 | 4450000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | FAYETTE | 7-224.53 | CS 4174 | 1.8 | 3.593 | 3.883 | RELIABILITY | MINOR WIDENING(O) | CLAYS MILL ROAD (SECTION 2B); WIDEN FROM HIGBEE MILL ROAD TO TWAIN RIDGE DRIVE. (LOCAL MATCH) (ALL WORK BY LFUCG) (SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | 5 | C | SLX | 2012 | 5353920 | 5353920 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.045 | 2011-03-02 | TIP AMENDMENT #1. INCREASE FUNDING TO 5,354,000. MOD |  |  | FAYETTE | 7-224.53 | CS 4174 | 1.8 | 3.593 | 3.883 | RELIABILITY | MINOR WIDENING(O) | CLAYS MILL ROAD ; WIDEN FROM HIGBEE MILL ROAD TO TWAIN RIDGE DRIVE. SECTION 2B | 5 | C | SLX | 2012 | 5354000 | 4283000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.130 | 2011-09-16 | TIP MOD #21. REDUCE C PHASE TO 3,000,000 AND CHANGE FUNDING TO 2 TYPES. MOD |  |  | FAYETTE | 7-224.53 | CS 4174 | 0.3 |  |  | RELIABILITY | MINOR WIDENING(O) | CLAYS MILL ROAD ; WIDEN FROM HIGBEE MILL ROAD TO TWAIN RIDGE DRIVE. SECTION 2B |  | C | STP | 2012 | 3000000 | 2500000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.130 | 2011-09-16 | TIP MOD #21. REDUCE C PHASE TO 3,000,000 AND CHANGE FUNDING TO 2 TYPES. MOD |  |  | FAYETTE | 7-224.53 | CS 4174 | 0.3 |  |  | RELIABILITY | MINOR WIDENING(O) | CLAYS MILL ROAD SECTION 2B; WIDEN FROM HIGBEE MILL ROAD TO TWAIN RIDGE DRIVE. SECTION 2B |  | C | SLX | 2012 | 3000000 | 500000 | [6 empty] | 0
[6 empty] | FAYETTE | 7-224.55 | CS 4174 |  | 2.01 | 2.684 | RELIABILITY | MINOR WIDENING(O) | CLAYS MILL ROAD (SECTION 2C); WIDEN FROM NEW CIRCLE ROAD TO KEITHSHIRE WAY. (LOCAL MATCH) (ALL WORK BY LFUCG) (SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | 5 | C | SLX | 2011 | 4689558 | 4689558 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.130 | 2011-09-16 | TIP MOD #21. ADD ROW PHASE TO STIP. NEW |  |  | FAYETTE | 7-224.55 | CS 4174 | 0.6 | 2.01 | 2.684 | RELIABILITY | MINOR WIDENING(O) | CLAYS MILL ROAD SECTION 2C; WIDEN FROM NEW CIRCLE ROAD TO KEITHSHIRE WAY. |  | R | SLX | 2012 | 250000 | 250000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.045 | 2011-03-02 | TIP AMENDMENT #1. INCREASE FUNDING TO 5,073,000 AND CHANGE FISCAL YEAR TO 2013. MOD |  |  | FAYETTE | 7-224.55 | CS 4174 |  | 2.01 | 2.684 | RELIABILITY | MINOR WIDENING(O) | CLAYS MILL ROAD; WIDEN FROM NEW CIRCLE ROAD TO KEITHSHIRE WAY. SECTION 2C | 5 | C | SLX | 2013 | 5073000 | 4058000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.130 | 2011-09-16 | TIP MOD #21. REDUCE CONSTRUCTION COSTS. MOD |  |  | FAYETTE | 7-224.55 | CS 4174 | 0.6 | 2.01 | 2.684 | RELIABILITY | MINOR WIDENING(O) | CLAYS MILL ROAD SECTION 2C; WIDEN FROM NEW CIRCLE ROAD TO KEITHSHIRE WAY. |  | C | SLX | 2012 | 3500000 | 3500000 | [6 empty] | 0
[6 empty] | FAYETTE | 7-225 | KY 1927 | 1 | 2.7 | 3.95 | RELIABILITY | MAJOR WIDENING(O) | LIBERTY ROAD/TODDS ROAD; WIDEN FROM 0.2 MI S OF ANDOVER FOREST DRIVE/FOREST HILL DRIVE TO I-75 (SECTION 2) (ALL WORK BY LFUCG)(SEE 7-590.00 FOR SECTION 1) (SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | 3 | R | SLX | 2011 | 3208937 | 3208937 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.045 | 2011-03-02 | TIP AMENDMENT #1. INCREASE R FUNDING TO 3,370,000. CHANGE FY TO 2012. MOD |  |  | FAYETTE | 7-225 | KY 1927 | 1 | 2.7 | 3.95 | RELIABILITY | MAJOR WIDENING(O) | LIBERTY ROAD/TODDS ROAD; WIDEN FROM 0.2 MI S OF ANDOVER FOREST DRIVE/FOREST HILL DRIVE TO I-75 (SECTION 2) | 3 | R | SLX | 2012 | 3370000 | 2696000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.051 | 2011-03-08 | TIP MOD #15. DECREASE R COST TO $1,000,000. MOD |  |  | FAYETTE | 7-225 | KY 1927 | 1 | 2.7 | 3.95 | RELIABILITY | MAJOR WIDENING(O) | LIBERTY ROAD/TODDS ROAD; WIDEN FROM 0.2 MI S OF ANDOVER FOREST DRIVE/FOREST HILL DRIVE TO I-75 (SECTION 2) | 3 | R | SLX | 2012 | 1000000 | 1000000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.130 | 2011-09-16 | TIP MOD #21. SPLIT PROJECT INTO 2 SECTIONS. MOD |  |  | FAYETTE | 7-225 | KY 1927 | 1.1 |  |  | RELIABILITY | MAJOR WIDENING(O) | LIBERTY ROAD/TODDS ROAD; WIDEN FROM 0.2 MI S OF ANDOVER FOREST DRIVE/FOREST HILL DRIVE TO KIMBOLTON DRIVE (SECTION 2A) |  | R | SLX | 2012 | 1000000 | 800000 |  | N |  |  |  |  | 0
[6 empty] | FAYETTE | 7-225 | KY 1927 | 1 | 2.7 | 3.95 | RELIABILITY | MAJOR WIDENING(O) | LIBERTY ROAD/TODDS ROAD; WIDEN FROM 0.2 MI S OF ANDOVER FOREST DRIVE/FOREST HILL DRIVE TO I-75 (SECTION 2) (ALL WORK BY LFUCG)(SEE 7-590.00 FOR SECTION 1) (SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | 4 | U | SLX | 2013 | 1953945 | 1953945 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.045 | 2011-03-02 | TIP AMENDMENT #1. INCREASE U FUNDING TO 1,954,000. MOD |  |  | FAYETTE | 7-225 | KY 1927 | 1 | 2.7 | 3.95 | RELIABILITY | MAJOR WIDENING(O) | LIBERTY ROAD/TODDS ROAD; WIDEN FROM 0.2 MI S OF ANDOVER FOREST DRIVE/FOREST HILL DRIVE TO I-75 (SECTION 2) | 3 | U | SLX | 2013 | 1954000 | 1563000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.130 | 2011-09-16 | TIP MOD #21. SPLIT PROJECT INTO 2 SECTIONS. MOD |  |  | FAYETTE | 7-225 | KY 1927 | 1.1 |  |  | RELIABILITY | MAJOR WIDENING(O) | LIBERTY ROAD/TODDS ROAD; WIDEN FROM 0.2 MI S OF ANDOVER FOREST DRIVE/FOREST HILL DRIVE TO KIMBOLTON DRIVE (SECTION 2A) | 3 | U | SLX | 2013 | 1954000 | 1563000 | [6 empty] | 0
[6 empty] | FAYETTE | 7-225 | KY 1927 | 1 | 2.7 | 3.95 | RELIABILITY | MAJOR WIDENING(O) | LIBERTY ROAD/TODDS ROAD; WIDEN FROM 0.2 MI S OF ANDOVER FOREST DRIVE/FOREST HILL DRIVE TO I-75 (SECTION 2) (ALL WORK BY LFUCG)(SEE 7-590.00 FOR SECTION 1) (SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | 5 | C | SLX | 2014 | 5224588 | 5224588 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.045 | 2011-03-02 | TIP AMENDMENT #1. DECREASE C FUNDING TO 5,225,000. MOD |  |  | FAYETTE | 7-225 | KY 1927 | 1 | 2.7 | 3.95 | RELIABILITY | MAJOR WIDENING(O) | LIBERTY ROAD/TODDS ROAD; WIDEN FROM 0.2 MI S OF ANDOVER FOREST DRIVE/FOREST HILL DRIVE TO I-75 (SECTION 2) | 3 | C | SLX | 2014 | 5225000 | 5225000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.130 | 2011-09-16 | TIP MOD #21. SPLIT PROJECT INTO 2 SECTIONS. MOD |  |  | FAYETTE | 7-225 | KY 1927 | 1.1 |  |  | RELIABILITY | MAJOR WIDENING(O) | LIBERTY ROAD/TODDS ROAD; WIDEN FROM 0.2 MI S OF ANDOVER FOREST DRIVE/FOREST HILL DRIVE TO KIMBOLTON DRIVE (SECTION 2A) |  | C | SLX | 2014 | 5225000 | 5225000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.047 | 2011-02-28 | TIP MOD #14. ADD PROJECT TO STIP. NEW |  |  | FAYETTE | 7-226 |  | 2.5 |  |  | RELIABILITY | NEW ROUTE(O) | CITATION BOULEVARD: PHASE II FROM SOUTHERN RR TO LEESTOWN RD; LENGTH = 2.5 MI |  | D | SLX | 2011 | 50000 | 50000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.047 | 2011-02-28 | TIP MOD #14. ADD PROJECT TO STIP. NEW |  |  | FAYETTE | 7-226 |  | 2.5 |  |  | RELIABILITY | NEW ROUTE(O) | CITATION BOULEVARD: PHASE II FROM SOUTHERN RR TO LEESTOWN RD; LENGTH = 2.5 MI |  | R | SLX | 2011 | 450000 | 450000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.130 | 2011-09-16 | TIP MOD #21. INCREASE RIGHT-OF-WAY COSTS AND MOVE TO FY 2012. MOD |  |  | FAYETTE | 7-226 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | CITATION BOULEVARD: PHASE II FROM SOUTHERN RR TO LEESTOWN RD; LENGTH = 2.5 MI |  | R | SLX | 2012 | 590000 | 472000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.040 | 2011-02-09 | TIP MOD NO. 13. ADDING PROJECT TO STIP FOR FY 2011. NEW |  |  | FAYETTE | 7-227.00 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | VARIOUS CONTINUING PROGRAMS (RIDESHARE/MOBILITY, AIR QUALITY PLANNING, TRAFFIC SIGNALS, CONGESTION MANAGEMENT, BICYCLE/PEDESTRIAN PLANNING) | 5 | C | SLX | 2011 | 650000 | 650000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.040 | 2011-02-09 | TIP MOD NO. 13. ADDING PROJECT TO STIP FOR FY 2012. NEW |  |  | FAYETTE | 7-227.00 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | VARIOUS CONTINUING PROGRAMS (RIDESHARE/MOBILITY, AIR QUALITY PLANNING, TRAFFIC SIGNALS, CONGESTION MANAGEMENT, BICYCLE/PEDESTRIAN PLANNING) | 5 | C | SLX | 2012 | 780000 | 780000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.091 | 2011-06-23 | TIP MOD NO. 18. INCREASING THE FY 2012 FUNDING BY $10,000. MOD |  |  | FAYETTE | 7-227.00 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | VARIOUS CONTINUING PROGRAMS (RIDESHARE/MOBILITY, AIR QUALITY PLANNING, TRAFFIC SIGNALS, CONGESTION MANAGEMENT, BICYCLE/PEDESTRIAN PLANNING) | 5 | C | SLX | 2012 | 790000 | 790000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.040 | 2011-02-09 | TIP MOD NO. 13. ADDING PROJECT TO STIP FOR FY 2013. NEW |  |  | FAYETTE | 7-227.00 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | VARIOUS CONTINUING PROGRAMS (RIDESHARE/MOBILITY, AIR QUALITY PLANNING, TRAFFIC SIGNALS, CONGESTION MANAGEMENT, BICYCLE/PEDESTRIAN PLANNING) | 5 | C | SLX | 2013 | 780000 | 780000 | ESTIMATED | N | 2010 |  |  |  | 0
|  |  |  | STPM | 3003259 3003260 3003261 3003262 3003264 | FAYETTE | 7-227.07 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | VARIOUS 'SLX' CONTINUING PROGRAM PROJECTS (RIDESHARE/MOBILITY, AIR QUALITY PLANNING, TRAFFIC SIGNAL) (LOCAL MATCH) (ALL WORK BY LFUCG) (SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). SEE 7-227.09 | 5 | C | SLX | 2011 | 650000 | 650000 | ESTIMATED | N | 2010 | OBLIGATED | 358000 |  | 358000 | 2011 | 3rd QUARTER | LEXINGTON-FAYETTE URBAN COUNTY GOVERNMENT
ADMINISTRATIVE MODIFICATION | 2010.028 | 2011-01-10 | THIS PROJECT IS A DUPLICATE IN THE STIP. THE PHASE IS BEING REMOVED TO SHOW THE PROJECT NOT BEING USED. SEE 7-227.09 MOD |  |  | FAYETTE | 7-227.08 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | VARIOUS 'SLX' CONTINUING PROGRAM PROJECTS (RIDESHARE/MOBILITY, AIR QUALITY PLANNING, TRAFFIC SIGNAL) (LOCAL MATCH) (ALL WORK BY LFUCG) (SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). SEE 7-227.09 | 5 |  | SLX | 2011 | 650000 | 650000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.040 | 2011-01-10 | TIP MOD NO. 13. ADDING PROJECT BACK TO STIP PER ITEM NO. 7-227.00 IN TIP MOD #13. NEW | STPM | 3003271 | FAYETTE | 7-227.08 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | VARIOUS CONTINUING PROGRAMS (RIDESHARE/MOBILITY, AIR QUALITY PLANNING, TRAFFIC SIGNALS, CONGESTION MANAGEMENT, BICYCLE/PEDESTRIAN PLANNING) | 5 | N | SLX | 2013 | 780000 | 780000 | ESTIMATED | N | 2010 | OBLIGATED | 470000 |  | 470000 | 2012 | 4th QUARTER | LEXINGTON-FAYETTE URBAN COUNTY GOVERNMENT
|  |  |  | STPM | 3003267 3003268 3003269 3003270 | FAYETTE | 7-227.09 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | VARIOUS 'SLX' CONTINUING PROGRAM PROJECTS (RIDESHARE/MOBILITY, AIR QUALITY PLANNING, TRAFFIC SIGNAL) (LOCAL MATCH) (ALL WORK BY LFUCG) (SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | 5 | C | SLX | 2011 | 650000 | 650000 | ESTIMATED | N | 2010 | OBLIGATED | 276000 |  | 276000 | 2012 | 3rd QUARTER | LEXINGTON-FAYETTE URBAN COUNTY GOVERNMENT
ADMINISTRATIVE MODIFICATION | 2010.045 | 2011-03-02 | TIP AMENDMENT #1. ADD PROJECT. NEW |  |  | FAYETTE | 7-228 |  | 1 |  |  | SAFETY | BIKE/PED FACIL(O) | BRIGHTON EAST RAIL TRAIL PHASE 2 FROM PLEASANT RIDGE DRIVE TO WALNUT GROVE LANE, LENGTH = 1 MI |  | C | SLX | 2011 | 300000 | 240000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.183 | 2012-04-30 | TIP MOD #25. INCREASE CONSTRUCTION COST TO $400,000 IN SLX FUNDS. MOD | STPM | 3003159 | FAYETTE | 7-228 |  | 1 |  |  | SAFETY | BIKE/PED FACIL(O) | BRIGHTON EAST RAIL TRAIL PHASE 2 FROM PLEASANT RIDGE DRIVE TO WALNUT GROVE LANE, LENGTH = 1 MI |  | C | SLX | 2012 | 400000 | 400000 |  |  |  | OBLIGATED | 701200 |  | 701200 | 2004 | 1st QUARTER | LEXINGTON-FAYETTE URBAN COUNTY GOVERNMENT
[6 empty] | FAYETTE | 7-229.2 |  | 0.3 |  |  | SAFETY | BIKE/PED FACIL(O) | SOUTH ELKHORN TRAIL IN LEXINGTON (PRIORITY SECTION 2); FROM JOSEPH BRYAN WAY THROUGH NS RAILROAD TUNNEL TO WAVELAND HISTORIC SITE (ALL WORK BY LFUCG). (TOTAL COST = $266,250) (SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | 5 | C | SLX | 2011 | 286000 | 286000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.040 | 2011-02-09 | TIP MOD NO. 13. CHANGING FY IN STIP AND DESCRIPTION. MOD |  |  | FAYETTE | 7-229.2 |  | 0.3 |  |  | SAFETY | BIKE/PED FACIL(O) | SOUTH ELKHORN TRAIL FROM JOSEPH BRYAN WAY THROUGH NS RR TUNNEL TO WAVELAND - SECTION 2; LENGTH = 0.3 MI | 5 | C | SLX | 2012 | 286000 | 229000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.045 | 2011-03-02 | TIP AMENDMENT #1. INCREASE C FUNDING TO $286,000 AND FY TO 2012. MOD |  |  | FAYETTE | 7-229.2 |  | 0.3 |  |  | SAFETY | BIKE/PED FACIL(O) | SOUTH ELKHORN TRAIL FROM JOSEPH BRYAN WAY THROUGH NS RR TUNNEL TO WAVELAND - SECTION 2; LENGTH = 0.3 MI | 5 | C | SLX | 2012 | 286000 | 229000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | FAYETTE | 7-229.3 |  | 0.3 |  |  | SAFETY | BIKE/PED FACIL(O) | SOUTH ELKHORN TRAIL(PRIORITY SECTION 3); FROM LOCHDALE TERRACE, EXTENDING NORTHERLY UNDER MAN O' WAR BOULEVARD TO SHILLITO PARK.(LOCAL MATCH)(DESIGN BY LFUCG)(ALL WORK BY LFUCG)(2004BOPC)(SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | 5 | C | SLX | 2011 | 511597 | 511597 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.040 | 2011-02-09 | TIP MOD NO. 13. CHANGING DESCRIPTION AND AMOUNT. MOD |  |  | FAYETTE | 7-229.3 |  | 0.3 |  |  | SAFETY | BIKE/PED FACIL(O) | SOUTH ELKHORN TRAIL FROM LOCHDALE TERRACE, EXTENDING N UNDER MAN O' WAR BLVD TO SHILLITO PARK - SECTION 3; LENGTH=0.3 M. | 5 | C | SLX | 2011 | 531000 | 425000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.045 | 2011-03-02 | TIP AMENDMENT #1. ADD PROJECT. NEW |  |  | FAYETTE | 7-230 |  | 1.5 |  |  | SAFETY | BIKE/PED FACIL(O) | WEST HICKMAN TRAIL PHASE 1B FROM CLEARWATER WAY AT MAN O' WAR BLVD TO VETERANS PARK; LENGTH =1.5 |  | C | SLX | 2014 | 758000 | 758000 |  | N |  |  |  |  | 0
[6 empty] | FAYETTE | 7-231 | CS 3817 |  | 0.504 | 0.591 | RELIABILITY | MATCHED FED FUNDS(O) | ADD BIKE LANE ON ROSE STREET FROM ROSE LANE TO EUCLID. (LFUCG T.I.P.) (LOCAL MATCH)(ALL WORK BY LFUCG) (SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | 3 | R | SLX | 2011 | 34650 | 34650 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.045 | 2011-03-02 | TIP AMENDMENT #1. INCREASE R FUNDING TO 37,000 AND FY TO 2012. MOD |  |  | FAYETTE | 7-231 | CS 3817 |  | 0.504 | 0.591 | RELIABILITY | MATCHED FED FUNDS(O) | ADD BIKE LANE ON ROSE STREET FROM ROSE LANE TO EUCLID. LENGTH = 0.2 MI | 3 | R | SLX | 2012 | 37000 | 30000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | FAYETTE | 7-231 | CS 3817 |  | 0.504 | 0.591 | RELIABILITY | MATCHED FED FUNDS(O) | ADD BIKE LANE ON ROSE STREET FROM ROSE LANE TO EUCLID. (LFUCG T.I.P.) (LOCAL MATCH)(ALL WORK BY LFUCG) (SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | 5 | C | SLX | 2011 | 160160 | 160160 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.045 | 2011-03-02 | TIP AMENDMENT #1. INCREASE C FUNDING TO 267,000 AND FY TO 2012. MOD |  |  | FAYETTE | 7-231 | CS 3817 |  | 0.504 | 0.591 | RELIABILITY | MATCHED FED FUNDS(O) | ADD BIKE LANE ON ROSE STREET FROM ROSE LANE TO EUCLID. LENGTH = 0.2 MI | 3 | C | SLX | 2012 | 267000 | 214000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | FAYETTE | 7-366 | KY 4 | 1.3 | 8.731 | 10.015 | RELIABILITY | PE & ENVIRONMENTAL(O) | WIDEN NEW CIRCLE ROAD IN LEXINGTON FROM GEORGETOWN ROAD TO BOARDWALK AVENUE INCLUDING INTERCHANGE RECONSTRUCTION AT NEWTOWN PIKE. (2002BOPC)(2004BOPP)(PHASE I DESIGN ONLY)(10CCR) | 3 | R | NH | 2011 | 15230000 | 15230000 | ESTIMATED | Y | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.045 | 2011-03-02 | TIP AMENDMENT #1. CHANGE TIP TO MATCH INFO IN STIP. |  |  | FAYETTE | 7-366 | KY 4 | 1.3 | 8.731 | 10.015 | RELIABILITY | PE & ENVIRONMENTAL(O) | WIDEN NEW CIRCLE ROAD IN LEXINGTON FROM GEORGETOWN ROAD TO BOARDWALK AVENUE INCLUDING INTERCHANGE RECONSTRUCTION AT NEWTOWN PIKE. (2002BOPC)(2004BOPP)(PHASE I DESIGN ONLY)(10CCR) | 3 | R | NH | 2011 | 15230000 | 15230000 | ESTIMATED | Y | 2010 |  |  |  | 0
[6 empty] | FAYETTE | 7-366 | KY 4 | 1.3 | 8.731 | 10.015 | RELIABILITY | PE & ENVIRONMENTAL(O) | WIDEN NEW CIRCLE ROAD IN LEXINGTON FROM GEORGETOWN ROAD TO BOARDWALK AVENUE INCLUDING INTERCHANGE RECONSTRUCTION AT NEWTOWN PIKE. (2002BOPC)(2004BOPP)(PHASE I DESIGN ONLY)(10CCR) | 3 | U | NH | 2011 | 5200000 | 5200000 | ESTIMATED | Y | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.045 | 2011-03-02 | TIP AMENDMENT #1. CHANGE TIP TO MATCH INFO IN STIP. |  |  | FAYETTE | 7-366 | KY 4 | 1.3 | 8.731 | 10.015 | RELIABILITY | PE & ENVIRONMENTAL(O) | WIDEN NEW CIRCLE ROAD IN LEXINGTON FROM GEORGETOWN ROAD TO BOARDWALK AVENUE INCLUDING INTERCHANGE RECONSTRUCTION AT NEWTOWN PIKE. (2002BOPC)(2004BOPP)(PHASE I DESIGN ONLY)(10CCR) | 4 | U | NH | 2011 | 5200000 | 5200000 | ESTIMATED | Y |  |  |  |  | 0
[6 empty] | FAYETTE | 7-366 | KY 4 | 1.3 | 8.731 | 10.015 | RELIABILITY | PE & ENVIRONMENTAL(O) | WIDEN NEW CIRCLE ROAD IN LEXINGTON FROM GEORGETOWN ROAD TO BOARDWALK AVENUE INCLUDING INTERCHANGE RECONSTRUCTION AT NEWTOWN PIKE. (2002BOPC)(2004BOPP)(PHASE I DESIGN ONLY)(10CCR) | 3 | C | NH | 2011 | 17650000 | 17650000 | ESTIMATED | Y | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.045 | 2011-03-02 | TIP AMENDMENT #1. CHANGE TIP TO MATCH INFO IN STIP. |  |  | FAYETTE | 7-366 | KY 4 | 1.3 | 8.731 | 10.015 | RELIABILITY | PE & ENVIRONMENTAL(O) | WIDEN NEW CIRCLE ROAD IN LEXINGTON FROM GEORGETOWN ROAD TO BOARDWALK AVENUE INCLUDING INTERCHANGE RECONSTRUCTION AT NEWTOWN PIKE. (2002BOPC)(2004BOPP)(PHASE I DESIGN ONLY)(10CCR) | 5 | C | NH | 2012 | 17650000 | 17650000 | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.051 | 2011-03-08 | TIP MOD #15. ADD PROJECT. NEW | DPR | 0179003 | FAYETTE | 7-408 | [6 empty] | LEXINGTON TRAFFIC MOVEMENT AND REVITALIZATION STUDY PROJECT: PLANNING/DESIGN/CONSTRUCTION COST OF $490,000 OF STP SECTION 129 DISCRETIONARY FUNDING. |  | D | KYD | 2011 | 490000 | 490000 |  |  |  | OBLIGATED | 490000 |  | 490000 | 2011 | 4th QUARTER | LEXINGTON-FAYETTE URBAN COUNTY GOVERNMENT
[6 empty] | FAYETTE | 7-593.04 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | NEWTOWN PIKE EXTENSION FROM WEST MAIN ST. TO SOUTH LIMESTONE STREET IN LEXINGTON. (ADDITIONAL FUNDING FOR DESIGN FOR CLT)(10CCR) | 2 | D | STP | 2012 | 5241000 | 5241000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.047 | 2011-02-28 | TIP MOD #14. DECREASE DESIGN FUNDING AND CHANGE FY. MOD | STP | 0114007 | FAYETTE | 7-593.04 | KY 922 | 2.5 |  |  | RELIABILITY | NEW ROUTE(O) | NEWTOWN PIKE EXTENSION FROM MAIN ST. TO SOUTH LIMESTONE (ADDITIONAL FUNDING FOR CLT)LENGTH =2.5 MI | 2 | D | STP | 2011 | 2584000 | 2584000 | ESTIMATED | N |  | OBLIGATED | 2583897 |  | 2583897 | 2011 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.047 | 2011-02-28 | TIP MOD #14. ADD PROJECT. NEW | HPP | 0114007 | FAYETTE | 7-593.05 | KY 922 | 2.5 |  |  | RELIABILITY | NEW ROUTE(O) | NEWTOWN PIKE EXTENSION FROM MAIN ST. TO SOUTH LIMESTONE (ADDITIONAL FUNDING FOR CLT)LENGTH =2.5 MI |  | D | HPP | 2011 | 2657000 | 2657000 |  | N |  | OBLIGATED | 2657103 |  | 2657103 | 2011 | 3rd QUARTER | N/A
[6 empty] | FAYETTE | 7-593.1 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | NEWTOWN PIKE EXTENSION - PRIORITY 2: REDEVELOPMENT OF SOUTHEND PARK NEIGHBORHOOD (MITIGATION AREA). (PHASE I) (2005HPP-KY114) | 4 | U | HPP | 2011 | 520000 | 520000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.047 | 2011-02-28 | TIP MOD #14. CHANGE FUNDING TYPE TO STP. MOD |  |  | FAYETTE | 7-593.1 | KY 922 |  |  |  | RELIABILITY | NEW ROUTE(O) | NEWTOWN PIKE EXTENSION - PRIORITY 2: REDEVELOPMENT OF SOUTHEND PARK NEIGHBORHOOD (MITIGATION AREA). (PHASE I) (2005HPP-KY114) | 4 | U | STP | 2011 | 520000 | 520000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | FAYETTE | 7-593.1 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | NEWTOWN PIKE EXTENSION - PRIORITY 2: REDEVELOPMENT OF SOUTHEND PARK NEIGHBORHOOD (MITIGATION AREA). (PHASE I) (2005HPP-KY114) | 5 | C | HPP | 2011 | 2137000 | 2137000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.047 | 2011-02-28 | TIP MOD #14. CHANGE FUNDING TYPE TO STP. MOD |  |  | FAYETTE | 7-593.1 | KY 922 |  |  |  | RELIABILITY | NEW ROUTE(O) | NEWTOWN PIKE EXTENSION - PRIORITY 2: REDEVELOPMENT OF SOUTHEND PARK NEIGHBORHOOD (MITIGATION AREA). (PHASE I) (2005HPP-KY114) | 4 | C | STP | 2011 | 2137000 | 2137000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | FAYETTE | 7-593.11 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | NEWTOWN PIKE EXTENSION - PRIORITY 2A: CONSTRUCT A SOUND BARRIER WALL ALONG THE RAILROAD YARD FROM VERSAILLES ROAD TO BROADWAY. (2008BOPC)(10CCR) | 5 | C | STP | 2011 | 2436500 | 2436500 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.045 | 2011-03-02 | LEXINGTON MPO TIP AMENDMENT #1 CHANGED TIP TO MATCH THE STIP INFO. |  |  | FAYETTE | 7-593.11 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | NEWTOWN PIKE EXTENSION - PRIORITY 2A: CONSTRUCT A SOUND BARRIER WALL ALONG THE RAILROAD YARD FROM VERSAILLES ROAD TO BROADWAY. (2008BOPC)(10CCR) | 5 | C | STP | 2011 | 2436500 | 2436500 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.130 | 2011-09-16 | TIP MOD #21. INCREASE FUNDING AMOUNT. MOD | STPM | 3003250 | FAYETTE | 7-593.11 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | NEWTOWN PIKE EXTENSION - PRIORITY 2A: CONSTRUCT A SOUND BARRIER WALL ALONG THE RAILROAD YARD FROM VERSAILLES ROAD TO BROADWAY. |  | C | SLX | 2011 | 2500000 | 2500000 |  | N |  | OBLIGATED | 2436500 |  | 2436500 | 2011 | 4th QUARTER | N/A
[6 empty] | FAYETTE | 7-593.12 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | NEWTOWN PIKE EXTENSION - PRIORITY 2: REDEVELOPMENT OF SOUTHEND PARK NEIGHBORHOOD (MITIGATION AREA). (PHASE I) (2005HPP-KY114)(10CCR) | 5 | C | STP | 2012 | 6106000 | 6106000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.045 | 2011-03-02 | LEXINGTON MPO TIP AMENDMENT #1 CHANGED TIP TO MATCH THE STIP INFO. |  |  | FAYETTE | 7-593.12 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | NEWTOWN PIKE EXTENSION - PRIORITY 2: REDEVELOPMENT OF SOUTHEND PARK NEIGHBORHOOD (MITIGATION AREA). (PHASE I) (2005HPP-KY114)(10CCR) | 5 | C | STP | 2012 | 6106000 | 6106000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.206 | 2012-06-18 | TIP MOD #26. ADD TO STIP.NEW |  |  | FAYETTE | 7-593.13 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | NEWTOWN PIKE EXTENSION - PRIORITY 2: REDEVELOPMENT OF SOUTHEND PARK NEIGHBORHOOD (MITIGATION AREA). (PHASE I BOX CULVERT FIRST SECTION).(2005HPP-KY114) |  | U | STP | 2012 | 110000 | 110000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.206 | 2012-06-18 | TIP MOD #26. ADD TO STIP.NEW |  |  | FAYETTE | 7-593.13 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | NEWTOWN PIKE EXTENSION - PRIORITY 2: REDEVELOPMENT OF SOUTHEND PARK NEIGHBORHOOD (MITIGATION AREA). (PHASE I BOX CULVERT FIRST SECTION).(2005HPP-KY114) |  | C | STP | 2012 | 1750000 | 1750000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.206 | 2012-06-18 | TIP MOD #26. ADD TO STIP.NEW |  |  | FAYETTE | 7-593.14 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | NEWTOWN PIKE EXTENSION - PRIORITY 2: REDEVELOPMENT OF SOUTHEND PARK NEIGHBORHOOD (MITIGATION AREA). (PHASE I SITE GRADING AND UTILITIES FOR THE NATHANIEL MISSION) (2005HPP-KY114) |  | C | STP | 2012 | 120000 | 120000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.175 | 2012-03-19 | TIP MOD #24. ADD TO STIP. | HSIP | 3003266 | FAYETTE | 7-919 | KY 1927 |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | TODDS ROAD: CULVERT EXTENSIONS, PLACE EMBANKMENT AND BOX CULVERT AT JONES CREEK EAST OF CLEVELAND RD (KY 1973) |  | C | SAF | 2012 | 185000 | 185000 |  |  |  | OBLIGATED | 187000 |  | 187000 | 2012 | 2nd QUARTER | N/A
[6 empty] | FAYETTE | 7-1111 | CR 1122 | 0.1 | 1.729 | 1.739 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER BOONE CREEK (C10) @ THE CLARK COUNTY LINE. (SR=9.2)(ALL WORK BY LFUCG): (034C00010N) | 5 | C | BRX | 2011 | 810000 | 810000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.045 | 2011-03-02 | LEXINGTON MPO TIP AMENDMENT #1 CHANGED TIP TO MATCH THE STIP INFO. |  |  | FAYETTE | 7-1111 | CR 1122 | 0.1 | 1.729 | 1.739 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER BOONE CREEK (C10) @ THE CLARK COUNTY LINE. (SR=9.2)(ALL WORK BY LFUCG): (034C00010N) | 5 | C | BRX | 2011 | 810000 | 810000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.014 | 2010-11-05 | TIP MOD #12. BREAKOUT FROM 99-65.07 TO ADD $645,000 IN IM FUNDS TO REPLACE NEOPRENE COMPRESSION JOINTS. NEW |  |  | FAYETTE | 7-2031 | I-75 |  |  |  | RELIABILITY | BRIDGE REHAB(P) | I-75 CLAYS FERRY BRIDGE IN FAYETTE COUNTY, REPLACE NEOPRENE COMPRESSION JOINTS. |  | C | IM | 2011 | 645000 | 645000 |  | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.040 | 2011-02-09 | TIP MOD #13. INCREASE IM FUNDING FROM 645,000 TO 1,130,000 FOR THE C PHASE. MOD | IM | 0754062 | FAYETTE | 7-2031 | I-75 |  |  |  | RELIABILITY | BRIDGE REHAB(P) | I-75 CLAYS FERRY BRIDGE IN FAYETTE COUNTY, REPLACE NEOPRENE COMPRESSION JOINTS. |  | C | IM | 2011 | 1130000 | 1130000 |  | N |  | OBLIGATED | 1130030 |  | 1130030 | 2011 | 2nd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.041 | 2011-02-09 | TIP MOD #10 DATED SEPT 2, 2010 ADDED PROJECT TO TIP. NOW ADDING TO STIP. NEW |  |  | FAYETTE | 7-3107 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | LEXINGTON-FAYETTE LEGACY TRAIL, KY: AMENITIES AND ENHANCEMENTS |  | C | TCSP | 2011 | 625000 | 500000 | [6 empty] | 0
[6 empty] | FAYETTE | 7-8507 | CS 2548 |  |  |  | RELIABILITY | NEW ROUTE(O) | COMPLETE CONSTRUCTION ON POLO CLUB BOULEVARD AT DEERHAVEN LANE AND TODDS ROAD. (08CCN)(FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | 2 | D | SLX | 2011 | 165000 | 165000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.045 | 2011-03-02 | TIP AMENDMENT #1. CHANGE D PHASE TO FY 2011. MOD | STPM | 3003265 | FAYETTE | 7-8507 | CS 2548 |  |  |  | RELIABILITY | NEW ROUTE(O) | COMPLETE CONSTRUCTION ON POLO CLUB BOULEVARD AT DEERHAVEN LANE AND TODDS ROAD. LENGTH=0.2 MI | 2 | D | SLX | 2011 | 165000 | 132000 | ESTIMATED | N | 2010 | OBLIGATED | 152000 |  | 152000 | 2011 | 4th QUARTER | LFUCG
[6 empty] | FAYETTE | 7-8507 | CS 2548 |  |  |  | RELIABILITY | NEW ROUTE(O) | COMPLETE CONSTRUCTION ON POLO CLUB BOULEVARD AT DEERHAVEN LANE AND TODDS ROAD. (08CCN)(FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | 3 | R | SLX | 2011 | 36383 | 36383 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.051 | 2011-03-08 | TIP MOD #15. ADD PROJECT. NEW |  |  | FAYETTE | [7 empty] | TATES CREEK ROAD SIGNAL UPGRADES TO REPLACE INADEQUATE FACILITIES, UPGRADE SIGNAL FACES AND TO ACCOMMODATE UPGRADED STREET CROSSWALKS |  | C | SLX | 2011 | 250000 | 250000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.091 | 2011-06-23 | TIP MOD #18. ADD PROJECT. NEW | HSIP | 0272111 | FAYETTE |  | US 27 |  | 4.674 | 5.769 |  |  | DEVELOP, IMPLEMENT, AND STUDY THE USE OF ADAPTIVE SIGNAL CONTROL ON US 27 (SOUTH LIMESTONE) FROM MP 4.674 (COOPER/WALLER) TO MP 5.769 (AVENUE OF CHAMPIONS/WINSLOW) |  | N | HES | 2011 | 201000 | 201000 |  |  |  | OBLIGATED | 200675 |  | 200675 | 2011 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.117 | 2011-09-06 | TIP MOD #20. ADD PROJECT. NEW | SB | KY10003 | FAYETTE | [7 empty] | OLD FRANKFORT PIKE CORRIDOR MANAGEMENT PLAN. |  | N | NAT SC BYW | 2011 | 65000 | 52000 |  |  |  | OBLIGATED | 52000 |  | 52000 | 2011 | 4th QUARTER | LFUCG
ADMINISTRATIVE MODIFICATION | 2010.130 | 2011-09-16 | TIP MOD #21. ADD PROJECT. NEW |  |  | FAYETTE |  | CS 4524 | [5 empty] | WIDEN MAN O' WAR BOULEVARD AT PINK PIGEON PARKWAY TO ALLOW FOR DUAL LEFT TURNS. |  | D | SLX | 2013 | 39000 | 31000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.130 | 2011-09-16 | TIP MOD #21. ADD PROJECT. NEW |  |  | FAYETTE |  | CS 4524 | [5 empty] | WIDEN MAN O' WAR BOULEVARD AT PINK PIGEON PARKWAY TO ALLOW FOR DUAL LEFT TURNS. |  | C | SLX | 2013 | 456000 | 365000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.130 | 2011-09-16 | TIP MOD #21. ADD PROJECT. NEW |  |  | FAYETTE |  | CS 4524 | [5 empty] | MAN O' WAR BOULEVARD AT ALUMNI DRIVE TURN LANE IMPROVEMENTS |  | D | SLX | 2013 | 112000 | 90000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.130 | 2011-09-16 | TIP MOD #21. ADD PROJECT. NEW |  |  | FAYETTE |  | CS 4524 | [5 empty] | MAN O' WAR BOULEVARD AT ALUMNI DRIVE TURN LANE IMPROVEMENTS |  | R/U | SLX | 2013 | 18000 | 14000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.130 | 2011-09-16 | TIP MOD #21. ADD PROJECT. NEW |  |  | FAYETTE |  | CS 4524 | [5 empty] | MAN O' WAR BOULEVARD AT ALUMNI DRIVE TURN LANE IMPROVEMENTS |  | C | SLX | 2013 | 725000 | 580000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.097 | 2011-07-11 | ADD PROJECT. AWARDED FY 2010 NHCB DISCRETIONARY FUNDING. NEW |  |  | FLEMING | 9-3021 | KY 158 |  |  |  | RELIABILITY | BRIDGE REHAB(P) | RESTORATION OF RINGO'S MILL COVERED BRIDGE LOCATED ON KY 158 AT RAWLINGS ROAD APPROX 7.274 MILES EAST OF HILLSBORO |  | C | KYD | 2011 | 406400 | 406400 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.115 | 2011-09-01 | ADD PROJECT. AWARDED FY 2011 NHCB DISCRETIONARY FUNDING. NEW |  |  | FLEMING | 9-3021 |  |  |  |  | RELIABILITY | BRIDGE REHAB(P) | RESTORATION OF RINGO'S MILL COVERED BRIDGE |  | C | KYD | 2012 | 101600 | 101600 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.214 | 2012-07-05 | ADD PROJECT TO STIP. NEW |  |  | FLOYD | 12-191 | US 23 |  |  |  | SAFETY | SAFETY(P) | MITIGATE SAFETY HAZARDS DUE TO SPEED, POOR ACCESS CONTROL BETWEEN KY 80 AND INTERSECTION WITH KY 3384.(12CCR) |  | D | NH | 2012 | 700000 | 700000 | [6 empty] | 0
|  |  |  | BRZ | 1203345 | FLOYD | 12-1071 | KY 1428 | 0.1 | 8.694 | 8.716 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER COW CREEK (B03) 0.02 MI S JCT. KY-194. (SR=31.5): (036B00003N) | 5 | C | BRX | 2011 | 1520000 | 1520000 | ESTIMATED | N |  | OBLIGATED | 1680000 |  | 1680000 | 2012 | 2nd QUARTER | N/A
|  |  |  | BRZ | 1203344 | FLOYD | 12-1074 | CR 1962 | 0.1 | 0.039 | 0.079 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER RIGHT FORK BEAVER CREEK (C59) 300' WEST JCT. KY-7. (SR=37.2)(PROJECT FUNDING CONTINGENT UPON BRIDGE POSTING COMPLIANCE): (036C00059N) | 5 | C | BRZ | 2012 | 900000 | 900000 | ESTIMATED | N |  | OBLIGATED | 480000 |  | 480000 | 2012 | 2nd QUARTER | N/A
[6 empty] | FLOYD | 12-1075 | KY 194 | 0.1 | 12.105 | 12.155 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-194 OVER BRUSHY CREEK (B65) AT THE FLOYD/PIKE COUNTY LINE. (SR=46.5): (036B00065N) | 5 | C | BRZ | 2011 | 730000 | 730000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | FLOYD | 12-1084 | KY 466 | 0.1 | 3.575 | 3.583 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-466 OVER LEFT FORK BEAVER CREEK (B30). (SR=37.5): (036B00030N) | 3 | R | BRX | 2011 | 280000 | 280000 | ESTIMATED | N | 2010 |  |  |  | 0
|  |  |  | BRZ | 1203350 | FLOYD | 12-1084 | KY 466 | 0.1 | 3.575 | 3.583 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-466 OVER LEFT FORK BEAVER CREEK (B30). (SR=37.5): (036B00030N) | 4 | U | BRX | 2011 | 280000 | 280000 | ESTIMATED | N | 2010 | OBLIGATED | 270000 |  | 270000 | 2012 | 4th QUARTER | N/A
[6 empty] | FLOYD | 12-1084 | KY 466 | 0.1 | 3.575 | 3.583 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-466 OVER LEFT FORK BEAVER CREEK (B30). (SR=37.5): (036B00030N) | 5 | C | BRX | 2011 | 1170000 | 1170000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | FLOYD | 12-1085 | KY 777 | 0.1 | 0.186 | 0.205 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-777 OVER RIGHT FORK BEAVER CREEK (B76). (SR=3.0): (036B00076N) | 3 | R | BRX | 2011 | 280000 | 280000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | FLOYD | 12-1085 | KY 777 | 0.1 | 0.186 | 0.205 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-777 OVER RIGHT FORK BEAVER CREEK (B76). (SR=3.0): (036B00076N) | 4 | U | BRX | 2011 | 330000 | 330000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | FLOYD | 12-1085 | KY 777 | 0.1 | 0.186 | 0.205 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-777 OVER RIGHT FORK BEAVER CREEK (B76). (SR=3.0): (036B00076N) | 5 | C | BRX | 2011 | 1290000 | 1290000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | FLOYD | 12-1093 | CR 1350 | 0.1 | 0.064 | 0.07 | SAFETY | BRIDGE REPLACEMENT(P) | MEADE BRANCH ROAD; REPLACE BRIDGE AND APPROACHES OVER ABBOTT CREEK (C31) 0.06 MILE SOUTH OF KY-1427. (SR=3.0): (036C00031N) | 2 | D | BRZ | 2011 | 225000 | 225000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | FLOYD | 12-1093 | CR 1350 | 0.1 | 0.064 | 0.07 | RELIABILITY | BRIDGE REPLACEMENT(P) | MEADE BRANCH ROAD; REPLACE BRIDGE AND APPROACHES OVER ABBOTT CREEK (C31) 0.06 MILE SOUTH OF KY-1427. (SR=3.0) | 3 | R | BRZ | 2014 | 175000 | 175000 | ESTIMATED | [5 empty] | 0
[6 empty] | FLOYD | 12-1093 | CR 1350 | 0.1 | 0.064 | 0.07 | RELIABILITY | BRIDGE REPLACEMENT(P) | MEADE BRANCH ROAD; REPLACE BRIDGE AND APPROACHES OVER ABBOTT CREEK (C31) 0.06 MILE SOUTH OF KY-1427. (SR=3.0) | 4 | U | BRZ | 2014 | 200000 | 200000 | ESTIMATED | [5 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.177 | 2012-03-26 | ADD PROJECT TO STIP. NEW |  |  | FLOYD |  | KY 1426 |  |  |  | SAFETY | SAFETY-RR PROTECTN(P) | ADD GATES TO EXISTING FLASHING LIGHTS AND BELL SYSTEM AT CSX RAILROAD CROSSING ON KY 1426 AT BANNER. (DOT# 227203K) |  | U | SAF | 2012 | 225000 | 225000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.177 | 2012-03-26 | ADD PROJECT TO STIP. NEW | RHPD | 1201064 | FLOYD | 99-352.07 | KY 1426 | 0.001 | 14.051 | 14.052 | SAFETY | SAFETY-RR PROTECTN(P) | ADD GATES TO EXISTING FLASHING LIGHTS AND BELL SYSTEM AT CSX RAILROAD CROSSING ON KY 1426 AT BANNER. (DOT# 227203K) |  | C | SAF | 2012 | 15000 | 15000 |  |  |  | OBLIGATED | 217500 |  | 217500 | 2012 | 3rd QUARTER | N/A
[6 empty] | FRANKLIN | 5-466 | KY 2919 |  | 0.001 | 0.002 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACEMENT OF BRIDGE ON INDIAN GAP ROAD (KY-2919) OVER CAMP PLEASANT BRANCH USING SELF CONSOLIDATING CONCRETE AND PRECAST BRIDGE COMPONENTS (FY09 IBRD DISCRETIONARY PROJECT). (037B00082N) | 5 | C | KYD | 2011 | 255000 | 255000 | ESTIMATED |  | 2010 |  |  |  | 0
[6 empty] | FRANKLIN | 5-963 | KY 151 | 0.4 | 1.8 | 2.2 | SAFETY | SAFETY-HAZARD ELIM(P) | CORRECT SIGHT DISTANCE ISSUES ON KY-151 S OF I-64, IMPROVE SAFETY AND OPERATION OF I-64/KY-151 I-CHNG AND WIDEN KY-151 TO ACCOMODATE LEFT TURN LANES. (2000BOP) | 3 | R | HES | 2011 | 290000 | 290000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | FRANKLIN | 5-963 | KY 151 | 0.4 | 1.8 | 2.2 | SAFETY | SAFETY-HAZARD ELIM(P) | CORRECT SIGHT DISTANCE ISSUES ON KY-151 S OF I-64, IMPROVE SAFETY AND OPERATION OF I-64/KY-151 I-CHNG AND WIDEN KY-151 TO ACCOMODATE LEFT TURN LANES. (2000BOP) | 4 | U | HES | 2011 | 70000 | 70000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | FRANKLIN | 5-963 | KY 151 | 0.4 | 1.8 | 2.2 | SAFETY | SAFETY-HAZARD ELIM(P) | CORRECT SIGHT DISTANCE ISSUES ON KY-151 S OF I-64, IMPROVE SAFETY AND OPERATION OF I-64/KY-151 I-CHNG AND WIDEN KY-151 TO ACCOMODATE LEFT TURN LANES. (2000BOP) | 5 | C | HES | 2011 | 1250000 | 1250000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.116 | 2011-09-06 | ADD PROJECT. NEW | BRO | 7353001 | FRANKLIN | 5-1051.11 | US 60 |  |  |  | RELIABILITY | BRIDGE PAINTING(P) | CLEAN AND PAINT, ALONG WITH BRIDGE DECK REPAIRS TO SINGING BRIDGE OVER KENTUCKY RIVER ON BRIDGE STREET (B65)(SR=14.6). |  | C | BRO | 2011 | 1200000 | 1200000 |  |  |  | OBLIGATED | 1459442.69 |  | 1459442.69 | 2011 | 4th QUARTER | N/A
|  |  |  | BRO | 4201071 | FRANKLIN | 5-1057 | US 421 | 0.1 | 13.04 | 13.14 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON US-421 (MP 13.09) OVER FLAT CREEK; 2.0 MI NORTH OF JCT KY 12; (STRUCTURALLY DEFICIENT, SR=46.8) 037B00023N | 2 | D | BRO | 2012 | 170000 | 170000 | ESTIMATED | N |  | OBLIGATED | 240000 |  | 240000 | 2012 | 1st QUARTER | N/A
|  |  |  | BRO | 4201072 | FRANKLIN | 5-1058 | US 421 | 0.1 | 14.009 | 14.109 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON US-421 (MP 14.059) OVER HUDSON CREEK; 2.8 MI NORTH OF JCT KY 12; (STRUCTURALLY DEFICIENT, SR=48.9) 037B00024N | 2 | D | BRO | 2012 | 120000 | 120000 | ESTIMATED | N |  | OBLIGATED | 200000 |  | 200000 | 2012 | 1st QUARTER | N/A
|  |  |  | BRO | 4201073 | FRANKLIN | 5-1059 | US 421 | 0.1 | 15.041 | 15.141 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON US-421 (MP 15.091) OVER LITTLE FLAT CREEK; 3.8 MI NORTH OF JCT KY 12; (STRUCTURALLY DEFICIENT, SR=48.7) 037B00025N | 2 | D | BRO | 2012 | 140000 | 140000 | ESTIMATED | N |  | OBLIGATED | 200000 |  | 200000 | 2012 | 1st QUARTER | N/A
[6 empty] | FRANKLIN | 5-2035.7 | I 64 | 5.42 | 47.7 | 53.75 | RELIABILITY | PAVEMENT REHAB-INT(P) | PAVEMENT REHAB AND BRIDGE WIDENING ON I-64 FROM MP 47.70 TO MP 53.75. (2004BOPC)(DESIGN FUNDED UNDER 5-2035.40) | 3 | R | IM | 2012 | 120000 | 120000 | ESTIMATED | Y |  |  |  |  | 0
[6 empty] | FRANKLIN | 5-2035.7 | I 64 | 5.42 | 47.7 | 53.75 | RELIABILITY | PAVEMENT REHAB-INT(P) | PAVEMENT REHAB AND BRIDGE WIDENING ON I-64 FROM MP 47.70 TO MP 53.75. (2004BOPC)(DESIGN FUNDED UNDER 5-2035.40) | 4 | U | IM | 2012 | 110000 | 110000 | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.066 | 2011-04-18 | ADD PROJECT TO STIP. BREAKOUT FROM 99-911.00. NEW | HSIP | 0644085 | FRANKLIN WOODFORD | 5-2806 | I 64 |  | 57 | 66 | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALL CABLE MEDIAN BARRIER ON I-64 FROM HANLEY LANE UNDERPASS TO THE EAST OF THE KY 341/US 421/US 62 INTERCHANGE AT MIDWAY.(TO BE LET WITH 5-2805 AND 6-2801) |  | C | SAF | 2011 | 1224000 | 1224000 |  | Y |  | OBLIGATED | 1099230 |  | 1099230 | 2011 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.215 | 2012-07-10 | ADD PROJECT TO STIP. NEW |  |  | FULTON | 1-1144 | KY 1909 | 0.04 | 0.712 | 0.752 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 1909 OVER LITTLE BAYOU DE CHIEN CREEK S OF INTERSECTION WITH KY 2149 (SR 28.7) 038B00074N |  | D | BRO | 2012 | 225000 | 225000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.197 | 2012-05-30 | ADD PROJECT TO STIP. NEW |  |  | FULTON | 1-1148 | CR 1011 | 0.04 | 0.247 | 0.287 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON HOLLAND LN (CR 1011) OVER BRANCH OF HARRIS FORK CREEK 0.26 MILE E OF KENTUCKY AVE (KY 307)(SR 31.9)038C00001N(12CCR) |  | D | BRZ | 2012 | 220000 | 220000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.171 | 2012-03-13 | ADD PROJECT TO STIP. BREAKOUT FROM 99-911.01. NEW | HSIP | 0713053 | GALLATIN | 6-2801 | I-71 | 1.9 | 61.6 | 63.5 | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALL HTC BARRIER ALONG I-71 IN GALLATIN COUNTY MP 61.6 SOUTH OF US 127 TO MP 63.5 SOUTH OF KY 3002. (2011 BOP) |  | C | SAF | 2012 | 413500 | 413500 |  |  |  | OBLIGATED | 413600 |  | 413600 | 2012 | 2nd QUARTER | N/A
[6 empty] | GARRARD | 7-196.01 | US 27 | 14.2 | 0 | 10.331 | RELIABILITY | RELOCATION(O) | WIDEN US 27 FROM KY 34 TO US 150 BYPASS, GARRARD COUNTY AND LINCOLN COUNTY. (2005HPP-KY115)(2006BOPP) | 2 | D | HPP | 2011 | 1439839 | 1439839 | ESTIMATED | Y | 2010 |  |  |  | 0
[6 empty] | GARRARD | 7-201.01 | KY 52 | 4.5 | 13.28 | 16.624 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT KY-52 FROM KY-954 IN GARRARD COUNTY TO WALLACE MILL ROAD IN MADISON COUNTY. (00CCR)(02CCR)(06CCR)(2004BOPC)(08CCR)(10CCR) | 3 | R | STP | 2011 | 4410000 | 4410000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.145 | 2011-11-15 | INCREASE FUNDING AMOUNT FOR R PHASE. MOD | STP | 5283002 | GARRARD/ MADISON | 7-201.01 | KY 52 | 4.5 | 13.28 | 16.624 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT KY-52 FROM KY-954 IN GARRARD COUNTY TO WALLACE MILL ROAD IN MADISON COUNTY. | 3 | R | STP | 2012 | 7500000 | 7500000 | ESTIMATED | N | 2010 | OBLIGATED | 7500000 |  | 7500000 | 2012 | 1st QUARTER | N/A
|  |  |  | STP | 5283001 | GARRARD | 7-201.01 | KY 52 | 4.5 | 13.28 | 16.624 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT KY-52 FROM KY-954 IN GARRARD COUNTY TO WALLACE MILL ROAD IN MADISON COUNTY. (00CCR)(02CCR)(06CCR)(2004BOPC)(08CCR)(10CCR) | 4 | U | STP | 2011 | 6530000 | 6530000 | ESTIMATED | N |  | OBLIGATED | 6530000 |  | 6530000 | 2012 | 1st QUARTER | N/A
[6 empty] | GARRARD | 7-201.01 | KY 52 | 4.5 | 13.28 | 16.624 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT KY-52 FROM KY-954 IN GARRARD COUNTY TO WALLACE MILL ROAD IN MADISON COUNTY. (00CCR)(02CCR)(06CCR)(2004BOPC)(08CCR)(10CCR) | 5 | C | STP | 2013 | 14850000 | 14850000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | GARRARD | 7-1120 | KY 1972 | 0.1 | 0.613 | 0.713 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-1972 (MP 0.663) OVER BR OF TURKEY CREEK; .50 MI EAST OF JCT KY 39; (STRUCTURALLY DEFICIENT, SR=19.4) 040B00023N | 2 | D | BRX | 2012 | 120000 | 120000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.076 | 2011-05-09 | INCREASE THE D PHASE FUNDING AMOUNT. MOD | BRZ | 0703302 | GARRARD | 7-1120 | KY 1972 | 0.1 | 0.613 | 0.713 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-1972 (MP 0.663) OVER BR OF TURKEY CREEK; .50 MI EAST OF JCT KY 39; (STRUCTURALLY DEFICIENT, SR=19.4) 040B00023N | 2 | D | BRZ | 2012 | 230000 | 230000 | ESTIMATED | N |  | OBLIGATED | 230000 |  | 230000 | 2011 | 3rd QUARTER | N/A
|  |  |  | BRZ | 0703308 | GARRARD | 7-1122 | KY 563 | 0.1 | 3.84 | 3.94 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-563 (MP 3.89) OVER SUGAR CREEK; E-@ JCT KY 39; (STRUCTURALLY DEFICIENT, SR=21.7) 040B00034N | 2 | D | BRX | 2012 | 140000 | 140000 | ESTIMATED | N |  | OBLIGATED | 305000 |  | 305000 | 2012 | 3rd Quarter | N/A
ADMINISTRATIVE MODIFICATION | 2010.161 | 2012-01-31 | ADD PROJECT TO STIP. NEW |  |  | GRANT | 6-910 | KY 22 |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALL SIGNS, GUARDRAIL, FRICTION TREATMENT, SHOULDERS, AND REMOVE TREES AND BRUSH ON KY-22 AT CLARKS CREEK BRIDGE AND BATON ROUGE ROAD INTERSECTION. |  | C | SAF | 2012 | 44000 | 44000 | [6 empty] | 0
|  |  |  | BRZ | 0603216 | GRANT | 6-1059 | CS 4009 | 0.1 | 0.037 | 0.063 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON STRINGTOWN ROAD IN CORINTH OVER NORFOLK SOUTHERN RAILROAD (C11) 0.1 MILE EAST JCT. US-25. (SR=32.9)(08CCR): (041C00011N) | 5 | C | BRZ | 2011 | 2110000 | 2110000 | ESTIMATED | N | 2010 | OBLIGATED | 1276800 |  | 1276800 | 2012 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.191 | 2012-05-16 | ADD PROJECT TO STIP. NEW |  |  | GRANT | 6-8714 | CR 1138 | 0.05 | 0.28 | 0.33 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON SOUTH END OF BLANCHET ROAD 0.3 MILES NORTHEAST OF US 25.(12CCN) |  | D | BRO | 2012 | 400000 | 400000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.191 | 2012-05-16 | ADD PROJECT TO STIP. NEW |  |  | GRANT | 6-8715 | CR 1138 | 0.07 | 1.95 | 2.02 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON NORTH END OF BLANCHET ROAD 0.2 MILES SOUTHEAST OF THE JUNCTION WITH US 25.(12CCN) |  | D | BRO | 2012 | 400000 | 400000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.191 | 2012-05-16 | ADD PROJECT TO STIP. NEW |  |  | GRANT | 6-8716 | CR 1142 | 0.05 | 0.02 | 0.07 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON NORTH END OF DELANEY ROAD 0.1 MILE NORTH OF THE JUNCTION WITH US 25.(12CCN) |  | D | BRO | 2012 | 400000 | 400000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.197 | 2012-05-30 | ADD PROJECT TO STIP. NEW |  |  | GRAVES | 1-193 | JC 9003 | 1 | 20.9 | 21.9 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT JULIAN CARROLL PKWY INTERSECTION W/THE MAYFIELD BYPASS TO PROVIDE SUPERIOR THROUGH MOVEMENT TO THE PARKWAY. (I-69 CORRIDOR IMPROVEMENT)(12CCR) |  | D | NH | 2012 | 2000000 | 2000000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.064 | 2011-04-12 | ADD PROJECT TO STIP. BREAKOUT FROM 99-354.06. NEW | HSIP | 9010066 | GRAVES | 1-901 | KY 994 | 0.092 | 3.808 | 3.9 | SAFETY | SAFETY-HAZARD ELIM(P) | RECONSTRUCT KY 994 AT DUNAWAY LANE TO IMPROVE SIGHT DISTANCE. |  | U | SAF | 2011 | 25000 | 25000 |  |  |  | OBLIGATED | 8000 |  | 8000 | 2011 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.035 | 2011-01-28 | ADD PROJECT. BREAKOUT FROM 99-354.06. NEW | HSIP | 9010041 | GRAVES | 1-901 | KY 994 | 0.092 | 3.808 | 3.9 | SAFETY | SAFETY-HAZARD ELIM(P) | RECONSTRUCT KY 994 AT DUNAWAY LANE TO IMPROVE SIGHT DISTANCE |  | C | SAF | 2011 | 251000 | 251000 |  |  |  | OBLIGATED | 226000 |  | 226000 | 2011 | 3rd QUARTER | N/A
|  |  | ADDED D PHASE TO STIP. R, U, C PHASES ALREADY IN STIP (PER SIGNED PR-1) NEW | BRZ | 0103271 | GRAVES | 1-1041 | CR 1430 | 0.1 | 0.725 | 0.759 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER P&L RAILWAY (C179) 0.2MI E OF JCT. CR-5485. (SR=36.8): (042C00179N) | 3 | D | BRZ | 2011 | 330000 | 330000 | ESTIMATED | N | 2010 | OBLIGATED | 330000 |  | 330000 | 2005 | 1st QUARTER | N/A
|  |  |  | BRZ | 0103293 | GRAVES | 1-1041 | CR 1430 | 0.1 | 0.725 | 0.759 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER P&L RAILWAY (C179) 0.2MI E OF JCT. CR-5485. (SR=36.8): (042C00179N) | 3 | R | BRZ | 2011 | 320000 | 320000 | ESTIMATED | N | 2010 | OBLIGATED | 320000 |  | 320000 | 2011 | 3rd QUARTER | N/A
|  |  |  | BRZ | 0103304 | GRAVES | 1-1041 | CR 1430 | 0.1 | 0.725 | 0.759 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER P&L RAILWAY (C179) 0.2MI E OF JCT. CR-5485. (SR=36.8): (042C00179N) | 4 | U | BRZ | 2011 | 190000 | 190000 | ESTIMATED | N | 2010 | OBLIGATED | 175000 |  | 175000 | 2012 | 3rd QUARTER | N/A
|  |  |  | BRZ | 0103303 | GRAVES | 1-1041 | CR 1430 | 0.1 | 0.725 | 0.759 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER P&L RAILWAY (C179) 0.2MI E OF JCT. CR-5485. (SR=36.8): (042C00179N) | 5 | C | BRZ | 2012 | 1690000 | 1690000 | ESTIMATED | N |  | OBLIGATED | 1171200 |  | 1171200 | 2012 | 3rd QUARTER | N/A
[6 empty] | GRAVES | 1-1056 | KY 97 | 0.1 | 8.111 | 8.118 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-97 OVER LEACH CREEK (B52) 0.13 MILE NORTH OF FRANKS ROAD. (SR=18.8): (042B00052N) | 3 | R | BRX | 2012 | 150000 | 150000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | GRAVES | 1-1056 | KY 97 | 0.1 | 8.111 | 8.118 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-97 OVER LEACH CREEK (B52) 0.13 MILE NORTH OF FRANKS ROAD. (SR=18.8): (042B00052N) | 4 | U | BRX | 2012 | 150000 | 150000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | GRAVES | 1-1056 | KY 97 | 0.1 | 8.111 | 8.118 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-97 OVER LEACH CREEK (B52) 0.13 MILE NORTH OF FRANKS ROAD. (SR=18.8) | 5 | C | BRX | 2013 | 600000 | 600000 | ESTIMATED | [5 empty] | 0
[6 empty] | GRAVES | 1-1058 | KY 945 | 0.1 | 5.013 | 5.035 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-945 OVER WILSONS CREEK (B187) 0.13 MILE SOUTH OF WILSON CREEK ROAD. (SR=20.6)(08CCR) | 3 | R | BRX | 2013 | 150000 | 150000 | ESTIMATED | [5 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.216 | 2012-07-25 | INCREASE R PHASE AMOUNT. MOD |  |  | GRAVES | 1-1058 | KY 945 | 0.1 | 5.013 | 5.035 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-945 OVER WILSONS CREEK (B187) 0.13 MILE SOUTH OF WILSON CREEK ROAD. (SR=20.6)(08CCR) | 3 | R | BRX | 2012 | 200000 | 200000 | ESTIMATED | [5 empty] | 0
[6 empty] | GRAVES | 1-1058 | KY 945 | 0.1 | 5.013 | 5.035 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-945 OVER WILSONS CREEK (B187) 0.13 MILE SOUTH OF WILSON CREEK ROAD. (SR=20.6)(08CCR) | 4 | U | BRX | 2013 | 225000 | 225000 | ESTIMATED | [5 empty] | 0
[6 empty] | GRAVES | 1-1058 | KY 945 | 0.1 | 5.013 | 5.035 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-945 OVER WILSONS CREEK (B187) 0.13 MILE SOUTH OF WILSON CREEK ROAD. (SR=20.6)(08CCR) | 5 | C | BRX | 2014 | 475000 | 475000 | ESTIMATED | [5 empty] | 0
[6 empty] | GRAVES | 1-1060 | KY 97 | 0.1 | 16.612 | 16.621 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-97 OVER TORIAN CREEK (B46) 0.5 MILE SOUTH OF EAST TUCKER ROAD. (SR=21.3)(08CCR) | 3 | R | BRX | 2013 | 200000 | 200000 | ESTIMATED | [5 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.216 | 2012-07-25 | INCREASE R PHASE FUNDING AMOUNT. MOD |  |  | GRAVES | 1-1060 | KY 97 | 0.1 | 16.612 | 16.621 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-97 OVER TORIAN CREEK (B46) 0.5 MILE SOUTH OF EAST TUCKER ROAD. (SR=21.3)(08CCR) | 3 | R | BRX | 2012 | 250000 | 250000 | ESTIMATED | [5 empty] | 0
[6 empty] | GRAVES | 1-1060 | KY 97 | 0.1 | 16.612 | 16.621 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-97 OVER TORIAN CREEK (B46) 0.5 MILE SOUTH OF EAST TUCKER ROAD. (SR=21.3)(08CCR) | 4 | U | BRX | 2013 | 300000 | 300000 | ESTIMATED | [5 empty] | 0
[6 empty] | GRAVES | 1-1060 | KY 97 | 0.1 | 16.612 | 16.621 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-97 OVER TORIAN CREEK (B46) 0.5 MILE SOUTH OF EAST TUCKER ROAD. (SR=21.3)(08CCR) | 5 | C | BRX | 2014 | 800000 | 800000 | ESTIMATED | [5 empty] | 0
|  |  |  | BRZ | 0103296 | GRAVES | 1-1134 | KY 1748 | 0.1 | 3.805 | 3.905 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-1748 (MP 3.855) OVER BRANCH OBION CREEK; .3 MI E OF JCT CR 5289; (STRUCTURALLY DEFICIENT, SR=20.2) 042B00236N | 2 | D | BRX | 2012 | 150000 | 150000 | ESTIMATED | N |  | OBLIGATED | 150000 |  | 150000 | 2011 | 4th QUARTER | N/A
|  |  |  | BRZ | 0103301 | GRAVES | 1-1137 | CR 1194 | 0.1 | 0.62 | 0.72 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON CR-1194 (MP 0.67) OVER CALDWELL CREEK; .6 MI S OF JCT CR 5221; (STRUCTURALLY DEFICIENT, SR=23.5) 042C00252N | 2 | D | BRZ | 2012 | 200000 | 200000 | ESTIMATED | N |  | OBLIGATED | 200000 |  | 200000 | 2012 | 2nd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.197 | 2012-05-30 | ADD PROJECT. NEW |  |  | GRAVES | 1-1146 | KY 945 | 0.4 | 7.197 | 7.237 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 945 OVER BRANCH OF BRUSH CREEK S OF INTERSECTION WITH BURCHARD RD (CR 1416)(SR 16.8)042B00206N |  | D | BRO | 2012 | 220000 | 220000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.215 | 2012-07-10 | ADD PROJECT. NEW |  |  | GRAVES | 1-1147 | CR 1384 | 0.04 | 0.403 | 0.443 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON RULE SHACK ROAD OVER IC RAILROAD 0.4 MILE E OF KY 339(SR29.3)042C00146N |  | D | BRZ | 2012 | 300000 | 300000 | [6 empty] | 0
|  |  | THIS ITEM NUMBER IS A BREAKOUT OF ZVARIOUS NO. 99-352.06. NEW | RHPD | 0801086 | GRAVES | 99-352.06 | KY 80 |  |  |  | SAFETY | SAFETY-RR PROTECTN(P) | BROADWAY (KY 80) AT P&L RAILROAD CROSSING IN MAYFIELD |  | C | RHPD | 2011 | 265000.01 | 240000 |  |  |  | OBLIGATED | 240000 |  | 240000 | 2011 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.062 | 2011-04-07 | ADD PROJECT. BREAKOUT FROM 99-911.00. NEW | HSIP | 0021029 | GRAYSON | 4-912 | WK 9001 | 31.25 | 88.4 | 119.7 | SAFETY | SAFETY-HAZARD ELIM(P) | REMOVE TREES AND BRUSH ALONG THE WESTERN KENTUCKY PARKWAY FROM THE BUTLER COUNTY LINE TO THE HARDIN COUNTY LINE. |  | C | SAF | 2011 | 154000 | 154000 |  |  |  | OBLIGATED | 154000 |  | 154000 | 2011 | 3rd QUARTER | N/A
|  |  |  | BRO | 5096009 | GRAYSON | 4-1067 | KY 88 | 0.1 | 2.435 | 2.535 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-88 OVER BEAR CREEK; AT JCTS KY 1214 E & W; (STRUCTURALLY DEFICIENT, SR=49.7) 043B00007N | 2 | D | BRO | 2011 | 170000 | 170000 | ESTIMATED | N | 2010 | OBLIGATED | 170000 |  | 170000 | 2011 | 1st QUARTER | N/A
|  |  |  | BRO | 5096012 | GRAYSON | 4-1067 | KY 88 | 0.1 | 2.435 | 2.535 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-88 OVER BEAR CREEK; AT JCTS KY 1214 E & W; (STRUCTURALLY DEFICIENT, SR=49.7) 043B00007N | 3 | R | BRO | 2012 | 75000 | 75000 | ESTIMATED | N |  | OBLIGATED | 130000 |  | 130000 | 2012 | 4th QUARTER | N/A
|  |  |  | BRO | 5096011 | GRAYSON | 4-1067 | KY 88 | 0.1 | 2.435 | 2.535 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-88 OVER BEAR CREEK; AT JCTS KY 1214 E & W; (STRUCTURALLY DEFICIENT, SR=49.7) 043B00007N | 4 | U | BRO | 2012 | 125000 | 125000 | ESTIMATED | N |  | OBLIGATED | 170000 |  | 170000 | 2012 | 3rd QUARTER | N/A
|  |  |  | BRZ | 0403180 | GRAYSON | 4-1070 | CR 1531 | 0.1 | 1.628 | 1.728 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON CR-1531 (MP 1.678) OVER MISTAKEN CREEK; 1.6 MI W OF JCT KY 736; (STRUCTURALLY DEFICIENT, SR=18.7) 043C00023N | 2 | D | BRZ | 2012 | 130000 | 130000 | ESTIMATED | N |  | OBLIGATED | 130000 |  | 130000 | 2011 | 2nd QUARTER | N/A
|  |  |  | BRZ | 0403179 | GRAYSON | 4-1071 | CR 1561 | 0.1 | 1.742 | 1.842 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON CR-1561 (MP 1.792) OVER SPRING FORK; .7 MI SW OF JCT KY 54; (STRUCTURALLY DEFICIENT, SR=16.8) 043C00024N | 2 | D | BRZ | 2012 | 120000 | 120000 | ESTIMATED | N |  | OBLIGATED | 120000 |  | 120000 | 2011 | 2nd QUARTER | N/A
|  |  |  | STP | 5038092 | GRAYSON | 4-8502 | US 62 |  | 22.786 | 25.249 | RELIABILITY | MINOR WIDENING(O) | WIDEN PORTIONS OF US-62 FROM LEITCHFIELD TO CLARKSON. (08CCN)(10CCR) | 2 | D | STP | 2011 | 1500000 | 1500000 | ESTIMATED | N | 2010 | OBLIGATED | 1500000 |  | 1500000 | 2011 | 1st QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.115 | 2011-09-01 | ADD PROJECT. FY 2011 IBRD PROGRAM. NEW | IBRD | 0403181 | GRAYSON | 4-1073 | KY 736 |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | KY 736 OVER PLEASANT RUN CREEK. USE OF GEOSYNTHETIC REINFORCED SOIL INTEGRATED BRIDGE SYSTEM. |  | C | KYD | 2011 | 170000 | 170000 |  |  |  | OBLIGATED | 170000 |  | 170000 | 2011 | 4th QUARTER | N/A
[6 empty] | GREEN | 8-128.11 | KY 61 | 5.1 |  |  | RELIABILITY | RECONSTRUCTION(O) | COLUMBIA TO GREENSBURG PRIORITY SECTION 1B; KY-61 FROM KY-487 AT GRESHAM, NW TO 5000' SE OF US-68 IN GREENSBURG. (2005HPP-KY125)(2005HPP-KY161). (2006BOPC)(10CCR) | 3 | R | HPP | 2011 | 1469625 | 1469625 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | GREEN | 8-128.11 | KY 61 | 5.1 |  |  | RELIABILITY | RECONSTRUCTION(O) | COLUMBIA TO GREENSBURG PRIORITY SECTION 1B; KY-61 FROM KY-487 AT GRESHAM, NW TO 5000' SE OF US-68 IN GREENSBURG. (2005HPP-KY125)(2005HPP-KY161). (2006BOPC)(10CCR) | 4 | U | STP | 2011 | 1090000 | 1090000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | GREENUP | 9-1038 | KY 2541 | 0.1 | 1.196 | 1.296 | RELIABILITY | BRIDGE REPLACEMENT(P) | MAIN STREET BR & APPRS AT LITTLE SANDY RIVER (B42) 0.20 S OF US-23 (SR=11.7) (08CCR). (045B00042N)(10CCR) | 5 | C | BRX | 2011 | 2710000 | 2710000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.020 | 2010-11-23 | TIP MOD FY 11-02. CHANGE C PHASE YEAR IN TIP. MOD |  |  | GREENUP | 9-1038 | KY 2541 | 0.1 | 1.196 | 1.296 | RELIABILITY | BRIDGE REPLACEMENT(P) | MAIN STREET BR & APPRS AT LITTLE SANDY RIVER 0.2 MILES SOUTH OF US-23 | 5 | C | BRX | 2011 | 2710000 | 2710000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.078 | 2011-05-11 | TIP MOD FY 11-05. CHANGE C PHASE FUNDING AMOUNT. MOD | BRZ | 0903172 | GREENUP | 9-1038 | KY 2541 | 0.1 | 1.196 | 1.296 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES AT LITTLE SANDY RIVER 0.2 MILES SOUTH OF US-23 | 5 | C | BRX | 2011 | 4000000 | 4000000 | ESTIMATED | N |  | OBLIGATED | 4000000 |  | 4000000 | 2011 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.027 | 2011-01-03 | TIP MOD FY 11-03. ADD DESIGN PHASE TO STIP. NEW |  |  | GREENUP | 9-1071 | CR 1283 | 0.1 | 7.4 | 7.5 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON CR-1283 OVER TYGARTS CREEK | 3 | D | BRZ | 2011 | 324800 | 324800 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | GREENUP | 9-1071 | CR 1283 | 0.1 | 7.406 | 7.433 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON CR-1283 OVER TYGARTS CREEK (C20)(08CCR). (045C00020N) | 3 | R | BRZ | 2011 | 80000 | 80000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.020 | 2010-11-23 | TIP MOD FY 11-02. CHANGE R PHASE YEAR IN TIP. MOD |  |  | GREENUP | 9-1071 | CR 1283 | 0.1 | 7.4 | 7.5 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON CR-1283 OVER TYGARTS CREEK | 3 | R | BRZ | 2011 | 80000 | 80000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.104 | 2011-08-10 | ALREADY IN TIP WITH TIP MOD FY 10-02. INCREASE R PHASE. MOD | BRZ | 0903176 | GREENUP | 9-1071 | CR 1283 | 0.1 | 7.4 | 7.5 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON CR-1283 (LAUREL ROAD) OVER TYGARTS CREEK (C20) | 3 | R | BRZ | 2011 | 100000 | 100000 | ESTIMATED | N | 2010 | OBLIGATED | 100000 |  | 100000 | 2012 | 2nd QUARTER | N/A
[6 empty] | GREENUP | 9-1071 | CR 1283 | 0.1 | 7.406 | 7.433 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON CR-1283 OVER TYGARTS CREEK (C20)(08CCR). (045C00020N) | 4 | U | BRZ | 2011 | 40000 | 40000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.020 | 2010-11-23 | TIP MOD FY 11-02. CHANGE U PHASE YEAR IN TIP. MOD |  |  | GREENUP | 9-1071 | CR 1283 | 0.1 | 7.4 | 7.5 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON CR-1283 OVER TYGARTS CREEK | 3 | U | BRZ | 2011 | 40000 | 40000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | GREENUP | 9-1071 | CR 1283 | 0.1 | 7.406 | 7.433 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON CR-1283 OVER TYGARTS CREEK (C20)(08CCR). (045C00020N) | 5 | C | BRZ | 2011 | 1130000 | 1130000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | GREENUP | 9-1073 | KY 244 | 0.1 | 0.053 | 0.153 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-244 (MP 0.103) OVER CSX RAILROAD; .05 MI N.E. OF JCT US 23; (STRUCTURALLY DEFICIENT, SR=47.9) 045B00039N | 2 | D | BRX | 2011 | 230000 | 230000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.057 | 2011-03-23 | TIP AMENDMENT NO. 2. NO CHANGE TO STIP. REVISING THE TIP TO MATCH THE INFORMATION IN THE STIP. |  |  | GREENUP | 9-1073 | KY 244 | 0.1 | 0.053 | 0.153 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-244 (MP 0.103) OVER CSX RAILROAD; .05 MI N.E. OF JCT US 23; (STRUCTURALLY DEFICIENT, SR=47.9) 045B00039N | 2 | D | BRX | 2011 | 230000 | 230000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.073 | 2011-05-02 | TIP MOD NO. FY 11-04. INCREASE FUNDING AMOUNT. MOD | BRZ | 0903175 | GREENUP | 9-1073 | KY 244 | 0.1 | 0.053 | 0.153 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-244 (MP 0.103) OVER CSX RAILROAD; .05 MI N.E. OF JCT US 23; (STRUCTURALLY DEFICIENT, SR=47.9) 045B00039N | 2 | D | BRX | 2011 | 330000 | 330000 | ESTIMATED | N |  | OBLIGATED | 330000 |  | 330000 | 2011 | 3rd QUARTER | N/A
[6 empty] | GREENUP | 9-1078 | CS 1023 | 0.1 | 0.071 | 0.171 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON CS-1023 (MP 0.121) OVER TOWN BRANCH; 100' S. JCT KY 2541; (STRUCTURALLY DEFICIENT, SR=16.5) 045C00051N | 2 | D | BRZ | 2012 | 110000 | 110000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.057 | 2011-03-23 | TIP AMENDMENT NO. 2. NO CHANGE TO STIP. REVISING THE TIP TO MATCH THE INFORMATION IN THE STIP. |  |  | GREENUP | 9-1078 | CS 1023 | 0.1 | 0.071 | 0.171 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON CS-1023 (MP 0.121) OVER TOWN BRANCH; 100' S. JCT KY 2541; (STRUCTURALLY DEFICIENT, SR=16.5) 045C00051N | 2 | D | BRZ | 2012 | 110000 | 110000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | HANCOCK | 2-1076 | CR 1324 | 0.1 | 0.935 | 1.035 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON CR-1324 (MP 0.985) OVER BLACKFORD CREEK; 0.1 MI NW JCT US 60; (STRUCTURALLY DEFICIENT, SR=17) 046C00028N | 2 | D | BRZ | 2012 | 130000 | 130000 | ESTIMATED | N |  |  |  |  | 0
|  |  |  | NH | 0654043 | HARDIN | 4-20.01 | I 65 |  | 85.313 | 86.064 | RELIABILITY | I-CHANGE RECONST(O) | IMPROVE THE SAFETY AND INCREASE THE CAPACITY OF THE I-65/KY-222 INTERCHANGE BASED ON EXISTING AND FUTURE NEEDS OF THE AREA. (2006BOPC)(08CCR)(10CCR) | 3 | R | NH | 2011 | 3970000 | 3970000 | ESTIMATED | Y | 2010 | OBLIGATED | 3527000 |  | 3527000 | 2011 | 2nd QUARTER | N/A
|  |  |  | NH | 0654041 | HARDIN | 4-20.01 | I 65 |  | 85.313 | 86.064 | RELIABILITY | I-CHANGE RECONST(O) | IMPROVE THE SAFETY AND INCREASE THE CAPACITY OF THE I-65/KY-222 INTERCHANGE BASED ON EXISTING AND FUTURE NEEDS OF THE AREA. (2006BOPC)(08CCR)(10CCR) | 4 | U | NH | 2011 | 920000 | 920000 | ESTIMATED | Y |  | OBLIGATED | 920000 |  | 920000 | 2011 | 1st QUARTER | N/A
[6 empty] | HARDIN | 4-20.01 | I 65 |  | 85.313 | 86.064 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | IMPROVE THE SAFETY AND INCREASE THE CAPACITY OF THE I-65/KY-222 INTERCHANGE BASED ON EXISTING AND FUTURE NEEDS OF THE AREA. (2006BOPC)(08CCR) | 5 | C | NH | 2013 | 43870000 | 43870000 | ESTIMATED | [5 empty] | 0
[6 empty] | HARDIN | 4-100 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | CONSTRUCT NEW ACCESS ROAD FROM KY-313 TO NORTH WILSON ROAD EAST OF RADCLIFF, KENTUCKY. (FUNDING NOT CURRENTLY AVAILABLE; REQUIRES ALLOCATION OF DEPARTMENT OF DEFENSE ACCESS ROAD FUNDING OR CONGRESSIONAL DISCRETIONARY FUNDING) | 2 | D | KYD | 2011 | 1100000 | 1100000 | ESTIMATED | [5 empty] | 0
[6 empty] | HARDIN | 4-286.1 | I 65 | 0.1 | 81.95 | 82.05 | RELIABILITY | WEIGH STA REHAB(P) | I-65 SOUTHBOUND PORT OF ENTRY FOR A COMMERCIAL VEHICLE MONITORING STATION.(10CCR) | 2 | D | IM | 2011 | 370000 | 370000 | ESTIMATED | Y | 2010 |  |  |  | 0
[6 empty] | HARDIN | 4-286.1 | I 65 | 0.1 | 81.95 | 82.05 | RELIABILITY | WEIGH STA REHAB(P) | I-65 SOUTHBOUND PORT OF ENTRY FOR A COMMERCIAL VEHICLE MONITORING STATION. | 3 | R | IM | 2013 | 90000 | 90000 | ESTIMATED | [5 empty] | 0
[6 empty] | HARDIN | 4-286.1 | I 65 | 0.1 | 81.95 | 82.05 | RELIABILITY | WEIGH STA REHAB(P) | I-65 SOUTHBOUND PORT OF ENTRY FOR A COMMERCIAL VEHICLE MONITORING STATION. | 4 | U | IM | 2013 | 110000 | 110000 | ESTIMATED | [5 empty] | 0
[6 empty] | HARDIN | 4-286.1 | I 65 | 0.1 | 81.95 | 82.05 | RELIABILITY | WEIGH STA REHAB(P) | I-65 SOUTHBOUND PORT OF ENTRY FOR A COMMERCIAL VEHICLE MONITORING STATION. | 5 | C | IM | 2014 | 9570000 | 9570000 | ESTIMATED | [5 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.063 | 2011-04-07 | ADD PROJECT. BREAKOUT FROM TIP GROUPED PROJECT ON PAGE 12 OF TIP. NEW | HSIP | 7872008 | HARDIN | 4-909 | KY 251 | 3.52 | 2.72 | 6.326 | SAFETY | SAFETY-HAZARD ELIM(P) | REMOVE HEADWALLS, EXTEND PIPES, AND FLATTEN SLOPES ON KY 251 IN ELIZABETHTOWN FROM RING ROAD (KY 3005) TO KY 434. |  | C | SAF | 2011 | 50000 | 50000 |  |  |  | OBLIGATED | 50050 |  | 50050 | 2011 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.063 | 2011-04-07 | ADD PROJECT. BREAKOUT FROM TIP GROUPED PROJECT ON PAGE 12 OF TIP. NEW | HSIP | 0311026 | HARDIN | 4-910 | US 31W | 3.36 | 34 | 37.367 | SAFETY | SAFETY-HAZARD ELIM(P) | REMOVE AND RESET ALL LOW GUARDRAIL AND REPLACE "TWIST" END TREATMENTS ON US 31W FROM TOGA CREEK CULVERT TO THE JEFFERSON COUNTY LINE AND REMOVE SOUTHBOUND SLIP RAMP AT US 31WX. |  | C | SAF | 2011 | 425000 | 425000 |  |  |  | OBLIGATED | 425000 |  | 425000 | 2011 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.063 | 2011-04-07 | ADD PROJECT. BREAKOUT FROM TIP GROUPED PROJECT ON PAGE 12 OF TIP. NEW | HSIP | 0021030 | HARDIN | 4-913 | WK 9001 | 17.16 | 119.65 | 136.8 | SAFETY | SAFETY-HAZARD ELIM(P) | REMOVE TREES AND BRUSH ALONG THE WESTERN KENTUCKY PARKWAY FROM THE GRAYSON COUNTY LINE TO US 31W. |  | C | SAF | 2011 | 86000 | 86000 |  |  |  | OBLIGATED | 381000 |  | 381000 | 2011 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.043 | 2011-02-21 | TIP MOD #10. ADD PROJECT. NEW | IM | 0654044 | HARDIN | 4-2042 | I 65 |  |  |  | RELIABILITY | WEIGH STA REHAB(P) | I-65 PAVEMENT REPAIRS TO INTERSTATE RAMPS FOR HARDIN COUNTY I-65 WEIGH STATIONS |  | D | IM | 2011 | 10000 | 10000 |  |  |  | OBLIGATED | 10000 |  | 10000 | 2011 | 2nd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.043 | 2011-02-21 | TIP MOD #10. ADD PROJECT. NEW |  |  | HARDIN | 4-2042 | I 65 |  |  |  | RELIABILITY | WEIGH STA REHAB(P) | I-65 PAVEMENT REPAIRS TO INTERSTATE RAMPS FOR HARDIN COUNTY I-65 WEIGH STATIONS |  | C | IM | 2011 | 122000 | 122000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.080 | 2011-05-13 | TIP MOD #12. INCREASE PHASE COST. MOD | IM | 0654045 | HARDIN | 4-2042 | I 65 |  |  |  | RELIABILITY | WEIGH STA REHAB(P) | I-65 PAVEMENT REPAIRS TO INTERSTATE RAMPS FOR HARDIN COUNTY I-65 WEIGH STATIONS |  | C | IM | 2011 | 250000 | 250000 |  |  |  | OBLIGATED | 250000 |  | 250000 | 2011 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.172 | 2012-04-03 | TIP MOD #14. ADD TO STIP. NEW | IM | 0653038 | HARDIN | 4-2802 | I-65 |  | 78.66 | 80.4 | SAFETY | SAFETY(P) | INSTALL MEDIAN CABLE BARRIERS ON I-65 FROM MP 78.66 TO MP 80.4. |  | C | IM | 2012 | 312620 | 312620 |  |  |  | OBLIGATED | 312620 |  | 312620 | 2012 | 2nd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.008 | 2010-10-20 | TIP MOD #7. ADD PROJECT. NEW | STP | 0311025 | HARDIN | 4-8103.11 | US 31W | 2.4 | 0 | 2.4 | RELIABILITY | NEW ROUTE(O) | US 31W BYPASS - NEW CONNECTOR ROAD: PAVEMENT REPAIR & REHABILITATION FROM NEW GLENDALE ROAD (MP 0.00) TO ST. JOHN ROAD (MP 2.40) |  | C | STP | 2011 | 10500000 | 10500000 |  | N |  | OBLIGATED | 10500050 |  | 10500050 | 2011 | 1st QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.177 | 2012-03-26 | ADD PROJECT TO STIP. NEW |  |  | HARDIN |  | KY 220 |  |  |  | SAFETY | SAFETY-RR PROTECTN(P) | ADD GATES TO EXISTING FLASHING LIGHTS AND BELL SYSTEM AT P&L RAILROAD CROSSING ON KY 220 AT RINEYVILLE. (DOT# 296882N) |  | U | SAF | 2012 | 225000 | 225000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.177 | 2012-03-26 | ADD PROJECT TO STIP. NEW | RHPD | 0401074 | HARDIN | 99-352.07 | KY 220 |  |  |  | SAFETY | SAFETY-RR PROTECTN(P) | ADD GATES TO EXISTING FLASHING LIGHTS AND BELL SYSTEM AT P&L RAILROAD CROSSING ON KY 220 AT RINEYVILLE. (DOT# 296882N) |  | C | SAF | 2012 | 15000 | 15000 |  |  |  | OBLIGATED | 217500 |  | 217500 | 2012 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.099 | 2011-07-14 | ADD PROJECT TO STIP. BREAKOUT FROM 99-911.00. NEW | HSIP | 9010061 | HARLAN | 11-920 | US 119 | 39.182 | 0 | 39.182 | SAFETY | SAFETY-HAZARD ELIM(P) | REPLACE GUARDRAIL END TREATMENTS ON US 119 FROM THE BELL COUNTY LINE TO THE LETCHER COUNTY LINE |  | C | SAF | 2011 | 450000 | 450000 |  |  |  | OBLIGATED | 450000 |  | 450000 | 2011 | 4th QUARTER | N/A
[6 empty] | HARLAN | 11-1061 | KY 413 | 0.1 | 0.027 | 0.071 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER CUMBERLAND RIVER (B89) 0.1MI N JCT. KY-840. (SR=27.3): (048B00089N) | 3 | R | BRX | 2011 | 80000 | 80000 | ESTIMATED | N | 2010 |  |  |  | 0
|  |  |  | BRZ | 1103253 | HARLAN | 11-1061 | KY 413 | 0.1 | 0.027 | 0.071 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER CUMBERLAND RIVER (B89) 0.1MI N JCT. KY-840. (SR=27.3): (048B00089N) | 4 | U | BRX | 2011 | 160000 | 160000 | ESTIMATED | N | 2010 | OBLIGATED | 175000 |  | 175000 | 2012 | 3rd QUARTER | N/A
[6 empty] | HARLAN | 11-1061 | KY 413 | 0.1 | 0.027 | 0.071 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER CUMBERLAND RIVER (B89) 0.1MI N JCT. KY-840. (SR=27.3): (048B00089N) | 5 | C | BRX | 2011 | 1040000 | 1040000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | HARLAN | 11-1064 | CR 1125 | 0.1 | 0.003 | 0.022 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON CR-1125 OVER CLOVER FORK OF CUMBERLAND RIVER (C30). (SR=2.0)(PROJECT FUNDING CONTINGENT UPON BRIDGE POSTING COMPLIANCE): (048C00030N) | 3 | R | BRZ | 2011 | 230000 | 230000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | HARLAN | 11-1064 | CR 1125 | 0.1 | 0.003 | 0.022 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON CR-1125 OVER CLOVER FORK OF CUMBERLAND RIVER (C30). (SR=2.0)(PROJECT FUNDING CONTINGENT UPON BRIDGE POSTING COMPLIANCE): (048C00030N) | 4 | U | BRZ | 2011 | 120000 | 120000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | HARLAN | 11-1064 | CR 1125 | 0.1 | 0.003 | 0.022 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON CR-1125 OVER CLOVER FORK OF CUMBERLAND RIVER (C30). (SR=2.0)(PROJECT FUNDING CONTINGENT UPON BRIDGE POSTING COMPLIANCE): (048C00030N) | 5 | C | BRZ | 2011 | 810000 | 810000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | HARLAN | 11-1065 | PV 1000 | 0.1 | 0.016 | 0.035 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON PV-1000 OVER CLOVER FORK OF CUMBERLAND RIVER (C29). (SR=3.0)(PROJECT FUNDING CONTINGENT UPON BRIDGE POSTING COMPLIANCE): (048C00029N) | 3 | R | BRZ | 2011 | 340000 | 340000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | HARLAN | 11-1065 | PV 1000 | 0.1 | 0.016 | 0.035 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON PV-1000 OVER CLOVER FORK OF CUMBERLAND RIVER (C29). (SR=3.0)(PROJECT FUNDING CONTINGENT UPON BRIDGE POSTING COMPLIANCE): (048C00029N) | 4 | U | BRZ | 2011 | 170000 | 170000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | HARLAN | 11-1065 | PV 1000 | 0.1 | 0.016 | 0.035 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON PV-1000 OVER CLOVER FORK OF CUMBERLAND RIVER (C29). (SR=3.0)(PROJECT FUNDING CONTINGENT UPON BRIDGE POSTING COMPLIANCE): (048C00029N) | 5 | C | BRZ | 2011 | 1110000 | 1110000 | ESTIMATED | N |  |  |  |  | 0
|  |  |  | BRZ | 1103237 | HARLAN | 11-1074 | KY 3459 | 0.1 | 0.059 | 0.095 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-3459 OVER MARTINS FORK CUMBERLAND RIVER (B143) 0.1 MILE WEST JCT. US-421 NEAR DRESSEN. (SR=14.6): (048B00143N) | 3 | R | BRX | 2011 | 250000 | 250000 | ESTIMATED | N |  | OBLIGATED | 250000 |  | 250000 | 2011 | 2nd QUARTER | N/A
|  |  |  | BRZ | 1103238 | HARLAN | 11-1074 | KY 3459 | 0.1 | 0.059 | 0.095 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-3459 OVER MARTINS FORK CUMBERLAND RIVER (B143) 0.1 MILE WEST JCT. US-421 NEAR DRESSEN. (SR=14.6): (048B00143N) | 4 | U | BRX | 2011 | 150000 | 150000 | ESTIMATED | N |  | OBLIGATED | 150000 |  | 150000 | 2011 | 3rd QUARTER | N/A
|  |  |  | BRZ | 1103242 | HARLAN | 11-1074 | KY 3459 | 0.1 | 0.059 | 0.095 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-3459 OVER MARTINS FORK CUMBERLAND RIVER (B143) 0.1 MILE WEST JCT. US-421 NEAR DRESSEN. (SR=14.6) | 5 | C | BRX | 2014 | 445000 | 445000 | ESTIMATED |  |  | OBLIGATED | 1197866.4 |  | 1197866.4 | 2012 | 1st QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.191 | 2012-05-16 | ADD PROJECT TO STIP. NEW |  |  | HARLAN | 11-1087 | KY 72 | 0.04 | 6.539 | 6.579 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 72 OVER CATRON CREEK AT INTERSECTION OF KY 72 AND SMITH LANE (CR 1226L)(SR 30) 048B00030N |  | D | BRO | 2012 | 400000 | 400000 | [6 empty] | 0
|  |  |  | BRZ | 0603210 | HARRISON | 6-1052 | KY 356 | 0.1 | 12.038 | 12.066 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER MILL CREEK (B30) 2.5 MI W OF JCT. KY-36. (SR=33.5): (049B00030N) | 5 | C | BRX | 2011 | 940000 | 940000 | ESTIMATED | N | 2010 | OBLIGATED | 1299103 |  | 1299103 | 2012 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.191 | 2012-05-16 | ADD PROJECT TO STIP. NEW | BRZ | 0603227 | HARRISON | 6-1083 | CR 1052 | 0.04 | 2.913 | 2.953 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON STRATTON ROAD (CR 1052) OVER STRATTON BRANCH 0.3 MILE NE OF CSX RAILROAD(SR 23.5) 049C00018N |  | D | BRZ | 2012 | 150000 | 150000 |  |  |  | OBLIGATED | 150000 |  | 150000 | 2012 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.044 | 2011-02-21 | ADD PROJECT TO STIP. BREAKOUT D PHASE FROM 99-337.05. FUNDING IS BOTH IM AND NH FOR D PHASE. NEW | IM | 0652079 | HART | 4-14 |  |  |  |  | RELIABILITY | MAJOR WIDENING(O) | TENNESSEE STATE LINE-ELIZABETHTOWN: WIDEN TO 6 LANES FROM 0.1 MILE SOUTH OF THE GREEN RIVER BRIDGE (B31) TO 0.1 MILE NORTH OF THE US 31W BRIDGE (B27) |  | D | IM | 2011 | 1080000 | 1080000 |  |  |  | OBLIGATED | 1080000 |  | 1080000 | 2011 | 2nd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.044 | 2011-02-21 | ADD PROJECT TO STIP. BREAKOUT D PHASE FROM 99-337.05. FUNDING IS BOTH IM AND NH FOR D PHASE. NEW | NH | 0652079 | HART | 4-14 |  |  |  |  | RELIABILITY | MAJOR WIDENING(O) | TENNESSEE STATE LINE-ELIZABETHTOWN: WIDEN TO 6 LANES FROM 0.1 MILE SOUTH OF THE GREEN RIVER BRIDGE (B31) TO 0.1 MILE NORTH OF THE US 31W BRIDGE (B27) |  | D | NH | 2011 | 1620000 | 1620000 |  |  |  | OBLIGATED | 1620000 |  | 1620000 | 2011 | 2nd QUARTER | N/A
[6 empty] | HART | 4-15 | I 65 | 6.7 | 64.3 | 71 | RELIABILITY | MAJOR WIDENING(O) | TENN. STATE LINE-ELIZABETHTOWN; WIDEN TO 6 LANES FROM 0.1 MI N OF THE US 31W BRIDGE (B27) TO 0.6 MI N OF THE KY 728 BRIDGE. (PE & ENV UNDER 4-10.05) (04CCN) (08CCR)(10CCR) | 3 | R | NHG | 2011 | 500000 | 500000 | ESTIMATED | Y | 2010 |  |  |  | 0
[6 empty] | HART | 4-15 | I 65 | 6.7 | 64.3 | 71 | RELIABILITY | MAJOR WIDENING(O) | TENN. STATE LINE-ELIZABETHTOWN; WIDEN TO 6 LANES FROM 0.1 MI N OF THE US 31W BRIDGE (B27) TO 0.6 MI N OF THE KY 728 BRIDGE. (PE & ENV UNDER 4-10.05) (04CCN) (08CCR)(10CCR) | 4 | U | NH | 2011 | 550000 | 550000 | ESTIMATED | Y |  |  |  |  | 0
[6 empty] | HART | 4-16 | I 65 | 5 | 71 | 74.622 | RELIABILITY | MAJOR WIDENING(O) | TENN. STATE LINE-ELIZABETHTOWN; WIDEN TO 6 LANES FROM 0.6 MI N OF THE KY 728 BRIDGE TO 0.1 MI N OF KY 224. (PE & ENV UNDER 4-10.05)(04CCN) | 3 | R | NH | 2011 | 530000 | 530000 | ESTIMATED | Y | 2010 |  |  |  | 0
[6 empty] | HART | 4-16 | I 65 | 5 | 71 | 74.622 | RELIABILITY | MAJOR WIDENING(O) | TENN. STATE LINE-ELIZABETHTOWN; WIDEN TO 6 LANES FROM 0.6 MI N OF THE KY 728 BRIDGE TO 0.1 MI N OF KY 224. (PE & ENV UNDER 4-10.05)(04CCN) | 4 | U | NH | 2011 | 520000 | 520000 | ESTIMATED | Y | 2010 |  |  |  | 0
[6 empty] | HART | 4-1065 | US 31W | 0.1 | 10.051 | 10.329 | SAFETY | BRIDGE PAINTING(P) | STEEL REPAIR AND PAINT DECK TRUSS ON US-31W BRIDGE OVER GREEN RIVER SOUTHEAST OF MUNFORDVILLE (B4). (050B00004N) | 2 | D | BRO | 2011 | 100000 | 100000 | ESTIMATED | N | 2010 |  |  |  | 0
|  |  |  | BRO | 5082023 | HART | 4-1065 | US 31W | 0.1 | 10.051 | 10.329 | SAFETY | BRIDGE PAINTING(P) | STEEL REPAIR AND PAINT DECK TRUSS ON US-31W BRIDGE OVER GREEN RIVER SOUTHEAST OF MUNFORDVILLE (B4). (050B00004N) | 5 | C | BRO | 2011 | 3000000 | 3000000 | ESTIMATED | N |  | OBLIGATED | 3450000 |  | 3450000 | 2011 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.173 | 2012-03-19 | ADD TO STIP. | IM | 0653038 | HART | 4-2802 | I-65 |  |  |  | SAFETY | SAFETY(P) | INSTALL HTC MEDIAN CABLE BARRIER ON I-65 IN HART, LARUE, AND HARDIN COUNTIES FROM MP 74.2 TO MP 80.4 (KY 84 INTERCHANGE) |  | C | IM | 2012 | 28160 | 28160 |  |  |  | OBLIGATED | 28160 |  | 28160 | 2012 | 2nd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.177 | 2012-03-26 | ADD PROJECT TO STIP. NEW |  |  | HART |  | CR 5440 |  |  |  | SAFETY | SAFETY-RR PROTECTN(P) | ADD GATES TO EXISTING FLASHING LIGHTS AND BELL SYSTEM AT CSX RAILROAD CROSSING ON FALLING SPRINGS ROAD. (DOT# 343594Y) |  | U | SAF | 2012 | 225000 | 225000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.177 | 2012-03-26 | ADD PROJECT TO STIP. NEW | RHPD | 0401075 | HART | 99-352.07 | CR 5440 |  |  |  | SAFETY | SAFETY-RR PROTECTN(P) | ADD GATES TO EXISTING FLASHING LIGHTS AND BELL SYSTEM AT CSX RAILROAD CROSSING ON FALLING SPRINGS ROAD. (DOT# 343594Y) |  | C | SAF | 2012 | 15000 | 15000 |  |  |  | OBLIGATED | 217500 |  | 217500 | 2012 | 3rd QUARTER | N/A
|  |  |  | HPP | 0153007 | HENDERSON | 2-152.02 |  |  |  |  | RELIABILITY | TRANSP ENHANCEMENT(P) | HENDERSON RIVERFRONT DEVELOPMENT PROJECT IN HENDERSON. (2005HPP-KY153) | 5 | C | HPP | 2011 | 8948901 | 8948901 | ESTIMATED | N | 2010 | OBLIGATED | 1628917 |  | 1628917 | 2011 | 2nd QUARTER | CITY OF HENDERSON
|  |  | ADD TO STIP PER FY 2010-2013 TIP. NEW | HPP | 0153008 | HENDERSON | 2-152.03 |  |  |  |  | RELIABILITY | TRANSP ENHANCEMENT(P) | HENDERSON RIVERFRONT DEVELOPMENT PROJECT IN HENDERSON. (2005HPP-KY153) | 5 | C | HPP | 2011 | 8948901 | 8948901 | ESTIMATED | N | 2010 | OBLIGATED | 2487633 |  | 2487633 | 2011 | 3rd QUARTER | CITY OF HENDERSON
|  |  | ADD TO STIP PER FY 2010-2013 TIP. THIS 25,000 IS FOR CONSTRUCTION OVERSIGHT ACTIVITIES BY STATE FORCES. | HPP | 0153009 | HENDERSON | 2-152.03 |  |  |  |  | RELIABILITY | TRANSP ENHANCEMENT(P) | HENDERSON RIVERFRONT DEVELOPMENT PROJECT IN HENDERSON. (2005HPP-KY153) | 5 | C | HPP | 2011 | 8948901 | 8948901 | ESTIMATED | N | 2010 | OBLIGATED | 25000 |  | 25000 | 2011 | 3rd QUARTER | CITY OF HENDERSON
|  |  | ADD TO STIP PER FY 2010-2013 TIP. NEW | HPP | 0153010 | HENDERSON | 2-152.04 |  |  |  |  | RELIABILITY | TRANSP ENHANCEMENT(P) | HENDERSON RIVERFRONT DEVELOPMENT PROJECT IN HENDERSON. (2005HPP-KY153) | 5 | C | HPP | 2011 | 8948901 | 8948901 | ESTIMATED | N | 2010 | OBLIGATED | 3554889 |  | 3554889 | 2011 | 3rd QUARTER | CITY OF HENDERSON
|  |  | ADD TO STIP PER FY 2010-2013 TIP. NEW | HPP | 0153011 | HENDERSON | 2-152.04 |  |  |  |  | RELIABILITY | TRANSP ENHANCEMENT(P) | HENDERSON RIVERFRONT DEVELOPMENT PROJECT IN HENDERSON. (2005HPP-KY153) | 5 | C | HPP | 2011 | 8948901 | 8948901 | ESTIMATED | N | 2010 | OBLIGATED | 50000 |  | 50000 | 2011 | 3rd QUARTER | CITY OF HENDERSON
[6 empty] | HENDERSON | 2-700.05 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | FEDERAL 'STP' FUNDS DEDICATED TO HENDERSON. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | 5 | C | SHN | 2011 | 400000 | 400000 | ESTIMATED |  | 2010 |  |  |  | 0
[6 empty] | HENDERSON | 2-700.07 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | FEDERAL 'STP' FUNDS DEDICATED TO HENDERSON. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | 5 | C | SHN | 2012 | 400000 | 400000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | HENDERSON | 2-700.08 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | FEDERAL 'STP' FUNDS DEDICATED TO HENDERSON. | 5 | C | SHN | 2013 | 400000 | 400000 | ESTIMATED | [5 empty] | 0
[6 empty] | HENDERSON | 2-700.09 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | FEDERAL 'STP' FUNDS DEDICATED TO HENDERSON. | 5 | C | SHN | 2014 | 400000 | 400000 | ESTIMATED | [5 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.098 | 2011-07-14 | ADD TO STIP. TIP RESOLUTION 11-6. NEW |  |  | HENDERSON | 2-711 |  |  |  |  | SAFETY | SAFETY(P) | US 41 AT KY 812 INTERSECTION IMPROVEMENT TO CREATE DEDICATED LEFT, THROUGH AND RIGHT TURN LANES WITH RELATED TRAFFIC SIGNAL UPDATES. ALL PHASES WILL BE FUNDED 80% BY FEDERAL STP FUNDS (SHN) AND A KYTC 20% MATCH PROVIDED THROUGH TOLL CREDITS. |  | PE | SHN | 2013 | 250000 | 200000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.098 | 2011-07-14 | ADD TO STIP. TIP RESOLUTION 11-6. NEW |  |  | HENDERSON | 2-711 |  |  |  |  | SAFETY | SAFETY(P) | US 41 AT KY 812 INTERSECTION IMPROVEMENT TO CREATE DEDICATED LEFT, THROUGH AND RIGHT TURN LANES WITH RELATED TRAFFIC SIGNAL UPDATES. ALL PHASES WILL BE FUNDED 80% BY FEDERAL STP FUNDS (SHN) AND A KYTC 20% MATCH PROVIDED THROUGH TOLL CREDITS. |  | R | SHN | 2014 | 50000 | 40000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.098 | 2011-07-14 | ADD TO STIP. TIP RESOLUTION 11-6. NEW |  |  | HENDERSON | 2-711 |  |  |  |  | SAFETY | SAFETY(P) | US 41 AT KY 812 INTERSECTION IMPROVEMENT TO CREATE DEDICATED LEFT, THROUGH AND RIGHT TURN LANES WITH RELATED TRAFFIC SIGNAL UPDATES. ALL PHASES WILL BE FUNDED 80% BY FEDERAL STP FUNDS (SHN) AND A KYTC 20% MATCH PROVIDED THROUGH TOLL CREDITS. |  | U | SHN | 2014 | 100000 | 80000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.098 | 2011-07-14 | ADD TO STIP. TIP RESOLUTION 11-6. NEW |  |  | HENDERSON | 2-711 |  |  |  |  | SAFETY | SAFETY(P) | US 41 AT KY 812 INTERSECTION IMPROVEMENT TO CREATE DEDICATED LEFT, THROUGH AND RIGHT TURN LANES WITH RELATED TRAFFIC SIGNAL UPDATES. ALL PHASES WILL BE FUNDED 80% BY FEDERAL STP FUNDS (SHN) AND A KYTC 20% MATCH PROVIDED THROUGH TOLL CREDITS. |  | C | SHN | 2014 | 550000 | 440000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.098 | 2011-07-14 | ADD TO STIP. TIP RESOLUTION 11-6. NEW | STPM | 7983001 | HENDERSON | 2-712 |  |  |  |  | RELIABILITY | RECONSTRUCTION(O) | GREEN RIVER ROAD: ROAD RECONSTRUCTION PROJECT. RECONSTRUCT 0.6 MILE SECTION OF GREEN RIVER ROAD (OSAGE DR TO WOODSPOINT DR) WITH TWELVE FOOT TRAVEL LANES, CURB AND GUTTER AND SIDEWALKS. ALL PHASES WILL BE FUNDED 80% BY FEDERAL STP FUNDS (SHN) WITH A 20% LOCAL MATCH. |  | PE | SHN | 2011 | 160000 | 128000 |  |  |  | OBLIGATED | 128000 |  | 128000 | 2012 | 1st QUARTER | CITY OF HENDERSON
ADMINISTRATIVE MODIFICATION | 2010.098 | 2011-07-14 | ADD TO STIP. TIP RESOLUTION 11-6. NEW |  |  | HENDERSON | 2-712 |  |  |  |  | RELIABILITY | RECONSTRUCTION(O) | GREEN RIVER ROAD: ROAD RECONSTRUCTION PROJECT. RECONSTRUCT 0.6 MILE SECTION OF GREEN RIVER ROAD (OSAGE DR TO WOODSPOINT DR) WITH TWELVE FOOT TRAVEL LANES, CURB AND GUTTER AND SIDEWALKS. ALL PHASES WILL BE FUNDED 80% BY FEDERAL STP FUNDS (SHN) WITH A 20% LOCAL MATCH. |  | R | SHN | 2012 | 175000 | 140000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.098 | 2011-07-14 | ADD TO STIP. TIP RESOLUTION 11-6. NEW |  |  | HENDERSON | 2-712 |  |  |  |  | RELIABILITY | RECONSTRUCTION(O) | GREEN RIVER ROAD: ROAD RECONSTRUCTION PROJECT. RECONSTRUCT 0.6 MILE SECTION OF GREEN RIVER ROAD (OSAGE DR TO WOODSPOINT DR) WITH TWELVE FOOT TRAVEL LANES, CURB AND GUTTER AND SIDEWALKS. ALL PHASES WILL BE FUNDED 80% BY FEDERAL STP FUNDS (SHN) WITH A 20% LOCAL MATCH. |  | U | SHN | 2012 | 300000 | 240000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.098 | 2011-07-14 | ADD TO STIP. TIP RESOLUTION 11-6. NEW |  |  | HENDERSON | 2-712 |  |  |  |  | RELIABILITY | RECONSTRUCTION(O) | GREEN RIVER ROAD: ROAD RECONSTRUCTION PROJECT. RECONSTRUCT 0.6 MILE SECTION OF GREEN RIVER ROAD (OSAGE DR TO WOODSPOINT DR) WITH TWELVE FOOT TRAVEL LANES, CURB AND GUTTER AND SIDEWALKS. ALL PHASES WILL BE FUNDED 80% BY FEDERAL STP FUNDS (SHN) WITH A 20% LOCAL MATCH. |  | C | SHN | 2013 | 675000 | 540000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.098 | 2011-07-14 | ADD TO STIP. TIP RESOLUTION 11-6. NEW |  |  | HENDERSON | 2-713 |  |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | WATHEN LANE: BRIDGE REPLACEMENT PROJECT. REPLACE EXISTING BRIDGE STRUCTURE WITH BOX CULVERT AND GUARD RAILS. ALL PHASES WILL BE FUNDED 80% BY FEDERAL STP FUNDS (SHN) WITH A 20% LOCAL MATCH. |  | PE | SHN | 2013 | 25000 | 20000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.098 | 2011-07-14 | ADD TO STIP. TIP RESOLUTION 11-6. NEW |  |  | HENDERSON | 2-713 |  |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | WATHEN LANE: BRIDGE REPLACEMENT PROJECT. REPLACE EXISTING BRIDGE STRUCTURE WITH BOX CULVERT AND GUARD RAILS. ALL PHASES WILL BE FUNDED 80% BY FEDERAL STP FUNDS (SHN) WITH A 20% LOCAL MATCH. |  | R | SHN | 2013 | 10000 | 8000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.098 | 2011-07-14 | ADD TO STIP. TIP RESOLUTION 11-6. NEW |  |  | HENDERSON | 2-713 |  |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | WATHEN LANE: BRIDGE REPLACEMENT PROJECT. REPLACE EXISTING BRIDGE STRUCTURE WITH BOX CULVERT AND GUARD RAILS. ALL PHASES WILL BE FUNDED 80% BY FEDERAL STP FUNDS (SHN) WITH A 20% LOCAL MATCH. |  | U | SHN | 2013 | 15000 | 12000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.098 | 2011-07-14 | ADD TO STIP. TIP RESOLUTION 11-6. NEW |  |  | HENDERSON | 2-713 |  |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | WATHEN LANE: BRIDGE REPLACEMENT PROJECT. REPLACE EXISTING BRIDGE STRUCTURE WITH BOX CULVERT AND GUARD RAILS. ALL PHASES WILL BE FUNDED 80% BY FEDERAL STP FUNDS (SHN) WITH A 20% LOCAL MATCH. |  | C | SHN | 2014 | 200000 | 160000 | [6 empty] | 0
[6 empty] | HENDERSON | 2-966.02 | US 41A | 0.1 | 14.48 | 14.68 | SAFETY | PREFINANCD CONVRSN(P) | WIDENING OF US-41A AT KY-136 IN HENDERSON TO CONSTRUCT LEFT TURN LANE (ADDITIONAL FUNDING FOR C PHASE)(SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | 5 | C | SHN | 2011 | 450000 | 450000 | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.038 | 2011-02-15 | TIP AMENDMENT RESOLUTION 11-2. ADD PHASE. NEW |  |  | HENDERSON | 2-968 | KY 351 | 0.6 | 4.7 | 5.3 | SAFETY | SAFETY-HAZARD ELIM(P) | KY-351 NEAR ZION, HORIZONTAL & VERTICAL REALIGNMENT, SHOULDER WIDENING, AND INSTALL GUARDRAIL (B/C=2.5) (D-DISTRICT, C-CONTRACTOR) (2002BOP) | 3 | D | SHN | 2011 | 100000 | 100000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | HENDERSON | 2-968 | KY 351 | 0.6 | 4.7 | 5.3 | SAFETY | SAFETY-HAZARD ELIM(P) | KY-351 NEAR ZION, HORIZONTAL & VERTICAL REALIGNMENT, SHOULDER WIDENING, AND INSTALL GUARDRAIL (B/C=2.5) (D-DISTRICT, C-CONTRACTOR) (2002BOP) | 3 | R | HES | 2011 | 90000 | 90000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | HENDERSON | 2-968 | KY 351 | 0.6 | 4.7 | 5.3 | SAFETY | SAFETY-HAZARD ELIM(P) | KY-351 NEAR ZION, HORIZONTAL & VERTICAL REALIGNMENT, SHOULDER WIDENING, AND INSTALL GUARDRAIL (B/C=2.5) (D-DISTRICT, C-CONTRACTOR) (2002BOP) | 4 | U | HES | 2011 | 170000 | 170000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.038 | 2011-02-15 | TIP AMENDMENT RESOLUTION 11-2. INCREASE FUNDING AMOUNT. MOD |  |  | HENDERSON | 2-968 | KY 351 | 0.6 | 4.7 | 5.3 | SAFETY | SAFETY-HAZARD ELIM(P) | KY-351 NEAR ZION, HORIZONTAL & VERTICAL REALIGNMENT, SHOULDER WIDENING, AND INSTALL GUARDRAIL (B/C=2.5) (D-DISTRICT, C-CONTRACTOR) (2002BOP) | 4 | U | HES/ SHN | 2011 | 285000 | 285000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | HENDERSON | 2-968 | KY 351 | 0.6 | 4.7 | 5.3 | SAFETY | SAFETY-HAZARD ELIM(P) | KY-351 NEAR ZION, HORIZONTAL & VERTICAL REALIGNMENT, SHOULDER WIDENING, AND INSTALL GUARDRAIL (B/C=2.5) (D-DISTRICT, C-CONTRACTOR) (2002BOP) | 5 | C | HES | 2011 | 1170000 | 1170000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.038 | 2011-02-15 | TIP AMENDMENT RESOLUTION 11-2. INCREASE FUNDING AMOUNT. MOD |  |  | HENDERSON | 2-968 | KY 351 | 0.6 | 4.7 | 5.3 | SAFETY | SAFETY-HAZARD ELIM(P) | KY-351 NEAR ZION, HORIZONTAL & VERTICAL REALIGNMENT, SHOULDER WIDENING, AND INSTALL GUARDRAIL (B/C=2.5) (D-DISTRICT, C-CONTRACTOR) (2002BOP) | 4 | C | HES/ SHN | 2011 | 1955000 | 1955000 | ESTIMATED | N | 2010 |  |  |  | 0
|  |  |  | BRZ | 0203293 | HENDERSON | 2-1069 | KY 136 | 0.1 | 24.607 | 24.612 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-136 OVER EAST FORK CANOE CREEK DITCH .6 MILE SOUTH OF KY 520 (B24)(SR=23.3)(08CCR): (051B00024N) | 2 | D | BRX | 2011 | 150000 | 150000 | ESTIMATED | N | 2010 | OBLIGATED | 150000 |  | 150000 | 2011 | 2nd QUARTER | N/A
[6 empty] | HENDERSON | 2-1069 | KY 136 | 0.1 | 24.607 | 24.612 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-136 OVER EAST FORK CANOE CREEK DITCH .6 MILE SOUTH OF KY 520 (B24)(SR=23.3)(08CCR). | 3 | R | BRX | 2013 | 75000 | 75000 | ESTIMATED | [5 empty] | 0
[6 empty] | HENDERSON | 2-1069 | KY 136 | 0.1 | 24.607 | 24.612 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-136 OVER EAST FORK CANOE CREEK DITCH .6 MILE SOUTH OF KY 520 (B24)(SR=23.3)(08CCR). | 4 | U | BRX | 2013 | 75000 | 75000 | ESTIMATED | [5 empty] | 0
[6 empty] | HENDERSON | 2-1069 | KY 136 | 0.1 | 24.607 | 24.612 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-136 OVER EAST FORK CANOE CREEK DITCH .6 MILE SOUTH OF KY 520 (B24)(SR=23.3)(08CCR). | 5 | C | BRX | 2014 | 450000 | 450000 | ESTIMATED | [5 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.038 | 2011-02-15 | TIP AMENDMENT RESOLUTION 11-2. INCREASE FUNDING AMOUNT. SAME PROJECT AS ZVARIOUS SECTION ITEM NO. 99-8010. MOD | NH | 9005003 | HENDERSON | 2-2040 | AU 9005 | 7.133 | 8.75 | 15.883 | RELIABILITY | PAVEMENT REHAB-PRK(P) | AUDUBON PARKWAY: REPAIR AND REGRIND PAVEMENT FROM 0.178 MILES WEST OF KY-6110 TO DAVIESS COUNTY LINE |  | C | NH | 2011 | 15600000 | 15600000 |  | Y |  | OBLIGATED | 17391737 |  | 17391737 | 2011 | 3rd QUARTER | N/A
|  |  | SEE STIP MOD 2010.038 FOR TIP CHANGES. NO CHANGES TO STIP. |  |  | HENDERSON | 2-8304 | EB 9004 |  | 68.25 | 68.75 | RELIABILITY | I-CHANGE RECONST(O) | RECONSTRUCT/COMPLETE THE HALF INTERCHANGE AT EXIT 68 ON THE BREATHITT PARKWAY. (I-69 CORRIDOR IMPROVEMENT)(06CCN)(08CCR) | 2 | D | NHG | 2011 | 360000 | 360000 | ESTIMATED | Y | 2010 |  |  |  | 0
|  |  | SEE STIP MOD 2010.038 FOR TIP CHANGES. NO CHANGES TO STIP. |  |  | HENDERSON | 2-8304 | EB 9004 |  | 68.25 | 68.75 | RELIABILITY | I-CHANGE RECONST(O) | RECONSTRUCT/COMPLETE THE HALF INTERCHANGE AT EXIT 68 ON THE BREATHITT PARKWAY. (I-69 CORRIDOR IMPROVEMENT)(06CCN)(08CCR) | 3 | R | NHG | 2011 | 730000 | 730000 | ESTIMATED | Y |  |  |  |  | 0
|  |  | SEE STIP MOD 2010.038 FOR TIP CHANGES. NO CHANGES TO STIP. |  |  | HENDERSON | 2-8304 | EB 9004 |  | 68.25 | 68.75 | RELIABILITY | I-CHANGE RECONST(O) | RECONSTRUCT/COMPLETE THE HALF INTERCHANGE AT EXIT 68 ON THE BREATHITT PARKWAY. (I-69 CORRIDOR IMPROVEMENT)(06CCN)(08CCR) | 4 | U | NHG | 2011 | 400000 | 400000 | ESTIMATED | Y |  |  |  |  | 0
|  |  | SEE STIP MOD 2010.038 FOR TIP CHANGES. NO CHANGES TO STIP. |  |  | HENDERSON | 2-8304 | EB 9004 |  | 68.25 | 68.75 | RELIABILITY | I-CHANGE RECONST(O) | RECONSTRUCT/COMPLETE THE HALF INTERCHANGE AT EXIT 68 ON THE BREATHITT PARKWAY. (I-69 CORRIDOR IMPROVEMENT)(06CCN)(08CCR) | 5 | C | NH | 2012 | 4680000 | 4680000 | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.162 | 2012-02-13 | MPO RESOLUTION NO. 12-2. ADD PROJECT. NEW |  |  | HENDERSON |  | US 41 |  |  |  | SAFETY | SAFETY | US 41 AT WOLF HILLS ROAD: INTERSECTION IMPROVEMENT PROJECT TO IMPROVE CORNER RADII. |  | PE | SHN | 2012 | 60000 | 60000 |  | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.162 | 2012-02-13 | MPO RESOLUTION NO. 12-2. ADD PROJECT. NEW |  |  | HENDERSON |  | US 41 |  |  |  | SAFETY | SAFETY | US 41 AT WOLF HILLS ROAD: INTERSECTION IMPROVEMENT PROJECT TO IMPROVE CORNER RADII. |  | R | SHN | 2013 | 100000 | 100000 |  | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.162 | 2012-02-13 | MPO RESOLUTION NO. 12-2. ADD PROJECT. NEW |  |  | HENDERSON |  | US 41 |  |  |  | SAFETY | SAFETY | US 41 AT WOLF HILLS ROAD: INTERSECTION IMPROVEMENT PROJECT TO IMPROVE CORNER RADII. |  | U | SHN | 2013 | 100000 | 100000 |  | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.162 | 2012-02-13 | MPO RESOLUTION NO. 12-2. ADD PROJECT. NEW |  |  | HENDERSON |  | US 41 |  |  |  | SAFETY | SAFETY | US 41 AT WOLF HILLS ROAD: INTERSECTION IMPROVEMENT PROJECT TO IMPROVE CORNER RADII. |  | C | SHN | 2016 | 500000 | 500000 |  | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.162 | 2012-02-13 | MPO RESOLUTION NO. 12-2. ADD PROJECT. NEW |  |  | HENDERSON |  | KY 2183 |  |  |  | SAFETY | SAFETY | KY 2183 AT KY 1539: INTERSECTION PROJECT TO IMPROVE SAFETY. |  | PE | SHN | 2012 | 150000 | 150000 |  | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.162 | 2012-02-13 | MPO RESOLUTION NO. 12-2. ADD PROJECT. NEW |  |  | HENDERSON |  | KY 2183 |  |  |  | SAFETY | SAFETY | KY 2183 AT KY 1539: INTERSECTION PROJECT TO IMPROVE SAFETY. |  | R | SHN | 2013 | 400000 | 400000 |  | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.162 | 2012-02-13 | MPO RESOLUTION NO. 12-2. ADD PROJECT. NEW |  |  | HENDERSON |  | KY 2183 |  |  |  | SAFETY | SAFETY | KY 2183 AT KY 1539: INTERSECTION PROJECT TO IMPROVE SAFETY. |  | U | SHN | 2013 | 400000 | 400000 |  | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.162 | 2012-02-13 | MPO RESOLUTION NO. 12-2. ADD PROJECT. NEW |  |  | HENDERSON |  | KY 2183 |  |  |  | SAFETY | SAFETY | KY 2183 AT KY 1539: INTERSECTION PROJECT TO IMPROVE SAFETY. |  | C | SHN | 2014 | 600000 | 600000 |  | Y |  |  |  |  | 0
[6 empty] | HENRY | 5-1031.01 | KY 22 | 0.1 | 22.473 | 22.522 | RELIABILITY | PREFINANCD CONVRSN(P) | REPLACE BRIDGE & APPROACHES OVER KENTUCKY RIVER AT GRATZ ON THE OWEN-HENRY COUNTY LINE (B15).(ADDITIONAL FUNDING FOR C PHASE) AWARDED (10CCN) | 5 | C | BRO | 2011 | 5000000 | 5000000 | REESTIMATED | N |  |  |  |  | 0
|  |  |  | BRO | 5165002 | HENRY | 5-1054 | KY 193 | 0.1 | 2.408 | 2.508 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-193 (MP 2.458) OVER EMILY RUN CREEK; 2.5 MI N. OF JCT US 421; (STRUCTURALLY DEFICIENT, SR=47.4) 052B00007N | 2 | D | BRO | 2011 | 130000 | 130000 | ESTIMATED | N | 2010 | OBLIGATED | 242500 |  | 242500 | 2011 | 1st QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.012 | 2010-11-05 | CHANGE FUNDING AMOUNT. MOD |  |  | HENRY | 5-1054 | KY 193 | 0.1 | 2.408 | 2.508 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-193 (MP 2.458) OVER EMILY RUN CREEK; 2.5 MI N. OF JCT US 421; (STRUCTURALLY DEFICIENT, SR=47.4) 052B00007N | 2 | D | BRO | 2011 | 242500 | 242500 | ESTIMATED | N |  |  |  |  | 0
|  |  |  | BRO | 5165003 | HENRY | 5-1054 | KY 193 | 0.1 | 2.408 | 2.508 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-193 (MP 2.458) OVER EMILY RUN CREEK; 2.5 MI N. OF JCT US 421; (STRUCTURALLY DEFICIENT, SR=47.4) 052B00007N | 3 | R | BRO | 2012 | 100000 | 100000 | ESTIMATED | N |  | OBLIGATED | 17000 |  | 17000 | 2012 | 2nd QUARTER | N/A
[6 empty] | HENRY | 5-1054 | KY 193 | 0.1 | 2.408 | 2.508 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-193 (MP 2.458) OVER EMILY RUN CREEK; 2.5 MI N. OF JCT US 421; (STRUCTURALLY DEFICIENT, SR=47.4) 052B00007N | 4 | U | BRO | 2012 | 30000 | 30000 | ESTIMATED | N |  |  |  |  | 0
|  |  | ADDED PROJECT PER FHWA'S APPROVAL OF PR-1 ON 4/27/12. | BRO | 5165004 | HENRY | 5-1054 | KY 193 | 0.1 | 2.408 | 2.508 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-193 (MP 2.458) OVER EMILY RUN CREEK; 2.5 MI N. OF JCT US 421; (STRUCTURALLY DEFICIENT, SR=47.4) 052B00007N | 4 | C | BRO | 2012 | 468000 | 468000 | ESTIMATED | N |  | OBLIGATED | 605848 |  | 605848 | 2012 | 3RD QUARTER | N/A
[6 empty] | HICKMAN | 1-1007 | CS 1035 | 0.1 | 0.086 | 0.09 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE & APPROACHES AT BRANCH OF CANE CREEK ON WATER ST 300' S OF DEPOT STREET IN CLINTON (C39). (SR=20.3): (053C00039N)(10CCR) | 5 | C | BRZ | 2011 | 440000 | 440000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.088 | 2011-06-15 | INCREASE C PHASE FUNDING AMOUNT. MOD | BRZ | 0103276 | HICKMAN | 1-1007 | CS 1035 | 0.1 | 0.086 | 0.09 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE & APPROACHES AT BRANCH OF CANE CREEK ON WATER ST 300' S OF DEPOT STREET IN CLINTON (C39). (SR=20.3): (053C00039N)(10CCR) | 5 | C | BRZ | 2011 | 480000 | 480000 | ESTIMATED | N |  | OBLIGATED | 480000 |  | 480000 | 2011 | 3rd QUARTER | N/A
[6 empty] | HICKMAN | 1-1018 | KY 307 | 0.2 | 4.582 | 4.847 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE 3 BRIDGES ON KY-307 OVER UNNAMED STREAM 0.95 MI AND 0.84 MI S OF JCT. KY-944 (B15)(B16). (SR=15.4)(INCLUDES R, U & C PHASES FOR B14 SHOWN UNDER 1-1005.00 IN THE 2004 HIGHWAY PLAN): (053B00015N)(10CCR) | 3 | R | BRO | 2011 | 400000 | 400000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | HICKMAN | 1-1018 | KY 307 | 0.2 | 4.582 | 4.847 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE 3 BRIDGES ON KY-307 OVER UNNAMED STREAM 0.95 MI AND 0.84 MI S OF JCT. KY-944 (B15)(B16). (SR=15.4)(INCLUDES R, U & C PHASES FOR B14 SHOWN UNDER 1-1005.00 IN THE 2004 HIGHWAY PLAN): (053B00015N)(10CCR) | 4 | U | BRO | 2011 | 370000 | 370000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | HICKMAN | 1-1018 | KY 307 | 0.2 | 4.582 | 4.847 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE 3 BRIDGES ON KY-307 OVER UNNAMED STREAM 0.95 MI AND 0.84 MI S OF JCT. KY-944 (B15)(B16). (SR=15.4)(INCLUDES R, U & C PHASES FOR B14 SHOWN UNDER 1-1005.00 IN THE 2004 HIGHWAY PLAN): (053B00015N)(10CCR) | 5 | C | BRO | 2011 | 3250000 | 3250000 | ESTIMATED | N |  |  |  |  | 0
|  |  |  | BRZ | 0103298 | HICKMAN | 1-1057 | KY 1037 | 0.1 | 0.466 | 0.496 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-1037 OVER SOUTHERN RAILROAD (RR615) BETWEEN KY-123 AND KY-780. (SR=18.9): (053R00615N) | 3 | R | BRX | 2012 | 150000 | 150000 | ESTIMATED | N |  | OBLIGATED | 150000 |  | 150000 | 2012 | 1st QUARTER | N/A
|  |  |  | BRZ | 0103305 | HICKMAN | 1-1057 | KY 1037 | 0.1 | 0.466 | 0.496 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-1037 OVER SOUTHERN RAILROAD (RR615) BETWEEN KY-123 AND KY-780. (SR=18.9): (053R00615N) | 4 | U | BRX | 2012 | 225000 | 225000 | ESTIMATED | N |  | OBLIGATED | 200000 |  | 200000 | 2012 | 3rd QUARTER | N/A | ``````````````````
[6 empty] | HICKMAN | 1-1057 | KY 1037 | 0.1 | 0.466 | 0.496 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-1037 OVER SOUTHERN RAILROAD (RR615) BETWEEN KY-123 AND KY-780. (SR=18.9) | 5 | C | BRX | 2013 | 1100000 | 1100000 | ESTIMATED | [5 empty] | 0
|  |  |  | BRZ | 0103299 | HICKMAN | 1-1062 | KY 1826 | 0.1 | 4.945 | 4.951 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-1826 OVER TOWN CREEK (B79) IN CLINTON. (SR=24.4): (053B00079N) | 2 | D | BRX | 2011 | 500000 | 500000 | ESTIMATED | N |  | OBLIGATED | 500000 |  | 500000 | 2012 | 2nd QUARTER | N/A
[6 empty] | HOPKINS | 2-137.02 | US 41A | 3.6 | 0 | 3.426 | RELIABILITY | MAJOR WIDENING(O) | US 41A PHASE II DESIGN AND RIGHT-OF-WAY. (2005HPP-KY135)(SEE 2-137.01 FOR "STP" COMPONENT) | 5 | C | HPP | 2011 | 2879680 | 2879680 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | HOPKINS | 2-137.03 | US 41A | 3.6 | 0 | 3.426 | RELIABILITY | MAJOR WIDENING(O) | US HIGHWAY 41A HOPKINS COUNTY, KENTUCKY. (05KYD-KY103)(SEE 2-137.02 FOR 2005HPP COMPONENT) | 5 | C | KYD | 2011 | 983928 | 983928 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.214 | 2012-07-05 | ADD PROJECT TO STIP. NEW |  |  | HOPKINS | 2-225 | I-69 | 0.41 | 106 | 106.41 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE RAMP CONFIGURATION AT THE EXISTING I-69/WESTERN KENTUCKY PARKWAY/PENNYRILE PARKWAY INTERCHANGE (I-69 CORRIDOR IMPROVEMENT)(12CCR) |  | P | IM | 2012 | 1500000 | 1500000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.214 | 2012-07-05 | ADD PROJECT TO STIP. NEW |  |  | HOPKINS | 2-225 | I-69 | 0.41 | 106 | 106.41 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE RAMP CONFIGURATION AT THE EXISTING I-69/WESTERN KENTUCKY PARKWAY/PENNYRILE PARKWAY INTERCHANGE (I-69 CORRIDOR IMPROVEMENT)(12CCR) |  | D | IM | 2012 | 500000 | 500000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.214 | 2012-07-05 | ADD PROJECT TO STIP. NEW |  |  | HOPKINS | 2-225 | I-69 | 0.41 | 106 | 106.41 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE RAMP CONFIGURATION AT THE EXISTING I-69/WESTERN KENTUCKY PARKWAY/PENNYRILE PARKWAY INTERCHANGE (I-69 CORRIDOR IMPROVEMENT)(12CCR) |  | C | IM | 2014 | 10000000 | 10000000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.216 | 2012-07-25 | ADD PROJECT TO STIP. NEW |  |  | HOPKINS | 2-232 | EB 9004 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT ELEMENTS OF EXISTING EDWARD T BREATHITT PKWY (PENNYRILE PARKWAY) BETWEEN MP 37.0 AND MP 73.4 TO UPGRADE GEOMETRICS TO INTERSTATE STANDARDS (I-69 CORRIDOR IMPROVEMENT)(INCLUDED 2-235.00) |  | D | NH | 2012 | 1600000 | 1600000 | [6 empty] | 0
[6 empty] | HOPKINS | 2-1067 | CR 1092 | 0.1 | 1.857 | 1.873 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON CR-1092 OVER CSX RAILROAD (C04). (SR=48.9): (054C00004N) | 5 | C | BRZ | 2011 | 2350000 | 2350000 | ESTIMATED | N |  |  |  |  | 0
|  |  |  | BRZ | 0203301 | HOPKINS | 2-1070 | KY 502 | 0.1 | 3.231 | 3.261 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-502 OVER CLEAR CREEK 1.58 MILES SOUTH OF JOHN LANSDEN ROAD (B125) (SR=25.4): (054B00125N) | 2 | D | BRX | 2011 | 225000 | 225000 | ESTIMATED | N | 2010 | OBLIGATED | 225000 |  | 225000 | 2011 | 2nd QUARTER | N/A
[6 empty] | HOPKINS | 2-1070 | KY 502 | 0.1 | 3.231 | 3.261 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-502 OVER CLEAR CREEK 1.58 MILES SOUTH OF JOHN LANSDEN ROAD (B125) (SR=25.4). | 3 | R | BRX | 2013 | 75000 | 75000 | ESTIMATED | [5 empty] | 0
[6 empty] | HOPKINS | 2-1070 | KY 502 | 0.1 | 3.231 | 3.261 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-502 OVER CLEAR CREEK 1.58 MILES SOUTH OF JOHN LANSDEN ROAD (B125) (SR=25.4). | 4 | U | BRX | 2013 | 25000 | 25000 | ESTIMATED | [5 empty] | 0
[6 empty] | HOPKINS | 2-1070 | KY 502 | 0.1 | 3.231 | 3.261 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-502 OVER CLEAR CREEK 1.58 MILES SOUTH OF JOHN LANSDEN ROAD (B125) (SR=25.4). | 5 | C | BRX | 2014 | 1000000 | 1000000 | ESTIMATED | [5 empty] | 0
|  |  |  | BRZ | 0203303 | HOPKINS | 2-1072 | KY 260 | 0.1 | 2.09 | 2.19 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-260 (MP 2.14) OVER OTTER CREEK; .20 MI EAST OF PENNYRILE PARKWAY; (FUNCTIONALLY OBSOLETE, SR=49.9) 054B00022N | 2 | D | BRX | 2012 | 140000 | 140000 | ESTIMATED | N |  | OBLIGATED | 140000 |  | 140000 | 2012 | 2nd QUARTER | N/A
[6 empty] | HOPKINS | 2-2055 | EB 9004 |  | 36.7 | 37.2 | RELIABILITY | I-CHANGE RECONST(O) | UPGRADE MORTON'S GAP INTERCHANGE (MP 37.07) TO INTERSTATE STANDARDS. (I-69 CORRIDOR IMPROVEMENT) | 2 | D | NH | 2012 | 1000000 | 1000000 | REESTIMATED | [5 empty] | 0
|  |  |  | NH | 0021032 | HOPKINS | 2-8500 | WK 9001 |  | 24.3 | 24.5 | RELIABILITY | I-CHANGE RECONST(O) | WESTERN KENTUCKY PARKWAY/KY109 INTERCHANGE IMPROVEMENTS. (I-69 CORRIDOR IMPROVEMENT) (08CCN) | 3 | R | NHG | 2011 | 500000 | 500000 | ESTIMATED | N |  | OBLIGATED | 500000 |  | 500000 | 2012 | 2nd QUARTER | N/A
|  |  |  | NH | 0021033 | HOPKINS | 2-8500 | WK 9001 |  | 24.3 | 24.5 | RELIABILITY | I-CHANGE RECONST(O) | WESTERN KENTUCKY PARKWAY/KY109 INTERCHANGE IMPROVEMENTS. (I-69 CORRIDOR IMPROVEMENT) (08CCN) | 4 | U | NHG | 2011 | 300000 | 300000 | ESTIMATED | N |  | OBLIGATED | 520000 |  | 520000 | 2012 | 2nd QUARTER | N/A
[6 empty] | HOPKINS | 2-8500 | WK 9001 |  | 24.3 | 24.5 | RELIABILITY | I-CHANGE RECONST(O) | WESTERN KENTUCKY PARKWAY/KY109 INTERCHANGE IMPROVEMENTS. (I-69 CORRIDOR IMPROVEMENT) (08CCN) | 5 | C | NHG | 2012 | 4500000 | 4500000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | HOPKINS | 2-8501 | US 62 | 0.521 | 0.829 | 1.35 | RELIABILITY | MINOR WIDENING(O) | US-62; THREE LANES FROM BOARD OF EDUCATION TO CITY PARK IN DAWSON SPRINGS. (08CCN)(10CCR) | 3 | R | STP | 2011 | 500000 | 500000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | HOPKINS | 2-8501 | US 62 | 0.521 | 0.829 | 1.35 | RELIABILITY | MINOR WIDENING(O) | US-62; THREE LANES FROM BOARD OF EDUCATION TO CITY PARK IN DAWSON SPRINGS. (08CCN)(10CCR) | 4 | U | STP | 2011 | 500000 | 500000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | HOPKINS | 2-8501 | US 62 | 0.521 | 0.829 | 1.35 | RELIABILITY | MINOR WIDENING(O) | US-62; THREE LANES FROM BOARD OF EDUCATION TO CITY PARK IN DAWSON SPRINGS. (08CCN)(10CCR) | 5 | C | STP | 2012 | 1500000 | 1500000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.002 | 2010-10-01 | THIS PROJECT IS THE SAME AS 2-2055 IN THE STIP. KYTC WILL USE THE D PHASE NH FUNDS DESIGNATED FOR 2-2055 TO FUND THE D PHASE FOR 2-8633. NEW | NH | 9004021 | HOPKINS | 2-8633 | EB 9004 |  | 36.7 | 37.2 | RELIABILITY | I-CHANGE RECONST(O) | UPGRADE MORTON'S GAP INTERCHANGE (MP 37.07) TO INTERSTATE STANDARDS. (I-69 CORRIDOR IMPROVEMENT) |  | D | NH | 2011 | 1000000 | 1000000 |  |  |  | OBLIGATED | 1000000 |  | 1000000 | 2011 | 1st QUARTER | N/A
[6 empty] | JEFFERSON | 5-21 | I 265 | 0.3 | 25.3 | 25.6 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | SNYDER FREEWAY; RECONSTRUCT 2 RAMPS AT I-265/I-64 INTERCHANGE EAST OF LOUISVILLE. (DESIGNED WITH 5-41.00)(2006BOPP) | 3 | R | IM | 2011 | 3150000 | 3150000 | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.111 | 2011-08-26 | KIPDA MOD #9. KIPDA ID 179. ADDING PROJECT TO TIP. ALREADY IN STIP WITH CORRECT INFORMATION. |  |  | JEFFERSON | 5-21 | I 265 | 0.3 | 25.3 | 25.6 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | RECONSTRUCT I-265 (GENE SNYDER FREEWAY) INTERCHANGE AT I-64, INCLUDING: NB TO WB 2 LANE FLYOVER, SB TO WB 2 LANE RAMP, AND AUXILIARY LANE TO TIE INTO KIPDA #197; ALSO INCLUDES WB AUXILIARY LANE ON I-64 FROM I-265 TO BLANKENBAKER PKWY. | 3 | R | IM | 2011 | 3150000 | 3150000 | ESTIMATED | Y |  |  |  |  | 0
[6 empty] | JEFFERSON | 5-21 | I 265 | 0.3 | 25.3 | 25.6 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | SNYDER FREEWAY; RECONSTRUCT 2 RAMPS AT I-265/I-64 INTERCHANGE EAST OF LOUISVILLE. (DESIGNED WITH 5-41.00)(2006BOPP) | 4 | U | IM | 2012 | 2170000 | 2170000 | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.111 | 2011-08-26 | KIPDA MOD #9. KIPDA ID 179. ADDING PROJECT TO TIP. ALREADY IN STIP WITH CORRECT INFORMATION. |  |  | JEFFERSON | 5-21 | I 265 | 0.3 | 25.3 | 25.6 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | RECONSTRUCT I-265 (GENE SNYDER FREEWAY) INTERCHANGE AT I-64, INCLUDING: NB TO WB 2 LANE FLYOVER, SB TO WB 2 LANE RAMP, AND AUXILIARY LANE TO TIE INTO KIPDA #197; ALSO INCLUDES WB AUXILIARY LANE ON I-64 FROM I-265 TO BLANKENBAKER PKWY. | 3 | U | IM | 2011 | 2170000 | 2170000 | ESTIMATED | Y |  |  |  |  | 0
[6 empty] | JEFFERSON | 5-21 | I 265 | 0.3 | 25.3 | 25.6 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | SNYDER FREEWAY; RECONSTRUCT 2 RAMPS AT I-265/I-64 INTERCHANGE EAST OF LOUISVILLE. (DESIGNED WITH 5-41.00)(2006BOPP) | 5 | C | IM | 2013 | 25000000 | 25000000 | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.111 | 2011-08-26 | KIPDA MOD #9. KIPDA ID 179. ADDING PROJECT TO TIP. ALREADY IN STIP WITH CORRECT INFORMATION. |  |  | JEFFERSON | 5-21 | I 265 | 0.3 | 25.3 | 25.6 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | RECONSTRUCT I-265 (GENE SNYDER FREEWAY) INTERCHANGE AT I-64, INCLUDING: NB TO WB 2 LANE FLYOVER, SB TO WB 2 LANE RAMP, AND AUXILIARY LANE TO TIE INTO KIPDA #197; ALSO INCLUDES WB AUXILIARY LANE ON I-64 FROM I-265 TO BLANKENBAKER PKWY. | 3 | C | IM | 2011 | 25000000 | 25000000 | ESTIMATED | Y |  |  |  |  | 0
[6 empty] | JEFFERSON | 5-21.03 | I 265 | 0.3 | 25.3 | 25.6 | RELIABILITY | PREFINANCD CONVRSN(O) | SNYDER FREEWAY; RECONSTRUCT 2 RAMPS AT I-265/I-64 INTERCHANGE EAST OF LOUISVILLE. (ADDITIONAL FUNDING FOR C PHASE) | 5 | C | IM | 2013 | 15000000 | 15000000 | REESTIMATED | Y |  |  |  |  | 0
[6 empty] | JEFFERSON | 5-21.04 | I 265 | 0.3 | 25.3 | 25.6 | RELIABILITY | PREFINANCD CONVRSN(O) | SNYDER FREEWAY; RECONSTRUCT 2 RAMPS AT I-265/I-64 INTERCHANGE EAST OF LOUISVILLE. (ADDITIONAL FUNDING FOR C PHASE) | 5 | C | IM | 2014 | 12000000 | 12000000 | ESTIMATED | Y |  |  |  |  | 0
[6 empty] | JEFFERSON | 5-41 | I 265 | 0.3 | 26.645 | 26.945 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | SNYDER FREEWAY; RECONSTRUCT I-265/US-60 INTERCHANGE TO ENHANCE CAPACITY AND SAFETY (DESIGNED WITH 5-21.00); ALT. 1 IMPROVEMENTS ON SOUTH SIDE. (2006BOPP) | 3 | R | IM | 2011 | 110000 | 110000 | ESTIMATED | Y | 2010 |  |  |  | 0
|  |  |  | IM | 2653031 | JEFFERSON | 5-41 | I 265 | 0.3 | 26.645 | 26.945 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | SNYDER FREEWAY; RECONSTRUCT I-265/US-60 INTERCHANGE TO ENHANCE CAPACITY AND SAFETY (DESIGNED WITH 5-21.00); ALT. 1 IMPROVEMENTS ON SOUTH SIDE. (2006BOPP) | 4 | U | IM | 2011 | 370000 | 370000 | ESTIMATED | Y | 2010 | OBLIGATED | 185000 |  | 185000 | 2011 | 1st QUARTER | N/A
|  |  |  | IM | 2653032 | JEFFERSON | 5-41 | I 265 | 0.3 | 26.645 | 26.945 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | SNYDER FREEWAY; RECONSTRUCT I-265/US-60 INTERCHANGE TO ENHANCE CAPACITY AND SAFETY (DESIGNED WITH 5-21.00); ALT. 1 IMPROVEMENTS ON SOUTH SIDE. (2006BOPP) | 5 | C | IM | 2011 | 3680000 | 3680000 | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.095 | 2011-07-05 | KIPDA TIP AMENDMENT #1. KIPDA ID #197. INCREASE C PHASE AMOUNT. MOD | IM | 2653032 | JEFFERSON | 5-41 | I 265 | 0.3 | 26.645 | 26.945 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | RECONSTRUCT I-265 (GENE SNYDER FREEWAY) INTERCHANGE AT US 60 (SHELBYVILLE ROAD). AUXILIARY LANES WILL BE ADDED TO NB AND SB I-265 FROM THE US 60 INTERCHANGE SOUTH TO REDUCE CONGESTION AND IMPROVE SAFETY. LANES WILL BE ADDED AT THE BASE OF THE EXIT RAMPS. | 5 | C | IM | 2011 | 6610000 | 6610000 | ESTIMATED | Y |  | OBLIGATED | 8383322.5 |  | 8383322.5 | 2011 | 2nd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.104 | 2011-08-10 | ALREADY IN TIP ON PAGE 13 OF 71. ADD PHASE TO STIP. NEW | NH | 0711102 | JEFFERSON | 5-48.2 | I 71 | 2.2 | 3.6 | 5.8 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT I-71/I-264 INTERCHANGE INCLUDING THE ADDITION OF NORTH AND SOUTHBOUND AUXILIARY LANES ON I-71 AND I-264. PROJECT LENGTH IS 2.2 MILES. | 5 | U | NH | 2011 | 715000 | 715000 | ESTIMATED | Y |  | OBLIGATED | 715000 |  | 715000 | 2011 | 4th QUARTER | N/A
[6 empty] | JEFFERSON | 5-48.2 | I 71 | 2.2 | 3.6 | 5.8 | RELIABILITY | RECONSTRUCTION(O) | INTERIM IMPROVEMENTS ON I-71 INCLUDING ADDITION OF NB AND SB AUXILIARY LANES ON I-71 AND I-264. (2004BOPC)(10CCR) | 5 | C | NH | 2012 | 5000000 | 5000000 | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.163 | 2012-02-13 | TIP AMENDMENT #3. KIPDA ID 1479. ADDING PHASE TO TIP. NO CHANGE TO STIP. | NH | 0711104 | JEFFERSON | 5-48.2 | I 71 | 2.2 | 3.6 | 5.8 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT I-71/I-264 INTERCHANGE INCLUDING THE ADDITION OF NORTH AND SOUTHBOUND AUXILIARY LANES ON I-71 AND I-264. PROJECT LENGTH IS 2.2 MILES. | 5 | C | NH | 2012 | 5000000 | 5000000 | ESTIMATED | Y |  | OBLIGATED | 5060000 |  | 5060000 | 2012 | 3RD QUARTER | N/A
[6 empty] | JEFFERSON | 5-48.3 | I 71 | 2.3 | 7.5 | 9.8 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCTION OF THE I-71/I-265 (SNYDER FREEWAY) INTERCHANGE (INTERIM IMPROVEMENTS). (2004BOPC)(08CCR)(10CCR) | 2 | D | NH | 2012 | 500000 | 500000 | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.083 | 2011-06-06 | TIP MOD #6. KIPDA ID 1480. ADDING THIS D PHASE TO TIP. NO CHANGE TO STIP. | NH | 0711103 | JEFFERSON | 5-48.3 | I 71 | 2.3 | 7.5 | 9.8 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCTION OF THE I-71/I-265 (GENE SNYDER FREEWAY) INTERCHANGE INCLUDING A POSSIBLE FLYOVER RAMP FROM I-265 NORTHBOUND TO I-71 SOUTHBOUND. | 2 | D | NH | 2012 | 500000 | 500000 | ESTIMATED | Y |  | OBLIGATED | 500000 |  | 500000 | 2012 | 3RD QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.163 | 2012-02-13 | KIPDA ID 1804. ADD DESIGN PHASE. NEW |  |  | JEFFERSON | 5-52 | I 64 | 0.2 | 14.894 | 15.094 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | RECONSTRUCT I-64/HURSTBOURNE PARKWAY INTERCHANGE AND RAMPS AND OTHER NEEDED IMPROVEMENTS TO HURSTBOURNE PARKWAY.(08CCR) | 5 | D | IM | 2011 | 1800000 | 1800000 | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.109 | 2011-08-26 | PROJECT ALREADY IN FY 2011-2015 TIP. ADD PHASE TO STIP. NEW |  |  | JEFFERSON | 5-52 | I 64 | 0.2 | 14.894 | 15.094 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | RECONSTRUCT I-64/HURSTBOURNE PARKWAY INTERCHANGE AND RAMPS AND OTHER NEEDED IMPROVEMENTS TO HURSTBOURNE PARKWAY.(08CCR) | 5 | R | IM | 2011 | 2210000 | 2210000 | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.163 | 2012-02-13 | KIPDA ID 1804. REDUCE FUNDING AMOUNT. MOD | IM | 0642175 | JEFFERSON | 5-52 | I 64 | 0.2 | 14.894 | 15.094 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | RECONSTRUCT I-64/HURSTBOURNE PARKWAY INTERCHANGE AND RAMPS AND OTHER NEEDED IMPROVEMENTS TO HURSTBOURNE PARKWAY.(08CCR) | 5 | R | IM | 2011 | 118000 | 118000 | ESTIMATED | Y |  | OBLIGATED | 118000 |  | 118000 | 2011 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.109 | 2011-08-26 | PROJECT ALREADY IN FY 2011-2015 TIP. ADD PHASE TO STIP. NEW |  |  | JEFFERSON | 5-52 | I 64 | 0.2 | 14.894 | 15.094 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | RECONSTRUCT I-64/HURSTBOURNE PARKWAY INTERCHANGE AND RAMPS AND OTHER NEEDED IMPROVEMENTS TO HURSTBOURNE PARKWAY.(08CCR) | 5 | U | IM | 2011 | 5410000 | 5410000 | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.163 | 2012-02-13 | KIPDA ID 1804. REDUCE FUNDING AMOUNT. MOD | IM | 0642176 | JEFFERSON | 5-52 | I 64 | 0.2 | 14.894 | 15.094 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | RECONSTRUCT I-64/HURSTBOURNE PARKWAY INTERCHANGE AND RAMPS AND OTHER NEEDED IMPROVEMENTS TO HURSTBOURNE PARKWAY.(08CCR) | 5 | U | IM | 2011 | 2015000 | 2015000 | ESTIMATED | Y |  | OBLIGATED | 2015000 |  | 2015000 | 2011 | 4th QUARTER | N/A
[6 empty] | JEFFERSON | 5-52 | I 64 | 0.2 | 14.894 | 15.094 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | RECONSTRUCT I-64/HURSTBOURNE PARKWAY INTERCHANGE AND RAMPS AND OTHER NEEDED IMPROVEMENTS TO HURSTBOURNE PARKWAY.(08CCR) | 5 | C | IM | 2011 | 10000000 | 10000000 | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.163 | 2012-02-13 | KIPDA ID 1804. REDUCE FUNDING AMOUNT. MOD | IM | 0642178 | JEFFERSON | 5-52 | I 64 | 0.2 | 14.894 | 15.094 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | RECONSTRUCT I-64/HURSTBOURNE PARKWAY INTERCHANGE AND RAMPS AND OTHER NEEDED IMPROVEMENTS TO HURSTBOURNE PARKWAY.(08CCR) | 5 | C | IM | 2011 | 6067000 | 6067000 | ESTIMATED | Y |  | OBLIGATED | 2948000 |  | 2948000 | 2012 | 3RD QUARTER | N/A
[6 empty] | JEFFERSON | 5-63 | I 64 | 0.3 | 0 | 0.316 | SAFETY | BRIDGE INSPECTION(P) | I-64 BRIDGE (SHERMAN MINTON) OVER OHIO RIVER @ LOUISVILLE (B279); JOINT PROJECT WITH INDIANA TO PERFORM IN-DEPTH INSPECTION. (056B00279N) | 5 | C | IM | 2011 | 160000 | 160000 | ESTIMATED | Y | 2010 |  |  |  | 0
[6 empty] | JEFFERSON | 5-64 | I 64 | 0.3 | 0 | 0.316 | RELIABILITY | BRIDGE PAINTING(P) | I-64 BRIDGE (SHERMAN MINTON) OVER THE OHIO RIVER @ LOUISVILLE (B279); JOINT PROJECT WITH INDIANA TO PAINT THIS BRIDGE. | 5 | C | IM | 2013 | 4160000 | 4160000 | ESTIMATED | Y |  |  |  |  | 0
[6 empty] | JEFFERSON | 5-91.02 | CS 1001B | 1.5 | 1.6 | 2.925 | RELIABILITY | MAJOR WIDENING(O) | WIDEN FROM 2 TO 4 LANES FROM BEARGRASS CREEK TO ZORN AVENUE. (LOU T.I.P.) (KYTC MATCH) (SEE 5-91.07 FOR ADDITIONAL 'KYD' FUNDING FOR R PHASE.) (SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | 3 | R | SLO | 2011 | 5430000 | 5430000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.148 | 2011-12-01 | TIP MOD #12. KIPDA ID 163. MOVE FY TO FY 2012. MOD |  |  | JEFFERSON | 5-91.02 | CS 1001B | 1.3 |  |  | RELIABILITY | MAJOR WIDENING(O) | WIDEN RIVER ROAD FROM 2 TO 4 LANES FROM EAST OF BEARGRASS CREEK NEAR POPE AVENUE TO ZORN AVENUE. TO INCLUDE BIKE LANES. PROJECT LENGTH IS 1.3 MILES. | 5 | R | SLO | 2012 | 5430000 | 5430000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | JEFFERSON | 5-91.02 | CS 1001B | 1.5 | 1.6 | 2.925 | RELIABILITY | MAJOR WIDENING(O) | WIDEN FROM 2 TO 4 LANES FROM BEARGRASS CREEK TO ZORN AVENUE. (LOU T.I.P.) (KYTC MATCH) (SEE 5-91.07 FOR ADDITIONAL 'KYD' FUNDING FOR R PHASE.) (SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | 4 | U | SLO | 2011 | 5700000 | 5700000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.148 | 2011-12-01 | TIP MOD #12. KIPDA ID 163. MOVE FY TO FY 2012. MOD |  |  | JEFFERSON | 5-91.02 | CS 1001B | 1.3 |  |  | RELIABILITY | MAJOR WIDENING(O) | WIDEN RIVER ROAD FROM 2 TO 4 LANES FROM EAST OF BEARGRASS CREEK NEAR POPE AVENUE TO ZORN AVENUE. TO INCLUDE BIKE LANES. PROJECT LENGTH IS 1.3 MILES. | 5 | U | SLO | 2012 | 5700000 | 5700000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | JEFFERSON | 5-91.02 | CS 1001B | 1.5 | 1.6 | 2.925 | RELIABILITY | MAJOR WIDENING(O) | WIDEN FROM 2 TO 4 LANES FROM BEARGRASS CREEK TO ZORN AVENUE. (LOU T.I.P.) (KYTC MATCH) (SEE 5-91.07 FOR ADDITIONAL 'KYD' FUNDING FOR R PHASE.) (SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | 5 | C | SLO | 2012 | 11190000 | 11190000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.074 | 2011-05-05 | TIP MOD #5. KIPDA ID 163. INCREASE FUNDING AMOUNT IN STIP. MOD |  |  | JEFFERSON | 5-91.02 | CS 1001B | 1.3 |  |  | RELIABILITY | MAJOR WIDENING(O) | WIDEN RIVER ROAD FROM 2 TO 4 LANES FROM EAST OF BEARGRASS CREEK NEAR POPE AVENUE TO ZORN AVENUE. TO INCLUDE BIKE LANES. PROJECT LENGTH IS 1.3 MILES. | 5 | C | SLO | 2012 | 16700000 | 16700000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.148 | 2011-12-01 | TIP MOD #12. KIPDA ID 163. MOVE FY TO FY 2013. MOD |  |  | JEFFERSON | 5-91.02 | CS 1001B | 1.3 |  |  | RELIABILITY | MAJOR WIDENING(O) | WIDEN RIVER ROAD FROM 2 TO 4 LANES FROM EAST OF BEARGRASS CREEK NEAR POPE AVENUE TO ZORN AVENUE. TO INCLUDE BIKE LANES. PROJECT LENGTH IS 1.3 MILES. | 5 | C | SLO | 2013 | 16700000 | 16700000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.185 | 2012-05-09 | KIPDA TIP MOD #16. CHANGE PROJECT SPONSOR FROM KYTC TO LOUISVILLE METRO PUBLIC WORKS |  |  | JEFFERSON | 5-91.02 | CS 1001B | 1.3 |  |  | RELIABILITY | MAJOR WIDENING(O) | WIDEN RIVER ROAD FROM 2 TO 4 LANES FROM EAST OF BEARGRASS CREEK NEAR POPE AVENUE TO ZORN AVENUE. TO INCLUDE BIKE LANES. PROJECT LENGTH IS 1.3 MILES. | 5 | C | SLO | 2013 | 16700000 | 16700000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.111 | 2011-08-26 | TIP MOD #9. KIPDA ID 275. ADD TO STIP. NEW |  |  | JEFFERSON | 5-105 | US 60A | [5 empty] | RE-CURB US 60A (EASTERN PARKWAY) FROM KY 1631 (CRITTENDEN DRIVE) TO US 31E (BARDSTOWN ROAD). APPROXIMATELY 2.9 MILES. |  | D | SLO | 2011 | 500000 | 400000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.127 | 2011-09-29 | TIP MOD #10. KIPDA ID 275. MOVE FY 2011 DESIGN TO FY 2012. MOD |  |  | JEFFERSON | 5-105 | US 60A | [5 empty] | RE-CURB US 60A (EASTERN PARKWAY) FROM KY 1631 (CRITTENDEN DRIVE) TO US 31E (BARDSTOWN ROAD). APPROXIMATELY 2.9 MILES. |  | D | SLO | 2012 | 500000 | 400000 | [6 empty] | 0
[6 empty] | JEFFERSON | 5-159.1 | I 64 | 0.4 | 0.502 | 0.779 | RELIABILITY | RECONSTRUCTION(O) | PRIORITY SECTION - ADD AUXILIARY LANE ON I-64 WB AS IT APPROACHES I-264. (2006BOPC)(10CCR) | 4 | U | IM | 2011 | 500000 | 500000 | NOT REQUIRED | Y | 2010 |  |  |  | 0
[6 empty] | JEFFERSON | 5-205 | I 65 |  | 0 | 0.621 | SAFETY | SAFETY(P) | RECONSTRUCT SECOND CURVE ONLY ON I-65 SOUTHBOUND RAMP AT KY-1065 (OUTER LOOP). | 5 | C | IM | 2011 | 1820000 | 1820000 | ESTIMATED | Y | 2010 |  |  |  | 0
[6 empty] | JEFFERSON | 5-263 | I 265 | 0.7 | 11.3 | 12 | SAFETY | SAFETY(P) | IMPROVE I-265/KY-61 (PRESTON HWY) INTERCHANGE AS RECOMMENDED BY KIPDA'S INTERCHANGE STUDY. | 5 | C | IM | 2011 | 2640000 | 2640000 | ESTIMATED | Y | 2010 |  |  |  | 0
[6 empty] | JEFFERSON | 5-264 | I 265 | 0.8 | 16.9 | 17.7 | SAFETY | SAFETY(P) | IMPROVE I-265/US-31E (BARDSTOWN RD) INTERCHANGE AS RECOMMENDED BY KIPDA'S INTERCHANGE STUDY. | 5 | C | IM | 2011 | 1560000 | 1560000 | ESTIMATED | Y | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.095 | 2011-07-05 | KIPDA TIP AMENDMENT #1. KIPDA ID #1483. CHANGE DESCRIPTION AND CHANGE C PHASE FY AND NCREASE C PHASE AMOUNT. MOD | IM | 2652024 | JEFFERSON | 5-264 | I 265 | 0.8 | 16.9 | 17.7 | SAFETY | SAFETY(P) | IMPROVE I-265/US-31E (BARDSTOWN RD) INTERCHANGE AS RECOMMENDED BY KIPDA'S INTERCHANGE STUDY INCLUDING THE ADDITION OF 1 SOUTHBOUND LANE ON BARDSTOWN ROAD FROM THE KROGER DRIVEWAY TO THE I-265 WESTBOUND ON-RAMP. | 5 | C | IM | 2011 | 1560000 | 1560000 | ESTIMATED | Y | 2010 | OBLIGATED | 1954812 |  | 1954812 | 2011 | 3rd QUARTER | N/A
[6 empty] | JEFFERSON | 5-264.1 | US 31E |  | 4.5 | 4.926 | SAFETY | SAFETY(P) | IMPROVE US 31-E SOUTH OF I-265 (BARDSTOWN ROAD)INTERCHANGE TO PROVIDE TURN LANES AND NEW ACCESS.(10CCR) | 3 | R | NH | 2011 | 25000 | 25000 | ESTIMATED | Y | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.095 | 2011-07-05 | KIPDA TIP AMENDMENT #1. ADD TO TIP. CHANGE FUND CODE IN STIP. MOD |  |  | JEFFERSON | 5-264.1 | US 31E |  | 4.5 | 4.926 | SAFETY | SAFETY(P) | IMPROVE US 31-E SOUTH OF I-265 (BARDSTOWN ROAD)INTERCHANGE TO PROVIDE TURN LANES AND NEW ACCESS. | 3 | R | IM | 2011 | 25000 | 25000 | ESTIMATED | Y | 2010 |  |  |  | 0
[6 empty] | JEFFERSON | 5-264.1 | US 31E |  | 4.5 | 4.926 | SAFETY | SAFETY(P) | IMPROVE US 31-E SOUTH OF I-265 (BARDSTOWN ROAD)INTERCHANGE TO PROVIDE TURN LANES AND NEW ACCESS.(10CCR) | 4 | U | NH | 2011 | 100000 | 100000 | ESTIMATED | Y | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.095 | 2011-07-05 | KIPDA TIP AMENDMENT #1. ADD TO TIP. CHANGE FUND CODE IN STIP. MOD |  |  | JEFFERSON | 5-264.1 | US 31E |  | 4.5 | 4.926 | SAFETY | SAFETY(P) | IMPROVE US 31-E SOUTH OF I-265 (BARDSTOWN ROAD)INTERCHANGE TO PROVIDE TURN LANES AND NEW ACCESS. | 4 | U | IM | 2011 | 100000 | 100000 | ESTIMATED | Y | 2010 |  |  |  | 0
[6 empty] | JEFFERSON | 5-264.1 | US 31E |  | 4.5 | 4.926 | SAFETY | SAFETY(P) | IMPROVE US 31-E SOUTH OF I-265 (BARDSTOWN ROAD)INTERCHANGE TO PROVIDE TURN LANES AND NEW ACCESS.(10CCR) | 5 | C | NH | 2011 | 2400000 | 2400000 | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.095 | 2011-07-05 | KIPDA TIP AMENDMENT #1. ADD TO TIP. CHANGE FUND CODE IN STIP. MOD |  |  | JEFFERSON | 5-264.1 | US 31E |  | 4.5 | 4.926 | SAFETY | SAFETY(P) | IMPROVE US 31-E SOUTH OF I-265 (BARDSTOWN ROAD)INTERCHANGE TO PROVIDE TURN LANES AND NEW ACCESS. | 5 | C | IM | 2011 | 2400000 | 2400000 | ESTIMATED | Y |  |  |  |  | 0
|  |  | ADDED TO STIP PER APPROVED PR-1 BY FHWA ON 11/14/11 | STP | 8411047 | JEFFERSON | 5-284 | KY 841 | 0.8 | 2.7 | 3.5 | SAFETY | SAFETY(P) | IMPROVE KY-841/STONESTREET ROAD INTERCHANGE AS RECOMMENDED BY KIPDA'S INTERCHANGE STUDY. | 5 | D | STP | 2011 | 150000 | 150000 | ESTIMATED | Y | 2010 | OBLIGATED | 150000 |  | 150000 | 2012 | 1st QUARTER | N/A
[6 empty] | JEFFERSON | 5-284 | KY 841 | 0.8 | 2.7 | 3.5 | SAFETY | SAFETY(P) | IMPROVE KY-841/STONESTREET ROAD INTERCHANGE AS RECOMMENDED BY KIPDA'S INTERCHANGE STUDY. | 5 | C | STP | 2011 | 360000 | 360000 | ESTIMATED | Y | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.163 | 2012-02-13 | KIPDA TIP AMENDMENT #3. KIPDA ID 1467. CHANGE DESCRIPTION AND REDUCE FUNDING AMOUNT. MOD |  |  | JEFFERSON | 5-284 | KY 841 | 0.8 | 2.7 | 3.5 | SAFETY | SAFETY(P) | IMPROVE KY-841/STONESTREET ROAD INTERCHANGE AS RECOMMENDED BY KIPDA'S INTERCHANGE STUDY. (INCLUDES ADDITIONAL NB LANE NORTH OF INTERCHANGE). | 5 | C | STP | 2011 | 300000 | 300000 | ESTIMATED | Y | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.006 ALSO 2010.031 | 10/13/2010 1/18/11 | TIP MOD #31. KIPDA ID 1476. ADD D PHASE, NEW TIP MOD #1 HAD SAME INFO | IM | 0642170 | JEFFERSON | 5-286 | I 64 | 0.7 | 16.8 | 17.55 | SAFETY | SAFETY(P) | IMPROVE I-64/KY-913 (BLANKENBAKER PARKWAY) INTERCHANGE AS RECOMMENDED BY KIPDA'S INTERCHANGE STUDY, INCLUDING THE ADDITION OF 1 NORTHBOUND LANE ON BLANKENBAKER PARKWAY FROM BLUEGRASS PARKWAY TO THE I-64 EASTBOUND ON-RAMP. | 5 | D | IM | 2011 | 250000 | 250000 | ESTIMATED | Y |  | OBLIGATED | 250000 |  | 250000 | 2011 | 1st QUARTER | N/A
[6 empty] | JEFFERSON | 5-286 | I 64 | 0.7 | 16.8 | 17.55 | SAFETY | SAFETY(P) | IMPROVE I-64/KY-913 (BLANKENBAKER RD) INTERCHANGE AS RECOMMENDED BY KIPDA'S INTERCHANGE STUDY. | 5 | C | IM | 2011 | 1920000 | 1920000 | ESTIMATED | Y | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.006 ALSO 2010.031 | 10/13/2010 1/18/11 | TIP MOD #31. KIPDA ID 1476. REDUCE C PHASE, AND CHANGE DESCRIPTION. MOD TIP MOD #1 HAD SAME INFO |  |  | JEFFERSON | 5-286 | I 64 | 0.7 | 16.8 | 17.55 | SAFETY | SAFETY(P) | IMPROVE I-64/KY-913 (BLANKENBAKER PARKWAY) INTERCHANGE AS RECOMMENDED BY KIPDA'S INTERCHANGE STUDY, INCLUDING THE ADDITION OF 1 NORTHBOUND LANE ON BLANKENBAKER PARKWAY FROM BLUEGRASS PARKWAY TO THE I-64 EASTBOUND ON-RAMP. | 5 | C | IM | 2011 | 1670000 | 1670000 | ESTIMATED | Y |  |  |  |  | 0
[6 empty] | JEFFERSON | 5-353 | CR 1006C | 0.85 | 0.773 | 1.236 | RELIABILITY | MINOR WIDENING(O) | ENGLISH STATION ROAD IN LOUISVILLE; WIDEN TO 3 LANES FROM AVOCA ROAD TO AIKEN ROAD. (SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | 3 | R | SLO | 2011 | 2425500 | 2425500 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.074 | 2011-05-05 | TIP MOD #5. KIPDA ID 188. MOVE ROW TO FY 2012. MOD |  |  | JEFFERSON | 5-353 | CR 1006C | 0.85 | 0.773 | 1.236 | RELIABILITY | MINOR WIDENING(O) | WIDEN ENGLISH STATION ROAD FROM 2 TO 3 LANES (3RD LANE WILL BE A CENTER TURN LANE) FROM AIKEN ROAD TO AVOCA ROAD. | 3 | R | SLO | 2012 | 2425500 | 2425500 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | JEFFERSON | 5-353 | CR 1006C | 0.85 | 0.773 | 1.236 | RELIABILITY | MINOR WIDENING(O) | ENGLISH STATION ROAD IN LOUISVILLE; WIDEN TO 3 LANES FROM AVOCA ROAD TO AIKEN ROAD. (SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | 4 | U | SLO | 2011 | 247470 | 247470 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.074 | 2011-05-05 | TIP MOD #5. KIPDA ID 188. MOVE UTILITIES TO FY 2013. MOD |  |  | JEFFERSON | 5-353 | CR 1006C | 0.85 | 0.773 | 1.236 | RELIABILITY | MINOR WIDENING(O) | WIDEN ENGLISH STATION ROAD FROM 2 TO 3 LANES (3RD LANE WILL BE A CENTER TURN LANE) FROM AIKEN ROAD TO AVOCA ROAD. | 3 | U | SLO | 2013 | 247470 | 247470 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | JEFFERSON | 5-353 | CR 1006C | 0.85 | 0.773 | 1.236 | RELIABILITY | MINOR WIDENING(O) | ENGLISH STATION ROAD IN LOUISVILLE; WIDEN TO 3 LANES FROM AVOCA ROAD TO AIKEN ROAD. (SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | 5 | C | SLO | 2012 | 3093376 | 3093376 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.140 | 2011-10-27 | TIP AMENDMENT #2. KIPDA ID #224. ADD DESIGN PHASE. NEW |  |  | JEFFERSON | 5-378.1 | I 65 | 0.1 | 0 | 0.155 | RELIABILITY | RECONSTRUCTION(O) | EXTEND AND RECONSTRUCT I-65 SOUTHBOUND RAMP TO BROOK STREET AND FLOYD STREET. THE PROJECT WILL INCLUDE THE CONSIDERATION OF BICYCLE AND PEDESTRIAN FACILITIES. | 5 | D | SLO | 2012 | 750000 | 750000 | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.163 | 2012-02-13 | TIP AMENDMENT #3. KIPDA ID #224. CHANGE FUNDING TYPE. MOD |  |  | JEFFERSON | 5-378.1 | I 65 | 0.1 | 0 | 0.155 | RELIABILITY | RECONSTRUCTION(O) | EXTEND AND RECONSTRUCT I-65 SOUTHBOUND RAMP TO BROOK STREET AND FLOYD STREET. THE PROJECT WILL INCLUDE THE CONSIDERATION OF BICYCLE AND PEDESTRIAN FACILITIES. | 5 | D | IMD | 2012 | 750000 | 750000 | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.140 | 2011-10-27 | TIP AMENDMENT #2. KIPDA ID #224. ADD UTILITY PHASE. NEW |  |  | JEFFERSON | 5-378.1 | I 65 | 0.1 | 0 | 0.155 | RELIABILITY | RECONSTRUCTION(O) | EXTEND AND RECONSTRUCT I-65 SOUTHBOUND RAMP TO BROOK STREET AND FLOYD STREET. THE PROJECT WILL INCLUDE THE CONSIDERATION OF BICYCLE AND PEDESTRIAN FACILITIES. | 5 | U | SLO | 2013 | 750000 | 750000 | ESTIMATED | Y |  |  |  |  | 0
[6 empty] | JEFFERSON | 5-378.1 | I 65 | 0.1 | 0 | 0.155 | RELIABILITY | RECONSTRUCTION(O) | EXTEND/RECONSTRUCT I-65 SB RAMP TO BROOK STREET | 5 | C | SLO | 2011 | 4000000 | 4000000 | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.140 | 2011-10-27 | TIP AMENDMENT #2. KIPDA ID #224. MOVE C PHASE FY TO 2015 IN TIP BUT CHANGING TO FY 2014 IN STIP. MOD |  |  | JEFFERSON | 5-378.1 | I 65 | 0.1 | 0 | 0.155 | RELIABILITY | RECONSTRUCTION(O) | EXTEND AND RECONSTRUCT I-65 SOUTHBOUND RAMP TO BROOK STREET AND FLOYD STREET. THE PROJECT WILL INCLUDE THE CONSIDERATION OF BICYCLE AND PEDESTRIAN FACILITIES. | 5 | C | SLO | 2014 | 4000000 | 4000000 | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.163 | 2012-02-13 | TIP AMENDMENT #3. KIPDA ID #224. MOVE C PHASE FY TO 2012, CHANGE FUNDING TYPE, AND |  |  | JEFFERSON | 5-378.1 | I 65 | 0.1 | 0 | 0.155 | RELIABILITY | RECONSTRUCTION(O) | EXTEND AND RECONSTRUCT I-65 SOUTHBOUND RAMP TO BROOK STREET AND FLOYD STREET. THE PROJECT WILL INCLUDE THE CONSIDERATION OF BICYCLE AND PEDESTRIAN FACILITIES. | 5 | C | SLO | 2014 | 1500000 | 1500000 | ESTIMATED | Y |  |  |  |  | 0
[6 empty] | JEFFERSON | 5-378.11 | I 65 | 0.1 | 0 | 0.155 | RELIABILITY | RECONSTRUCTION(O) | RENOVATE I-65 BROOK ST. RAMP, LOUISVILLE. (2006KYD)(SEE 5-378.10 FOR "SLO" COMPONENT) | 5 | C | KYD | 2011 | 430650 | 430650 | ESTIMATED | Y | 2010 |  |  |  | 0
[6 empty] | JEFFERSON | 5-393.02 |  |  |  |  | RELIABILITY | TRANSP ENHANCEMENT(P) | 21ST CENTURY PARKS PROJECT IN LOUISVILLE, KENTUCKY. (2005HPP-KY163) | 5 | C | HPP | 2011 | 27533280 | 27533280 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.095 | 2011-07-05 | TIP AMENDMENT #1. KIPDA ID 1415. CHANGE FUNDING. MOD |  |  | JEFFERSON | 5-393.02 |  |  |  |  | RELIABILITY | TRANSP ENHANCEMENT(P) | 21ST CENTURY PARKS PROJECT IN LOUISVILLE, KENTUCKY. (2005HPP-KY163) | 5 | C | HPP | 2011 | 34416600 | 27533280 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.095 | 2011-07-05 | TIP AMENDMENT #1. KIPDA ID 1415. CHANGE FUNDING. MOD |  |  | JEFFERSON | 5-393.02 |  |  |  |  | RELIABILITY | TRANSP ENHANCEMENT(P) | 21ST CENTURY PARKS PROJECT IN LOUISVILLE, KENTUCKY. (2005HPP-KY163) | 5 | C | KYD | 2011 | 7350000 | 5880000 | ESTIMATED | N | 2010 |  |  |  | 0
AMENDMENT | 2010.002 | 2010-12-08 | AMENDMENT FOR NEW KIPDA TIP FY 2011-2015. ADD PROJECT TO STIP PER THE KIPDA FY 2011-2015 TIP. NEW | DPR | 0176003 | JEFFERSON | 5-393.03 |  |  |  |  | RELIABILITY | TRANSP ENHANCEMENT(P) | 21ST CENTURY PARKS PROJECT IN LOUISVILLE, KENTUCKY. |  | C | DPR | 2011 | 415150 | 415150 |  | N |  | OBLIGATED | 415150 |  | 415150 | 2011 | 2nd QUARTER | N/A
AMENDMENT | 2010.002 | 2010-12-08 | AMENDMENT FOR NEW KIPDA TIP FY 2011-2015. ADD PROJECT TO STIP PER THE KIPDA FY 2011-2015 TIP. NEW | TIP | 0163032 | JEFFERSON | 5-393.03 |  |  |  |  | RELIABILITY | TRANSP ENHANCEMENT(P) | 21ST CENTURY PARKS PROJECT IN LOUISVILLE, KENTUCKY. |  | C | HPP | 2011 | 9133300 | 9133300 |  | N |  | OBLIGATED | 9133300 |  | 9133300 | 2011 | 2nd QUARTER | 21ST CENTURY PARKS
AMENDMENT | 2010.002 | 2010-12-08 | AMENDMENT FOR NEW KIPDA TIP FY 2011-2015. ADD PROJECT TO STIP PER THE KIPDA FY 2011-2015 TIP. NEW | TIP | 0163033 | JEFFERSON | 5-393.04 |  |  |  |  | RELIABILITY | TRANSP ENHANCEMENT(P) | 21ST CENTURY PARKS PROJECT IN LOUISVILLE, KENTUCKY. |  | C | TIP | 2012 | 12463000 | 12463000 |  | N |  | OBLIGATED | 12833800 |  | 12833800 | 2012 | 3rd QUARTER | 21ST CENTURY PARKS
AMENDMENT | 2010.002 | 2010-12-08 | AMENDMENT FOR NEW KIPDA TIP FY 2011-2015. ADD PROJECT TO STIP PER THE KIPDA FY 2011-2015 TIP. NEW | DPR | 0176004 | JEFFERSON | 5-393.05 |  |  |  |  | RELIABILITY | TRANSP ENHANCEMENT(P) | 21ST CENTURY PARKS PROJECT IN LOUISVILLE, KENTUCKY. |  | D | DPR | 2012 | 50000 | 50000 |  | N |  | OBLIGATED | 50000 |  | 50000 | 2012 | 3rd QUARTER | N/A
AMENDMENT | 2010.002 | 2010-12-08 | AMENDMENT FOR NEW KIPDA TIP FY 2011-2015. ADD PROJECT TO STIP PER THE KIPDA FY 2011-2015 TIP. NEW | TIP | 0163034 | JEFFERSON | 5-393.05 |  |  |  |  | RELIABILITY | TRANSP ENHANCEMENT(P) | 21ST CENTURY PARKS PROJECT IN LOUISVILLE, KENTUCKY. |  | D | TIP | 2012 | 3000000 | 3000000 |  | N |  | OBLIGATED | 3000000 |  | 3000000 | 2012 | 3rd QUARTER | 21ST CENTURY PARKS
ADMINISTRATIVE MODIFICATION | 2010.111 | 2011-08-26 | KIPDA MOD #9. KIPDA ID 222. MOVE PREVIOUSLY OBLIGATED FY 2003 UTILITY FUNDS TO FY 2011 AND MOVE 600,000 FED FUNDS FOR ROW PHASE TO FY 2011 UTILITIES TO SHOW FY 2011 UTILITIES 1,200,000 FEDERAL AND 1,500,000 TOTAL. NEW |  |  | JEFFERSON | 5-403 | CR 1002M | 1.8 | 0 | 1.853 | RELIABILITY | MINOR WIDENING(O) | COOPER CHAPEL ROAD PHASE 1: RECONSTRUCT COOPER CHAPEL ROAD FROM 2 TO 3 LANES (3RD LANE WILL BE A CENTER TURN LANE) FROM KY 61 TO SMYRNA PARKWAY. PROJECT LENGTH IS 1.8 MILES. | C | U | SLO | 2011 | 1500000 | 1200000 |  | N |  |  |  |  | 0
[6 empty] | JEFFERSON | 5-403 | CR 1002M | 1.8 | 0 | 1.853 | RELIABILITY | MINOR WIDENING(O) | RECONSTRUCT COOPER CHAPEL ROAD FROM 2 TO 3 LANES (3RD LANE WILL BE A CENTER TURN LANE) FROM KY 61 TO SMYRNA PARKWAY. PROJECT LENGTH IS 1.8 MILES. | 5 | C | SLO | 2011 | 7150000 | 7150000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.074 | 2011-05-05 | TIP MOD #5. KIPDA ID 222. MOVE CONSTRUCTION PHASE TO FY 2012. MOD |  |  | JEFFERSON | 5-403 | CR 1002M | 1.8 | 0 | 1.853 | RELIABILITY | MINOR WIDENING(O) | PHASE 1: RECONSTRUCT COOPER CHAPEL ROAD FROM 2 TO 3 LANES (3RD LANE WILL BE A CENTER TURN LANE) FROM KY 61 TO SMYRNA PARKWAY. PROJECT LENGTH IS 1.8 MILES. | C | C | SLO | 2012 | 7150000 | 7150000 |  | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.083 | 2011-06-06 | TIP MOD #6. KIPDA ID 223. ADD TO STIP. NEW |  |  | JEFFERSON | 5-404 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | COOPER CHAPEL ROAD PHASE 3: EXTEND AND CONSTRUCT 2 LANE ROADWAY WITH A CONTINUOUS CENTER-TURN LANE FROM KY 864 (BEULAH CHURCH ROAD) TO US 31E (BARDSTOWN ROAD) AT BARDSTOWN FALLS ROAD. PROJECT WILL INCORPORATE SIDEWALKS AND 10' PAVED SHOULDERS. | 3 | R | SLO | 2013 | 6366938 | 5093550 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.111 | 2011-08-26 | KIPDA MOD #9. KIPDA ID 223. CHANGE DESCRIPTION. MOD |  |  | JEFFERSON | 5-404 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | COOPER CHAPEL ROAD PHASE 3: EXTEND AND CONSTRUCT 2 LANE ROADWAY WITH A CONTINUOUS CENTER-TURN LANE FROM KY 864 (BEULAH CHURCH ROAD) TO US 31E (BARDSTOWN ROAD) AT BARDSTOWN FALLS ROAD. PROJECT WILL INCLUDE CONSIDERATION OF BICYCLE AND PEDESTRIAN FACILITIES. | 3 | R | SLO | 2013 | 6366938 | 5093550 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | JEFFERSON | 5-404.01 |  | 2.7 |  |  | RELIABILITY | NEW ROUTE(O) | EXTEND COOPER CHAPEL ROAD FROM BEULAH CHURCH ROAD TO BARDSTOWN ROAD (LOU T.I.P.) (ALL WORK BY LOUISVILLE METRO)(LOCALMATCH)(2004BOPC) (SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | 3 | R | SLO | 2012 | 3400000 | 3400000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.034 | 2011-01-28 | KIPDA ID #1192. KIPDA MOD #2-REVISED. ADD R PHASE. NEW |  |  | JEFFERSON | 5-413 | US 150 | 0.1 | 1.07 | 1.12 | SAFETY | SAFETY(P) | ALIGN INTERSECTION OF BROADWAY AND 18TH STREET BY MOVING THE SOUTH LEG OF 18TH STREET TO THE EAST | 4 | R | SLO | 2011 | 100000 | 80000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.194 | 2012-05-30 | KIPDA ID #1192. KIPDA AMENDMENT #4. MOVE R PHASE TO FY 2012 AND REDUCE FUNDING AMOUNT TO $6,250 TOTAL. MOD |  |  | JEFFERSON | 5-413 |  |  |  |  | SAFETY | SAFETY(P) | ALIGN INTERSECTION OF BROADWAY AND 18TH STREET BY MOVING THE SOUTH LEG OF 18TH STREET TO THE EAST. | 4 | R | SLO | 2012 | 6250 | 5000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | JEFFERSON | 5-413 | US 150 | 0.1 | 1.07 | 1.12 | SAFETY | SAFETY(P) | ALIGN INTERSECTION OF BROADWAY AND 18TH STREET BY MOVING THE SOUTH LEG OF 18TH STREET TO THE EAST | 4 | U | SLO | 2011 | 62500 | 62500 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.074 | 2011-05-05 | TIP MOD #5. KIPDA ID 1192. MOVE UTILITIES TO FY 2012. MOD |  |  | JEFFERSON | 5-413 | US 150 | 0.1 | 1.07 | 1.12 | SAFETY | SAFETY(P) | ALIGN INTERSECTION OF BROADWAY AND 18TH STREET BY MOVING THE SOUTH LEG OF 18TH STREET TO THE EAST | U | U | SLO | 2012 | 62500 | 62500 | N | N |  |  |  |  | 0
[6 empty] | JEFFERSON | 5-413 | US 150 | 0.1 | 1.07 | 1.12 | SAFETY | SAFETY(P) | ALIGN INTERSECTION OF BROADWAY AND 18TH STREET BY MOVING THE SOUTH LEG OF 18TH STREET TO THE EAST | 5 | C | SLO | 2011 | 375000 | 375000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.034 | 2011-01-28 | KIPDA ID #1192. KIPDA MOD #2-REVISED. CHANGE FY AND DECREASE FUNDING AMOUNT. MOD |  |  | JEFFERSON | 5-413 | US 150 | 0.1 | 1.07 | 1.12 | SAFETY | SAFETY(P) | ALIGN INTERSECTION OF BROADWAY AND 18TH STREET BY MOVING THE SOUTH LEG OF 18TH STREET TO THE EAST |  | C | SLO | 2012 | 275000 | 220000 |  | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.194 | 2012-05-30 | KIPDA ID #1192. KIPDA AMENDMENT #4. CHANGE FY AND INCREASE FUNDING AMOUNT. MOD |  |  | JEFFERSON | 5-413 | US 150 | 0.1 | 1.07 | 1.12 | SAFETY | SAFETY(P) | ALIGN INTERSECTION OF BROADWAY AND 18TH STREET BY MOVING THE SOUTH LEG OF 18TH STREET TO THE EAST |  | C | SLO | 2013 | 368750 | 295000 |  | N |  |  |  |  | 0
[6 empty] | JEFFERSON | 5-417 | US 60 |  | 1.9 | 2 | RELIABILITY | PE & ENVIRONMENTAL(O) | FRANKFORT AVENUE; REALIGN INTERSECTION WITH STILZ AND HILLCREST. (TO BE LET BY LOU METRO). (SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | 2 | D | SLO | 2011 | 70000 | 70000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.074 | 2011-05-05 | TIP MOD #5. KIPDA ID 465. ADD TO STIP. NEW |  |  | JEFFERSON | 5-437 | KY 907 |  |  |  | RELIABILITY | PE & ENVIRONMENTAL(O) | WIDEN KY 907 (SOUTHSIDE DRIVE) FROM 2 TO 5 LANES (5TH LANE WILL BE A CENTER TURN LANE) FROM KY 1865 (NEW CUT ROAD) TO KY 1020 (NATIONAL TURNPIKE). THE DESIGN WILL INCLUDE THE CONSIDERATION OF BICYCLE AND PEDESTRIAN FACILITIES. PROJECT LENGTH IS 0.7 MILES. |  | D | SLO | 2011 | 1100000 | 1100000 |  | N |  |  |  |  | 0
[6 empty] | JEFFERSON | 5-437.01 | KY 907 | 0.7 | 6.31 | 7.036 | RELIABILITY | MAJOR WIDENING(O) | WIDEN SOUTHSIDE DRIVE (KY-907) TO 5 LANES FROM NEW CUT ROAD TO NATIONAL TURNPIKE. (2004BOPC) (SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | 2 | D | SLO | 2012 | 520000 | 520000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | JEFFERSON | 5-439.03 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | CONSTRUCTION OF VARIOUS SIDEWALK PROJECTS IN LOUISVILLE METRO ON VARIOUS LOCALLY MAINTAINED ROADS. (2006BOPC) (SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | 5 | C | SLO | 2011 | 70000 | 70000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | JEFFERSON | 5-440.01 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | INSTALLATION OF SIDEWALKS TO FIX GAPS IN PEDESTRIAN NETWORK ON VARIOUS STATE MAINTAINED ROADS IN THE LOUISVILLE URBANIZED AREA. (SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | 5 | C | SLO | 2011 | 54000 | 54000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | JEFFERSON | 5-440.02 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | INSTALLATION OF SIDEWALKS TO FIX GAPS IN PEDESTRIAN NETWORK ON VARIOUS STATE MAINTAINED ROADS IN THE LOUISVILLE URBANIZED AREA. (SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | 5 | C | SLO | 2011 | 56000 | 56000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | JEFFERSON | 5-442 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | SENECA PARK LOOP EXTENSIONS (EAST AND WEST). (LOCAL MATCH)(ALL WORK BY LOUISVILLE METRO)(2004BOPC) (SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | 5 | C | SLO | 2011 | 320000 | 320000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.074 | 2011-05-05 | TIP MOD #5. KIPDA ID 1401. CHANGE FY IN TIP ONLY TO FY 2011. STIP IS OK. |  |  | JEFFERSON | 5-442 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | SENECA PARK LOOP EXTENSIONS (EAST AND WEST). (LOCAL MATCH)(ALL WORK BY LOUISVILLE METRO)(2004BOPC) (SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | 5 | C | SLO | 2011 | 320000 | 320000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.148 | 2011-12-01 | TIP MOD #12. KIPDA ID 1401. CHANGE FY TO FY 2012. MOD |  |  | JEFFERSON | 5-442 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | SENECA PARK LOOP EXTENSIONS (EAST AND WEST). (LOCAL MATCH)(ALL WORK BY LOUISVILLE METRO)(2004BOPC) (SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | 5 | C | SLO | 2012 | 320000 | 320000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | JEFFERSON | 5-442.02 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | SENECA PARK LOOP EXTENSIONS (EAST AND WEST). (LOCAL MATCH)(ALL WORK BY LOUISVILLE METRO)(2004BOPC) (SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | 5 | C | SLO | 2011 | 770000 | 770000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | JEFFERSON | 5-443.1 | KY 2053 | 0.3 | 0 | 0.343 | RELIABILITY | RECONSTRUCTION(O) | MT. WASHINGTON ROAD (KY-2053) SECTION 1; FROM PRESTON TO MAPLE WAY. (KYTC MATCH)(2004BOPC)(FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | 2 | D | SLO | 2011 | 320000 | 320000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | JEFFERSON | 5-443.1 | KY 2053 | 0.3 | 0 | 0.343 | RELIABILITY | RECONSTRUCTION(O) | MT. WASHINGTON ROAD (KY-2053) SECTION 1; FROM PRESTON TO MAPLE WAY. (KYTC MATCH)(2004BOPC)(FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | 3 | R | SLO | 2011 | 490000 | 490000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | JEFFERSON | 5-443.1 | KY 2053 | 0.3 | 0 | 0.343 | RELIABILITY | RECONSTRUCTION(O) | MT. WASHINGTON ROAD (KY-2053) SECTION 1; FROM PRESTON TO MAPLE WAY. (KYTC MATCH)(2004BOPC)(FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | 4 | U | SLO | 2011 | 120000 | 120000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | JEFFERSON | 5-443.2 | KY 2053 | 2.46 | 0.343 | 2.804 | RELIABILITY | RECONSTRUCTION(O) | MT. WASHINGTON ROAD (KY-2053) SECTION 2; FROM MAPLE WAY TO CEDAR CREEK RD. (KYTC MATCH)(2004BOPC)(FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | 2 | D | SLO | 2011 | 290000 | 290000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | JEFFERSON | 5-446 | KY 155 | 0.756 | 3.947 | 4.703 | RELIABILITY | SAFETY(P) | RECONSTRUCT INTERSECTION OF KY-155 AND KY-148. (SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | 3 | R | SLO | 2011 | 638000 | 638000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.074 | 2011-05-05 | TIP MOD #5. KIPDA ID 1507. CHANGE FY AND INCREASE FUNDING AMOUNT. MOD |  |  | JEFFERSON | 5-446 | KY 155 | 0.756 | 3.947 | 4.703 | RELIABILITY | SAFETY(P) | RECONSTRUCT INTERSECTION OF KY-155 AND KY-148. | 3 | R | SLO | 2011 | 1422500 | 1138000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.163 | 2012-02-13 | TIP AMENDMENT #3. KIPDA ID 1507. CHANGE FY. MOD |  |  | JEFFERSON | 5-446 | KY 155 | 0.756 | 3.947 | 4.703 | RELIABILITY | SAFETY(P) | RECONSTRUCT INTERSECTION OF KY-155 AND KY-148. | 3 | R | SLO | 2012 | 1422500 | 1138000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | JEFFERSON | 5-446 | KY 155 | 0.756 | 3.947 | 4.703 | RELIABILITY | SAFETY(P) | RECONSTRUCT INTERSECTION OF KY-155 AND KY-148. (SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | 4 | U | SLO | 2011 | 374000 | 374000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.163 | 2012-02-13 | TIP AMENDMENT #3. KIPDA ID 1507. CHANGE FY. MOD |  |  | JEFFERSON | 5-446 | KY 155 | 0.756 | 3.947 | 4.703 | RELIABILITY | SAFETY(P) | RECONSTRUCT INTERSECTION OF KY-155 AND KY-148. | 3 | U | SLO | 2012 | 374000 | 374000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | JEFFERSON | 5-446 | KY 155 | 0.756 | 3.947 | 4.703 | RELIABILITY | SAFETY(P) | RECONSTRUCT INTERSECTION OF KY-155 AND KY-148. (SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | 5 | C | SLO | 2012 | 1034000 | 1034000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.074 | 2011-05-05 | TIP MOD #5. KIPDA ID 1507. INCREASE FUNDING AMOUNT. MOD |  |  | JEFFERSON | 5-446 | KY 155 | 0.756 | 3.947 | 4.703 | RELIABILITY | SAFETY(P) | RECONSTRUCT INTERSECTION OF KY-155 AND KY-148. | 3 | C | SLO | 2012 | 1917500 | 1534000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.163 | 2012-02-13 | TIP AMENDMENT #3. KIPDA ID 1507. CHANGE FY. MOD |  |  | JEFFERSON | 5-446 | KY 155 | 0.756 | 3.947 | 4.703 | RELIABILITY | SAFETY(P) | RECONSTRUCT INTERSECTION OF KY-155 AND KY-148. | 3 | C | SLO | 2013 | 1917500 | 1534000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | JEFFERSON | 5-464 | KY 155 |  | 7.5 | 7.58 | RELIABILITY | MATCHED FED FUNDS(O) | CONSTRUCT LEFT TURN LANE ON KY 155 (TAYLORSVILLE RD.) AT OLD HEADY ROAD, 1.6 MILES NORTHWEST OF THE I-265 UNDERPASS IN LOUISVILLE. (2008BOPC) | 3 | R | SLO | 2011 | 250000 | 250000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.148 | 2011-12-01 | TIP MOD #12. KIPDA ID 1609. MOVE R PHASE TO FY 2012. MOD |  |  | JEFFERSON | 5-464 | KY 155 |  | 7.5 | 7.58 | RELIABILITY | MATCHED FED FUNDS(O) | CONSTRUCT LEFT TURN LANE ON KY 155 (TAYLORSVILLE RD.) AT OLD HEADY ROAD, 1.6 MILES NORTHWEST OF THE I-265 UNDERPASS IN LOUISVILLE. (2008BOPC) | 4 | R | SLO | 2012 | 250000 | 250000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | JEFFERSON | 5-464 | KY 155 |  | 7.5 | 7.58 | RELIABILITY | MATCHED FED FUNDS(O) | CONSTRUCT LEFT TURN LANE ON KY 155 (TAYLORSVILLE RD.) AT OLD HEADY ROAD, 1.6 MILES NORTHWEST OF THE I-265 UNDERPASS IN LOUISVILLE. (2008BOPC) | 4 | U | SLO | 2011 | 130000 | 130000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | JEFFERSON | 5-464 | KY 155 |  | 7.5 | 7.58 | RELIABILITY | MATCHED FED FUNDS(O) | CONSTRUCT LEFT TURN LANE ON KY 155 (TAYLORSVILLE RD.) AT OLD HEADY ROAD, 1.6 MILES NORTHWEST OF THE I-265 UNDERPASS IN LOUISVILLE. (2008BOPC) | 5 | C | SLO | 2012 | 1000000 | 1000000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.021 | 2010-11-29 | TIP MOD #28 TO THE FY 2007-2011 TIP. ADD PROJECT TO STIP. NEW | STPM | 3001413 | JEFFERSON | 5-470 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | DESIGN AND CONSTRUCTION FOR THE CONVERSION OF THE FOLLOWING ONE-WAY STREETS IN DOWNTOWN LOUISVILLE TO TWO-WAY TRAFFIC FLOW: MAIN STREET (4TH ST. TO STORY AVE.); JEFFERSON STREET (FLOYD TO BAXTER AVENUE); LIBERTY STREET (JACKSON TO BAXTER); MUHAMMAD ALI BLVD. (JACKSON TO CHESTNUT CONNECTOR); CHESTNUT STREET (JACKSON TO CHESTNUT CONNECTOR); AND 3RD STREET (MARKET TO MAIN). DESIGN FOR THE CONVERSION OF THE FOLLOWING ONE-WAY STREETS IN DOWNTOWN LOUISVILLE TO TWO-WAY TRAFFIC FLOW: 8TH STREET (KENTUCKY TO MAIN); 7TH STREET (OAK TO MAIN); SHELBY STREET (ORMSBY TO MAIN STREET); AND CAMPBELL STREET (JACKSON TO BAXTER). |  | D | SLO | 2011 | 225000 | 225000 |  | N |  | OBLIGATED | 225000 |  | 225000 | 2011 | 1st QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.148 | 2011-12-01 | TIP MOD #12 TO THE FY 2011-2015 TIP. KIPDA ID 1809. MOVE FY 2011 DESIGN TO FY 2012. MOD |  |  | JEFFERSON | 5-470 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | DESIGN AND CONSTRUCTION FOR THE CONVERSION OF THE FOLLOWING ONE-WAY STREETS IN DOWNTOWN LOUISVILLE TO TWO-WAY TRAFFIC FLOW: MAIN STREET (4TH ST. TO STORY AVE.); JEFFERSON STREET (FLOYD TO BAXTER AVENUE); LIBERTY STREET (JACKSON TO BAXTER); MUHAMMAD ALI BLVD. (JACKSON TO CHESTNUT CONNECTOR); CHESTNUT STREET (JACKSON TO CHESTNUT CONNECTOR); AND 3RD STREET (MARKET TO MAIN). DESIGN FOR THE CONVERSION OF THE FOLLOWING ONE-WAY STREETS IN DOWNTOWN LOUISVILLE TO TWO-WAY TRAFFIC FLOW: 8TH STREET (KENTUCKY TO MAIN); 7TH STREET (OAK TO MAIN); SHELBY STREET (ORMSBY TO MAIN STREET); AND CAMPBELL STREET (JACKSON TO BAXTER). |  | D | SLO | 2012 | 225000 | 225000 |  | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.021 | 2010-11-29 | TIP MOD #28 TO THE FY 2007-2011 TIP. ADD PROJECT TO STIP. NEW |  |  | JEFFERSON | 5-470 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | DESIGN AND CONSTRUCTION FOR THE CONVERSION OF THE FOLLOWING ONE-WAY STREETS IN DOWNTOWN LOUISVILLE TO TWO-WAY TRAFFIC FLOW: MAIN STREET (4TH ST. TO STORY AVE.); JEFFERSON STREET (FLOYD TO BAXTER AVENUE); LIBERTY STREET (JACKSON TO BAXTER); MUHAMMAD ALI BLVD. (JACKSON TO CHESTNUT CONNECTOR); CHESTNUT STREET (JACKSON TO CHESTNUT CONNECTOR); AND 3RD STREET (MARKET TO MAIN). DESIGN FOR THE CONVERSION OF THE FOLLOWING ONE-WAY STREETS IN DOWNTOWN LOUISVILLE TO TWO-WAY TRAFFIC FLOW: 8TH STREET (KENTUCKY TO MAIN); 7TH STREET (OAK TO MAIN); SHELBY STREET (ORMSBY TO MAIN STREET); AND CAMPBELL STREET (JACKSON TO BAXTER). |  | C | SLO | 2011 | 2381500 | 2381500 |  | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.074 | 2011-05-05 | KIPDA ID 1809. TIP MOD #5 TO THE FY 2011-2015 TIP. CHANGE C PHASE TO FY 2012. MOD |  |  | JEFFERSON | 5-470 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | DESIGN AND CONSTRUCTION FOR THE CONVERSION OF THE FOLLOWING ONE-WAY STREETS IN DOWNTOWN LOUISVILLE TO TWO-WAY TRAFFIC FLOW: MAIN STREET (4TH ST. TO STORY AVE.); JEFFERSON STREET (FLOYD TO BAXTER AVENUE); LIBERTY STREET (JACKSON TO BAXTER); MUHAMMAD ALI BLVD. (JACKSON TO CHESTNUT CONNECTOR); CHESTNUT STREET (JACKSON TO CHESTNUT CONNECTOR); AND 3RD STREET (MARKET TO MAIN). DESIGN FOR THE CONVERSION OF THE FOLLOWING ONE-WAY STREETS IN DOWNTOWN LOUISVILLE TO TWO-WAY TRAFFIC FLOW: 8TH STREET (KENTUCKY TO MAIN); 7TH STREET (OAK TO MAIN); SHELBY STREET (ORMSBY TO MAIN STREET); AND CAMPBELL STREET (JACKSON TO BAXTER). |  | C | SLO | 2012 | 2381500 | 2381500 |  | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.118 | 2011-09-06 | RECEIVED FY 2011 TCSP FUNDS. WILL BE INCLUDED ON TIP MOD #10. NEW |  |  | JEFFERSON | 5-473 | US 60 |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | SHELBYVILLE ROAD OLD US 60 BRIDGE ENGINEERING STUDY |  | P | TCSP | 2011 | 125000 | 100000 | [6 empty] | 0
AMENDMENT | 2010.002 | 2010-12-08 | ADDING THIS PROJECT PER THE FY 2011-2015 TIP. NEW | STPM | 3001426 | JEFFERSON | 5-479 |  |  |  |  | RELIABILITY | RECONSTRUCTION(O) | PE & ENVIRONMENTAL FOR DEVELOPMENT OF CONTRACT PLANS TO WIDEN HUBBARDS LANE FROM US 60 TO KY 1447 AND ADD BIKE LANES FROM KRESAGE WAY TO KY 1447. |  | D | STPM | 2012 | 343200 | 343200 |  |  |  | OBLIGATED | 343200 |  | 343200 | 2012 | 2nd QUARTER | LOUISVILLE METRO
AMENDMENT | 2010.002 | 2010-12-08 | ADDING THIS PROJECT PER THE FY 2011-2015 TIP. NEW | STPM | 8776029 | JEFFERSON | 5-480 | KY 1931 | 2.225 | 5.477 | 7.702 | RELIABILITY | MATCHED FED FUNDS(O) | CONDUCT SCOPING STUDY AND ENVIRONMENTAL OVERVIEW FOR RECONSTRUCTION OF MANSLICK ROAD (KY 1931) FROM ST.ANDREWS CHURCH ROAD TO I-264. (KIPDA # 446). |  | D | STPM | 2012 | 400000 | 400000 |  |  |  | OBLIGATED | 400000 |  | 400000 | 2012 | 3rd QUARTER | N/A
AMENDMENT | 2010.002 | 2010-12-08 | ADDING THIS PROJECT PER THE FY 2011-2015 TIP. NEW | STPM | 8743004 | JEFFERSON | 5-481 | KY 864 | 1.547 | 1.898 | 3.445 | RELIABILITY | MATCHED FED FUNDS(O) | KY 864 - WIDEN BEULAH CHURCH ROAD FROM 2 TO 3 LANES FROM I-265 TO CEDAR CREEK ROAD. |  | D | STPM | 2012 | 700000 | 700000 |  |  |  | OBLIGATED | 700000 |  | 700000 | 2012 | 3rd QUARTER | N/A
[6 empty] | JEFFERSON | 5-502 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | DESIGN FOR THE CONVERSION OF THE FOLLOWING ONE-WAY STREETS IN DOWNTOWN LOUISVILLE TO TWO-WAY TRAFFIC FLOW: 8TH STREET (KENTUCKY TO MAIN); 7TH STREET (OAK TO MAIN); SHELBY STREET (ORMSBY TO MAIN STREET); AND CAMPBELL STREET (JACKSON TO BAXTER). | 5 | C | KYD | 2011 | 491964 | 491964 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.140 | 2011-10-27 | KIPDA TIP AMENDMENT #2. KIPDA ID #1810. MOVE FY TO 2013. MOD |  |  | JEFFERSON | 5-502 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | CONVERSION OF ONE-WAY STREETS IN DOWNTOWN LOUISVILLE TO TWO-WAY TRAFFIC (8TH, 7TH , SHELBY, CAMPBELL STREETS) | 5 | C | SLO | 2013 | 491964 | 491964 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.074 | 2011-05-05 | TIP MOD #5. KIPDA ID 1109. ADD TO STIP. NEW |  |  | JEFFERSON | 5-505 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | OHIO RIVER LEVEE TRAIL - PHASE IIB AND PHASE III: COMPLETE THE ORLT, A SHARED USE PATH ALONG THE OHIO RIVER IN WEST JEFFERSON CO. PHASE IIB WILL RUN FROM CANE RUN ROAD NORTH TO SOUTH OF LEES LANE AND PHASE III WILL RUN FROM CHICKASAW PARK TO LEES LANE. |  | D | SLO | 2011 | 248000 | 198400 |  | N |  | OBLIGATED | 196786 | 10000 | 206786 | 2012 | 1st QUARTER | LOUISVILLE METRO
ADMINISTRATIVE MODIFICATION | 2010.148 | 2011-12-01 | TIP MOD #12. KIPDA ID 1109. MOVE D PHASE TO FY 2012. MOD |  |  | JEFFERSON | 5-505 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | OHIO RIVER LEVEE TRAIL - PHASE IIB AND PHASE III: COMPLETE THE ORLT, A SHARED USE PATH ALONG THE OHIO RIVER IN WEST JEFFERSON CO. PHASE IIB WILL RUN FROM CANE RUN ROAD NORTH TO SOUTH OF LEES LANE AND PHASE III WILL RUN FROM CHICKASAW PARK TO LEES LANE. |  | D | SLO | 2012 | 248000 | 198400 |  | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.074 | 2011-05-05 | TIP MOD #5. KIPDA ID 1109. ADD TO STIP. NEW |  |  | JEFFERSON | 5-505 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | OHIO RIVER LEVEE TRAIL - PHASE IIB AND PHASE III: COMPLETE THE ORLT, A SHARED USE PATH ALONG THE OHIO RIVER IN WEST JEFFERSON CO. PHASE IIB WILL RUN FROM CANE RUN ROAD NORTH TO SOUTH OF LEES LANE AND PHASE III WILL RUN FROM CHICKASAW PARK TO LEES LANE. |  | C | SLO | 2012 | 550000 | 440000 |  | N |  | OBLIGATED | 1500000 | 400000 | 1900000 | 2012 | 1st QUARTER | LOUISVILLE METRO
ADMINISTRATIVE MODIFICATION | 2010.148 | 2011-12-01 | TIP MOD #12. KIPDA ID 1109. MOVE C PHASE TO FY 2013. MOD |  |  | JEFFERSON | 5-505 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | OHIO RIVER LEVEE TRAIL - PHASE IIB AND PHASE III: COMPLETE THE ORLT, A SHARED USE PATH ALONG THE OHIO RIVER IN WEST JEFFERSON CO. PHASE IIB WILL RUN FROM CANE RUN ROAD NORTH TO SOUTH OF LEES LANE AND PHASE III WILL RUN FROM CHICKASAW PARK TO LEES LANE. |  | C | SLO | 2013 | 550000 | 440000 |  | N |  |  |  |  | 0
[6 empty] | JEFFERSON | 5-513 |  |  |  |  | SAFETY | MATCHED FED FUNDS(O) | CONSTRUCT SHARED USE PATH FROM NEIGHBORHOOD SIDEWALK TO REAR OF SCHOOL PROPERTY, AND PROVIDE OUTDOOR CLASSROOM AMENITIES ALONG THE SHARED USE PATH. PROJECT WILL INCLUDE WETLAND RESTORATION ON SCHOOL SITE. | 2 | D | SLO | 2011 | 12500 | 12500 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.160 | 2012-01-31 | TIP MOD #13. KIPDA ID 1610. ADDITIONAL FUNDING FOR D PHASE. MOD |  |  | JEFFERSON | 5-513 |  |  |  |  | SAFETY | MATCHED FED FUNDS(O) | STONESTREET ROAD ELEMENTARY SCHOOL: CONSTRUCT SHARED USE PATH FROM NEIGHBORHOOD SIDEWALK TO REAR OF SCHOOL PROPERTY, AND PROVIDE OUTDOOR CLASSROOM AMENITIES ALONG THE SHARED USE PATH. PROJECT WILL INCLUDE WETLAND RESTORATION ON SCHOOL SITE. | 2 | D | SLO | 2012 | 35000 | 35000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | JEFFERSON | 5-513 |  |  |  |  | SAFETY | MATCHED FED FUNDS(O) | CONSTRUCT SHARED USE PATH FROM NEIGHBORHOOD SIDEWALK TO REAR OF SCHOOL PROPERTY, AND PROVIDE OUTDOOR CLASSROOM AMENITIES ALONG THE SHARED USE PATH. PROJECT WILL INCLUDE WETLAND RESTORATION ON SCHOOL SITE. | 5 | C | SLO | 2011 | 70000 | 70000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.160 | 2012-01-31 | TIP MOD #13. KIPDA ID 1610. ADDITIONAL FUNDING FOR C PHASE. MOD |  |  | JEFFERSON | 5-513 |  |  |  |  | SAFETY | MATCHED FED FUNDS(O) | CONSTRUCT SHARED USE PATH FROM NEIGHBORHOOD SIDEWALK TO REAR OF SCHOOL PROPERTY, AND PROVIDE OUTDOOR CLASSROOM AMENITIES ALONG THE SHARED USE PATH. PROJECT WILL INCLUDE WETLAND RESTORATION ON SCHOOL SITE. | 5 | C | SLO | 2012 | 136000 | 136000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.195 | 2012-05-30 | TIP AMENDMENT #5. KIPDA ID 185. ADD FY 2012 DESIGN 1,560,000 STP FUNDS. NEW |  |  | JEFFERSON | 5-700 |  |  |  |  | RELIABILITY | I-CHANGE RECONST(O) | CONSTRUCTION OF TWO NEW OHIO RIVER BRIDGES, 1 IN DOWNTOWN (I-65) CORRIDOR AND 1 IN THE FAR EAST (I-265) CORRIDOR AND RECONSTRUCTION OF THE KENNEDY INTERCHANGE. ALSO INCLUDED ARE ENHANCED BUS SERVICE IMPROVEMENTS. |  | D | STP | 2012 | 1560000 | 1560000 |  | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.195 | 2012-05-30 | TIP AMENDMENT #5. KIPDA ID 185. ADD FY 2013 CONSTRUCTION 25,000,000 IM FUNDS. NEW |  |  | JEFFERSON | 5-700 |  |  |  |  | RELIABILITY | I-CHANGE RECONST(O) | CONSTRUCTION OF TWO NEW OHIO RIVER BRIDGES, 1 IN DOWNTOWN (I-65) CORRIDOR AND 1 IN THE FAR EAST (I-265) CORRIDOR AND RECONSTRUCTION OF THE KENNEDY INTERCHANGE. ALSO INCLUDED ARE ENHANCED BUS SERVICE IMPROVEMENTS. |  | C | IM | 2013 | 25000000 | 25000000 |  | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.195 | 2012-05-30 | TIP AMENDMENT #5. KIPDA ID 185. ADD FY 2013 CONSTRUCTION 26,050,000 NHS FUNDS. NEW |  |  | JEFFERSON | 5-700 |  |  |  |  | RELIABILITY | I-CHANGE RECONST(O) | CONSTRUCTION OF TWO NEW OHIO RIVER BRIDGES, 1 IN DOWNTOWN (I-65) CORRIDOR AND 1 IN THE FAR EAST (I-265) CORRIDOR AND RECONSTRUCTION OF THE KENNEDY INTERCHANGE. ALSO INCLUDED ARE ENHANCED BUS SERVICE IMPROVEMENTS. |  | C | NHS | 2013 | 26050000 | 26050000 |  | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.195 | 2012-05-30 | TIP AMENDMENT #5. KIPDA ID 185. ADD FY 2013 CONSTRUCTION 23,380,000 GARVEE BONDS . NEW |  |  | JEFFERSON | 5-700 |  |  |  |  | RELIABILITY | I-CHANGE RECONST(O) | CONSTRUCTION OF TWO NEW OHIO RIVER BRIDGES, 1 IN DOWNTOWN (I-65) CORRIDOR AND 1 IN THE FAR EAST (I-265) CORRIDOR AND RECONSTRUCTION OF THE KENNEDY INTERCHANGE. ALSO INCLUDED ARE ENHANCED BUS SERVICE IMPROVEMENTS. |  | C | GARVEE | 2013 | 23380000 | 23380000 |  | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.195 | 2012-05-30 | TIP AMENDMENT #5. KIPDA ID 185. ADD FY 2014 CONSTRUCTION 25,000,000 IM FUNDS. NEW |  |  | JEFFERSON | 5-700 |  |  |  |  | RELIABILITY | I-CHANGE RECONST(O) | CONSTRUCTION OF TWO NEW OHIO RIVER BRIDGES, 1 IN DOWNTOWN (I-65) CORRIDOR AND 1 IN THE FAR EAST (I-265) CORRIDOR AND RECONSTRUCTION OF THE KENNEDY INTERCHANGE. ALSO INCLUDED ARE ENHANCED BUS SERVICE IMPROVEMENTS. |  | C | IM | 2014 | 25000000 | 25000000 |  | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.195 | 2012-05-30 | TIP AMENDMENT #5. KIPDA ID 185. ADD FY 2014 CONSTRUCTION 26,100,000 NHS FUNDS. NEW |  |  | JEFFERSON | 5-700 |  |  |  |  | RELIABILITY | I-CHANGE RECONST(O) | CONSTRUCTION OF TWO NEW OHIO RIVER BRIDGES, 1 IN DOWNTOWN (I-65) CORRIDOR AND 1 IN THE FAR EAST (I-265) CORRIDOR AND RECONSTRUCTION OF THE KENNEDY INTERCHANGE. ALSO INCLUDED ARE ENHANCED BUS SERVICE IMPROVEMENTS. |  | C | NHS | 2014 | 26100000 | 26100000 |  | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.195 | 2012-05-30 | TIP AMENDMENT #5. KIPDA ID 185. ADD FY 2014 CONSTRUCTION 175,876,000 GARVEE BONDS. NEW |  |  | JEFFERSON | 5-700 |  |  |  |  | RELIABILITY | I-CHANGE RECONST(O) | CONSTRUCTION OF TWO NEW OHIO RIVER BRIDGES, 1 IN DOWNTOWN (I-65) CORRIDOR AND 1 IN THE FAR EAST (I-265) CORRIDOR AND RECONSTRUCTION OF THE KENNEDY INTERCHANGE. ALSO INCLUDED ARE ENHANCED BUS SERVICE IMPROVEMENTS. |  | C | GARVEE | 2014 | 175876000 | 175876000 |  | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.195 | 2012-05-30 | TIP AMENDMENT #5. KIPDA ID 185. ADD FY 2015 CONSTRUCTION 25,000,000 IM FUNDS. NEW |  |  | JEFFERSON | 5-700 |  |  |  |  | RELIABILITY | I-CHANGE RECONST(O) | CONSTRUCTION OF TWO NEW OHIO RIVER BRIDGES, 1 IN DOWNTOWN (I-65) CORRIDOR AND 1 IN THE FAR EAST (I-265) CORRIDOR AND RECONSTRUCTION OF THE KENNEDY INTERCHANGE. ALSO INCLUDED ARE ENHANCED BUS SERVICE IMPROVEMENTS. |  | C | IM | 2015 | 25000000 | 25000000 |  | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.195 | 2012-05-30 | TIP AMENDMENT #5. KIPDA ID 185. ADD FY 2015 CONSTRUCTION 25,000,000. NHS FUNDS. NEW |  |  | JEFFERSON | 5-700 |  |  |  |  | RELIABILITY | I-CHANGE RECONST(O) | CONSTRUCTION OF TWO NEW OHIO RIVER BRIDGES, 1 IN DOWNTOWN (I-65) CORRIDOR AND 1 IN THE FAR EAST (I-265) CORRIDOR AND RECONSTRUCTION OF THE KENNEDY INTERCHANGE. ALSO INCLUDED ARE ENHANCED BUS SERVICE IMPROVEMENTS. |  | C | NHS | 2015 | 25000000 | 25000000 |  | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.195 | 2012-05-30 | TIP AMENDMENT #5. KIPDA ID 185. ADD FY 2015 CONSTRUCTION 36,744,000 GARVEE BONDS. NEW |  |  | JEFFERSON | 5-700 |  |  |  |  | RELIABILITY | I-CHANGE RECONST(O) | CONSTRUCTION OF TWO NEW OHIO RIVER BRIDGES, 1 IN DOWNTOWN (I-65) CORRIDOR AND 1 IN THE FAR EAST (I-265) CORRIDOR AND RECONSTRUCTION OF THE KENNEDY INTERCHANGE. ALSO INCLUDED ARE ENHANCED BUS SERVICE IMPROVEMENTS. |  | C | GARVEE | 2015 | 36744000 | 36744000 |  | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.195 | 2012-05-30 | TIP AMENDMENT #5. KIPDA ID 185. ADD FY 2015 CONSTRUCTION 165,450,000 IF FUNDS. NEW |  |  | JEFFERSON | 5-700 |  |  |  |  | RELIABILITY | I-CHANGE RECONST(O) | CONSTRUCTION OF TWO NEW OHIO RIVER BRIDGES, 1 IN DOWNTOWN (I-65) CORRIDOR AND 1 IN THE FAR EAST (I-265) CORRIDOR AND RECONSTRUCTION OF THE KENNEDY INTERCHANGE. ALSO INCLUDED ARE ENHANCED BUS SERVICE IMPROVEMENTS. |  | C | IF | 2015 | 165450000 | 165450000 |  | Y |  |  |  |  | 0
[6 empty] | JEFFERSON | 5-700.02 |  |  |  |  | RELIABILITY | ENVIRO MITIGATION(P) | LOUISVILLE BRIDGES; OVERALL PROJECT MITIGATION REQUIREMENTS.(CRAFTSMAN TRAINING) | 2 | D | STP | 2011 | 1560000 | 1560000 | ESTIMATED | [5 empty] | 0
[6 empty] | JEFFERSON | 5-700.03 |  |  |  |  | RELIABILITY | ENVIRO MITIGATION(P) | LOUISVILLE BRIDGES; OVERALL MISC DESIGN ACTIVITIES | 2 | D | IF | 2012 | 8100000 | 8100000 | ESTIMATED | [5 empty] | 0
AMENDMENT | 2010.002 | 2010-12-08 | AMENDMENT FOR NEW KIPDA TIP FY 2011-2015. ADD PROJECT TO STIP PER THE KIPDA FY 2011-2015 TIP. NEW | HPP | 0141012 | JEFFERSON | 5-701.01 |  |  |  |  | RELIABILITY | I-CHANGE RECONST(O) | GEC AND KYTC OVERSIGHT OF ENGINEERING SERVICES FOR THE LOUISVILLE BRIDGES PROJECT, DOWNTOWN AND EAST END BRIDGES AND ASSOCIATED ROADWAYS. |  | D | HPP | 2011 | 12000000 | 12000000 |  | Y |  | OBLIGATED | 12000000 |  | 12000000 | 2011 | 3rd QUARTER | N/A
[6 empty] | JEFFERSON | 5-711.3 |  |  |  |  | RELIABILITY | I-CHANGE RECONST(O) | LOUISVILLE BRIDGES; SECTION ONE - KENNEDY INTERCHANGE DESIGN. (08CCR)(10CCR) | 2 | D | GV2 | 2011 | 62400000 | 62400000 | ESTIMATED | Y |  |  |  |  | 0
|  |  |  | IMNH | 0659014 | JEFFERSON | 5-712.11 | I 65 |  |  |  | RELIABILITY | I-CHANGE RECONST(O) | LOUISVILLE BRIDGES; SECTION ONE - KENNEDY INTERCHANGE RIGHT OF WAY. (08CCR)(2008BOPC)(10CCR) | 3 | R | GV1 | 2011 | 38550000 | 38550000 | ESTIMATED | Y | 2010 | OBLIGATED | 48187500 |  | 48187500 | 2010 | 2nd QUARTER | N/A
[6 empty] | JEFFERSON | 5-712.3 |  |  |  |  | RELIABILITY | I-CHANGE RECONST(O) | LOUISVILLE BRIDGES; SECTION ONE - KENNEDY INTERCHANGE RIGHT OF WAY.(10CCR) | 3 | R | GV2 | 2011 | 14200000 | 14200000 | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.195 | 2012-05-30 | KIPDA TIP AMENDMENT #5. KIPDA ID 185. DELETE ROW 12,300,000. MOD | DELETE | PHASE | JEFFERSON | 5-712.4 |  |  |  |  | RELIABILITY | I-CHANGE RECONST(O) | LOUISVILLE BRIDGES; SECTION ONE - KENNEDY INTERCHANGE RIGHT OF WAY. | 3 | R | IM | 2011 |  |  | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.195 | 2012-05-30 | KIPDA TIP AMENDMENT #5. KIPDA ID 185. DELETE ROW 15,100,000. MOD | DELETE | PHASE | JEFFERSON | 5-712.41 |  |  |  |  | RELIABILITY | I-CHANGE RECONST(O) | LOUISVILLE BRIDGES; SECTION ONE - KENNEDY INTERCHANGE RIGHT OF WAY. | 3 | R | NH | 2011 |  |  | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.195 | 2012-05-30 | KIPDA TIP AMENDMENT #5. KIPDA ID 185. DELETE UTILITY 11,700,000. MOD | DELETE | PHASE | JEFFERSON | 5-713.1 |  |  |  |  | RELIABILITY | I-CHANGE RECONST(O) | LOUISVILLE BRIDGES; SECTION ONE - KENNEDY INTERCHANGE UTILITIES. | 4 | U | IM | 2011 |  |  | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.195 | 2012-05-30 | KIPDA TIP AMENDMENT #5. KIPDA ID 185. DELETE UTILITY 14,300,000. MOD | DELETE | PHASE | JEFFERSON | 5-713.2 |  |  |  |  | RELIABILITY | I-CHANGE RECONST(O) | LOUISVILLE BRIDGES; SECTION ONE - KENNEDY INTERCHANGE UTILITIES. | 4 | U | NH | 2011 |  |  | ESTIMATED | Y |  |  |  |  | 0
[6 empty] | JEFFERSON | 5-715.2 |  |  |  |  | RELIABILITY | I-CHANGE RECONST(O) | LOUISVILLE BRIDGES; SECTION ONE - KENNEDY INTERCHANGE CONSTRUCTION. (08CCR) | 5 | C | IM | 2012 | 22500000 | 22500000 | ESTIMATED | Y |  |  |  |  | 0
[6 empty] | JEFFERSON | 5-715.21 |  |  |  |  | RELIABILITY | I-CHANGE RECONST(O) | LOUISVILLE BRIDGES; SECTION ONE - KENNEDY INTERCHANGE CONSTRUCTION. (08CCR) | 5 | C | NH | 2012 | 27500000 | 27500000 | ESTIMATED | Y |  |  |  |  | 0
[6 empty] | JEFFERSON | 5-721.4 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | LOUISVILLE BRIDGES; SECTION TWO - DOWNTOWN BRIDGE DESIGN (KY SHARE). (08CCR)(10CCR) | 2 | D | GV2 | 2011 | 7800000 | 7800000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | JEFFERSON | 5-731.3 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | LOUISVILLE BRIDGES; SECTION FOUR - EAST END BRIDGE APPROACH DESIGN. (08CCR)(10CCR) | 2 | D | GV2 | 2011 | 15600000 | 15600000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | JEFFERSON | 5-733.2 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | LOUISVILLE BRIDGES; SECTION FOUR - EAST END BRIDGE APPROACH UTILITIES. (08CCR)(10CCR) | 4 | U | GV2 | 2011 | 31200000 | 31200000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | JEFFERSON | 5-735.4 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | LOUISVILLE BRIDGES; SECTION FOUR - EAST END BRIDGE APPROACH CONSTRUCTION. | 5 | C | IF | 2012 | 81100000 | 81100000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | JEFFERSON | 5-745 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | LOUISVILLE BRIDGES; SECTION FIVE - EAST END OHIO RIVER BRIDGE CONSTRUCTION. | 5 | C | IF | 2012 | 43300000 | 43300000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.127 | 2011-09-29 | KIPDA TIP MOD #10. ADD TO STIP AS PART OF KIPDA ID #173. NEW | IM | 0659021 | JEFFERSON | 5-801 | I 65 | 2 | 136 | 138 | RELIABILITY | PAVEMENT REHAB-INT(P) | I-65 KENNEDY BRIDGE DECK REHABILITATION WITH FULL DEPTH AND PARTIAL DEPTH PATCHING, REPLACE/REPAIR FINGER EXPANSION JOINTS, REPLACE/REPAIR 18 SMALL JOINTS ALONG WITH ASPHALT WATERPROOFING MIX OVERLAY, AND PAVEMENT REHABILITATION INCLUDING RAMPS AT KENNEDY BRIDGE AND TWO RAMPS ENTERING AND EXITING THE SPAGHETTI JUNCTION TO I-65. |  | C | IM | 2011 | 1000000 | 1000000 |  |  |  | OBLIGATED | 8000000 | 4449023.79 | 12449023.79 | 2011 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.127 | 2011-09-29 | KIPDA TIP MOD #10. ADD TO STIP AS PART OF KIPDA ID #173. NEW | STPM | 0659021 | JEFFERSON | 5-801 | I 65 | 2 | 136 | 138 | RELIABILITY | PAVEMENT REHAB-INT(P) | I-65 KENNEDY BRIDGE DECK REHABILITATION WITH FULL DEPTH AND PARTIAL DEPTH PATCHING, REPLACE/REPAIR FINGER EXPANSION JOINTS, REPLACE/REPAIR 18 SMALL JOINTS ALONG WITH ASPHALT WATERPROOFING MIX OVERLAY, AND PAVEMENT REHABILITATION INCLUDING RAMPS AT KENNEDY BRIDGE AND TWO RAMPS ENTERING AND EXITING THE SPAGHETTI JUNCTION TO I-65. |  | C | SLO | 2011 | 8000000 | 8000000 |  |  |  | OBLIGATED | 8000000 |  | 8000000 | 2011 | 4th QUARTER | N/A
[6 empty] | JEFFERSON | 5-802 | I 264 | 2.291 | 18.41 | 20.701 | RELIABILITY | PAVEMENT REHAB-INT(P) | REPAIR AND GRIND PAVEMENT ON WESTBOUND I-264 FROM MP 18.41 TO MP 20.701 | 5 | C | IM | 2011 | 1079000 | 1079000 | ESTIMATED | Y |  |  |  |  | 0
[6 empty] | JEFFERSON | 5-803 | I 264 | 2.291 | 18.41 | 20.701 | RELIABILITY | PAVEMENT REHAB-INT(P) | REPAIR AND GRIND I-264 EASTBOUND FROM MP 18.41 TO 20.701 | 5 | C | IM | 2011 | 2506000 | 2506000 | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.095 | 2011-07-05 | KIPDA TIP AMENDMENT #1. ADD PROJECT. NEW | STP | 2641173 | JEFFERSON | 5-804 | I 264/ US 42 | 0.5 | 21.8 | 22.3 | RELIABILITY | I-CHANGE RECONST(O) | RECONSTRUCT THE WATTERSON EXPRESSWAY INTERCHANGE AT US-42 INCLUDING SLIP RAMP TO KY 22. INTERIM OPERATIONAL IMPROVEMENTS INCLUDING SLIP RAMP FROM THE I-264 NB/US-42 EB OFF RAMP DIRECT TO KY-22 (OLD BROWNSBORO ROAD) AS RECOMMENDED BY 5-390.00 I-264/US-42 INTERCHANGE SCOPING STUDY. |  | D | STP | 2011 | 450000 | 450000 |  | Y |  | OBLIGATED | 510000 |  | 510000 | 2011 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.095 | 2011-07-05 | KIPDA TIP AMENDMENT #1. ADD D PHASE FOR FY 2013 ALSO. NEW |  |  | JEFFERSON | 5-804 | I 264/ US 42 | 0.5 | 21.8 | 22.3 | RELIABILITY | I-CHANGE RECONST(O) | RECONSTRUCT THE WATTERSON EXPRESSWAY INTERCHANGE AT US-42 INCLUDING SLIP RAMP TO KY 22. INTERIM OPERATIONAL IMPROVEMENTS INCLUDING SLIP RAMP FROM THE I-264 NB/US-42 EB OFF RAMP DIRECT TO KY-22 (OLD BROWNSBORO ROAD) AS RECOMMENDED BY 5-390.00 I-264/US-42 INTERCHANGE SCOPING STUDY. |  | D | STP | 2013 | 3500000 | 3500000 |  | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.095 | 2011-07-05 | KIPDA TIP AMENDMENT #1. ADD PROJECT. NEW |  |  | JEFFERSON | 5-804 | I 264/ US 42 | 0.5 | 21.8 | 22.3 | RELIABILITY | I-CHANGE RECONST(O) | RECONSTRUCT THE WATTERSON EXPRESSWAY INTERCHANGE AT US-42 INCLUDING SLIP RAMP TO KY 22. INTERIM OPERATIONAL IMPROVEMENTS INCLUDING SLIP RAMP FROM THE I-264 NB/US-42 EB OFF RAMP DIRECT TO KY-22 (OLD BROWNSBORO ROAD) AS RECOMMENDED BY 5-390.00 I-264/US-42 INTERCHANGE SCOPING STUDY. |  | R | STP | 2012 | 500000 | 500000 |  | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.140 | 2011-10-27 | KIPDA TIP AMENDMENT #2. MOVE FY TO 2011. MOD |  |  | JEFFERSON | 5-804 | I 264/ US 42 | 0.5 | 21.8 | 22.3 | RELIABILITY | I-CHANGE RECONST(O) | RECONSTRUCT THE WATTERSON EXPRESSWAY INTERCHANGE AT US-42 INCLUDING SLIP RAMP TO KY 22. INTERIM OPERATIONAL IMPROVEMENTS INCLUDING SLIP RAMP FROM THE I-264 NB/US-42 EB OFF RAMP DIRECT TO KY-22 (OLD BROWNSBORO ROAD) AS RECOMMENDED BY 5-390.00 I-264/US-42 INTERCHANGE SCOPING STUDY. |  | R | STP | 2011 | 500000 | 500000 |  | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.095 | 2011-07-05 | KIPDA TIP AMENDMENT #1. ADD PROJECT. NEW |  |  | JEFFERSON | 5-804 | I 264/ US 42 | 0.5 | 21.8 | 22.3 | RELIABILITY | I-CHANGE RECONST(O) | RECONSTRUCT THE WATTERSON EXPRESSWAY INTERCHANGE AT US-42 INCLUDING SLIP RAMP TO KY 22. INTERIM OPERATIONAL IMPROVEMENTS INCLUDING SLIP RAMP FROM THE I-264 NB/US-42 EB OFF RAMP DIRECT TO KY-22 (OLD BROWNSBORO ROAD) AS RECOMMENDED BY 5-390.00 I-264/US-42 INTERCHANGE SCOPING STUDY. |  | U | STP | 2012 | 400000 | 400000 |  | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.140 | 2011-10-27 | KIPDA TIP AMENDMENT #2. MOVE FY TO 2011. MOD | STP | 2641175 | JEFFERSON | 5-804 | I 264/ US 42 | 0.5 | 21.8 | 22.3 | RELIABILITY | I-CHANGE RECONST(O) | RECONSTRUCT THE WATTERSON EXPRESSWAY INTERCHANGE AT US-42 INCLUDING SLIP RAMP TO KY 22. INTERIM OPERATIONAL IMPROVEMENTS INCLUDING SLIP RAMP FROM THE I-264 NB/US-42 EB OFF RAMP DIRECT TO KY-22 (OLD BROWNSBORO ROAD) AS RECOMMENDED BY 5-390.00 I-264/US-42 INTERCHANGE SCOPING STUDY. |  | U | STP | 2011 | 400000 | 400000 |  | Y |  | OBLIGATED | 65000 |  | 65000 | 2012 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.095 | 2011-07-05 | KIPDA TIP AMENDMENT #1. ADD PROJECT. NEW |  |  | JEFFERSON | 5-804 | I 264/ US 42 | 0.5 | 21.8 | 22.3 | RELIABILITY | I-CHANGE RECONST(O) | RECONSTRUCT THE WATTERSON EXPRESSWAY INTERCHANGE AT US-42 INCLUDING SLIP RAMP TO KY 22. INTERIM OPERATIONAL IMPROVEMENTS INCLUDING SLIP RAMP FROM THE I-264 NB/US-42 EB OFF RAMP DIRECT TO KY-22 (OLD BROWNSBORO ROAD) AS RECOMMENDED BY 5-390.00 I-264/US-42 INTERCHANGE SCOPING STUDY. |  | C | STP | 2013 | 2775000 | 2775000 |  | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.140 | 2011-10-27 | KIPDA TIP AMENDMENT #2. MOVE FY TO 2012. MOD | STP | 2641174 | JEFFERSON | 5-804 | I 264/ US 42 | 0.5 | 21.8 | 22.3 | RELIABILITY | I-CHANGE RECONST(O) | RECONSTRUCT THE WATTERSON EXPRESSWAY INTERCHANGE AT US-42 INCLUDING SLIP RAMP TO KY 22. INTERIM OPERATIONAL IMPROVEMENTS INCLUDING SLIP RAMP FROM THE I-264 NB/US-42 EB OFF RAMP DIRECT TO KY-22 (OLD BROWNSBORO ROAD) AS RECOMMENDED BY 5-390.00 I-264/US-42 INTERCHANGE SCOPING STUDY. |  | C | STP | 2012 | 2775000 | 2775000 |  | Y |  | OBLIGATED | 2208000 |  | 2208000 | 2012 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.035 | 2011-01-28 | ADD PROJECT. BREAKOUT FROM 99-354.06. NEW | HSIP | 8765027 | JEFFERSON | 5-906 | KY 907 | 0.59 | 2.55 | 3.14 | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALL DRAINAGE IMPROVEMENTS TO REMOVE HAZARDOUS CONDITIONS ON THIRD STREET ROAD (KY 907) FROM 0.4 MI N OF PAGES LANE TO MITCHELL ROAD IN LOUISVILLE |  | C | SAF | 2011 | 60000 | 60000 |  |  |  | OBLIGATED | 114000 |  | 114000 | 2011 | 2nd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.099 | 2011-07-14 | ADD PROJECT TO STIP. BREAKOUT FROM KIPDA ID #1270 ON PAGE 37 OF 73 IN KIPDA'S FY 2011-2015 TIP. NEW | HSIP | 9010057 | JEFFERSON | 5-908 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | REPLACE GUARDRAIL END TREATMENTS IN JEFFERSON COUNTY: KY 1703 (MP 2.38), KY 1934 (MP 5.002), US 31W (MP 1.750, 0.346, 0.265, 2.927, 2.274, 1.901, 1.315). |  | C | SAF | 2011 | 128000 | 128000 |  |  |  | OBLIGATED | 128000 |  | 128000 | 2011 | 4th QUARTER | N/A
|  |  |  | STPM STPM STPM STPM | 3001417 3001418 3001429 3001430 | JEFFERSON | 5-965.15 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | DEDICATED FEDERAL AID STP FUNDS EARMARKED FOR LOUISVILLE URBANIZED AREA AND SUBJECT TO MPO CONTROL | 5 | C | SLO | 2013 | 6800000 | 6800000 | ESTIMATED |  |  | OBLIGATED | 2430260 |  | 2430260 | 2011 | 3rd QUARTER | KIPDA
[6 empty] | JEFFERSON | 5-965.16 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | DEDICATED FEDERAL AID STP FUNDS EARMARKED FOR LOUISVILLE URBANIZED AREA AND SUBJECT TO MPO CONTROL | 5 | C | SLO | 2014 | 12800000 | 12800000 | ESTIMATED | [5 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.095 | 2011-07-05 | KIPDA TIP AMENDMENT #1. KIPDA ID 133. ADD PROJECT - C PHASE FOR FY 2011. NEW |  |  | JEFFERSON | 5-1012.07 |  |  |  |  | RELIABILITY | CONGESTION MITIGTN(O) | INTELLIGENT TRANSPORTATION SYSTEMS (ITS) PROJECTS INCLUDING DATA COLLECTION, EVALUATION, AND IMPLEMENTATION FOR INTERSTATES AND ARTERIALS IN THE MPO AREA. |  | C | CM | 2011 | 1200000 | 1000000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.095 | 2011-07-05 | KIPDA TIP AMENDMENT #1. KIPDA ID 133. ADD PROJECT - C PHASE FOR FY 2012. NEW |  |  | JEFFERSON | 5-1012.07 |  |  |  |  | RELIABILITY | CONGESTION MITIGTN(O) | INTELLIGENT TRANSPORTATION SYSTEMS (ITS) PROJECTS INCLUDING DATA COLLECTION, EVALUATION, AND IMPLEMENTATION FOR INTERSTATES AND ARTERIALS IN THE MPO AREA. |  | C | CM | 2012 | 1200000 | 1000000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.095 | 2011-07-05 | KIPDA TIP AMENDMENT #1. KIPDA ID 133. ADD PROJECT - C PHASE FOR FY 2013. NEW |  |  | JEFFERSON | 5-1012.07 |  |  |  |  | RELIABILITY | CONGESTION MITIGTN(O) | INTELLIGENT TRANSPORTATION SYSTEMS (ITS) PROJECTS INCLUDING DATA COLLECTION, EVALUATION, AND IMPLEMENTATION FOR INTERSTATES AND ARTERIALS IN THE MPO AREA. |  | C | CM | 2013 | 1200000 | 1000000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.095 | 2011-07-05 | KIPDA TIP AMENDMENT #1. KIPDA ID 133. ADD PROJECT - C PHASE FOR FY 2014. NEW |  |  | JEFFERSON | 5-1012.07 |  |  |  |  | RELIABILITY | CONGESTION MITIGTN(O) | INTELLIGENT TRANSPORTATION SYSTEMS (ITS) PROJECTS INCLUDING DATA COLLECTION, EVALUATION, AND IMPLEMENTATION FOR INTERSTATES AND ARTERIALS IN THE MPO AREA. |  | C | CM | 2014 | 1200000 | 1000000 | [6 empty] | 0
[6 empty] | JEFFERSON | 5-1012.12 |  |  |  |  | RELIABILITY | CONGESTION MITIGTN(O) | LOUISVILLE INCIDENT MANAGEMENT PROGRAM (TRIMARC) CONSTRUCTION. (KYTC SHARE) | 5 | C | CM | 2011 | 1410000 | 1410000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | JEFFERSON | 5-1052 | US 42 | 0.1 | 0.254 | 0.265 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES OVER BEARGRASS CREEK ON EAST MAIN STREET 0.25 MILE EAST OF US 31E (BAXTER AVE.) (B347) (SR=25.3). (056B00347N) | 2 | D | BRO | 2011 | 150000 | 150000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.031 | 2011-01-18 | TIP MOD #1 . KIPDA ID# 1887-IS BREAKOUT FROM KIPDA ID #1643. ADDING PROJECT TO TIP. INCREASE FUNDING AMOUNT IN STIP. MOD |  |  | JEFFERSON | 5-1052 | US 42 | 0.1 | 0.254 | 0.265 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES OVER BEARGRASS CREEK ON EAST MAIN STREET 0.25 MILE EAST OF US 31E (BAXTER AVE.) | 2 | D | BRO | 2011 | 250000 | 250000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.034 | 2011-01-28 | KIPDA ID #1887. KIPDA MOD #2-REVISED. INCREASE FUNDING AMOUNT. MOD | BRO | 8703001 | JEFFERSON | 5-1052 | US 42 | 0.1 | 0.254 | 0.265 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES OVER BEARGRASS CREEK ON EAST MAIN STREET 0.25 MILE EAST OF US 31E (BAXTER AVE.) | 2 | D | BRO | 2011 | 265000 | 265000 | ESTIMATED | N | 2010 | OBLIGATED | 265000 |  | 265000 | 2011 | 2nd QUARTER | N/A
[6 empty] | JEFFERSON | 5-1052 | US 42 | 0.1 | 0.254 | 0.265 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES OVER BEARGRASS CREEK ON EAST MAIN STREET 0.25 MILE EAST OF US 31E (BAXTER AVE.) (B347) (SR=25.3). (056B00347N) | 4 | U | BRO | 2012 | 50000 | 50000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.031 | 2011-01-18 | TIP MOD #1 . KIPDA ID# 1887-IS BREAKOUT FROM KIPDA ID #1643. ADDING PROJECT TO TIP. NO CHANGE TO STIP. |  |  | JEFFERSON | 5-1052 | US 42 | 0.1 | 0.254 | 0.265 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES OVER BEARGRASS CREEK ON EAST MAIN STREET 0.25 MILE EAST OF US 31E (BAXTER AVE.) | 2 | U | BRO | 2012 | 50000 | 50000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | JEFFERSON | 5-1052 | US 42 | 0.1 | 0.254 | 0.265 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES OVER BEARGRASS CREEK ON EAST MAIN STREET 0.25 MILE EAST OF US 31E (BAXTER AVE.) (B347) (SR=25.3). | 5 | C | BRO | 2014 | 450000 | 450000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.031 | 2011-01-18 | TIP MOD #1 . KIPDA ID# 1887-IS BREAKOUT FROM KIPDA ID #1643. ADDING PROJECT TO TIP. NO CHANGE TO STIP. |  |  | JEFFERSON | 5-1052 | US 42 | 0.1 | 0.254 | 0.265 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES OVER BEARGRASS CREEK ON EAST MAIN STREET 0.25 MILE EAST OF US 31E (BAXTER AVE.) | 2 | C | BRO | 2014 | 450000 | 450000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.090 | 2011-06-21 | PART OF KIPDA #1643. KIPDA TIP MOD #7. CHANGE DESCRIPTION AND INCREASE C PHASE FUNDING. |  |  | JEFFERSON | 5-1056 | KY 61 |  |  |  | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 61 (MP 7.609) OVER BARLEY CREEK; 0.10 MILES NORTH OF JCT. KY 251 |  | D | BRO | 2011 | 200000 | 200000 | [6 empty] | 0
[6 empty] | JEFFERSON | 5-1061 | CR 1019 | 0.1 | 0.129 | 0.229 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON CR-1019 (MP 0.179) OVER BEE LICK CREEK; .4 MI NE-MANSLICK RD-K2055; (STRUCTURALLY DEFICIENT, SR=4) 056C00104N | 2 | D | BRZ | 2012 | 200000 | 200000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | JEFFERSON | 5-1062 |  |  |  |  | RELIABILITY | BRIDGE REHAB(P) | OLMSTED PARKS HISTORIC BRIDGES: REHABILITATE 11 BRIDGES THROUGH OLMSTED PARK: (056C00032N, 056C00031N, 056C00026N, 056C00027N, 056C00028N, 056C00030N, 056C00029N, 056C00034N, 056C00033N, 056C00139N, 056C00138N) | 2 | D | BRZ | 2012 | 200000 | 200000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | JEFFERSON | 5-2000.76 | I 264 |  | 7.4 | 7.455 | RELIABILITY | TRANSP ENHANCEMENT(P) | SHAWNEE EXPRESSWAY LANDSCAPING; I-264 AT DIXIE HIGHWAY. (2004BOPC) | 5 | C | IM | 2011 | 1020000 | 1020000 | ESTIMATED | Y |  |  |  |  | 0
[6 empty] | JEFFERSON | 5-2000.77 | I 264 | 7.8 | 0.46 | 8.22 | RELIABILITY | TRANSP ENHANCEMENT(P) | SHAWNEE EXPRESSWAY LANDSCAPING; I-264 FENCING PROJECT. (2002BOPC)(10CCR) | 5 | C | IM | 2011 | 110000 | 110000 | ESTIMATED | Y |  |  |  |  | 0
[6 empty] | JEFFERSON | 5-2038 | I 64 | 4.3 | 20.765 | 23.974 | RELIABILITY | PAVEMENT REHAB-INT(P) | MILL 1" THIN OVERLAY ON I-64 FROM MP 20.765 IN JEFFERSON COUNTY TO MP 25.094 IN SHELBY COUNTY. | 5 | C | IM | 2011 | 3330000 | 3330000 | ESTIMATED | Y | 2010 |  |  |  | 0
[6 empty] | JEFFERSON | 5-2043.01 | I 65 |  | 128.13 | 131.289 | RELIABILITY | SCOPING STUDY DD (O) | SCOPING STUDY USING CURRENT STANDARDS/POLICIES TO EVALUATE SIGNING AND LIGHTING FOR I-65 FROM MP 128.13 TO MP 131.289 (2006BOPC). | 2 | D | STP | 2011 | 100000 | 100000 | ESTIMATED |  | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.031 | 2011-01-18 | TIP MOD #1 . KIPDA ID #1459. ADDING PROJECT TO STIP. NEW |  |  | JEFFERSON | 5-2046 | I 264 | 4.66 | 8.04 | 12.7 | RELIABILITY | PAVEMENT REHAB-INT(P) | PAVEMENT REHABILITATION - REPAIR AND GRIND PAVEMENT ON I-264 FROM MP 8.04 TO MP 12.70 |  | C | NHS | 2011 | 10800000 | 10800000 |  | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.034 | 2011-01-28 | KIPDA ID #1456. KIPDA MOD #2-REVISED. ADD PROJECT. NEW |  |  | JEFFERSON | 5-2053 | I-71 | 5.55 | 0 | 5.55 | RELIABILITY | PAVEMENT REHAB-INT(P) | PAVEMENT REHABILITATION - MILL 2' INTERMEDIATE OVERLAY ON I-71 FROM MP 0.0 TO MP 5.55 |  | D | NHS | 2011 | 450000 | 450000 |  | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.034 | 2011-01-28 | KIPDA ID #1456. KIPDA MOD #2-REVISED. ADD PROJECT. NEW |  |  | JEFFERSON | 5-2053 | I-71 | 5.55 | 0 | 5.55 | RELIABILITY | PAVEMENT REHAB-INT(P) | PAVEMENT REHABILITATION - MILL 2' INTERMEDIATE OVERLAY ON I-71 FROM MP 0.0 TO MP 5.55 |  | C | IM | 2011 | 2220000 | 2220000 |  | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.090 | 2011-06-21 | KIPDA ID #1456. KIPDA TIP MOD #7. CHANGE DESCRIPTION AND INCREASE C PHASE FUNDING. MOD | IM | 0711101 | JEFFERSON | 5-2053 | I-71 | 5.55 | 0 | 5.55 | RELIABILITY | PAVEMENT REHAB-INT(P) | PAVEMENT REHABILITATION AND BRIDGE DECK REPAIRS ON I-71 FROM MP 0.0 TO MP 5.55. |  | C | IM | 2011 | 11500000 | 11500000 |  | Y |  | OBLIGATED | 11440000 |  | 11440000 | 2011 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.034 | 2011-01-28 | KIPDA ID #1437. KIPDA MOD #2-REVISED. ADD PROJECT. NEW |  |  | JEFFERSON | 5-2054 | I-265 | 1.25 | 25.35 | 26.6 | RELIABILITY | PAVEMENT REHAB-INT(P) | PAVEMENT REHABILITATION - MILL 1/2" INTERMEDIATE OVERLAY ON I-265 FROM MP 25.35 TO MP 26.60 |  | C | IM | 2010 | 1000000 | 1000000 |  | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.031 | 2011-01-18 | TIP MOD #1 . KIPDA ID #1438. ADDING PROJECT TO STIP. NEW |  |  | JEFFERSON | 5-2055 | I-265 | 4 | 26.6 | 30.637 | RELIABILITY | PAVEMENT REHAB-INT(P) | PAVEMENT REHABILITATION - REPAIR AND GRIND PAVEMENT ON I-265 FROM MP 26.6 TO MP 30.637 |  | C | IM | 2011 | 6600000 | 6600000 |  | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.141 | 2011-10-28 | TIP MOD #11. BREAKOUT PROJECT FROM KIPDA ID #173. ADD PROJECT. NEW | IM | 0649007 | JEFFERSON | 5-2059 | I-64 | 0.316 | 0 | 0.316 | RELIABILITY | BRIDGE REHAB(P) | REHABILITATION OF THE SHERMAN MINTON BRIDGE OVER THE OHIO RIVER . THIS PROJECT IS A 50/50 JOINT PROJECT WITH INDIANA DOT TO CONDUCT EMERGENCY STRUCTURE REPAIRS TO REOPEN CLOSED SHERMAN MINTON BRIDGE. INDIANA DOT WILL LET THE PROJECT TO CONSTRUCTION AND THE KYTC WILL REIMBURSE INDIANA DOT FOR 50 PERCENT OF THE PROJECT COST. (056B00279N) |  | C | IM | 2012 | 10000000 | 10000000 |  | Y |  | OBLIGATED | 10000000 | 2500000 | 12500000 | 2012 | 1st QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.185 | 2012-05-09 | TIP MOD #16. ADD AS PART OF KIPDA #173. NEW |  |  | JEFFERSON | 5-2060 | I-265 |  |  |  | RELIABILITY | BRIDGE REHAB(P) | PARTIAL AND FULL DEPTH PATCHING, LATEX MODIFIED CONCRETE OVERLAY AND JOINT REPLACEMENT ON TWIN I-265 BRIDGES OVER BROWNSBORO ROAD. |  | C | IM | 2012 | 550000 | 550000 |  | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.185 | 2012-05-09 | TIP MOD #16. ADD AS PART OF KIPDA #173. NEW |  |  | JEFFERSON | 5-2061 | I-65 |  |  |  | RELIABILITY | BRIDGE REHAB(P) | PATCH CONCRETE, POWER WASH ALL STRUCTURAL STEEL, AND CLEAN AND SEAL EXPOSED CONCRETE ON THE I-65 BRIDGE OVER BROOK AND KENTUCKY STREETS. |  | C | IM | 2012 | 485000 | 485000 |  | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.141 | 2011-10-28 | TIP MOD #11. KIPDA ID #1956. ADD DESIGN PHASE. NEW | IM | 0656082 | JEFFERSON | 5-2808 | I-65 | 4.2 | 131.2 | 135.4 | RELIABILITY | PAVEMENT REHAB-INT(P) | I-65 PAVEMENT REHABILITATION WITH BRIDGE DECK OVERLAYS AND INCIDENTAL BRIDGE JOINT WORK ON I-65 BEGINNING AT MP 131.2 AND ENDING AT MP 135.4. |  | D | IM | 2012 | 100000 | 100000 |  |  |  | OBLIGATED | 100000 |  | 100000 | 2012 | 1st QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.127 | 2011-09-29 | KIPDA TIP MOD #10. ADD AS PART OF KIPDA ID #173. NEW | IM | 0656083 | JEFFERSON | 5-2808 | I-65 | 4.2 | 131.2 | 135.4 | RELIABILITY | PAVEMENT REHAB-INT(P) | I-65 PAVEMENT REHABILITATION WITH BRIDGE DECK OVERLAYS AND INCIDENTAL BRIDGE JOINT WORK ON I-65 BEGINNING AT MP 131.2 AND ENDING AT MP 135.4. |  | C | IM | 2011 | 1000000 | 1000000 |  |  |  | OBLIGATED |  | 1000000 | 1000000 | 2011 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.127 | 2011-09-29 | KIPDA TIP MOD #10. ADD AS PART OF KIPDA ID #173. NEW | STPM | 0656083 | JEFFERSON | 5-2808 | I-65 | 4.2 | 131.2 | 135.4 | RELIABILITY | PAVEMENT REHAB-INT(P) | I-65 PAVEMENT REHABILITATION WITH BRIDGE DECK OVERLAYS AND INCIDENTAL BRIDGE JOINT WORK ON I-65 BEGINNING AT MP 131.2 AND ENDING AT MP 135.4. |  | C | SLO | 2011 | 17000000 | 17000000 |  |  |  | OBLIGATED | 17000000 | 6906300 | 23906300 | 2011 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.160 | 2012-01-31 | TIP MOD #13. KIPDA ID #1581. ADD DESIGN PHASE. NEW |  |  | JEFFERSON | 5-3013 | KY 155 |  | 8.925 | 9.77 | SAFETY | BIKE/PED FACIL(O) | KY 155 STREETSCAPE: IMPROVE STREETSCAPE, RECONSTRUCT SIDEWALKS, AND ENHANCE LANDSCAPING FROM COLLEGE DRIVE TO RUCKRIEGEL PARKWAY | 5 | D | SLO | 2012 | 122000 | 122000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | JEFFERSON | 5-3013 | KY 155 |  | 8.925 | 9.77 | SAFETY | BIKE/PED FACIL(O) | IMPROVE STREETSCAPE, RECONSTRUCT SIDEWALKS, AND ENHANCE LANDSCAPING FROM COLLEGE DRIVE TO RUCKRIEGEL PARKWAY (KIPDA ID 1581)(2008BOPC)(FUNDING SUBJECT TO FISCAL CONSTRAINT) | 5 | C | SLO | 2011 | 840000 | 840000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.141 | 2011-10-28 | TIP MOD #11. KIPDA ID #1581. CHANGE FY AND INCREASE FUNDING AMOUNT. MOD |  |  | JEFFERSON | 5-3013 | KY 155 |  | 8.925 | 9.77 | SAFETY | BIKE/PED FACIL(O) | IMPROVE STREETSCAPE, RECONSTRUCT SIDEWALKS, AND ENHANCE LANDSCAPING FROM COLLEGE DRIVE TO RUCKRIEGEL PARKWAY | 5 | C | SLO | 2012 | 1840000 | 1640000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.002 | 2010-10-01 | ADDING THIS PROJECT PER THE FY 2011-2015 TIP. NEW | STPM | 8701018 | JEFFERSON | 5-3025 | US 42 |  |  |  | SAFETY | BIKE/PED FACIL(O) | REDUCE US 42 (BROWNSBORO ROAD) FROM 4 LANES TO 3 LANES BETWEEN EWING AND LINDSAY AVENUE AND CONSTRUCT SIDEWALK ON NORTH SIDE OF US 42 BETWEEN LINDSAY AND DRESHER BRIDGE AVENUE |  | C | SLO | 2010 | 357610 | 286088 |  |  |  | OBLIGATED | 286088 |  | 286088 | 2011 | 2nd QUARTER | LOUISVILLE METRO
ADMINISTRATIVE MODIFICATION | 2010.074 | 2011-05-05 | KIPDA ID 1827. TIP MOD #5. PER TIP MOD, CHANGE FY TO 2011. MOD |  |  | JEFFERSON | 5-3025 | US 42 |  |  |  | SAFETY | BIKE/PED FACIL(O) | MODIFICATION OF US 42 (BROWNSBORO RD) BETWEEN EWING AVE. AND LINDSAY AVE., INCLUDES REDUCE THE EXISTING 4 LANE ROAD TO 3 LANES AND PROVIDE A SIDEWALK ON THE NORTH SIDE OF ROAD BETWEEN LINDSAY AND DRESHER BRIDGE AVE. |  | C | SLO | 2011 | 357610 | 286088 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.163 | 2012-02-13 | KIPDA AMENDMENT #3, ADD TO STIP. NEW | STPM | 3001428 | JEFFERSON | 5-3030 | US 60 |  |  |  | RELIABILITY | TRANSP ENHANCEMENT(P) | NORTHEAST LOUISVILLE LOOP: CONSTRUCT A SHARED USE PATH ALONG US 60 (SHELBYVILLE ROAD) FROM BECKLEY STATION TO EASTWOOD CUT-OFF. |  | D | SLO | 2012 | 662500 | 530000 |  |  |  | OBLIGATED | 530000 |  | 530000 | 2012 | 3rd QUARTER | LOUISVILLE METRO
ADMINISTRATIVE MODIFICATION | 2010.194 | 2012-05-30 | KIPDA ID 1964. TIP AMENDMENT #4. ADD C PHASE. NEW |  |  | JEFFERSON | 5-3030 | US 60 |  |  |  | RELIABILITY | TRANSP ENHANCEMENT(P) | NORTHEAST LOUISVILLE LOOP: CONSTRUCT A SHARED USE PATH ALONG US 60 (SHELBYVILLE ROAD) FROM BECKLEY STATION TO EASTWOOD CUT-OFF. |  | C | SLO | 2013 | 850000 | 680000 | [6 empty] | 0
[6 empty] | JEFFERSON | 5-8412 |  |  |  |  | SAFETY | SAFETY-RR PROTECTN(P) | CONSTRUCT A RAILROAD SAFETY CROSSING, IMPROVE LIGHTING, ERECT SIGNALS, AND ROADWAY CROSSINGS FROM THE OHIO RIVER BRIDGE CROSSING SOUTH OF ALGONQUIN PARKWAY AND THE UNIVERSITY OF LOUISVILLE. (08CCN) | 5 | C | HES | 2011 | 200000 | 200000 | ESTIMATED |  | 2010 |  |  |  | 0
[6 empty] | JEFFERSON | 5-8501 | KY 2055 |  | 1.36 | 1.42 | RELIABILITY | RECONSTRUCTION(O) | CONSTRUCT ROUNDABOUT AT WEST MANSLICK ROAD AND MT. HOLLY ROAD AT THE INTERSECTIONS OF FAIRDALE AND MITCHELL ROAD AS WELL AS PAVEMENT REHABILITATION (06CCN). (10CCR) | 3 | R | STP | 2011 | 300000 | 300000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | JEFFERSON | 5-8501 | KY 2055 |  | 1.36 | 1.42 | RELIABILITY | RECONSTRUCTION(O) | CONSTRUCT ROUNDABOUT AT WEST MANSLICK ROAD AND MT. HOLLY ROAD AT THE INTERSECTIONS OF FAIRDALE AND MITCHELL ROAD AS WELL AS PAVEMENT REHABILITATION (06CCN). (10CCR) | 4 | U | STP | 2011 | 1500000 | 1500000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | JEFFERSON | 5-8501 | KY 2055 |  | 1.36 | 1.42 | RELIABILITY | RECONSTRUCTION(O) | CONSTRUCT ROUNDABOUT AT WEST MANSLICK ROAD AND MT. HOLLY ROAD AT THE INTERSECTIONS OF FAIRDALE AND MITCHELL ROAD AS WELL AS PAVEMENT REHABILITATION (06CCN). (10CCR) | 5 | C | STP | 2011 | 2800000 | 2800000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | JEFFERSON | 5-8611 | KY 2053 | 1.501 | 0 | 1.501 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE AND WIDEN MT. WASHINGTON ROAD FROM PRESTON HIGHWAY TO PENN RUN CREEK BRIDGE. (10CCN) | 2 | D | STP | 2011 | 550000 | 550000 | ESTIMATED | [5 empty] | 0
[6 empty] | JEFFERSON | 5-8614 |  |  |  |  | RELIABILITY | TRANSP ENHANCEMENT(P) | CONSTRUCT NEW DRIVES, PARKING, AND WALKWAYS AT FARNSLEY-MOREMAN LANDING. (10CCN) | 5 | C | SLO | 2012 | 326332 | 326332 | ESTIMATED | [5 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.074 | 2011-05-05 | TIP MOD #5. KIPDA ID PART OF 1273. ADD TO STIP. NEW |  |  | JEFFERSON | [7 empty] | OLMSTED PKWYS. BICYCLE AND PEDESTRIAN IMPROVEMENTS: CONSTRUCTION OF A 1.2 MILE SHARED USE PATH SYSTEM ALONG ALGONQUIN PARKWAY BETWEEN DIXIE HWY AND SHARP AVE. |  | C | SLO | 2014 | 1250000 | 1000000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.074 | 2011-05-05 | TIP MOD #5. KIPDA ID PART OF 1273. ADD TO STIP. NEW |  |  | JEFFERSON | [7 empty] | OLMSTED PKWYS. BICYCLE AND PEDESTRIAN IMPROVEMENTS: CONSTRUCTION OF A 0.45 MILE SHARED USE PATH SYSTEM ALONG ALGONQUIN PARKWAY BETWEEN CYPRESS STREET AND DIXIE HWY. |  | C | SLO | 2013 | 1250000 | 1000000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.074 | 2011-05-05 | TIP MOD #5. KIPDA ID PART OF 1273. ADD TO STIP. NEW |  |  | JEFFERSON | [7 empty] | OLMSTED PKWYS. BICYCLE AND PEDESTRIAN IMPROVEMENTS: CONSTRUCTION OF A 0.5 MILE SHARED USE PATH SYSTEM ALONG ALGONQUIN PARKWAY BETWEEN WILSON AVENUE AND CYPRESS STREET. |  | C | SLO | 2012 | 1250000 | 1000000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.148 | 2011-12-01 | TIP MOD #12. KIPDA ID 1900. CHANGE FY 2012 TO FY 2013. MOD |  |  | JEFFERSON | [7 empty] | OLMSTED PKWYS. BICYCLE AND PEDESTRIAN IMPROVEMENTS: CONSTRUCTION OF A 0.5 MILE SHARED USE PATH SYSTEM ALONG ALGONQUIN PARKWAY BETWEEN WILSON AVENUE AND CYPRESS STREET. |  | C | SLO | 2013 | 1250000 | 1000000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.074 | 2011-05-05 | TIP MOD #5. KIPDA ID 1662. ADD TO STIP. NEW |  |  | JEFFERSON | [7 empty] | AB SAWYER GREENWAY SHARED USE PATH: CONSTRUCT A 2,800' LONG, 10' WIDE MULTIUSE PATH THROUGH A.B. SAWYER PARK AND CONNECTING TO SURROUNDING NEIGHBORHOODS INCLUDES AN UNDERPASS, BRIDGE, AND SITE AMENITIES | C | C | SLO | 2011 | 616000 | 616000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.148 | 2011-12-01 | TIP MOD #12. KIPDA ID 1662. CHANGE FY. MOD |  |  | JEFFERSON | [7 empty] | AB SAWYER GREENWAY SHARED USE PATH: CONSTRUCT A 2,800' LONG, 10' WIDE MULTIUSE PATH THROUGH A.B. SAWYER PARK AND CONNECTING TO SURROUNDING NEIGHBORHOODS INCLUDES AN UNDERPASS, BRIDGE, AND SITE AMENITIES | C | C | SLO | 2012 | 616000 | 616000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.074 | 2011-05-05 | TIP MOD #5. KIPDA ID 337. ADD TO STIP. NEW |  |  | JEFFERSON | [7 empty] | BICYCLE AND PEDESTRIAN EDUCATION, ENCOURAGEMENT, ENFORCEMENT, AND EVALUATION - DEVELOPMENT OF EDUCATIONAL AND AWARENESS PROGRAMS CONCERNING BICYCLE AND PEDESTRIAN ISSUES. PROVIDE EDUCATION AND TRAINING FOR CYCLISTS, MOTORISTS, AND CITY OFFICIALS ABOUT LAWS GOVERNING CYCLISTS' RIGHTS AND RESPONSIBILITIES. | N | N | SLO | 2011 | 150000 | 120000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.074 | 2011-05-05 | TIP MOD #5. KIPDA ID 337. ADD TO STIP. NEW |  |  | JEFFERSON | [7 empty] | BICYCLE AND PEDESTRIAN EDUCATION, ENCOURAGEMENT, ENFORCEMENT, AND EVALUATION - DEVELOPMENT OF EDUCATIONAL AND AWARENESS PROGRAMS CONCERNING BICYCLE AND PEDESTRIAN ISSUES. PROVIDE EDUCATION AND TRAINING FOR CYCLISTS, MOTORISTS, AND CITY OFFICIALS ABOUT LAWS GOVERNING CYCLISTS' RIGHTS AND RESPONSIBILITIES. | N | N | SLO | 2012 | 150000 | 120000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.212 | 2012-06-29 | TIP MOD #18. KIPDA ID 337. ADDITIONAL FUNDING. MOD |  |  | JEFFERSON | [7 empty] | BICYCLE AND PEDESTRIAN EDUCATION, ENCOURAGEMENT, ENFORCEMENT, AND EVALUATION - DEVELOPMENT OF EDUCATIONAL AND AWARENESS PROGRAMS CONCERNING BICYCLE AND PEDESTRIAN ISSUES. PROVIDE EDUCATION AND TRAINING FOR CYCLISTS, MOTORISTS, AND CITY OFFICIALS ABOUT LAWS GOVERNING CYCLISTS' RIGHTS AND RESPONSIBILITIES. | N | N | SLO | 2013 | 150000 | 120000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.212 | 2012-06-29 | TIP MOD #18. KIPDA ID 337. ADDITIONAL FUNDING. MOD |  |  | JEFFERSON | [7 empty] | BICYCLE AND PEDESTRIAN EDUCATION, ENCOURAGEMENT, ENFORCEMENT, AND EVALUATION - DEVELOPMENT OF EDUCATIONAL AND AWARENESS PROGRAMS CONCERNING BICYCLE AND PEDESTRIAN ISSUES. PROVIDE EDUCATION AND TRAINING FOR CYCLISTS, MOTORISTS, AND CITY OFFICIALS ABOUT LAWS GOVERNING CYCLISTS' RIGHTS AND RESPONSIBILITIES. | N | N | SLO | 2014 | 150000 | 120000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.212 | 2012-06-29 | TIP MOD #18. KIPDA ID 337. ADDITIONAL FUNDING. MOD |  |  | JEFFERSON | [7 empty] | BICYCLE AND PEDESTRIAN EDUCATION, ENCOURAGEMENT, ENFORCEMENT, AND EVALUATION - DEVELOPMENT OF EDUCATIONAL AND AWARENESS PROGRAMS CONCERNING BICYCLE AND PEDESTRIAN ISSUES. PROVIDE EDUCATION AND TRAINING FOR CYCLISTS, MOTORISTS, AND CITY OFFICIALS ABOUT LAWS GOVERNING CYCLISTS' RIGHTS AND RESPONSIBILITIES. | N | N | SLO | 2015 | 150000 | 120000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.074 | 2011-05-05 | TIP MOD #5. KIPDA ID 384. ADD TO STIP. NEW |  |  | JEFFERSON |  |  | 0.6 |  |  | RELIABILITY | MAJOR WIDENING(O) | WIDEN HUBBARD'S LANE FROM 2 TO 3 LANES (3RD LANE WILL BE A CENTER TURN LANE) FROM US 60 (SHELBYVILLE ROAD) TO KY 1447 (WESTPORT ROAD). ADD BIKE LANES TO HUBBARDS LANE FROM KRESGE WAY TO KY 1447. PROJECT LENGTH IS 0.6 MI. | D | D | SLO | 2011 | 343200 | 343200 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.148 | 2011-12-01 | TIP MOD #12. KIPDA ID 384. CHANGE FY TO 2012. MOD |  |  | JEFFERSON |  |  | 0.6 |  |  | RELIABILITY | MAJOR WIDENING(O) | WIDEN HUBBARD'S LANE FROM 2 TO 3 LANES (3RD LANE WILL BE A CENTER TURN LANE) FROM US 60 (SHELBYVILLE ROAD) TO KY 1447 (WESTPORT ROAD). ADD BIKE LANES TO HUBBARDS LANE FROM KRESGE WAY TO KY 1447. PROJECT LENGTH IS 0.6 MI. |  | D | SLO | 2012 | 343200 | 343200 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.074 | 2011-05-05 | TIP MOD #5. KIPDA ID 446. ADD TO STIP. NEW |  |  | JEFFERSON |  | KY 1931 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | WIDEN KY 1931 (MANSLICK RD) FROM 2 TO 4 LANES FROM KY 1931 (ST. ANDREWS CHURCH ROAD) TO I-264 (HENRY WATTERSON EXPWY). |  | D | SLO | 2012 | 1250000 | 1000000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.195 | 2012-05-30 | TIP AMENDMENT #5. KIPDA ID 446. MOVE FY TO 2013 AND REDUCE FUNDING AMOUNT. MOD |  |  | JEFFERSON |  | KY 1931 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | WIDEN KY 1931 (MANSLICK RD) FROM 2 TO 4 LANES FROM KY 1931 (ST. ANDREWS CHURCH ROAD) TO I-264 (HENRY WATTERSON EXPWY). |  | D | SLO | 2013 | 600000 | 600000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.194 | 2012-05-30 | TIP AMENDMENT #4 . ADD PROJECT. NEW |  |  | JEFFERSON |  | KY 1931 |  |  |  | RELIABILITY | SCOPING STUDY(O) | SCOPING STUDY OF THE KY 1931 CORRIDOR FROM US 31W (DIXIE HWY.) TO I-264. |  | PE | SLO | 2012 | 400000 | 400000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.074 | 2011-05-05 | TIP MOD #5. KIPDA ID 1640. ADD TO STIP. NEW |  |  | JEFFERSON | [7 empty] | OHIO RIVER LEVEE TRAIL - CONSTRUCT A SHARED USE PATH OF APPROXIMATELY 13,000 LINEAR FEET BETWEEN RIVERSIDE HISTORIC SITE AND THE MILL CREEK GENERATING STATION. |  | C | SLO | 2011 | 687500 | 687500 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.148 | 2011-12-01 | TIP MOD #12. KIPDA ID 1640. CHANGE FY TO 2012. MOD |  |  | JEFFERSON | [7 empty] | OHIO RIVER LEVEE TRAIL - CONSTRUCT A SHARED USE PATH OF APPROXIMATELY 13,000 LINEAR FEET BETWEEN RIVERSIDE HISTORIC SITE AND THE MILL CREEK GENERATING STATION. |  | C | SLO | 2012 | 687500 | 687500 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.174 | 2012-03-26 | TIP MOD #15. KIPDA ID 1423. ADD PHASE TO STIP. NEW |  |  | JEFFERSON | [7 empty] | RIVER ROAD BICYCLE & PEDESTRIAN IMPROVEMENTS FROM DOWNTOWN LOUISVILLE TO THE CITY OF PROSPECT (US 42) 8.5 MILES |  | P | SLO | 2014 | 66250 | 53000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.185 | 2012-05-09 | TIP MOD #16. KIPDA ID 1423. MOVE FY TO 2012. MOD |  |  | JEFFERSON | [7 empty] | RIVER ROAD BICYCLE & PEDESTRIAN IMPROVEMENTS FROM DOWNTOWN LOUISVILLE TO THE CITY OF PROSPECT (US 42) 8.5 MILES |  | P | SLO | 2012 | 66250 | 53000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.074 | 2011-05-05 | TIP MOD #5. KIPDA ID 1423. ADD TO STIP. NEW |  |  | JEFFERSON | [7 empty] | RIVER RD. BICYCLE & PEDESTRIAN IMPROVEMENTS: RIVER ROAD BICYCLE AND PEDESTRIAN IMPROVEMENTS FROM DOWNTOWN LOUISVILLE TO THE CITY OF PROSPECT (US 42) 8.5 MILES |  | D | SLO | 2014 | 286000 | 228800 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.083 | 2011-06-06 | TIP MOD #6. KIPDA ID 1423. DECREASE D PHASE , CHANGE FUNDING SOURCE, AND CHANGE FY. MOD |  |  | JEFFERSON | [7 empty] | RIVER ROAD BICYCLE & PEDESTRIAN IMPROVEMENTS FROM DOWNTOWN LOUISVILLE TO THE CITY OF PROSPECT (US 42) 8.5 MILES |  | D | NAT SC BYW | 2013 | 80000 | 40000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.174 | 2012-03-26 | TIP MOD #15. KIPDA ID 1423. REDUCE FY 2014 DESIGN. MOD |  |  | JEFFERSON | [7 empty] | RIVER ROAD BICYCLE & PEDESTRIAN IMPROVEMENTS FROM DOWNTOWN LOUISVILLE TO THE CITY OF PROSPECT (US 42) 8.5 MILES |  | D | SLO | 2014 | 219750 | 175800 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.083 | 2011-06-06 | TIP MOD #6. KIPDA ID 1423. ADD PHASE TO STIP. NEW |  |  | JEFFERSON | [7 empty] | RIVER ROAD BICYCLE & PEDESTRIAN IMPROVEMENTS FROM DOWNTOWN LOUISVILLE TO THE CITY OF PROSPECT (US 42) 8.5 MILES |  | R | NAT SC BYW | 2012 | 500000 | 250000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.083 | 2011-06-06 | TIP MOD #6. KIPDA ID 1423. MOVE C PHASE TO 2014. MOD |  |  | JEFFERSON | [7 empty] | RIVER ROAD BICYCLE & PEDESTRIAN IMPROVEMENTS FROM DOWNTOWN LOUISVILLE TO THE CITY OF PROSPECT (US 42) 8.5 MILES |  | C | NAT SC BYW | 2014 | 915000 | 700000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.083 | 2011-06-06 | TIP MOD #6. KIPDA ID 1647. ADD PROJECT TO STIP. NEW |  |  | JEFFERSON | [7 empty] | RIVER ROAD BICYCLE & PEDESTRIAN IMPROVEMENTS PHASE II. CONSTRUCT BICYCLE AND PEDESTRIAN IMPROVEMENTS ALONG RIVER ROAD BETWEEN ZORN AVENUE AND US 42. PHASE II IS SPECIFICALLY BETWEEN BLANKENBAKER LANE AND GLENVIEW ROAD. |  | D | CM | 2012 | 67100 | 53700 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.083 | 2011-06-06 | TIP MOD #6. KIPDA ID 1647. ADD PROJECT TO STIP. NEW |  |  | JEFFERSON | [7 empty] | RIVER ROAD BICYCLE & PEDESTRIAN IMPROVEMENTS PHASE II. CONSTRUCT BICYCLE AND PEDESTRIAN IMPROVEMENTS ALONG RIVER ROAD BETWEEN ZORN AVENUE AND US 42. PHASE II IS SPECIFICALLY BETWEEN BLANKENBAKER LANE AND GLENVIEW ROAD. |  | R | CM | 2013 | 519000 | 259500 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.083 | 2011-06-06 | TIP MOD #6. KIPDA ID 1647. ADD PROJECT TO STIP. NEW |  |  | JEFFERSON | [7 empty] | RIVER ROAD BICYCLE & PEDESTRIAN IMPROVEMENTS PHASE II. CONSTRUCT BICYCLE AND PEDESTRIAN IMPROVEMENTS ALONG RIVER ROAD BETWEEN ZORN AVENUE AND US 42. PHASE II IS SPECIFICALLY BETWEEN BLANKENBAKER LANE AND GLENVIEW ROAD. |  | U | CM | 2013 | 100000 | 80000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.083 | 2011-06-06 | TIP MOD #6. KIPDA ID 1647. ADD PROJECT TO STIP. NEW |  |  | JEFFERSON | [7 empty] | RIVER ROAD BICYCLE & PEDESTRIAN IMPROVEMENTS PHASE II. CONSTRUCT BICYCLE AND PEDESTRIAN IMPROVEMENTS ALONG RIVER ROAD BETWEEN ZORN AVENUE AND US 42. PHASE II IS SPECIFICALLY BETWEEN BLANKENBAKER LANE AND GLENVIEW ROAD. |  | C | CM | 2014 | 718400 | 574700 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.083 | 2011-06-06 | TIP MOD #6. KIPDA ID 1513. ADD PROJECT TO STIP. NEW |  |  | JEFFERSON | [7 empty] | BICYCLE PRIORITY CORRIDOR IMPROVEMENT PROJECT. IMPROVEMENTS FOR BICYCLING ON RIVER ROAD BETWEEN ZORN AVENUE AND BLANKENBAKER LANE. |  | U | CM | 2012 | 100000 | 80000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.083 | 2011-06-06 | TIP MOD #6. KIPDA ID 1513. ADD PROJECT TO STIP. NEW |  |  | JEFFERSON | [7 empty] | BICYCLE PRIORITY CORRIDOR IMPROVEMENT PROJECT. IMPROVEMENTS FOR BICYCLING ON RIVER ROAD BETWEEN ZORN AVENUE AND BLANKENBAKER LANE. |  | C | CM | 2012 | 562500 | 450000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.074 | 2011-05-05 | TIP MOD #5. KIPDA ID 329. ADD TO STIP. CHANGE DESCRIPTION IN TIP. NEW |  |  | JEFFERSON | [7 empty] | VARIOUS SIDEWALK PROJECTS IN LOUISVILLE METRO: REHABILITATION AND CONSTRUCTION OF VARIOUS SIDEWALK PROJECTS IN LOUISVILLE METRO |  | C | SLO | 2012 | 125000 | 100000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.212 | 2012-06-29 | TIP MOD #18. KIPDA ID 329. CHANGE FY AND INCREASE FUNDING AMT. MOD |  |  | JEFFERSON | [7 empty] | VARIOUS SIDEWALK PROJECTS IN LOUISVILLE METRO: REHABILITATION AND CONSTRUCTION OF VARIOUS SIDEWALK PROJECTS IN LOUISVILLE METRO |  | C | SLO | 2013 | 250000 | 200000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.074 | 2011-05-05 | TIP MOD #5. KIPDA ID 329. ADD TO STIP. CHANGE DESCRIPTION IN TIP. NEW |  |  | JEFFERSON | [7 empty] | VARIOUS SIDEWALK PROJECTS IN LOUISVILLE METRO: REHABILITATION AND CONSTRUCTION OF VARIOUS SIDEWALK PROJECTS IN LOUISVILLE METRO |  | C | SLO | 2013 | 125000 | 100000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.074 | 2011-05-05 | TIP MOD #5. KIPDA ID 329. ADD TO STIP. CHANGE DESCRIPTION IN TIP. NEW |  |  | JEFFERSON | [7 empty] | VARIOUS SIDEWALK PROJECTS IN LOUISVILLE METRO: REHABILITATION AND CONSTRUCTION OF VARIOUS SIDEWALK PROJECTS IN LOUISVILLE METRO |  | C | SLO | 2014 | 125000 | 100000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.074 | 2011-05-05 | TIP MOD #5. KIPDA ID 1582. ADD TO STIP. CHANGE FISCAL YEAR IN TIP. NEW |  |  | JEFFERSON | [7 empty] | WATTERSON TRAIL PHASE I: IMPROVE STREETSCAPE, RECONSTRUCT SIDEWALKS, AND ENHANCE LANDSCAPING FROM MAPLE ROAD TO OLD TAYLORSVILLE ROAD |  | D | SLO | 2011 | 52500 | 42000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.148 | 2011-12-01 | TIP MOD #12. KIPDA ID 1582. MOVE FY TO FY 2012. MOD |  |  | JEFFERSON | [7 empty] | WATTERSON TRAIL PHASE I: IMPROVE STREETSCAPE, RECONSTRUCT SIDEWALKS, AND ENHANCE LANDSCAPING FROM MAPLE ROAD TO OLD TAYLORSVILLE ROAD |  | D | SLO | 2012 | 52500 | 42000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.212 | 2012-06-29 | TIP MOD #18. KIPDA ID 1582. INCREASE FUNDING AMOUNT. MOD |  |  | JEFFERSON | [7 empty] | WATTERSON TRAIL PHASE I: IMPROVE STREETSCAPE, RECONSTRUCT SIDEWALKS, AND ENHANCE LANDSCAPING FROM MAPLE ROAD TO OLD TAYLORSVILLE ROAD |  | D | SLO | 2012 | 57500 | 46000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.074 | 2011-05-05 | TIP MOD #5. KIPDA ID 1582. ADD TO STIP. CHANGE FISCAL YEAR IN TIP. NEW |  |  | JEFFERSON | [7 empty] | WATTERSON TRAIL PHASE I: IMPROVE STREETSCAPE, RECONSTRUCT SIDEWALKS, AND ENHANCE LANDSCAPING FROM MAPLE ROAD TO OLD TAYLORSVILLE ROAD |  | C | SLO | 2012 | 303750 | 243000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.148 | 2011-12-01 | TIP MOD #12. KIPDA ID 1582. MOVE FY TO FY 2013. MOD |  |  | JEFFERSON | [7 empty] | WATTERSON TRAIL PHASE I: IMPROVE STREETSCAPE, RECONSTRUCT SIDEWALKS, AND ENHANCE LANDSCAPING FROM MAPLE ROAD TO OLD TAYLORSVILLE ROAD |  | C | SLO | 2013 | 303750 | 243000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.212 | 2012-06-29 | TIP MOD #18. KIPDA ID 1582. INCREASE FUNDING AMT. MOD |  |  | JEFFERSON | [7 empty] | WATTERSON TRAIL PHASE I: IMPROVE STREETSCAPE, RECONSTRUCT SIDEWALKS, AND ENHANCE LANDSCAPING FROM MAPLE ROAD TO OLD TAYLORSVILLE ROAD |  | C | SLO | 2013 | 520000 | 416000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.074 | 2011-05-05 | TIP MOD #5. KIPDA ID 1583. ADD TO STIP. CHANGE FISCAL YEAR IN TIP. NEW |  |  | JEFFERSON | [7 empty] | WATTERSON TRAIL PHASE II: WIDEN WATTERSON TRAIL FROM 2 TO 3 LANES FROM RUCKRIEGEL PARKWAY TO MAPLE ROAD |  | D | SLO | 2013 | 72600 | 58080 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.074 | 2011-05-05 | TIP MOD #5. KIPDA ID 1583. ADD TO STIP. CHANGE FISCAL YEAR IN TIP. NEW |  |  | JEFFERSON | [7 empty] | WATTERSON TRAIL PHASE II: WIDEN WATTERSON TRAIL FROM 2 TO 3 LANES FROM RUCKRIEGEL PARKWAY TO MAPLE ROAD |  | R | SLO | 2014 | 116424 | 93139 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.074 | 2011-05-05 | TIP MOD #5. KIPDA ID 1583. ADD TO STIP. CHANGE FISCAL YEAR IN TIP. NEW |  |  | JEFFERSON | [7 empty] | WATTERSON TRAIL PHASE II: WIDEN WATTERSON TRAIL FROM 2 TO 3 LANES FROM RUCKRIEGEL PARKWAY TO MAPLE ROAD |  | U | SLO | 2014 | 118976 | 95181 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.074 | 2011-05-05 | TIP MOD #5. KIPDA ID 1584. ADD TO STIP. CHANGE FISCAL YEAR IN TIP. NEW |  |  | JEFFERSON | [7 empty] | WATTERSON TRAIL PHASE III: WIDEN WATTERSON TRAIL FROM 2 TO 3 LANES FROM OLD TAYLORSVILLE ROAD TO GRAND AVENUE |  | R | SLO | 2013 | 76404 | 61123 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.074 | 2011-05-05 | TIP MOD #5. KIPDA ID 1584. ADD TO STIP. CHANGE FISCAL YEAR IN TIP. NEW |  |  | JEFFERSON | [7 empty] | WATTERSON TRAIL PHASE III: WIDEN WATTERSON TRAIL FROM 2 TO 3 LANES FROM OLD TAYLORSVILLE ROAD TO GRAND AVENUE |  | U | SLO | 2013 | 123735 | 98988 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.074 | 2011-05-05 | TIP MOD #5. KIPDA ID 1584. ADD TO STIP. CHANGE FISCAL YEAR IN TIP. NEW |  |  | JEFFERSON | [7 empty] | WATTERSON TRAIL PHASE III: WIDEN WATTERSON TRAIL FROM 2 TO 3 LANES FROM OLD TAYLORSVILLE ROAD TO GRAND AVENUE |  | C | SLO | 2014 | 352644 | 282115 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.111 | 2011-08-26 | KIPDA MOD #9. KIPDA ID 1879. ADD PROJECT TO STIP. NEW |  |  | JEFFERSON | [7 empty] | WIDEN BEULAH CHURCH ROAD FROM 2 LANES TO 3 LANES FROM I-265 TO CEDAR CREEK ROAD. |  | D | SLO | 2011 | 700000 | 700000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.148 | 2011-12-01 | KIPDA MOD #12. KIPDA ID 1879. MOVE D PHASE TO FY 2012. MOD |  |  | JEFFERSON | [7 empty] | WIDEN BEULAH CHURCH ROAD FROM 2 LANES TO 3 LANES FROM I-265 TO CEDAR CREEK ROAD. |  | D | SLO | 2012 | 700000 | 700000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.163 | 2012-02-13 | KIPDA AMENDMENT #3, KIPDA ID 1829. ADD TO STIP. NEW |  |  | JEFFERSON | [7 empty] | SYNCHRONIZATION OF TRAFFIC SIGNALS: UPGRADE AND EXPANSION OF EXISTING METRO TRAFFIC SIGNAL SYSTEM IN TERMS OF NEW AND MORE FLEXIBLE EQUIPMENT AND CENTRAL CONTROL CAPABILITIES ON A COUNTYWIDE LEVEL INCLUDING COMMUNICATIONS TO TRAFFIC SIGNALS ALONG CRITICAL SUBURBAN CORRIDORS. |  | C | TIGER | 2012 | 6250000 | 5000000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.177 | 2012-03-26 | ADD PROJECT TO STIP. NEW |  |  | JEFFERSON | [5 empty] | SAFETY | SAFETY-RR PROTECTN(P) | ADD GATES TO EXISTING FLASHING LIGHTS AND BELL SYSTEM AT NORFOLK SOUTHERN RAILROAD CROSSING ON OLD SIX MILE LANE IN JEFFERSONTOWN. (DOT# 725132P) |  | U | SAF | 2012 | 247500 | 247500 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.185 | 2012-05-09 | TIP MOD #16. ADD AS PART OF KIPDA #174. ADD PROJECT TO STIP. NEW |  |  | JEFFERSON |  | KY 362 |  |  |  | SAFETY | SAFETY-RR PROTECTN(P) | ADD GATES TO EXISTING FLASHING LIGHTS AND BELL SYSTEM AT CSX RAILROAD CROSSING ON CENTRAL AVENUE IN PEWEE VALLEY. |  | U | SAF | 2012 | 247500 | 247500 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.185 | 2012-05-09 | TIP MOD #16. ADD AS PART OF KIPDA #174. ADD PROJECT TO STIP. NEW |  |  | JEFFERSON |  | KY 362 |  |  |  | SAFETY | SAFETY-RR PROTECTN(P) | ADD GATES TO EXISTING FLASHING LIGHTS AND BELL SYSTEM AT CSX RAILROAD CROSSING ON CENTRAL AVENUE IN PEWEE VALLEY. |  | C | SAF | 2012 | 15000 | 15000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.177 | 2012-03-26 | ADD PROJECT TO STIP. NEW | RHPD | 3001427 | JEFFERSON | 99-352.07 |  |  |  |  | SAFETY | SAFETY-RR PROTECTN(P) | ADD GATES TO EXISTING FLASHING LIGHTS AND BELL SYSTEM AT NORFOLK SOUTHERN RAILROAD CROSSING ON OLD SIX MILE LANE IN JEFFERSONTOWN. (DOT# 725132P) |  | C | SAF | 2012 | 15000 | 15000 |  |  |  | OBLIGATED | 237750 |  | 237750 | 2012 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.185 | 2012-05-09 | TIP MOD #16. ADD AS PART OF KIPDA #174. ADD PROJECT TO STIP. NEW |  |  | JEFFERSON | [5 empty] | SAFETY | SAFETY-RR PROTECTN(P) | ADD GATES TO EXISTING FLASHING LIGHTS AND BELL SYSTEM AT NORFOLK SOUTHERN RAILROAD CROSSING ON OLD SIX MILE LANE IN JEFFERSONTOWN. |  | U | SAF | 2012 | 247500 | 247500 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.185 | 2012-05-09 | TIP MOD #16. ADD AS PART OF KIPDA #174. ADD PROJECT TO STIP. NEW |  |  | JEFFERSON | [5 empty] | SAFETY | SAFETY-RR PROTECTN(P) | ADD GATES TO EXISTING FLASHING LIGHTS AND BELL SYSTEM AT NORFOLK SOUTHERN RAILROAD CROSSING ON OLD SIX MILE LANE IN JEFFERSONTOWN. |  | C | SAF | 2012 | 15000 | 15000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.196 | 2012-05-30 | KIPDA AMENDMENT #6. ADD PROJECT TO STIP. NEW |  |  | JEFFERSON | [5 empty] | SAFETY | SAFETY-HAZARD ELIM(P) | KY 2860 (GRINSTEAD DRIVE) RESURFACE AND ROAD DIET: HIGHWAY SAFETY IMPROVEMENT PROJECT (HSIP) TO ADDRESS LANE DEPARTURE CRASH OCCURRENCE ON KY 2860 (GRINSTEAD DRIVE) BETWEEN US 31E (BARDSTOWN RD, MP 0.000) AND US 60A (CHEROKEE PKWY, MP 0.981). PROJECT TO INCLUDE RESURFACING WITH CLASS A SKID-RESISTANT ASPHALT, A ROAD DIET BETWEEN EVERETT AVE (MP 0.188) AND US 60A, AND INSTALLATION OF RAISED PAVEMENT MARKERS. THE EXISTING CROSS SECTION IS A FOUR-LANE TYPICAL UNDIVIDED WITH 10FT LANES. THE PROPOSED CROSS SECTION REMAINS UNCHANGED BETWEEN US 31E AND EVERETT AVE. BETWEEN EVERETT AND HILLIARD THE CROSS SECTION CHANGES TO TWO 10FT TRAVEL LANES WITH A 12FT TWO WAY LEFT TURN LANE (TWLTL) AND AN 8FT DEDICATED PARKING LANE. EAST OF HILLIARD, THE CROSS SECTION CHANGES TO TWO 10FT TRAVEL LANES WITH AN 11FT TWLTL AND 4.5FT BIKE LANES ON BOTH SIDES. |  | C | SAF | 2012 | 300000 | 300000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.212 | 2012-06-29 | KIPDA MOD #18. KIPDA ID 1374. ADD PROJECT TO STIP AS VARIOUS SIDEWALK PROJECTS. NEW |  |  | JEFFERSON | [7 empty] | SIDEWALK, PEDESTRIAN FACILITIES AND STREETSCAPE IMPROVEMENTS IN THE VICINITY OF THE HAYMARKET BLOCK IN DOWNTOWN LOUISVILLE. BLOCK BOUNDED BY MARKET STREET, FLOYD STREET, JEFFERSON STREET, AND PRESTON STREET. FY 2005 SECTION 117 FEDERAL EARMARK FUNDS. |  | C | KYD | 2012 | 491964 | 491964 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.111 | 2011-08-26 | KIPDA MOD #9. KIPDA ID 1270. ADD PROJECT TO STIP. NEW |  |  | JEFFERSON BULLITT OLDHAM | [7 empty] | VARIOUS SAFETY PROJECTS IN THE LOUISVILLE URBANIZED AREA. |  | C | SLO | 2012 | 625000 | 500000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.212 | 2012-06-29 | KIPDA MOD #18. KIPDA ID 1270. REDUCE C PHASE FOR FY 2012. MOD |  |  | JEFFERSON BULLITT OLDHAM | [7 empty] | VARIOUS SAFETY PROJECTS IN THE LOUISVILLE URBANIZED AREA. |  | C | SLO | 2012 | 130000 | 104000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.111 | 2011-08-26 | KIPDA MOD #9. KIPDA ID 1270. ADD PROJECT TO STIP. NEW |  |  | JEFFERSON BULLITT OLDHAM | [7 empty] | VARIOUS SAFETY PROJECTS IN THE LOUISVILLE URBANIZED AREA. |  | C | SLO | 2013 | 625000 | 500000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.111 | 2011-08-26 | KIPDA MOD #9. KIPDA ID 1270. ADD PROJECT TO STIP. NEW |  |  | JEFFERSON BULLITT OLDHAM | [7 empty] | VARIOUS SAFETY PROJECTS IN THE LOUISVILLE URBANIZED AREA. |  | C | SLO | 2014 | 625000 | 500000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.163 | 2012-02-13 | KIPDA AMENDMENT #3. KIPDA ID 1643. ADD PROJECT TO STIP. NEW |  |  | JEFFERSON BULLITT OLDHAM | [7 empty] | VARIOUS BRIDGE INSPECTION, REPAIR, AND REPLACEMENT PROJECTS: GENERAL CATEGORY NEEDED FOR BRIDGE INSPECTION, REPAIR, AND REPLACEMENT PROJECTS THAT ARE AIR QUALITY EXEMPT AND NOT REGIONALLY SIGNIFICANT |  | C | BR | 2011 | 4375000 | 4375000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.163 | 2012-02-13 | KIPDA AMENDMENT #3. KIPDA ID 1553. ADD PROJECT TO STIP. NEW |  |  | JEFFERSON BULLITT OLDHAM | [7 empty] | INSTALLATION OF REFERENCE MARKERS AT VARIOUS LOCATIONS IN THE LOUISVILLE MPO REGION |  | C | NHS | 2012 | 5000 | 5000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.163 | 2012-02-13 | KIPDA AMENDMENT #3. KIPDA ID 1553. ADD PROJECT TO STIP. NEW |  |  | JEFFERSON BULLITT OLDHAM | [7 empty] | INSTALLATION OF REFERENCE MARKERS AT VARIOUS LOCATIONS IN THE LOUISVILLE MPO REGION |  | C | NHS | 2013 | 5000 | 5000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.163 | 2012-02-13 | KIPDA AMENDMENT #3. KIPDA ID 1553. ADD PROJECT TO STIP. NEW |  |  | JEFFERSON BULLITT OLDHAM | [7 empty] | INSTALLATION OF REFERENCE MARKERS AT VARIOUS LOCATIONS IN THE LOUISVILLE MPO REGION |  | C | NHS | 2014 | 5000 | 5000 | [6 empty] | 0
[6 empty] | JESSAMINE | 7-87.1 |  | 4.3 |  |  | RELIABILITY | NEW ROUTE(O) | EAST NICHOLASVILLE BYPASS SECTION I; FROM US-27 NORTH OF NICHOLASVILLE, EXTENDING SOUTHEASTERLY TO KY-39. (2000BOP)(04CCR)(06CCR)(08CCR)(10CCR) | 3 | R | STP | 2011 | 35890000 | 35890000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.045 | 2011-03-02 | LEXINGTON MPO TIP AMENDMENT #1 REVISED THE TIP TO MATCH THE STIP. UTILITY PHASE IS IN THE REGIONALLY SIGNIFICANT SECTION OF THE STIP-NO CHANGE TO STIP. | STP | 0271080 | JESSAMINE | 7-87.1 |  | 4.3 |  |  | RELIABILITY | NEW ROUTE(O) | EAST NICHOLASVILLE BYPASS SECTION I; FROM US-27 NORTH OF NICHOLASVILLE, EXTENDING SOUTHEASTERLY TO KY-39. (2000BOP)(04CCR)(06CCR)(08CCR)(10CCR) | 3 | R | STP | 2011 | 35890000 | 35890000 | ESTIMATED | N |  | OBLIGATED | 10000000 | 21000000 | 31000000 | 2012 | 3rd QUARTER | N/A
[6 empty] | JESSAMINE | 7-237 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | CONSTRUCT PEDESTRIAN MALL AND STREETSCAPE IMPROVEMENTS ON LEXINGTON, COLLEGE, WALNUT AND GILESPIE STS, WILMORE. (2005HPP-KY123)(MOA WITH WILMORE). | 5 | C | HPP | 2011 | 2347287 | 2347287 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.045 | 2011-03-02 | LEXINGTON MPO TIP AMENDMENT #1 REVISED THE TIP TO MATCH THE STIP. | HPP | 0123012 | JESSAMINE | 7-237 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | CONSTRUCT PEDESTRIAN MALL AND STREETSCAPE IMPROVEMENTS ON LEXINGTON, COLLEGE, WALNUT AND GILESPIE STS, WILMORE. (2005HPP-KY123)(MOA WITH WILMORE). | 5 | C | HPP | 2011 | 2347287 | 2347287 | ESTIMATED | N | 2010 | OBLIGATED | 2192288 |  | 2192288 | 2012 | 2nd QUARTER | CITY OF WILMORE
[6 empty] | FAYETTE | 7-8507 | CS 2548 |  |  |  | RELIABILITY | NEW ROUTE(O) | COMPLETE CONSTRUCTION ON POLO CLUB BOULEVARD AT DEERHAVEN LANE AND TODDS ROAD. (08CCN)(FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | 5 | C | SLX | 2013 | 3954122 | 3954122 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | JESSAMINE | 7-396 | KY 129 |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | WILMORE DOWNTOWN DRAINAGE AND STREET IMPROVEMENTS. (2008BOPC)(FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | 3 | R | SLX | 2011 | 50000 | 50000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | JESSAMINE | 7-396 | KY 129 |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | WILMORE DOWNTOWN DRAINAGE AND STREET IMPROVEMENTS. (2008BOPC)(FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | 4 | U | SLX | 2011 | 125000 | 125000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | JESSAMINE | 7-396 | KY 129 |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | WILMORE DOWNTOWN DRAINAGE AND STREET IMPROVEMENTS. (2008BOPC)(FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | 5 | C | SLX | 2011 | 275000 | 275000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | JESSAMINE | 7-397 | KY 29 |  | 8.15 | 8.31 | SAFETY | SAFETY(P) | TURN LANES AT W. JESSAMINE HIGH SCHOOL AND E. JESSAMINE MIDDLE SCHOOL. (2008BOPC)(FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | 5 | C | SLX | 2011 | 20000 | 20000 | ESTIMATED | Y | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.045 | 2011-03-02 | LEXINGTON MPO TIP AMENDMENT #1. REVISED THE TIP TO MATCH THE STIP. |  |  | JESSAMINE | 7-397 | KY 29 |  | 8.15 | 8.31 | SAFETY | SAFETY(P) | TURN LANES AT W. JESSAMINE HIGH SCHOOL AND E. JESSAMINE MIDDLE SCHOOL. (2008BOPC)(FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | 5 | C | SLX | 2011 | 20000 | 20000 | ESTIMATED | Y | 2010 |  |  |  | 0
[6 empty] | JESSAMINE | 7-398 | KY 169 |  | 14.85 | 14.95 | RELIABILITY | CULVERT REPLACMENT(P) | CULVERT REPLACEMENT ON KY 169, 0.500 MILE WEST OF US 68. (2008BOPC) (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | 3 | R | SLX | 2011 | 40000 | 40000 | ESTIMATED | Y | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.014 | 2010-11-05 | TIP MOD #12. ADD $60,000 IN SLX FUNDS AND CHANGE FY TO 2011. MOD | STPM | 5191003 | JESSAMINE | 7-398 | KY 169 |  | 14.85 | 14.95 | RELIABILITY | CULVERT REPLACMENT(P) | CULVERT REPLACEMENT ON KY 169, 0.500 MILE WEST OF US 68. (2008BOPC) (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | 3 | R | SLX | 2011 | 100000 | 100000 | ESTIMATED | Y |  | OBLIGATED | 100000 |  | 100000 | 2011 | 4th QUARTER | N/A
[6 empty] | JESSAMINE | 7-398 | KY 169 |  | 14.85 | 14.95 | RELIABILITY | CULVERT REPLACMENT(P) | CULVERT REPLACEMENT ON KY 169, 0.500 MILE WEST OF US 68. (2008BOPC) (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | 4 | U | SLX | 2011 | 100000 | 100000 | ESTIMATED | Y | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.045 | 2011-03-02 | LEXINGTON MPO TIP AMENDMENT #1 MADE REVISIONS TO TIP CHANGING FY TO 2011 FOR R, U, AND C PHASES. STIP HAD CORRECT INFO. | STPM | 5191002 | JESSAMINE | 7-398 | KY 169 |  | 14.85 | 14.95 | RELIABILITY | CULVERT REPLACMENT(P) | CULVERT REPLACEMENT ON KY 169, 0.500 MILE WEST OF US 68. (2008BOPC) (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | 4 | U | SLX | 2011 | 100000 | 100000 | ESTIMATED | Y | 2010 | OBLIGATED | 100000 |  | 100000 | 2011 | 4th QUARTER | N/A
[6 empty] | JESSAMINE | 7-398 | KY 169 |  | 14.85 | 14.95 | RELIABILITY | CULVERT REPLACMENT(P) | CULVERT REPLACEMENT ON KY 169, 0.500 MILE WEST OF US 68. (2008BOPC) (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | 4 | C | SLX | 2011 | 220000 | 220000 | ESTIMATED | Y | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.045 | 2011-03-02 | LEXINGTON MPO TIP AMENDMENT #1 MADE REVISIONS TO TIP CHANGING FY TO 2011 FOR R, U, AND C PHASES. STIP HAD CORRECT INFO. | STPM | 5191005 | JESSAMINE | 7-398 | KY 169 |  | 14.85 | 14.95 | RELIABILITY | CULVERT REPLACMENT(P) | CULVERT REPLACEMENT ON KY 169, 0.500 MILE WEST OF US 68. (2008BOPC) (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | 5 | C | SLX | 2011 | 220000 | 220000 | ESTIMATED | Y | 2010 | OBLIGATED | 295536 |  | 295536 | 2012 | 2nd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.105 | 2011-08-23 | TIP MOD #19. ADD PROJECT TO STIP. NEW | FBD | 3000906 | JESSAMINE MADISON FAYETTE | 7-409 |  |  |  |  | RELIABILITY | FERRY OPERATION(P) | VALLEY VIEW FERRY TOWBOAT REPLACEMENT |  | N | FBD | 2011 | 750000 | 600000 |  |  |  | OBLIGATED | 600000 |  | 600000 | 2011 | 4th QUARTER | N/A
[6 empty] | JESSAMINE | 7-8404 | US 27 |  |  |  | RELIABILITY | NEW ROUTE(O) | CONSTRUCT A NEW 4 LANE CONNECTOR BETWEEN US-27 AND I-75. (08CCN) | 1 | P | STP | 2011 | 500000 | 500000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | JOHNSON | 12-134.02 | KY 172 |  | 9.132 | 9.232 | RELIABILITY | RECONSTRUCTION(O) | FEDERAL HIGHWAY FUNDS DEDICATED TO RECONSTRUCT STONE COAL ROAD IN JOHNSON COUNTY. ("KYD" FUNDS NOT AVAILABLE FOR ADDITIONAL AMOUNT NEEDED TO COVER COST) | 5 | C | KYD | 2012 | 45762 | 45762 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.094 | 2011-06-28 | ADD TO STIP. NEW | HSIP | 5387010 | JOHNSON | 12-924 | KY 40 | 7.034 | 16.232 | 23.27 | SAFETY | SAFETY-HAZARD ELIM(P) | SAFETY IMPROVEMENTS ON KY40 FROM BUFFALO-PIGEON ROOST ROAD (MP 16.232) TO 0.3MI WEST OF THE MARTIN COUNTY LINE. |  | C | SAF | 2011 | 475000 | 475000 |  |  |  | OBLIGATED | 475000 |  | 475000 | 2011 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.171 | 2012-03-13 | ADD PROJECT TO STIP. BREAKOUT FROM 99-911.01. NEW | HSIP | 5328008 | JOHNSON | 12-930 | KY 172 | 2.42 | 9.95 | 12.37 | SAFETY | SAFETY-HAZARD ELIM(P) | DITCHING AND SHOULDERING, EXTEND/REPLACE DRAINAGE STRUCTURES AND EXCAVATE TO IMPROVE SIGHT DISTANCE AT VARIOUS LOCATIONS ON KY 172 FROM KY 1559 EAST OF VOLGA TO KY 40 WEST OF STAFFORDSVILLE. |  | C | SAF | 2012 | 279000 | 279000 |  |  |  | OBLIGATED | 280000 |  | 280000 | 2012 | 3rd QUARTER | N/A
|  |  |  | BRZ | 1203320 | JOHNSON | 12-1086 | KY 3387 | 0.1 | 0.549 | 0.555 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-3387 OVER FROGONERY BRANCH (B66). (SR=5.9): (058B00066N) | 3 | R | BRX | 2011 | 230000 | 230000 | ESTIMATED | N | 2010 | OBLIGATED | 30450 |  | 30450 | 2010 | 4th QUARTER | N/A
|  |  |  | BRZ | 1203321 | JOHNSON | 12-1086 | KY 3387 | 0.1 | 0.549 | 0.555 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-3387 OVER FROGONERY BRANCH (B66). (SR=5.9): (058B00066N) | 4 | U | BRX | 2011 | 160000 | 160000 | ESTIMATED | N | 2010 | OBLIGATED | 45000 |  | 45000 | 2010 | 4th QUARTER | N/A
[6 empty] | JOHNSON | 12-1086 | KY 3387 | 0.1 | 0.549 | 0.555 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-3387 OVER FROGONERY BRANCH (B66). (SR=5.9): (058B00066N) | 5 | C | BRX | 2011 | 350000 | 350000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | KENTON | 6-17.04 | I 75 |  | 191.277 | 191.777 | RELIABILITY | BRIDGE REPLACEMENT(P) | TRANSPORTATION IMPROVEMENTS TO BRENT SPENCE BRIDGE. (2005HPP-KY154)(SEE 6-17.03 FOR ADDITIONAL 2005HPP FUNDING): (059B00046N) | 3 | R | HPP | 2011 | 16540000 | 16540000 | ESTIMATED | Y | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.017 | 2010-11-18 | TIP AMENDMENT #31. ADD RIGHT-OF-WAY PHASE TO TIP. MOD |  |  | KENTON | 6-17.04 | I 75 |  | 191.277 | 191.777 | RELIABILITY | BRIDGE REPLACEMENT(P) | TRANSPORTATION IMPROVEMENTS TO THE BRENT SPENCE BRIDGE. TOLL CREDITS | 3 | R | HPP | 2011 | 16540000 | 16540000 | ESTIMATED | Y | 2010 |  |  |  | 0
[6 empty] | KENTON | 6-17.04 | I 75 |  | 191.277 | 191.777 | RELIABILITY | BRIDGE REPLACEMENT(P) | TRANSPORTATION IMPROVEMENTS TO BRENT SPENCE BRIDGE. (2005HPP-KY154)(SEE 6-17.03 FOR ADDITIONAL 2005HPP FUNDING): (059B00046N) | 4 | U | HPP | 2011 | 4300000 | 4300000 | ESTIMATED | Y | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.017 | 2010-11-18 | TIP AMENDMENT #31. ADD UTILITY PHASE TO TIP. MOD |  |  | KENTON | 6-17.04 | I 75 |  | 191.277 | 191.777 | RELIABILITY | BRIDGE REPLACEMENT(P) | TRANSPORTATION IMPROVEMENTS TO THE BRENT SPENCE BRIDGE. TOLL CREDITS | 3 | U | HPP | 2011 | 4300000 | 4300000 | ESTIMATED | Y | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.016 | 2010-11-15 | TIP MOD #31. ADD PROJECT. NEW |  |  | KENTON | 6-287 |  |  |  |  | RELIABILITY | CONGESTION MITIGTN(O) | KYLES LANE: ROADWAY REALIGNMENT |  | R | CM | 2011 | 500000 | 500000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.016 | 2010-11-15 | TIP MOD #31. ADD PROJECT. NEW |  |  | KENTON | 6-287 |  |  |  |  | RELIABILITY | CONGESTION MITIGTN(O) | KYLES LANE: ROADWAY REALIGNMENT |  | U | CM | 2011 | 100000 | 100000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.016 | 2010-11-15 | TIP MOD #31. ADD PROJECT. NEW |  |  | KENTON | 6-287 |  |  |  |  | RELIABILITY | CONGESTION MITIGTN(O) | KYLES LANE: ROADWAY REALIGNMENT |  | C | CM | 2011 | 1100000 | 1100000 | [6 empty] | 0
|  |  | ADDED OBLIGATED AMOUNT FOR THIS PHASE TO STIP PER SIGNED PR-1 ON 11/22/11. | CM | 8122024 | KENTON | 6-361 | KY 1303 |  | 5.55 | 5.609 | RELIABILITY | CONGESTION MITIGTN(O) | EXTEND THE RIGHT TURN LANE ON NORTHBOUND TURKEYFOOT ROAD (KY-1303) TO THE I-275 EASTBOUND RAMP. (2006BOPC) | 5 | R | CM | 2012 | 350000 | 350000 | ESTIMATED | N |  | OBLIGATED | 350000 |  | 350000 | 2012 | 1st QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.151 | 2011-12-14 | TIP MOD #6. ADD UTILITY PHASE. NEW | CM | 8122025 | KENTON | 6-361 | KY 1303 |  | 5.55 | 5.609 | RELIABILITY | CONGESTION MITIGTN(O) | EXTEND THE RIGHT TURN LANE ON NORTHBOUND TURKEYFOOT ROAD (KY-1303) TO THE I-275 EASTBOUND RAMP. (2006BOPC) | 5 | U | CM | 2012 | 255000 | 255000 | ESTIMATED | N |  | OBLIGATED | 255000 |  | 255000 | 2012 | 1st QUARTER | N/A
|  |  |  | CM CM | 8120039 8122026 | KENTON | 6-361 | KY 1303 |  | 5.55 | 5.609 | RELIABILITY | CONGESTION MITIGTN(O) | EXTEND THE RIGHT TURN LANE ON NORTHBOUND TURKEYFOOT ROAD (KY-1303) TO THE I-275 EASTBOUND RAMP. (2006BOPC) | 5 | C | CM | 2011 | 1310000 | 1310000 | ESTIMATED | N | 2010 | OBLIGATED | 1056800 |  | 1056800 | 2011 | 2nd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.016 | 2010-11-15 | TIP MOD #31. ADD PHASE. NEW |  |  | KENTON | 6-362 | KY 1303 |  | 5.7 | 5.797 | RELIABILITY | CONGESTION MITIGTN(O) | WIDEN THE IR 275 WB ON RAMP FROM TURKEYFOOT ROAD FOR DUAL LEFT TURNS. TOLL CREDITS. | 5 | R | CM | 2011 | 50000 | 50000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.016 | 2010-11-15 | TIP MOD #31. ADD PHASE. NEW |  |  | KENTON | 6-362 | KY 1303 |  | 5.7 | 5.797 | RELIABILITY | CONGESTION MITIGTN(O) | WIDEN THE IR 275 WB ON RAMP FROM TURKEYFOOT ROAD FOR DUAL LEFT TURNS. TOLL CREDITS. | 5 | U | CM | 2011 | 50000 | 50000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | KENTON | 6-362 | KY 1303 |  | 5.7 | 5.797 | RELIABILITY | CONGESTION MITIGTN(O) | WIDEN THE I-275 WESTBOUND ON RAMP FROM TURKEYFOOT ROAD (KY-1303) TO ALLOW A DUAL LEFT TURN LANE FROM NORTHBOUND TURKEYFOOT ROAD. (2006BOPC). | 5 | C | CM | 2011 | 750000 | 750000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.016 | 2010-11-15 | TIP MOD #31. CHANGE DESCRIPTION, FY, AND AMOUNT. MOD | CM | 2759125 | KENTON | 6-362 | KY 1303 |  | 5.7 | 5.797 | RELIABILITY | CONGESTION MITIGTN(O) | WIDEN THE IR 275 WB ON RAMP FROM TURKEYFOOT ROAD FOR DUAL LEFT TURNS. TOLL CREDITS. | 5 | C | CM | 2011 | 600000 | 600000 | ESTIMATED | N |  | OBLIGATED | 613000 |  | 613000 | 2012 | 3rd QUARTER | N/A
[6 empty] | KENTON | 6-363 | US 25 |  | 7.1 | 7.15 | RELIABILITY | CONGESTION MITIGTN(O) | CONSTRUCT A RIGHT TURN LANE ON US-25 (DIXIE HIGHWAY) AT THE DUDLEY PIKE INTERSECTION. (2006BOPC). | 5 | C | CM | 2011 | 1240000 | 1240000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.016 | 2010-11-15 | TIP MOD #31. CHANGE TIP AMOUNT AND DESCRIPTION, MOD |  |  | KENTON | 6-363 | US 25 |  | 7.1 | 7.15 | RELIABILITY | CONGESTION MITIGTN(O) | CONSTRUCT RIGHT TURN LANE ON DIXIE HIGHWAY TO DUDLEY PIKE. | 5 | C | CM | 2011 | 1240000 | 1240000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | KENTON | 6-1070 | CS 2097 | 0.1 | 0.164 | 0.198 | SAFETY | BRIDGE REPLACEMENT(P) | WEST 15TH STREET; REPLACE BRIDGE AND APPROACHES OVER CSX RR IN COVINGTON (C29). (SR=3.9): (059C00029N) | 2 | D | BRZ | 2011 | 200000 | 200000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.017 | 2010-11-18 | TIP AMENDMENT #31. ADD TO TIP. MOD | BRO | 8164001 | KENTON | 6-1070 | CS 2097 | 0.1 | 0.164 | 0.198 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES OVER CSX RR IN COVINGTON. TOLL CREDITS | 2 | D | BRZ | 2011 | 200000 | 200000 | ESTIMATED | N |  | OBLIGATED | 200000 |  | 200000 | 2012 | 3rd QUARTER | N/A
[6 empty] | KENTON | 6-1070 | CS 2097 | 0.1 | 0.164 | 0.198 | RELIABILITY | BRIDGE REPLACEMENT(P) | WEST 15TH STREET; REPLACE BRIDGE AND APPROACHES OVER CSX RR IN COVINGTON (C29). (SR=3.9) | 3 | R | BRZ | 2013 | 200000 | 200000 | ESTIMATED | [5 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.017 | 2010-11-18 | TIP AMENDMENT #31. ADD TO TIP. MOD |  |  | KENTON | 6-1070 | CS 2097 | 0.1 | 0.164 | 0.198 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES OVER CSX RR IN COVINGTON. TOLL CREDITS | 2 | R | BRZ | 2013 | 200000 | 200000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | KENTON | 6-1070 | CS 2097 | 0.1 | 0.164 | 0.198 | RELIABILITY | BRIDGE REPLACEMENT(P) | WEST 15TH STREET; REPLACE BRIDGE AND APPROACHES OVER CSX RR IN COVINGTON (C29). (SR=3.9) | 4 | U | BRZ | 2013 | 150000 | 150000 | ESTIMATED | [5 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.017 | 2010-11-18 | TIP AMENDMENT #31. ADD TO TIP. MOD |  |  | KENTON | 6-1070 | CS 2097 | 0.1 | 0.164 | 0.198 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES OVER CSX RR IN COVINGTON. TOLL CREDITS | 2 | U | BRZ | 2013 | 150000 | 150000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.170 | 2012-03-22 | TIP AMENDMENT #6. ADD PHASE. NEW |  |  | KENTON | 6-1070 | CS 2097 | 0.1 | 0.164 | 0.198 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES OVER CSX RR IN COVINGTON. TOLL CREDITS | 2 | C | BRZ | 2015 | 1305000 | 1305000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | KENTON | 6-1075 | KY 1120 | 0.1 | 0.571 | 0.671 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-1120 (MP 0.621) OVER CSX RAILROAD; 11TH ST E OF RUSSELL ST; (STRUCTURALLY DEFICIENT, SR=3) 059B00083N | 2 | D | BRO | 2012 | 170000 | 170000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.030 | 2011-01-27 | OKI TIP AMENDMENT #32. ADD PROJECT TO TIP. CHANGE FY IN STIP. MOD | BRO | 0273016 | KENTON | 6-1075 | KY 1120 | 0.1 | 0.571 | 0.671 | RELIABILITY | BRIDGE REPLACEMENT(P) | BRIDGE REPLACEMENT ON KY 1120 OVER CSX RAILROAD; 11TH STREET EAST OF RUSSELL STREET. (TOLL CREDITS) | 2 | D | BRO | 2011 | 170000 | 170000 | ESTIMATED | N |  | OBLIGATED | 170000 |  | 170000 | 2011 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.170 | 2012-03-22 | TIP AMENDMENT #6. ADD CONSTRUCTION PHASE. NEW |  |  | KENTON | 6-1075 | KY 1120 | 0.1 | 0.571 | 0.671 | RELIABILITY | BRIDGE REPLACEMENT(P) | BRIDGE REPLACEMENT ON KY 1120 OVER CSX RAILROAD; 11TH STREET EAST OF RUSSELL STREET. (TOLL CREDITS) | 2 | C | BRO | 2015 | 1000000 | 1000000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.210 | 2012-06-27 | OKI TIP AMENDMENT #9 FY 2012-15. ADD PROJECT. NEW |  |  | KENTON | 6-1080 | KY 2045 |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON PRUETT RD (KY 2045) OVER DECOURSEY CREEK AT JCT WITH MARSHALL RD (CS 1007)(SR 18.2) 059B00030N |  | D | BRO | 2013 | 350000 | 350000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.210 | 2012-06-27 | OKI TIP AMENDMENT #9 FY 2012-15. ADD PROJECT. NEW |  |  | KENTON | 6-1080 | KY 2045 |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON PRUETT RD (KY 2045) OVER DECOURSEY CREEK AT JCT WITH MARSHALL RD (CS 1007)(SR 18.2) 059B00030N |  | R | BRO | 2014 | 50000 | 50000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.210 | 2012-06-27 | OKI TIP AMENDMENT #9 FY 2012-15. ADD PROJECT. NEW |  |  | KENTON | 6-1080 | KY 2045 |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON PRUETT RD (KY 2045) OVER DECOURSEY CREEK AT JCT WITH MARSHALL RD (CS 1007)(SR 18.2) 059B00030N |  | U | BRO | 2014 | 50000 | 50000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.015 | 2010-11-15 | BREAKOUT PROJECT FROM ZVARIOUS 99-337.05 IN STIP AND LINE ITEM IN OKI TIP PAGE 27: VARIOUS;BOONE, CAMPBELL, AND KENTON COUNTIES; OPERATIONS PROJECTS ELIGIBLE FOR RESURFACING, RESTORATION, AND REHABILITATION. NEW | IM | 0757135 | KENTON | 6-2034 | I-75 | 3.176 | 166.263 | 169.439 | RELIABILITY | PAVEMENT REHAB-INT(P) | MILL 1.5" AND RESURFACE ON I-75 NB FROM MP 166.263 TO MP 169.439 AND ALL ADJACENT RAMPS IN KENTON COUNTY. |  | D | IM | 2011 | 5000 | 5000 |  | Y |  | OBLIGATED | 5000 |  | 5000 | 2011 | 1st QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.015 | 2010-11-15 | BREAKOUT PROJECT FROM ZVARIOUS 99-337.05 IN STIP AND LINE ITEM IN OKI TIP PAGE 27: VARIOUS;BOONE, CAMPBELL, AND KENTON COUNTIES; OPERATIONS PROJECTS ELIGIBLE FOR RESURFACING, RESTORATION, AND REHABILITATION. NEW | IM | 0757136 | KENTON | 6-2034 | I-75 | 3.176 | 166.263 | 169.439 | RELIABILITY | PAVEMENT REHAB-INT(P) | MILL 1.5" AND RESURFACE ON I-75 NB FROM MP 166.263 TO MP 169.439 AND ALL ADJACENT RAMPS IN KENTON COUNTY. |  | C | IM | 2011 | 800000 | 800000 |  | Y |  | OBLIGATED | 726426.18 |  | 726426.18 | 2011 | 2nd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.170 | 2012-03-22 | TIP AMENDMENT #6. ADD PROJECT TO STIP. NEW |  |  | KENTON | [5 empty] | RELIABILITY | SIGNAL SYS IMPROVE(P) | SIGNAL UPGRADE PROJECT IN EDGEWOOD ALONG DUDLEY ROAD AND THOMAS MORE PARKWAY. |  | C | SNK | 2013 | 50960 | 50960 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.099 | 2011-07-14 | ADD PROJECT TO STIP. BREAKOUT FROM 99-911.00. NEW | HSIP | 9010062 | KNOTT LETCHER | 12-925 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | REPLACE GUARDRAIL END TREATMENTS ON VARIOUS ROUTES: KNOTT KY 15 (MP 0.00-9.329), KY 80 (MP 0.00-20.093), LETCHER US 119 (MP 0.00-27.917), KY 15 (MP 0.00-10.675), KY 7 (MP 14.157-15.295), US 23 (MP 0.00-7.319). |  | C | SAF | 2011 | 545000 | 545000 |  |  |  | OBLIGATED | 545000 |  | 545000 | 2011 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.161 | 2012-01-31 | ADD PROJECT TO STIP. NEW | HSIP | 9010071 | KNOTT | 12-927 | KY 1393 |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | REPAIR SUPER ELEVATION AND APPLY HIGH FRICTION TREATMENT ON KY-1393 AT JCT. HEAD OF BRANHAMS BR. ROAD |  | C | SAF | 2012 | 35000 | 35000 |  |  |  | OBLIGATED | 131877 |  | 131877 | 2012 | 3rd QUARTER | N/A
|  |  |  | BRZ | 1203342 | KNOTT | 12-1082 | CR 1137 | 0.1 | 0 | 0.039 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON CR-5137 OVER STEER FORK (C62). (SR=14.7): (060C00062N) | 3 | R | BRZ | 2011 | 230000 | 230000 | ESTIMATED | N | 2010 | OBLIGATED |  | 62500 | 62500 | 2012 | 1st QUARTER | N/A
[6 empty] | KNOTT | 12-1082 | CR 1137 | 0.1 | 0 | 0.039 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON CR-5137 OVER STEER FORK (C62). (SR=14.7): (060C00062N) | 4 | U | BRZ | 2011 | 210000 | 210000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.146 | 2011-11-22 | INCREASE THE FUNDING AMOUNT FOR THE U PHASE. | BRZ | 1203343 | KNOTT | 12-1082 | CR 1137 | 0.1 | 0 | 0.039 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON CR-5137 OVER STEER FORK (C62). (SR=14.7): (060C00062N) | 4 | U | BRZ | 2012 | 245000 | 245000 | ESTIMATED | N | 2010 | OBLIGATED |  | 245000 | 245000 | 2012 | 1st QUARTER | N/A
|  |  |  | BRZ | 1203349 | KNOTT | 12-1082 | CR 1137 | 0.1 | 0 | 0.039 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON CR-5137 OVER STEER FORK (C62). (SR=14.7): (060C00062N) | 5 | C | BRZ | 2011 | 470000 | 470000 | ESTIMATED | N |  | OBLIGATED | 756000 |  | 756000 | 2012 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.191 | 2012-05-16 | ADD PROJECT TO STIP. NEW | NH | 0251032 | KNOX | 11-188 | US 25E | 1.976 | 24.221 | 26.197 | RELIABILITY | MAJOR WIDENING(O) | MAJOR WIDENING - ADDRESS SAFETY AND CAPACITY ON US 25E FROM CORBIN BYPASS TO KNOX/LAUREL COUNTY LINE. IMPROVE SAFETY ALONG CORRIDOR BY PROVIDING IMPROVED ACCESS MANAGEMENT.(12CCR) |  | D | NH | 2012 | 1280000 | 1280000 |  |  |  | OBLIGATED | 700000 |  | 700000 | 2012 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.064 | 2011-04-12 | ADD PROJECT TO STIP. BREAKOUT FROM 99-911.00. NEW | HSIP | 0251024 | KNOX | 11-913 | US 25E | 0.1 | 7 | 7.1 | SAFETY | SAFETY-HAZARD ELIM(P) | INTERSECTION IMPROVEMENTS ON US 25E AT KNOX CENTRAL HIGH SCHOOL. |  | C | SAF | 2011 | 125000 | 125000 |  |  |  | OBLIGATED | 125000 |  | 125000 | 2011 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.084 | 2011-06-06 | ADD PROJECT TO STIP. BREAKOUT FROM 99-911.00. NEW | HSIP | 0251027 | KNOX | 11-919 | US 25E | 17 | 8 | 25 | SAFETY | SAFETY-HAZARD ELIM(P) | CONSTRUCT LEFT AND RIGHT TURN LANES ALONG US 25E AT VARIOUS LOCATIONS FROM KY 3153 TO THE LAUREL COUNTY LINE. |  | C | SAF | 2011 | 418500 | 418500 |  |  |  | OBLIGATED | 449868 |  | 449868 | 2012 | 1st QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.179 | 2012-04-10 | ADD PROJECT TO STIP. NEW | HSIP | 5156006 | KNOX | 11-921 | KY 11 | 3.272 | 0 | 3.272 | SAFETY | SAFETY-HAZARD ELIM(P) | SLOPE IMPROVEMENTS, DRAINAGE STRUCTURE REPLACEMENT, DITCHING AND SHOULDERING ON KY 11 FROM THE WHITLEY COUNTY LINE TO KY 1809 AT KING. |  | C | SAF | 2012 | 800000 | 800000 |  |  |  | OBLIGATED | 800000 |  | 800000 | 2012 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.179 | 2012-04-10 | ADD PROJECT TO STIP. NEW |  |  | KNOX | 11-922 | US 25E | 24 | 2 | 26 | SAFETY | SAFETY-HAZARD ELIM(P) | TRENCH AND PLACE BITUMINOUS BASE ON SHOULDERS AND INSTALL UPDATED GUARDRAIL END TREATMENTS ON US 25E FROM 2.0 MILE NORTH OF THE BELL COUNTY LINE, NORTHWEST TO THE LAUREL COUNTY LINE AT CORBIN. |  | C | SAF | 2012 | 925000 | 925000 | [6 empty] | 0
[6 empty] | KNOX | 11-1075 | KY 6 | 0.1 | 0.238 | 0.248 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-6 OVER LYNN CAMP CREEK (B42) 0.24 MILE EAST OF KNOX/WHITLEY COUNTY LINE. (SR=23.4): (061B00042N) | 2 | D | BRX | 2011 | 25000 | 25000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.001 | 2010-10-01 | INCREASE THE FUNDING AMOUNT OF THE D PHASE FROM $25,000 TO $250,000. MOD | BRZ | 1103233 | KNOX | 11-1075 | KY 6 | 0.1 | 0.238 | 0.248 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-6 OVER LYNN CAMP CREEK (B42) 0.24 MILE EAST OF KNOX/WHITLEY COUNTY LINE. (SR=23.4): (061B00042N) | 2 | D | BRX | 2011 | 250000 | 250000 | ESTIMATED | N |  | OBLIGATED | 250000 |  | 250000 | 2011 | 1st QUARTER | N/A
[6 empty] | KNOX | 11-1075 | KY 6 | 0.1 | 0.238 | 0.248 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-6 OVER LYNN CAMP CREEK (B42) 0.24 MILE EAST OF KNOX/WHITLEY COUNTY LINE. (SR=23.4): (061B00042N) | 3 | R | BRX | 2012 | 100000 | 100000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | KNOX | 11-1075 | KY 6 | 0.1 | 0.238 | 0.248 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-6 OVER LYNN CAMP CREEK (B42) 0.24 MILE EAST OF KNOX/WHITLEY COUNTY LINE. (SR=23.4): (061B00042N) | 4 | U | BRX | 2012 | 75000 | 75000 | ESTIMATED | N |  |  |  |  | 0
|  |  |  | BRZ | 1103235 | KNOX | 11-1076 | KY 6 | 0.1 | 0.825 | 0.833 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-6 OVER STEWARTS CREEK (B43) 0.27 MILE WEST OF KY-3436.(SR=23.4). (061B00043N) | 2 | D | BRX | 2011 | 250000 | 250000 | ESTIMATED | N | 2010 | OBLIGATED | 250000 |  | 250000 | 2011 | 1st QUARTER | N/A
[6 empty] | KNOX | 11-1076 | KY 6 | 0.1 | 0.825 | 0.833 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-6 OVER STEWARTS CREEK (B43) 0.27 MILE WEST OF KY-3436.(SR=23.4). (061B00043N) | 3 | R | BRX | 2012 | 100000 | 100000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | KNOX | 11-1076 | KY 6 | 0.1 | 0.825 | 0.833 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-6 OVER STEWARTS CREEK (B43) 0.27 MILE WEST OF KY-3436.(SR=23.4). (061B00043N) | 4 | U | BRX | 2012 | 75000 | 75000 | ESTIMATED | N |  |  |  |  | 0
|  |  |  | BRZ | 1103234 | KNOX | 11-1077 | KY 2418 | 0.1 | 0.07 | 0.078 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-2418 OVER LITTLE RICHLAND CREEK(B01) 0.6 MILE SE OF US-25E. (SR=25.6): (061B00001N) | 2 | D | BRX | 2011 | 290000 | 290000 | ESTIMATED | N | 2010 | OBLIGATED | 290000 |  | 290000 | 2011 | 1st QUARTER | N/A
[6 empty] | KNOX | 11-1077 | KY 2418 | 0.1 | 0.07 | 0.078 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-2418 OVER LITTLE RICHLAND CREEK(B01) 0.6 MILE SE OF US-25E. (SR=25.6): (061B00001N) | 3 | R | BRX | 2012 | 70000 | 70000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | KNOX | 11-1077 | KY 2418 | 0.1 | 0.07 | 0.078 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-2418 OVER LITTLE RICHLAND CREEK(B01) 0.6 MILE SE OF US-25E. (SR=25.6): (061B00001N) | 4 | U | BRX | 2012 | 70000 | 70000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | KNOX | 11-1082 | KY 3437 | 0.1 | 1.589 | 1.689 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-3437 (MP 1.639) OVER EAST FORK BIG INDIAN CREEK; .100 MILE WEST OF KY 1232 AT GRAY; (STRUCTURALLY DEFICIENT, SR=19.3) 061B00086N | 2 | D | BRX | 2012 | 120000 | 120000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.094 | 2011-06-28 | INCREASE THE FUNDING AMOUNT. MOD | BRZ | 1103244 | KNOX | 11-1082 | KY 3437 | 0.1 | 1.589 | 1.689 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-3437 (MP 1.639) OVER EAST FORK BIG INDIAN CREEK; .100 MILE WEST OF KY 1232 AT GRAY; (STRUCTURALLY DEFICIENT, SR=19.3) 061B00086N | 2 | D | BRX | 2011 | 250000 | 250000 | ESTIMATED | N |  | OBLIGATED | 250000 |  | 250000 | 2011 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.216 | 2012-07-25 | ADD PHASE TO STIP. NEW |  |  | KNOX | 11-1082 | KY 3437 | 0.1 | 1.589 | 1.689 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-3437 (MP 1.639) OVER EAST FORK BIG INDIAN CREEK; .100 MILE WEST OF KY 1232 AT GRAY; (STRUCTURALLY DEFICIENT, SR=19.3) 061B00086N(12CCR) | 2 | R | BRX | 2012 | 150000 | 150000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.216 | 2012-07-25 | ADD PHASE TO STIP. NEW |  |  | KNOX | 11-1082 | KY 3437 | 0.1 | 1.589 | 1.689 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-3437 (MP 1.639) OVER EAST FORK BIG INDIAN CREEK; .100 MILE WEST OF KY 1232 AT GRAY; (STRUCTURALLY DEFICIENT, SR=19.3) 061B00086N(12CCR) | 2 | U | BRX | 2012 | 75000 | 75000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | KNOX | 11-1084 | CR 1067 | 0.1 | 0.187 | 0.287 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON CR-1067 (MP 0.237) OVER COLLINS FORK; .2 MI SE-KY 11 @GREEN RD.; (STRUCTURALLY DEFICIENT, SR=18.1) 061C00023N | 2 | D | BRZ | 2012 | 200000 | 200000 | ESTIMATED | N |  |  |  |  | 0
|  |  |  | BRZ | 1103239 | KNOX | 11-8200 | KY 223 | 0.1 | 3.911 | 3.933 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE ROAD FORK BRIDGE AT DEWITT. (SR=55.1)(04CCN) (08CCR): (061B00026N) | 3 | R | BRX | 2011 | 190000 | 190000 | ESTIMATED | N | 2010 | OBLIGATED | 75000 |  | 75000 | 2011 | 2nd QUARTER | N/A
|  |  |  | BRZ | 1103236 | KNOX | 11-8200 | KY 223 | 0.1 | 3.911 | 3.933 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE ROAD FORK BRIDGE AT DEWITT. (SR=55.1)(04CCN) (08CCR): (061B00026N) | 4 | U | BRX | 2011 | 110000 | 110000 | ESTIMATED | N | 2010 | OBLIGATED | 165000 |  | 165000 | 2011 | 2nd QUARTER | N/A
|  |  |  | BRZ | 1103240 | KNOX | 11-8200 | KY 223 | 0.1 | 3.911 | 3.933 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE ROAD FORK BRIDGE AT DEWITT. (SR=55.1)(04CCN) (08CCR): (061B00026N) | 5 | C | BRX | 2011 | 760000 | 760000 | ESTIMATED | N |  | OBLIGATED | 1321182 |  | 1321182 | 2011 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.173 | 2012-03-19 | ADD TO STIP. NEW | IM | 0653038 | LARUE | 4-2802 | I-65 |  |  |  | SAFETY | SAFETY(P) | INSTALL HTC MEDIAN CABLE BARRIER ON I-65 IN HART, LARUE, AND HARDIN COUNTIES FROM MP 74.2 TO MP 80.4 (KY 84 INTERCHANGE) |  | C | IM | 2012 | 692230 | 692230 |  |  |  | OBLIGATED | 692230 |  | 692230 | 2012 | 2nd QUARTER | N/A
[6 empty] | LAUREL | 11-139.01 |  | 3 |  |  | RELIABILITY | NEW ROUTE(O) | I-75 CORRIDOR BORDER BETWEEN EXIT 38 AND EXIT 41. (2006KYD) (ALL PHASE 1 WORK BY COUNTY PER AGREEMENT) | 5 | C | KYD | 2011 | 861300 | 861300 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.154 | 2011-12-27 | ADD U PHASE TO STIP USING KYD FUNDS. | DPR | 0090002 | LAUREL | 11-139.02 | I 75 |  |  |  | RELIABILITY | NEW ROUTE(O) | I-75 LONDON, KENTUCKY; FRONTAGE ROAD ALONG I-75 BETWEEN EXIT 38 AND EXIT 41 AT LONDON | 5 | U | KYD | 2012 | 983928 | 983928 | ESTIMATED | Y | 2010 | OBLIGATED | 983928 |  | 983928 | 2012 | 2nd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.154 | 2011-12-27 | ADD U PHASE TO STIP USING STP FUNDS. | STP | 0090002 | LAUREL | 11-139.02 | I 75 |  |  |  | RELIABILITY | NEW ROUTE(O) | I-75 LONDON, KENTUCKY; FRONTAGE ROAD ALONG I-75 BETWEEN EXIT 38 AND EXIT 41 AT LONDON | 5 | U | STP | 2012 | 300000 | 300000 | ESTIMATED | Y | 2010 | OBLIGATED | 266072 |  | 266072 | 2012 | 2nd QUARTER | N/A
[6 empty] | LAUREL | 11-139.02 | I 75 |  |  |  | RELIABILITY | NEW ROUTE(O) | I-75 LONDON, KENTUCKY; CORRIDOR BETWEEN EXIT 38 AND EXIT 41 PRELIMINARY ENGINEERING AND ENVIRONMENTAL PHASE FOR CONSTRUCTION OF A FRONTAGE ROAD. (05KYD-KY090) | 5 | C | KYD | 2011 | 983928 | 983928 | ESTIMATED | Y | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.191 | 2012-05-16 | ADD PROJECT TO STIP. NEW | NH | 0251031 | LAUREL | 11-185 | US 25E | 2.024 | 0 | 2.024 | RELIABILITY | MAJOR WIDENING(O) | MAJOR WIDENING - ADDRESS SAFETY, CAPACITY, AND ACCESS MANAGEMENT ON US 25E FROM KNOX/LAUREL COUNTY LINE TO KY 770 |  | D | NH | 2012 | 1300000 | 1300000 |  |  |  | OBLIGATED | 700000 |  | 700000 | 2012 | 4th QUARTER | N/A
[6 empty] | LAUREL | 11-904.01 | KY 363 | 0.2 | 9.1 | 9.3 | SAFETY | SAFETY-HAZARD ELIM(P) | CONSTRUCT A ROUNDABOUT ON KY-363 AT KY-1006. (06CCR) | 3 | R | HES | 2011 | 580000 | 580000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | LAUREL | 11-904.01 | KY 363 | 0.2 | 9.1 | 9.3 | SAFETY | SAFETY-HAZARD ELIM(P) | CONSTRUCT A ROUNDABOUT ON KY-363 AT KY-1006. (06CCR) | 4 | U | HES | 2011 | 640000 | 640000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | LAUREL | 11-904.01 | KY 363 | 0.2 | 9.1 | 9.3 | SAFETY | SAFETY-HAZARD ELIM(P) | CONSTRUCT A ROUNDABOUT ON KY-363 AT KY-1006. (06CCR) | 5 | C | HES | 2011 | 1170000 | 1170000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.064 | 2011-04-12 | ADD PROJECT TO STIP. BREAKOUT FROM 99-911.00. NEW | HSIP | 5291001 | LAUREL | 11-914 | KY 312 | 0.2 | 6.6 | 6.8 | SAFETY | SAFETY-HAZARD ELIM(P) | INTERSECTION IMPROVEMENTS ON KY 312 AT KY 770 NORTH OF LAUREL LAKE. |  | C | SAF | 2011 | 125000 | 125000 |  |  |  | OBLIGATED | 125000 |  | 125000 | 2011 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.084 | 2011-06-06 | ADD PROJECT TO STIP. BREAKOUT FROM 99-911.00. NEW | HSIP | 5267001 | LAUREL | 11-917 | KY 472 | 0.159 | 0.442 | 0.601 | SAFETY | SAFETY-HAZARD ELIM(P) | CONSTRUCT RIGHT TURN LANE ON KY 472 AT NORTH LAUREL MIDDLE SCHOOL. |  | C | SAF | 2011 | 240000 | 240000 |  |  |  | OBLIGATED | 240000 |  | 240000 | 2011 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.084 | 2011-06-06 | ADD PROJECT TO STIP. BREAKOUT FROM 99-911.00. NEW | HSIP | 5153004 | LAUREL | 11-918 | KY 1006 | 0.05 | 6.5 | 6.55 | SAFETY | SAFETY-HAZARD ELIM(P) | WIDEN SHOULDER ON WEST 5TH STREET AT COLLEGE STREET IN LONDON. |  | C | SAF | 2011 | 85000 | 85000 |  |  |  | OBLIGATED | 85000 |  | 85000 | 2011 | 4th QUARTER | N/A
[6 empty] | LAUREL | 11-1060 | KY 490 | 0.1 | 11.49 | 11.509 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER ROCKCASTLE RIVER (B04) AT THE ROCKCASTLE-LAUREL COUNTY LINE. (SR=11.4): (063B00004N)(10CCR) | 3 | R | BRO | 2011 | 80000 | 80000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.023 | 2010-12-03 | INCREASE THE FUNDING AMOUNT OF THE R PHASE. MOD |  |  | LAUREL ROCKCASTLE | 11-1060 | KY 490 | 0.1 | 11.49 | 11.509 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER ROCKCASTLE RIVER (B04) AT THE ROCKCASTLE-LAUREL COUNTY LINE. (SR=11.4): (063B00004N)(10CCR) | 3 | R | BRO | 2011 | 90000 | 90000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | LAUREL | 11-1060 | KY 490 | 0.1 | 11.49 | 11.509 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER ROCKCASTLE RIVER (B04) AT THE ROCKCASTLE-LAUREL COUNTY LINE. (SR=11.4): (063B00004N)(10CCR) | 4 | U | BRO | 2011 | 80000 | 80000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.023 | 2010-12-03 | INCREASE THE FUNDING AMOUNT OF THE U PHASE. MOD |  |  | LAUREL ROCKCASTLE | 11-1060 | KY 490 | 0.1 | 11.49 | 11.509 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER ROCKCASTLE RIVER (B04) AT THE ROCKCASTLE-LAUREL COUNTY LINE. (SR=11.4): (063B00004N)(10CCR) | 3 | U | BRO | 2011 | 150000 | 150000 | ESTIMATED | N | 2010 |  |  |  | 0
|  |  |  | BRZ | 1103249 | LAUREL | 11-1060 | KY 490 | 0.1 | 11.49 | 11.509 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER ROCKCASTLE RIVER (B04) AT THE ROCKCASTLE-LAUREL COUNTY LINE. (SR=11.4): (063B00004N)(10CCR) | 5 | C | BRO | 2011 | 1670000 | 1670000 | ESTIMATED | N |  | OBLIGATED | 960000 |  | 960000 | 2011 | 4th QUARTER | N/A
[6 empty] | LAUREL | 11-1080 | KY 578 | 0.1 | 5.104 | 5.204 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-578 (MP 5.154) OVER RACCOON CREEK; .10 MI W OF W-JCT KY 638; (STRUCTURALLY DEFICIENT, SR=24.9) 063B00069N | 2 | D | BRX | 2012 | 130000 | 130000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.094 | 2011-06-28 | INCREASE THE FUNDING AMOUNT. MOD | BRZ | 1103243 | LAUREL | 11-1080 | KY 578 | 0.1 | 5.104 | 5.204 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-578 (MP 5.154) OVER RACCOON CREEK; .10 MI W OF W-JCT KY 638; (STRUCTURALLY DEFICIENT, SR=24.9) 063B00069N | 2 | D | BRX | 2011 | 250000 | 250000 | ESTIMATED | N |  | OBLIGATED | 250000 |  | 250000 | 2011 | 4th QUARTER | N/A
[6 empty] | LAWRENCE | 12-284 | KY 32 | 4 | 23.64 | 27.64 | RELIABILITY | RECONSTRUCTION(O) | LOUISA-SANDY HOOK ROAD; RECONSTRUCT A PRIORITY SECTION OF KY-32 BETWEEN THE END OF CORPS OF ENGRS RECONSTRUCTION AT YATESVILLE LAKE AND US-23. (04CCR)(06CCR)(08CCR) | 5 | C | STP | 2011 | 20250000 | 20250000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | LAWRENCE | 12-1106 | PR 1116 | 0.1 | 0 | 0.1 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON PR-1116 (MP 0.015) OVER ROCKCASTLE CREEK; .034 MI W JCT KY 3; (STRUCTURALLY DEFICIENT, SR=18.4) 064C00073N | 2 | D | BRZ | 2012 | 140000 | 140000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.101 | 2011-07-25 | INCREASE FUNDING AMOUNT FOR D PHASE. MOD | BRZ | 1203337 | LAWRENCE | 12-1106 | PR 1116 | 0.1 | 0 | 0.1 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON PR-1116 (MP 0.015) OVER ROCKCASTLE CREEK; .034 MI W JCT KY 3; (STRUCTURALLY DEFICIENT, SR=18.4) 064C00073N | 2 | D | BRZ | 2012 | 320000 | 320000 | ESTIMATED | N |  | OBLIGATED | 320000 |  | 320000 | 2011 | 4th QUARTER | N/A
[6 empty] | LAWRENCE | 12-8405 | KY 32 | 1.5 | 27.64 | 29.162 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT A PRIORITY SECTION OF KY-32 BEGINNING AT MILEPOST 27.64. (08CCN)(10CCR) | 2 | D | STP | 2011 | 500000 | 500000 | ESTIMATED |  | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.023 | 2010-12-03 | INCREASE THE FUNDING AMOUNT OF THE D PHASE. MOD | STP | 5255018 | LAWRENCE | 12-8405 | KY 32 | 1.5 | 27.64 | 29.162 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT A PRIORITY SECTION OF KY-32 BEGINNING AT MILEPOST 27.64. (08CCN)(10CCR) | 2 | D | STP | 2011 | 1100000 | 1100000 | ESTIMATED |  | 2010 | OBLIGATED | 1100000 |  | 1100000 | 2011 | 1st QUARTER | N/A
[6 empty] | LAWRENCE | 12-8405 | KY 32 | 1.5 | 27.64 | 29.162 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT A PRIORITY SECTION OF KY-32 BEGINNING AT MILEPOST 27.64. (08CCN)(10CCR) | 3 | R | STP | 2011 | 1500000 | 1500000 | ESTIMATED | [5 empty] | 0
[6 empty] | LAWRENCE | 12-8405 | KY 32 | 1.5 | 27.64 | 29.162 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT A PRIORITY SECTION OF KY-32 BEGINNING AT MILEPOST 27.64. (08CCN)(10CCR) | 4 | U | STP | 2011 | 1000000 | 1000000 | ESTIMATED | [5 empty] | 0
[6 empty] | LAWRENCE | 12-8405 | KY 32 | 1.5 | 27.64 | 29.162 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT A PRIORITY SECTION OF KY-32 BEGINNING AT MILEPOST 27.64. (08CCN)(10CCR) | 5 | C | STP | 2012 | 4500000 | 4500000 | ESTIMATED | [5 empty] | 0
[6 empty] | LEE | 10-142 | KY 52 | 0.5 | 11.7 | 12.2 | RELIABILITY | MINOR WIDENING(O) | KY 52 PROJECT, CITY OF BEATTYVILLE: WIDEN AND ADD SIDEWALKS. (2006KYD) | 5 | C | KYD | 2011 | 602910 | 602910 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.059 | 2011-03-23 | ADD PROJECT TO STIP. BREAKOUT FROM 99-911.00. NEW | HSIP | 9010048 | LEE | 10-908 | KY 1144 | 0.6 | 0.4 | 1 | SAFETY | SAFETY-HAZARD ELIM(P) | RECONSTRUCT KY 1144 AT ENTRANCE TO LEE COUNTY HIGH SCHOOL AT BEATTYVILLE |  | R | SAF | 2011 | 5000 | 5000 |  |  |  | OBLIGATED | 5000 |  | 5000 | 2011 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.059 | 2011-03-23 | ADD PROJECT TO STIP. BREAKOUT FROM 99-911.00. NEW | HSIP | 9010049 | LEE | 10-908 | KY 1144 | 0.6 | 0.4 | 1 | SAFETY | SAFETY-HAZARD ELIM(P) | RECONSTRUCT KY 1144 AT ENTRANCE TO LEE COUNTY HIGH SCHOOL AT BEATTYVILLE |  | U | SAF | 2011 | 30000 | 30000 |  |  |  | OBLIGATED | 30000 |  | 30000 | 2011 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.059 | 2011-03-23 | ADD PROJECT TO STIP. BREAKOUT FROM 99-911.00. NEW | HSIP | 9010050 | LEE | 10-908 | KY 1144 | 0.6 | 0.4 | 1 | SAFETY | SAFETY-HAZARD ELIM(P) | RECONSTRUCT KY 1144 AT ENTRANCE TO LEE COUNTY HIGH SCHOOL AT BEATTYVILLE |  | C | SAF | 2011 | 210000 | 210000 |  |  |  | OBLIGATED | 317877.25 |  | 317877.25 | 2012 | 2nd QUARTER | N/A
|  |  |  | BRZ | 1003197 | LEE | 10-1091 | CR 1224 | 0.1 | 0.052 | 0.152 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON CR-1224 (MP 0.102) OVER ELK LICK BR-ELK CK; .1 MI-W JCT CR 5212; (FUNCTIONALLY OBSOLETE, SR=21.9) 065C00023N | 2 | D | BRZ | 2012 | 120000 | 120000 | ESTIMATED | N |  | OBLIGATED | 150000 |  | 150000 | 2011 | 1st QUARTER | N/A
[6 empty] | LESLIE | 11-1067 | CR 1214 | 0.1 | 0.024 | 0.064 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON CR-1214 OVER BEECH FORK (C24). (SR=6.0)(PROJECT FUNDING CONTINGENT UPON BRIDGE POSTING COMPLIANCE): (066C00024N) | 3 | R | BRZ | 2011 | 230000 | 230000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | LESLIE | 11-1067 | CR 1214 | 0.1 | 0.024 | 0.064 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON CR-1214 OVER BEECH FORK (C24). (SR=6.0)(PROJECT FUNDING CONTINGENT UPON BRIDGE POSTING COMPLIANCE): (066C00024N) | 4 | U | BRZ | 2011 | 120000 | 120000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | LESLIE | 11-1067 | CR 1214 | 0.1 | 0.024 | 0.064 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON CR-1214 OVER BEECH FORK (C24). (SR=6.0)(PROJECT FUNDING CONTINGENT UPON BRIDGE POSTING COMPLIANCE): (066C00024N) | 5 | C | BRZ | 2011 | 490000 | 490000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | LESLIE | 11-1068 | CR 1241 | 0.1 | 0.006 | 0.016 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON CR-1241 OVER BEECH FORK (C25). (SR=3.0)(PROJECT FUNDING CONTINGENT UPON BRIDGE POSTING COMPLIANCE): (066C00025N) | 3 | R | BRZ | 2011 | 230000 | 230000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | LESLIE | 11-1068 | CR 1241 | 0.1 | 0.006 | 0.016 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON CR-1241 OVER BEECH FORK (C25). (SR=3.0)(PROJECT FUNDING CONTINGENT UPON BRIDGE POSTING COMPLIANCE): (066C00025N) | 4 | U | BRZ | 2011 | 120000 | 120000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | LESLIE | 11-1068 | CR 1241 | 0.1 | 0.006 | 0.016 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON CR-1241 OVER BEECH FORK (C25). (SR=3.0)(PROJECT FUNDING CONTINGENT UPON BRIDGE POSTING COMPLIANCE): (066C00025N) | 5 | C | BRZ | 2011 | 440000 | 440000 | ESTIMATED | N |  |  |  |  | 0
|  |  |  | BRO | 4211021 | LESLIE | 11-1078 | US 421 | 0.1 | 15.137 | 15.177 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON US-421 OVER STINNET CREEK (B08) 0.028 MILE SOUTH OF KY-406 NEAR STINNETT.(SR=26.0) (10CCR) | 2 | D | BRO | 2011 | 400000 | 400000 | ESTIMATED | N |  | OBLIGATED | 400000 |  | 400000 | 2011 | 1st QUARTER | N/A
[6 empty] | LESLIE | 11-1078 | US 421 | 0.1 | 15.137 | 15.177 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON US-421 OVER STINNET CREEK (B08) 0.028 MILE SOUTH OF KY-406 NEAR STINNETT.(SR=26.0) | 3 | R | BRO | 2013 | 200000 | 200000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | LESLIE | 11-1078 | US 421 | 0.1 | 15.137 | 15.177 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON US-421 OVER STINNET CREEK (B08) 0.028 MILE SOUTH OF KY-406 NEAR STINNETT.(SR=26.0) | 4 | U | BRO | 2013 | 150000 | 150000 | ESTIMATED | N |  |  |  |  | 0
|  |  |  | BRZ | 1103241 | LESLIE | 11-8519 | KY 699 |  | 4.8 | 4.815 | RELIABILITY | BRIDGE REPLACEMENT(P) | CONSTRUCT A NEW HIGH WATER BRIDGE ON KY-699. (08CCN): (066B00056N)(10CCR) | 3 | R | BRX | 2011 | 50000 | 50000 | ESTIMATED | N | 2010 | OBLIGATED | 110000 |  | 110000 | 2011 | 4th QUARTER | N/A
|  |  |  | BRZ | 1103248 | LESLIE | 11-8519 | KY 699 |  | 4.8 | 4.815 | RELIABILITY | BRIDGE REPLACEMENT(P) | CONSTRUCT A NEW HIGH WATER BRIDGE ON KY-699. (08CCN): (066B00056N)(10CCR) | 4 | U | BRX | 2011 | 50000 | 50000 | ESTIMATED | N | 2010 | OBLIGATED | 60000 |  | 60000 | 2011 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.094 | 2011-06-28 | INCREASE THE FUNDING AMOUNT. MOD | BRZ | 1103248 | LESLIE | 11-8519 | KY 699 |  | 4.8 | 4.815 | RELIABILITY | BRIDGE REPLACEMENT(P) | CONSTRUCT A NEW HIGH WATER BRIDGE ON KY-699. (08CCN): (066B00056N)(10CCR) | 4 | U | BRX | 2011 | 60000 | 60000 | ESTIMATED | N | 2010 | OBLIGATED | 85000 |  | 85000 | 2012 | 3rd QUARTER | N/A
|  |  |  | BRZ | 1103250 | LESLIE | 11-8519 | KY 699 |  | 4.8 | 4.815 | RELIABILITY | BRIDGE REPLACEMENT(P) | CONSTRUCT A NEW HIGH WATER BRIDGE ON KY-699. (08CCN): (066B00056N)(10CCR) | 5 | C | BRX | 2011 | 650000 | 650000 | ESTIMATED | N | 2010 | OBLIGATED | 925000 |  | 925000 | 2012 | 1st QUARTER | N/A
|  |  |  | HSIP | 0151069 | LETCHER | 12-121 | KY 15 | 1 | 5.725 | 6.725 | SAFETY | SAFETY(P) | HAZARD-WHITESBURG; CONSTRUCT NEW INTERSECTION WITH LEFT TURN LANES AT KY-160 NEAR VAN. | 5 | C | HES | 2011 | 1230000 | 1230000 | ESTIMATED | Y | 2010 | OBLIGATED | 1311206.54 |  | 1311206.54 | 2011 | 2nd QUARTER | N/A
[6 empty] | LETCHER | 12-311.3 | US 119 | 3.48 |  |  | RELIABILITY | RELOCATION(O) | HARLAN-WHITESBURG; PINE MOUNTAIN; PARTRIDGE TO OVEN FORK; BEGINNING 1.3 MILES EAST OF THE HARLAN COUNTY LINE TO 1.71 MILES EAST OF KY-3404 NEAR JOE DAY BRANCH. (R/W FOR SECTIONS 1A & 1B) (F16) (2000BOPP) | 3 | R | APD | 2011 | 3150000 | 2520000 | ESTIMATED | Y | 2010 |  |  |  | 0
[6 empty] | LETCHER | 12-311.35 | US 119 | 1.24 |  |  | RELIABILITY | RELOCATION(O) | HARLAN-WHITESBURG; PINE MOUNTAIN; PARTRIDGE TO OVEN FORK SECTION 2; US-119 RELOCATION FROM 1000 FEET WEST JCT. KY-3404 TO 1.0 MILE SOUTHWEST MAGGARD BRANCH ROAD. (F16) (2004BOPC)(GRADE & DRAIN)(CONST. SEQUENCE 3) | 5 | C | APD | 2011 | 20670000 | 16536000 | ESTIMATED | Y | 2010 |  |  |  | 0
[6 empty] | LETCHER | 12-311.36 | US 119 | 3.01 |  |  | RELIABILITY | RELOCATION(O) | HARLAN-WHITESBURG; PINE MOUNTAIN; PARTRIDGE TO OVEN FORK SECTION 3; US-119 RELOCATION FROM 1.0 MILE SOUTHWEST MAGGARD BRANCH ROAD TO 0.1 MILE WEST OF BROWN BRANCH. (F16) (2004BOPC)(GRADE & DRAIN)(CONST. SEQUENCE 2) | 5 | C | APD | 2011 | 52940000 | 42352000 | ESTIMATED | Y | 2010 |  |  |  | 0
[6 empty] | LETCHER | 12-311.39 | US 119 | 4.25 |  |  | RELIABILITY | RELOCATION(O) | HARLAN-WHITESBURG; PINE MOUNTAIN; PARTRIDGE TO OVEN FORK (SURFACING FOR SECTIONS 2 AND 3); US-119 RELOCATION FROM 1000 FEET WEST JCT. KY-3404 TO 0.1 MILE WEST OF BROWN BRANCH. (F16) (2004BOPC)(CONSTRUCTION SEQUENCE 5) | 5 | C | APD | 2014 | 12000000 | 9600000 | ESTIMATED | [5 empty] | 0
[6 empty] | LETCHER | 12-311.7 | US 119 | 2.86 |  |  | RELIABILITY | RELOCATION(O) | HARLAN-WHITESBURG; PINE MOUNTAIN; PARTRIDGE TO OVEN FORK; BEGINNING 1.71 MILES EAST OF KY-3404 NEAR JOE DAY BRANCH TO THE COMMUNITY OF OVEN FORK. (R/W FOR SECTIONS 3 & 4) (F16) (2000BOP) | 3 | R | APD | 2011 | 3310000 | 2648000 | ESTIMATED | Y | 2010 |  |  |  | 0
[6 empty] | LETCHER | 12-311.77 | US 119 | 1.55 |  |  | RELIABILITY | RELOCATION(O) | HARLAN-WHITESBURG; PINE MOUNTAIN; PARTRIDGE TO OVEN FORK SECTION 4; US-119 RELOCATION FROM 0.1 MI WEST OF BROWN BRANCH TO 0.15 MI WEST OF KY-806 AT OVEN FORK INCLUDING APPROACH TO EXISTING US-119. (F16) (2004BOPC)(CONST. SEQUENCE 4)(GRADE, DRAIN AND SURF) | 5 | C | APD | 2014 | 25070000 | 20056000 | ESTIMATED | [5 empty] | 0
[6 empty] | LETCHER | 12-314 | US 119 | 4.3 |  |  | RELIABILITY | RECONSTRUCTION(O) | HARLAN-WHITESBURG; PINE MOUNTAIN; OVEN FORK TO WHITESBURG (F16.1) | 2 | D | APD | 2012 | 4180000 | 3344000 | ESTIMATED | Y |  |  |  |  | 0
[6 empty] | LETCHER | 12-314.1 | US 119 | 0.72 |  |  | RELIABILITY | RECONSTRUCTION(O) | HARLAN-WHITESBURG; PINE MOUNTAIN; OVEN FORK TO WHITESBURG SECTION 1 (SOUTHERN PORTAL); BEGINNING 0.65 MILE WEST OF KY-806 TO JUST NORTH OF KY-806 NEAR COMMUNITY OF OVEN FORK. (F16.1)(CONSTRUCTION SEQUENCE 3) | 3 | R | APD | 2013 | 1790000 | 1432000 | ESTIMATED | [5 empty] | 0
[6 empty] | LETCHER | 12-314.1 | US 119 | 0.72 |  |  | RELIABILITY | RECONSTRUCTION(O) | HARLAN-WHITESBURG; PINE MOUNTAIN; OVEN FORK TO WHITESBURG SECTION 1 (SOUTHERN PORTAL); BEGINNING 0.65 MILE WEST OF KY-806 TO JUST NORTH OF KY-806 NEAR COMMUNITY OF OVEN FORK. (F16.1)(CONSTRUCTION SEQUENCE 3) | 4 | U | APD | 2013 | 730000 | 584000 | ESTIMATED | [5 empty] | 0
[6 empty] | LETCHER | 12-314.1 | US 119 | 0.72 |  |  | RELIABILITY | RECONSTRUCTION(O) | HARLAN-WHITESBURG; PINE MOUNTAIN; OVEN FORK TO WHITESBURG SECTION 1 (SOUTHERN PORTAL); BEGINNING 0.65 MILE WEST OF KY-806 TO JUST NORTH OF KY-806 NEAR COMMUNITY OF OVEN FORK. (F16.1)(CONSTRUCTION SEQUENCE 3) | 5 | C | APD | 2014 | 23750000 | 19000000 | ESTIMATED | [5 empty] | 0
[6 empty] | LETCHER | 12-314.2 | US 119 | 1.83 |  |  | RELIABILITY | RECONSTRUCTION(O) | HARLAN-WHITESBURG; PINE MOUNTAIN; OVEN FORK TO WHITESBURG SECTION 2 (TUNNEL); BEGINNING JUST NORTH OF KY-806 NEAR COMMUNITY OF OVEN FORK TO JUST SOUTH OF KY-2035 ON LITTLE COWAN CREEK. (F16.1)(CONSTRUCTION SEQUENCE 4) | 3 | R | APD | 2013 | 1790000 | 1432000 | ESTIMATED | [5 empty] | 0
[6 empty] | LETCHER | 12-314.2 | US 119 | 1.83 |  |  | RELIABILITY | RECONSTRUCTION(O) | HARLAN-WHITESBURG; PINE MOUNTAIN; OVEN FORK TO WHITESBURG SECTION 2 (TUNNEL); BEGINNING JUST NORTH OF KY-806 NEAR COMMUNITY OF OVEN FORK TO JUST SOUTH OF KY-2035 ON LITTLE COWAN CREEK. (F16.1)(CONSTRUCTION SEQUENCE 4) | 4 | U | APD | 2013 | 730000 | 584000 | ESTIMATED | [5 empty] | 0
[6 empty] | LETCHER | 12-314.26 | US 119 | 1.97 |  |  | RELIABILITY | RECONSTRUCTION(O) | HARLAN-WHITESBURG; PINE MOUNTAIN TUNNEL OPTION; SECTION 2 - PILOT BORE. | 3 | R | APD | 2013 | 890000 | 712000 | ESTIMATED | [5 empty] | 0
[6 empty] | LETCHER | 12-314.26 | US 119 | 1.97 |  |  | RELIABILITY | RECONSTRUCTION(O) | HARLAN-WHITESBURG; PINE MOUNTAIN TUNNEL OPTION; SECTION 2 - PILOT BORE. | 4 | U | APD | 2013 | 330000 | 264000 | ESTIMATED | [5 empty] | 0
[6 empty] | LETCHER | 12-314.26 | US 119 | 1.97 |  |  | RELIABILITY | RECONSTRUCTION(O) | HARLAN-WHITESBURG; PINE MOUNTAIN TUNNEL OPTION; SECTION 2 - PILOT BORE. | 5 | C | APD | 2014 | 18450000 | 14760000 | ESTIMATED | [5 empty] | 0
[6 empty] | LETCHER | 12-314.3 | US 119 | 1.75 |  |  | RELIABILITY | RECONSTRUCTION(O) | HARLAN-WHITESBURG; PINE MOUNTAIN; OVEN FORK TO WHITESBURG SECTION 3 (NORTHERN PORTAL); BEGINNING JUST SOUTH OF KY-2035 ON LITTLE COWAN CREEK TO THE US119/KY15 INTERSECTION AT WHITESBURG. (F16.1)(CONSTRUCTION SEQUENCE 2) | 3 | R | APD | 2013 | 1320000 | 1056000 | ESTIMATED | [5 empty] | 0
[6 empty] | LETCHER | 12-314.3 | US 119 | 1.75 |  |  | RELIABILITY | RECONSTRUCTION(O) | HARLAN-WHITESBURG; PINE MOUNTAIN; OVEN FORK TO WHITESBURG SECTION 3 (NORTHERN PORTAL); BEGINNING JUST SOUTH OF KY-2035 ON LITTLE COWAN CREEK TO THE US119/KY15 INTERSECTION AT WHITESBURG. (F16.1)(CONSTRUCTION SEQUENCE 2) | 4 | U | APD | 2013 | 550000 | 440000 | ESTIMATED | [5 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.161 | 2012-01-31 | ADD PROJECT TO STIP. NEW |  |  | LETCHER | 12-926 | KY 931 | 0.776 | 5.907 | 6.683 | SAFETY | SAFETY-HAZARD ELIM(P) | REMOVE TREES ALONG KY-931 FROM BARTESTA BRANCH ROAD TO COWAN CREEK BRIDGE |  | C | SAF | 2012 | 85000 | 85000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.167 | 2012-02-15 | ADD PROJECT TO STIP. NEW | HSIP | 9010073 | LETCHER | 12-929 | KY 588 | 2.5 | 5 | 7.5 | SAFETY | SAFETY | RESTORE SHOULDERS, DITCHES, AND DRAINAGE STRUCTURES AND EXCAVATE BACK-SLOPES TO IMPROVE CURVE RADII AND SIGHT DISTANCE ON KY 588 FROM KY 160 NEAR PREMIUM TO 1.5 MILE WEST OF KY 3401 AT UZ. |  | C | SAF | 2012 | 335000 | 335000 |  |  |  | OBLIGATED | 335000 |  | 335000 | 2012 | 2nd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.179 | 2012-04-10 | ADD PROJECT TO STIP. NEW | HSIP | 5337032 | LETCHER | 12-931 | KY 7 | 0.3 | 11.205 | 11.505 | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALL GUARDRAIL ON KY 7 FROM SPRING BRANCH ROAD TO 700' SOUTH OF DOTY CREEK BRIDGE. |  | C | SAF | 2012 | 34000 | 34000 |  |  |  | OBLIGATED | 34000 |  | 34000 | 2012 | 3rd QUARTER | N/A
|  |  |  | BRZ | 1203308 | LETCHER | 12-1081 | CR 1376 | 0.1 | 0.005 | 0.036 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON CR-1376 OVER NORTH FORK KENTUCKY RIVER (C46). (SR=7.8): (067C00046N) | 5 | C | BRZ | 2011 | 1410000 | 1410000 | ESTIMATED | N | 2010 | OBLIGATED | 1737601.32 |  | 1737601.32 | 2011 | 4th QUARTER | N/A
|  |  |  | BRZ | 1203330 | LETCHER | 12-1091 | CR 1245 | 0.1 | 0.051 | 0.057 | SAFETY | BRIDGE REPLACEMENT(P) | PACIES BRANCH ROAD; REPLACE BRIDGE AND APPROACHES OVER KINGS CREEK (C27) 0.05 MILE NW OF KY-160. (SR=2.0): (067C00027N) | 2 | D | BRZ | 2011 | 300000 | 300000 | ESTIMATED | N |  | OBLIGATED | 300000 |  | 300000 | 2011 | 2nd QUARTER | N/A
[6 empty] | LETCHER | 12-1091 | CR 1245 | 0.1 | 0.051 | 0.057 | RELIABILITY | BRIDGE REPLACEMENT(P) | PACIES BRANCH ROAD; REPLACE BRIDGE AND APPROACHES OVER KINGS CREEK (C27) 0.05 MILE NW OF KY-160. (SR=2.0) | 3 | R | BRZ | 2013 | 100000 | 100000 | ESTIMATED | [5 empty] | 0
[6 empty] | LETCHER | 12-1091 | CR 1245 | 0.1 | 0.051 | 0.057 | RELIABILITY | BRIDGE REPLACEMENT(P) | PACIES BRANCH ROAD; REPLACE BRIDGE AND APPROACHES OVER KINGS CREEK (C27) 0.05 MILE NW OF KY-160. (SR=2.0) | 4 | U | BRZ | 2013 | 125000 | 125000 | ESTIMATED | [5 empty] | 0
[6 empty] | LETCHER | 12-1091 | CR 1245 | 0.1 | 0.051 | 0.057 | RELIABILITY | BRIDGE REPLACEMENT(P) | PACIES BRANCH ROAD; REPLACE BRIDGE AND APPROACHES OVER KINGS CREEK (C27) 0.05 MILE NW OF KY-160. (SR=2.0) | 5 | C | BRZ | 2014 | 550000 | 550000 | ESTIMATED | [5 empty] | 0
[6 empty] | LETCHER | 12-1094 | KY 343 | 0.1 | 0.638 | 0.645 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-343 OVER WRIGHT FORK (B79) 50 FEET NE OF HAYMOND HILL ROAD. (SR=3.0): (067B00079N) | 3 | R | BRX | 2012 | 150000 | 150000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.094 | 2011-06-28 | INCREASE THE FUNDING AMOUNT. MOD | BRZ | 1203334 | LETCHER | 12-1094 | KY 343 | 0.1 | 0.638 | 0.645 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-343 OVER WRIGHT FORK (B79) 50 FEET NE OF HAYMOND HILL ROAD. (SR=3.0): (067B00079N) | 3 | R | BRX | 2011 | 266100 | 266100 | ESTIMATED | N |  | OBLIGATED | 266100 |  | 266100 | 2012 | 1st QUARTER | N/A
[6 empty] | LETCHER | 12-1094 | KY 343 | 0.1 | 0.638 | 0.645 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-343 OVER WRIGHT FORK (B79) 50 FEET NE OF HAYMOND HILL ROAD. (SR=3.0): (067B00079N) | 4 | U | BRX | 2012 | 150000 | 150000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.112 | 2011-08-30 | INCREASE THE FUNDING AMOUNT. MOD | BRZ | 1203339 | LETCHER | 12-1094 | KY 343 | 0.1 | 0.638 | 0.645 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-343 OVER WRIGHT FORK (B79) 50 FEET NE OF HAYMOND HILL ROAD. (SR=3.0): (067B00079N) | 4 | U | BRX | 2011 | 230000 | 230000 | ESTIMATED | N |  | OBLIGATED | 230000 |  | 230000 | 2011 | 4th QUARTER | N/A
[6 empty] | LETCHER | 12-1094 | KY 343 | 0.1 | 0.638 | 0.645 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-343 OVER WRIGHT FORK (B79) 50 FEET NE OF HAYMOND HILL ROAD. (SR=3.0) | 5 | C | BRX | 2014 | 550000 | 550000 | ESTIMATED | [5 empty] | 0
|  |  |  | BRZ | 1203331 | LETCHER | 12-1096 | CR 1391 | 0.1 | 0.055 | 0.067 | SAFETY | BRIDGE REPLACEMENT(P) | BIG BLUE BLVD; REPLACE BRIDGE OVER ROCKHOUSE CREEK (C35) 0.05 MILE SE OF KY-7. (SR=5.0): (067C00035N) | 2 | D | BRZ | 2011 | 320000 | 320000 | ESTIMATED | N |  | OBLIGATED | 320000 |  | 320000 | 2011 | 3rd QUARTER | N/A
[6 empty] | LETCHER | 12-1096 | CR 1391 | 0.1 | 0.055 | 0.067 | RELIABILITY | BRIDGE REPLACEMENT(P) | BIG BLUE BLVD; REPLACE BRIDGE OVER ROCKHOUSE CREEK (C35) 0.05 MILE SE OF KY-7. (SR=5.0) | 3 | R | BRZ | 2013 | 100000 | 100000 | ESTIMATED | [5 empty] | 0
[6 empty] | LETCHER | 12-1096 | CR 1391 | 0.1 | 0.055 | 0.067 | RELIABILITY | BRIDGE REPLACEMENT(P) | BIG BLUE BLVD; REPLACE BRIDGE OVER ROCKHOUSE CREEK (C35) 0.05 MILE SE OF KY-7. (SR=5.0) | 4 | U | BRZ | 2013 | 100000 | 100000 | ESTIMATED | [5 empty] | 0
[6 empty] | LETCHER | 12-1096 | CR 1391 | 0.1 | 0.055 | 0.067 | RELIABILITY | BRIDGE REPLACEMENT(P) | BIG BLUE BLVD; REPLACE BRIDGE OVER ROCKHOUSE CREEK (C35) 0.05 MILE SE OF KY-7. (SR=5.0) | 5 | C | BRZ | 2014 | 900000 | 900000 | ESTIMATED | [5 empty] | 0
|  |  |  | BRZ | 1203335 | LETCHER | 12-1097 | KY 343 | 0.1 | 1.621 | 1.627 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-343 OVER WRIGHT FORK (B15) 30 FEET EAST OF MASTERS DRIVE. (SR=7.0): (067B00015N) | 3 | R | BRX | 2012 | 200000 | 200000 | ESTIMATED | N |  | OBLIGATED | 107500 |  | 107500 | 2012 | 1st QUARTER | N/A
|  |  |  | BRZ | 1203338 | LETCHER | 12-1097 | KY 343 | 0.1 | 1.621 | 1.627 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-343 OVER WRIGHT FORK (B15) 30 FEET EAST OF MASTERS DRIVE. (SR=7.0): (067B00015N) | 4 | U | BRX | 2012 | 200000 | 200000 | ESTIMATED | N |  | OBLIGATED | 160000 |  | 160000 | 2012 | 2nd QUARTER | N/A
[6 empty] | LETCHER | 12-1097 | KY 343 | 0.1 | 1.621 | 1.627 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-343 OVER WRIGHT FORK (B15) 30 FEET EAST OF MASTERS DRIVE. (SR=7.0) | 5 | C | BRX | 2014 | 625000 | 625000 | ESTIMATED | [5 empty] | 0
|  |  |  | BRZ | 1203346 | LETCHER | 12-1107 | CS 2026 | 0.1 | 0 | 0.1 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON CS-2026 OVER (MP 0.032) ELKHORN CREEK; AT EAST JENKINS; (STRUCTURALLY DEFICIENT, SR=13) 067C00058N | 2 | D | BRZ | 2012 | 110000 | 110000 | ESTIMATED | N |  | OBLIGATED | 190000 |  | 190000 | 2012 | 2nd QUARTER | N/A
[6 empty] | LETCHER | 12-1108 | CR 1841 | 0.1 | 0 | 0.1 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON CR-1841 (MP 0.015) OVER NORTH FORK KY RIVER; 1 MI N JCT KY 1862; (STRUCTURALLY DEFICIENT, SR=15.7) 067C00063N | 2 | D | BRZ | 2012 | 130000 | 130000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.101 | 2011-07-25 | INCREASE THE D PHASE FUNDING AMOUNT. MOD | BRZ | 1203336 | LETCHER | 12-1108 | CR 1841 | 0.1 | 0 | 0.1 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON CR-1841 (MP 0.015) OVER NORTH FORK KY RIVER; 1 MI N JCT KY 1862; (STRUCTURALLY DEFICIENT, SR=15.7) 067C00063N | 2 | D | BRZ | 2012 | 320000 | 320000 | ESTIMATED | N |  | OBLIGATED | 320000 |  | 320000 | 2011 | 4th QUARTER | N/A
[6 empty] | LEWIS | 9-1079 | CR 1068 | 0.1 | 0.175 | 0.275 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON CR-1068 (MP 0.225) OVER TOWN BRANCH; 3.5 MI EAST OF JCT KY 59; (STRUCTURALLY DEFICIENT, SR=9.5) 068C00061N | 2 | D | BRZ | 2012 | 110000 | 110000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.060 | 2011-03-29 | INCREASE THE FUNDING AMOUNT FROM 110,000 TO 261,000 AND CHANGE FISCAL YEAR. MOD | BRZ | 0903174 | LEWIS | 9-1079 | CR 1068 | 0.1 | 0.175 | 0.275 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON CR-1068 (MP 0.225) OVER TOWN BRANCH; 3.5 MI EAST OF JCT KY 59; (STRUCTURALLY DEFICIENT, SR=9.5) 068C00061N | 2 | D | BRZ | 2011 | 261000 | 261000 | ESTIMATED | N |  | OBLIGATED | 261000 |  | 261000 | 2011 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.214 | 2012-07-05 | ADD PROJECT TO STIP. NEW |  |  | LEWIS | 9-1082 | KY 8 | 0.074 | 22.563 | 22.637 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 8 OVER KINNICONNICK CREEK 0.094 MILE W OF DUDLEY AVE (CR-1031A) (SR 26.5) 068B00003N |  | D | BRO | 2012 | 650000 | 650000 | [6 empty] | 0
|  |  |  | HPP | 0142009 | LINCOLN | 8-141 | KY 698 |  | 10.251 | 10.8 | RELIABILITY | RECONSTRUCTION(O) | WIDEN AND RECONSTRUCT KY 698 AT MASON GAP ROAD, LINCOLN COUNTY. (2005HPP-KY142) | 5 | C | HPP | 2011 | 438904 | 438904 | ESTIMATED | N | 2010 | OBLIGATED | 769451 |  | 769451 | 2011 | 2nd QUARTER | N/A
|  |  |  | STPS | 5180023 | LINCOLN | 8-907 | KY 78 | 0.45 | 8.2 | 8.65 | SAFETY | SAFETY-HAZARD ELIM(P) | HORIZONTAL/VERTICAL REALIGNMENT AND SIGHT DISTANCE IMPROVEMENT ON KY-78 1.5 MILES EAST OF TURNERSVILLE. B/C=2.11 (2004BOPC) | 3 | R | HES | 2011 | 80000 | 80000 | ESTIMATED | N | 2010 | OBLIGATED | 80000 |  | 80000 | 2011 | 3rd QUARTER | N/A
[6 empty] | LINCOLN | 8-907 | KY 78 | 0.45 | 8.2 | 8.65 | SAFETY | SAFETY-HAZARD ELIM(P) | HORIZONTAL/VERTICAL REALIGNMENT AND SIGHT DISTANCE IMPROVEMENT ON KY-78 1.5 MILES EAST OF TURNERSVILLE. B/C=2.11 (2004BOPC) | 4 | U | HES | 2011 | 110000 | 110000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.072 | 2011-04-28 | INCREASE THE U PHASE. MOD | STPS | 5180024 | LINCOLN | 8-907 | KY 78 | 0.45 | 8.2 | 8.65 | SAFETY | SAFETY-HAZARD ELIM(P) | HORIZONTAL/VERTICAL REALIGNMENT AND SIGHT DISTANCE IMPROVEMENT ON KY-78 1.5 MILES EAST OF TURNERSVILLE. B/C=2.11 (2004BOPC) | 4 | U | HES | 2011 | 300000 | 300000 | ESTIMATED | N | 2010 | OBLIGATED | 300000 |  | 300000 | 2011 | 3rd QUARTER | N/A
[6 empty] | LINCOLN | 8-907 | KY 78 | 0.45 | 8.2 | 8.65 | SAFETY | SAFETY-HAZARD ELIM(P) | HORIZONTAL/VERTICAL REALIGNMENT AND SIGHT DISTANCE IMPROVEMENT ON KY-78 1.5 MILES EAST OF TURNERSVILLE. B/C=2.11 (2004BOPC) | 5 | C | HES | 2011 | 870000 | 870000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.179 | 2012-04-10 | ADD PROJECT TO STIP. NEW |  |  | LINCOLN | 8-914 | KY 78 | 10.935 | 2.2 | 13.135 | SAFETY | SAFETY-HAZARD ELIM(P) | RECONSTRUCT SHOULDERS, INSTALL CURVE SIGNS, GUARDRAIL DELINERATORS, EDGELINE RUMBLE STRIPS, AND REMOVE STUMPS ON KY 78 FROM US 127 AT HUSTONVILLE TO US 150 AT STANFORD. |  | C | SAF | 2012 | 161000 | 161000 | [6 empty] | 0
[6 empty] | LINCOLN | 8-1049 | KY 78 |  | 11.166 | 11.266 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-78 (MP 11.216) OVER PEVYHOUSE BRANCH; .30 MI WEST OF JCT KY 300; (STRUCTURALLY DEFICIENT, SR=43.3) 069B00027N | 2 | D | BRO | 2011 | 130000 | 130000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.033 | 2011-01-26 | INCREASE THE FUNDING AMOUNT OF THE D PHASE. MOD | BRO | 5180022 | LINCOLN | 8-1049 | KY 78 |  | 11.166 | 11.266 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-78 (MP 11.216) OVER PEVYHOUSE BRANCH; .30 MI WEST OF JCT KY 300; (STRUCTURALLY DEFICIENT, SR=43.3) 069B00027N | 2 | D | BRO | 2011 | 165000 | 165000 | ESTIMATED | N | 2010 | OBLIGATED | 165000 |  | 165000 | 2011 | 2nd QUARTER | N/A
[6 empty] | LINCOLN | 8-1049 | KY 78 |  | 11.166 | 11.266 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-78 (MP 11.216) OVER PEVYHOUSE BRANCH; .30 MI WEST OF JCT KY 300; (STRUCTURALLY DEFICIENT, SR=43.3) 069B00027N | 3 | R | BRO | 2012 | 75000 | 75000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | LINCOLN | 8-1049 | KY 78 |  | 11.166 | 11.266 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-78 (MP 11.216) OVER PEVYHOUSE BRANCH; .30 MI WEST OF JCT KY 300; (STRUCTURALLY DEFICIENT, SR=43.3) 069B00027N | 4 | U | BRO | 2012 | 50000 | 50000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.067 | 2011-04-20 | ADD D PHASE. BREAKOUT FROM C PHASE. NEW | STP | 0601160 | LIVINGSTON | 1-184 | US 60 | 2.1 | 17.163 | 19.3 | RELIABILITY | RECONSTRUCTION(O) | PADUCAH-HENDERSON; RECONSTRUCT FROM 0.5 MILES EAST OF DYER HILL MINE ROAD TO LIVINGSTON CENTRAL MIDDLE SCHOOL(10CCR) | 5 | D | STP | 2011 | 350000 | 350000 | ESTIMATED | N |  | OBLIGATED | 350000 |  | 350000 | 2011 | 3rd QUARTER | N/A
|  |  |  | STP | 0601163 | LIVINGSTON | 1-184 | US 60 | 2.1 | 17.163 | 19.3 | RELIABILITY | RECONSTRUCTION(O) | PADUCAH-HENDERSON; RECONSTRUCT FROM 0.5 MILES EAST OF DYER HILL MINE ROAD TO LIVINGSTON CENTRAL MIDDLE SCHOOL(10CCR) | 4 | U | STP | 2011 | 2190000 | 2190000 | ESTIMATED | N |  | OBLIGATED | 2190000 |  | 2190000 | 2011 | 2nd QUARTER | N/A
[6 empty] | LIVINGSTON | 1-184 | US 60 | 2.1 | 17.163 | 19.3 | RELIABILITY | RECONSTRUCTION(O) | PADUCAH-HENDERSON; RECONSTRUCT FROM 0.5 MILES EAST OF DYER HILL MINE ROAD TO LIVINGSTON CENTRAL MIDDLE SCHOOL(10CCR) | 5 | C | STP | 2012 | 11250000 | 11250000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | LIVINGSTON | 1-1059 | KY 453 | 0.1 | 14.162 | 14.167 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-453 OVER ECHO SPRING BRANCH (B29) 0.177 MILE NW OF COON CHAPEL ROAD. (SR=12.5)(08CCR) | 3 | R | BRX | 2013 | 225000 | 225000 | ESTIMATED | [5 empty] | 0
[6 empty] | LIVINGSTON | 1-1059 | KY 453 | 0.1 | 14.162 | 14.167 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-453 OVER ECHO SPRING BRANCH (B29) 0.177 MILE NW OF COON CHAPEL ROAD. (SR=12.5)(08CCR) | 4 | U | BRX | 2013 | 250000 | 250000 | ESTIMATED | [5 empty] | 0
[6 empty] | LIVINGSTON | 1-1059 | KY 453 | 0.1 | 14.162 | 14.167 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-453 OVER ECHO SPRING BRANCH (B29) 0.177 MILE NW OF COON CHAPEL ROAD. (SR=12.5)(08CCR) | 5 | C | BRX | 2014 | 900000 | 900000 | ESTIMATED | [5 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.215 | 2012-07-10 | ADD PROJECT TO STIP. NEW |  |  | LIVINGSTON | 1-1142 | US 60 | 0.344 | 12.348 | 12.692 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON US 60 OVER THE CUMBERLAND RIVER 0.27 MILE N OF KY 70 (SR 32.7) 070B00017N. |  | P | BRO | 2012 | 400000 | 400000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.215 | 2012-07-10 | ADD PROJECT TO STIP. NEW |  |  | LIVINGSTON | 1-1145 | KY 866 | 0.04 | .022 | .062 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 866 OVER FORK OF GUM CREEK 0.02 MILE N OF KY 1664(SR 28.1)070B00050N |  | D | BRO | 2012 | 200000 | 200000 | [6 empty] | 0
[6 empty] | LIVINGSTON | 1-8601 | US 60 | 0.862 | 0 | 0.489 | RELIABILITY | BRIDGE REPLACEMENT(P) | SMITHLAND-PADUCAH BRIDGE AND APPROACHES OVER TENNESSEE RIVER AT MCCRACKEN COUNTY LINE PHASE II ADDITIONAL FUNDING. (10CCN) | 5 | C | BRO | 2011 | 20000000 | 20000000 | ESTIMATED |  |  | OBLIGATED | 20000000 |  | 20000000 | 2010 | 4th QUARTER | N/A
[6 empty] | LIVINGSTON | 1-8602 | US 60 | 0.862 | 0 | 0.489 | RELIABILITY | PREFINANCD CONVRSN(P) | SMITHLAND-PADUCAH BRIDGE AND APPROACHES OVER TENNESSEE RIVER AT MCCRACKEN COUNTY LINE PHASE II ADDITIONAL FUNDING. (10CCN) | 5 | C | BRO | 2012 | 32200000 | 32200000 | ESTIMATED |  |  | OBLIGATED | 45000000 |  | 45000000 | 2010 | 4th QUARTER | N/A
[6 empty] | LIVINGSTON | 1-8602 | US 60 | 0.862 | 0 | 0.489 | RELIABILITY | PREFINANCD CONVRSN(P) | SMITHLAND-PADUCAH BRIDGE AND APPROACHES OVER TENNESSEE RIVER AT MCCRACKEN COUNTY LINE PHASE II ADDITIONAL FUNDING. (10CCN) | 5 | C | BRO | 2013 | 12800000 | 12800000 | ESTIMATED | [5 empty] | 0
[6 empty] | LOGAN | 3-273.01 | US 431 | 4.4 | 21.965 | 26.871 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT/RELOCATE AND CONTINUE FOUR LANING OF US-431 FROM THE END OF THE EXISTING FOUR-LANE NORTH OF EPLEYS TO APPROXIMATELY 1.5 MILES NORTH OF KY-106 EAST (NORTH OF LEWISBURG). (06CCR)(2002BOPC) | 3 | R | STP | 2013 | 6120000 | 6120000 | ESTIMATED | [5 empty] | 0
[6 empty] | LOGAN | 3-273.01 | US 431 | 4.4 | 21.965 | 26.871 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT/RELOCATE AND CONTINUE FOUR LANING OF US-431 FROM THE END OF THE EXISTING FOUR-LANE NORTH OF EPLEYS TO APPROXIMATELY 1.5 MILES NORTH OF KY-106 EAST (NORTH OF LEWISBURG). (06CCR)(2002BOPC) | 4 | U | STP | 2013 | 2540000 | 2540000 | ESTIMATED | [5 empty] | 0
[6 empty] | LOGAN | 3-903 | US 68X |  | 1.477 | 1.577 | SAFETY | SAFETY-HAZARD ELIM(P) | RECONSTRUCTION TO IMPROVE GEOMETRICS OF THE US 68X AND KY 2146 INTERSECTION IN RUSSELLVILLE. (2008BOPC)(10CCR) | 3 | R | HES | 2011 | 20000 | 20000 | ESTIMATED |  | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.094 | 2011-06-28 | INCREASE THE FUNDING AMOUNT. MOD | HSIP | 0801079 | LOGAN | 3-903 | US 68X |  | 1.477 | 1.577 | SAFETY | SAFETY-HAZARD ELIM(P) | RECONSTRUCTION TO IMPROVE GEOMETRICS OF THE US 68X AND KY 2146 INTERSECTION IN RUSSELLVILLE. (2008BOPC)(10CCR) | 3 | R | SAF | 2011 | 75000 | 75000 | ESTIMATED |  | 2010 | OBLIGATED | 75000 |  | 75000 | 2011 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.072 | 2011-04-28 | ADD UTILITY PHASE TO STIP. BREAKOUT FROM 99-911.00. NEW | HSIP | 0801080 | LOGAN | 3-903 | US 68X |  | 1.477 | 1.577 | SAFETY | SAFETY-HAZARD ELIM(P) | RECONSTRUCTION TO IMPROVE GEOMETRICS OF THE US 68X AND KY 2146 INTERSECTION IN RUSSELLVILLE. (2008BOPC)(10CCR) | 3 | U | SAF | 2011 | 70000 | 70000 | ESTIMATED |  | 2010 | OBLIGATED | 180000 |  | 180000 | 2011 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.084 | 2011-06-06 | ADD PROJECT TO STIP. BREAKOUT FROM 99-911.00. NEW | HSIP | 9010054 | LOGAN | 3-908 | KY 178 | 8.206 | 0 | 8.206 | SAFETY | SAFETY-HAZARD ELIM(P) | SAFETY IMPROVEMENTS ALONG KY 178 FROM THE TODD COUNTY LINE TO 0.3MI EAST OF SPORTSMAN CLUB ROAD IN RUSSELLVILLE. |  | C | SAF | 2011 | 1100000 | 1100000 |  |  |  | OBLIGATED | 1100000 |  | 1100000 | 2011 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.084 | 2011-06-06 | ADD PROJECT TO STIP. BREAKOUT FROM 99-911.00. NEW | HSIP | 0801081 | LOGAN | 3-909 | US 68 | 0.3 | 8.7 | 9 | SAFETY | SAFETY-HAZARD ELIM(P) | CONSTRUCT OFFSET LEFT TURN LANES ON US 68 AT HIGHLAND LICK ROAD (KY 178) IN RUSSELLVILLE. |  | C | SAF | 2011 | 315000 | 315000 |  |  |  | OBLIGATED | 330000 |  | 330000 | 2011 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.171 | 2012-03-13 | ADD PROJECT TO STIP. BREAKOUT FROM 99-911.01. NEW |  |  | LOGAN | 3-914 | KY 100 | 9.077 | 0 | 9.077 | SAFETY | SAFETY-HAZARD ELIM(P) | DITCHING AND SHOULDERING, EXTEND CROSS DRAINS AND REMOVE HEADWALLS ON KY 100 FROM US 68 AT RUSSELLVILLE TO LOCUST GROVE ROAD NEAR THE SIMPSON COUNTY LINE. |  | C | SAF | 2012 | 1500000 | 1500000 | [6 empty] | 0
|  |  |  | BRZ | 0303232 | LOGAN | 3-1073 | KY 664 | 0.1 | 3.248 | 3.348 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-664 (MP 3.298) OVER PLEASANT RUN CREEK; 2.3 MI N.W. OF JCT KY 663; (STRUCTURALLY DEFICIENT, SR=29.8) 071B00040N | 2 | D | BRX | 2012 | 150000 | 150000 | ESTIMATED | N |  | OBLIGATED | 150000 |  | 150000 | 2011 | 2nd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.215 | 2012-07-10 | ADD PROJECT TO STIP. NEW |  |  | LOGAN | 3-1078 | KY 2146 | 0.04 | 0.609 | 0.649 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 2146 OVER TOWN BRANCH 0.1 MILE W OF KY 3519(SR 49.3) 071B00067N |  | D | BRO | 2012 | 300000 | 300000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.215 | 2012-07-10 | ADD PROJECT TO STIP. NEW |  |  | LOGAN | 3-1079 | KY 663 | 0.04 | 8.52 | 8.56 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 663 OVER PLEASANT RUN CREEK 2.099 MILES S OF KY 100(SR 49.1) 071B00057N |  | D | BRO | 2012 | 300000 | 300000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.215 | 2012-07-10 | ADD PROJECT TO STIP. NEW |  |  | LOGAN | 3-1083 | CR 1249 | 0.04 | 0.786 | 0.826 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON LOGAN MILL RD (CR 1249) OVER RED RIVER 0.78 MILE SE OF ORNDORFF MILL RD (KY 96)(SR 25.3)071C00023N |  | D | BRZ | 2012 | 250000 | 250000 | [6 empty] | 0
[6 empty] | LYON | 1-7 | I 24 | 0.1 | 35.8 | 35.9 | RELIABILITY | WEIGH STA REHAB(P) | ADD RESTROOM FACILITY TO I-24 EASTBOUND & WESTBOUND WEIGH STATIONS IN LYON COUNTY (DESIGN FUNDS AUTHORIZED UNDER ITEM NO. 99-44.00) | 5 | C | IM | 2014 | 560000 | 560000 | ESTIMATED | [5 empty] | 0
|  |  | TRANSFERRED FUNDS TO 2-2057.00 PER STIP MOD 2010.113 $8,000,000 |  |  | LYON | 99-389 | KY 9001 |  | 0 | 37 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT ELEMENTS OF EXISTING WESTERN KENTUCKY PARKWAY BETWEEN MP 0.0 AND MP 37.0 TO UPGRADE GEOMETRICS TO INTERSTATE STANDARDS (I-69 CORRIDOR IMPROVEMENT) | 5 | C | NH | 2012 | 8000000 | 8000000 | ESTIMATED | [5 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.025 | 2010-12-15 | ADD PROJECT TO STIP. BREAKOUT FROM 99-337.06 ZVARIOUS SECTION OF STIP USING NCIIP DISCRETIONARY FUNDS. NEW | DPR | 0168014 | LYON, CALDWELL, HOPKINS | 2-2057 | KY 9001 | 37 | 0 | 37 | RELIABILITY | RECONSTRUCTION(O) | PROVIDE REQUIRED MODIFICATIONS AND IMPROVEMENTS TO EXISTING W. H. FORD (WESTERN KENTUCKY) PARKWAY BETWEEN MILEPOINT 0.00 IN LYON COUNTY TO MILEPOINT 37.00 IN HOPKINS COUNTY FOR FHWA TO OFFICIALLY DESIGNATE THIS SECTION OF THE PARKWAY PART OF I-69 |  | D | KYD | 2011 | 720000 | 720000 |  | Y |  | OBLIGATED | 720000 |  | 720000 | 2011 | 2nd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.113 | 2011-08-31 | ADD C PHASE TO STIP. MOVING FUNDS FROM ITEM NO. 99-389.00 TO THIS ITEM. MOD | NH | 0021031 | LYON, CALDWELL, HOPKINS | 2-2057 | KY 9001 | 37 | 0 | 37 | RELIABILITY | RECONSTRUCTION(O) | PROVIDE REQUIRED MODIFICATIONS AND IMPROVEMENTS TO EXISTING W. H. FORD (WESTERN KENTUCKY) PARKWAY BETWEEN MILEPOINT 0.00 IN LYON COUNTY TO MILEPOINT 37.00 IN HOPKINS COUNTY FOR FHWA TO OFFICIALLY DESIGNATE THIS SECTION OF THE PARKWAY PART OF I-69 |  | C | NH | 2012 | 8000000 | 8000000 |  |  |  | OBLIGATED | 8183062 | 1830614.88 | 10013676.88 | 2011 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.093 | 2011-06-27 | ADD PROJECT TO STIP. NEW | DPR | 0168015 | LYON, CALDWELL, HOPKINS, MARSHALL, LIVINGSTON | 2-2058 | I 69 |  |  |  | RELIABILITY | PAVEMENT REHAB-INT(P) | INSTALLATION OF I-69 SIGNAGE BEGINNING AT THE I-24/PURCHASE PKWY INTERCHANGE IN MARSHALL CO, PROCEEDING EAST ALONG I-24 TO THE I-24/WESTERN KY PKWY INTERCHANGE IN LYON CO, PROCEEDING EAST ALONG WESTERN KY PKWY TO THE WK PKWY/PENNYRILE PKWY INTERCHANGE IN HOPKINS CO. APPROX 55 MI. |  | D | KYD | 2011 | 150000 | 150000 |  |  |  | OBLIGATED | 150000 |  | 150000 | 2011 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.093 | 2011-06-27 | ADD PROJECT TO STIP. NEW | DPR | 0168016 | LYON, CALDWELL, HOPKINS, MARSHALL, LIVINGSTON | 2-2058 | I 69 |  |  |  | RELIABILITY | PAVEMENT REHAB-INT(P) | INSTALLATION OF I-69 SIGNAGE BEGINNING AT THE I-24/PURCHASE PKWY INTERCHANGE IN MARSHALL CO, PROCEEDING EAST ALONG I-24 TO THE I-24/WESTERN KY PKWY INTERCHANGE IN LYON CO, PROCEEDING EAST ALONG WESTERN KY PKWY TO THE WK PKWY/PENNYRILE PKWY INTERCHANGE IN HOPKINS CO. APPROX 55 MI. |  | C | KYD | 2011 | 1500000 | 1500000 |  |  |  | OBLIGATED | 887665.54 |  | 887665.54 | 2012 | 2nd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.116 | 2011-09-06 | INCREASE FUNDING AMOUNT. MOD | DPR | 0168016 | LYON, CALDWELL, HOPKINS, MARSHALL, LIVINGSTON | 2-2058 | I 69 |  |  |  | RELIABILITY | PAVEMENT REHAB-INT(P) | INSTALL I-69 SIGNAGE BEGIN AT I-24/PURCHASE PKWY INCH IN MARSHALL CO,PROCEED EAST ALONG I-24 TO I-24/WESTERN KY PKWY INCH IN LYON CO,PROCEED EAST ALONG WESTERN KY PKWY TO THE WK PKWY/PENNYRILE PKWY INCH IN HOPKINS CO. APPX 55 MI. |  | C | KYD | 2011 | 2000000 | 2000000 |  |  |  | OBLIGATED | 2000000 |  | 2000000 | 2011 | 4th QUARTER | N/A
[6 empty] | MADISON | 7-236 | KY 595 |  | 2.565 | 2.665 | RELIABILITY | SCOPING STUDY(O) | COMPREHENSIVE TRAFFIC STUDY FOR INTERSECTION OF MAIN STREET AND BEREA COLLEGE CAMPUS, BEREA. (2005HPP-KY112)(MOA WITH BEREA). | 5 | C | HPP | 2011 | 431951 | 431951 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | MADISON | 7-251.01 | US 25 | 3.5 | 11.903 | 15.442 | RELIABILITY | MAJOR WIDENING(O) | WIDEN US-25 FROM US-421 NORTH TO KY-876. STATE TO PROVIDE DESIGN AND PLANS, AND FUNDS FOR THIS PROJECT ARE REQUESTED TO BE PAID TO THE MADISON COUNTY FISCAL COURT, WHICH SHALL COORDINATE THE PROJECT. (2005HPP-KY110)(06CCR) | 5 | C | HPP | 2011 | 719920 | 719920 | ESTIMATED | Y | 2010 |  |  |  | 0
[6 empty] | MADISON | 7-251.4 | US 25 | 2.14 | 12.744 | 14.883 | RELIABILITY | MAJOR WIDENING(O) | PRIORITY SECTION II: WIDEN US-25 FROM 1500' SOUTH OF DUNCANNON ROAD TO PUMPKIN RUN. (2006BOPC)(08CCR)(10CCR) | 3 | R | NHG | 2011 | 4310000 | 4310000 | ESTIMATED | Y | 2010 |  |  |  | 0
[6 empty] | MADISON | 7-251.4 | US 25 | 2.14 | 12.744 | 14.883 | RELIABILITY | MAJOR WIDENING(O) | PRIORITY SECTION II: WIDEN US-25 FROM 1500' SOUTH OF DUNCANNON ROAD TO PUMPKIN RUN. (2006BOPC)(08CCR)(10CCR) | 4 | U | NHG | 2011 | 3020000 | 3020000 | ESTIMATED | Y | 2010 |  |  |  | 0
[6 empty] | MADISON | 7-251.4 | US 25 | 2.14 | 12.744 | 14.883 | RELIABILITY | MAJOR WIDENING(O) | PRIORITY SECTION II: WIDEN US-25 FROM 1500' SOUTH OF DUNCANNON ROAD TO PUMPKIN RUN. (2006BOPC)(08CCR)(10CCR) | 5 | C | NH | 2011 | 6760000 | 6760000 | ESTIMATED | Y | 2010 |  |  |  | 0
|  |  |  | STPR | 4212043 | MADISON | 7-251.7 | US 25 | 0.56 | 14.883 | 15.442 | RELIABILITY | MAJOR WIDENING(O) | PRIORITY SECTION I: WIDEN US-25 FROM PUMPKIN RUN TO KY-876. (2006BOPC)("KYD" FUNDS FOR R, U AND C PHASES TO BE PROVIDED JAN 09 BY DEPARTMENT OF DEFENSE ACCESS ROAD (7C10) FUNDING AS PER AGREEMENT)(08CCR) | 5 | C | KYD | 2011 | 12000000 | 12000000 | ESTIMATED | Y | 2010 | OBLIGATED | 8834000 |  | 8834000 | 2011 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.202 | 2012-06-11 | ADD PROJECT TO STIP. NEW | HSIP | 0753096 | MADISON | 7-920 | I-75 | 0.6 | 89.3 | 89.9 | SAFETY | SAFETY-HAZARD ELIM(P) | MILL AND INLAY WITH POLISH RESISTANT AGGREGATE, DITCH AND DELINEATE SB EXIT RAMP FROM I 75 TO US 25 AND SB ENTRANCE RAMP FROM US 25 TO I 75 AT RICHMOND. |  | C | SAF | 2012 | 260000 | 260000 |  |  |  | OBLIGATED | 260000 |  | 260000 | 2012 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.214 | 2012-07-05 | ADD PROJECT TO STIP. NEW |  |  | MADISON | 7-1126 | KY 3376 | 0.04 | 4.586 | 4.626 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 3376 OVER HAYS FORK 0.048 SOUTH OF US 421 (SR 23.1) 076B00086N. |  | D | BRO | 2012 | 300000 | 300000 | [6 empty] | 0
[6 empty] | MADISON | 7-8403 | KY 627 | 0.1 | 0.073 | 0.193 | RELIABILITY | MAJOR WIDENING(O) | RECONSTRUCT AND WIDEN THE KY-627 BRIDGE OVER I-75 TO FIVE LANES TO IMPROVE TRAFFIC CONGESTION AND IMPROVE SAFETY. (B40) (08CCN)(10CCR) | 3 | R | STP | 2011 | 1300000 | 1300000 | ESTIMATED | [5 empty] | 0
[6 empty] | MADISON | 7-8403 | KY 627 | 0.1 | 0.073 | 0.193 | RELIABILITY | MAJOR WIDENING(O) | RECONSTRUCT AND WIDEN THE KY-627 BRIDGE OVER I-75 TO FIVE LANES TO IMPROVE TRAFFIC CONGESTION AND IMPROVE SAFETY. (B40) (08CCN)(10CCR) | 4 | U | STP | 2011 | 1600000 | 1600000 | ESTIMATED | [5 empty] | 0
[6 empty] | MADISON | 7-8403 | KY 627 | 0.1 | 0.073 | 0.193 | RELIABILITY | MAJOR WIDENING(O) | RECONSTRUCT AND WIDEN THE KY-627 BRIDGE OVER I-75 TO FIVE LANES TO IMPROVE TRAFFIC CONGESTION AND IMPROVE SAFETY. (B40) (08CCN)(10CCR) | 5 | C | STP | 2012 | 13000000 | 13000000 | ESTIMATED | [5 empty] | 0
[6 empty] | MADISON | 7-8503 | KY 21 |  | 9.115 | 9.189 | SAFETY | BIKE/PED FACIL(O) | IMPROVE PROSPECT STREET PEDESTRIAN ACCESS BEREA. (2005HPP-KY128) (MOA WITH BEREA) (SUPPLEMENTAL FUNDING FOR 07-239) (08CCN) | 5 | C | STP | 2011 | 370000 | 370000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.216 | 2012-07-25 | ADD PROJECT TO STIP. NEW |  |  | MAGOFFIN | 10-126.12 | KY 9009 | 3.7 | 70.8 | 74.5 | RELIABILITY | SCOPING STUDY(O) | WIDEN THE MOUNTAIN PARKWAY TO 4 LANES FROM APPROXIMATELY 0.25 MILES EAST OF KY 3050 OVERPASS (MP 70.80) TO BRIDGE OVER LICKING RIVER (MP 74.50). (2012BOP) |  | D | STP | 2012 | 1250000 | 1250000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.216 | 2012-07-25 | ADD PROJECT TO STIP. NEW |  |  | MAGOFFIN | 10-126.4 | KY 9009 | 5.3 | 64.9 | 70.2 | RELIABILITY | MAJOR WIDENING(O) | WIDEN THE MOUNTAIN PARKWAY TO 4 LANES FROM 0.3MI W OF THE CUTINO-HAGER RD O-PASS TO 0.3MI W OF GIFFORD ROAD. (2012 BOP) |  | D | STP | 2012 | 1000000 | 1000000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.211 | 2012-06-28 | ADD PROJECT TO STIP. NEW |  |  | MAGOFFIN MORGAN | 10-126.50 | KY 9009 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | WIDEN THE MOUNTAIN PARKWAY TO 4 LANES FROM 0.3MI E OF THE KY-134-JOHNSON CREEK BR TO 0.3MI W OF THE CUTINO-HAGER RD O-PASS - SECTION 5 |  | D | NH | 2012 | 1500000 | 1500000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.211 | 2012-06-28 | ADD PROJECT TO STIP. NEW |  |  | MAGOFFIN MORGAN | 10-126.60 | KY 9009 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | WIDEN THE MOUNTAIN PARKWAY TO 4 LANES FROM 0.45 MI WEST OF KY-134 @ INSKO TO 0.3 MI EAST OF THE KY-134-JOHNSON CREEK BRIDGE - SECTION 6 (12CCR) |  | D | NH | 2012 | 1040000 | 1040000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.216 | 2012-07-25 | ADD PROJECT TO STIP. NEW |  |  | MAGOFFIN | 10-166 | US 460 | 2.080 | 12.486 | 14.566 | RELIABILITY | MAJOR WIDENING(O) | WIDEN THE MOUNTAIN PARKWAY EXTENSION (KY 114/US 460) THROUGH THE CONGESTED AREA AT SALYERSVILLE. |  | P | NH | 2012 | 900000 | 900000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.216 | 2012-07-25 | ADD PROJECT TO STIP. NEW |  |  | MAGOFFIN | 10-166 | US 460 | 2.080 | 12.486 | 14.566 | RELIABILITY | MAJOR WIDENING(O) | WIDEN THE MOUNTAIN PARKWAY EXTENSION (KY 114/US 460) THROUGH THE CONGESTED AREA AT SALYERSVILLE. |  | D | NH | 2012 | 1100000 | 1100000 | [6 empty] | 0
|  |  |  | BRZ | 1003196 | MAGOFFIN | 10-1092 | CR 1756 | 0.1 | 0 | 0.1 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON CR-1756 (MP 0.031) OVER TRACE FORK; .08 MI-N JCT KY 542; (STRUCTURALLY DEFICIENT, SR=17.3) 077C00048N | 2 | D | BRZ | 2012 | 120000 | 120000 | ESTIMATED | N |  | OBLIGATED | 150000 |  | 150000 | 2011 | 1st QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.207 | 2012-06-18 | ADD PROJECT TO STIP. NEW |  |  | MAGOFFIN | 10-1098 | KY 2019 |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 2019 OVER LICK CREEK 0.055 MILE SOUTH OF KY 3334 (SR 31.9) |  | D | BRO | 2012 | 200000 | 200000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.207 | 2012-06-18 | ADD PROJECT TO STIP. NEW |  |  | MAGOFFIN | 10-1099 | KY 2019 |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 2019 OVER RACCOON CREEK 0.039 SOUTH OF KY 1081 (SR 33.2) |  | D | BRO | 2012 | 200000 | 200000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.157 | 2012-01-19 | ADD PROJECT TO STIP. NEW | HSIP | 0551040 | MARION | 4-917 | US 68 | 4.53 | 0 | 4.53 | SAFETY | SAFETY | EXTEND CULVERTS, REPLACE HEADWALLS AND PLACE EMBANKMENT TO WIDEN SHOULDERS ON US 68 FROM THE TAYLOR COUNTY LINE, NORTH TO KY 412 |  | C | SAF | 2012 | 354000 | 354000 |  | N |  | OBLIGATED | 354000 |  | 354000 | 2012 | 2nd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.157 | 2012-01-19 | ADD PROJECT TO STIP. NEW |  |  | MARION | 4-918 | KY 49 | 3.21 | 13.19 | 16.4 | SAFETY | SAFETY | EXTEND CULVERTS, REPLACE HEADWALLS AND PLACE EMBANKMENT TO WIDEN SHOULDERS ON KY 49 FROM CANEY CREEK BRIDGE TO HARDIN CREEK CULVERT 0.4 MI SOUTH OF KY 3221 |  | C | SAF | 2012 | 88000 | 88000 |  | N |  |  |  |  | 0
|  |  |  | BRZ | 0403178 | MARION | 4-1066 | KY 1195 | 0.1 | 0.834 | 0.934 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-1195 (MP 0.884) OVER CARTWRIGHTS CREEK; .80 MI NORTH OF JCT US 68; (STRUCTURALLY DEFICIENT, SR=43.3) 078B00051N | 2 | D | BRX | 2012 | 150000 | 150000 | ESTIMATED | N |  | OBLIGATED | 150000 |  | 150000 | 2011 | 2nd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.197 | 2012-05-30 | ADD PROJECT TO STIP. NEW |  |  | MARION | 4-1076 | KY 49 | 0.04 | 20.553 | 20.593 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 49 OVER HAMILTON BRANCH 0.33 MILE E OF COWHERD LN (CR-1301) (SR 41.4) 078B00031N. |  | D | BRO | 2012 | 75000 | 75000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.142 | 2011-11-09 | ADD DESIGN PHASE TO STIP. NEW | BRO | 0801088 | MARSHALL | 1-180.7 | US 68 | 1.2 | 27.801 | 28.146 | RELIABILITY | BRIDGE REPLACEMENT(P) | CADIZ-AURORA; BRIDGE OVER KY. LAKE, PHASE II DESIGN | 4 | D | BRO | 2012 | 10000000 | 10000000 | ESTIMATED | Y |  | OBLIGATED |  | 10000000 | 10000000 | 2012 | 1ST QUARTER | N/A
[6 empty] | MARSHALL | 1-180.7 | US 68 | 1.2 | 27.801 | 28.146 | RELIABILITY | BRIDGE REPLACEMENT(P) | CADIZ-AURORA; BRIDGE OVER KY. LAKE (ESTIMATED CONSTRUCTION PHASE COST IS $165 MILLION): (079B00023N)(10CCR) | 4 | U | GVR | 2011 | 330000 | 330000 | ESTIMATED | Y |  |  |  |  | 0
[6 empty] | MARSHALL | 1-180.7 | US 68 | 1.2 | 27.801 | 28.146 | RELIABILITY | BRIDGE REPLACEMENT(P) | CADIZ-AURORA; BRIDGE OVER KY. LAKE (ESTIMATED CONSTRUCTION PHASE COST IS $165 MILLION): (079B00023N)(10CCR) | 5 | C | GVR | 2012 | 99990000 | 99990000 | ESTIMATED | Y |  |  |  |  | 0
[6 empty] | MARSHALL | 1-180.71 | US 68 | 1.2 | 27.801 | 28.146 | RELIABILITY | PREFINANCD CONVRSN(O) | CADIZ-AURORA; BRIDGE OVER KY. LAKE (ADDITIONAL FUNDING FOR C PHASE)(10CCR) | 5 | C | GVR | 2012 | 65000000 | 65000000 | REESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.191 | 2012-05-16 | ADD PROJECT TO STIP. NEW | NH | 0241084 | MARSHALL | 1-800 | I-24 | 0.879 | 24.5 | 25.379 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | RECONSTRUCT I-24/PURCHASE PARKWAY INTERCHANGE (I-69 CORRIDOR IMPROVEMENT) (12CCR) |  | D | NH | 2012 | 2400000 | 2400000 |  |  |  | OBLIGATED | 2400000 |  | 2400000 | 2012 | 4th QUARTER | N/A
[6 empty] | MARTIN | 12-154.04 | KY 40 | 1.6 |  |  | RELIABILITY | RELOCATION(O) | INEZ TO WARFIELD (SECTION 1-3); FR EXISTING KY-40, EXTENDING EAST 1.5 MILES ALONG LITTLE BLACKLOG FORK INCLUDING MAINLINE BRIDGE OVER EXISTING KY-40 AND EAST SIDE I-CHNG RAMPS. [STA. 3+293.000 TO STA. 5+800.000 (METRIC)] (10CCR) | 5 | C | STP | 2012 | 15000000 | 15000000 | ESTIMATED | N |  |  |  |  | 0
|  |  |  | STPR | 0401073 | MARTIN | 12-154.04 | KY 40 | 1.6 |  |  | RELIABILITY | PREFINANCD CONVRSN(O) | INEZ TO WARFIELD (SECTION 1-3); FR EXISTING KY-40, EXTENDING EAST 1.5 MILES ALONG LITTLE BLACKLOG FORK INCLUDING MAINLINE BRIDGE OVER EXISTING KY-40 AND EAST SIDE I-CHNG RAMPS. [STA. 3+293.000 TO STA. 5+800.000 (METRIC)] (10CCR) | 5 | C | STP | 2013 | 24100000 | 24100000 | ESTIMATED | N |  | OBLIGATED | 39936842 |  | 39936842 | 2011 | 2nd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.193 | 2012-05-25 | ADD PROJECT TO STIP. NEW |  |  | MARTIN | 12-154.10 | KY 40 |  |  |  | RELIABILITY | RELOCATION(O) | INEZ TO WARFIELD (PRIORITY SECTION II): FROM LITTLE BLACK LOG TO KY-292. |  | D | STP | 2012 | 1750000 | 1750000 |  | N |  |  |  |  | 0
|  |  |  | BRZ | 1203327 | MARTIN | 12-1083 | CR 1351 | 0.1 | 0.004 | 0.03 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON CR-1351 OVER ROCKCASTLE CREEK (C52)(TO BE LET WITH 12-1087.00). (SR=23.5) | 3 | R | BRZ | 2011 | 160000 | 160000 | ESTIMATED | N | 2010 | OBLIGATED | 100000 |  | 100000 | 2011 | 2nd QUARTER | N/A
|  |  |  | BRZ | 1203319 | MARTIN | 12-1083 | CR 1351 | 0.1 | 0.004 | 0.03 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON CR-1351 OVER ROCKCASTLE CREEK (C52)(TO BE LET WITH 12-1087.00). (SR=23.5) | 4 | U | BRZ | 2011 | 160000 | 160000 | ESTIMATED | N | 2010 | OBLIGATED | 230000 |  | 230000 | 2011 | 1st QUARTER | N/A
|  |  |  | BRZ | 1203332 | MARTIN | 12-1083 | CR 1351 | 0.1 | 0.004 | 0.03 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON CR-1351 OVER ROCKCASTLE CREEK (C52)(TO BE LET WITH 12-1087.00). (SR=23.5) | 5 | C | BRZ | 2011 | 510000 | 510000 | ESTIMATED | N | 2010 | OBLIGATED | 675393.75 |  | 675393.75 | 2011 | 4th QUARTER | N/A
|  |  |  | BRZ | 1203328 | MARTIN | 12-1087 | KY 3411 | 0.1 | 0.168 | 0.187 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-3411 OVER ROCKCASTLE CREEK (B27)(TO BE LET WITH 12-1083.00). (SR=3.1): (080B00027N) | 3 | R | BRX | 2011 | 340000 | 340000 | ESTIMATED | N | 2010 | OBLIGATED | 100000 |  | 100000 | 2011 | 2nd QUARTER | N/A
|  |  |  | BRZ | 1203318 | MARTIN | 12-1087 | KY 3411 | 0.1 | 0.168 | 0.187 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-3411 OVER ROCKCASTLE CREEK (B27)(TO BE LET WITH 12-1083.00). (SR=3.1): (080B00027N) | 4 | U | BRX | 2011 | 220000 | 220000 | ESTIMATED | N | 2010 | OBLIGATED | 110000 |  | 110000 | 2011 | 1st QUARTER | N/A
|  |  |  | BRZ | 1203333 | MARTIN | 12-1087 | KY 3411 | 0.1 | 0.168 | 0.187 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-3411 OVER ROCKCASTLE CREEK (B27)(TO BE LET WITH 12-1083.00). (SR=3.1): (080B00027N) | 5 | C | BRX | 2011 | 660000 | 660000 | ESTIMATED | N |  | OBLIGATED | 725006.25 |  | 725006.25 | 2011 | 4th QUARTER | N/A
[6 empty] | MARTIN | 12-1092 | PR 1015 | 0.1 | 0 | 0.028 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON PR-1015 OVER ROCKCASTLE CREEK (C26) 275 FEET WEST JCT. KY-3 JUST SOUTH OF CROOKED RUN ROAD. (SR=2.0): (080C00026N) | 5 | C | BRZ | 2012 | 90000 | 90000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | MASON | 9-169 | KY 9 | 3.5 | 10.256 | 13.987 | RELIABILITY | MAJOR WIDENING(O) | WIDEN THE AA HWY TO 4-LANES FROM THE NEW MAYSVILLE BRIDGE APPROACH INTERSECTION WEST TO KY-10 (FERNLEAF-GERMANTOWN RD). (00CCR) (04CCN)(06CCR)(08CCR)(10CCR) | 3 | R | NHG | 2011 | 1580000 | 1580000 | ESTIMATED | Y | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.012 | 2010-11-05 | CHANGE FUNDING AMOUNT. MOD | NH | 5462019 | MASON | 9-169 | KY 9 | 3.5 | 10.256 | 13.987 | RELIABILITY | MAJOR WIDENING(O) | WIDEN THE AA HWY TO 4-LANES FROM THE NEW MAYSVILLE BRIDGE APPROACH INTERSECTION WEST TO KY-10 (FERNLEAF-GERMANTOWN RD). (00CCR) (04CCN)(06CCR)(08CCR)(10CCR) | 3 | R | NHG | 2011 | 2450000 | 2450000 | ESTIMATED | Y |  | OBLIGATED | 2450000 |  | 2450000 | 2011 | 1st QUARTER | N/A
[6 empty] | MASON | 9-169 | KY 9 | 3.5 | 10.256 | 13.987 | RELIABILITY | MAJOR WIDENING(O) | WIDEN THE AA HWY TO 4-LANES FROM THE NEW MAYSVILLE BRIDGE APPROACH INTERSECTION WEST TO KY-10 (FERNLEAF-GERMANTOWN RD). (00CCR) (04CCN)(06CCR)(08CCR)(10CCR) | 4 | U | NHG | 2011 | 1040000 | 1040000 | ESTIMATED | Y | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.012 | 2010-11-05 | CHANGE FUNDING AMOUNT. MOD | NH | 5462020 | MASON | 9-169 | KY 9 | 3.5 | 10.256 | 13.987 | RELIABILITY | MAJOR WIDENING(O) | WIDEN THE AA HWY TO 4-LANES FROM THE NEW MAYSVILLE BRIDGE APPROACH INTERSECTION WEST TO KY-10 (FERNLEAF-GERMANTOWN RD). (00CCR) (04CCN)(06CCR)(08CCR)(10CCR) | 3 | U | NHG | 2011 | 2300000 | 2300000 | ESTIMATED | Y |  | OBLIGATED | 2300000 |  | 2300000 | 2011 | 1st QUARTER | N/A
[6 empty] | MASON | 9-202 | KY 11 |  | 5.08 | 5.129 | RELIABILITY | BRIDGE REHAB(P) | REPAIR BRIDGE ON KY-11 OVER CSX RAILROAD AND STRODES RUN PIKE USING HIGH STRENGTH STEEL REINFORCED POLYMER (SRP) FIBERS. (FY09 IBRD DISCRETIONARY PROJECT): (081B00049N) | 5 | C | KYD | 2011 | 210000 | 210000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.171 | 2012-03-13 | ADD PROJECT TO STIP. BREAKOUT FROM 99-911.01. NEW | HSIP | 5390005 | MASON | 9-909 | KY 10 | 4.3 | 5.2 | 9.5 | SAFETY | SAFETY-HAZARD ELIM(P) | GUARDRAIL END TREATMENTS, DITCHING AND SHOULDERING AND DRAINAGE STRUCTURE REPAIRS ON KY 10 FROM CARMEL STREET (KY 2513) IN MAYSVILLE TO DAY PIKE AT PLUMVILLE. |  | C | SAF | 2012 | 330000 | 330000 |  |  |  | OBLIGATED | 330000 |  | 330000 | 2012 | 2nd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.216 | 2012-07-25 | ADD PROJECT TO STIP. NEW |  |  | MASON | 9-915 | KY 3170 | 1.297 | 0 | 1.297 | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALL GUARDRAIL END TREATMENTS, RESHAPE DITCHES AND SHOULDERS AND REPAIR DRAINAGE STRUCTURES ON KY 3170 FROM KY 11 (MP 0.000) TO KY 419 (MP 1.297)(2012BOP) |  | C | SAF | 2012 | 105000 | 105000 | [6 empty] | 0
[6 empty] | MCCRACKEN | 1-2 | I 24 | 1 | 0 | 1.067 | SAFETY | BRIDGE INSPECTION(P) | I-24 BRIDGE OVER THE OHIO RIVER @ PADUCAH (B100); JOINT PROJECT WITH ILLINOIS TO MITIGATE SCOUR (073B00100N) | 5 | C | IM | 2011 | 260000 | 260000 | ESTIMATED | Y | 2010 |  |  |  | 0
[6 empty] | MCCRACKEN | 1-122.01 |  |  |  |  | RELIABILITY | TRANSP ENHANCEMENT(P) | PADUCAH WATERFRONT DEVELOPMENT PROJECT. (2006KYD) | 5 | C | KYD | 2011 | 6196900 | 6196900 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | MCCRACKEN | 1-1014 | KY 1014 | 0.1 | 1.324 | 1.336 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER BLIZZARD BOTTOM DITCH (B12) 0.65MI S OF JCT. KY-999. (SR=8.8): (073B00012N)(10CCR) | 5 | C | BRX | 2011 | 470000 | 470000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.106 | 2011-08-23 | INCREASE FUNDING AMOUNT. MOD | BRZ | 0103297 | MCCRACKEN | 1-1014 | KY 1014 | 0.1 | 1.324 | 1.336 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER BLIZZARD BOTTOM DITCH (B12) 0.65MI S OF JCT. KY-999. (SR=8.8): (073B00012N)(10CCR) | 5 | C | BRZ | 2011 | 600000 | 600000 | ESTIMATED | N | 2010 | OBLIGATED | 1157517.6 |  | 1157517.6 | 2011 | 4th QUARTER | N/A
[6 empty] | MCCRACKEN | 1-1055 | US 62 | 0.1 | 0.884 | 0.892 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON US-62 OVER SUGG CREEK (B24) 0.2 MILE NORTH OF WOBLE ROAD. (SR=29.5): (073B00024N) | 3 | R | BRO | 2012 | 250000 | 250000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | MCCRACKEN | 1-1055 | US 62 | 0.1 | 0.884 | 0.892 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON US-62 OVER SUGG CREEK (B24) 0.2 MILE NORTH OF WOBLE ROAD. (SR=29.5): (073B00024N) | 4 | U | BRO | 2012 | 350000 | 350000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | MCCRACKEN | 1-1055 | US 62 | 0.1 | 0.884 | 0.892 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON US-62 OVER SUGG CREEK (B24) 0.2 MILE NORTH OF WOBLE ROAD. (SR=29.5) | 5 | C | BRO | 2014 | 1200000 | 1200000 | ESTIMATED | [5 empty] | 0
[6 empty] | MCCRACKEN | 1-1115.1 | US 60 | 1 | 18.65 | 19.673 | RELIABILITY | RELOCATION(O) | RELOCATION AND MINOR WIDENING OF US-60 FROM CLARKS RIVER TO US-62 JCT. | 2 | D | STP | 2013 | 320000 | 320000 | ESTIMATED | [5 empty] | 0
[6 empty] | MCCRACKEN | 1-1115.1 | US 60 | 1 | 18.65 | 19.673 | RELIABILITY | RELOCATION(O) | RELOCATION AND MINOR WIDENING OF US-60 FROM CLARKS RIVER TO US-62 JCT. | 3 | R | STP | 2013 | 4640000 | 4640000 | ESTIMATED | [5 empty] | 0
[6 empty] | MCCRACKEN | 1-1115.1 | US 60 | 1 | 18.65 | 19.673 | RELIABILITY | RELOCATION(O) | RELOCATION AND MINOR WIDENING OF US-60 FROM CLARKS RIVER TO US-62 JCT. | 4 | U | STP | 2013 | 3510000 | 3510000 | ESTIMATED | [5 empty] | 0
[6 empty] | MCCRACKEN | 1-1115.1 | US 60 | 1 | 18.65 | 19.673 | RELIABILITY | RELOCATION(O) | RELOCATION AND MINOR WIDENING OF US-60 FROM CLARKS RIVER TO US-62 JCT. | 5 | C | STP | 2014 | 15190000 | 15190000 | ESTIMATED | [5 empty] | 0
[6 empty] | MCCRACKEN | 1-1115.11 | US 60 | 1 | 18.65 | 19.673 | RELIABILITY | RELOCATION(O) | RELOCATION AND MINOR WIDENING OF US-60 FROM CLARKS RIVER TO US-62 JCT. | 5 | C | BRO | 2014 | 15000000 | 15000000 | ESTIMATED | [5 empty] | 0
[6 empty] | MCCRACKEN | 1-1115.2 | US 62 | 1.5 | 12.881 | 14.358 | RELIABILITY | RELOCATION(O) | RELOCATION OF US-62 FROM US-60 DEPARTURE TO KY-1887 (PARK ROAD). | 2 | D | STP | 2013 | 520000 | 520000 | ESTIMATED | [5 empty] | 0
[6 empty] | MCCRACKEN | 1-1115.2 | US 62 | 1.5 | 12.881 | 14.358 | RELIABILITY | RELOCATION(O) | RELOCATION OF US-62 FROM US-60 DEPARTURE TO KY-1887 (PARK ROAD). | 3 | R | STP | 2013 | 6950000 | 6950000 | ESTIMATED | [5 empty] | 0
[6 empty] | MCCRACKEN | 1-1115.2 | US 62 | 1.5 | 12.881 | 14.358 | RELIABILITY | RELOCATION(O) | RELOCATION OF US-62 FROM US-60 DEPARTURE TO KY-1887 (PARK ROAD). | 4 | U | STP | 2014 | 3510000 | 3510000 | ESTIMATED | [5 empty] | 0
|  |  |  | BRO | 5021008 | MCCRACKEN | 1-1135 | KY 348 | 0.1 | 6.011 | 6.111 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-348 (MP 6.061) OVER CAMP CREEK; .02 MI NORTH OF JCT KY 168; (STRUCTURALLY DEFICIENT, SR=4). 073B00099N | 2 | D | BRO | 2012 | 170000 | 170000 | ESTIMATED | N |  | OBLIGATED | 170000 |  | 170000 | 2011 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.211 | 2012-06-28 | ADD PROJECT TO STIP. NEW |  |  | MCCRACKEN | 1-1141 | KY 305 | 0.04 | 6.045 | 6.085 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-305 OVER MASSAC CREEK 0.023 E OF KY 1565(SR 20.7)073B00098N. |  | D | BRO | 2012 | 325000 | 325000 | [6 empty] | 0
|  |  | THIS ITEM NUMBER IS A BREAKOUT OF ZVARIOUS NO. 99-354.06. NEW | HSIP | 3015023 | MCCRACKEN | 99-354.06 | KY 998 | 1.878 | 0.322 | 2.2 | SAFETY | SAFETY-HAZARD ELIM(P) | TREE AND BRUSH REMOVAL, DITCH RESTORATION, SHOULDER IMPROVEMENTS, INSTALL ENTRANCE PIPES AND ENTRANCE PAVEMENT'S SIGNING. OLIVET CHURCH ROAD SOUTHWEST OF PADUCAH FROM 0.3 MILE NORTH OF US 62 TO 0.3 MILE NORTH OF HANSEN ROAD. |  | C | HES | 2011 | 325000 | 325000 |  |  |  | OBLIGATED | 325000 |  | 325000 | 2011 | 2nd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.215 | 2012-07-10 | ADD PROJECT TO STIP. NEW |  |  | MCLEAN | 2-1078 | US 431 |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE OVERFLOW STRUCTURE ON US-431 AT THE MUHLENBERG-MCLEAN CO LINE (SR 39) B00056N. |  | D | BRO | 2012 | 400000 | 400000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.216 | 2012-07-25 | ADD PROJECT TO STIP. NEW |  |  | MEADE | 4-919 | US 31W | 0.865 | 2.524 | 3.389 | SAFETY | SAFETY-HAZARD ELIM(P) | REPLACE TURN DOWN GUARDRAIL END TREATMENTS AND REMOVE AND RESET LOW RAIL ON US 31W AT MULDRAUGH FROM 0.24 MILE NORTH OF KY 1638 (MP 2.524) TO 0.438 MILE SOUTH OF THE HARDIN COUNTY LINE (MP 3.389).(2012BOP) |  | C | SAF | 2012 | 170000 | 170000 | [6 empty] | 0
|  |  |  | BRZ | 1003198 | MENIFEE | 10-1090 | KY 36 | 0.1 | 6.031 | 6.131 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-36 (MP 6.081) OVER BEAVER CREEK IN FRENCHBURG; .05 MI NORTH OF JCT US-460; (STRUCTURALLY DEFICIENT, SR=39.7) 083B00001N | 2 | D | BRO | 2012 | 210000 | 210000 | ESTIMATED | N |  | OBLIGATED | 335000 |  | 335000 | 2011 | 1st QUARTER | N/A
|  |  |  | BRO | 5129012 | MERCER | 7-1116 | KY 152 | 0.1 | 18.818 | 18.894 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-152 OVER HERRINGTON LAKE AT THE MERCER/GARRARD COUNTY LINE (B05). (SR=3.0); (084B00005N) | 2 | D | BRO | 2011 | 1000000 | 1000000 | ESTIMATED | N | 2010 | OBLIGATED | 1000000 |  | 1000000 | 2011 | 3rd QUARTER | N/A
[6 empty] | MERCER | 7-1116 | KY 152 | 0.1 | 18.818 | 18.894 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-152 OVER HERRINGTON LAKE AT THE MERCER/GARRARD COUNTY LINE (B05). (SR=3.0); (084B00005N) | 3 | R | BRO | 2012 | 500000 | 500000 | NON-SIXYEAR | N |  |  |  |  | 0
[6 empty] | MERCER | 7-1116 | KY 152 | 0.1 | 18.818 | 18.894 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-152 OVER HERRINGTON LAKE AT THE MERCER/GARRARD COUNTY LINE (B05). (SR=3.0); (084B00005N) | 4 | U | BRO | 2012 | 400000 | 400000 | NON-SIXYEAR | N |  |  |  |  | 0
|  |  |  | BRZ | 0703301 | MERCER | 7-1117 | CR 1225 | 0.1 | 2.217 | 2.261 | SAFETY | BRIDGE REPLACEMENT(P) | DEEP CREEK ROAD; REPLACE BRIDGE AND APPROACHES OVER CHAPLIN RIVER 0.38 MILE SOUTH OF KY-152 (C13). (SR=0.0): (084C00013N) | 2 | D | BRZ | 2011 | 150000 | 150000 | ESTIMATED | N |  | OBLIGATED | 150000 |  | 150000 | 2011 | 2nd QUARTER | N/A
[6 empty] | MERCER | 7-1117 | CR 1225 | 0.1 | 2.217 | 2.261 | SAFETY | BRIDGE REPLACEMENT(P) | DEEP CREEK ROAD; REPLACE BRIDGE AND APPROACHES OVER CHAPLIN RIVER 0.38 MILE SOUTH OF KY-152 (C13). (SR=0.0): (084C00013N) | 3 | R | BRZ | 2012 | 100000 | 100000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | MERCER | 7-1117 | CR 1225 | 0.1 | 2.217 | 2.261 | RELIABILITY | BRIDGE REPLACEMENT(P) | DEEP CREEK ROAD; REPLACE BRIDGE AND APPROACHES OVER CHAPLIN RIVER 0.38 MILE SOUTH OF KY-152 (C13). (SR=0.0) | 4 | U | BRZ | 2013 | 75000 | 75000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | MERCER | 7-1117 | CR 1225 | 0.1 | 2.217 | 2.261 | RELIABILITY | BRIDGE REPLACEMENT(P) | DEEP CREEK ROAD; REPLACE BRIDGE AND APPROACHES OVER CHAPLIN RIVER 0.38 MILE SOUTH OF KY-152 (C13). (SR=0.0) | 5 | C | BRZ | 2014 | 750000 | 750000 | ESTIMATED | N |  |  |  |  | 0
|  |  |  | BRZ | 0703299 | MERCER | 7-1118 | CR 1310 | 0.1 | 0.407 | 0.426 | SAFETY | BRIDGE REPLACEMENT(P) | CENTRAL PIKE; REPLACE BRIDGE AND APPROACHES OVER THOMPSON CREEK 0.4 MILE EAST OF KY-390 (C28). (SR=14.6): (084C00028N) | 2 | D | BRX | 2011 | 90000 | 90000 | ESTIMATED | N | 2010 | OBLIGATED | 120000 |  | 120000 | 2011 | 1st QUARTER | N/A
|  |  |  | BRZ | 0703304 | MERCER | 7-1118 | CR 1310 | 0.1 | 0.407 | 0.426 | SAFETY | BRIDGE REPLACEMENT(P) | CENTRAL PIKE; REPLACE BRIDGE AND APPROACHES OVER THOMPSON CREEK 0.4 MILE EAST OF KY-390 (C28). (SR=14.6): (084C00028N) | 3 | R | BRX | 2012 | 100000 | 100000 | ESTIMATED | N |  | OBLIGATED | 118000 |  | 118000 | 2012 | 1st QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.101 | 2011-07-25 | INCREASE THE RIGHT-OF-WAY PHASE FUNDING AMOUNT. MOD |  |  | MERCER | 7-1118 | CR 1310 | 0.1 | 0.407 | 0.426 | SAFETY | BRIDGE REPLACEMENT(P) | CENTRAL PIKE; REPLACE BRIDGE AND APPROACHES OVER THOMPSON CREEK 0.4 MILE EAST OF KY-390 (C28). (SR=14.6): (084C00028N) | 3 | R | BRX | 2012 | 118000 | 118000 | ESTIMATED | N |  |  |  |  | 0
|  |  |  | BRZ | 0703305 | MERCER | 7-1118 | CR 1310 | 0.1 | 0.407 | 0.426 | SAFETY | BRIDGE REPLACEMENT(P) | CENTRAL PIKE; REPLACE BRIDGE AND APPROACHES OVER THOMPSON CREEK 0.4 MILE EAST OF KY-390 (C28). (SR=14.6): (084C00028N) | 4 | U | BRX | 2012 | 100000 | 100000 | ESTIMATED | N |  | OBLIGATED | 100000 |  | 100000 | 2012 | 1st QUARTER | N/A
|  |  |  | BRZ | 0703306 | MERCER | 7-1118 | CR 1310 | 0.1 | 0.407 | 0.426 | RELIABILITY | BRIDGE REPLACEMENT(P) | CENTRAL PIKE; REPLACE BRIDGE AND APPROACHES OVER THOMPSON CREEK 0.4 MILE EAST OF KY-390 (C28). (SR=14.6) | 5 | C | BRX | 2013 | 430000 | 430000 | ESTIMATED | N |  | OBLIGATED | 480000 |  | 480000 | 2012 | 2nd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.214 | 2012-07-05 | ADD PROJECT TO STIP. NEW |  |  | MERCER | 7-1128 | US 68 | 0.4 | 12.5 | 12.9 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON US 68 OVER SHAKER CREEK 0.21 E OF CHATHAM RD(CR-1113)(SR 36.2) 084B0001N |  | D | BRO | 2012 | 300000 | 300000 | [6 empty] | 0
[6 empty] | METCALFE | 3-112.1 | KY 90 |  | 0 | 11.719 | RELIABILITY | SPOT IMPROVEMENTS(O) | SPOT IMPROVEMENTS ALONG KY-90 BETWEEN THE BARREN COUNTY LINE AND THE CUMBERLAND COUNTY LINE. (06CCR)(2006BOPC)(08CCR) | 5 | C | STP | 2011 | 5000000 | 5000000 | ESTIMATED | N | 2010 |  |  |  | 0
|  |  |  | BRZ | 0303231 | METCALFE | 3-1075 | CS 1053 | 0.1 | 0.277 | 0.377 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON CS-1053 (MP 0.327) OVER CLAY LICK CREEK; 0.4 MI SOUTH OF JCT US 68; (STRUCTURALLY DEFICIENT, SR=33.1) 085C00007N | 2 | D | BRZ | 2012 | 150000 | 150000 | ESTIMATED | N |  | OBLIGATED | 150000 |  | 150000 | 2011 | 2nd QUARTER | N/A
|  |  |  | ARRA | 3000808 | MONROE | 3-156 | KY 214 | 0.1 | 1.737 | 1.837 | RELIABILITY | FERRY OPERATION(P) | TURKEY NECK BEND FERRY BARGE TUGBOAT- REPLACE AGING FERRY AND TRAILER. | 5 | C | FS | 2011 | 300000 | 300000 | ESTIMATED |  | 2010 | OBLIGATED | 300000 |  | 300000 | 2010 | 4th QUARTER | N/A
|  |  |  | STPR | 5104011 | MONROE | 3-276.5 | KY 163 | 3.95 | 17.45 | 18.188 | RELIABILITY | RELOCATION(O) | TOMPKINSVILLE - KY-90 (SECTION 2): FROM 0.68 MI SOUTH OF CYCLONE ROAD IN MONROE COUNTY, EXTENDING NORTHERLY TO KY-90 IN METCALFE COUNTY (GRADE, DRAIN AND INC. SURFACE). (02CCR) (2002BOP)(10CCR) | 5 | C | STP | 2011 | 9410000 | 9410000 | ESTIMATED | N | 2010 | OBLIGATED | 9410000 |  | 9410000 | 2011 | 3rd QUARTER | N/A
[6 empty] | MONROE | 3-276.57 | KY 163 | 3.61 | 17.45 | 18.188 | RELIABILITY | RELOCATION(O) | TOMPKINSVILLE - KY-90 (SECTION 2 SURFACE): FROM 0.68 MI SOUTH OF CYCLONE ROAD IN MONROE COUNTY, EXTENDING NORTHERLY TO KY-90 IN METCALFE COUNTY (FINAL SURFACING). (02CCR)(06CCR) (2002BOP)(10CCR) | 5 | C | STP | 2011 | 4660000 | 4660000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.215 | 2012-07-10 | ADD PROJECT TO STIP. NEW |  |  | MONROE | 3-1084 | CR 1354 | 0.04 | 1.954 | 1.994 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON NEW SALEM RD (CR 1354) OVER PETER CREEK 0.2 MILE E OF BETHLEHAM CHURCH RD (CR 1335)(SR 35.4) 086C00015N |  | D | BRZ | 2012 | 300000 | 300000 | [6 empty] | 0
[6 empty] | MONROE | 3-7020.01 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | CONSTRUCT NEW ROUTE FOR THE EAST TOMPKINSVILLE BYPASS . (98CCN)(02CCR) (2002BOPC)(DESIGN "STP" FUNDING SHALL BE SUPPLEMENTAL TO THE AUTHORIZED AMOUNT ALREADY EXPENDED ON THIS PROJECT).(08CCR)(10CCR) | 3 | R | STP | 2011 | 4200000 | 4200000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | MONROE | 3-7020.01 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | CONSTRUCT NEW ROUTE FOR THE EAST TOMPKINSVILLE BYPASS . (98CCN)(02CCR) (2002BOPC)(DESIGN "STP" FUNDING SHALL BE SUPPLEMENTAL TO THE AUTHORIZED AMOUNT ALREADY EXPENDED ON THIS PROJECT).(08CCR)(10CCR) | 4 | U | STP | 2011 | 3250000 | 3250000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | MONROE | 3-7020.01 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | CONSTRUCT NEW ROUTE FOR THE EAST TOMPKINSVILLE BYPASS . (98CCN)(02CCR) (2002BOPC)(DESIGN "STP" FUNDING SHALL BE SUPPLEMENTAL TO THE AUTHORIZED AMOUNT ALREADY EXPENDED ON THIS PROJECT).(08CCR)(10CCR) | 5 | C | STP | 2013 | 13500000 | 13500000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.050 | 2011-03-08 | ADD PROJECT TO STIP. BREAKOUT FROM 99-337.06. NEW | IM | 0645077 | MONTGOMERY | 7-6.03 |  |  |  |  | RELIABILITY | REST AREA REHAB(P) | I-64 WESTBOUND REST AREA IMPROVEMENTS |  | D | IM | 2011 | 44000 | 44000 |  | Y |  | OBLIGATED | 44000 |  | 44000 | 2011 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.050 | 2011-03-08 | ADD PROJECT TO STIP. BREAKOUT FROM 99-337.06. NEW |  |  | MONTGOMERY | 7-6.03 |  |  |  |  | RELIABILITY | REST AREA REHAB(P) | I-64 WESTBOUND REST AREA IMPROVEMENTS |  | C | IM | 2011 | 440000 | 440000 |  | Y |  |  |  |  | 0
[6 empty] | MONTGOMERY | 7-240 | KY 1991 | 1.8 | 0 | 1.768 | RELIABILITY | MAJOR WIDENING(O) | WIDEN KY-1991 FROM MAYSVILLE ROAD TO MIDLAND TRAIL INDUSTRIAL PARK, MONTGOMERY COUNTY. (SEE 7-8501.00 FOR "SPB" FUNDS) (2005HPP-KY129) | 5 | C | HPP | 2011 | 749899 | 749899 | ESTIMATED | N | 2010 |  |  |  | 0
|  |  |  | HPP | 0136005 | MONTGOMERY | 7-244 | KY 11 | 0.8 | 9.246 | 10.007 | RELIABILITY | MAJOR WIDENING(O) | WIDEN KY 11 FROM U.S. 460 TO THE MOUNT STERLING BYPASS, MONTGOMERY COUNTY. (2005HPP-KY136)(AGREEMENT WITH COUNTY IN PLACE). | 5 | C | HPP | 2011 | 581799 | 581799 | ESTIMATED | N | 2010 | OBLIGATED | 2311500 |  | 2311500 | 2012 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.193 | 2012-05-29 | ADD PROJECT TO STIP. NEW |  |  | MONTGOMERY | 7-250.10 | US 460 | 1.2 | 18.4 | 19.6 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT US 460 AT LUCKY STOP HILL. |  | D | STP | 2012 | 500000 | 500000 | [6 empty] | 0
|  |  |  | BRZ | 0703309 | MONTGOMERY | 7-1125 | CR 1008 | 0.1 | 4.234 | 4.334 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON CR-1008 (MP 4.284) OVER STEPSTONE CREEK; .2MI S-STEPSTONE @BATH CL; (STRUCTURALLY DEFICIENT, SR=32.9) 087C00006N | 2 | D | BRZ | 2012 | 145000 | 145000 | ESTIMATED | N |  | OBLIGATED | 305000 |  | 305000 | 2012 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.179 | 2012-04-10 | ADD PROJECT TO STIP. NEW | HSIP | 5325009 | MORGAN | 10-917 | KY 172 | 12.275 | 5.8 | 18.075 | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALL GUARDRAIL, LEVEL AND WEDGE, ESTABLISH SHOULDER AND RESURFACE WITH A SKID RESISTANT MATERIAL ON KY 172 AT TWO LOCATIONS: FROM 0.3 MILE EAST OF KY 650, EAST 0.75 MILE AND FROM 0.3 MILE EAST OF KY 1715 EAST 0.3 MILE. |  | C | SAF | 2012 | 196000 | 196000 |  |  |  | OBLIGATED | 196000 |  | 196000 | 2012 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.214 | 2012-07-05 | ADD PROJECT TO STIP. NEW |  |  | MORGAN | 10-918 | KY 172 | 0.25 | 6.211 | 6.461 | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALL GUARDRAIL ON KY 172 FROM 0.481 MILE EAST OF KY 650, EAST TO 0.731 MILE EAST OF KY 650. |  | C | SAF | 2012 | 37000 | 37000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.216 | 2012-07-25 | ADD PROJECT TO STIP. NEW |  |  | MORGAN | 10-919 | KY 519 | 0.29 | 1.28 | 1.57 | SAFETY | SAFETY-HAZARD ELIM(P) | MILL/INLAY WITH POLISH RESISTANT AGGREGATE AND RESET GUARDRAIL ON KY 519 FROM 1.28 MILE NORTH OF KY 7 (MP 1.280) NORTH 0.29 MILE TO (MP 1.570).(2012BOP) |  | C | SAF | 2012 | 105000 | 105000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.216 | 2012-07-25 | ADD PROJECT TO STIP. NEW |  |  | MORGAN | 10-920 | KY 7 | 0.19 | 3.65 | 3.84 | SAFETY | SAFETY-HAZARD ELIM(P) | MILL/INLAY WITH POLISH RESISTANT AGGREGATE AND RESET GUARDRAIL ON KY 7 FROM KY 1161 AT POMP (MP 3.650), NORTH 0.19 MILE TO (MP 3.840).(2012BOP) |  | C | SAF | 2012 | 50000 | 50000 | [6 empty] | 0
|  |  |  | HSIP | 4312047 | MUHLENBERG | 2-976 | US 431 | 0.3 | 23 | 23.3 | SAFETY | SAFETY-HAZARD ELIM(P) | US431 @ SOUTH CARROLLTON MP 23.0 TO 23.3, HORIZONTAL & VERTICAL REALIGNMENT, SHOULDER WIDENING, & INSTALL GUARDRAIL (B/C=1.9) (D-DISTRICT, C-CONTRACTOR) (2002BOP) | 3 | R | HES | 2011 | 500000 | 500000 | ESTIMATED | N | 2010 | OBLIGATED | 500000 |  | 500000 | 2011 | 1st QUARTER | N/A
|  |  |  | HSIP | 4312048 | MUHLENBERG | 2-976 | US 431 | 0.3 | 23 | 23.3 | SAFETY | SAFETY-HAZARD ELIM(P) | US431 @ SOUTH CARROLLTON MP 23.0 TO 23.3, HORIZONTAL & VERTICAL REALIGNMENT, SHOULDER WIDENING, & INSTALL GUARDRAIL (B/C=1.9) (D-DISTRICT, C-CONTRACTOR) (2002BOP) | 4 | U | HES | 2011 | 100000 | 100000 | ESTIMATED | N | 2010 | OBLIGATED | 100000 |  | 100000 | 2011 | 2nd QUARTER | N/A
[6 empty] | MUHLENBERG | 2-976 | US 431 | 0.3 | 23 | 23.3 | SAFETY | SAFETY-HAZARD ELIM(P) | US431 @ SOUTH CARROLLTON MP 23.0 TO 23.3, HORIZONTAL & VERTICAL REALIGNMENT, SHOULDER WIDENING, & INSTALL GUARDRAIL (B/C=1.9) (D-DISTRICT, C-CONTRACTOR) (2002BOP) | 5 | C | HES | 2011 | 790000 | 790000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.125 | 2011-09-13 | ADD PROJECT TO STIP. NEW | HSIP | 1501105 | NELSON/ WASHINGTON | 4-914 | US 150 |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | TRENCH A 3'X4" EARTH SHOULDER AND REPLACE WITH 4" ASPHALT BINDER AND MILL AND SAW RUMBLE STRIPS ON US 150 FROM 0.3 MILE EAST OF BG PARKWAY IN NELSON COUNTY TO 0.3 MILE EAST OF KY 152 IN WASHINGTON COUNTY. |  | C | SAF | 2011 | 746400 | 746400 |  |  |  | OBLIGATED | 714000 |  | 714000 | 2012 | 2nd QUARTER | N/A
|  |  |  | BRO | 1501101 | NELSON | 4-1068 | US 150 | 0.1 | 7.606 | 7.706 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON US-150 (MP 7.656) OVER BEECH FORK; ON WASHINGTON - NELSON CL; (STRUCTURALLY DEFICIENT, SR=45.8) 090B00028N | 2 | D | BRO | 2011 | 490000 | 490000 | ESTIMATED | N | 2010 | OBLIGATED | 490000 |  | 490000 | 2011 | 1st QUARTER | N/A
|  |  |  | BRO | 1501106 | NELSON | 4-1068 | US 150 | 0.1 | 7.606 | 7.706 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON US-150 (MP 7.656) OVER BEECH FORK; ON WASHINGTON - NELSON CL; (STRUCTURALLY DEFICIENT, SR=45.8) 090B00028N | 3 | R | BRO | 2012 | 180000 | 180000 | ESTIMATED | N |  | OBLIGATED | 150000 |  | 150000 | 2012 | 3rd QUARTER | N/A
|  |  |  | BRO | 1501108 | NELSON | 4-1068 | US 150 | 0.1 | 7.606 | 7.706 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON US-150 (MP 7.656) OVER BEECH FORK; ON WASHINGTON - NELSON CL; (STRUCTURALLY DEFICIENT, SR=45.8) 090B00028N | 4 | U | BRO | 2012 | 75000 | 75000 | ESTIMATED | N |  | OBLIGATED | 150000 |  | 150000 | 2012 | 3rd QUARTER | N/A
|  |  | ADDED PROJECT RIGHT-OF-WAY PHASE TO STIP PER APPROVED PR-1 ON 12/16/11 | BRO | 5112009 | NELSON | 4-1072 | KY 84 | 0.02 | 0.259 | 0.279 | SAFETY | BRIDGE INSPECTION(P) | INSTALL SCOUR COUNTERMEASURES ON KY 84 BRIDGE OVER A SLOUGH OF ROLLING FORK RIVER WEST OF HOWARDSTOWN. |  | R | BRO | 2011 | 25000 | 25000 |  |  |  | OBLIGATED | 25000 |  | 25000 | 2012 | 1st QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.106 | 2011-08-23 | ADD PROJECT TO STIP. NEW | BRO | 5112008 | NELSON | 4-1072 | KY 84 | 0.02 | 0.259 | 0.279 | SAFETY | BRIDGE INSPECTION(P) | INSTALL SCOUR COUNTERMEASURES ON KY 84 BRIDGE OVER A SLOUGH OF ROLLING FORK RIVER WEST OF HOWARDSTOWN. |  | C | BRO | 2011 | 250000 | 250000 |  |  |  | OBLIGATED | 488267 |  | 488267 | 2011 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.197 | 2012-05-30 | ADD PROJECT TO STIP. NEW |  |  | NELSON | 4-1075 | US 62 | 0.04 | 24.917 | 24.957 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON US-62 OVER EAST FRK OF SIMPSON CREEK 0.01 MILES S OF KY-55 (SR 49.5) 090B00023N.(12CCR) |  | D | BRO | 2012 | 100000 | 100000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.197 | 2012-05-30 | ADD PROJECT TO STIP. NEW |  |  | NELSON | 4-1078 | US 62 | 0.04 | 27.278 | 27.318 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON US 62 OVER HINKLE CREEK 0.012 MILE E OF KY 55(SR 34.6) 090B00096N (12CCR) |  | D | BRO | 2012 | 225000 | 225000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.197 | 2012-05-30 | ADD PROJECT TO STIP. NEW |  |  | NELSON/ WASHINGTON | 4-1079 | KY 458 | 0.09 |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON OLD TUNNEL MILL RD (KY 458) OVER CHAPLIN RIVER AT COUNTY LINE (SR 49.2) 090B00066 (12CCR) |  | D | BRO | 2012 | 200000 | 200000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.197 | 2012-05-30 | ADD PROJECT TO STIP. NEW |  |  | NELSON | 4-1083 | CR 1327 | 0.04 | 3.411 | 3.451 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON MOBLEY MILL RD (CR 1327) OVER FROMAN CREEK 0.72 MILE W OF LENORE RD (KY 2739)(SR 24.5) 090C00039N (12CCR) |  | D | BRX | 2012 | 75000 | 75000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.208 | 2012-06-20 | ADD PROJECT TO STIP. THIS PROJECT IS UTILIZING THE REMAINING FY 2005 NCPD FUNDS. NEW | NCPD | 3000937 | NELSON | 4-8200 | KY 247 |  |  |  | RELIABILITY | RELOCATION(O) | REALIGN KY-247 NEAR THE ABBEY OF GETHSEMANI: RECONSTRUCT ROADWAY TO FLATTEN A VERTICAL CURVE TO IMPROVE SIGHT DISTANCE ON KY-247 0.7 MILE NORTH OF KY-52. |  | C | NCPD | 2012 | 135000 | 135000 |  |  |  | OBLIGATED |  | 135000 | 135000 | 2012 | 3rd QUARTER | N/A
[6 empty] | NICHOLAS | 7-310.3 | US 68 | 3.8 | 0.4 | 4.827 | RELIABILITY | MAJOR WIDENING(O) | PARIS-MAYSVILLE ROAD; RECONSTRUCT FROM MILLERSBURG TO KY-32 AT CARLISLE (SECTION 3). (08CCR) | 3 | R | NHG | 2011 | 3490000 | 3490000 | ESTIMATED | Y | 2010 |  |  |  | 0
[6 empty] | NICHOLAS | 7-310.3 | US 68 | 3.8 | 0.4 | 4.827 | RELIABILITY | MAJOR WIDENING(O) | PARIS-MAYSVILLE ROAD; RECONSTRUCT FROM MILLERSBURG TO KY-32 AT CARLISLE (SECTION 3). (08CCR) | 4 | U | NHG | 2011 | 7580000 | 7580000 | ESTIMATED | Y | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.202 | 2012-06-11 | ADD PROJECT TO STIP. NEW |  |  | NICHOLAS | 9-205 | KY 36 | 0.183 | 3.1 | 3.283 | SAFETY | SAFETY(P) | RECONSTRUCT KY 36-KY 32 NEAR THE NICHOLAS COUNTY SCHOOLS PROPERTY. MP 3.10 TO MP 3.283. (12CCR) |  | D | STP | 2012 | 750000 | 750000 | [6 empty] | 0
|  |  |  | BRO | 5215010 | NICHOLAS | 9-1074 | KY 32 | 0.1 | 13.846 | 13.946 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-32 (MP 13.896) OVER TTI RR & SCRUBGRASS CREEK; 4.2 MILE NORTHEAST OFJCT KY 1455; (FUNCTIONALLY OBSOLETE, SR=49.2) 091B00008N | 2 | D | BRO | 2011 | 200000 | 200000 | ESTIMATED | N | 2010 | OBLIGATED | 380000 |  | 330000 | 2011 | 1st QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.012 | 2010-11-05 | CHANGE FUNDING AMOUNT. MOD |  |  | NICHOLAS | 9-1074 | KY 32 | 0.1 | 13.846 | 13.946 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-32 (MP 13.896) OVER TTI RR & SCRUBGRASS CREEK; 4.2 MILE NORTHEAST OFJCT KY 1455; (FUNCTIONALLY OBSOLETE, SR=49.2) 091B00008N | 2 | D | BRO | 2011 | 330000 | 330000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | NICHOLAS | 9-1074 | KY 32 | 0.1 | 13.846 | 13.946 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-32 (MP 13.896) OVER TTI RR & SCRUBGRASS CREEK; 4.2 MILE NORTHEAST OFJCT KY 1455; (FUNCTIONALLY OBSOLETE, SR=49.2) 091B00008N | 3 | R | BRO | 2012 | 250000 | 250000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | NICHOLAS | 9-1074 | KY 32 | 0.1 | 13.846 | 13.946 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-32 (MP 13.896) OVER TTI RR & SCRUBGRASS CREEK; 4.2 MILE NORTHEAST OFJCT KY 1455; (FUNCTIONALLY OBSOLETE, SR=49.2) 091B00008N | 4 | U | BRO | 2012 | 100000 | 100000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | NICHOLAS | 9-8503 | KY 1285 |  | 2.609 | 2.649 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-1285 OVER NORTH FORK SOMERSET CREEK (B04) 2.6 MILES NORTH JCT. KY-57. (SR=33.9) (08CCN): (091B00004N)(10CCR) | 2 | D | BRX | 2011 | 90000 | 90000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.012 | 2010-11-05 | CHANGE FUNDING AMOUNT. MOD | BRZ | 0903173 | NICHOLAS | 9-8503 | KY 1285 |  | 2.609 | 2.649 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-1285 OVER NORTH FORK SOMERSET CREEK (B04) 2.6 MILES NORTH JCT. KY-57. (SR=33.9) (08CCN): (091B00004N)(10CCR) | 2 | D | BRZ | 2011 | 240000 | 240000 | ESTIMATED | N | 2010 | OBLIGATED | 410000 |  | 410000 | 2011 | 1st QUARTER | N/A
[6 empty] | NICHOLAS | 9-8503 | KY 1285 |  | 2.609 | 2.649 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-1285 OVER NORTH FORK SOMERSET CREEK (B04) 2.6 MILES NORTH JCT. KY-57. (SR=33.9) (08CCN): (091B00004N)(10CCR) | 3 | R | BRX | 2011 | 100000 | 100000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | NICHOLAS | 9-8503 | KY 1285 |  | 2.609 | 2.649 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-1285 OVER NORTH FORK SOMERSET CREEK (B04) 2.6 MILES NORTH JCT. KY-57. (SR=33.9) (08CCN): (091B00004N)(10CCR) | 4 | U | BRX | 2011 | 100000 | 100000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | NICHOLAS | 9-8503 | KY 1285 |  | 2.609 | 2.649 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-1285 OVER NORTH FORK SOMERSET CREEK (B04) 2.6 MILES NORTH JCT. KY-57. (SR=33.9) (08CCN): (091B00004N)(10CCR) | 5 | C | BRX | 2012 | 300000 | 300000 | ESTIMATED | N |  |  |  |  | 0
|  |  |  | HSIP | 5075052 | OHIO | 2-987 | US 231 | 0.4 | 6.75 | 7.124 | SAFETY | SAFETY-HAZARD ELIM(P) | WIDEN US-231 TO 3 LANES AT THE WESTERN KENTUCKY PARKWAY INTERCHANGE AND NORTHWARD. | 3 | R | HES | 2011 | 80000 | 80000 | ESTIMATED | N | 2010 | OBLIGATED | 80000 |  | 80000 | 2011 | 2nd QUARTER | N/A
|  |  |  | HSIP | 5075053 | OHIO | 2-987 | US 231 | 0.4 | 6.75 | 7.124 | SAFETY | SAFETY-HAZARD ELIM(P) | WIDEN US-231 TO 3 LANES AT THE WESTERN KENTUCKY PARKWAY INTERCHANGE AND NORTHWARD. | 4 | U | HES | 2011 | 210000 | 210000 | ESTIMATED | N | 2010 | OBLIGATED | 210000 |  | 210000 | 2011 | 2nd QUARTER | N/A
[6 empty] | OHIO | 2-987 | US 231 | 0.4 | 6.75 | 7.124 | SAFETY | SAFETY-HAZARD ELIM(P) | WIDEN US-231 TO 3 LANES AT THE WESTERN KENTUCKY PARKWAY INTERCHANGE AND NORTHWARD. | 5 | C | HES | 2011 | 1300000 | 1300000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.088 | 2011-06-15 | INCREASE C PHASE FUNDING AMOUNT. MOD | HSIP | 5075054 | OHIO | 2-987 | US 231 | 0.4 | 6.75 | 7.124 | SAFETY | SAFETY-HAZARD ELIM(P) | WIDEN US-231 TO 3 LANES AT THE WESTERN KENTUCKY PARKWAY INTERCHANGE AND NORTHWARD. | 5 | C | HES | 2011 | 1800000 | 1800000 | ESTIMATED | N | 2010 | OBLIGATED | 1800000 |  | 1800000 | 2011 | 3rd QUARTER | N/A
|  |  |  | BRO | 5038093 | OHIO | 2-1071 | US 62 | 0.1 | 12.264 | 12.364 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON US-62 (MP 12.264) OVER MUDDY CK.; .4 MI W OF JCT KY 1543; (STRUCTURALLY DEFICIENT, SR=49.3) 092B00034N | 2 | D | BRO | 2011 | 200000 | 200000 | ESTIMATED | N | 2010 | OBLIGATED | 200000 |  | 200000 | 2011 | 2nd QUARTER | N/A
[6 empty] | OHIO | 2-1071 | US 62 | 0.1 | 12.264 | 12.364 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON US-62 (MP 12.264) OVER MUDDY CK.; .4 MI W OF JCT KY 1543; (STRUCTURALLY DEFICIENT, SR=49.3) 092B00034N | 3 | R | BRO | 2012 | 100000 | 100000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | OHIO | 2-1071 | US 62 | 0.1 | 12.264 | 12.364 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON US-62 (MP 12.264) OVER MUDDY CK.; .4 MI W OF JCT KY 1543; (STRUCTURALLY DEFICIENT, SR=49.3) 092B00034N | 4 | U | BRO | 2012 | 75000 | 75000 | ESTIMATED | N |  |  |  |  | 0
|  |  |  | BRZ | 0203302 | OHIO | 2-1077 | CR 1194 | 0.1 | 0.029 | 0.129 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON CR-1194 (MP 0.079) OVER THREELICK CREEK; .15 MI W JCT CR 5172; (STRUCTURALLY DEFICIENT, SR=2) 092C00128N | 2 | D | BRZ | 2012 | 120000 | 120000 | ESTIMATED | N |  | OBLIGATED | 120000 |  | 120000 | 2012 | 2nd QUARTER | N/A
|  |  |  | NH | 9001012 | OHIO | 2-8508 | WK 9001 |  | 76.3 | 77.2 | SAFETY | LIGHTING(P) | IMPROVE LIGHTING AT THE EXCHANGE FROM THE WESTERN KENTUCKY PARKWAY ONTO THE WILLIAM H. NATCHER PARKWAY. (08CCN) | 5 | C | NHG | 2011 | 500000 | 500000 | ESTIMATED | N | 2010 | OBLIGATED | 834409 |  | 834409 | 2011 | 4th QUARTER | N/A
[6 empty] | OLDHAM | 5-234 | KY 393 | 1.243 | 4.672 | 5.868 | RELIABILITY | MAJOR WIDENING(O) | KY-393 RECONSTRUCT FROM NORTHERN RAMP OF I-71 TO NORTH OF KY-146 (STATIONS 10+100 TO 12+100)(DESIGN UNDER 5-230.00) | 5 | C | STP | 2011 | 9310000 | 9310000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.034 | 2011-01-28 | KIPDA ID #327. KIPDA MOD #2-REVISED. ADD PROJECT. NEW |  |  | OLDHAM | 5-410 | [6 empty] | OLDHAM COUNTY BICYCLE AND PEDESTRIAN TRAIL: CONSTRUCT A NON-MOTORIZED CORRIDOR FROM LAGRANGE TO JEFFERSON COUNTY LINE. |  | D | SLO | 2011 | 178464 | 178464 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.148 | 2011-12-01 | TIP MOD #12. KIPDA ID #327. MOVE FISCAL YEAR. MOD |  |  | OLDHAM | 5-410 | [6 empty] | OLDHAM COUNTY BICYCLE AND PEDESTRIAN TRAIL: CONSTRUCT A NON-MOTORIZED CORRIDOR FROM LAGRANGE TO JEFFERSON COUNTY LINE. |  | D | SLO | 2012 | 178464 | 178464 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.034 | 2011-01-28 | KIPDA ID #327. KIPDA MOD #2-REVISED. ADD PROJECT. NEW |  |  | OLDHAM | 5-410 | [6 empty] | OLDHAM COUNTY BICYCLE AND PEDESTRIAN TRAIL: CONSTRUCT A NON-MOTORIZED CORRIDOR FROM LAGRANGE TO JEFFERSON COUNTY LINE. |  | R | SLO | 2012 | 332531 | 332531 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.148 | 2011-12-01 | TIP MOD #12. KIPDA ID #327. MOVE FISCAL YEAR. MOD |  |  | OLDHAM | 5-410 | [6 empty] | OLDHAM COUNTY BICYCLE AND PEDESTRIAN TRAIL: CONSTRUCT A NON-MOTORIZED CORRIDOR FROM LAGRANGE TO JEFFERSON COUNTY LINE. |  | R | SLO | 2013 | 332531 | 332531 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.034 | 2011-01-28 | KIPDA ID #327. KIPDA MOD #2-REVISED. ADD PROJECT. NEW |  |  | OLDHAM | 5-410 | [6 empty] | OLDHAM COUNTY BICYCLE AND PEDESTRIAN TRAIL: CONSTRUCT A NON-MOTORIZED CORRIDOR FROM LAGRANGE TO JEFFERSON COUNTY LINE. |  | C | SLO | 2013 | 1000000 | 1000000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.074 | 2011-05-05 | TIP MOD #5. KIPDA ID #327. INCREASE FUNDING AMOUNT. MOD |  |  | OLDHAM | 5-410 | [6 empty] | OLDHAM COUNTY BICYCLE AND PEDESTRIAN TRAIL: CONSTRUCT A NON-MOTORIZED CORRIDOR FROM LAGRANGE TO JEFFERSON COUNTY LINE. |  | C | SLO | 2013 | 2000000 | 2000000 |  | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.148 | 2011-12-01 | TIP MOD #12. KIPDA ID #327. MOVE FISCAL YEAR. MOD |  |  | OLDHAM | 5-410 | [6 empty] | OLDHAM COUNTY BICYCLE AND PEDESTRIAN TRAIL: CONSTRUCT A NON-MOTORIZED CORRIDOR FROM LAGRANGE TO JEFFERSON COUNTY LINE. |  | C | SLO | 2014 | 2000000 | 2000000 |  | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.074 | 2011-05-05 | TIP MOD #5. KIPDA ID 321. ADD DESIGN PHASE. NEW |  |  | OLDHAM | 5-434 | CR 1002 | 0.75 | 0 | 0.747 | SAFETY | SAFETY(P) | CONSTRUCT A 4 LANE UNINTERRUPTED RAIL UNDERPASS WEST OF LAGRANGE. | 3 | D | SLO | 2011 | 500000 | 400000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.148 | 2011-12-01 | TIP MOD #12. KIPDA ID 321. MOVE FISCAL YEAR. MOD |  |  | OLDHAM | 5-434 | CR 1002 | 0.75 | 0 | 0.747 | SAFETY | SAFETY(P) | CONSTRUCT A 4 LANE UNINTERRUPTED RAIL UNDERPASS WEST OF LAGRANGE. |  | D | SLO | 2012 | 500000 | 400000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | OLDHAM | 5-434 | CR 1002 | 0.75 | 0 | 0.747 | SAFETY | SAFETY(P) | CONSTRUCT AN UNINTERRUPTED RAIL UNDERPASS WEST OF LAGRANGE. (LOCAL MATCH)(ALL WORK BY OLDHAM COUNTY) (SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | 3 | R | SLO | 2011 | 3032000 | 3032000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.074 | 2011-05-05 | TIP MOD #5. KIPDA ID 321. MOVE ROW TO FY 2012 AND DECREASE AMOUNT. MOD |  |  | OLDHAM | 5-434 | CR 1002 | 0.75 | 0 | 0.747 | SAFETY | SAFETY(P) | CONSTRUCT A 4 LANE UNINTERRUPTED RAIL UNDERPASS WEST OF LAGRANGE. | 3 | R | SLO | 2012 | 2531875 | 2025500 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.148 | 2011-12-01 | TIP MOD #12. KIPDA ID 321. MOVE FISCAL YEAR. MOD |  |  | OLDHAM | 5-434 | CR 1002 | 0.75 | 0 | 0.747 | SAFETY | SAFETY(P) | CONSTRUCT A 4 LANE UNINTERRUPTED RAIL UNDERPASS WEST OF LAGRANGE. | 3 | R | SLO | 2013 | 2531875 | 2025500 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | OLDHAM | 5-434 | CR 1002 | 0.75 | 0 | 0.747 | SAFETY | SAFETY(P) | CONSTRUCT AN UNINTERRUPTED RAIL UNDERPASS WEST OF LAGRANGE. (LOCAL MATCH)(ALL WORK BY OLDHAM COUNTY) (SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | 4 | U | SLO | 2011 | 1240000 | 1240000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.074 | 2011-05-05 | TIP MOD #5. KIPDA ID 321. MOVE UTILITIES TO FY 2013. MOD |  |  | OLDHAM | 5-434 | CR 1002 | 0.75 | 0 | 0.747 | SAFETY | SAFETY(P) | CONSTRUCT A 4 LANE UNINTERRUPTED RAIL UNDERPASS WEST OF LAGRANGE. | 3 | U | SLO | 2013 | 1240000 | 1240000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.148 | 2011-12-01 | TIP MOD #12. KIPDA ID 321. MOVE FISCAL YEAR. MOD |  |  | OLDHAM | 5-434 | CR 1002 | 0.75 | 0 | 0.747 | SAFETY | SAFETY(P) | CONSTRUCT A 4 LANE UNINTERRUPTED RAIL UNDERPASS WEST OF LAGRANGE. | 3 | U | SLO | 2014 | 1240000 | 1240000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | OLDHAM | 5-434 | CR 1002 | 0.75 | 0 | 0.747 | SAFETY | SAFETY(P) | CONSTRUCT AN UNINTERRUPTED RAIL UNDERPASS WEST OF LAGRANGE. (LOCAL MATCH)(ALL WORK BY OLDHAM COUNTY) (SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | 5 | C | SLO | 2012 | 8662000 | 8662000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.148 | 2011-12-01 | TIP MOD #12. KIPDA ID 1271. ADD TO STIP PER TIP MOD. NEW |  |  | OLDHAM | 5-441 | US 42 | 0.9 | 0 | 0.942 | RELIABILITY | PE & ENVIRONMENTAL(O) | RECONSTRUCT US 42 AND WIDEN FROM 2 LANES TO 3 LANES (3RD LANE WILL BE A CENTER TURN LANE) FROM JEFFERSON/OLDHAM COUNTY LINE TO RIDGEMOOR DRIVE. PROJECT WILL INCLUDE THE CONSIDERATION OF IMPROVEMENTS TO THE HAYFIELD WAY INTERSECTION.(2004BOPC) |  | R | SLO | 2012 | 2205000 | 2205000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.148 | 2011-12-01 | TIP MOD #12. KIPDA ID 1271. ADD TO STIP PER TIP MOD. NEW |  |  | OLDHAM | 5-441 | US 42 | 0.9 | 0 | 0.942 | RELIABILITY | PE & ENVIRONMENTAL(O) | RECONSTRUCT US 42 AND WIDEN FROM 2 LANES TO 3 LANES (3RD LANE WILL BE A CENTER TURN LANE) FROM JEFFERSON/OLDHAM COUNTY LINE TO RIDGEMOOR DRIVE. PROJECT WILL INCLUDE THE CONSIDERATION OF IMPROVEMENTS TO THE HAYFIELD WAY INTERSECTION.(2004BOPC) |  | U | SLO | 2013 | 811200 | 811200 | [6 empty] | 0
|  |  |  | STPM | 5138059 | OLDHAM | 5-441.01 | US 42 | 0.9 | 0 | 0.942 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT US-42 FROM THE JEFFERSON/OLDHAM COUNTY LINE TO RIDGEMOOR DRIVE. (2004BOPC) (SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | 2 | D | SLO | 2011 | 180000 | 180000 | ESTIMATED | N | 2010 | OBLIGATED | 520000 |  | 520000 | 2011 | 1st QUARTER | N/A
[6 empty] | OLDHAM | 5-441.01 | US 42 | 0.9 | 0 | 0.942 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT US-42 FROM THE JEFFERSON/OLDHAM COUNTY LINE TO RIDGEMOOR DRIVE. (2004BOPC) (SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | 3 | R | SLO | 2011 | 2205000 | 2205000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | OLDHAM | 5-441.01 | US 42 | 0.9 | 0 | 0.942 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT US-42 FROM THE JEFFERSON/OLDHAM COUNTY LINE TO RIDGEMOOR DRIVE. (2004BOPC) (SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | 4 | U | SLO | 2011 | 811000 | 811000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | OLDHAM | 5-441.01 | US 42 | 0.9 | 0 | 0.942 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT US-42 FROM THE JEFFERSON/OLDHAM COUNTY LINE TO RIDGEMOOR DRIVE. (2004BOPC) (SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | 5 | C | SLO | 2012 | 3600000 | 3600000 | NON-SIXYEAR | N |  |  |  |  | 0
[6 empty] | OLDHAM | 5-444 | KY 53 |  | 6.488 | 7.137 | RELIABILITY | CONGESTION MITIGTN(O) | ACCESS MANAGEMENT AND INTERSECTION/SIGNAL IMPROVEMENTS TO PROVIDE CONGESTION RELIEF ON KY-53 FROM DOWNTOWN LAGRANGE TO I-71. (2004BOPC) | 5 | C | CM | 2011 | 1120000 | 1120000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | OLDHAM | 5-449 | KY 22 |  | 3.15 | 3.35 | RELIABILITY | RECONSTRUCTION(O) | INTERSECTION IMPROVEMENT AT KY 22 AND KY 329 IN CRESTWOOD. (ALL WORK BY KYTC)(2006BOPC)(FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | 3 | R | SLO | 2011 | 579000 | 579000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.148 | 2011-12-01 | KIPDA MOD #12 KIPDA ID 1508. MOVE R PHASE TO FY 2012. MOD |  |  | OLDHAM | 5-449 | KY 22 |  | 3.15 | 3.35 | RELIABILITY | RECONSTRUCTION(O) | INTERSECTION IMPROVEMENT AT KY 22 AND KY 329 IN CRESTWOOD. | 5 | R | SLO | 2012 | 1688000 | 1688000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | OLDHAM | 5-449 | KY 22 |  | 3.15 | 3.35 | RELIABILITY | RECONSTRUCTION(O) | INTERSECTION IMPROVEMENT AT KY 22 AND KY 329 IN CRESTWOOD. (ALL WORK BY KYTC)(2006BOPC)(FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | 4 | U | SLO | 2011 | 563000 | 563000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | OLDHAM | 5-449 | KY 22 |  | 3.15 | 3.35 | RELIABILITY | RECONSTRUCTION(O) | INTERSECTION IMPROVEMENT AT KY 22 AND KY 329 IN CRESTWOOD. (ALL WORK BY KYTC)(2006BOPC)(FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | 5 | C | SLO | 2012 | 1688000 | 1688000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.074 | 2011-05-05 | KIPDA MOD #5. KIPDA ID 1508. MOVE C PHASE TO FY 2014. MOD |  |  | OLDHAM | 5-449 | KY 22 |  | 3.15 | 3.35 | RELIABILITY | RECONSTRUCTION(O) | INTERSECTION IMPROVEMENT AT KY 22 AND KY 329 IN CRESTWOOD. | 5 | C | SLO | 2014 | 1688000 | 1688000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.148 | 2011-12-01 | KIPDA ID #1632. KIPDA MOD #12. ADD D PHASE. NEW | STP | 3001400 | OLDHAM | 5-467 | I-71 |  |  |  | SAFETY | SAFETY(P) | INTERURBAN GREENWAY I-71 OVERPASS: CONSTRUCTION OF A PEDESTRIAN/BICYCLE BRIDGE OVER INTERSTATE I-71 ALONG KY 146 |  | D | SLO | 2012 | 162000 | 162000 |  | Y |  | OBLIGATED | 242000 |  | 242000 | 2012 | 2nd QUARTER | OLDHAM COUNTY
ADMINISTRATIVE MODIFICATION | 2010.148 | 2011-12-01 | KIPDA ID #1632. KIPDA MOD #12. ADD R PHASE. NEW |  |  | OLDHAM | 5-467 | I-71 |  |  |  | SAFETY | SAFETY(P) | INTERURBAN GREENWAY I-71 OVERPASS: CONSTRUCTION OF A PEDESTRIAN/BICYCLE BRIDGE OVER INTERSTATE I-71 ALONG KY 146 |  | R | SLO | 2012 | 5000 | 5000 |  | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.034 | 2011-01-28 | KIPDA ID #1632. KIPDA MOD #2-REVISED. ADD PROJECT. NEW |  |  | OLDHAM | 5-467 | I-71 |  |  |  | SAFETY | SAFETY(P) | INTERURBAN GREENWAY I-71 OVERPASS: CONSTRUCTION OF A PEDESTRIAN/BICYCLE BRIDGE OVER INTERSTATE I-71 ALONG KY 146 |  | C | SLO | 2011 | 796853 | 796853 |  | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.148 | 2011-12-01 | KIPDA ID #1632. KIPDA MOD #12. CHANGE FY TO 2012. MOD |  |  | OLDHAM | 5-467 | I-71 |  |  |  | SAFETY | SAFETY(P) | INTERURBAN GREENWAY I-71 OVERPASS: CONSTRUCTION OF A PEDESTRIAN/BICYCLE BRIDGE OVER INTERSTATE I-71 ALONG KY 146 |  | C | SLO | 2012 | 796853 | 796853 |  | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.215 | 2012-07-10 | ADD PROJECT TO STIP. USING TIP LINE ITEM KIPDA ID #1270. PAGE 75 OF TIP FY 11-15. NEW |  |  | OLDHAM | 5-909 | KY 2858 | 0.142 | 0.24 | 0.382 | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALL GUARDRAIL ALONG BOTH SIDES OF KY 2858 FROM 0.24 MILE NORTH OF KY 1818 TO 0.185 MILE SOUTH OF MYERS AVENUE. |  | C | SAF | 2012 | 41000 | 41000 | [6 empty] | 0
[6 empty] | OLDHAM | 5-8510 | I 71 |  |  |  | RELIABILITY | PAVEMENT REHAB-INT(P) | SPOT IMPROVEMENTS AND PAVEMENT REHAB ON I-71. (08CCN) | 5 | C | IMG | 2011 | 6000000 | 6000000 | ESTIMATED | Y | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.034 | 2011-01-28 | KIPDA ID #1623. KIPDA MOD #2-REVISED. ADD PROJECT. NEW |  |  | OLDHAM |  | KY 1793 | [5 empty] | CONSTRUCT SIDEWALKS ON KY 1793 FROM RIDGEVIEW DRIVE TO SETTLERS POINT TRAIL, AND A SIDEWALK CONNECTION FROM TIMOTHY WAY TO PEGGY BAKER PARK. |  | D | SLO | 2011 | 13000 | 13000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.148 | 2011-12-01 | KIPDA ID #1623. KIPDA MOD #12. CHANGE FY TO 2012 AND ADDITIONAL 10,000 FOR DESIGN PHASE. MOD |  |  | OLDHAM |  | KY 1793 | [5 empty] | CONSTRUCT SIDEWALKS ON KY 1793 FROM RIDGEVIEW DRIVE TO SETTLERS POINT TRAIL, AND A SIDEWALK CONNECTION FROM TIMOTHY WAY TO PEGGY BAKER PARK. |  | D | SLO | 2012 | 23000 | 23000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.034 | 2011-01-28 | KIPDA ID #1623. KIPDA MOD #2-REVISED. ADD PROJECT. NEW |  |  | OLDHAM |  | KY 1793 | [5 empty] | CONSTRUCT SIDEWALKS ON KY 1793 FROM RIDGEVIEW DRIVE TO SETTLERS POINT TRAIL, AND A SIDEWALK CONNECTION FROM TIMOTHY WAY TO PEGGY BAKER PARK. |  | C | SLO | 2011 | 72690 | 72690 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.148 | 2011-12-01 | KIPDA ID #1623. KIPDA MOD #12. MOVE FY 2011 CONSTRUCTION TO FY 2012. MOD |  |  | OLDHAM |  | KY 1793 | [5 empty] | CONSTRUCT SIDEWALKS ON KY 1793 FROM RIDGEVIEW DRIVE TO SETTLERS POINT TRAIL, AND A SIDEWALK CONNECTION FROM TIMOTHY WAY TO PEGGY BAKER PARK. |  | C | SLO | 2012 | 72690 | 72690 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.212 | 2012-06-29 | KIPDA ID #1623. KIPDA MOD #18. MODIFY DESCRIPTION TO BETTER REFLECT PROJECT SCOPE AND CHANGE FY. MOD |  |  | OLDHAM |  | KY 1793 | [5 empty] | CONSTRUCT SIDEWALKS ON KY 1793 FROM RIDGEVIEW DRIVE TO SETTLERS POINT TRAIL. |  | C | SLO | 2013 | 72690 | 72690 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.034 | 2011-01-28 | KIPDA ID #1606. KIPDA MOD #2-REVISED. ADD PROJECT. NEW |  |  | OLDHAM | [7 empty] | OLD FLOYDSBURG ROAD: REPLACE NARROW ONE-LANE CULVERT CROSSING; CLEAR TREES AND VEGETATION OUT OF RIGHT-OF-WAY; ADD SHOULDER TO THE ROAD, AND ADD SIGNAGE FOR SAFETY |  | C | SLO | 2011 | 440000 | 440000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.148 | 2011-12-01 | KIPDA ID #1606. KIPDA MOD #12. MOVE FY 2011 CONSTRUCTION TO FY 2012. MOD |  |  | OLDHAM | [7 empty] | OLD FLOYDSBURG ROAD: REPLACE NARROW ONE-LANE CULVERT CROSSING; CLEAR TREES AND VEGETATION OUT OF RIGHT-OF-WAY; ADD SHOULDER TO THE ROAD, AND ADD SIGNAGE FOR SAFETY |  | C | SLO | 2012 | 440000 | 440000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.034 | 2011-01-28 | KIPDA ID #1427. KIPDA MOD #2-REVISED. ADD PROJECT. NEW |  |  | OLDHAM | [7 empty] | CONSTRUCT VARIOUS SIDEWALKS IN OLDHAM COUNTY |  | C | SLO | 2011 | 107654 | 86123 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.148 | 2011-12-01 | KIPDA ID #1427. KIPDA MOD #12. MOVE FY TO FY 2012. MOD |  |  | OLDHAM | [7 empty] | CONSTRUCT VARIOUS SIDEWALKS IN OLDHAM COUNTY |  | C | SLO | 2012 | 186123 | 186123 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.074 | 2011-05-05 | KIPDA MOD #5. KIPDA ID 1808. ADD TO STIP. NEW |  |  | OLDHAM |  |  | 0.8 |  |  |  |  | BUCKNER CONNECTOR: CONSTRUCT NEW CONNECTION FROM OLD LAGRANGE ROAD TO KY 393. |  | R | SLO | 2012 | 143880 | 115104 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.074 | 2011-05-05 | KIPDA MOD #5. KIPDA ID 1808. ADD TO STIP. NEW |  |  | OLDHAM |  |  | 0.8 |  |  |  |  | BUCKNER CONNECTOR: CONSTRUCT NEW CONNECTION FROM OLD LAGRANGE ROAD TO KY 393. |  | C | SLO | 2013 | 1151040 | 920832 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.212 | 2012-06-29 | KIPDA ID #1808. KIPDA TIP MOD #18. ADD PE PHASE. NEW |  |  | OLDHAM |  |  | 0.8 |  |  |  |  | BUCKNER CONNECTOR: CONSTRUCT NEW CONNECTION FROM OLD LAGRANGE ROAD TO KY 393. |  | P | SLO | 2012 | 25000 | 20000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.090 | 2011-06-21 | KIPDA ID #1801. KIPDA TIP MOD #7. MOVE FY 2013 CONSTRUCTION TO FY 2012. MOVED TO FY 2013 IN ERROR ON MOD #5. MOD |  |  | OLDHAM |  |  | 0.8 |  |  |  |  | BUCKNER CONNECTOR: CONSTRUCT NEW CONNECTION FROM OLD LAGRANGE ROAD TO KY 393. |  | C | SLO | 2012 | 1151040 | 920832 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.148 | 2011-12-01 | KIPDA ID #1808. KIPDA TIP MOD #12. ADD D PHASE TO STIP. NEW |  |  | OLDHAM |  |  | 0.8 |  |  |  |  | BUCKNER CONNECTOR: CONSTRUCT NEW CONNECTION FROM OLD LAGRANGE ROAD TO KY 393. |  | D | SLO | 2012 | 143880 | 115104 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.212 | 2012-06-29 | KIPDA ID #1808. KIPDA TIP MOD #18. CHANGE FY AND AMOUNT. MOD |  |  | OLDHAM |  |  | 0.8 |  |  |  |  | BUCKNER CONNECTOR: CONSTRUCT NEW CONNECTION FROM OLD LAGRANGE ROAD TO KY 393. |  | D | SLO | 2013 | 118880 | 95104 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.148 | 2011-12-01 | KIPDA ID #1808. KIPDA TIP MOD #12. ADD R PHASE TO STIP. NEW |  |  | OLDHAM |  |  | 0.8 |  |  |  |  | BUCKNER CONNECTOR: CONSTRUCT NEW CONNECTION FROM OLD LAGRANGE ROAD TO KY 393. |  | R | SLO | 2013 | 143880 | 115104 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.127 | 2011-09-29 | KIPDA ID #1808. KIPDA TIP MOD #10. MOVE FY 2012 CONSTRUCTION TO FY 2014. MOD |  |  | OLDHAM |  |  | 0.8 |  |  |  |  | BUCKNER CONNECTOR: CONSTRUCT NEW CONNECTION FROM OLD LAGRANGE ROAD TO KY 393. |  | C | SLO | 2014 | 1151040 | 920832 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.148 | 2011-12-01 | KIPDA ID #1808. KIPDA TIP MOD #12. MOVE C PHASE TO FY 2015. MOD |  |  | OLDHAM |  |  | 0.8 |  |  |  |  | BUCKNER CONNECTOR: CONSTRUCT NEW CONNECTION FROM OLD LAGRANGE ROAD TO KY 393. |  | C | SLO | 2015 | 1151040 | 920832 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.163 | 2012-02-13 | KIPDA ID #1808. KIPDA TIP AMENDMENT #3. MOVE C PHASE TO FY 2014. MOD |  |  | OLDHAM |  |  | 0.8 |  |  |  |  | BUCKNER CONNECTOR: CONSTRUCT NEW CONNECTION FROM OLD LAGRANGE ROAD TO KY 393. |  | C | SLO | 2014 | 1151040 | 920832 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.177 | 2012-03-26 | ADD PROJECT TO STIP. NEW |  |  | OLDHAM |  | KY 362 |  |  |  | SAFETY | SAFETY-RR PROTECTN(P) | ADD GATES TO EXISTING FLASHING LIGHTS AND BELL SYSTEM AT CSX RAILROAD CROSSING ON CENTRAL AVENUE IN PEWEE VALLEY. (DOT# 345533P) |  | U | SAF | 2012 | 247500 | 247500 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.177 | 2012-03-26 | ADD PROJECT TO STIP. NEW | RHPD | 0501100 | OLDHAM | 99-352.07 | KY 362 | 0.002 | 0.966 | 0.968 | SAFETY | SAFETY-RR PROTECTN(P) | ADD GATES TO EXISTING FLASHING LIGHTS AND BELL SYSTEM AT CSX RAILROAD CROSSING ON CENTRAL AVENUE IN PEWEE VALLEY. (DOT# 345533P) |  | C | SAF | 2012 | 15000 | 15000 |  |  |  | OBLIGATED | 237750 |  | 237750 | 2012 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.194 | 2012-05-30 | KIPDA ID 1877. TIP AMENDMENT #4. ADD PROJECT TO STIP. NEW |  |  | OLDHAM |  | KY 329 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | INTERSECTION REALIGNMENT/RECONSTRUCTION AT KY 329 AND KY 329 BYPASS. |  | D | SLO | 2013 | 99000 | 79200 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.194 | 2012-05-30 | KIPDA ID 1877. TIP AMENDMENT #4. ADD PROJECT TO STIP. NEW |  |  | OLDHAM |  | KY 329 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | INTERSECTION REALIGNMENT/RECONSTRUCTION AT KY 329 AND KY 329 BYPASS. |  | R | SLO | 2015 | 82500 | 66000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.194 | 2012-05-30 | KIPDA ID 1877. TIP AMENDMENT #4. ADD PROJECT TO STIP. NEW |  |  | OLDHAM |  | KY 329 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | INTERSECTION REALIGNMENT/RECONSTRUCTION AT KY 329 AND KY 329 BYPASS. |  | U | SLO | 2015 | 55000 | 44000 | [6 empty] | 0
[6 empty] | OWEN | 6-1066 | KY 355 | 0.1 | 13.511 | 13.547 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-355 OVER LITTLE TWIN CREEK 380 FEET SOUTHEAST OF KY-355/KY-325 INTERSECTION (B09). (SR=30.3): (094B00009N) | 3 | R | BRX | 2011 | 80000 | 80000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | OWEN | 6-1066 | KY 355 | 0.1 | 13.511 | 13.547 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-355 OVER LITTLE TWIN CREEK 380 FEET SOUTHEAST OF KY-355/KY-325 INTERSECTION (B09). (SR=30.3): (094B00009N) | 4 | U | BRX | 2011 | 50000 | 50000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | OWEN | 6-1066 | KY 355 | 0.1 | 13.511 | 13.547 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-355 OVER LITTLE TWIN CREEK 380 FEET SOUTHEAST OF KY-355/KY-325 INTERSECTION (B09). (SR=30.3): (094B00009N) | 5 | C | BRX | 2012 | 935000 | 935000 | ESTIMATED | N |  |  |  |  | 0
|  |  |  | BRO | 0302015 | OWSLEY | 10-1084 | KY 30 | 0.1 | 5.074 | 5.086 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-30 OVER LITTLE STURGEON CREEK (B13) 40 FEET EAST OF LITTLE STURGEON CREEK ROAD. (SR=8.7): (095B00013N) | 3 | R | BRO | 2011 | 50000 | 50000 | ESTIMATED | N |  | OBLIGATED | 406000 |  | 406000 | 2012 | 3rd QUARTER | N/A
[6 empty] | OWSLEY | 10-1084 | KY 30 | 0.1 | 5.074 | 5.086 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-30 OVER LITTLE STURGEON CREEK (B13) 40 FEET EAST OF LITTLE STURGEON CREEK ROAD. (SR=8.7): (095B00013N) | 4 | U | BRO | 2011 | 50000 | 50000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.182 | 2012-04-26 | INCREASE FUNDING AMOUNT. | BRO | 0302016 | OWSLEY | 10-1084 | KY 30 | 0.1 | 5.074 | 5.086 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-30 OVER LITTLE STURGEON CREEK (B13) 40 FEET EAST OF LITTLE STURGEON CREEK ROAD. (SR=8.7): (095B00013N) | 4 | U | BRO | 2012 | 420000 | 420000 | ESTIMATED | N |  | OBLIGATED | 420000 |  | 420000 | 2012 | 3rd QUARTER | N/A
[6 empty] | OWSLEY | 10-1084 | KY 30 | 0.1 | 5.074 | 5.086 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-30 OVER LITTLE STURGEON CREEK (B13) 40 FEET EAST OF LITTLE STURGEON CREEK ROAD. (SR=8.7): (095B00013N) | 5 | C | BRO | 2012 | 620000 | 620000 | ESTIMATED | N |  |  |  |  | 0
|  |  |  | BRZ | 1003199 | OWSLEY | 10-1093 | CR 1136 | 0.1 | 0.387 | 0.487 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON CR-1136 (MP 0.437) OVER S. FORK KY. RIVER; .4 MI E OF JCT KY 11; (STRUCTURALLY DEFICIENT, SR=15.8) 095C00007N | 2 | D | BRZ | 2012 | 150000 | 150000 | ESTIMATED | N |  | OBLIGATED | 325000 |  | 325000 | 2011 | 1st QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.214 | 2012-07-05 | ADD PROJECT TO STIP. NEW |  |  | OWSLEY | 10-1093 | CR 1136 | 0.1 | 0.387 | 0.487 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON CR-1136 (MP 0.437) OVER S. FORK KY. RIVER; .4 MI E OF JCT KY 11; (STRUCTURALLY DEFICIENT, SR=15.8) 095C00007N |  | R | BRZ | 2012 | 100000 | 100000 | [6 empty] | 0
|  |  |  | BRO | 5218004 | PENDLETON | 6-1048 | KY 22 | 0.1 | 11.402 | 11.461 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE & APPROACHES AT SOUTH FORK LICKING RIVER 1.0 MI E US-27 (B07). (SR=13.4): (096B00007N) | 5 | C | BRO | 2011 | 8320000 | 8320000 | ESTIMATED | N |  | OBLIGATED | 8320000 |  | 8320000 | 2011 | 4th QUARTER | N/A
|  |  |  | BRZ | 0603223 | PENDLETON | 6-1071 | KY 3185 | 0.1 | 1.485 | 1.585 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-3185 (MP 1.535) OVER LICK CREEK; 1.6 MI NE - JCT KY 17; (STRUCTURALLY DEFICIENT, SR=13.7) 096B00038N | 2 | D | BRX | 2012 | 130000 | 130000 | ESTIMATED | N |  | OBLIGATED | 130000 |  | 130000 | 2011 | 3rd QUARTER | N/A
|  |  |  | BRZ | 0603222 | PENDLETON | 6-1073 | KY 159 | 0.1 | 3.589 | 3.689 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-159 (MP 3.639) OVER KINCAID CREEK; .2 MI. SOUTH OF JCT.KY 609; (STRUCTURALLY DEFICIENT, SR=24.4) 096B00004N | 2 | D | BRX | 2012 | 240000 | 240000 | ESTIMATED | N |  | OBLIGATED | 240000 |  | 240000 | 2011 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.197 | 2012-05-30 | ADD PROJECT TO STIP. NEW |  |  | PENDLETON | 6-1081 | KY 330 | 0.04 | 8.638 | 8.678 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 330 OVER SHORT CREEK 0.35 MILE N OF J H GODMAN RD (CR 1238)(SR 47.3) 096B00012N |  | D | BRO | 2012 | 350000 | 350000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.191 | 2012-05-16 | ADD PROJECT TO STIP. NEW | NH | 0151072 | PERRY | 10-158 | KY 15 | 1.243 | 13.269 | 14.512 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE SAFETY, UPGRADE GEOMETRICS, AND ADDRESS CAPACITY ISSUES FOR KY 15 IN PERRY COUNTY FROM MORTON BOULEVARD TO KY 15 BYPASS |  | D | NH | 2012 | 1500000 | 1500000 |  |  |  | OBLIGATED | 900000 |  | 900000 | 2012 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.214 | 2012-07-05 | ADD PROJECT TO STIP. NEW |  |  | PERRY | 10-269 | KY 15 | 2.361 | 14.486 | 16.847 | RELIABILITY | MAJOR WIDENING(O) | HAZARD-MOUNTAIN PARKWAY; RECONSTRUCT FROM 0.7 MI NORTH OF KY-550 TO 0.8 MI NORTH OF KY-267 (CONST PHASE IN ITEM NO. 10-269.02)(RU-04DEOB)(12CCN) |  | D | NH | 2012 | 300000 | 300000 | [6 empty] | 0
|  |  |  | BRO | 5271036 | PERRY | 10-1082 | KY 80 | 0.1 | 7.091 | 7.177 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-80 AT THE CSX RAILROAD AND KENTUCKY RIVER (B29). (SR=6.5): (097B00029N)(10CCR) | 3 | R | BRO | 2012 | 570000 | 570000 | ESTIMATED | Y |  | OBLIGATED | 600000 |  | 600000 | 2012 | 3rd QUARTER | N/A
[6 empty] | PERRY | 10-1082 | KY 80 | 0.1 | 7.091 | 7.177 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-80 AT THE CSX RAILROAD AND KENTUCKY RIVER (B29). (SR=6.5): (097B00029N)(10CCR) | 4 | U | BRO | 2012 | 500000 | 500000 | ESTIMATED | Y |  |  |  |  | 0
[6 empty] | PERRY | 10-1082 | KY 80 | 0.1 | 7.091 | 7.177 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-80 AT THE CSX RAILROAD AND KENTUCKY RIVER (B29). (SR=6.5) | 5 | C | BRO | 2014 | 3200000 | 3200000 | ESTIMATED | Y |  |  |  |  | 0
|  |  |  | BRO | 5375032 | PERRY | 10-1087 | KY 476 | 0.1 | 18.32 | 18.42 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-476 (MP 18.37) OVER TROUBLESOME CREEK; .05 MILE SOUTH OF JCT KY 267; (STRUCTURALLY DEFICIENT, SR=32.2) 097B00008N | 2 | D | BRO | 2011 | 250000 | 250000 | ESTIMATED | N | 2010 | OBLIGATED | 375000 |  | 375000 | 2011 | 1st QUARTER | N/A
[6 empty] | PERRY | 10-1087 | KY 476 | 0.1 | 18.32 | 18.42 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-476 (MP 18.37) OVER TROUBLESOME CREEK; .05 MILE SOUTH OF JCT KY 267; (STRUCTURALLY DEFICIENT, SR=32.2) 097B00008N | 3 | R | BRO | 2012 | 150000 | 150000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | PERRY | 10-1087 | KY 476 | 0.1 | 18.32 | 18.42 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-476 (MP 18.37) OVER TROUBLESOME CREEK; .05 MILE SOUTH OF JCT KY 267; (STRUCTURALLY DEFICIENT, SR=32.2) 097B00008N | 4 | U | BRO | 2012 | 25000 | 25000 | ESTIMATED | N |  |  |  |  | 0
|  |  |  | BRO | 1003200 | PERRY | 10-1088 | KY 451 | 0.1 | 0.004 | 0.104 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-451 (MP 0.054) OVER CSX RAILROAD AND NORTH FORK KENTUCKY RIVER; .100 MILE NORTH OF JCT KY-15; (STRUCTURALLY DEFICIENT, SR=37.4) 097B00016N | 2 | D | BRO | 2011 | 300000 | 300000 | ESTIMATED | N | 2010 | OBLIGATED | 350000 |  | 350000 | 2011 | 1st QUARTER | N/A
[6 empty] | PERRY | 10-1088 | KY 451 | 0.1 | 0.004 | 0.104 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-451 (MP 0.054) OVER CSX RAILROAD AND NORTH FORK KENTUCKY RIVER; .100 MILE NORTH OF JCT KY-15; (STRUCTURALLY DEFICIENT, SR=37.4) 097B00016N | 3 | R | BRO | 2012 | 100000 | 100000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | PERRY | 10-1088 | KY 451 | 0.1 | 0.004 | 0.104 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-451 (MP 0.054) OVER CSX RAILROAD AND NORTH FORK KENTUCKY RIVER; .100 MILE NORTH OF JCT KY-15; (STRUCTURALLY DEFICIENT, SR=37.4) 097B00016N | 4 | U | BRO | 2012 | 125000 | 125000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.097 | 2011-07-11 | ADD PROJECT. AWARDED FY 2010 IBRD DISCRETIONARY FUNDING. NEW | IBRD | 1003203 | PERRY | 10-1095 | KY 1096 | 0.4 |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | KY 1096 OVER BIG CREEK BRIDGE PROJECT |  | D | KYD | 2011 | 300000 | 300000 |  |  |  | OBLIGATED | 300000 |  | 300000 | 2011 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.211 | 2012-06-28 | ADD PROJECT. NEW |  |  | PERRY | 10-1101 | KY 1166 | 0.04 | 2.137 | 2.177 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON RIGHT FORK MACES CREEK RD (KY 1166) OVER RIGHT FORK MACES CREEK AT INTERSECTION WITH HUNTER RIDGE LN (CR 1226Q3)(SR 36.3) 097B00101N |  | D | BRO | 2012 | 275000 | 275000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.211 | 2012-06-28 | ADD PROJECT. NEW |  |  | PERRY | 10-1102 | KY 1146 | 0.033 | 2.679 | 2.712 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON BULAN HINER RD (KY 1146) OVER TRACE FORK AT JCT WITH KENTUCKY HIGHWAY 476 (KY 476)(SR 25.5) 097B00103N |  | D | BRO | 2012 | 300000 | 300000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.211 | 2012-06-28 | ADD PROJECT. NEW |  |  | PERRY | 10-1103 | KY 2021 | 0.04 | 1.075 | 1.115 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON BIG WILLARD RD (KY 2021) OVER WILLARD CREEK AT INTERSECTION WITH BEECH NUT LN (CR 1213)(SR 44.6) 097B00027N |  | D | BRO | 2012 | 275000 | 275000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.211 | 2012-06-28 | ADD PROJECT. NEW |  |  | PERRY | 10-1104 | CR 1539 | 0.03 | 0 | 0.03 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON OLD BEECH FORK RD (CR 1539) OVER LEATHERWOOD CREEK AT JCT WITH KENTUCKY HIGHWAY 699 (KY 699)(SR 7.3) 097C00045N |  | D | BRZ | 2012 | 275000 | 275000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.211 | 2012-06-28 | ADD PROJECT. NEW |  |  | PERRY | 10-1107 | CR 1107 | 0.04 | 0.062 | 0.102 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON BLACK HAWK RD (CR 1107) OVER CARR FORK AT JCT WITH RAPTOR LN (CR 1179)(SR 4.3) 097C00006N |  | D | BRZ | 2012 | 275000 | 275000 | [6 empty] | 0
[6 empty] | PIKE | 12-66.01 | I 66 |  |  |  | RELIABILITY | NEW ROUTE(O) | I-66 PIKE COUNTY, KENTUCKY. (05KYD-KY088) | 5 | C | KYD | 2011 | 983928 | 983928 | ESTIMATED | Y | 2010 |  |  |  | 0
|  |  |  | APD | 0806038 | PIKE | 12-263.05 | US 460 | 0.4 |  |  | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | PIKEVILLE TO VA. STATE LINE; US-460/US-23 INTERCHANGE (D, R & U INCLUDED IN SECTION 1-ITEM NO. 263.10) | 5 | C | APD | 2012 | 27040000 | 21632000 | ESTIMATED | Y |  | OBLIGATED | 25400072 |  | 25400072 | 2011 | 1st QUARTER | N/A
[6 empty] | PIKE | 12-263.35 | US 460 | 1.3 |  |  | RELIABILITY | RELOCATION(O) | PIKEVILLE TO VA. STATE LINE; US-460/KY-80 FROM GREASY CREEK TO SNAKE BRANCH. (SECTION 3) GRADE & DRAIN ONLY (WILL BE LET WITH 12-263.08).(10CCR) | 5 | C | APD | 2011 | 27040000 | 21632000 | ESTIMATED | Y | 2010 |  |  |  | 0
|  |  |  | APD | 0806040 | PIKE | 12-263.49 | US 460 | 4.5 |  |  | RELIABILITY | SURFACE(O) | PIKEVILLE TO VA. STATE LINE; US-460/KY-80 FROM GREASY CREEK TO KY-195. (SURFACING FOR SECTIONS 3, 4A, 4B & 5) (2000BOP) | 5 | C | APD | 2011 | 21640000 | 17312000 | ESTIMATED | Y |  | OBLIGATED | 22696960 |  | 22696960 | 2012 | 1st QUARTRER | N/A
[6 empty] | PIKE | 12-263.61 | US 460 | 1.7 |  |  | RELIABILITY | RELOCATION(O) | PIKEVILLE TO VA. STATE LINE; US-460/KY-80 FROM KY-195 TO EAST OF POND CREEK - SECTION 6A (D, R & U INCLUDED IN SECTION 6-ITEM NO. 263.60) GRADE, DRAIN & INC. SRF. | 5 | C | APD | 2011 | 25000000 | 20000000 | ESTIMATED | Y |  |  |  |  | 0
|  |  |  | APD | 0806035 | PIKE | 12-263.62 | CR 1641 | 0.1 | 0.125 | 0.225 | RELIABILITY | BRIDGE REPLACEMENT(P) | CONSTRUCT A BRIDGE AND APPROACHES ON POND CREEK ROAD OVER RUSSELL FORK AND CSX RAILROAD @ US-460/KY-80 NEAR DRAFFIN. (2004BOPC) | 5 | C | APD | 2011 | 8220000 | 6576000 | ESTIMATED | Y | 2010 | OBLIGATED | 7357296.08 |  | 7357296.08 | 2011 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.116 | 2011-09-06 | ADD PROJECT. NEW | APD | 0806039 | PIKE | 12-263.65 | US 460 |  |  |  | RELIABILITY | PREFINANCD CONVRSN(O) | PIKEVILLE TO VA. STATE LINE; US-460/KY-80 FROM EAST OF POND CREEK TO DUNLEARY HOLLOW - SECTION 6B. |  | C | APD | 2011 | 62400000 | 62400000 |  |  |  | OBLIGATED | 69994316.21 |  | 69994316.21 | 2011 | 4th QUARTER | N/A
|  |  |  | APD | 0806027 | PIKE | 12-263.72 | US 460 | 0.6 |  |  | RELIABILITY | RELOCATION(O) | PIKEVILLE TO VA. STATE LINE; US-460/KY-80 FROM KY-80 AT BEAVER CREEK TO EAST OF BEAVER BOTTOM (SECTION 7A) GRADE, DRAIN & INC. SRF. (2000BOP) | 5 | C | APD | 2011 | 57200000 | 45760000 | ESTIMATED | Y | 2010 | OBLIGATED | 34327620 |  | 34327620 | 2011 | 1st QUARTER | N/A
[6 empty] | PIKE | 12-263.8 | US 460 | 2.7 |  |  | RELIABILITY | RELOCATION(O) | PIKEVILLE TO VA. STATE LINE; US-460/KY-80 FROM BEAVER CREEK NEAR FLAT FORK TO VIRGINIA STATE LINE (SECTION 8). | 5 | C | APD | 2011 | 24840000 | 19872000 | ESTIMATED | Y |  |  |  |  | 0
[6 empty] | PIKE | 12-263.8 | US 460 | 2.7 |  |  | RELIABILITY | PREFINANCD CONVRSN(O) | PIKEVILLE TO VA. STATE LINE; US-460/KY-80 FROM BEAVER CREEK NEAR FLAT FORK TO VIRGINIA STATE LINE (SECTION 8). | 5 | C | APD | 2012 | 25000000 | 20000000 | ESTIMATED | Y |  |  |  |  | 0
[6 empty] | PIKE | 12-263.8 | US 460 | 2.7 |  |  | RELIABILITY | PREFINANCD CONVRSN(O) | PIKEVILLE TO VA. STATE LINE; US-460/KY-80 FROM BEAVER CREEK NEAR FLAT FORK TO VIRGINIA STATE LINE (SECTION 8). | 5 | C | APD | 2013 | 24000000 | 19200000 | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.079 | 2011-05-12 | BREAKOUT FROM 12-263.80 AS SECTION 8A AND CHANGE FUNDING AMOUNT. MOD |  |  | PIKE | 12-263.8 | US 460 | 2.7 |  |  | RELIABILITY | PREFINANCD CONVRSN(O) | PIKEVILLE TO VA. STATE LINE: US-460/KY-80 FROM BEAVER CREEK NEAR FLAT FORK TO BEAVER CREEK STATION 885+00 NEAR KY 1373 (SECTION 8A). | 5 | C | APD | 2011 | 19872000 | 19872000 | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.079 | 2011-05-12 | BREAKOUT NEW PROJECT FROM 12-263.80 AS SECTION 8B. NEW | APD | 0806033 | PIKE | 12-263.82 | US 460 | 2.7 |  |  | RELIABILITY | PREFINANCD CONVRSN(O) | PIKEVILLE TO VA. STATE LINE: RELOCATE US 460 FROM EAST OF KY 1373 ON RIGHT FORK OF BEAVER CREEK NORTH OF ELKHORN CITY TO THE VIRGINIA STATE LINE (SECTION 8B). | 5 | C | APD | 2011 | 39200000 | 39200000 | ESTIMATED | Y |  | OBLIGATED | 38578899 |  | 38578899 | 2011 | 3rd QUARTER | N/A
[6 empty] | PIKE | 12-263.89 | US 460 | 4.5 |  |  | RELIABILITY | SURFACE(O) | PIKEVILLE TO VA. STATE LINE; US-460/KY-80 FROM KY-80 AT BEAVER CREEK TO VIRGINIA STATE LINE (SURFACING FOR SECTIONS 7A, 7B, 8 & 9V) (2000BOP) | 5 | C | APD | 2012 | 18250000 | 14600000 | ESTIMATED | Y |  |  |  |  | 0
[6 empty] | PIKE | 12-263.9 | US 460 | 0.5 |  |  | RELIABILITY | RELOCATION(O) | PIKEVILLE TO VA. STATE LINE; US460/KY80 IN VIRGINIA FROM VIRGINIA STATE LINE TO BREAKS INTERSTATE PARK (SECTION 9V). (KYTC SHARE) (GRADE & DRAIN ONLY) | 3 | R | APD | 2013 | 1580000 | 1264000 | ESTIMATED | [5 empty] | 0
[6 empty] | PIKE | 12-263.9 | US 460 | 0.5 |  |  | RELIABILITY | RELOCATION(O) | PIKEVILLE TO VA. STATE LINE; US460/KY80 IN VIRGINIA FROM VIRGINIA STATE LINE TO BREAKS INTERSTATE PARK (SECTION 9V). (KYTC SHARE) (GRADE & DRAIN ONLY) | 4 | U | APD | 2013 | 520000 | 416000 | ESTIMATED | [5 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.161 | 2012-01-31 | ADD PROJECT. NEW |  |  | PIKE | 12-928 | KY 319 | 1.05 | 3.245 | 4.295 | SAFETY | SAFETY-HAZARD ELIM(P) | REMOVE TREES ALONG KY-319 FROM 0.4 MI SOUTH OF MUD LICK BRANCH ROAD, NORTH 1.05 MILES |  | C | SAF | 2012 | 45000 | 45000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.202 | 2012-06-11 | ADD PROJECT. NEW | HSIP | 5362019 | PIKE | 12-932 | KY 1056 | 0.31 | 8.43 | 8.74 | SAFETY | SAFETY(P) | INSTALL GUARDRAIL ON KY 1056 FROM 200 FEET WEST OF BLACKBERRY CREEK BRIDGE TO FARLEY BOTTOM BRIDGE. |  | C | SAF | 2012 | 40000 | 40000 |  |  |  | OBLIGATED | 47300 |  | 47300 | 2012 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.202 | 2012-06-11 | ADD PROJECT. NEW | HSIP | 5364005 | PIKE | 12-933 | KY 1499 | 0.682 | 3.093 | 3.775 | SAFETY | SAFETY(P) | INSTALL GUARDRAIL ON KY 1499 FROM 1.2 MILE NORTH OF JCT FEDS CREEK RD (KY 366), EXTENDING NORTH 0.682 MILE. |  | C | SAF | 2012 | 75000 | 75000 |  |  |  | OBLIGATED | 95700 |  | 95700 | 2012 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.202 | 2012-06-11 | ADD PROJECT. NEW | HSIP | 9010074 | PIKE | 12-934 | KY 1441 | 0.465 | 9.202 | 9.667 | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALL GUARDRAIL ON KY 1441 FROM FROZEN CREEK ROAD TO 0.054 MI SOUTH OF GRASSY BRANCH ROAD. |  | C | SAF | 2012 | 71500 | 71500 |  |  |  | OBLIGATED | 71500 |  | 71500 | 2012 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.056 | 2011-03-14 | ADD PROJECT. BREAKOUT FROM 99-1073.01. NEW | BRO | 0806032 | PIKE | 12-1070 | KY 80 | 0.4 |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE KY 80 BRIDGE OVER CSX RAILROAD AND RUSSELL FORK (B137) 0.4 MILE SOUTH OF JCT. KY-197 |  | C | BRO | 2011 | 9192295 | 9192295 |  |  |  | OBLIGATED | 9200000 |  | 9200000 | 2011 | 4th QUARTER | N/A
[6 empty] | PIKE | 12-1076 | KY 199 | 0.1 | 8.633 | 8.643 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-199 OVER POND CREEK (B33)(TO BE LET WITH 12-1089.00). (SR=46.8): (098B00033N) | 5 | C | BRO | 2011 | 960000 | 960000 | ESTIMATED | N | 2010 |  |  |  | 0
|  |  |  | BRO | 5365011 | PIKE | 12-1089 | KY 199 | 0.1 | 8.199 | 8.207 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-199 OVER POND CREEK (B34) (TO BE LET WITH 12-1076.00). (SR=20.5): (098B00034N) | 5 | C | BRO | 2011 | 1300000 | 1300000 | ESTIMATED | N | 2010 | OBLIGATED | 2318053.24 |  | 2318053.24 | 2012 | 1st QUARTER | N/A
|  |  |  | BRZ | 1203315 | PIKE | 12-1090 | CR 1291 | 0.1 | 0.042 | 0.05 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON LONG BRANCH ROAD OVER ISLAND CREEK (C64) 0.1 MILE SOUTH JCT. KY-3416 NEAR PIGEON. (SR=3.0): (098C00064N) | 5 | C | BRZ | 2011 | 430000 | 430000 | ESTIMATED | N | 2010 | OBLIGATED | 516000 |  | 516000 | 2011 | 2nd QUARTER | N/A
|  |  |  | BRZ | 1203329 | PIKE | 12-1098 | CR 1584 | 0.1 | 0.056 | 0.064 | SAFETY | BRIDGE REPLACEMENT(P) | RATTLESNAKE BRANCH ROAD; REPLACE BRIDGE AND APPROACHES OVER JOHNS CREEK (C152) 0.05 MILE NE OF KY-632. (SR=7.4): (098C00152N) | 2 | D | BRZ | 2011 | 320000 | 320000 | ESTIMATED | N |  | OBLIGATED | 320000 |  | 320000 | 2011 | 2nd QUARTER | N/A
[6 empty] | PIKE | 12-1098 | CR 1584 | 0.1 | 0.056 | 0.064 | RELIABILITY | BRIDGE REPLACEMENT(P) | RATTLESNAKE BRANCH ROAD; REPLACE BRIDGE AND APPROACHES OVER JOHNS CREEK (C152) 0.05 MILE NE OF KY-632. (SR=7.4) | 3 | R | BRZ | 2013 | 100000 | 100000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | PIKE | 12-1098 | CR 1584 | 0.1 | 0.056 | 0.064 | RELIABILITY | BRIDGE REPLACEMENT(P) | RATTLESNAKE BRANCH ROAD; REPLACE BRIDGE AND APPROACHES OVER JOHNS CREEK (C152) 0.05 MILE NE OF KY-632. (SR=7.4) | 4 | U | BRZ | 2013 | 200000 | 200000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | PIKE | 12-1098 | CR 1584 | 0.1 | 0.056 | 0.064 | RELIABILITY | BRIDGE REPLACEMENT(P) | RATTLESNAKE BRANCH ROAD; REPLACE BRIDGE AND APPROACHES OVER JOHNS CREEK (C152) 0.05 MILE NE OF KY-632. (SR=7.4) | 5 | C | BRZ | 2014 | 625000 | 625000 | ESTIMATED | N |  |  |  |  | 0
|  |  |  | BRZ | 1203323 | PIKE | 12-1100 | CR 1270 |  | 0.005 | 0.045 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER SHELBY CREEK 121 FEET WEST OF KY 122. (C00093N)(2006BOPC): (098C00093N) | 3 | R | BRZ | 2011 | 75000 | 75000 | ESTIMATED |  | 2010 | OBLIGATED | 40200 |  | 40200 | 2011 | 2nd QUARTER | N/A
|  |  |  | BRZ | 1203326 | PIKE | 12-1100 |  |  | 0.005 | 0.045 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER SHELBY CREEK 121 FEET WEST OF KY 122. (C00093N)(2006BOPC): (098C00093N) | 4 | U | BRZ | 2011 | 125000 | 125000 | ESTIMATED |  | 2010 | OBLIGATED | 90000 |  | 90000 | 2011 | 2nd QUARTER | N/A
|  |  |  | BRZ | 1203340 | PIKE | 12-1100 | CR 1270 |  | 0.005 | 0.045 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER SHELBY CREEK 121 FEET WEST OF KY 122. (C00093N)(2006BOPC): (098C00093N) | 5 | C | BRZ | 2011 | 585000 | 585000 | ESTIMATED |  |  | OBLIGATED | 809397.28 |  | 809397.28 | 2011 | 4th QUARTER | N/A
[6 empty] | PIKE | 12-1101 | KY 1426 | 0.1 | 17.244 | 17.344 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-1426 (MP 17.294) OVER BENT BRANCH; 0.4 MILES EAST OF NORTHEAST JCT KY 194; (STRUCTURALLY DEFICIENT, SR=4) 098B00014N | 2 | D | BRX | 2012 | 140000 | 140000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.023 | 2010-12-03 | INCREASE THE FUNDING AMOUNT OF THE D PHASE. MOD | BRZ | 1203324 | PIKE | 12-1101 | KY 1426 | 0.1 | 17.244 | 17.344 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-1426 (MP 17.294) OVER BENT BRANCH; 0.4 MILES EAST OF NORTHEAST JCT KY 194; (STRUCTURALLY DEFICIENT, SR=4) 098B00014N | 2 | D | BRZ | 2011 | 260000 | 260000 | ESTIMATED | N |  | OBLIGATED | 260000 |  | 260000 | 2011 | 2nd QUARTER | N/A
[6 empty] | PIKE | 12-1102 | KY 1426 | 0.1 | 17.907 | 18.007 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-1426 (MP 17.957) OVER BENT BRANCH; 1.1 MILE EAST OF NORTHEAST JCT KY 194; (STRUCTURALLY DEFICIENT, SR=4) 098B00015N | 2 | D | BRX | 2012 | 140000 | 140000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.023 | 2010-12-03 | INCREASE THE FUNDING AMOUNT OF THE D PHASE. MOD | BRZ | 1203325 | PIKE | 12-1102 | KY 1426 | 0.1 | 17.907 | 18.007 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-1426 (MP 17.957) OVER BENT BRANCH; 1.1 MILE EAST OF NORTHEAST JCT KY 194; (STRUCTURALLY DEFICIENT, SR=4) 098B00015N | 2 | D | BRZ | 2011 | 260000 | 260000 | ESTIMATED | N |  | OBLIGATED | 260000 |  | 260000 | 2011 | 2nd QUARTER | N/A
[6 empty] | PIKE | 12-1103 | KY 80 | 0.1 | 2.122 | 2.222 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-80 (MP 2.172) OVER BEAVER CREEK; NORTH AT JCT KY-1373 AT CEDARVILLE; (STRUCTURALLY DEFICIENT, SR=12.5) 098B00052N | 2 | D | BRO | 2012 | 140000 | 140000 | ESTIMATED | N |  |  |  |  | 0
|  |  |  | BRO | 1203348 | PIKE | 12-1104 | KY 610 | 0.1 | 8.096 | 8.196 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-610 (MP 8.146) OVER LONG FORK; .1 MI S OF JCT KY-1469; (STRUCTURALLY DEFICIENT, SR=32) 098B00069N | 2 | D | BRO | 2012 | 180000 | 180000 | ESTIMATED | N |  | OBLIGATED | 340000 |  | 340000 | 2012 | 2nd QUARTER | N/A
|  |  |  | BRO | 1203347 | PIKE | 12-1105 | KY 1469 | 0.1 | 5.193 | 5.293 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-1469 (MP 5.243) OVER MARSHALL'S BRANCH; .72 MI E. JCT KY-3414; (STRUCTURALLY DEFICIENT, SR=7.5) 098B00242N | 2 | D | BRO | 2012 | 120000 | 120000 | ESTIMATED | N |  | OBLIGATED | 210000 |  | 210000 | 2012 | 2nd QUARTER | N/A
[6 empty] | PIKE | 12-1109 | CR 1584 | 0.1 | 0.01 | 0.11 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON CR-1584 (MP 0.06) OVER JOHNS CREEK; .05 MI NORTH JCT KY-632; (STRUCTURALLY DEFICIENT, SR=7.4) 098C00152N | 2 | D | BRZ | 2012 | 120000 | 120000 | ESTIMATED | N |  |  |  |  | 0
|  |  |  | HPP/ NH | 0121006 | POWELL | 10-138 | KY 9000 |  | 18.4 | 18.5 | RELIABILITY | NEW INTERCHANGE(O) | CONSTRUCT WESTBOUND ACCESS TO MOUNTAIN PARKWAY FROM EXIT 18 (KY 1057), POWELL COUNTY. (SEE 10-8500.00 FOR "NH" FUNDS)(2005HPP-KY121) | 5 | C | HPP | 2011 | 1002767 | 1002767 | ESTIMATED | N | 2010 | OBLIGATED | 3867940 |  | 3867940 | 2011 | 2nd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.103 | 2011-08-09 | ADD PROJECT. NEW | HSIP | 9010060 | POWELL WOLFE | 10-911 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | REPLACE GUARDRAIL END TREATMENTS: POWELL KY 11 (MP 3.598 TO 21.00), KY 15 (MP 0.261 TO 7.186), WOLFE KY 15 (MP 9.250 TO 18.701) |  | C | SAF | 2011 | 210000 | 210000 |  |  |  | OBLIGATED | 210000 |  | 210000 | 2011 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.164 | 2012-02-09 | ADD PROJECT. BREAKOUT FROM 99-911.01. NEW | HSIP | 0061044 | POWELL | 10-915 | KY 9000 | 0.743 | 35.28 | 36.023 | SAFETY | SAFETY | MILL AND INLAY WITH POLISH RESISTANT STONE AND INSTALL SIGNS ON A SEGMENT OF THE MOUNTAIN PARKWAY FROM 0.6MI WEST OF THE TUNNEL RIDGE ROAD UNDERPASS TO THE WOLFE COUNTY LINE |  | C | SAF | 2012 | 375000 | 375000 |  |  |  | OBLIGATED | 375000 |  | 375000 | 2012 | 2nd QUARTER | N/A
[6 empty] | POWELL | 10-1085 | KY 11 | 0.1 | 4.108 | 4.12 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-11 OVER MIDDLE FORK OF RED RIVER (B39) SE OF BERT T COMBS MOUNTAIN PARKWAY UNDERPASS. (SR=15.7): (099B00039N) | 3 | R | BRO | 2011 | 50000 | 50000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | POWELL | 10-1085 | KY 11 | 0.1 | 4.108 | 4.12 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-11 OVER MIDDLE FORK OF RED RIVER (B39) SE OF BERT T COMBS MOUNTAIN PARKWAY UNDERPASS. (SR=15.7): (099B00039N) | 4 | U | BRO | 2011 | 80000 | 80000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | POWELL | 10-1085 | KY 11 | 0.1 | 4.108 | 4.12 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-11 OVER MIDDLE FORK OF RED RIVER (B39) SE OF BERT T COMBS MOUNTAIN PARKWAY UNDERPASS. (SR=15.7): (099B00039N) | 5 | C | BRO | 2012 | 740000 | 740000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | POWELL | 10-8500 | KY 9000 |  | 18.4 | 18.5 | RELIABILITY | NEW INTERCHANGE(O) | CONSTRUCT WESTBOUND ACCESS TO MOUNTAIN PARKWAY FROM EXIT 18 (KY-1057). (2005HPP-KY121) (08CCN) | 3 | R | NHG | 2011 | 10000 | 10000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | POWELL | 10-8500 | KY 9000 |  | 18.4 | 18.5 | RELIABILITY | NEW INTERCHANGE(O) | CONSTRUCT WESTBOUND ACCESS TO MOUNTAIN PARKWAY FROM EXIT 18 (KY-1057). (2005HPP-KY121) (08CCN) | 4 | U | NHG | 2011 | 20000 | 20000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | POWELL | 10-8500 | KY 9000 |  | 18.4 | 18.5 | RELIABILITY | NEW INTERCHANGE(O) | CONSTRUCT WESTBOUND ACCESS TO MOUNTAIN PARKWAY FROM EXIT 18 (KY-1057). (2005HPP-KY121) (08CCN) | 5 | C | NHG | 2011 | 1629000 | 1629000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | PULASKI | 8-59.11 | I 66 | 25 |  |  | RELIABILITY | PE & ENVIRONMENTAL(O) | I-66 SOMERSET TO LONDON. (2006KYD)(10CCR) | 5 | C | KYD | 2011 | 3192694 | 3192694 | ESTIMATED | Y | 2010 |  |  |  | 0
[6 empty] | PULASKI | 8-59.21 | I 66 | 10 |  |  | RELIABILITY | NEW ROUTE(O) | I-66 NORTHERN BYPASS AROUND SOMERSET. (2006KYD) | 5 | C | KYD | 2011 | 2858313 | 2858313 | ESTIMATED | Y | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.211 | 2012-06-28 | ADD PROJECT TO STIP. NEW |  |  | PULASKI | 8-119 | KY 914 | 3.2 | 10.1 | 13.3 | RELIABILITY | MAJOR WIDENING(O) | SOMERSET SOUTHEAST BYPASS; MAJOR WIDENING TO 4 LANES FROM APPROXIMATELY 0.4 MI WEST OF KY 769 TO KY 80. (12CCR) |  | D | STP | 2012 | 500000 | 500000 | [6 empty] | 0
[6 empty] | PULASKI | 8-908 | US 27 | 0.158 | 16.862 | 17.02 | SAFETY | SAFETY(P) | CONSTRUCT TWO WAY LEFT TURN LANE IN PULASKI COUNTY ON US-27 FROM KY-80 BYPASS TO TURNER STREET (WORK WILL BE CONDUCTED WITH STATE FORCES). (2008BOPC) | 5 | C | HES | 2011 | 34000 | 34000 | ESTIMATED |  | 2010 |  |  |  | 0
|  |  |  | HSIP | 0802002 | PULASKI | 8-909 | KY 80 |  | 27.82 | 28.3 | SAFETY | SAFETY-HAZARD ELIM(P) | RECONSTRUCTION OF KY-80 AND US-461 INTERSECTION TO IMPROVE TRAFFIC FLOW FROM MP 27.82 TO MP 28.30. (2008BOPC). | 5 | C | HES | 2011 | 715000 | 715000 | ESTIMATED |  | 2010 | OBLIGATED | 715000 |  | 715000 | 2012 | 2nd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.099 | 2011-07-14 | ADD PROJECT TO STIP. BREAKOUT FROM 99-911.00. NEW | HSIP | 9010058 | PULASKI MCCREARY | 8-912 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | REPLACE GUARDRAIL END TREATMENTS ON VARIOUS ROUTES: PULASKI KY 90 (MP 0.421-2.408), PULASKI KY 80 (MP 18.8-39.6) MCCREARY US 27 (MP 10.7-22.2). |  | C | SAF | 2011 | 1418000 | 1418000 |  |  |  | OBLIGATED | 1418000 |  | 1418000 | 2011 | 4th QUARTER | N/A
[6 empty] | PULASKI | 8-1042 | KY 1677 | 0.1 | 5.007 | 5.017 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-1677 OVER SINKING VALLEY CREEK (B23). (SR=11.5): (100B00023N) | 3 | R | BRX | 2011 | 300000 | 300000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | PULASKI | 8-1042 | KY 1677 | 0.1 | 5.007 | 5.017 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-1677 OVER SINKING VALLEY CREEK (B23). (SR=11.5): (100B00023N) | 4 | U | BRX | 2011 | 180000 | 180000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | PULASKI | 8-1042 | KY 1677 | 0.1 | 5.007 | 5.017 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-1677 OVER SINKING VALLEY CREEK (B23). (SR=11.5): (100B00023N) | 5 | C | BRX | 2011 | 680000 | 680000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.211 | 2012-06-28 | ADD PROJECT TO STIP. NEW |  |  | PULASKI | 8-1054 | KY 196 | 0.04 | 5.568 | 5.608 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 196 OVER SPUTTER CREEK 0.757 MILE W OF KY 1664(SR 30.5) 100B00026N |  | D | BRO | 2012 | 300000 | 300000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.211 | 2012-06-28 | ADD PROJECT TO STIP. NEW |  |  | PULASKI | 8-1056 | KY 1674 | 0.4 | 2.421 | 2.461 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 1674 OVER BIG CLIFTY CREEK AT BETHLEHEM RIDGE RD (CR 1672)(SR 44.7) 100B00056N |  | D | BRO | 2012 | 350000 | 350000 | [6 empty] | 0
[6 empty] | ROBERTSON | 6-8507 | US 62 |  |  |  | RELIABILITY | DESIGN ENGINEERING(O) | SPOT IMPROVEMENTS ON US-62 EAST TO MASON COUNTY LINE AND US-62 WEST TO THE HARRISON COUNTY LINE. (08CCN) (10CCR) | 5 | C | STP | 2011 | 300000 | 300000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | ROCKCASTLE | 8-6.02 | I 75 | 4.5 | 64.5 | 69 | RELIABILITY | MAJOR WIDENING(O) | I-75 IN ROCKCASTLE COUNTY, KENTUCKY (MILEPOINT 64.5 TO MILEPOINT 69.0), 4.5 MILES. (04KYD-KY070) | 5 | C | KYD | 2011 | 1500000 | 1500000 | ESTIMATED | Y | 2010 |  |  |  | 0
[6 empty] | ROCKCASTLE | 8-6.03 | I 75 | 13.25 | 55.745 | 69 | RELIABILITY | MAJOR WIDENING(O) | I-75 IN ROCKCASTLE COUNTY, KENTUCKY. (05KYD) | 5 | C | KYD | 2011 | 855000 | 855000 | ESTIMATED | Y | 2010 |  |  |  | 0
[6 empty] | ROCKCASTLE | 8-1043 | KY 1786 | 0.1 | 0.142 | 0.148 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-1786 OVER ROUNDSTONE CREEK (B49). (SR=12.4): (102B00049N)(10CCR) | 3 | R | BRX | 2011 | 230000 | 230000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | ROCKCASTLE | 8-1043 | KY 1786 | 0.1 | 0.142 | 0.148 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-1786 OVER ROUNDSTONE CREEK (B49). (SR=12.4): (102B00049N)(10CCR) | 4 | U | BRX | 2011 | 170000 | 170000 | ESTIMATED | N | 2010 |  |  |  | 0
|  |  |  | BRZ | 0803165 | ROCKCASTLE | 8-1043 | KY 1786 | 0.1 | 0.142 | 0.148 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-1786 OVER ROUNDSTONE CREEK (B49). (SR=12.4): (102B00049N)(10CCR) | 5 | C | BRX | 2011 | 510000 | 510000 | ESTIMATED | N | 2010 | OBLIGATED | 167851.2 |  | 167851.2 | 2011 | 2nd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.103 | 2011-08-09 | ADD PROJECT. NEW |  |  | ROWAN | 9-187.10 | KY 801 | 0.4 | 7.147 | 7.547 | SAFETY | SAFETY | CONSTRUCT TURN LANES ON KY 801 AT SCOTT CREEK MARINA AND BOAT RAMP |  | R | FH | 2011 | 100000 | 100000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.103 | 2011-08-09 | ADD PROJECT. NEW | KYFH | 1251003 | ROWAN | 9-187.10 | KY 801 | 0.4 | 7.147 | 7.547 | SAFETY | SAFETY | CONSTRUCT TURN LANES ON KY 801 AT SCOTT CREEK MARINA AND BOAT RAMP |  | U | FH | 2011 | 320000 | 320000 |  |  |  | OBLIGATED | 330000 |  | 330000 | 2011 | 4th QUARTER | N/A
[6 empty] | ROWAN | 9-192.01 | KY 32 |  | 16.619 | 21.636 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT KY-32 FROM KY-504 NEAR ELLIOTTVILLE TO KY-7 NEAR NEWFOUNDLAND. (PRIORITY SECTION I)(06CCR) (08CCR) (10CCR) | 2 | D | STP | 2011 | 3800000 | 3800000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | ROWAN | 9-192.01 | KY 32 |  | 16.619 | 21.636 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT KY-32 FROM KY-504 NEAR ELLIOTTVILLE TO KY-7 NEAR NEWFOUNDLAND. (PRIORITY SECTION I)(06CCR) (08CCR) (10CCR) | 3 | R | STP | 2013 | 4800000 | 4800000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | ROWAN | 9-192.03 | KY 32 |  | 16.619 | 21.636 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT KY-32 FROM KY-504 NEAR ELLIOTTVILLE TO KY-7 NEAR NEWFOUNDLAND. (ADDITIONAL DESIGN AND R/W FUNDING) (10CCR) | 2 | D | STP | 2013 | 2600000 | 2600000 | ESTIMATED | [5 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.214 | 2012-07-05 | ADD PROJECT TO STIP. NEW |  |  | ROWAN | 9-913 | KY 1167 | 0.609 | 2.206 | 2.815 | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALL GUARDRAIL ALONG KY 1167 FROM 0.1 MILE SOUTH OF NICHOLAS BRANCH, NORTH TO 0.25 MILE NORTH OF THE WALLACE BRANCH CULVERT. |  | C | SAF | 2012 | 40000 | 40000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.214 | 2012-07-05 | ADD PROJECT TO STIP. NEW |  |  | ROWAN | 9-914 | US 60 | 0.765 | 15.43 | 16.195 | SAFETY | SAFETY-HAZARD ELIM(P) | INSTALL GUARDRAIL ALONG US 60 FROM MATTHEWS BRANCH, EAST TO 300 FEET WEST OF GLENWOOD HOLLOW. |  | C | SAF | 2012 | 93500 | 93500 | [6 empty] | 0
|  |  |  | BRO | 5211098 | ROWAN | 9-1061 | US 60 | 0.1 | 14.918 | 14.925 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON US-60 OVER HAYS BRANCH (B06). (SR=13.3): (103B00006N) | 3 | R | BRO | 2011 | 690000 | 690000 | ESTIMATED | N | 2010 | OBLIGATED | 900000 |  | 900000 | 2012 | 2nd QUARTER | N/A
[6 empty] | ROWAN | 9-1061 | US 60 | 0.1 | 14.918 | 14.925 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON US-60 OVER HAYS BRANCH (B06). (SR=13.3): (103B00006N) | 4 | U | BRO | 2011 | 150000 | 150000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.197 | 2012-05-30 | INCREASE FUNDING AMOUNT. MOD |  |  | ROWAN | 9-1061 | US 60 | 0.1 | 14.855 | 14.955 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON US-60 OVER HAYS BRANCH (B06). (SR=13.3): (103B00006N) | 4 | U | BRO | 2012 | 430000 | 430000 | ESTIMATED |  | 2010 |  |  |  | 0
[6 empty] | ROWAN | 9-1061 | US 60 | 0.1 | 14.918 | 14.925 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON US-60 OVER HAYS BRANCH (B06). (SR=13.3): (103B00006N) | 5 | C | BRO | 2011 | 440000 | 440000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | ROWAN | 9-1076 | KY 32 | 0.1 | 13.239 | 13.339 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-32 (MP 13.289) OVER SEAYS BRANCH; 3.5 MI W OF JCT KY 504; (STRUCTURALLY DEFICIENT, SR=40) 103B00013N | 2 | D | BRO | 2012 | 130000 | 130000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.060 | 2011-03-29 | INCREASE THE FUNDING AMOUNT FROM 130,000 TO 290,000 AND CHANGE FISCAL YEAR. MOD | BRO | 5253019 | ROWAN | 9-1076 | KY 32 | 0.1 | 13.239 | 13.339 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-32 (MP 13.289) OVER SEAYS BRANCH; 3.5 MI W OF JCT KY 504; (STRUCTURALLY DEFICIENT, SR=40) 103B00013N | 2 | D | BRO | 2011 | 290000 | 290000 | ESTIMATED | N |  | OBLIGATED | 290000 |  | 290000 | 2011 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.214 | 2012-07-05 | ADD PROJECT TO STIP. NEW |  |  | ROWAN | 9-1086 | CR 1070 | 0.04 | 0.01 | 0.05 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON HAMILTON RD (CR 1070) OVER TRIPLETT CREEK 0.02 MILE N OF US 60 (SR 26.1) 103C00056N |  | D | BRZ | 2012 | 350000 | 350000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.042 | 2011-02-14 | ADD PROJECT TO STIP. BREAKOUT FROM 99-337.06. NEW | IM | 0647049 | ROWAN | 9-2022 | I-64 | 0.628 | 147.412 | 148.04 | RELIABILITY | PAVEMENT REHAB-INT(P) | PAVEMENT REPAIRS TO INTERSTATE RAMPS FOR ROWAN COUNTY I-64 WEIGH STATIONS |  | D | IM | 2011 | 10000 | 10000 |  | Y |  | OBLIGATED | 10000 |  | 10000 | 2011 | 2nd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.042 | 2011-02-14 | ADD PROJECT TO STIP. BREAKOUT FROM 99-337.06. NEW | IM | 0647050 | ROWAN | 9-2022 | I-64 | 0.628 | 147.412 | 148.04 | RELIABILITY | PAVEMENT REHAB-INT(P) | PAVEMENT REPAIRS TO INTERSTATE RAMPS FOR ROWAN COUNTY I-64 WEIGH STATIONS |  | C | IM | 2011 | 970000 | 970000 |  | Y |  | OBLIGATED | 547000 |  | 547000 | 2011 | 3rd QUARTER | N/A
[6 empty] | SCOTT | 7-102.01 |  | 6.3 |  |  | RELIABILITY | BYPASS(O) | GEORGETOWN NORTHWEST BYPASS FROM U.S. 460 EAST TO I-75 NORTH, SCOTT COUNTY. (04CCR)(2005HPP-KY122)(SEE 7-102.10 & 7-102.50 FOR "STP" COMPONENT) | 5 | C | HPP | 2011 | 1335481 | 1335481 | REESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | SCOTT | 7-102.1 |  | 2.8 |  |  | RELIABILITY | BYPASS(O) | GEORGETOWN NORTHWEST BYPASS (PRIORITY SECTION); FROM US-460, EAST TO KY-32. (2004BOPC)(SEE 7-102.01 FOR "HPP" COMPONENT) (08CCR)(10CCR) | 5 | C | STP | 2012 | 13500000 | 13500000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | SCOTT | 7-102.5 |  | 4.7 |  |  | RELIABILITY | BYPASS(O) | GEORGETOWN NORTHWEST BYPASS; FROM KY-32, EAST TO I-75. (04CCR)(2004BOPC)(SEE 7-102.01 FOR "HPP" COMPONENT)(10CCR) | 3 | R | STP | 2013 | 4140000 | 4140000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | SCOTT | 7-102.5 |  | 4.7 |  |  | RELIABILITY | BYPASS(O) | GEORGETOWN NORTHWEST BYPASS; FROM KY-32, EAST TO I-75. (04CCR)(2004BOPC)(SEE 7-102.01 FOR "HPP" COMPONENT)(10CCR) | 4 | U | STP | 2013 | 3360000 | 3360000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | SCOTT | 7-102.5 |  | 4.7 |  |  | RELIABILITY | BYPASS(O) | GEORGETOWN NORTHWEST BYPASS; FROM KY-32, EAST TO I-75. (04CCR)(2004BOPC)(SEE 7-102.01 FOR "HPP" COMPONENT) | 5 | C | STP | 2013 | 21150000 | 21150000 | ESTIMATED | [5 empty] | 0
[6 empty] | SCOTT | 7-212 | US 460 | 1.6 | 7.055 | 8.583 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT US-460 FROM KY-227 AT GREAT CROSSING TO GEORGETOWN BYPASS. (04CCR)(10CCR) | 3 | R | STP | 2011 | 1000000 | 1000000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | SCOTT | 7-212 | US 460 | 1.6 | 7.055 | 8.583 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT US-460 FROM KY-227 AT GREAT CROSSING TO GEORGETOWN BYPASS. (04CCR)(10CCR) | 4 | U | STP | 2011 | 500000 | 500000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | SCOTT | 7-212 | US 460 | 1.6 | 7.055 | 8.583 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT US-460 FROM KY-227 AT GREAT CROSSING TO GEORGETOWN BYPASS. (04CCR)(10CCR) | 5 | C | STP | 2012 | 7000000 | 7000000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | SHELBY | 5-65.25 | I 64 | 4.8 | 27.361 | 27.786 | RELIABILITY | MAJOR WIDENING(O) | RECONSTRUCT I-64/KY 1848 INTERCHANGE IN SHELBY COUNTY TO IMPROVE ACCESS CONTROL. (SEE 5-65.21 FOR R PHASE INFORMATION) (2008BOPC) | 2 | D | NH | 2011 | 100000 | 100000 | ESTIMATED | Y | 2010 |  |  |  | 0
[6 empty] | SHELBY | 5-65.25 | I 64 | 4.8 | 27.361 | 27.786 | RELIABILITY | MAJOR WIDENING(O) | RECONSTRUCT I-64/KY 1848 INTERCHANGE IN SHELBY COUNTY TO IMPROVE ACCESS CONTROL. (SEE 5-65.21 FOR R PHASE INFORMATION) (2008BOPC) | 4 | U | NH | 2011 | 1220000 | 1220000 | ESTIMATED | Y |  |  |  |  | 0
[6 empty] | SHELBY | 5-65.25 | I 64 | 4.8 | 27.361 | 27.786 | RELIABILITY | MAJOR WIDENING(O) | RECONSTRUCT I-64/KY 1848 INTERCHANGE IN SHELBY COUNTY TO IMPROVE ACCESS CONTROL. (SEE 5-65.21 FOR R PHASE INFORMATION) (2008BOPC) | 5 | C | NH | 2012 | 2200000 | 2200000 | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.209 | 2012-06-21 | ADD PROJECT TO STIP. BREAKOUT FROM 99-337.07. NEW | IMNH | 0642179 | SHELBY | 5-65.31 | I 64 | 4.91 | 27.91 | 32.82 | RELIABILITY | MAJOR WIDENING(O) | WIDEN I-64 TO 6 LANES FROM JUST WEST OF THE EASTBOUND REST AREA TO 0.980 MILE EAST OF THE KY-55 INTERCHANGE AT WCL OF SHELBYVILLE |  | C | GARVEE/ IM/NH/STP | 2012 | 40000000 | 40000000 |  |  |  | OBLIGATED |  | 43500000 | 43500000 | 2012 | 3rd QUARTER | N/A
|  |  |  | STP | 5137034 | SHELBY | 5-348.01 | KY 1848 | 1 | 5.054 | 6.025 | RELIABILITY | MAJOR WIDENING(O) | 5-LANE KY-1848 FROM THE I-64 INTERCHANGE TO US-60 AT SIMPSONVILLE. (02KYD)(NCPD)(2004BOPC) (08CCR)(10CCR) | 3 | R | STP | 2011 | 2840000 | 2840000 | PENDING | N | 2010 | OBLIGATED | 731000 |  | 731000 | 2011 | 2nd QUARTER | N/A
|  |  |  | STP | 5137036 | SHELBY | 5-348.01 | KY 1848 | 1 | 5.054 | 6.025 | RELIABILITY | MAJOR WIDENING(O) | 5-LANE KY-1848 FROM THE I-64 INTERCHANGE TO US-60 AT SIMPSONVILLE. (02KYD)(NCPD)(2004BOPC) (08CCR)(10CCR) | 4 | U | STP | 2011 | 1560000 | 1560000 | PENDING | N | 2010 | OBLIGATED | 2505000 |  | 2505000 | 2012 | 2nd QUARTER | N/A
|  |  |  | HSIP | 5160014 | SHELBY | 5-997 | KY 395 | 0.6 | 8.352 | 9 | SAFETY | SAFETY-HAZARD ELIM(P) | KY-395 @ I-64, HORIZONTAL/VERTICAL REALIGNMENT & CONSTRUCT LEFT TURN LANE ON KY395 AT FLYING J, SHOULDER WIDENING (B/C=3.2) (D-CONSLT, C-CONTRACTOR) (2002BOP)(10CCR) | 5 | C | HES | 2011 | 920000 | 920000 | ESTIMATED | N | 2010 | OBLIGATED | 1272000 |  | 1272000 | 2011 | 2nd QUARTER | N/A
[6 empty] | SHELBY | 5-1041 | CR 1329 | 0.1 | 0.395 | 0.413 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER CLEAR CREEK (C47) 0.1MI N OF WASHINGTON STREET/US-60W. (SR=17.7) (10CCN) | 5 | C | BRX | 2011 | 940000 | 940000 | ESTIMATED | N | 2010 |  |  |  | 0
|  |  |  | BRZ | 0503220 | SHELBY | 5-1053 | KY 362 | 0.1 | 6.23 | 6.234 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES OVER JUNKINS RUN 0.765 MILE EAST OF WEBB ROAD (B27) (SR=21.9). (106B00027N) | 2 | D | BRX | 2011 | 150000 | 150000 | ESTIMATED | N | 2010 | OBLIGATED | 225000 |  | 225000 | 2011 | 1st QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.012 | 2010-11-05 | CHANGE FUNDING AMOUNT. MOD |  |  | SHELBY | 5-1053 | KY 362 | 0.1 | 6.23 | 6.234 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES OVER JUNKINS RUN 0.765 MILE EAST OF WEBB ROAD (B27) (SR=21.9). (106B00027N) | 2 | D | BRZ | 2011 | 225000 | 225000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | SHELBY | 5-1053 | KY 362 | 0.1 | 6.23 | 6.234 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES OVER JUNKINS RUN 0.765 MILE EAST OF WEBB ROAD (B27) (SR=21.9). (106B00027N) | 3 | R | BRX | 2012 | 200000 | 200000 | NON-SIXYEAR | N |  |  |  |  | 0
[6 empty] | SHELBY | 5-1053 | KY 362 | 0.1 | 6.23 | 6.234 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES OVER JUNKINS RUN 0.765 MILE EAST OF WEBB ROAD (B27) (SR=21.9). (106B00027N) | 4 | U | BRX | 2012 | 100000 | 100000 | NON-SIXYEAR | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.066 | 2011-04-18 | ADD C PHASE TO STIP. BREAKOUT OF 99-1074.03. NEW | BRZ | 0503221 | SHELBY | 5-1053 | KY 362 | 0.1 | 6.23 | 6.234 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES OVER JUNKINS RUN 0.765 MILE EAST OF WEBB ROAD (B27) (SR=21.9). (106B00027N) | 2 | C | BRZ | 2011 | 430000 | 430000 | ESTIMATED | N | 2010 | OBLIGATED | 430000 |  | 430000 | 2011 | 3rd QUARTER | N/A
[6 empty] | SHELBY | 5-1060 | KY 53 | 0.1 | 11.316 | 11.416 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-53 (MP 11.366) OVER FOX RUN CREEK; 3.0 MI NORTH OF JCT US-60W; (STRUCTURALLY DEFICIENT, SR=38.9) 106B00031N | 2 | D | BRO | 2012 | 110000 | 110000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.190 | 2012-05-15 | INCREASE D PHASE FUNDING. MOD |  |  | SHELBY | 5-1060 | KY 53 | 0.1 | 11.316 | 11.416 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-53 (MP 11.366) OVER FOX RUN CREEK; 3.0 MI NORTH OF JCT US-60W; (STRUCTURALLY DEFICIENT, SR=38.9) 106B00031N | 2 | D | BRO | 2012 | 237500 | 237500 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.215 | 2012-07-10 | ADD PROJECT TO STIP. NEW |  |  | SHELBY | 5-1063 | KY 55 | 0.04 | 3.839 | 3.879 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-55 OVER BULL SKIN CREEK 0.18 MILE N OF HERITAGE LN (PR-1212)(SR 35.9) 106B00020N. |  | D | BRO | 2012 | 702500 | 702500 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.215 | 2012-07-10 | ADD PROJECT TO STIP. NEW |  |  | SHELBY | 5-1069 | CR 1036 | 0.04 | 0.462 | 0.502 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON SCRABBLE RD (CR 1036) OVER BACKBONE CREEK 0.47 MILE E OF CEDARMORE RD (KY 1922)(SR 44.2) 106C00055N |  | D | BRZ | 2012 | 474000 | 474000 | [6 empty] | 0
[6 empty] | SHELBY | 5-2035.4 | I 64 | 4.37 | 43.33 | 46.303 | RELIABILITY | PAVEMENT REHAB-INT(P) | PAVEMENT REHAB AND BRIDGE WIDENING ON I-64 FROM MP 43.33 TO MP 47.70. (2004BOPC)(DESIGN FUNDING COVERS 5-2035.70 SECTION ALSO) | 3 | R | IM | 2011 | 110000 | 110000 | ESTIMATED | Y |  |  |  |  | 0
[6 empty] | SHELBY | 5-2035.4 | I 64 | 4.37 | 43.33 | 46.303 | RELIABILITY | PAVEMENT REHAB-INT(P) | PAVEMENT REHAB AND BRIDGE WIDENING ON I-64 FROM MP 43.33 TO MP 47.70. (2004BOPC)(DESIGN FUNDING COVERS 5-2035.70 SECTION ALSO) | 4 | U | IM | 2011 | 110000 | 110000 | ESTIMATED | Y |  |  |  |  | 0
[6 empty] | SHELBY | 5-2042 | I 64 | 6.75 | 25.094 | 31.842 | RELIABILITY | PAVEMENT REHAB-INT(P) | MILL 1" INTERMEDIATE OVERLAY ON I-64 FROM MP 25.094 TO MP 31.842. (10CCR) | 5 | C | IM | 2011 | 3900000 | 3900000 | ESTIMATED | Y |  |  |  |  | 0
[6 empty] | SHELBY | 5-8511 | KY 53 | 1.9 | 6.064 | 8.006 | RELIABILITY | DESIGN ENGINEERING(O) | WIDEN KY-53 TO FOUR LANES FROM I-64 TO US-60. (08CCN)(10CCN) | 3 | R | STP | 2012 | 2000000 | 2000000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | SHELBY | 5-8511 | KY 53 | 1.9 | 6.064 | 8.006 | RELIABILITY | DESIGN ENGINEERING(O) | WIDEN KY-53 TO FOUR LANES FROM I-64 TO US-60. (08CCN)(10CCN) | 4 | U | STP | 2012 | 2000000 | 2000000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | SHELBY | 5-8511 | KY 53 | 1.9 | 6.064 | 8.006 | RELIABILITY | DESIGN ENGINEERING(O) | WIDEN KY-53 TO FOUR LANES FROM I-64 TO US-60. (08CCN)(10CCN) | 5 | C | STP | 2013 | 9000000 | 9000000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | SIMPSON | 3-8.1 | US 31W | 1.981 | 0 | 1.981 | RELIABILITY | MAJOR WIDENING(O) | US-31W SECTION 1: FROM TENNESSEE STATE LINE TO SOUTH OF I-65 INTERCHANGE. (04CCR) (08CCR)(10CCR) | 3 | R | STP | 2011 | 1550000 | 1550000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.046 | 2011-02-24 | INCREASE THE FUNDING AMOUNT FOR THE RIGHT-OF-WAY PHASE. MOD | STPR | 5386001 | SIMPSON | 3-8.1 | US 31W | 1.981 | 0 | 1.981 | RELIABILITY | MAJOR WIDENING(O) | WIDEN US 31W SECTION 1: FROM TENNESSEE STATE LINE TO SOUTH OF I-65 INTERCHANGE | 3 | R | STP | 2011 | 1600000 | 1600000 | ESTIMATED | N | 2010 | OBLIGATED | 1600000 |  | 1600000 | 2011 | 3rd QUARTER | N/A
[6 empty] | SIMPSON | 3-8.1 | US 31W | 1.981 | 0 | 1.981 | RELIABILITY | MAJOR WIDENING(O) | US-31W SECTION 1: FROM TENNESSEE STATE LINE TO SOUTH OF I-65 INTERCHANGE. (04CCR) (08CCR)(10CCR) | 4 | U | STP | 2011 | 1860000 | 1860000 | ESTIMATED | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.046 | 2011-02-24 | INCREASE THE FUNDING AMOUNT FOR THE U PHASE. MOD | STPR | 5386002 | SIMPSON | 3-8.1 | US 31W | 1.981 | 0 | 1.981 | RELIABILITY | MAJOR WIDENING(O) | WIDEN US 31W SECTION 1: FROM TENNESSEE STATE LINE TO SOUTH OF I-65 INTERCHANGE | 3 | U | STP | 2011 | 2290000 | 2290000 | ESTIMATED | N | 2010 | OBLIGATED | 2290000 |  | 2290000 | 2011 | 3rd QUARTER | N/A
[6 empty] | SIMPSON | 3-8.1 | US 31W | 1.981 | 0 | 1.981 | RELIABILITY | MAJOR WIDENING(O) | US-31W SECTION 1: FROM TENNESSEE STATE LINE TO SOUTH OF I-65 INTERCHANGE. (04CCR) (08CCR)(10CCR) | 5 | C | STP | 2012 | 8100000 | 8100000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | SIMPSON | 3-15 | I 65 | 0.1 | 0 | 0.7 | RELIABILITY | WEIGH STA REHAB(P) | ADD RESTROOM FACILITY TO I-65 WEIGH STATION IN SIMPSON COUNTY (DESIGN AUTHORIZED UNDER ITEM NO. 99-44.00) | 5 | C | IM | 2014 | 500000 | 500000 | ESTIMATED | [5 empty] | 0
|  |  |  | STP | 7005003 | SIMPSON | 3-106 | KY 1008 | 2.8 |  |  | RELIABILITY | PHASE I DESIGN(O) | FRANKLIN NORTHWEST BYPASS; EXTEND KY-1008 FROM US-31W TO KY-100 WEST. (2002BOPP)(10CCR) | 2 | D | STP | 2011 | 400000 | 400000 | ESTIMATED | N | 2010 | OBLIGATED | 500000 |  | 500000 | 2011 | 1st QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.072 | 2011-04-28 | ADD PROJECT TO STIP. BREAKOUT FROM 99-911.00. NEW | STP | 1001021 | SIMPSON | 3-907 | KY 100 | 0.318 | 13.232 | 13.55 | SAFETY | SAFETY(P) | RECONSTRUCTION OF KY 100 FROM PAGE DRIVE TO 1000 FEET EAST OF RAINES DRIVE (MP 13.232 TO MP 13.55) TO REMOVE CREST VERTICAL CURVE, PROVIDE WEST BOUND LEFT TURN LANE FOR PAGE DRIVE, AND TO PROVIDE E-BOUND RIGHT TURN AND W-BOUND LEFT TURN LANE AT RAINES DR. |  | D | STP | 2011 | 100000 | 100000 |  |  |  | OBLIGATED | 119683.63 |  | 119683.63 | 2011 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.100 | 2011-07-14 | ADD PROJECT TO STIP. BREAKOUT FROM 99-911.00. NEW | STP | 5071011 | SIMPSON | 3-907 | KY 100 | 0.318 | 13.232 | 13.55 | SAFETY | SAFETY(P) | RECONSTRUCTION OF KY 100 FROM PAGE DRIVE TO 1000 FEET EAST OF RAINES DRIVE (MP 13.232 TO MP 13.55) TO REMOVE CREST VERTICAL CURVE, PROVIDE WEST BOUND LEFT TURN LANE FOR PAGE DRIVE, AND TO PROVIDE E-BOUND RIGHT TURN AND W-BOUND LEFT TURN LANE AT RAINES DR. |  | R | STP | 2011 | 350000 | 350000 |  |  |  | OBLIGATED | 350000 |  | 350000 | 2011 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.100 | 2011-07-14 | ADD PROJECT TO STIP. BREAKOUT FROM 99-911.00. NEW | STP | 5071012 | SIMPSON | 3-907 | KY 100 | 0.318 | 13.232 | 13.55 | SAFETY | SAFETY(P) | RECONSTRUCTION OF KY 100 FROM PAGE DRIVE TO 1000 FEET EAST OF RAINES DRIVE (MP 13.232 TO MP 13.55) TO REMOVE CREST VERTICAL CURVE, PROVIDE WEST BOUND LEFT TURN LANE FOR PAGE DRIVE, AND TO PROVIDE E-BOUND RIGHT TURN AND W-BOUND LEFT TURN LANE AT RAINES DR. |  | U | STP | 2011 | 1100000 | 1100000 |  |  |  | OBLIGATED | 1040000 |  | 1040000 | 2011 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.100 | 2011-07-14 | ADD PROJECT TO STIP. BREAKOUT FROM 99-911.00. NEW | STP | 5071013 | SIMPSON | 3-907 | KY 100 | 0.318 | 13.232 | 13.55 | SAFETY | SAFETY(P) | RECONSTRUCTION OF KY 100 FROM PAGE DRIVE TO 1000 FEET EAST OF RAINES DRIVE (MP 13.232 TO MP 13.55) TO REMOVE CREST VERTICAL CURVE, PROVIDE WEST BOUND LEFT TURN LANE FOR PAGE DRIVE, AND TO PROVIDE E-BOUND RIGHT TURN AND W-BOUND LEFT TURN LANE AT RAINES DR. |  | C | STP | 2011 | 1800000 | 1800000 |  |  |  | OBLIGATED | 1795735.59 |  | 1795735.59 | 2011 | 4th QUARTER | N/A
[6 empty] | SIMPSON | 3-8306 | KY 100 | 3.4 | 13.534 | 16.34 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCTION AND WIDENING KY-100 FROM I-65 TO KY-622. (06CCN)(10CCR) | 3 | R | STP | 2011 | 2210000 | 2210000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | SIMPSON | 3-8306 | KY 100 | 3.4 | 13.534 | 16.34 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCTION AND WIDENING KY-100 FROM I-65 TO KY-622. (06CCN)(10CCR) | 4 | U | STP | 2011 | 1560000 | 1560000 | ESTIMATED | N | 2010 |  |  |  | 0
|  |  |  | STP | 1001020 | SIMPSON | 3-8307 | KY 100 | 2.3 | 10.715 | 12.191 | RELIABILITY | MAJOR WIDENING(O) | MAJOR WIDENING TO FOUR LANES FROM KY-1008 IN FRANKLIN TO I-65. (06CCN) | 2 | D | STP | 2011 | 900000 | 900000 | ESTIMATED | N | 2010 | OBLIGATED | 900000 |  | 900000 | 2011 | 1st QUARTER | N/A
|  |  |  | BRO | 5125009 | SPENCER | 5-1033 | KY 55 | 0.2 | 6.228 | 6.311 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE SALT RIVER BRIDGE IN TAYLORSVILLE (B04). (SR=41.2) (08CCR): (108B00004N)(10CCR) | 3 | R | BRO | 2011 | 1060000 | 1060000 | ESTIMATED | N |  | OBLIGATED | 450000 |  | 450000 | 2012 | 1st QUARTER | N/A
[6 empty] | SPENCER | 5-1033 | KY 55 | 0.2 | 6.228 | 6.311 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE SALT RIVER BRIDGE IN TAYLORSVILLE (B04). (SR=41.2) (08CCR): (108B00004N)(10CCR) | 4 | U | BRO | 2011 | 520000 | 520000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | SPENCER | 5-1033 | KY 55 | 0.2 | 6.228 | 6.311 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE SALT RIVER BRIDGE IN TAYLORSVILLE (B04). (SR=41.2) (08CCR): (108B00004N)(10CCR) | 5 | C | BRO | 2012 | 4440000 | 4440000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | SPENCER | 5-1055 | KY 3192 | 0.1 | 0.008 | 0.108 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-3192 (MP 0.058) OVER ELK CREEK; .1 MI WEST OF JCT KY-1633; (STRUCTURALLY DEFICIENT, SR=49.3) 108B00013N | 2 | D | BRX | 2012 | 160000 | 160000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.190 | 2012-05-15 | INCREASE D PHASE FUNDING. MOD |  |  | SPENCER | 5-1055 | KY 3192 | 0.1 | 0.008 | 0.108 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-3192 (MP 0.058) OVER ELK CREEK; .1 MI WEST OF JCT KY-1633; (STRUCTURALLY DEFICIENT, SR=49.3) 108B00013N | 2 | D | BRX | 2012 | 237500 | 237500 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.103 | 2011-08-09 | ADD PROJECT. NEW | R | 0012016 | STATEWIDE | [7 empty] | TRANSPORTATION RESEARCH PROGRAM ADMINISTERED BY THE TRANSPORTATION CENTER AT THE UNIVERSITY OF KENTUCKY |  | N | SPR | 2011 | 3200000 | 3200000 |  |  |  | OBLIGATED | 4624894 | 0 | 4624894 | 2011 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.213 | 2012-06-29 | ADD PROJECT FOR FY 2012. MOD |  |  | STATEWIDE | [7 empty] | TRANSPORTATION RESEARCH PROGRAM ADMINISTERED BY THE TRANSPORTATION CENTER AT THE UNIVERSITY OF KENTUCKY |  | N | SPR | 2012 | 3000000 | 3000000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.115 | 2011-09-01 | ADD PROJECT. FY 2011 DBE/SS PROGRAM. NEW | DBESS | 3000918 | STATEWIDE | [7 empty] | TECHNICAL TRAINING AND DEVELOPMENT OF UNDERUTILIZED DISADVANTAGED BUSINESS ENTERPRISE FIRMS. |  | N | KYD | 2011 | 145500 | 145500 |  |  |  | OBLIGATED | 145500 |  | 145500 | 2011 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.115 | 2011-09-01 | ADD PROJECT. OJB/SS PROGRAM. NEW | OJTSS | 3000919 | STATEWIDE | [7 empty] | TRAINING AND EQUIPMENT FOR LABORERS |  | N | KYD | 2011 | 175000 | 175000 |  |  |  | OBLIGATED | 232232.45 |  | 232232.45 | 2011 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.120 | 2011-09-06 | ADD PROJECT. BREAKOUT FROM 99-911.01. NEW | HSIP | 9010065 | STATEWIDE | [5 empty] | SAFETY | SAFETY-HAZARD ELIM(P) | DESIGN ENGINEERING FOR PREPARING THE HORIZONTAL ALIGNMENT SIGNING PLANS FOR HSIP STATEWIDE CORRIDORS |  | D | SAF | 2011 | 12000000 | 12000000 |  |  |  | OBLIGATED | 12000000 |  | 12000000 | 2011 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.125 | 2011-09-13 | ADD PROJECT. BREAKOUT FROM 99-911.01 NEW | HSIP | 9010064 | STATEWIDE | [5 empty] | SAFETY | SAFETY-HAZARD ELIM(P) | RETROFIT CENTERLINE, SHOULDER, AND EDGELINE RUMBLE STRIPS AT VARIOUS LOCATIONS STATEWIDE. |  | C | SAF | 2011 | 3500000 | 3500000 |  |  |  | OBLIGATED | 2978006.79 | 521993.21 | 3500000 | 2011 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.132 | 2011-09-23 | ADD PROJECT. BREAKOUT FROM 99-911.01 NEW | HSIP | 9010067 | STATEWIDE | [5 empty] | SAFETY | SAFETY-HAZARD ELIM(P) | PLACE HIGH FRICTION SURFACE ON VARIOUS ROUTES STATEWIDE |  | C | SAF | 2011 | 2821000 | 2821000 |  |  |  | OBLIGATED |  | 2821000 | 2821000 | 2011 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.198 | 2012-06-01 | ADD PROJECT. NEW | STP | 3000933 | STATEWIDE | [7 empty] | TRAINING SESSIONS FOR TRANSPORTATION PERSONNEL RESPONSIBLE FOR DEVELOPMENT, IMPLEMENTATION, AND SUPERVISION OF VARIOUS ASPECTS OF PROVIDING A FINISHED TRANSPORTATION FACILITY. |  | N | STP | 2013 2014 | 1937000 | 1937000 |  |  |  | OBLIGATED | 1937000 |  | 1937000 | 2012 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.200 | 2012-06-05 | ADD PROJECT. NEW |  |  | STATEWIDE | [7 empty] | ACQUISITION OF LIGHT DETECTION AND RANGING EQUIPMENT FOR VIDEO-LOGGING VANS. |  | N | STP | 2012 | 400000 | 400000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.200 | 2012-06-05 | ADD PROJECT. NEW |  |  | STATEWIDE | [7 empty] | ACQUISITION OF A NEW DATA COLLECTION VEHICLE WITH UPGRADED PROFILE TECHNOLOGY EQUIPMENT. |  | N | STP | 2012 | 600000 | 600000 | [6 empty] | 0
[6 empty] | TAYLOR | 4-142.1 | KY 555 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | PRIORITY SECTION OF THE HEARTLAND PARKWAY (CAMPBELLSVILLE BYPASS). (2005HPP-KY127)(2006BOPC)(FUNDS NOT CURRENTLY AVAILABLE FOR R, U & C) | 5 | C | HPP | 2011 | 3819200 | 3819200 | NON-SIXYEAR | N | 2010 |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.062 | 2011-04-07 | ADD PROJECT. BREAKOUT FROM 99-911.00. NEW | HSIP | 0551038 | TAYLOR | 4-911 | US 68 | 6.13 | 7.4 | 13.53 | SAFETY | SAFETY-HAZARD ELIM(P) | TRENCH/REMOVE 3" OF SHOULDER MATERIAL AND REPLACE WITH BITUMINOUS BASE ALONG EACH SIDE OF US 68 FROM KY 1799 AT CAMPBELLSVILLE, EAST TO THE MARION COUNTY LINE AND EXTEND THE MERGING LANE AT KY 1799. |  | C | SAF | 2011 | 493000 | 493000 |  |  |  | OBLIGATED | 658000 |  | 658000 | 2011 | 3rd QUARTER | N/A
[6 empty] | TAYLOR | 4-1058 | CR 1236 | 0.1 | 2.317 | 2.349 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER GREEN RIVER (C15) 0.75MI SW OF N-JCT. KY-55. (SR=25.2): (109C00015N) | 3 | R | BRZ | 2011 | 60000 | 60000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | TAYLOR | 4-1058 | CR 1236 | 0.1 | 2.317 | 2.349 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER GREEN RIVER (C15) 0.75MI SW OF N-JCT. KY-55. (SR=25.2): (109C00015N) | 5 | C | BRZ | 2011 | 1090000 | 1090000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.197 | 2012-05-30 | ADD PROJECT. NEW |  |  | TAYLOR | 4-1082 | CR 1001 | 0.04 | 1.58 | 1.62 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON WISE RD (CR 1001) OVER LONG BRANCH .08 MILE W OF LONG BRANCH RD (CR 1002)(SR 23.7) 109C00001N |  | D | BRZ | 2012 | 100000 | 100000 | [6 empty] | 0
|  |  |  | NH | 0801082 | TRIGG | 1-180.1 | US 68 | 1.358 | 11.382 | 12.74 | RELIABILITY | MAJOR WIDENING(O) | CADIZ-AURORA; FROM 200 METERS WEST OF KY-1489 TO 200 METERS WEST OF PETE LIGHT SPRING ROAD.(10CCR) | 3 | R | NH | 2012 | 1660000 | 1660000 | ESTIMATED | Y |  | OBLIGATED | 165000 |  | 165000 | 2011 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.214 | 2012-07-05 | INCREASE R PHASE FUNDING AMOUNT. MOD |  |  | TRIGG | 1-180.1 | US 68 KY 80 | 1.358 | 11.382 | 12.74 | RELIABILITY | MAJOR WIDENING(O) | CADIZ-AURORA; FROM 200 METERS WEST OF KY-1489 TO 200 METERS WEST OF PETE LIGHT SPRING ROAD.(10CCR) |  | R | NH | 2012 | 2370000 | 2370000 | [6 empty] | 0
[6 empty] | TRIGG | 1-180.1 | US 68 | 1.358 | 11.382 | 12.74 | RELIABILITY | MAJOR WIDENING(O) | CADIZ-AURORA; FROM 200 METERS WEST OF KY-1489 TO 200 METERS WEST OF PETE LIGHT SPRING ROAD.(10CCR) | 4 | U | NH | 2012 | 3810000 | 3810000 | ESTIMATED | Y |  |  |  |  | 0
[6 empty] | TRIGG | 1-180.1 | US 68 | 1.358 | 11.382 | 12.74 | RELIABILITY | MAJOR WIDENING(O) | CADIZ-AURORA; FR 200 METERS W OF KY-1489 TO 200 METERS W OF PETE LIGHT SPRING RD. | 5 | C | STP | 2013 | 18140000 | 18140000 | ESTIMATED | [5 empty] | 0
|  |  |  | NH | 0801090 | TRIGG | 1-180.11 | US 68 | 3.11 | 12.74 | 16.35 | RELIABILITY | MAJOR WIDENING(O) | CADIZ-AURORA; FROM 200 METERS WEST OF PETE LIGHT SPRING ROAD.TO CADIZ BYPASS (GRADE, DRAIN & SURFACE)(10CCR) | 3 | R | NH | 2011 | 1930000 | 1930000 | ESTIMATED | Y |  | OBLIGATED | 2370000 |  | 2370000 | 2012 | 3rd QUARTER | N/A
[6 empty] | TRIGG | 1-180.11 | US 68 | 3.11 | 12.74 | 16.35 | RELIABILITY | MAJOR WIDENING(O) | CADIZ-AURORA; FROM 200 METERS WEST OF PETE LIGHT SPRING ROAD.TO CADIZ BYPASS (GRADE, DRAIN & SURFACE)(10CCR) | 4 | U | NH | 2012 | 3810000 | 3810000 | ESTIMATED | Y |  |  |  |  | 0
[6 empty] | TRIGG | 1-180.11 | US 68 | 3.11 | 12.74 | 16.35 | RELIABILITY | MAJOR WIDENING(O) | CADIZ-AURORA; FR 200 METERS W OF PETE LIGHT SPRING RD.TO CADIZ BYPASS (GRADE, DRAIN & SURFACE) | 5 | C | STP | 2013 | 17550000 | 17550000 | ESTIMATED | [5 empty] | 0
|  |  |  | NH | 0801087 | TRIGG | 1-180.51 | US 68 | 3.1 | 8.284 | 11.382 | RELIABILITY | MAJOR WIDENING(O) | CADIZ-AURORA; FROM EAST END OF LAKE BARKLEY BRIDGE TO 200 METERS WEST OF KY-1489 (08CCR)(10CCR) | 3 | R | NHG | 2011 | 5250000 | 5250000 | ESTIMATED | Y | 2010 | OBLIGATED |  | 5250000 | 5250000 | 2012 | 1st Q UARTER | N/A
[6 empty] | TRIGG | 1-180.51 | US 68 | 3.1 | 8.284 | 11.382 | RELIABILITY | MAJOR WIDENING(O) | CADIZ-AURORA; FROM EAST END OF LAKE BARKLEY BRIDGE TO 200 METERS WEST OF KY-1489 (08CCR)(10CCR) | 4 | U | NHG | 2011 | 3380000 | 3380000 | ESTIMATED | Y | 2010 |  |  |  | 0
[6 empty] | TRIGG | 1-180.51 | US 68 | 3.1 | 8.284 | 11.382 | RELIABILITY | MAJOR WIDENING(O) | CADIZ-AURORA; FROM EAST END OF LAKE BARKLEY BRIDGE TO 200 METERS WEST OF KY-1489 (08CCR)(10CCR) | 5 | C | NH | 2011 | 11700000 | 11700000 | ESTIMATED | Y |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.142 | 2011-11-09 | ADD DESIGN PHASE TO STIP. NEW |  |  | TRIGG | 1-180.6 | US 68 | 0.6 | 8.284 | 8.872 | RELIABILITY | BRIDGE REPLACEMENT(P) | CADIZ-AURORA; BRIDGE OVER LAKE BARKLEY, PHASE II DESIGN | 4 | D | STP | 2012 | 15000000 | 15000000 | ESTIMATED | Y | 2010 |  |  |  | 0
[6 empty] | TRIGG | 1-180.6 | US 68 | 0.6 | 8.284 | 8.872 | RELIABILITY | BRIDGE REPLACEMENT(P) | CADIZ-AURORA; BRIDGE OVER LAKE BARKLEY (TOTAL CONSTRUCTION COST IS $165 MILLION)(2006BOPP): (111B00020N)(10CCR) | 4 | U | GVR | 2011 | 330000 | 330000 | ESTIMATED | Y | 2010 |  |  |  | 0
[6 empty] | TRIGG | 1-180.6 | US 68 | 0.6 | 8.284 | 8.872 | RELIABILITY | BRIDGE REPLACEMENT(P) | CADIZ-AURORA; BRIDGE OVER LAKE BARKLEY (TOTAL CONSTRUCTION COST IS $165 MILLION)(2006BOPP): (111B00020N)(10CCR) | 5 | C | GVR | 2011 | 99990000 | 99990000 | ESTIMATED | Y |  |  |  |  | 0
[6 empty] | TRIGG | 1-180.61 | US 68 | 0.6 | 8.284 | 8.872 | RELIABILITY | PREFINANCD CONVRSN(P) | CADIZ-AURORA; BRIDGE OVER LAKE BARKLEY (ADDITIONAL FUNDING FOR C PHASE)(10CCR) | 5 | C | GVR | 2011 | 25000000 | 25000000 | REESTIMATED | Y |  |  |  |  | 0
[6 empty] | TRIGG | 1-180.62 | US 68 | 0.6 | 8.284 | 8.872 | RELIABILITY | PREFINANCD CONVRSN(P) | CADIZ-AURORA; BRIDGE OVER LAKE BARKLEY (ADDITIONAL FUNDING FOR C PHASE)(10CCR) | 5 | C | GVR | 2012 | 40000000 | 40000000 | REESTIMATED | Y |  |  |  |  | 0
|  |  |  | BRZ | 0103294 | TRIGG | 1-1133 | KY 1585 | 0.1 | 4.82 | 4.92 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-1585 (MP 4.87) OVER SINKING FORK; .3 MI. NORTH OF HWY. 272 JCT.; (STRUCTURALLY DEFICIENT, SR=19.7) 111B00054N | 2 | D | BRX | 2012 | 140000 | 140000 | ESTIMATED | N |  | OBLIGATED | 200000 |  | 200000 | 2011 | 3rd QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.062 | 2011-04-07 | ADD PROJECT. BREAKOUT FROM 99-65.08. NEW | IM | 0243051 | TRIGG | 1-2023 | I 24 | 0.09 | 65.3 | 65.39 | RELIABILITY | BRIDGE REHAB(P) | JOINT REPLACEMENT, PARTIAL DEPTH PATCHING AND CONCRETE OVERLAY ON THE I-24 BRIDGE OVER US68. (111B00044L) |  | C | IM | 2011 | 260000 | 260000 |  |  |  | OBLIGATED | 361452 |  | 361452 | 2011 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.211 | 2012-06-28 | ADD PROJECT. NEW |  |  | TRIMBLE | 5-905 | US 421 | 0.4 | 11.278 | 11.678 | SAFETY | SAFETY(P) | ADDRESS SAFETY ISSUES AND ACCESS AT THE INTERSECTION OF US-421/KY-1226 AT MP 11.5. (12CCR) |  | D | STP | 2012 | 220000 | 220000 | [6 empty] | 0
[6 empty] | UNION | 2-122.01 | US 60 | 3.7 | 17.8 | 21.5 | RELIABILITY | MAJOR WIDENING(O) | PADUCAH-HENDERSON; MORGANFIELD BYPASS TO WAVERLY (08CCR) | 3 | R | STP | 2011 | 3860000 | 3860000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | UNION | 2-122.01 | US 60 | 3.7 | 17.8 | 21.5 | RELIABILITY | MAJOR WIDENING(O) | PADUCAH-HENDERSON; MORGANFIELD BYPASS TO WAVERLY (08CCR) | 4 | U | STP | 2011 | 2710000 | 2710000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | UNION | 2-310.1 | KY 56 | 4.3 | 7.182 | 11.5 | RELIABILITY | MINOR WIDENING(O) | KY-56 FROM JUST WEST OF KY-360 TO THE MORGANFIELD BYPASS; WIDENING, ADDING SHOULDERS AND ELIMINATING HORIZONTAL & VERTICAL DEFICIENCIES.(10CCR) | 5 | C | STP | 2011 | 9740000 | 9740000 | ESTIMATED | N | 2010 |  |  |  | 0
|  |  |  | BRO | 5050002 | UNION | 2-1073 | KY 359 | 0.1 | 0.921 | 1.021 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-359 (MP 0.971) OVER LOST CREEK; .95 MI N.E. OF JCT US-60; (FUNCTIONALLY OBSOLETE, SR=48.6) 113B00006N | 2 | D | BRO | 2012 | 150000 | 150000 | ESTIMATED | N |  | OBLIGATED | 150000 |  | 150000 | 2012 | 2nd QUARTER | N/A
|  |  |  | BRO | 5050003 | UNION | 2-1074 | KY 359 | 0.1 | 1.143 | 1.243 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-359 (MP 1.193) OVER SINKING CREEK; 1.1 MI N.E. OF JCT US-60; (FUNCTIONALLY OBSOLETE, SR=48.6) 113B00007N | 2 | D | BRO | 2012 | 150000 | 150000 | ESTIMATED | N |  | OBLIGATED | 150000 |  | 150000 | 2012 | 2nd QUARTER | N/A
AMENDMENT | 2010.005 | 2011-11-08 | PER BOWLING GREEN MPO'S NEW TIP, ADDING PHASE TO STIP. NEW | HPP | 0150009 | WARREN | 3-16 | I 65 |  |  |  | RELIABILITY | NEW INTERCHANGE(O) | CONSTRUCTION OF NEW INTERCHANGE ON I-65 AND ACCESS ROAD TO CONNECT US-31W NORTH OF BOWLING GREEN |  | R | HPP | 2012 | 5000000 | 5000000 |  | Y |  | OBLIGATED | 5000000 |  | 5000000 | 2012 | 1st QUARTER | N/A
AMENDMENT | 2010.005 | 2011-11-08 | PER BOWLING GREEN MPO'S NEW TIP, ADDING PHASE TO STIP. NEW | HPP | 0150008 | WARREN | 3-16 | I 65 |  |  |  | RELIABILITY | NEW INTERCHANGE(O) | CONSTRUCTION OF NEW INTERCHANGE ON I-65 AND ACCESS ROAD TO CONNECT US-31W NORTH OF BOWLING GREEN |  | U | HPP | 2012 | 7750000 | 7750000 |  | Y |  | OBLIGATED | 7750000 |  | 7750000 | 2012 | 1st QUARTER | N/A
[6 empty] | WARREN | 3-16.02 | I 65 |  |  |  | RELIABILITY | NEW INTERCHANGE(O) | CONSTRUCTION OF INTERCHANGE CONNECTING US-31W TO I-65 AT MILE MARKER 32 IN WARREN COUNTY. (2005HPP-KY137)(SEE 3-16.00 FOR "SP" COMPONENT) | 5 | C | HPP | 2011 | 1439839 | 1439839 | REESTIMATED | Y | 2010 |  |  |  | 0
[6 empty] | WARREN | 3-16.03 | I 65 |  |  |  | RELIABILITY | NEW INTERCHANGE(O) | CONSTRUCTION OF NEW I-65 INTERCHANGE IN WARREN COUNTY. (2005HPP-KY150)(SEE 3-16.00 FOR "SP" COMPONENT) | 5 | C | HPP | 2011 | 20697699 | 20697699 | ESTIMATED | Y | 2010 |  |  |  | 0
[6 empty] | WARREN | 3-16.04 | I 65 |  |  |  | RELIABILITY | NEW INTERCHANGE(O) | CONSTRUCTION OF NEW I-65 INTERCHANGE IN WARREN COUNTY, KENTUCKY. (2005HPP-KY164) | 5 | C | HPP | 2011 | 10873668 | 10873668 | ESTIMATED | Y | 2010 |  |  |  | 0
[6 empty] | WARREN | 3-16.11 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | KENTUCKY TRIMODAL TRANSPARK. (04KYD) | 5 | C | KYD | 2011 | 5250000 | 5250000 | ESTIMATED | N | 2010 |  |  |  | 0
[6 empty] | WARREN | 3-16.12 | US 68 | 1.1 | 15.248 | 16.7 | RELIABILITY | NEW ROUTE(O) | 4 LANE US-68, US-31W TO TRANSPARK ENTRANCE ON US-68, KENTUCKY. (05KYD) | 5 | C | KYD | 2011 | 1967856 | 1967856 | ESTIMATED | N | 2010 |  |  |  | 0
|  |  |  | NH | 0651094 | WARREN | 3-17 | I 65 | 0.6 | 22.088 | 22.624 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | RECONSTRUCT I-65/US-231 (SCOTTSVILLE ROAD) INTERCHANGE AT BOWLING GREEN. (02CCR)(06CCR)(PHASE I DESIGN INCLUDED WITH 3-9.00) (08CCR) | 3 | R | NHG | 2011 | 530000 | 530000 | ESTIMATED | Y | 2010 | OBLIGATED | 200000 |  | 200000 | 2011 | 1st QUARTER | N/A
|  |  |  | IM | 0651092 | WARREN | 3-17 | I 65 | 0.6 | 22.088 | 22.624 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | RECONSTRUCT I-65/US-231 (SCOTTSVILLE ROAD) INTERCHANGE AT BOWLING GREEN. (02CCR)(06CCR)(PHASE I DESIGN INCLUDED WITH 3-9.00) (08CCR) | 4 | U | NHG | 2011 | 520000 | 520000 | ESTIMATED | Y | 2010 | OBLIGATED | 760000 |  | 760000 | 2011 | 1st QUARTER | N/A
|  |  |  | NH | 0651095 | WARREN | 3-17 | I 65 | 0.6 | 22.088 | 22.624 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | RECONSTRUCT I-65/US-231 (SCOTTSVILLE ROAD) INTERCHANGE AT BOWLING GREEN. (02CCR)(06CCR)(PHASE I DESIGN INCLUDED WITH 3-9.00) (08CCR) | 5 | C | NH | 2012 | 14000000 | 14000000 | ESTIMATED | Y |  | OBLIGATED | 21807453.02 |  | 21807453.02 | 2011 | 4th QUARTER | N/A
[6 empty] | WARREN | 3-17.01 | I 65 | 0.6 | 22.088 | 22.624 | RELIABILITY | PREFINANCD CONVRSN(O) | RECONSTRUCT I-65/US-231 (SCOTTSVILLE ROAD) INTERCHANGE AT BOWLING GREEN. (ADDITIONAL FUNDING FOR C PHASE) | 5 | C | NH | 2013 | 10750000 | 10750000 | ESTIMATED | [5 empty] | 0
|  |  |  | STP | 0031007 | WARREN | 3-53.1 |  | 1.9 |  |  | RELIABILITY | NEW ROUTE(O) | SURFACING FOR THE EXTENSION OF WILLIAM H. NATCHER PARKWAY TO US-231 AT DYE FORD RD. (SEE 5-53.00 FOR GRADE AND DRAIN PORTION)(2008BOPC) | 5 | C | STP | 2012 | 13000000 | 13000000 | ESTIMATED | N |  | OBLIGATED | 10537252 |  | 10537252 | 2011 | 2nd QUARTER | N/A
|  |  |  | STP | 7434022 | WARREN | 3-317 | US 31W | 2.1 | 6.684 | 8.788 | RELIABILITY | MAJOR WIDENING(O) | BOWLING GREEN-FRANKLIN ROAD; WIDEN US31W WEST OF THE NATCHER PARKWAY TO DILLARD ROAD.(10CCR) | 5 | C | STP | 2012 | 14180000 | 14180000 | ESTIMATED | N |  | OBLIGATED | 9036671 | 5180000 | 14216671 | 2011 | 4th QUARTER | N/A
|  |  |  | TCSP | 09KY003 | WARREN | 3-594 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | WESTERN KENTUCKY UNIVERSITY (WKU)- COMMUNITY BIKEWAY PROJECT. CONSTRUCTION OF 4.5 MILES OF BICYCLE AND PEDESTRIAN PATHS TO CONNECT WKU CAMPUS WITH RECREATIONAL FACILITIES, BUSINESSES, AND LOCAL PUBLIC SCHOOLS WITHIN THE CITY OF BOWLING GREEN. | 5 | C | KYD | 2011 | 950000 | 950000 | ESTIMATED |  | 2010 | OBLIGATED | 889200 |  | 889200 | 2010 | 4th QUARTER | CITY OF BOWLING GREEN
ADMINISTRATIVE MODIFICATION | 2010.158 | 2012-01-24 | ADD PROJECT. TIP MOD NO. 2012.02. NEW | HSIP | 3011023 | WARREN | 3-913.00 | KY 1402 | 5.7 | 0 | 5.7 | SAFETY | SAFETY-HAZARD ELIM(P) | EXTEND CULVERTS, ADD EMBANKMENT, REMOVE HEADWALLS, AND INSTALL GUARDRAIL METAL END SECTIONS ON PORTER ROAD (KY 1402) AT BOWLING GREEN FROM US 31W, EAST TO 0.3 MI WEST OF KY 1297 |  | C | SAF | 2012 | 300000 | 300000 |  |  |  | OBLIGATED | 300000 |  | 300000 | 2012 | 2nd QUARTER | N/A
|  |  |  | BRZ | 0303230 | WARREN | 3-1070 | CR 1301 | 0.1 | 0.222 | 0.232 | SAFETY | BRIDGE REPLACEMENT(P) | WEST BOGLE ROAD; REPLACE BRIDGE AND APPROACHES OVER RJC RAILROAD 0.20 MILE SOUTHEAST OF US-68 (C7). (SR=16.5): (114C00007N) | 2 | D | BRZ | 2011 | 160000 | 160000 | ESTIMATED | N |  | OBLIGATED | 160000 |  | 160000 | 2011 | 1st QUARTER | N/A
[6 empty] | WARREN | 3-1070 | CR 1301 | 0.1 | 0.222 | 0.232 | RELIABILITY | BRIDGE REPLACEMENT(P) | WEST BOGLE ROAD; REPLACE BRIDGE AND APPROACHES OVER RJC RAILROAD 0.20 MILE SOUTHEAST OF US-68 (C7). (SR=16.5) | 3 | R | BRZ | 2013 | 50000 | 50000 | ESTIMATED | [5 empty] | 0
[6 empty] | WARREN | 3-1070 | CR 1301 | 0.1 | 0.222 | 0.232 | RELIABILITY | BRIDGE REPLACEMENT(P) | WEST BOGLE ROAD; REPLACE BRIDGE AND APPROACHES OVER RJC RAILROAD 0.20 MILE SOUTHEAST OF US-68 (C7). (SR=16.5) | 4 | U | BRZ | 2013 | 300000 | 300000 | ESTIMATED | [5 empty] | 0
[6 empty] | WARREN | 3-1070 | CR 1301 | 0.1 | 0.222 | 0.232 | RELIABILITY | BRIDGE REPLACEMENT(P) | WEST BOGLE ROAD; REPLACE BRIDGE AND APPROACHES OVER RJC RAILROAD 0.20 MILE SOUTHEAST OF US-68 (C7). (SR=16.5) | 5 | C | BRZ | 2014 | 450000 | 450000 | ESTIMATED | [5 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.035 | 2011-01-28 | ADD PROJECT. BREAKOUT FROM 99-911.00. NEW | HSIP | 5129013 | WASHINGTON | 4-906 | KY 152 | 0.25 | 9.45 | 9.7 | SAFETY | SAFETY-HAZARD ELIM(P) | REALIGNMENT OF A VERTICAL CURVE ON KY 152 AT HAYDEN BRANCH EAST OF SPRINGFIELD |  | C | SAF | 2011 | 147000 | 147000 |  |  |  | OBLIGATED | 176067 |  | 176067 | 2011 | 2nd QUARTER | N/A
|  |  |  | BRO | 1501100 | WASHINGTON | 4-1069 | US 150 | 0.1 | 0.035 | 0.135 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON US-150 (MP 0.085) OVER CARTWRIGHT CREEK; .1 MI EAST OF NELSON CL; (STRUCTURALLY DEFICIENT, SR=41.1) 115B00022N | 2 | D | BRO | 2011 | 250000 | 250000 | ESTIMATED | N | 2010 | OBLIGATED | 250000 |  | 250000 | 2011 | 1st QUARTER | N/A
[6 empty] | WASHINGTON | 4-1069 | US 150 | 0.1 | 0.035 | 0.135 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON US-150 (MP 0.085) OVER CARTWRIGHT CREEK; .1 MI EAST OF NELSON CL; (STRUCTURALLY DEFICIENT, SR=41.1) 115B00022N | 3 | R | BRO | 2012 | 120000 | 120000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | WASHINGTON | 4-1069 | US 150 | 0.1 | 0.035 | 0.135 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON US-150 (MP 0.085) OVER CARTWRIGHT CREEK; .1 MI EAST OF NELSON CL; (STRUCTURALLY DEFICIENT, SR=41.1) 115B00022N | 4 | U | BRO | 2012 | 75000 | 75000 | ESTIMATED | N |  |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2010.097 | 2011-07-11 | ADD PROJECT. AWARDED FY 2010 NHCB DISCRETIONARY FUNDING. NEW |  |  | WASHINGTON | 4-3013 |  |  |  |  | RELIABILITY | BRIDGE REHAB(P) | RESTORATION OF BEECH FORK COVERED BRIDGE APPROX. 7 MILES SOUTH OF CHAPLIN. |  | C | KYD | 2011 | 955960 | 955960 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.115 | 2011-09-01 | ADD PROJECT. AWARDED FY 2011 NHCB DISCRETIONARY FUNDING. NEW |  |  | WASHINGTON | 4-3013 |  |  |  |  | RELIABILITY | BRIDGE REHAB(P) | RESTORATION OF BEECH FORK COVERED BRIDGE |  | C | KYD | 2012 | 694440 | 694440 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.149 | 2011-12-07 | ADD PROJECT. PROJECT SPONSOR: WASHINGTON COUNTY FISCAL COURT. NEW | SB | KY10002 | WASHINGTON LARUE NELSON BOYLE | [7 empty] | THIS PROJECT WILL FUND SEVERAL KEY IMPLEMENTATION STRATEGIES IDENTIFIED IN THE CORRIDOR MANAGEMENT PLAN AND STRATEGIC VISION WORKSHOP CONDUCTED BY THE LINCOLN HERITAGE SCENIC HIGHWAY (LHSH) ADVISORY COMMITTEE SINCE NATIONAL DESIGNATION IN OCTOBER 2009. THIS PROJECT WILL IMPLEMENT SPECIFIC STRATEGIES OUTLINED IN THE CORRIDOR MANAGEMENT PLAN (CMP), SPECIFICALLY CATEGORIES 2 – PRESERVATION AND MAINTENANCE OF THE INTRINSIC QUALITIES, AND 4 - INTERPRETATION AND EDUCATION OF THE CORRIDOR VISION, GOALS, AND STRATEGIES, WHILE ENSURING THAT EFFECTIVE PUBLIC OUTREACH AND COMMUNITY INVOLVEMENT OCCURS. |  | N | NAT SC BYW | 2012 | 50000 | 40000 |  |  |  | OBLIGATED | 40000 |  | 40000 | 2012 | 2nd QUARTER | WASHINGTON COUNTY FISCAL COURT
|  |  |  | BRZ | 0803167 | WAYNE | 8-1050 | CR 1136 | 0.1 | 0.175 | 0.275 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON CR-1136 (MP 0.225) OVER LITTLE SOUTH FORK RIVER; 0.25 MI SE OF JCT CR-5137; (STRUCTURALLY DEFICIENT, SR=16.6) 116C00007N | 2 | D | BRZ | 2012 | 175000 | 175000 | ESTIMATED | N |  | OBLIGATED | 201000 |  | 201000 | 2012 | 2nd QUARTER | N/A
|  |  |  | BRZ | 0803166 | WAYNE | 8-1051 | CR 1700 | 0.1 | 0 | 0.1 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON CR-1700 (MP 0.008) OVER DRY HOLLOW CREEK; 15' E. JCT CR-5213; (STRUCTURALLY DEFICIENT, SR=5.6) 116C00040N | 2 | D | BRZ | 2012 | 175000 | 175000 | ESTIMATED | N |  | OBLIGATED | 160500 |  | 160500 | 2012 | 2nd QUARTER | N/A
[6 empty] | WHITLEY | 11-19 | I 75 | 0.5 | 0.253 | 0.563 | RELIABILITY | REST AREA REHAB(P) | MODERNIZE I-75 NB REST AREA. | 5 | C | IM | 2014 | 9590000 | 9590000 | ESTIMATED | [5 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.191 | 2012-05-16 | ADD PROJECT TO STIP. NEW | STP | 0902005 | WHITLEY | 11-186 | US 25W | 2.225 | 28.2 | 30.425 | RELIABILITY | MAJOR WIDENING(O) | MAJOR WIDENING, ADDRESSES CONGESTION, FREIGHT MOVEMENT, AND ACCESS ALONG 25W FROM KY 727 TO KY 3041. (12CCR) |  | D | STP | 2012 | 1345000 | 1345000 |  |  |  | OBLIGATED | 700000 |  | 700000 | 2012 | 4th QUARTER | N/A
|  |  |  | BRO | 5147021 | WHITLEY | 11-1081 | KY 92 | 0.1 | 3 | 3.03 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER JELLICO CREEK; .80 MILE EAST OF KY 1898 (B00022N). | 2 | D | BRO | 2011 | 350000 | 350000 | ESTIMATED | N | 2010 | OBLIGATED | 350000 |  | 350000 | 2011 | 1st QUARTER | N/A
[6 empty] | WHITLEY | 11-1081 | KY 92 | 0.1 | 3 | 3.03 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER JELLICO CREEK; .80 MILE EAST OF KY 1898 (B00022N). | 3 | R | BRO | 2012 | 175000 | 175000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | WHITLEY | 11-1081 | KY 92 | 0.1 | 3 | 3.03 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER JELLICO CREEK; .80 MILE EAST OF KY 1898 (B00022N). | 4 | U | BRO | 2012 | 100000 | 100000 | ESTIMATED | N |  |  |  |  | 0
[6 empty] | WHITLEY | 11-1081 | KY 92 | 0.1 | 3 | 3.03 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER JELLICO CREEK; .80 MILE EAST OF KY 1898 (B00022N). | 5 | C | BRO | 2012 | 2500000 | 2500000 | ESTIMATED | N |  |  |  |  | 0
|  |  |  | BRZ | 1103247 | WHITLEY | 11-1085 | CR 1184 |  | 0.089 | 0.189 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON CR-1184 (MP 0.139) OVER PATTERSON CREEK; .2 MI EAST OF JCT KY 904; (STRUCTURALLY DEFICIENT, SR=16.5) 118C00012N | 2 | D | BRZ | 2012 | 250000 | 250000 | ESTIMATED |  |  | OBLIGATED | 250000 |  | 250000 | 2012 | 1st QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.062 | 2011-04-07 | ADD PROJECT. BREAKOUT FROM 99-65.08. NEW | IM | 0751077 | WHITLEY | 11-2033 | I 75 | 0.044 | 15.456 | 15.5 | RELIABILITY | BRIDGE REHAB(P) | JOINT REPLACEMENT, PARTIAL DEPTH PATCHING AND CONCRETE OVERLAY ON THE US 25 BRIDGE OVER I-75 NORTH OF WILLIAMSBURG.(118B00030) |  | C | IM | 2011 | 175000 | 175000 |  |  |  | OBLIGATED | 233460 |  | 233460 | 2011 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.084 | 2011-06-06 | ADD PROJECT TO STIP. BREAKOUT FROM 99-337.05. NEW | IM | 0751078 | WHITLEY | 11-2034 | I 75 | 0.1 | 27.89 | 27.99 | RELIABILITY | PAVEMENT REHAB-INT(P) | REPLACE BEARINGS AND EXPANSION JOINTS ON THE I-75 BRIDGES OVER LYNN CAMP CREEK AT THE WHITLEY/LAUREL COUNTY LINE. |  | C | IM | 2011 | 125000 | 125000 |  |  |  | OBLIGATED | 252000 |  | 252000 | 2011 | 4th QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.004 | 2010-10-05 | ADD 10-126.03 USING ZVARIOUS 99-224.06 FUNDING ON PAGE 2 OF 10 IN THE STIP. 3 COUNTIES: WOLFE, MORGAN, MAGOFFIN. NEW |  |  | WOLFE MORGAN MAGOFFIN | 10-126.03 | KY 9009 | 14.577 5.403 10.429 | 43.104 57.681 63.084 | 57.681 63.084 73.513 | RELIABILITY | MAJOR WIDENING(O) | WIDEN THE MOUNTAIN PARKWAY TO 4-LANES FROM CAMPTON TO SALYERSVILLE, PHASE II DESIGN |  | D | STP | 2013 | 3500000 | 3500000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.216 | 2012-07-25 | ADD PROJECT TO STIP. NEW |  |  | WOLFE | 10-126.70 | KY 9009 |  | 57.2 | 59.2 | RELIABILITY | SCOPING STUDY(O) | WIDEN THE MOUNTAIN PARKWAY TO 4 LANES FROM KY 205 (MP 57.2) TO CR 1226 PARKWAY ROAD TUNNEL (MP 59.20). (2012BOP) |  | D | STP | 2012 | 750000 | 750000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.216 | 2012-07-25 | ADD PROJECT TO STIP. NEW |  |  | WOLFE | 10-168 | KY 9009 |  | 46.2 | 57.2 | RELIABILITY | SCOPING STUDY(O) | WIDEN THE MOUNTAIN PARKWAY TO 4 LANES FROM KY 191 OVERPASS BRIDGE (MP 46.2) TO KY 205 INTERCHANGE (MP 57.2). (SEE 2012 HIGHWAY PLAN ITEM NO 10-126.03 FOR PE & ENVIR FUNDING)(2012BOP) |  | D | STP | 2012 | 1500000 | 1500000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.164 | 2012-02-09 | ADD PROJECT. BREAKOUT FROM 99-911.01. NEW | HSIP | 0061045 | WOLFE | 10-916 | KY 9000 | 0.356 | 38.144 | 38.5 | SAFETY | SAFETY | MILL AND INLAY WITH POLISH RESISTANT STONE AND INSTALL FLASHING BEACONS AND SIGNS ON A SEGMENT OF THE MOUNTAIN PARKWAY FROM THE KY 15 UNDERPASS, EAST 0.4MI TO 1.0MI WEST OF KY 715 UNDERPASS |  | C | SAF | 2012 | 225000 | 225000 |  |  |  | OBLIGATED | 225000 |  | 225000 | 2012 | 2nd QUARTER | N/A
|  |  |  | BRZ | 1003204 | WOLFE | 10-1086 | KY 191 | 0.1 | 10.04 | 10.076 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-191 OVER RED RIVER AT HAZEL GREEN (B02). (SR=21.2) (08CCR): (119B00002N) | 3 | R | BRX | 2011 | 75000 | 75000 | ESTIMATED | N |  | OBLIGATED | 75000 |  | 75000 | 2012 | 2nd QUARTER | N/A
|  |  |  | BRZ | 1003205 | WOLFE | 10-1086 | KY 191 | 0.1 | 10.04 | 10.076 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-191 OVER RED RIVER AT HAZEL GREEN (B02). (SR=21.2) (08CCR): (119B00002N) | 4 | U | BRX | 2011 | 75000 | 75000 | ESTIMATED | N |  | OBLIGATED | 85000 |  | 85000 | 2012 | 3rd QUARTER | N/A
[6 empty] | WOLFE | 10-1086 | KY 191 | 0.1 | 10.04 | 10.076 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-191 OVER RED RIVER AT HAZEL GREEN (B02). (SR=21.2) (08CCR) | 5 | C | BRX | 2013 | 722000 | 722000 | ESTIMATED | [5 empty] | 0
[6 empty] | WOODFORD | 7-2021 | US 60 | 9.4 | 0 | 9.385 | RELIABILITY | PAVEMENT REHAB-PRI(P) | PAVEMENT REHAB ON US-60 FROM THE FRANKLIN COUNTY LINE TO US-60X (MP 9.385) IN VERSAILLES. (2006BOPC)(08CCR) | 5 | C | NHG | 2011 | 2290000 | 2290000 | ESTIMATED | Y | 2010 |  |  |  | 0
|  |  |  | IM IM IM IM IM | 0645073 0241083 0242069 0243049 0645072 | ZVARIOUS | 99-65.07 |  |  |  |  | RELIABILITY | BRIDGE REHAB(P) | BRIDGE REPAIRS ON VARIOUS BRIDGES ON THE INTERSTATE HIGHWAY SYSTEM. | 5 | C | IM | 2011 | 3500000 | 3500000 |  |  |  | OBLIGATED | 1912744.5 |  | 1912744.5 | 2011 | 1st QUARTER | N/A
[6 empty] | ZVARIOUS | 99-65.08 |  |  |  |  | RELIABILITY | BRIDGE REHAB(P) | BRIDGE REPAIRS ON VARIOUS BRIDGES ON THE INTERSTATE HIGHWAY SYSTEM. | 5 | C | IM | 2011 | 3500000 | 3500000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-65.09 |  |  |  |  | RELIABILITY | BRIDGE REHAB(P) | BRIDGE REPAIRS ON VARIOUS BRIDGES ON THE INTERSTATE HIGHWAY SYSTEM. | 5 | C | IM | 2012 | 3500000 | 3500000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-65.1 |  |  |  |  | RELIABILITY | BRIDGE REHAB(P) | BRIDGE REPAIRS ON VARIOUS BRIDGES ON THE INTERSTATE HIGHWAY SYSTEM. (2006BOPP) | 5 | C | IM | 2013 | 3500000 | 3500000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-65.11 |  |  |  |  | RELIABILITY | BRIDGE REHAB(P) | BRIDGE REPAIRS ON VARIOUS BRIDGES ON THE INTERSTATE HIGHWAY SYSTEM. (2006BOPP) | 5 | C | IM | 2014 | 3500000 | 3500000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-66.08 |  |  |  |  | RELIABILITY | ITS(P) | 'ITS' ACTIVITIES ON VARIOUS NHS ROUTES IN KENTUCKY. | 5 | C | NH | 2013 | 6000000 | 6000000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-66.09 |  |  |  |  | RELIABILITY | ITS(P) | 'ITS' ACTIVITIES ON VARIOUS NHS ROUTES IN KENTUCKY. | 5 | C | NH | 2014 | 7000000 | 7000000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-195.12 |  |  |  |  | RELIABILITY | TRANSP ENHANCEMENT(P) | STATEWIDE TRANSPORTATION ENHANCEMENT (98CCR) | 5 | C | TE | 2011 | 12800000 | 12800000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-195.13 |  |  |  |  | RELIABILITY | TRANSP ENHANCEMENT(P) | STATEWIDE TRANSPORTATION ENHANCEMENT (98CCR) | 5 | C | TE | 2011 | 12800000 | 12800000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-195.14 |  |  |  |  | RELIABILITY | TRANSP ENHANCEMENT(P) | STATEWIDE TRANSPORTATION ENHANCEMENT (98CCR) | 5 | C | TE | 2012 | 12800000 | 12800000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-195.15 |  |  |  |  | RELIABILITY | TRANSP ENHANCEMENT(P) | STATEWIDE TRANSPORTATION ENHANCEMENT (98CCR) | 5 | C | TE | 2013 | 13700000 | 13700000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-195.16 |  |  |  |  | RELIABILITY | TRANSP ENHANCEMENT(P) | STATEWIDE TRANSPORTATION ENHANCEMENT (98CCR) | 5 | C | TE | 2014 | 13700000 | 13700000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-219.08 |  |  |  |  | RELIABILITY | CONGESTION MITIGTN(O) | NON-ATTAINMENT AREAS STATEWIDE CMAQ FUNDED PROJECTS | 5 | C | CM | 2011 | 18600000 | 18600000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-219.09 |  |  |  |  | RELIABILITY | CONGESTION MITIGTN(O) | NON-ATTAINMENT AREAS STATEWIDE CMAQ FUNDED PROJECTS | 5 | C | CM | 2011 | 10300000 | 10300000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-219.1 |  |  |  |  | RELIABILITY | CONGESTION MITIGTN(O) | NON-ATTAINMENT AREAS STATEWIDE CMAQ FUNDED PROJECTS | 5 | C | CM | 2012 | 12900000 | 12900000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-219.11 |  |  |  |  | RELIABILITY | CONGESTION MITIGTN(O) | NON-ATTAINMENT AREAS STATEWIDE CMAQ FUNDED PROJECTS | 5 | C | CM | 2013 | 12900000 | 12900000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-219.12 |  |  |  |  | RELIABILITY | CONGESTION MITIGTN(O) | NON-ATTAINMENT AREAS STATEWIDE CMAQ FUNDED PROJECTS | 5 | C | CM | 2014 | 12900000 | 12900000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-224.06 |  |  |  |  | RELIABILITY | PAVEMENT REHAB-PRI(P) | PAVEMENT REHAB ON PRIMARY SYSTEM ROUTES IN KENTUCKY. | 5 | C | STP | 2013 | 35000000 | 35000000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-224.07 |  |  |  |  | RELIABILITY | PAVEMENT REHAB-PRI(P) | PAVEMENT REHAB ON PRIMARY SYSTEM ROUTES IN KENTUCKY. | 5 | C | STP | 2014 | 45000000 | 45000000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-302.08 |  |  |  |  | RELIABILITY | SIGNAL SYS IMPROVE(P) | SIGNAL SYSTEM UPGRADES. | 5 | C | STP | 2011 | 1000000 | 1000000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-327.06 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | STATEWIDE BRIDGE INSPECTION | 5 | C | BRO | 2011 | 2300000 | 2300000 | [6 empty] | 0
|  |  |  | BR | NBIS 161 | ZVARIOUS | 99-327.07 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | STATEWIDE BRIDGE INSPECTION | 5 | C | BRO | 2011 | 2300000 | 2300000 |  |  |  | OBLIGATED | 2300000 |  | 2300000 | 2011 | 3rd QUARTER | N/A
|  |  |  | BR | NBIS 161 | ZVARIOUS | 99-327.08 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | STATEWIDE BRIDGE INSPECTION | 5 | C | BRO | 2012 | 2300000 | 2300000 |  |  |  | OBLIGATED | 4600000 |  | 4600000 | 2012 | 3rd QUARTER | N/A
[6 empty] | ZVARIOUS | 99-327.09 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | STATEWIDE BRIDGE INSPECTION | 5 | C | BRO | 2013 | 2500000 | 2500000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-327.1 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | STATEWIDE BRIDGE INSPECTION | 5 | C | BRO | 2014 | 2500000 | 2500000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-333.06 |  |  |  |  | RELIABILITY | FOREST HIGHWAY(P) | STATEWIDE FOREST HIGHWAY FUNDS | 5 | C | FH | 2011 | 500000 | 500000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-333.07 |  |  |  |  | RELIABILITY | FOREST HIGHWAY(P) | STATEWIDE FOREST HIGHWAY FUNDS | 5 | C | FH | 2011 | 500000 | 500000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-333.08 |  |  |  |  | RELIABILITY | FOREST HIGHWAY(P) | STATEWIDE FOREST HIGHWAY FUNDS | 5 | C | FH | 2012 | 500000 | 500000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-333.09 |  |  |  |  | RELIABILITY | FOREST HIGHWAY(P) | STATEWIDE FOREST HIGHWAY FUNDS | 5 | C | FH | 2013 | 500000 | 500000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-333.1 |  |  |  |  | RELIABILITY | FOREST HIGHWAY(P) | STATEWIDE FOREST HIGHWAY FUNDS | 5 | C | FH | 2014 | 500000 | 500000 | [6 empty] | 0
|  |  |  | IM | 2653032 | ZVARIOUS | 99-337.05 |  |  |  |  | RELIABILITY | PAVEMENT REHAB-INT(P) | STATEWIDE I-STATE ROUTES | 5 | C | IM | 2011 | 20000000 | 20000000 |  |  |  | OBLIGATED |  | 5065242 | 5065242 | 2011 | 2nd QUARTER | N/A
[6 empty] | ZVARIOUS | 99-337.06 |  |  |  |  | RELIABILITY | PAVEMENT REHAB-INT(P) | STATEWIDE I-STATE ROUTES(10CCR) | 5 | C | IM | 2011 | 11000000 | 11000000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-337.07 |  |  |  |  | RELIABILITY | PAVEMENT REHAB-INT(P) | STATEWIDE I-STATE ROUTES | 5 | C | IM | 2013 | 40000000 | 40000000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-337.08 |  |  |  |  | RELIABILITY | PAVEMENT REHAB-INT(P) | STATEWIDE I-STATE ROUTES | 5 | C | IM | 2012 | 15000000 | 15000000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-337.09 |  |  |  |  | RELIABILITY | PAVEMENT REHAB-INT(P) | STATEWIDE I-STATE ROUTES | 5 | C | IM | 2014 | 20000000 | 20000000 | [6 empty] | 0
|  |  |  | BRZ | NBIS 162 | ZVARIOUS | 99-346.06 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | STATEWIDE OFF-SYSTEM BRIDGE INSPECTION | 5 | C | BRZ | 2011 | 800000 | 800000 |  |  |  | OBLIGATED | 800000 |  | 800000 | 2011 | 3rd QUARTER | N/A
[6 empty] | ZVARIOUS | 99-346.07 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | STATEWIDE OFF-SYSTEM BRIDGE INSPECTION | 5 | C | BRZ | 2011 | 800000 | 800000 | [6 empty] | 0
|  |  |  | BRZ | NBIS 162 | ZVARIOUS | 99-346.08 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | STATEWIDE OFF-SYSTEM BRIDGE INSPECTION | 5 | C | BRZ | 2012 | 800000 | 800000 |  |  |  | OBLIGATED | 1600000 |  | 1600000 | 2012 | 3rd QUARTER | N/A
[6 empty] | ZVARIOUS | 99-346.09 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | STATEWIDE OFF-SYSTEM BRIDGE INSPECTION | 5 | C | BRZ | 2013 | 900000 | 900000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-346.1 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | STATEWIDE OFF-SYSTEM BRIDGE INSPECTION | 5 | C | BRZ | 2014 | 900000 | 900000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-352.06 |  |  |  |  | SAFETY | SAFETY-RR PROTECTN(P) | RAIL PROTECTION ON VARIOUS ROUTES | 5 | C | RRP | 2011 | 1800000 | 1800000 | [6 empty] | 0
|  |  |  | STPS | 4312021 | ZVARIOUS | 99-352.07 |  |  |  |  | SAFETY | SAFETY-RR PROTECTN(P) | RAIL PROTECTION ON VARIOUS ROUTES | 5 | C | RRP | 2011 | 1800000 | 1800000 |  |  |  | OBLIGATED | 57829.87 |  | 57829.87 | 2011 | 1st QUARTER | N/A
[6 empty] | ZVARIOUS | 99-352.08 |  |  |  |  | SAFETY | SAFETY-RR PROTECTN(P) | RAIL PROTECTION ON VARIOUS ROUTES | 5 | C | RRP | 2012 | 1800000 | 1800000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-352.09 |  |  |  |  | SAFETY | SAFETY-RR PROTECTN(P) | RAIL PROTECTION ON VARIOUS ROUTES | 5 | C | RRP | 2013 | 1800000 | 1800000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-352.1 |  |  |  |  | SAFETY | SAFETY-RR PROTECTN(P) | RAIL PROTECTION ON VARIOUS ROUTES | 5 | C | RRP | 2014 | 1800000 | 1800000 | [6 empty] | 0
|  |  |  | HSIP | 9010040 | ZVARIOUS | 99-354.06 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | STATEWIDE SAFETY PROGRAM. | 5 | C | HES | 2011 | 13700000 | 13700000 |  |  |  | OBLIGATED | 200000 |  | 200000 | 2011 | 2nd QUARTER | N/A
[6 empty] | ZVARIOUS | 99-356.05 |  |  |  |  | SAFETY | SAFETY-RR SEPARATN(P) | RAIL SEPARATION ON VARIOUS ROUTES (PREFINANCE CONVERSION) | 5 | C | RRS | 2011 | 2000000 | 2000000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-356.06 |  |  |  |  | SAFETY | SAFETY-RR SEPARATN(P) | RAIL SEPARATION ON VARIOUS ROUTES (PREFINANCE CONVERSION) | 5 | C | RRS | 2011 | 2000000 | 2000000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-369.04 |  |  |  |  | RELIABILITY | PAVEMENT REHAB-PRI(P) | PAVEMENT REHABILITATION FOR VARIOUS NHS ROUTES IN KENTUCKY. | 5 | C | NH | 2013 | 40000000 | 40000000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-369.05 |  |  |  |  | RELIABILITY | PAVEMENT REHAB-PRI(P) | PAVEMENT REHABILITATION FOR VARIOUS NHS ROUTES IN KENTUCKY. | 5 | C | NH | 2014 | 10000000 | 10000000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-383.01 |  |  |  |  | SAFETY | GUARDRAIL REPLCMNT(P) | REPLACE TYPE 7/TEXAS TWIST GUARDRAIL ON INTERSTATES AND PARKWAYS. | 5 | C | NH | 2011 | 2000000 | 2000000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-383.02 |  |  |  |  | SAFETY | GUARDRAIL REPLCMNT(P) | REPLACE TYPE 7/TEXAS TWIST GUARDRAIL ON INTERSTATES AND PARKWAYS. | 5 | C | NH | 2011 | 2000000 | 2000000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-383.03 |  |  |  |  | SAFETY | GUARDRAIL REPLCMNT(P) | REPLACE TYPE 7/TEXAS TWIST GUARDRAIL ON INTERSTATES AND PARKWAYS. | 5 | C | NH | 2012 | 2000000 | 2000000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-383.04 |  |  |  |  | SAFETY | GUARDRAIL REPLCMNT(P) | REPLACE TYPE 7/TEXAS TWIST GUARDRAIL ON INTERSTATES AND PARKWAYS. | 5 | C | NH | 2013 | 2000000 | 2000000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-383.05 |  |  |  |  | SAFETY | GUARDRAIL REPLCMNT(P) | REPLACE TYPE 7/TEXAS TWIST GUARDRAIL ON INTERSTATES AND PARKWAYS. | 5 | C | NH | 2014 | 2000000 | 2000000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-388 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | OHIO RIVER BRIDGES FRACTURE CRITICAL. | 5 | C | BRO | 2011 | 1200000 | 1200000 | [6 empty] | 0
|  |  |  | BR | NBIS(163) | ZVARIOUS | 99-388.01 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | OHIO RIVER BRIDGES FRACTURE CRITICAL. | 5 | C | BRO | 2011 | 1200000 | 1200000 |  |  |  | OBLIGATED | 1655000 |  | 1655000 | 2011 | 4th QUARTER | N/A
[6 empty] | ZVARIOUS | 99-388.02 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | OHIO RIVER BRIDGES FRACTURE CRITICAL. | 5 | C | BRO | 2012 | 1200000 | 1200000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.010 | 2010-10-21 | ADD PROJECT TO STIP. NEW | DPR | 0185001 | ZVARIOUS | 99-392 |  |  |  |  | RELIABILITY | SCOPING STUDY(O) | UNIVERSITY OF KY ACADEMY FOR COMMUNITY TRANSPORTATION INNOVATION, WITH FOCUS ON REFINING NEW APPROACHES AND METHODS FOR ACCELERATING AND ENHANCING TRANSPORTATION DECISIONS. (2010BP) |  | P | KYD | 2011 | 999829 | 999829 |  |  |  | OBLIGATED | 999829 |  | 999829 | 2011 | 1st QUARTER | N/A
ADMINISTRATIVE MODIFICATION | 2010.022 | 2010-11-30 | ADD ARRA TIGER PROJECT TO STIP - APPALACHIAN REGIONAL SHORT-LINE RAIL PROJECT IN KENTUCKY. NEW |  |  | ZVARIOUS | 99-393 |  |  |  |  | RELIABILITY | RECONSTRUCTION(O) | APPALACHIAN REGIONAL SHORT-LINE RAIL PROJECT IN KENTUCKY: THIS GRANT WILL SUPPORT WORK FOR THE R. J. CORMAN APPALACHIAN REGIONAL SHORT-LINE PROJECT THROUGH VARIOUS COUNTIES IN KENTUCKY FOR REPLACING CROSS-TIES AND BALLAST; BRIDGE AND UNDERPASS REPAIRS; RESURFACING OF RAILS. |  | C | FS | 2011 | 12964443 | 12964443 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-900.04 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | DRIVER EDUCATION DRIVE SMART. | 5 | C | HES | 2011 | 2000000 | 2000000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-901.04 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | WORK ZONE SAFETY (REQ) | 5 | C | HES | 2011 | 100000 | 100000 | [6 empty] | 0
|  |  |  | HSIP HSIP | 9010039 9010042 | ZVARIOUS | 99-911 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | STATEWIDE SAFETY PROGRAM. | 5 | C | HES | 2011 | 16000000 | 16000000 |  |  |  | OBLIGATED | 625000 |  | 625000 | 2011 | 2nd QUARTER | N/A
|  |  |  | HSIP HSIP | 9010032 9010067 | ZVARIOUS | 99-911.01 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | STATEWIDE SAFETY PROGRAM. | 5 | C | HES | 2012 | 22100000 | 22100000 |  |  |  | OBLIGATED | 3546000 |  | 3546000 | 2012 | 4th QUARTER | N/A
[6 empty] | ZVARIOUS | 99-911.02 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | STATEWIDE SAFETY PROGRAM. | 5 | C | HES | 2013 | 22100000 | 22100000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-911.03 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | STATEWIDE SAFETY PROGRAM. | 5 | C | HES | 2014 | 22100000 | 22100000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-1063.06 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | STATEWIDE UNDERWATER BRIDGE INSPECTION | 5 | C | BRX | 2011 | 300000 | 300000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-1063.07 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | STATEWIDE UNDERWATER BRIDGE INSPECTION | 5 | C | BRX | 2011 | 300000 | 300000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-1063.08 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | STATEWIDE UNDERWATER BRIDGE INSPECTION | 5 | C | BRX | 2012 | 300000 | 300000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-1063.09 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | STATEWIDE UNDERWATER BRIDGE INSPECTION | 5 | C | BRX | 2013 | 350000 | 350000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-1063.1 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | STATEWIDE UNDERWATER BRIDGE INSPECTION | 5 | C | BRX | 2014 | 350000 | 350000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-1071 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | ESTABLISH STATEWIDE PROGRAM TO FUND BRIDGE SCOUR COUNTER-MEASURES FOR STATE-MAINTAINED BRIDGES | 5 | C | BRO | 2011 | 2000000 | 2000000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-1073.01 |  |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | STATEWIDE "BRO" FUNDS. | 5 | C | BRO | 2011 | 16000000 | 16000000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-1073.04 |  |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | STATEWIDE "BRO" FUNDS. | 5 | C | BRO | 2013 | 9500000 | 9500000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-1073.05 |  |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | STATEWIDE "BRO" FUNDS. | 5 | C | BRO | 2014 | 1500000 | 1500000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-1074.02 |  |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | STATEWIDE OFF SYSTEM BRIDGE REPLACEMENT PROJECTS. | 5 | C | BRZ | 2012 | 1500000 | 1500000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-1074.03 |  |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | STATEWIDE OFF SYSTEM BRIDGE REPLACEMENT PROJECTS. | 5 | C | BRZ | 2011 | 4000000 | 4000000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-1074.06 |  |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | STATEWIDE OFF SYSTEM BRIDGE REPLACEMENT PROJECTS. | 5 | C | BRZ | 2013 | 8600000 | 8600000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-1074.07 |  |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | STATEWIDE OFF SYSTEM BRIDGE REPLACEMENT PROJECTS. | 5 | C | BRZ | 2014 | 6000000 | 6000000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-1075 |  |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | STATEWIDE "BRX" FUNDS. | 5 | C | BRX | 2011 | 3500000 | 3500000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-1075.02 |  |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | STATEWIDE "BRX" FUNDS. | 5 | C | BRX | 2012 | 2000000 | 2000000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-1075.06 |  |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | STATEWIDE "BRX" FUNDS. | 5 | C | BRX | 2013 | 3700000 | 3700000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-1075.07 |  |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | STATEWIDE "BRX" FUNDS. | 5 | C | BRX | 2014 | 3000000 | 3000000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.036 | 2011-01-31 | ADD PROJECT TO STIP. BREAKOUT PROJECT FROM 99-195.13. NEW | STP | 3000905 | ZVARIOUS | 99-3004 | [6 empty] | CONDUCT INVENTORY OF OUTDOOR ADVERTISING DEVICES ALONG THE FEDERAL-AID HIGHWAY SYSTEM IN ACCORDANCE WITH THE FEDERAL HIGHWAY BEAUTIFICATION ACT AND AN AGREEMENT BETWEEN THE KENTUCKY TRANSPORTATION CABINET AND THE FEDERAL HIGHWAY ADMINISTRATION |  | D | STP | 2011 | 1212000 | 1212000 |  |  |  | OBLIGATED | 1212000 |  | 1212000 | 2011 | 2nd QUARTER | N/A
[6 empty] | ZVARIOUS | 99-8000 | I 275 | 22.605 | 1.582 | 13.858 | SAFETY | SAFETY(P) | BREAKOUT FROM ZVARIOUS 99-374 MEDIAN CABLE GUARD. (BOONE 6-2800) (10CCN) | 5 | C | IM | 2011 | 2790000 | 2790000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-8001 | WN 9007 | 6.22 | 26.42 | 32.64 | RELIABILITY | PAVEMENT REHAB-PRK(P) | BREAKOUT FROM ZVARIOUS 99-337. INTERMEDIATE OVERLAY ON WILLIAM NATCHER PARKWAY (BUTLER 3-2023). (10CCN) | 5 | C | NH | 2011 | 7720000 | 7720000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-8002 | I 275 | 1.836 | 73.55 | 75.386 | RELIABILITY | PAVEMENT REHAB-INT(P) | BREAKOUT FROM ZVARIOUS 99-337. (CAMPBELL 6-2020) (10CCN) | 5 | C | IM | 2011 | 1980000 | 1980000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-8004 | I 275 | 1.637 | 75.386 | 77.023 | RELIABILITY | PAVEMENT REHAB-INT(P) | BREAKOUT FROM ZVARIOUS 99-337. (CAMPBELL 6-2026) (10CCN) | 5 | C | IM | 2011 | 11500000 | 11500000 | [6 empty] | 0
|  |  | SEE ITEM NO. 2-2040 ABOVE FOR TIP AND STIP MODS |  |  | ZVARIOUS | 99-8010 | AU 9005 | 7.133 | 8.75 | 15.883 | RELIABILITY | PAVEMENT REHAB-PRK(P) | BREAKOUT FROM ZVARIOUS 99-337. (HENDERSON 2-2040) (10CCN) | 5 | C | NH | 2011 | 7000000 | 7000000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-8012 | I 71 | 5.55 | 0 | 5.55 | RELIABILITY | PAVEMENT REHAB-INT(P) | BREAKOUT FROM ZVARIOUS 99-337. (JEFFERSON 5-2053) (10CCN) | 5 | C | IM | 2011 | 5000000 | 5000000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-8013 | I 265 | 1.25 | 25.35 | 26.6 | RELIABILITY | PAVEMENT REHAB-INT(P) | BREAKOUT FROM ZVARIOUS 99-337. (JEFFERSON 5-2054) (10CCN) | 5 | C | IM | 2011 | 1040000 | 1040000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-8018 | I 275 | 3 | 1.054 | 1.582 | RELIABILITY | PAVEMENT REHAB-INT(P) | BREAKOUT FROM ZVARIOUS 99-337. (KENTON 6-2024) (10CCN) | 5 | C | IM | 2011 | 1670000 | 1670000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-8021 | I 24 | 0.911 | 29.543 | 30.454 | RELIABILITY | PAVEMENT REHAB-INT(P) | BREAKOUT FROM ZVARIOUS 99-337. (LIVINGSTON 1-2015) (10CCN) | 5 | C | IM | 2011 | 1560000 | 1560000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-8022 | I 24 | 2.578 | 26.558 | 29.136 | RELIABILITY | PAVEMENT REHAB-INT(P) | BREAKOUT FROM ZVARIOUS 99-337. (MARSHALL 1-2017) (10CCN) | 5 | C | IM | 2011 | 3000000 | 3000000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-8023 | I 24 | 0.9 | 16.27 | 17.32 | RELIABILITY | PAVEMENT REHAB-INT(P) | BREAKOUT FROM ZVARIOUS 99-337. (MCCRACKEN 1-2014) (10CCN) | 5 | C | IM | 2011 | 7800000 | 7800000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-8024 | BG 9002 | 10.7 | 24.24 | 34.94 | RELIABILITY | PAVEMENT REHAB-PRK(P) | BREAKOUT FROM ZVARIOUS 99-337. (NELSON 4-2038) (10CCN) | 5 | C | NH | 2011 | 4500000 | 4500000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-8025 | I 75 | 15.9 | 9.3 | 25.2 | RELIABILITY | SAFETY(P) | BREAKOUT FROM ZVARIOUS 99-374. MEDIAN CABLE GUARD. (WHITLEY 11-2800) (10CCN) | 5 | C | IM | 2011 | 2385000 | 2385000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-9064 | I 64 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | GARVEE BOND DEBT SERVICE FOR I-64. (JM03-FD53 "IM" COMPONENT) | 5 | C | IM | 2011 | 1600000 | 1600000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-9064.01 | I 64 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | GARVEE BOND DEBT SERVICE FOR I-64. (JM03-FD53 "NH" COMPONENT) | 5 | C | NH | 2011 | 2400000 | 2400000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-9064.02 | I 64 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | GARVEE BOND DEBT SERVICE FOR I-64. (JM03-FD53 "IM" COMPONENT) | 5 | C | IM | 2011 | 1600000 | 1600000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-9064.03 | I 64 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | GARVEE BOND DEBT SERVICE FOR I-64. (JM03-FD53 "NH" COMPONENT) | 5 | C | NH | 2011 | 2400000 | 2400000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-9064.04 | I 64 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | GARVEE BOND DEBT SERVICE FOR I-64. (JM03-FD53 "IM" COMPONENT) | 5 | C | IM | 2012 | 1600000 | 1600000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-9064.05 | I 64 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | GARVEE BOND DEBT SERVICE FOR I-64. (JM03-FD53 "NH" COMPONENT) | 5 | C | NH | 2012 | 2400000 | 2400000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-9064.06 | I 64 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | GARVEE BOND DEBT SERVICE FOR I-64. (JM03-FD53 "IM" COMPONENT) | 5 | C | IM | 2013 | 1600000 | 1600000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-9064.07 | I 64 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | GARVEE BOND DEBT SERVICE FOR I-64. (JM03-FD53 "NH" COMPONENT) | 5 | C | NH | 2013 | 2400000 | 2400000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-9064.08 | I 64 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | GARVEE BOND DEBT SERVICE FOR I-64. (JM03-FD53 "IM" COMPONENT) | 5 | C | IM | 2014 | 1600000 | 1600000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-9064.09 | I 64 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | GARVEE BOND DEBT SERVICE FOR I-64. (JM03-FD53 "NH" COMPONENT) | 5 | C | NH | 2014 | 2400000 | 2400000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-9065.06 | I 65 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | GARVEE BOND DEBT SERVICE FOR I-65. (JM01-FD53 "IM" COMPONENT) | 5 | C | IM | 2011 | 8400000 | 8400000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-9065.07 | I 65 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | GARVEE BOND DEBT SERVICE FOR I-65. (JM01-FD53 "NH" COMPONENT) | 5 | C | NH | 2011 | 12500000 | 12500000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-9065.08 | I 65 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | GARVEE BOND DEBT SERVICE FOR I-65. (JM01-FD53 "IM" COMPONENT) | 5 | C | IM | 2011 | 8400000 | 8400000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-9065.09 | I 65 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | GARVEE BOND DEBT SERVICE FOR I-65. (JM01-FD53 "NH" COMPONENT) | 5 | C | NH | 2011 | 12500000 | 12500000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-9065.1 | I 65 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | GARVEE BOND DEBT SERVICE FOR I-65. (JM01-FD53 "IM" COMPONENT) | 5 | C | IM | 2012 | 8400000 | 8400000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-9065.11 | I 65 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | GARVEE BOND DEBT SERVICE FOR I-65. (JM01-FD53 "NH" COMPONENT) | 5 | C | NH | 2012 | 12500000 | 12500000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-9065.12 | I 65 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | GARVEE BOND DEBT SERVICE FOR I-65. (JM01-FD53 "IM" COMPONENT) | 5 | C | IM | 2013 | 8400000 | 8400000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-9065.13 | I 65 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | GARVEE BOND DEBT SERVICE FOR I-65. (JM01-FD53 "NH" COMPONENT) | 5 | C | NH | 2013 | 12500000 | 12500000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-9065.14 | I 65 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | GARVEE BOND DEBT SERVICE FOR I-65. (JM01-FD53 "IM" COMPONENT) | 5 | C | IM | 2014 | 8400000 | 8400000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-9065.15 | I 65 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | GARVEE BOND DEBT SERVICE FOR I-65. (JM01-FD53 "NH" COMPONENT) | 5 | C | NH | 2014 | 12500000 | 12500000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-9068.00 | US 68 |  |  |  | SAFETY | BRIDGE REPLACEMENT(P) | US 68/KY 80 LAKE BARKLEY AND KENTUCKY LAKE GARVEE BOND DEBT SERVICE (BRO).(079B00023N, 111B00020N) (JM05-FD53 "BRO" COMPONENT) | 5 | C | BRO | 2013 | 17500000 | 17500000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-9068.01 | US 68 |  |  |  | SAFETY | BRIDGE REPLACEMENT(P) | US 68/KY 80 LAKE BARKLEY AND KENTUCKY LAKE GARVEE BOND DEBT SERVICE (BRO).(079B00023N, 111B00020N) (JM05-FD53 "BRO" COMPONENT) | 5 | C | BRO | 2014 | 17500000 | 17500000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-9068.60 | US 68 |  |  |  | SAFETY | BRIDGE REPLACEMENT(P) | US 68/KY 80 LAKE BARKLEY AND KENTUCKY LAKE GARVEE BOND DEBT SERVICE (STP).(079B00023N, 111B00020N) (JM05-FD53 "STP" COMPONENT) | 5 | C | STP | 2013 | 17500000 | 17500000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-9068.61 | US 68 |  |  |  | SAFETY | BRIDGE REPLACEMENT(P) | US 68/KY 80 LAKE BARKLEY AND KENTUCKY LAKE GARVEE BOND DEBT SERVICE (STP).(079B00023N, 111B00020N) (JM05-FD53 "STP" COMPONENT) | 5 | C | STP | 2014 | 17500000 | 17500000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-9075.06 | I 75 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | GARVEE BOND DEBT SERVICE FOR I-75. (JM02-FD53 "IM" COMPONENT) | 5 | C | IM | 2011 | 7800000 | 7800000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-9075.07 | I 75 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | GARVEE BOND DEBT SERVICE FOR I-75. (JM02-FD53 "NH" COMPONENT) | 5 | C | NH | 2011 | 11700000 | 11700000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-9075.08 | I 75 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | GARVEE BOND DEBT SERVICE FOR I-75. (JM02-FD53 "IM" COMPONENT) | 5 | C | IM | 2011 | 7800000 | 7800000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-9075.09 | I 75 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | GARVEE BOND DEBT SERVICE FOR I-75. (JM02-FD53 "NH" COMPONENT) | 5 | C | NH | 2011 | 11700000 | 11700000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-9075.1 | I 75 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | GARVEE BOND DEBT SERVICE FOR I-75. (JM02-FD53 "IM" COMPONENT) | 5 | C | IM | 2012 | 7800000 | 7800000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-9075.11 | I 75 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | GARVEE BOND DEBT SERVICE FOR I-75. (JM02-FD53 "NH" COMPONENT) | 5 | C | NH | 2012 | 11700000 | 11700000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-9075.12 | I 75 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | GARVEE BOND DEBT SERVICE FOR I-75. (JM02-FD53 "IM" COMPONENT) | 5 | C | IM | 2013 | 7800000 | 7800000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-9075.13 | I 75 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | GARVEE BOND DEBT SERVICE FOR I-75. (JM02-FD53 "NH" COMPONENT) | 5 | C | NH | 2013 | 11700000 | 11700000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-9075.14 | I 75 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | GARVEE BOND DEBT SERVICE FOR I-75. (JM02-FD53 "IM" COMPONENT) | 5 | C | IM | 2014 | 7800000 | 7800000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-9075.15 | I 75 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | GARVEE BOND DEBT SERVICE FOR I-75. (JM02-FD53 "NH" COMPONENT) | 5 | C | NH | 2014 | 11700000 | 11700000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-9659 | I 65 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | GARVEE BOND DEBT SERVICE FOR LOUISVILLE BRIDGES PROJECT. (JZ1-FD53 "IM" COMPONENT) | 5 | C | IM | 2011 | 600000 | 600000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-9659.01 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | GARVEE BOND DEBT SERVICE FOR LOUISVILLE BRIDGES PROJECT. (JZ1-FD53 "NH" COMPONENT) | 5 | C | NH | 2011 | 1300000 | 1300000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-9659.02 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | GARVEE BOND DEBT SERVICE FOR LOUISVILLE BRIDGES PROJECT. (JZ1-FD53 "STP" COMPONENT) | 5 | C | STP | 2011 | 100000 | 100000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-9659.03 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | GARVEE BOND DEBT SERVICE FOR LOUISVILLE BRIDGES PROJECT. (JZ1-FD53 "IM" COMPONENT) | 5 | C | IM | 2011 | 1300000 | 1300000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-9659.04 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | GARVEE BOND DEBT SERVICE FOR LOUISVILLE BRIDGES PROJECT. (JZ1-FD53 "NH" COMPONENT) | 5 | C | NH | 2011 | 2600000 | 2600000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-9659.05 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | GARVEE BOND DEBT SERVICE FOR LOUISVILLE BRIDGES PROJECT. (JZ1-FD53 "STP" COMPONENT) | 5 | C | STP | 2011 | 100000 | 100000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-9659.06 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | GARVEE BOND DEBT SERVICE FOR LOUISVILLE BRIDGES PROJECT. (JZ1-FD53 "IM" COMPONENT) | 5 | C | IM | 2012 | 1300000 | 1300000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-9659.07 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | GARVEE BOND DEBT SERVICE FOR LOUISVILLE BRIDGES PROJECT. (JZ1-FD53 "NH" COMPONENT) | 5 | C | NH | 2012 | 2600000 | 2600000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-9659.08 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | GARVEE BOND DEBT SERVICE FOR LOUISVILLE BRIDGES PROJECT. (JZ1-FD53 "STP" COMPONENT) | 5 | C | STP | 2012 | 100000 | 100000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-9659.09 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | GARVEE BOND DEBT SERVICE FOR LOUISVILLE BRIDGES PROJECT. (JZ1-FD53 "IM" COMPONENT) | 5 | C | IM | 2013 | 1300000 | 1300000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-9659.10 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | GARVEE BOND DEBT SERVICE FOR LOUISVILLE BRIDGES PROJECT. (JZ1-FD53 "NH" COMPONENT) | 5 | C | NH | 2013 | 2600000 | 2600000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-9659.11 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | GARVEE BOND DEBT SERVICE FOR LOUISVILLE BRIDGES PROJECT. (JZ1-FD53 "STP" COMPONENT) | 5 | C | STP | 2013 | 100000 | 100000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-9659.12 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | GARVEE BOND DEBT SERVICE FOR LOUISVILLE BRIDGES PROJECT. (JZ1-FD53 "IM" COMPONENT) | 5 | C | IM | 2014 | 1300000 | 1300000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-9659.13 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | GARVEE BOND DEBT SERVICE FOR LOUISVILLE BRIDGES PROJECT. (JZ1-FD53 "NH" COMPONENT) | 5 | C | NH | 2014 | 2600000 | 2600000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-9659.14 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | GARVEE BOND DEBT SERVICE FOR LOUISVILLE BRIDGES PROJECT. (JZ1-FD53 "STP" COMPONENT) | 5 | C | STP | 2014 | 100000 | 100000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-9659.6 |  |  |  |  | RELIABILITY | RECONSTRUCTION(O) | GARVEE BOND DEBT SERVICE FOR LOUISVILLE BRIDGES PROJECT. (JZ2-FD53 "IM" COMPONENT) | 5 | C | IM | 2012 | 7700000 | 7700000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-9659.61 |  |  |  |  | RELIABILITY | RECONSTRUCTION(O) | GARVEE BOND DEBT SERVICE FOR LOUISVILLE BRIDGES PROJECT. (JZ2-FD53 "NH" COMPONENT) | 5 | C | NH | 2012 | 9400000 | 9400000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-9659.62 |  |  |  |  | RELIABILITY | RECONSTRUCTION(O) | GARVEE BOND DEBT SERVICE FOR LOUISVILLE BRIDGES PROJECT. (JZ2-FD53 "IM" COMPONENT) | 5 | C | IM | 2013 | 7700000 | 7700000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-9659.63 |  |  |  |  | RELIABILITY | RECONSTRUCTION(O) | GARVEE BOND DEBT SERVICE FOR LOUISVILLE BRIDGES PROJECT. (JZ2-FD53 "NH" COMPONENT) | 5 | C | NH | 2013 | 9400000 | 9400000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-9659.64 |  |  |  |  | RELIABILITY | RECONSTRUCTION(O) | GARVEE BOND DEBT SERVICE FOR LOUISVILLE BRIDGES PROJECT. (JZ2-FD53 "IM" COMPONENT) | 5 | C | IM | 2014 | 7700000 | 7700000 | [6 empty] | 0
[6 empty] | ZVARIOUS | 99-9659.65 |  |  |  |  | RELIABILITY | RECONSTRUCTION(O) | GARVEE BOND DEBT SERVICE FOR LOUISVILLE BRIDGES PROJECT. (JZ2-FD53 "NH" COMPONENT) | 5 | C | NH | 2014 | 9400000 | 9400000 | [6 empty] | 0
ADMINISTRATIVE MODIFICATION | 2010.026 | 2010-12-17 | ADD TO STIP. TCSP PROJECT NO. 10KY002. NEW | TCSP | 10KY002 | ZVARIOUS | 2-85 |  |  |  |  | RELIABILITY | SCOPING STUDY(O) | SCOPING STUDY ON AUDUBON AND NATCHER PARKWAYS IN WESTERN KENTUCKY, KY |  | D | TCSP | 2011 | 375000 | 375000 |  |  |  | OBLIGATED | 353707 |  | 353707 | 2011 | 1st QUARTER | N/A

## STATE-FUNDED REG SIGNIFICANT
MODIFICATION OR AMENDMENT | STIP ADMINISTRATIVE MODIFICATION OR AMENDMENT NUMBER | APPROVAL DATE | COMMENTS | COUNTY | DISTRICT | ITEM | ID NUMBER | ROUTE | BEG MILEPOINT | END MILEPOINT | PRIORITY | TYPE OF WORK | DESCRIPTION | FUNDING | PHASE | FY | AMOUNT | STATUS OF STATE FUNDS | CURRENT AMOUNT OF STATE FUNDS AUTHORIZED | FISCAL YEAR OF INITIAL AUTHORIZATION OF STATE FUNDS
|  |  |  | BOONE | 6 | 158 | 6-158 | KY-536 | 10.4 | 13.4 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT KY-536 TO A 5-LANE URBAN SECTION FROM 1500' WEST OF US-42 TO I-75 (MP 10.4 TO MP 13.4). (DOES NOT INCLUDE INTERCHANGE RECONSTRUCTION) (00CCR) | SP | R | 2010 | 5780000
|  |  |  | BOONE | 6 | 158 | 6-158 | KY-536 | 10.4 | 13.4 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT KY-536 TO A 5-LANE URBAN SECTION FROM 1500' WEST OF US-42 TO I-75 (MP 10.4 TO MP 13.4). (DOES NOT INCLUDE INTERCHANGE RECONSTRUCTION) (00CCR) | SP | U | 2010 | 2600000
|  |  |  | BOONE | 6 | 158 | 6-158 | KY-536 | 10.4 | 13.4 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT KY-536 TO A 5-LANE URBAN SECTION FROM 1500' WEST OF US-42 TO I-75 (MP 10.4 TO MP 13.4). (DOES NOT INCLUDE INTERCHANGE RECONSTRUCTION) (00CCR) | SP | C | 2012 | 16880000
|  |  |  | BOONE | 6 | 351.1 | 6-351.1 | US-25 | 4.859 | 5.085 | RELIABILITY | MAJOR WIDENING(O) | DRY RIDGE-FLORENCE ROAD; 5-LANE US-25 FROM RICHWOOD ROAD TO WINNING COLORS DRIVE WITH GRADE SEPARATION OF KY-338 AT US-25 & RR OVERPASS FOR KY-338. (2004BOPC)(2006BOPC) | SP | D | 2010 | 610000
|  |  |  | BOONE | 6 | 351.2 | 6-351.2 | US-25 | 5.085 | 7.431 | RELIABILITY | MAJOR WIDENING(O) | DRY RIDGE-FLORENCE ROAD; 5-LANE US-25 FROM WINNING COLORS DRIVE TO BEESOM DRIVE. (2006BOPC) | SP | D | 2010 | 1520000
|  |  |  | BOONE | 6 | 351.3 | 6-351.3 | US-25 | 7.431 | 7.81 | RELIABILITY | MAJOR WIDENING(O) | DRY RIDGE-FLORENCE ROAD; 5-LANE US-25 FROM BEESOM DRIVE TO ARISTOCRAT DRIVE WITH GRADE SEPARATION OF KY 536 AT US 25. (2006BOPC) | SP | D | 2010 | 900000
|  |  |  | BOONE | 6 | 351.4 | 6-351.4 | US-25 | 7.81 | 9.18 | RELIABILITY | MAJOR WIDENING(O) | DRY RIDGE-FLORENCE ROAD; 5-LANE US-25 FROM ARISTOCRAT DRIVE TO RR SPUR CROSSING. (2004BOPC)(2006BOPC) | SP | D | 2010 | 910000
|  |  |  | BOONE | 6 | 351.5 | 6-351.5 | US-25 | 0 | 0 | RELIABILITY | RECONSTRUCTION(O) | DRY RIDGE-FLORENCE ROAD; 3-LANE US-25 FRONTAGE ROAD FROM 0.11 MILE SOUTH OF KY 338 TO WINNING COLORS. (2006BOPC) | SP | D | 2010 | 100000
|  |  |  | BOONE | 6 | 8001.21 | 6-8001.21 | KY-237 | 3.166 | 5.37 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT AND WIDEN KY-237 FROM WOODCREEK DRIVE TO ROGERS LANE (MIDDLE SECTION) (PRIORITY 3). (00CCN)(2004BOPC)(08CCR) | SP | R | 2010 | 4730000
|  |  |  | BOONE | 6 | 8001.21 | 6-8001.21 | KY-237 | 3.166 | 5.37 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT AND WIDEN KY-237 FROM WOODCREEK DRIVE TO ROGERS LANE (MIDDLE SECTION) (PRIORITY 3). (00CCN)(2004BOPC)(08CCR) | SP | U | 2010 | 2790000
|  |  |  | BOONE | 6 | 8001.21 | 6-8001.21 | KY-237 | 3.166 | 5.37 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT AND WIDEN KY-237 FROM WOODCREEK DRIVE TO ROGERS LANE (MIDDLE SECTION) (PRIORITY 3). (00CCN)(2004BOPC)(08CCR) | SP | C | 2012 | 7800000
|  |  |  | BOONE | 6 | 8001.25 | 6-8001.25 | KY-237 | 5.37 | 6.262 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT AND WIDEN KY-237 FROM ROGERS LANE TO KY-18 (PRIORITY SECTION). (00CCN)(2004BOPC)(08CCR) | SPP | D | 2010 | 700000
|  |  |  | BOONE | 6 | 8413 | 6-8413 | KY-1829 | 1.5 | 1.93 | RELIABILITY | MAJOR WIDENING(O) | WIDEN INDUSTRIAL ROAD (KY-1829) FROM US-42 IN FLORENCE TO TURKEYFOOT ROAD. (FUNDS TRANSFERRED FROM 6-300.00)(TO BE ADMINISTERED BY BOONE COUNTY AS PER AGREEMENT)(2002BOP) (08CCN) | SPB | C | 2010 | 8150000
|  |  |  | BOYD | 9 | 8400 | 9-8400 | US-60 | 0.2 | 4.02 | RELIABILITY | CONGESTION MITIGTN(O) | US 60 FROM I-64 AT INTERCHANGE 181 (MP 0.2) EXTENDING NORTHERLY TO THE KY 180 (MP 4.02) INTERSECTION AT CANNONSBURG CONSISTING OF 4 DRIVING LANES WITH WIDE, DGA SHOULDERS. (08CCN) | SPB | R | 2010 | 4700000
|  |  |  | BOYD | 9 | 8400 | 9-8400 | US-60 | 0.2 | 4.02 | RELIABILITY | CONGESTION MITIGTN(O) | US 60 FROM I-64 AT INTERCHANGE 181 (MP 0.2) EXTENDING NORTHERLY TO THE KY 180 (MP 4.02) INTERSECTION AT CANNONSBURG CONSISTING OF 4 DRIVING LANES WITH WIDE, DGA SHOULDERS. (08CCN) | SB2 | U | 2011 | 2500000
|  |  |  | BOYD | 9 | 8400 | 9-8400 | US-60 | 0.2 | 4.02 | RELIABILITY | CONGESTION MITIGTN(O) | US 60 FROM I-64 AT INTERCHANGE 181 (MP 0.2) EXTENDING NORTHERLY TO THE KY 180 (MP 4.02) INTERSECTION AT CANNONSBURG CONSISTING OF 4 DRIVING LANES WITH WIDE, DGA SHOULDERS. (08CCN) | SP | C | 2012 | 20000000
|  |  |  | BULLITT | 5 | 117.1 | 5-117.1 | KY-61 | 14.43 | 16.667 | RELIABILITY | MAJOR WIDENING(O) | KY-61 BEGINS SOUTH OF KY-44 AND ENDS NORTH OF THE NEWLY CONSTRUCTED CONESTOGA PARKWAY. (CONSTRUCTION SEQUENCE 3) | SP | C | 2011 | 17200000
|  |  |  | BULLITT | 5 | 117.2 | 5-117.2 | KY-61 | 16.667 | 17.88 | RELIABILITY | MAJOR WIDENING(O) | KY-61 BEGINS NORTH OF CONESTOGA PARKWAY AND ENDS AT EXISTING KY-61 SOUTH OF BROOKS RUN CREEK. (CONSTRUCTION SEQUENCE 2) | SP | C | 2011 | 11610000
|  |  |  | BULLITT | 5 | 117.31 | 5-117.31 | KY-61 | 17.88 | 19.33 | RELIABILITY | MAJOR WIDENING(O) | KY-61 BEGINS AT EXISTING KY-61 SOUTH OF BROOKS RUN CREEK AND ENDS SOUTH OF JOHN HARPER HIGHWAY (BROOKS ROAD) (2006BOPC) | SP | C | 2010 | 12720000
|  |  |  | BULLITT | 5 | 150.1 | 5-150.1 | KY-44 | 17.6 | 18.2 | SAFETY | SAFETY(P) | RECONSTRUCT KY-44 AT BELLS MILL ROAD. (06CCN) | SPP | R | 2010 | 370000
|  |  |  | BULLITT | 5 | 150.1 | 5-150.1 | KY-44 | 17.6 | 18.2 | SAFETY | SAFETY(P) | RECONSTRUCT KY-44 AT BELLS MILL ROAD. (06CCN) | SPP | U | 2010 | 560000
|  |  |  | BULLITT | 5 | 150.1 | 5-150.1 | KY-44 | 17.6 | 18.2 | SAFETY | SAFETY(P) | RECONSTRUCT KY-44 AT BELLS MILL ROAD. (06CCN) | SP | C | 2012 | 850000
|  |  |  | BULLITT | 5 | 150.2 | 5-150.2 | KY-44 | 18.3 | 18.8 | SAFETY | SAFETY(P) | RECONSTRUCT KY-44 AT BOGARD/LLOYD LANE. (06CCN) | SPP | R | 2010 | 710000
|  |  |  | BULLITT | 5 | 150.2 | 5-150.2 | KY-44 | 18.3 | 18.8 | SAFETY | SAFETY(P) | RECONSTRUCT KY-44 AT BOGARD/LLOYD LANE. (06CCN) | SPP | U | 2010 | 800000
|  |  |  | BULLITT | 5 | 150.2 | 5-150.2 | KY-44 | 18.3 | 18.8 | SAFETY | SAFETY(P) | RECONSTRUCT KY-44 AT BOGARD/LLOYD LANE. (06CCN) | SP | C | 2012 | 2030000
|  |  |  | BULLITT | 5 | 150.3 | 5-150.3 | KY-44 | 20.8 | 21.3 | SAFETY | SAFETY(P) | RECONSTRUCT KY-44 AT ARMSTRONG/FISHER LANE. (06CCN) | SPP | R | 2010 | 1500000
|  |  |  | BULLITT | 5 | 150.3 | 5-150.3 | KY-44 | 20.8 | 21.3 | SAFETY | SAFETY(P) | RECONSTRUCT KY-44 AT ARMSTRONG/FISHER LANE. (06CCN) | SPP | U | 2010 | 410000
|  |  |  | BULLITT | 5 | 150.3 | 5-150.3 | KY-44 | 20.8 | 21.3 | SAFETY | SAFETY(P) | RECONSTRUCT KY-44 AT ARMSTRONG/FISHER LANE. (06CCN) | SP | C | 2012 | 1120000
|  |  |  | BULLITT | 5 | 347.5 | 5-347.5 | KY-44 | 23.39 | 25.5 | RELIABILITY | RECONSTRUCTION(O) | MT. WASHINGTON-TAYLORSVILLE RD; RECONSTRUCT KY 44 FROM MT. WASHINGTON BYPASS EAST 2.0 MILES (04CCN) | SP | R | 2010 | 890000
ADMINISTRATIVE MODIFICATION | 2010.095 | 2011-07-05 | KIPDA TIP AMENDMENT #1. KIPDA ID 493. CHANGE FY AND DESCRIPTION. MOD | BULLITT | 5 | 347.5 | 5-347.5 | KY-44 | 23.39 | 25.5 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT AND ADD CENTER TURN LANE (2 TO 3 LANES) FROM MOUNT WASHINGTON BYPASS TO 2.0 MILES EAST OF MOUNT WASHINGTON BYPASS. | SP | R | 2011 | 890000
|  |  |  | BULLITT | 5 | 347.5 | 5-347.5 | KY-44 | 23.39 | 25.5 | RELIABILITY | RECONSTRUCTION(O) | MT. WASHINGTON-TAYLORSVILLE RD; RECONSTRUCT KY 44 FROM MT. WASHINGTON BYPASS EAST 2.0 MILES (04CCN) | SP | U | 2010 | 1090000
ADMINISTRATIVE MODIFICATION | 2010.095 | 2011-07-05 | KIPDA TIP AMENDMENT #1. KIPDA ID 493. CHANGE FY AND DESCRIPTION. MOD | BULLITT | 5 | 347.5 | 5-347.5 | KY-44 | 23.39 | 25.5 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT AND ADD CENTER TURN LANE (2 TO 3 LANES) FROM MOUNT WASHINGTON BYPASS TO 2.0 MILES EAST OF MOUNT WASHINGTON BYPASS. | SP | U | 2011 | 1090000
|  |  |  | BULLITT | 5 | 391.1 | 5-391.1 | KY-480 | 0 | 0 | RELIABILITY | RECONSTRUCTION(O) | WIDEN CEDAR GROVE ROAD (KY-480) FROM THE NORTHBOUND I-65 RAMPS TO CEDAR GROVE ELEMENTARY SCHOOL. )AS PER AGREEMENT, KYTC WILL REIMBURSE THE CITY OF SHEPERDSVILLE UP TO $5.7M FOR PROJECT ACTIVITIES) (KYTC WILL LET PROJECT)(06CCR)(2006BOPC) PROJECT IS ALREAD | SP | C | 2011 | 1000000
|  |  |  | CAMPBELL | 6 | 352 | 6-352 | KY-536 | 0 | 0 | RELIABILITY | NEW ROUTE(O) | EXTEND PROPOSED POND CREEK ROAD FROM US-27 TO AA HIGHWAY VIA PORTION OF KY 10/KY 1997 CORRIDOR (NEW KY-536)(04CCN) | SP | R | 2010 | 4970000
|  |  |  | CAMPBELL | 6 | 352 | 6-352 | KY-536 | 0 | 0 | RELIABILITY | NEW ROUTE(O) | EXTEND PROPOSED POND CREEK ROAD FROM US-27 TO AA HIGHWAY VIA PORTION OF KY 10/KY 1997 CORRIDOR (NEW KY-536)(04CCN) | SP | U | 2010 | 5430000
|  |  |  | CAMPBELL | 6 | 8101.01 | 6-8101.01 | KY-9 | 0 | 0 | RELIABILITY | NEW ROUTE(O) | KY-9 RECONSTRUCTION ALONG A NEW ROUTE FROM MP 21.643 TO KY-8 NEAR THE 4TH STREET BRIDGE. (02CCN)(2004BOPC)(08CCR) | SB2 | R | 2010 | 10500000
|  |  |  | CAMPBELL | 6 | 8101.01 | 6-8101.01 | KY-9 | 0 | 0 | RELIABILITY | NEW ROUTE(O) | KY-9 RECONSTRUCTION ALONG A NEW ROUTE FROM MP 21.643 TO KY-8 NEAR THE 4TH STREET BRIDGE. (02CCN)(2004BOPC)(08CCR) | SPB | C | 2011 | 9200000
|  |  |  | CAMPBELL | 6 | 8104 | 6-8104 | I-471 | 4.722 | 4.822 | RELIABILITY | NEW ROUTE(O) | CONSTRUCT NEW I-471 SOUTHBOUND OFF-RAMP AT KY-8 (SEE ALSO 6-183.00). (02CCN)(06CCN) | SP | R | 2010 | 2440000
|  |  |  | CHRISTIAN | 2 | 136 | 2-136 | KY-1682 | 0 | 0 | RELIABILITY | NEW ROUTE(O) | EXTEND KY-1682 FROM THE E.T. BREATHITT PARKWAY TO US-68/KY-80 EAST OF HOPKINSVILLE (HOPKINSVILLE NORTHEAST BYPASS). | SP | D | 2010 | 2710000
|  |  |  | CHRISTIAN | 2 | 311.1 | 2-311.1 | US-41 | 4.427 | 12.157 | SAFETY | SAFETY(P) | MODERNIZE US-41A FROM I-24 TO LOVERS LANE BY ADDING SHOULDERS AND TURN LANES. (PRIORITY SECTION)(08CCR) | SPB | R | 2010 | 2210000
|  |  |  | CHRISTIAN | 2 | 311.1 | 2-311.1 | US-41 | 4.427 | 12.157 | SAFETY | SAFETY(P) | MODERNIZE US-41A FROM I-24 TO LOVERS LANE BY ADDING SHOULDERS AND TURN LANES. (PRIORITY SECTION)(08CCR) | SPB | U | 2010 | 7670000
|  |  |  | CHRISTIAN | 2 | 311.1 | 2-311.1 | US-41 | 4.427 | 12.157 | SAFETY | SAFETY(P) | MODERNIZE US-41A FROM I-24 TO LOVERS LANE BY ADDING SHOULDERS AND TURN LANES. (PRIORITY SECTION)(08CCR) | SPP | C | 2012 | 15750000
|  |  |  | CHRISTIAN | 2 | 311.2 | 2-311.2 | US-41 | 12.157 | 13.19 | SAFETY | SAFETY(P) | CORRIDOR MOBILITY IMPROVEMENTS TO US-41A BETWEEN LOVERS LANE AND SIVLEY ROAD. | SPP | R | 2011 | 790000
|  |  |  | CHRISTIAN | 2 | 311.2 | 2-311.2 | US-41 | 12.157 | 13.19 | SAFETY | SAFETY(P) | CORRIDOR MOBILITY IMPROVEMENTS TO US-41A BETWEEN LOVERS LANE AND SIVLEY ROAD. | SPP | U | 2011 | 840000
|  |  |  | CHRISTIAN | 2 | 311.2 | 2-311.2 | US-41 | 12.157 | 13.19 | SAFETY | SAFETY(P) | CORRIDOR MOBILITY IMPROVEMENTS TO US-41A BETWEEN LOVERS LANE AND SIVLEY ROAD. | SP | C | 2012 | 5850000
|  |  |  | CHRISTIAN | 2 | 8509 | 2-8509 | 0 | 0 | 0 | RELIABILITY | NEW ROUTE(O) | EXTEND MURRAY STATE UNIVERSITY'S JAMES E. BRUCE CONVENTION CENTER DRIVE. (08CCN) | SPB | C | 2010 | 373000
|  |  |  | DAVIESS | 2 | 221 | 2-221 | KY-2121 | 0 | 1.78 | RELIABILITY | MAJOR WIDENING(O) | WIDEN SOUTHTOWN BLVD. FROM CARTER ROAD (KY-2698) TO US-431 IN OWENSBORO | SPP | C | 2012 | 16230000
|  |  |  | DAVIESS | 2 | 8300 | 2-8300 | KY-54 | 4.51 | 8 | RELIABILITY | MAJOR WIDENING(O) | WIDENING KY-54 FROM THE US-60 BYPASS TO WHITESVILLE FROM MILEPOST 4.51 TO MILEPOST 8.0. (06CCN) | SPP | D | 2010 | 2820000
|  |  |  | DAVIESS | 2 | 8300 | 2-8300 | KY-54 | 4.51 | 8 | RELIABILITY | MAJOR WIDENING(O) | WIDENING KY-54 FROM THE US-60 BYPASS TO WHITESVILLE FROM MILEPOST 4.51 TO MILEPOST 8.0. (06CCN) | SP | R | 2011 | 7700000
|  |  |  | DAVIESS | 2 | 8300 | 2-8300 | KY-54 | 4.51 | 8 | RELIABILITY | MAJOR WIDENING(O) | WIDENING KY-54 FROM THE US-60 BYPASS TO WHITESVILLE FROM MILEPOST 4.51 TO MILEPOST 8.0. (06CCN) | SP | U | 2012 | 17040000
ADMINISTRATIVE MODIFICATION | 2010.045 | 2011-03-02 | TIP AMENDMENT #1. REMOVE U AND C PHASES FROM TIP AND STIP. C PHASE IS IN REG SIGNIFICANT SECTION IN STIP. AMOUNT WAS $17,650,000. MOD | FAYETTE | 7 | 113 | 7-113 | KY-4 | 8.731 | 10.015 | RELIABILITY | MAJOR WIDENING(O) | NEW CIRCLE ROAD REHAB AND WIDENING FROM VERSAILLES ROAD TO NEAR GEORGETOWN ROAD. | SB2 | C | 2012
|  |  |  | FAYETTE | 7 | 122.1 | 7-122.1 | US-25 | 18.264 | 21.415 | RELIABILITY | MAJOR WIDENING(O) | RECONSTRUCT/WIDEN US-25 FROM SPURR ROAD SOUTH OF I-75 TO 1400 FEET SOUTH OF IRONWORKS ROAD. (06CCN)(08CCR) | SPB | R | 2010 | 11030000
|  |  |  | FAYETTE | 7 | 122.1 | 7-122.1 | US-25 | 18.264 | 21.415 | RELIABILITY | MAJOR WIDENING(O) | RECONSTRUCT/WIDEN US-25 FROM SPURR ROAD SOUTH OF I-75 TO 1400 FEET SOUTH OF IRONWORKS ROAD. (06CCN)(08CCR) | SP | U | 2010 | 3250000
|  |  |  | FAYETTE | 7 | 122.1 | 7-122.1 | US-25 | 18.264 | 21.415 | RELIABILITY | MAJOR WIDENING(O) | RECONSTRUCT/WIDEN US-25 FROM SPURR ROAD SOUTH OF I-75 TO 1400 FEET SOUTH OF IRONWORKS ROAD. (06CCN)(08CCR) | SP | C | 2012 | 18000000
|  |  |  | FAYETTE | 7 | 226.1 | 7-226.1 | 0 | 0 | 0 | RELIABILITY | NEW ROUTE(O) | CITATION BOULEVARD - PHASE IIA; FROM SOUTHERN RR TO MERCER ROAD. (LOCAL MATCH) (ALL WORK BY LFUCG)(2006BOPC)(08CCR) | SP | C | 2011 | 21120000
|  |  |  | FAYETTE | 7 | 226.4 | 7-226.4 | 0 | 0 | 0 | RELIABILITY | NEW ROUTE(O) | CITATION BOULEVARD - PHASE IIB; FROM MERCER ROAD TO LEESTOWN ROAD/ALEXANDRIA DR. (LOCAL MATCH) (ALL WORK BY LFUCG)(2006BOPC)(08CCR) | SP | C | 2011 | 2710000
|  |  |  | FAYETTE | 7 | 357.08 | 7-357.08 | KY-169 | 0 | 0.1 | RELIABILITY | FERRY OPERATION(P) | OPERATION OF VALLEY VIEW FERRY AT KY RIVER. | SP | C | 2011 | 180000
|  |  |  | FAYETTE | 7 | 357.09 | 7-357.09 | KY-169 | 0 | 0.1 | RELIABILITY | FERRY OPERATION(P) | OPERATION OF VALLEY VIEW FERRY AT KY RIVER. | SP | C | 2012 | 180000
|  |  |  | FAYETTE | 7 | 593.2 | 7-593.2 | 0 | 0 | 0 | RELIABILITY | NEW ROUTE(O) | NEWTOWN PIKE EXTENSION - PRIORITY 3: FROM VERSAILLES ROAD TO BROADWAY. (PHASE II)(08CCR) | SPB | R | 2011 | 8970000
ADMINISTRATIVE MODIFICATION | 2010.047 | 2011-02-28 | TIP MOD #14. CHANGE FUNDING TYPE TO SPB/SPP AND INCREASE FUNDING AMOUNT. MOD | FAYETTE | 7 | 593.2 | 7-593.2 | 0 | 0 | 0 | RELIABILITY | NEW ROUTE(O) | NEWTOWN PIKE EXTENSION - PRIORITY 3: FROM VERSAILLES ROAD TO BROADWAY. (PHASE II)LENGTH = 0.6 MI | SPB/SPP | R | 2011 | 18000000
|  |  |  | FAYETTE | 7 | 593.2 | 7-593.2 | 0 | 0 | 0 | RELIABILITY | NEW ROUTE(O) | NEWTOWN PIKE EXTENSION - PRIORITY 3: FROM VERSAILLES ROAD TO BROADWAY. (PHASE II)(08CCR) | SPP | U | 2012 | 5440000
ADMINISTRATIVE MODIFICATION | 2010.047 | 2011-02-28 | TIP MOD #14. CHANGE FY TO 2011. MOD | FAYETTE | 7 | 593.2 | 7-593.2 | 0 | 0 | 0 | RELIABILITY | NEW ROUTE(O) | NEWTOWN PIKE EXTENSION - PRIORITY 3: FROM VERSAILLES ROAD TO BROADWAY. (PHASE II)LENGTH = 0.6 MI | SPP | U | 2011 | 5440000
|  |  |  | FAYETTE | 7 | 593.2 | 7-593.2 | 0 | 0 | 0 | RELIABILITY | NEW ROUTE(O) | NEWTOWN PIKE EXTENSION - PRIORITY 3: FROM VERSAILLES ROAD TO BROADWAY. (PHASE II)(08CCR) | SPP | C | 2012 | 16100000
|  |  |  | FAYETTE | 7 | 593.3 | 7-593.3 | 0 | 0 | 0 | RELIABILITY | NEW ROUTE(O) | NEWTOWN PIKE EXTENSION - PRIORITY 4: FROM EXISTING NEWTOWN PIKE & PATTERSON TO SOUTH LIMESTONE. (PHASE III - SCOTT STREET CONNECTOR) | SP | R | 2011 | 8657000
|  |  |  | FAYETTE | 7 | 593.3 | 7-593.3 | 0 | 0 | 0 | RELIABILITY | NEW ROUTE(O) | NEWTOWN PIKE EXTENSION - PRIORITY 4: FROM EXISTING NEWTOWN PIKE & PATTERSON TO SOUTH LIMESTONE. (PHASE III - SCOTT STREET CONNECTOR) | SP | U | 2012 | 3468000
|  |  |  | GREENUP | 9 | 8509 | 9-8509 | KY-207 | 0 | 0 | RELIABILITY | NEW ROUTE(O) | CONSTRUCT A NEW CONNECTOR ROAD CONNECTING FLATWOODS AT KY-207 AND KY-693 AND THE INDUSTRIAL PARKWAY CONNECTOR BETWEEN I-64 AND US-60. (08CCN) | SPB | D | 2010 | 950000
|  |  |  | HARDIN | 4 | 153 | 4-153 | KY-251 | 2.722 | 8.019 | RELIABILITY | SCOPING STUDY(O) | KY-251; FROM RING ROAD TO KY-313. (BRAC) | BRC | P | 2010 | 600000
|  |  |  | HARDIN | 4 | 153.01 | 4-153.01 | KY-251 | 2.722 | 6.326 | RELIABILITY | PHASE I DESIGN(O) | KY-251; FROM RING ROAD TO KY-434. (BRAC) | SP | D | 2012 | 3100000
|  |  |  | HARDIN | 4 | 153.01 | 4-153.01 | KY-251 | 2.722 | 6.326 | RELIABILITY | PHASE I DESIGN(O) | KY-251; FROM RING ROAD TO KY-434. (BRAC) | SP | R | 2012 | 2500000
|  |  |  | HARDIN | 4 | 153.01 | 4-153.01 | KY-251 | 2.722 | 6.326 | RELIABILITY | PHASE I DESIGN(O) | KY-251; FROM RING ROAD TO KY-434. (BRAC) | SP | U | 2012 | 1500000
|  |  |  | HARDIN | 4 | 153.05 | 4-153.05 | KY-251 | 6.326 | 8.019 | RELIABILITY | PHASE I DESIGN(O) | KY-251; FROM KY-434 TO KY-313. (BRAC) | SP | D | 2012 | 1500000
|  |  |  | HARDIN | 4 | 153.05 | 4-153.05 | KY-251 | 6.326 | 8.019 | RELIABILITY | PHASE I DESIGN(O) | KY-251; FROM KY-434 TO KY-313. (BRAC) | SP | R | 2012 | 1500000
|  |  |  | HARDIN | 4 | 153.05 | 4-153.05 | KY-251 | 6.326 | 8.019 | RELIABILITY | PHASE I DESIGN(O) | KY-251; FROM KY-434 TO KY-313. (BRAC) | SP | U | 2012 | 1000000
|  |  |  | HARDIN | 4 | 297.21 | 4-297.21 | KY-313 | 0 | 0 | RELIABILITY | NEW ROUTE(O) | KY 313 EXTENSION FROM KY 1500 TO ROLLING HILLS DRIVE WITH A TEMPORARY KY 144 CONNECTION. (SECTION 1) (2006BOPC)(BRAC)(08CCR) | BR2 | C | 2011 | 9990000
ADMINISTRATIVE MODIFICATION | 2010.009 | 2010-10-20 | TIP ADMINISTRATIVE MOD #9. CHANGE FUNDING AMOUNT. MOD | HARDIN | 4 | 297.21 | 4-297.21 | KY-313 | 0 | 0 | RELIABILITY | NEW ROUTE(O) | KY 313 EXTENSION FROM KY 1500 TO ROLLING HILLS DRIVE WITH A TEMPORARY KY 144 CONNECTION. (SECTION 1) (2006BOPC)(BRAC)(08CCR) | BR2 | C | 2011 | 5756059
|  |  |  | HARDIN | 4 | 7010.5 | 4-7010.5 | KY-3005 | 0 | 0 | RELIABILITY | NEW ROUTE(O) | EXTEND RING ROAD (KY 3005) FROM GAITHER STATION ROAD TO THE WESTERN KENTUCKY PARKWAY. (2006BOPC)(08CCR) | SPB | C | 2010 | 17090000
|  |  |  | HARDIN | 4 | 7030 | 4-7030 | KY-251 | 1.185 | 2.722 | RELIABILITY | RECONSTRUCTION(O) | EXTEND MILES STREET FROM PEAR ORCHARD TO RING ROAD. (98CCN) | SP | C | 2010 | 11820000
|  |  |  | HARDIN | 4 | 8103.1 | 4-8103.1 | 0 | 0 | 0 | RELIABILITY | NEW ROUTE(O) | NEW CONNECTOR ROAD SECTION 1: FROM E'TOWN BYPASS TO CECILLIANA DRIVE INCLUDING INTERCHANGE WITH E'TOWN BYPASS. (04CCR)(2004BOPC)(BRAC) | BR2 | C | 2011 | 22500000
|  |  |  | HARDIN | 4 | 8103.3 | 4-8103.3 | 0 | 0 | 0 | RELIABILITY | NEW ROUTE(O) | NEW CONNECTOR ROAD SECTION 3: FROM CECILLIANA DRIVE TO KY-220. (BRAC) | BR2 | C | 2011 | 14600000
|  |  |  | HARDIN | 4 | 8103.4 | 4-8103.4 | 0 | 0 | 0 | RELIABILITY | NEW ROUTE(O) | NEW CONNECTOR ROAD SECTION 4: FROM KY-220 TO KY-313. (BRAC) | BR2 | C | 2012 | 21520000
ADMINISTRATIVE MODIFICATION | 2010.009 | 2010-10-20 | TIP ADMINISTRATIVE MOD #9. CHANGE FUNDING AMOUNT. MOD | HARDIN | 4 | 8103.4 | 4-8103.4 | 0 | 0 | 0 | RELIABILITY | NEW ROUTE(O) | NEW CONNECTOR ROAD SECTION 4: FROM KY-220 TO KY-313. (BRAC) | BR2 | C | 2012 | 17000000
|  |  |  | HARDIN | 4 | 8103.5 | 4-8103.5 | 0 | 0 | 0 | RELIABILITY | NEW ROUTE(O) | NEW CONNECTOR FROM VETERAN'S PKWY (KY 1646) TO KY-313. (BRAC) | BR2 | R | 2011 | 6580000
|  |  |  | HARDIN | 4 | 8103.5 | 4-8103.5 | 0 | 0 | 0 | RELIABILITY | NEW ROUTE(O) | NEW CONNECTOR FROM VETERAN'S PKWY (KY 1646) TO KY-313. (BRAC) | BR2 | U | 2011 | 1300000
|  |  |  | HARDIN | 4 | 8103.5 | 4-8103.5 | 0 | 0 | 0 | RELIABILITY | NEW ROUTE(O) | NEW CONNECTOR FROM VETERAN'S PKWY (KY 1646) TO KY-313. (BRAC) | BR2 | C | 2012 | 19700000
|  |  |  | HENDERSON | 2 | 79.02 | 2-79.02 | US-60 | 5.531 | 8.71 | RELIABILITY | RECONSTRUCTION(O) | PADUCAH-HENDERSON; RECONSTRUCT US-60 FROM THE CORYDON BYPASS (CORYDON-GENEVA ROAD) TO THE HENDERSON BYPASS (KY-425).(04CCR) | SP | D | 2010 | 1300000
ADMINISTRATIVE MODIFICATION | 2010.038 | 2011-02-15 | TIP AMENDMENT RESOLUTION 11-2. CHANGE FISCAL YEAR. MOD SEE TIP MOD FOR C PHASE ILLUSTRATIVE. | HENDERSON | 2 | 79.02 | 2-79.02 | US-60 | 5.531 | 8.71 | RELIABILITY | RECONSTRUCTION(O) | PADUCAH-HENDERSON; RECONSTRUCT US-60 FROM THE CORYDON BYPASS (CORYDON-GENEVA ROAD) TO THE HENDERSON BYPASS (KY-425).(04CCR) | SP | D | 2011 | 1300000
|  |  |  | HENDERSON | 2 | 79.02 | 2-79.02 | US-60 | 5.531 | 8.71 | RELIABILITY | RECONSTRUCTION(O) | PADUCAH-HENDERSON; RECONSTRUCT US-60 FROM THE CORYDON BYPASS (CORYDON-GENEVA ROAD) TO THE HENDERSON BYPASS (KY-425).(04CCR) | SP | R | 2012 | 5760000
|  |  |  | HENDERSON | 2 | 79.02 | 2-79.02 | US-60 | 5.531 | 8.71 | RELIABILITY | RECONSTRUCTION(O) | PADUCAH-HENDERSON; RECONSTRUCT US-60 FROM THE CORYDON BYPASS (CORYDON-GENEVA ROAD) TO THE HENDERSON BYPASS (KY-425).(04CCR) | SP | U | 2012 | 4880000
|  |  |  | HENDERSON | 2 | 79.1 | 2-79.1 | US-60 | 0 | 0 | RELIABILITY | NEW ROUTE(O) | PADUCAH-HENDERSON; CONSTRUCT US-60 BYPASS OF CORYDON.(04CCR) | SP | D | 2010 | 1630000
ADMINISTRATIVE MODIFICATION | 2010.038 | 2011-02-15 | TIP AMENDMENT RESOLUTION 11-2. CHANGE FISCAL YEAR. MOD SEE TIP MOD FOR C PHASE ILLUSTRATIVE. | HENDERSON | 2 | 79.1 | 2-79.1 | US-60 | 0 | 0 | RELIABILITY | NEW ROUTE(O) | PADUCAH-HENDERSON; CONSTRUCT US-60 BYPASS OF CORYDON.(04CCR) | SP | D | 2011 | 1630000
|  |  |  | HENDERSON | 2 | 79.1 | 2-79.1 | US-60 | 0 | 0 | RELIABILITY | NEW ROUTE(O) | PADUCAH-HENDERSON; CONSTRUCT US-60 BYPASS OF CORYDON.(04CCR) | SP | R | 2012 | 3840000
|  |  |  | HENDERSON | 2 | 79.1 | 2-79.1 | US-60 | 0 | 0 | RELIABILITY | NEW ROUTE(O) | PADUCAH-HENDERSON; CONSTRUCT US-60 BYPASS OF CORYDON.(04CCR) | SP | U | 2012 | 1960000
ADMINISTRATIVE MODIFICATION | 2010.095 | 2011-07-05 | KIPDA TIP AMENDMENT #1. KIPDA ID 229. ADD D PHASE. NEW | JEFFERSON | 5 | 247.2 | 5-247.2 | KY-1450 | 0 | 1.873 | RELIABILITY | MAJOR WIDENING(O) | WIDEN BLUE LICK ROAD FROM BULLITT COUNTY LINE NORTH TO THE SNYDER FREEWAY (LOU T.I.P.)(08CCR) | SP | D | 2011 | 2200000
|  |  |  | JEFFERSON | 5 | 247.2 | 5-247.2 | KY-1450 | 0 | 1.873 | RELIABILITY | MAJOR WIDENING(O) | WIDEN BLUE LICK ROAD FROM BULLITT COUNTY LINE NORTH TO THE SNYDER FREEWAY (LOU T.I.P.)(08CCR) | SPB | R | 2010 | 10230000
ADMINISTRATIVE MODIFICATION | 2010.095 | 2011-07-05 | KIPDA TIP AMENDMENT #1. KIPDA ID 229. CHANGE FY. MOD | JEFFERSON | 5 | 247.2 | 5-247.2 | KY-1450 | 0 | 1.873 | RELIABILITY | MAJOR WIDENING(O) | WIDEN BLUE LICK ROAD FROM BULLITT COUNTY LINE NORTH TO THE SNYDER FREEWAY (LOU T.I.P.)(08CCR) | SPB | R | 2012 | 10230000
|  |  |  | JEFFERSON | 5 | 247.2 | 5-247.2 | KY-1450 | 0 | 1.873 | RELIABILITY | MAJOR WIDENING(O) | WIDEN BLUE LICK ROAD FROM BULLITT COUNTY LINE NORTH TO THE SNYDER FREEWAY (LOU T.I.P.)(08CCR) | SP | U | 2010 | 8860000
ADMINISTRATIVE MODIFICATION | 2010.095 | 2011-07-05 | KIPDA TIP AMENDMENT #1. KIPDA ID 229. CHANGE FY AND INCREASE FUNDING. MOD | JEFFERSON | 5 | 247.2 | 5-247.2 | KY-1450 | 0 | 1.873 | RELIABILITY | MAJOR WIDENING(O) | WIDEN BLUE LICK ROAD FROM BULLITT COUNTY LINE NORTH TO THE SNYDER FREEWAY (LOU T.I.P.)(08CCR) | SP | U | 2012 | 8900000
|  |  |  | JEFFERSON | 5 | 247.2 | 5-247.2 | KY-1450 | 0 | 1.873 | RELIABILITY | MAJOR WIDENING(O) | WIDEN BLUE LICK ROAD FROM BULLITT COUNTY LINE NORTH TO THE SNYDER FREEWAY (LOU T.I.P.)(08CCR) | SP | C | 2012 | 11100000
ADMINISTRATIVE MODIFICATION | 2010.095 | 2011-07-05 | KIPDA TIP AMENDMENT #1. KIPDA ID 229. CHANGE FY AND FUNDING AMOUNT. MOD | JEFFERSON | 5 | 247.2 | 5-247.2 | KY-1450 | 0 | 1.873 | RELIABILITY | MAJOR WIDENING(O) | WIDEN BLUE LICK ROAD FROM BULLITT COUNTY LINE NORTH TO THE SNYDER FREEWAY (LOU T.I.P.)(08CCR) | SP | C | 2014 | 11200000
|  |  |  | JEFFERSON | 5 | 247.5 | 5-247.5 | KY-1450 | 1.873 | 2.84 | RELIABILITY | MINOR WIDENING(O) | SNYDER FREEWAY TO BLUEBELL DRIVE (LOU T.I.P.) (SECTION 2) (CONSTRUCTION SEQUENCE 2)(RU-04DEOB)(2008BOPC) | SP | R | 2010 | 3350000
|  |  |  | JEFFERSON | 5 | 247.5 | 5-247.5 | KY-1450 | 1.873 | 2.84 | RELIABILITY | MINOR WIDENING(O) | SNYDER FREEWAY TO BLUEBELL DRIVE (LOU T.I.P.) (SECTION 2) (CONSTRUCTION SEQUENCE 2)(RU-04DEOB)(2008BOPC) | SP | U | 2010 | 1000000
|  |  |  | JEFFERSON | 5 | 247.5 | 5-247.5 | KY-1450 | 1.873 | 2.84 | RELIABILITY | MINOR WIDENING(O) | SNYDER FREEWAY TO BLUEBELL DRIVE (LOU T.I.P.) (SECTION 2) (CONSTRUCTION SEQUENCE 2)(RU-04DEOB)(2008BOPC) | SP | C | 2012 | 7250000
|  |  |  | JEFFERSON | 5 | 247.7 | 5-247.7 | KY-1450 | 2.84 | 3.6 | RELIABILITY | MINOR WIDENING(O) | BLUEBELL DRIVE TO KY-61 (LOU T.I.P.) (SECTION 3) (CONSTRUCTION SEQUENCE 1)(RU-04DEOB)(2008BOPC) | SPB | R | 2010 | 2700000
|  |  |  | JEFFERSON | 5 | 247.7 | 5-247.7 | KY-1450 | 2.84 | 3.6 | RELIABILITY | MINOR WIDENING(O) | BLUEBELL DRIVE TO KY-61 (LOU T.I.P.) (SECTION 3) (CONSTRUCTION SEQUENCE 1)(RU-04DEOB)(2008BOPC) | SPB | U | 2010 | 2300000
|  |  |  | JEFFERSON | 5 | 247.7 | 5-247.7 | KY-1450 | 2.84 | 3.6 | RELIABILITY | MINOR WIDENING(O) | BLUEBELL DRIVE TO KY-61 (LOU T.I.P.) (SECTION 3) (CONSTRUCTION SEQUENCE 1)(RU-04DEOB)(2008BOPC) | SPB | C | 2012 | 4560000
|  |  |  | JEFFERSON | 5 | 320.2 | 5-320.2 | KY-22 | 4.03 | 4.42 | SAFETY | SAFETY(P) | IMPLEMENT TRAFFIC FLOW IMPROVEMENT FROM CHAMBERLAIN LANE TO KY-1694. (LOCAL PARTICIPATION)(2002BOPC)(TO BE LET WITH 5-320.30 AND 5-320.40)(TO BE LET BY KYTC). | SP | C | 2010 | 6500000
|  |  |  | JEFFERSON | 5 | 320.4 | 5-320.4 | KY-22 | 5.185 | 5.639 | RELIABILITY | MINOR WIDENING(O) | RECONSTRUCT KY-22 FROM HITT ROAD TO MURPHY LANE. (DESIGN AND ROW BY AGREEMENT WITH METRO LOUISVILLE; UTILITIES AND CONSTRUCTION BY KYTC) (TO BE LET WITH 5-320.20 AND 5-320.30)(06CCN) (2004BOPC)(08CCR) | SPB | C | 2010 | 1460000
|  |  |  | JEFFERSON | 5 | 323.01 | 5-323.01 | KY-1931 | 0.54 | 3.148 | RELIABILITY | MAJOR WIDENING(O) | WIDEN GREENWOOD ROAD FROM GREENBELT HWY TO DIXIE HWY (US-31W) (5-LANE IMPROVEMENT) (98CCR)(R-04DEOB)(04CCR)(BOP2006P) | SPP | R | 2012 | 10480000
|  |  |  | JEFFERSON | 5 | 323.01 | 5-323.01 | KY-1931 | 0.54 | 3.148 | RELIABILITY | MAJOR WIDENING(O) | WIDEN GREENWOOD ROAD FROM GREENBELT HWY TO DIXIE HWY (US-31W) (5-LANE IMPROVEMENT) (98CCR)(R-04DEOB)(04CCR)(BOP2006P) | SPP | U | 2012 | 3940000
|  |  |  | JEFFERSON | 5 | 344.01 | 5-344.01 | KY-1747 | 11.89 | 13.503 | RELIABILITY | RECONSTRUCTION(O) | WIDEN SOUTHBOUND HURSTBOURNE LANE TO 3 LANES FROM US-60 TO I-64. (06CCR)(03KYD)(2006BOPP)(SEE 5-344.02 FOR KYD C PHASE) | SP | R | 2010 | 1680000
|  |  |  | JEFFERSON | 5 | 344.01 | 5-344.01 | KY-1747 | 11.89 | 13.503 | RELIABILITY | RECONSTRUCTION(O) | WIDEN SOUTHBOUND HURSTBOURNE LANE TO 3 LANES FROM US-60 TO I-64. (06CCR)(03KYD)(2006BOPP)(SEE 5-344.02 FOR KYD C PHASE) | SP | U | 2010 | 1670000
|  |  |  | JEFFERSON | 5 | 344.01 | 5-344.01 | KY-1747 | 11.89 | 13.503 | RELIABILITY | RECONSTRUCTION(O) | WIDEN SOUTHBOUND HURSTBOURNE LANE TO 3 LANES FROM US-60 TO I-64. (06CCR)(03KYD)(2006BOPP)(SEE 5-344.02 FOR KYD C PHASE) | SP | C | 2012 | 3960000
|  |  |  | JEFFERSON | 5 | 344.03 | 5-344.03 | KY-1747 | 13.453 | 13.553 | RELIABILITY | RECONSTRUCTION(O) | SOUTHBOUND HURSTBOURNE LANE: IMPROVEMENTS TO THE US-60 AND HURSTBOURNE LANE INTERSECTION. (ADDITIONAL AMOUNT NEEDED TO SUPPLEMENT "KYD" FUNDS TO COVER COST) | SP | C | 2010 | 700000
|  |  |  | JEFFERSON | 5 | 508.1 | 5-508.1 | 0 | 0 | 0 | SAFETY | BIKE/PED FACIL(O) | LOUISVILLE WATERFRONT PARK JOINTLY WITH INDIANA; CONSTRUCT PEDESTRIAN FACILITIES ON "BIG FOUR" BRIDGE OVER THE OHIO RIVER. (KENTUCKY'S SHARE OF PROJECT) | SPP | C | 2012 | 12000000
|  |  |  | JEFFERSON | 5 | 8010 | 5-8010 | KY-1450 | 0 | 3.542 | RELIABILITY | MAJOR WIDENING(O) | WIDEN BLUE LICK ROAD FROM BULLITT COUNTY LINE NORTH TO THE SNYDER FREEWAY (LOU T.I.P.) (CCN) | SP | R | 2010 | 4635000
|  |  |  | JEFFERSON | 5 | 8408 | 5-8408 |  | 0.54 | 3.139 | RELIABILITY | MINOR WIDENING(O) | WIDEN GREENWOOD ROAD FROM GREENBELT HWY TO DIXIE HWY (US-31W) (5-LANE IMPROVEMENT) (98CCR)(R-04DEOB)(04CCR) (08CCN) | SP | R | 2010 | 3200000
|  |  |  | JEFFERSON | 5 | 8408 | 5-8408 | KY-1931 | 0.54 | 3.139 | RELIABILITY | MINOR WIDENING(O) | WIDEN GREENWOOD ROAD FROM GREENBELT HWY TO DIXIE HWY (US-31W) (5-LANE IMPROVEMENT) (98CCR)(R-04DEOB)(04CCR) (08CCN) | SP | U | 2011 | 3500000
|  |  |  | JEFFERSON | 5 | 8408 | 5-8408 | KY-1931 | 0.54 | 3.139 | RELIABILITY | MINOR WIDENING(O) | WIDEN GREENWOOD ROAD FROM GREENBELT HWY TO DIXIE HWY (US-31W) (5-LANE IMPROVEMENT) (98CCR)(R-04DEOB)(04CCR) (08CCN) | SP | C | 2012 | 10000000
|  |  |  | JEFFERSON | 5 | 8414 | 5-8414 |  | 0 | 0 | RELIABILITY | RELOCATION(O) | RELOCATE CRITTENDEN DRIVE/LOUISVILLE REGIONAL AIRPORT AUTHORITY TO ALLOW FOR CONSTRUCTION FOR A TAXIWAY TO ACCOMMODATE GROUP 6 AIRCRAFT FOR THE UPS WORLDPORT EXPANSION. | SB2 | C | 2011 | 3000000
|  |  |  | JEFFERSON | 5 | 8502 | 5-8502 | KY-1020 | 0.615 | 2.669 | RELIABILITY | MAJOR WIDENING(O) | WIDEN KY-1020, NATIONAL TURNPIKE, FROM FAIRDALE ROAD TO SOUTH PARK ROAD, A DISTANCE OF FROM MP .615 TO MP 2.669. (08CCN) | SP | D | 2010 | 1350000
ADMINISTRATIVE MODIFICATION | 2010.034 | 2011-01-28 | KIPDA ID #1817. KIPDA MOD #2-REVISED. CHANGE FY. MOD | JEFFERSON | 5 | 8502 | 5-8502 | KY-1020 | 0.615 | 2.669 | RELIABILITY | MAJOR WIDENING(O) | WIDEN KY-1020, NATIONAL TURNPIKE, FROM FAIRDALE ROAD TO SOUTH PARK ROAD, A DISTANCE OF FROM MP .615 TO MP 2.669. (08CCN) | SP | D | 2011 | 1350000
|  |  |  | JEFFERSON | 5 | 8503 | 5-8503 | KY-2055 | 0 | 1.36 | RELIABILITY | MAJOR WIDENING(O) | WIDEN KY-2055 (MT. HOLLY ROAD) FROM NATIONAL TURNPIKE TO FAIRDALE ROAD. (08CCN) | SP | D | 2010 | 1050000
ADMINISTRATIVE MODIFICATION | 2010.034 | 2011-01-28 | KIPDA ID #1824. KIPDA MOD #2-REVISED. CHANGE FY. MOD | JEFFERSON | 5 | 8503 | 5-8503 | KY-2055 | 0 | 1.36 | RELIABILITY | MAJOR WIDENING(O) | WIDEN KY-2055 (MT. HOLLY ROAD) FROM NATIONAL TURNPIKE TO FAIRDALE ROAD. (08CCN) | SP | D | 2011 | 1050000
|  |  |  | JESSAMINE | 7 | 8305 | 7-8305 | 0 | 0 | 0 | RELIABILITY | NEW ROUTE(O) | EAST NICHOLASVILLE BY-PASS PHASE II FROM KY-39 EXTENDING SOUTHEASTERLY TO US-27 SOUTH OF NICHOLASVILLE. (06CCN)(08CCR) | SPP | R | 2012 | 4000000
|  |  |  | JESSAMINE | 7 | 8305 | 7-8305 | 0 | 0 | 0 | RELIABILITY | NEW ROUTE(O) | EAST NICHOLASVILLE BY-PASS PHASE II FROM KY-39 EXTENDING SOUTHEASTERLY TO US-27 SOUTH OF NICHOLASVILLE. (06CCN)(08CCR) | SPP | U | 2012 | 2000000
ADMINISTRATIVE MODIFICATION | 2010.045 | 2011-03-02 | LEXINGTON MPO TIP AMENDMENT #1 REVISED THE TIP TO MATCH THE STIP. RIGHT-OF-WAY PHASE IS IN THE FED FUNDED SECTION OF STIP-NO CHANGE TO STIP. | JESSAMINE | 7 | 87.1 | 7-87.1 | 0 | 0 | 0 | RELIABILITY | NEW ROUTE(O) | EAST NICHOLASVILLE BYPASS SECTION I; FROM US-27 NORTH OF NICHOLASVILLE, EXTENDING SOUTHEASTERLY TO KY-39. (2000BOP)(04CCR)(06CCR)(08CCR) | SP | U | 2012 | 1130000
|  |  |  | KENTON | 6 | 162.01 | 6-162.01 | KY-536 | 0 | 4.476 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT KY-536 TO A 4 LANE URBAN SECTION FROM THE BOONE COUNTY LINE TO KY-17 (MP 0.0 TO MP 4.5). (00CCR)(04CCN)(06CCR)(2006BOPC)(PHASE I DESIGN SHOWN UNDER 6-162.00) | SP | R | 2010 | 22050000
|  |  |  | KENTON | 6 | 162.01 | 6-162.01 | KY-536 | 0 | 4.476 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT KY-536 TO A 4 LANE URBAN SECTION FROM THE BOONE COUNTY LINE TO KY-17 (MP 0.0 TO MP 4.5). (00CCR)(04CCN)(06CCR)(2006BOPC)(PHASE I DESIGN SHOWN UNDER 6-162.00) | SP | U | 2010 | 4160000
|  |  |  | KENTON | 6 | 17.09 | 6-17.09 | I-75 | 191.277 | 191.777 | RELIABILITY | RELOCATION(O) | BRENT SPENCE BRIDGE RELOCATION PROJECT (ADDITIONAL UTILITY FUNDS) | SB2 | U | 2012 | 6520000
ADMINISTRATIVE MODIFICATION | 2010.205 | 2012-06-18 | TIP MOD #11. ADD PROJECT TO STIP AND REVISE DESCRIPTION IN TIP. NEW | KENTON |  |  | 6-162.00 | KY 536 |  |  | RELIABILITY | PHASE I DESIGN(O) | RECONSTRUCT KY-536 TO A 4 LN URBAN SECTION WITH ACCESS MANAGEMENT FROM E END OF THE CSX RAILRAOD BRIDGE (B91)(MP 14.363 IN BOONE) TO KY 17(MP 4.6 IN KENTON) & RECONSTRUCT KY1303 FROM KY536 TO THE END OF NEW CONSTRUCTION (PHASE II D, 6-162.01) | SP | R | 2013 | 25050000
ADMINISTRATIVE MODIFICATION | 2010.205 | 2012-06-18 | TIP MOD #11. ADD PROJECT TO STIP AND REVISE DESCRIPTION IN TIP. NEW | KENTON |  |  | 6-162.00 | KY 536 |  |  | RELIABILITY | PHASE I DESIGN(O) | RECONSTRUCT KY-536 TO A 4 LN URBAN SECTION WITH ACCESS MANAGEMENT FROM E END OF THE CSX RAILRAOD BRIDGE (B91)(MP 14.363 IN BOONE) TO KY 17(MP 4.6 IN KENTON) & RECONSTRUCT KY1303 FROM KY536 TO THE END OF NEW CONSTRUCTION (PHASE II D, 6-162.01) | SP | U | 2013 | 4160000
|  |  |  | KENTON | 6 | 344.21 | 6-344.21 | KY-16 | 9.323 | 10.279 | RELIABILITY | RELOCATION(O) | RECONSTRUCT KY-16 (TAYLOR MILL ROAD) FROM HANDS PIKE TO THE SOUTH INTERSECTION WITH OLD TAYLOR MILL ROAD. (SECTION 2) (2002BOP)(08CCR) | SPB | C | 2010 | 7800000
|  |  |  | KENTON | 6 | 344.5 | 6-344.5 | KY-16 | 0 | 0 | RELIABILITY | RELOCATION(O) | RECONSTRUCT KY-16 (TAYLOR MILL ROAD) FROM BLACKSTONE COURT TO I-275. (SECTION 1C) SEE 6-344.11 FOR R AND U PHASES)(2008BOPC) | SB2 | C | 2011 | 6800000
ADMINISTRATIVE MODIFICATION | 2010.030 | 2011-01-27 | OKI TIP AMENDMENT #32. ADD TO TIP. CHANGE DESCRIPTION IN STIP. MOD | KENTON | 6 | 344.5 | 6-344.5 | KY-16 | 0 | 0 | RELIABILITY | RELOCATION(O) | RECONSTRUCT KY 16 FROM BLACKSTONE COURT TO IR 275. (SEE 6-344.11 FOR ROW AND UTIL) | SB2 | C | 2011 | 6800000
ADMINISTRATIVE MODIFICATION | 2010.124 | 2011-09-09 | OKI TIP MOD #3. CHANGE FY IN TIP FROM FY 2014 TO FY 2012. | KENTON | 6 | 344.5 | 6-344.5 | KY-16 | 0 | 0 | RELIABILITY | RELOCATION(O) | RECONSTRUCT KY 16 FROM BLACKSTONE COURT TO IR 275. | SB2 | C | 2012 | 6800000
|  |  |  | KENTON | 6 | 8401 | 6-8401 | KY-8 | 4.369 | 4.686 | RELIABILITY | TRANSP ENHANCEMENT(P) | LUDLOW STREETSCAPE REVITALIZATION AND BEAUTIFICATION PROJECT ALONG KY-8 BETWEEN ELM STREET AND CARNEAL STREET. (08CCN) | SP | C | 2010 | 150000
|  |  |  | KENTON | 6 | 8405 | 6-8405 | KY-3187 | 0.72 | 0.954 | RELIABILITY | PLANNING-OKI(O) | IMPROVE KY-3187 BETWEEN FARRELL ROAD AND HIGHLAND PIKE. (08CCN) | SPB | P | 2010 | 200000
|  |  |  | MEADE | 4 | 297.23 | 4-297.23 | KY-313 | 0 | 0 | RELIABILITY | NEW ROUTE(O) | KY-313 EXTENSION FROM ROLLING HILLS DRIVE TO NORTHERN FLAHERTY CONNECTOR WITH A TEMPORARY KY-144 CONNECTION. (SECTION 2) (2006BOPC)(BRAC) | BR2 | C | 2011 | 11040000
ADMINISTRATIVE MODIFICATION | 2010.009 | 2010-10-20 | TIP ADMINISTRATIVE MOD #9. CHANGE FY AND FUNDING AMOUNT. MOD | MEADE | 4 | 297.23 | 4-297.23 | KY-313 | 0 | 0 | RELIABILITY | NEW ROUTE(O) | KY-313 EXTENSION FROM ROLLING HILLS DRIVE TO NORTHERN FLAHERTY CONNECTOR WITH A TEMPORARY KY-144 CONNECTION. (SECTION 2) (2006BOPC)(BRAC) | BR2 | C | 2012 | 10000000
|  |  |  | MEADE | 4 | 297.27 | 4-297.27 | KY-313 | 0 | 0 | RELIABILITY | NEW ROUTE(O) | KY-313 EXTENSION FROM THE NORTHERN FLAHERTY CONNECTOR TO THE US 60 FRONTAGE ROAD CONNECTION WITH A TEMPORARY US 60 CONNECTION. (SECTION 3) (2006BOPC)(BRAC) | BR2 | C | 2011 | 8890000
ADMINISTRATIVE MODIFICATION | 2010.009 | 2010-10-20 | TIP ADMINISTRATIVE MOD #9. CHANGE FY. MOD | MEADE | 4 | 297.27 | 4-297.27 | KY-313 | 0 | 0 | RELIABILITY | NEW ROUTE(O) | KY-313 EXTENSION FROM THE NORTHERN FLAHERTY CONNECTOR TO THE US 60 FRONTAGE ROAD CONNECTION WITH A TEMPORARY US 60 CONNECTION. (SECTION 3) (2006BOPC)(BRAC) | BR2 | C | 2012 | 8890000
|  |  |  | MEADE | 4 | 297.61 | 4-297.61 | KY-313 | 0 | 0 | RELIABILITY | NEW ROUTE(O) | KY-313 EXTENSION; US-60 FRONTAGE ROAD CONNECTOR TO THE NORTHERN KY-448 BUCK GROVE CONNECTOR. (SECTION II) (FORMERLY 98 SYP ITEM NO. 4-53.00)(08CCR) | SPB | R | 2010 | 9270000
|  |  |  | MEADE | 4 | 297.61 | 4-297.61 | KY-313 | 0 | 0 | RELIABILITY | NEW ROUTE(O) | KY-313 EXTENSION; US-60 FRONTAGE ROAD CONNECTOR TO THE NORTHERN KY-448 BUCK GROVE CONNECTOR. (SECTION II) (FORMERLY 98 SYP ITEM NO. 4-53.00)(08CCR) | SPB | U | 2010 | 1130000
|  |  |  | MEADE | 4 | 297.61 | 4-297.61 | KY-313 | 0 | 0 | RELIABILITY | NEW ROUTE(O) | KY-313 EXTENSION; US-60 FRONTAGE ROAD CONNECTOR TO THE NORTHERN KY-448 BUCK GROVE CONNECTOR. (SECTION II) (FORMERLY 98 SYP ITEM NO. 4-53.00)(08CCR) | SP | C | 2012 | 13400000
|  |  |  | MEADE | 4 | 297.65 | 4-297.65 | KY-313 | 0 | 0 | RELIABILITY | NEW ROUTE(O) | KY-313 EXTENSION FROM THE NORTHERN KY-448 BUCK GROVE CONNECTOR TO KY-1638. (SECTION II) (FORMERLY 98 SYP ITEM NO. 4-53.00) | SP | R | 2012 | 6950000
|  |  |  | MEADE | 4 | 297.65 | 4-297.65 | KY-313 | 0 | 0 | RELIABILITY | NEW ROUTE(O) | KY-313 EXTENSION FROM THE NORTHERN KY-448 BUCK GROVE CONNECTOR TO KY-1638. (SECTION II) (FORMERLY 98 SYP ITEM NO. 4-53.00) | SP | U | 2012 | 1410000
|  |  |  | OLDHAM | 5 | 304.1 | 5-304.1 | KY-22 | 3.25 | 5.32 | RELIABILITY | MAJOR WIDENING(O) | RECONSTRUCT KY-22 TO 3-LANES FROM KY-329 TO KY-329B AND TO 3-LANES FROM KY-329B TO ABBOTT LANE. ("BRIDGE HILL")(2004BOPC)(08CCR) | SPB | R | 2010 | 2100000
ADMINISTRATIVE MODIFICATION | 2010.095 | 2011-07-05 | KIPDA TIP AMENDMENT #1. KIPDA ID 1488. MOVE FY AND DECREASE AMOUNT. MOD | OLDHAM | 5 | 304.1 | 5-304.1 | KY-22 | 3.25 | 5.32 | RELIABILITY | MAJOR WIDENING(O) | RECONSTRUCT KY-22 TO 3-LANES FROM KY-329 TO KY-329B AND TO 3-LANES FROM KY-329B TO ABBOTT LANE. ("BRIDGE HILL")(2004BOPC)(08CCR) | SPB | R | 2011 | 300000
|  |  |  | OLDHAM | 5 | 304.1 | 5-304.1 | KY-22 | 3.25 | 5.32 | RELIABILITY | MAJOR WIDENING(O) | RECONSTRUCT KY-22 TO 3-LANES FROM KY-329 TO KY-329B AND TO 3-LANES FROM KY-329B TO ABBOTT LANE. ("BRIDGE HILL")(2004BOPC)(08CCR) | SPB | U | 2010 | 2080000
ADMINISTRATIVE MODIFICATION | 2010.095 | 2011-07-05 | KIPDA TIP AMENDMENT #1. KIPDA ID 1488. MOVE FY AND DECREASE AMOUNT. MOD | OLDHAM | 5 | 304.1 | 5-304.1 | KY-22 | 3.25 | 5.32 | RELIABILITY | MAJOR WIDENING(O) | RECONSTRUCT KY-22 TO 3-LANES FROM KY-329 TO KY-329B AND TO 3-LANES FROM KY-329B TO ABBOTT LANE. ("BRIDGE HILL")(2004BOPC)(08CCR) | SPB | U | 2011 | 1260000
|  |  |  | OLDHAM | 5 | 304.1 | 5-304.1 | KY-22 | 3.25 | 5.32 | RELIABILITY | MAJOR WIDENING(O) | RECONSTRUCT KY-22 TO 3-LANES FROM KY-329 TO KY-329B AND TO 3-LANES FROM KY-329B TO ABBOTT LANE. ("BRIDGE HILL")(2004BOPC)(08CCR) | SP | C | 2011 | 9740000
ADMINISTRATIVE MODIFICATION | 2010.095 | 2011-07-05 | KIPDA TIP AMENDMENT #1. KIPDA ID 1488. DECREASE AMOUNT. MOD | OLDHAM | 5 | 304.1 | 5-304.1 | KY-22 | 3.25 | 5.32 | RELIABILITY | MAJOR WIDENING(O) | RECONSTRUCT KY-22 TO 3-LANES FROM KY-329 TO KY-329B AND TO 3-LANES FROM KY-329B TO ABBOTT LANE. ("BRIDGE HILL")(2004BOPC)(08CCR) | SPB | C | 2011 | 4800000
|  |  |  | OLDHAM | 5 | 304.2 | 5-304.2 | KY-22 | 5.32 | 7.5 | RELIABILITY | MAJOR WIDENING(O) | RECONSTRUCT KY-22 TO 5-LANES FROM ABBOTT LANE TO PROPOSED KY-393 INTERSECTION AND CONTINUING WITH 3-LANES TO EXISTING KY-393. (2004BOPC) | SP | D | 2010 | 840000
ADMINISTRATIVE MODIFICATION | 2010.095 | 2011-07-05 | KIPDA TIP AMENDMENT #1. KIPDA ID 1489. CHANGE FY. MOD | OLDHAM | 5 | 304.2 | 5-304.2 | KY-22 | 5.32 | 7.5 | RELIABILITY | MAJOR WIDENING(O) | RECONSTRUCT KY-22 TO 5-LANES FROM ABBOTT LANE TO PROPOSED KY-393 INTERSECTION AND CONTINUING WITH 3-LANES TO EXISTING KY-393. (2004BOPC) | SP | D | 2011 | 840000
|  |  |  | OLDHAM | 5 | 304.2 | 5-304.2 | KY-22 | 5.32 | 7.5 | RELIABILITY | MAJOR WIDENING(O) | RECONSTRUCT KY-22 TO 5-LANES FROM ABBOTT LANE TO PROPOSED KY-393 INTERSECTION AND CONTINUING WITH 3-LANES TO EXISTING KY-393. (2004BOPC) | SP | R | 2012 | 3310000
|  |  |  | OLDHAM | 5 | 304.2 | 5-304.2 | KY-22 | 5.32 | 7.5 | RELIABILITY | MAJOR WIDENING(O) | RECONSTRUCT KY-22 TO 5-LANES FROM ABBOTT LANE TO PROPOSED KY-393 INTERSECTION AND CONTINUING WITH 3-LANES TO EXISTING KY-393. (2004BOPC) | SP | U | 2012 | 2170000
ADMINISTRATIVE MODIFICATION | 2010.095 | 2011-07-05 | KIPDA TIP AMENDMENT #1. KIPDA ID 1489. ADD C PHASE. NEW | OLDHAM | 5 | 304.2 | 5-304.2 | KY-22 | 5.32 | 7.5 | RELIABILITY | MAJOR WIDENING(O) | RECONSTRUCT KY-22 TO 5-LANES FROM ABBOTT LANE TO PROPOSED KY-393 INTERSECTION AND CONTINUING WITH 3-LANES TO EXISTING KY-393. (2004BOPC) | SP | C | 2014 | 9000000
|  |  |  | OLDHAM | 5 | 367 | 5-367 | 0 | 0 | 0 | RELIABILITY | NEW ROUTE(O) | CONSTRUCT NEW ROUTE FR OLD HENRY INTERCHANGE AT I-265 TO CRESTWOOD BYPASS. (98CCR)(2004BOPP) | SB2 | R | 2011 | 8000000
|  |  |  | OLDHAM | 5 | 367 | 5-367 | 0 | 0 | 0 | RELIABILITY | NEW ROUTE(O) | CONSTRUCT NEW ROUTE FR OLD HENRY INTERCHANGE AT I-265 TO CRESTWOOD BYPASS. (98CCR)(2004BOPP) | SB2 | U | 2012 | 3300000
|  |  |  | OLDHAM | 5 | 367 | 5-367 | 0 | 0 | 0 | RELIABILITY | NEW ROUTE(O) | CONSTRUCT NEW ROUTE FR OLD HENRY INTERCHANGE AT I-265 TO CRESTWOOD BYPASS. (98CCR)(2004BOPP) | SP | C | 2012 | 4000000
|  |  |  | OLDHAM | 5 | 8201.01 | 5-8201.01 | 0 | 0 | 0 | RELIABILITY | NEW INTERCHANGE(O) | CONSTRUCT NEW I-71 OVERPASS WITH APPROACHES FROM COMMERCE PARKWAY TO PEAK ROAD. (06CCR) | SP | R | 2010 | 1050000
|  |  |  | OLDHAM | 5 | 8201.01 | 5-8201.01 | 0 | 0 | 0 | RELIABILITY | NEW INTERCHANGE(O) | CONSTRUCT NEW I-71 OVERPASS WITH APPROACHES FROM COMMERCE PARKWAY TO PEAK ROAD. (06CCR) | SP | U | 2010 | 1040000
|  |  |  | OLDHAM | 5 | 8201.01 | 5-8201.01 | 0 | 0 | 0 | RELIABILITY | NEW INTERCHANGE(O) | CONSTRUCT NEW I-71 OVERPASS WITH APPROACHES FROM COMMERCE PARKWAY TO PEAK ROAD. (06CCR) | SP | C | 2012 | 11440000
ADMINISTRATIVE MODIFICATION | 2010.143 | 2011-11-10 | ADD PROJECT TO STIP PER FONSI APPROVAL. NEW | RUSSELL |  |  | 8-108.00 | US-127 |  |  | RELIABILITY | RECONSTRUCTION(O) | US-127 FROM KY-55 NEAR FREEDOM TO THE JAMESTOWN BYPASS | SPB | R | 2012 | 3050000