## 2016 STIP PROJECT PHASES
MODIFICATION OR AMENDMENT | STIP ADMINISTRATIVE MODIFICATION OR AMENDMENT NUMBER | APPROVAL DATE | COMMENTS | FUND PREFIX | FEDERAL PROJECT NUMBER | COUNTY | ITEM ID | ROUTE NO. | LENGTH | BMP1 | EMP1 | PRIORITY | TYPEWORK | DESCRIPTION | PHASE | FAST ACT FUND | TYPE OF FUND | FISCAL YEAR SCHEDULE | TOTAL PHASE COST | FEDERAL PORTION | ILLUSTRATIVE PROJECT | STATUS OF FEDERAL FUNDS | CURRENT AMOUNT OF FEDERAL FUNDS OBLIGATED | CURRENT ADVANCE CONSTRUCT (AC) AMOUNT OF FEDERAL FUNDS | TOTAL PHASE COST CURRENT FEDERAL FUNDS PLUS CURRENT AC | FISCAL YEAR OF INITIAL PROGRAMMING OF FEDERAL FUNDS | FISCAL YEAR QUARTER OF INITIAL PROGRAMMING OF FEDERAL FUNDS | NAME OF LOCAL PUBLIC AGENCY
[6 empty] | ADAIR | 8-1068 | KY 704 |  | 11.905 | 11.913 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 704 (11.909) OVER UNNAMED STREAM (SR=53.5) (001B00078N) | D | STP | BRX | 2020 | 250000 | 250000 | NO |  |  |  | 0
[6 empty] | ALLEN | 3-1088 | CR 1328 | 0.02 | 0.35 | 0.39 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER BAYS FORK ON MITCHELL WEAVER ROAD (CR 1328) 2.1 MI W OF KY 1332 (002C00063N)(SR=31.5)(16CCN) | D | STP | BRZ | 2020 | 400000 | 400000 | NO |  |  |  | 0
[6 empty] | BALLARD | 1-1140.01 | US 51 | 0.97 | 7.327 | 8.297 | RELIABILITY | BRIDGE REPLACEMENT(P) | PE AND ENVIRONMENTAL FOR REPLACEMENT OF CAIRO BRIDGE AT OR BESIDE EXISTING LOCATION. | D | NHPP | BRO | 2019 | 3000000 | 3000000 | NO |  |  |  | 0
[6 empty] | BALLARD | 1-1140.02 | US 51 | 0.97 | 7.327 | 8.297 | RELIABILITY | BRIDGE REPLACEMENT(P) | PE AND ENVIRONMENTAL FOR REPLACEMENT OF CAIRO BRIDGE AT OR BESIDE EXISTING LOCATION. | D | NHPP | BRO | 2020 | 6500000 | 6500000 | NO |  |  |  | 0
[6 empty] | BARREN | 3-8819 | KY 90 | 8.414 | 0.16 | 8.574 | RELIABILITY | MAJOR WIDENING(O) | MAJOR WIDENING FROM SANDERS STREET IN CAVE CITY TO US 68 (GLASGOW OUTER LOOP) IN GLASGOW. (14CCN)(16CCR). | D | STP | STP | 2017 | 2200000 | 2200000 | NO |  |  |  | 0
[6 empty] | BARREN | 3-8819 | KY 90 | 8.414 | 0.16 | 8.574 | RELIABILITY | MAJOR WIDENING(O) | MAJOR WIDENING FROM SANDERS STREET IN CAVE CITY TO US 68 (GLASGOW OUTER LOOP) IN GLASGOW. (14CCN)(16CCR). | R | STP | STP | 2017 | 6000000 | 6000000 | NO |  |  |  | 0
[6 empty] | BARREN | 3-8819 | KY 90 | 8.414 | 0.16 | 8.574 | RELIABILITY | MAJOR WIDENING(O) | MAJOR WIDENING FROM SANDERS STREET IN CAVE CITY TO US 68 (GLASGOW OUTER LOOP) IN GLASGOW. (14CCN)(16CCR). | U | STP | STP | 2017 | 3500000 | 3500000 | NO |  |  |  | 0
[6 empty] | BARREN | 3-8821 | KY 1297 | 1.721 | 11.078 | 12.799 | RELIABILITY | MAJOR WIDENING(O) | MAJOR WIDENING FROM DONNELLY DRIVE TO US-31E (ROGER WELLS) IN GLASGOW AND WIDEN DONNELLY DRIVE. (14CCN) (16CCN) | R | STP | STP | 2017 | 3860000 | 3860000 | NO |  |  |  | 0
[6 empty] | BARREN | 3-8821 | KY 1297 | 1.721 | 11.078 | 12.799 | RELIABILITY | MAJOR WIDENING(O) | MAJOR WIDENING FROM DONNELLY DRIVE TO US-31E (ROGER WELLS) IN GLASGOW AND WIDEN DONNELLY DRIVE. (14CCN) (16CCN) | U | STP | STP | 2019 | 4100000 | 4100000 | NO |  |  |  | 0
[6 empty] | BATH | 9-8813 | US 60 | 0.2 | 16.3 | 16.5 | RELIABILITY | SAFETY(P) | INTERSECTION IMPROVEMENT AT KY 211 AND US 60 IN SALT LICK. (14CCN) | R | STP | STP | 2017 | 560000 | 560000 | NO |  |  |  | 0
[6 empty] | BATH | 9-8813 | US 60 | 0.2 | 16.3 | 16.5 | RELIABILITY | SAFETY(P) | INTERSECTION IMPROVEMENT AT KY 211 AND US 60 IN SALT LICK. (14CCN) | U | STP | STP | 2017 | 300000 | 300000 | NO |  |  |  | 0
[6 empty] | BATH | 9-8813 | US 60 | 0.2 | 16.3 | 16.5 | RELIABILITY | SAFETY(P) | INTERSECTION IMPROVEMENT AT KY 211 AND US 60 IN SALT LICK. (14CCN) | C | STP | STP | 2018 | 1000000 | 1000000 | NO |  |  |  | 0
[6 empty] | BELL | 11-1079 | KY 2011 | 0.1 | 8.35 | 8.65 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-2011 (MP 8.498) OVER RED BIRD CREEK; .55 MI SOUTH OF JCT KY 66; (SR=3.5) 007B00074N | C | STP | BRX | 2017 | 550000 | 550000 | NO |  |  |  | 0
|  |  | TIP FY 2016-19 ADM MOD #10 CHANGED FY ONLY IN TIP. NO CHANGE TO STIP. |  |  | BOONE | 6-14 | I 75 | 0.1 | 177.659 | 178.345 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | RECONSTRUCT THE KY-536 (MT. ZION ROAD) INTERCHANGE. (14CCR)(16CCR) | R | NHPP | IM | 2017 | 14700000 | 14700000 | NO |  |  |  | 0
|  |  | TIP FY 2016-19 ADM MOD #10 CHANGED FY ONLY IN TIP. NO CHANGE TO STIP. |  |  | BOONE | 6-14 | I 75 | 0.1 | 177.659 | 178.345 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | RECONSTRUCT THE KY-536 (MT. ZION ROAD) INTERCHANGE. (14CCR)(16CCR) | U | NHPP | IM | 2019 | 7280000 | 7280000 | NO |  |  |  | 0
|  |  | TIP FY 2016-19 ADM MOD #10 CHANGED FY ONLY IN TIP. NO CHANGE TO STIP. |  |  | BOONE | 6-14 | I 75 | 0.1 | 177.659 | 178.345 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | RECONSTRUCT THE KY-536 (MT. ZION ROAD) INTERCHANGE. (14CCR)(16CCR) | C | NHPP | IM | 2019 | 22080000 | 22080000 | YES |  |  |  | 0
[6 empty] | BOONE | 6-14.5 | I 75 | 1.5 | 178.039 | 180.106 | RELIABILITY | MINOR WIDENING(O) | ADD AUXILIARY LANES ON I-71/75 FROM KY 536 TO US 42 (NB & SB) AS PER THE INTERCHANGE JUSTIFICATION STUDY (IJS).(10CCR)(12CCR) | U | NHPP | IM | 2018 | 800000 | 800000 | NO |  |  |  | 0
[6 empty] | BOONE | 6-14.5 | I 75 | 1.5 | 178.039 | 180.106 | RELIABILITY | MINOR WIDENING(O) | ADD AUXILIARY LANES ON I-71/75 FROM KY 536 TO US 42 (NB & SB) AS PER THE INTERCHANGE JUSTIFICATION STUDY (IJS).(10CCR)(12CCR) | C | NHPP | IM | 2020 | 19800000 | 19800000 | NO |  |  |  | 0
|  |  | TIP FY 2016-19 ADM MOD #10 CHANGED FY ONLY IN TIP. NO CHANGE TO STIP. |  |  | BOONE | 6-18 | I 75 | 0.1 | 175.217 | 175.622 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | RECONSTRUCT THE KY-338 (RICHWOOD ROAD) INTERCHANGE. (FUNDING FOR IMR SHOWN UNDER 6-14.01) (10CCR)(12CCR)(14CCR)(16CCR) | R | NHPP | IM | 2019 | 26250000 | 26250000 | NO |  |  |  | 0
|  |  | TIP FY 2016-19 ADM MOD #10 CHANGED FY ONLY IN TIP. NO CHANGE TO STIP. |  |  | BOONE | 6-18 | I 75 | 0.1 | 175.217 | 175.622 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | RECONSTRUCT THE KY-338 (RICHWOOD ROAD) INTERCHANGE. (FUNDING FOR IMR SHOWN UNDER 6-14.01) (10CCR)(12CCR)(14CCR)(16CCR) | U | NHPP | IM | 2020 | 12480000 | 12480000 | NO |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2016.002 | 2016-10-04 | TIP FY 2016-19 ADM MOD #10 ADDING C PHASE. NEW |  |  | BOONE | 6-18 | I 75 | 0.1 | 175.217 | 175.622 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | RECONSTRUCT THE KY-338 (RICHWOOD ROAD) INTERCHANGE. (FUNDING FOR IMR SHOWN UNDER 6-14.01) (10CCR)(12CCR)(14CCR)(16CCR) | C | NHPP | IM | 2020 | 15000000 | 15000000 | NO |  |  |  | 0
|  |  | TIP FY 2016-19 ADM MOD #10 CHANGED FY AND AMOUNT IN TIP. NO CHANGE TO STIP. |  |  | BOONE | 6-158 | KY 536 | 2.94 | 10.3 | 13.24 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT KY-536 TO A 5-LANE URBAN SECTION FROM 1500' WEST OF US-42 TO I-75 (MP 10.3 TO MP 13.24). (DOES NOT INCLUDE INTERCHANGE RECONSTRUCTION) (00CCR) (10CCR)(12CCR)(14CCR)(16CCR) | C | STP | STP | 2017 | 12930000 | 12930000 | NO |  |  |  | 0
|  |  | TIP FY 2016-19 ADM MOD #10 ADDED PROJECT TO TIP. NO CHANGE TO STIP. |  |  | BOONE | 6-158.01 | KY 536 | 3 | 10.4 | 13.4 | RELIABILITY | PREFINANCD CONVRSN(O) | RECONSTRUCT KY-536 TO A 5-LANE URBAN SECTION FROM 1500' WEST OF US-42 TO I-75 (MP 10.4 TO MP 13.4). (ADDITIONAL FUNDING FOR C PHASE) (16CCR) | C | STP | STP | 2018 | 17700000 | 17700000 | NO |  |  |  | 0
|  |  | TIP FY 2016-19 ADM MOD #10 CHANGED FY ONLY IN TIP. NO CHANGE TO STIP. |  |  | BOONE | 6-367 | US 42 | 0.263 | 12.803 | 13.066 | SAFETY | SAFETY(P) | CONSTRUCT ADDITIONAL TURN LANES AT THE INTERSECTION OF KY 842 AND US 42.(12CCR) (16CCN) | C | CM | CM | 2017 | 2500000 | 2000000 | NO |  |  |  | 0
[6 empty] | BOONE | 6-400.11 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | NORTHERN KENTUCKY RIDESHARE PROGRAM. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C | SNK | SNK | 2017 | 44000 | 35200 | NO |  |  |  | 0
[6 empty] | BOONE | 6-400.12 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | NORTHERN KENTUCKY RIDESHARE PROGRAM. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C | SNK | SNK | 2017 | 44000 | 35200 | NO |  |  |  | 0
[6 empty] | BOONE | 6-400.13 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | NORTHERN KENTUCKY RIDESHARE PROGRAM. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C | SNK | SNK | 2018 | 44000 | 35200 | NO |  |  |  | 0
[6 empty] | BOONE | 6-400.14 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | NORTHERN KENTUCKY RIDESHARE PROGRAM. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C | SNK | SNK | 2019 | 44000 | 35200 | NO |  |  |  | 0
[6 empty] | BOONE | 6-400.15 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | NORTHERN KENTUCKY RIDESHARE PROGRAM. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C | SNK | SNK | 2020 | 44000 | 35200 | NO |  |  |  | 0
[6 empty] | BOONE | 6-401.11 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | OKI REGIONAL TRANSPORTATION PLANNING. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C | SNK | SNK | 2017 | 56000 | 44800 | NO |  |  |  | 0
[6 empty] | BOONE | 6-401.12 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | OKI REGIONAL TRANSPORTATION PLANNING. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C | SNK | SNK | 2017 | 56000 | 44800 | NO |  |  |  | 0
[6 empty] | BOONE | 6-401.13 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | OKI REGIONAL TRANSPORTATION PLANNING. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C | SNK | SNK | 2018 | 56000 | 44800 | NO |  |  |  | 0
[6 empty] | BOONE | 6-401.14 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | OKI REGIONAL TRANSPORTATION PLANNING. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C | SNK | SNK | 2019 | 56000 | 44800 | NO |  |  |  | 0
[6 empty] | BOONE | 6-401.15 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | OKI REGIONAL TRANSPORTATION PLANNING. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C | SNK | SNK | 2020 | 56000 | 44800 | NO |  |  |  | 0
[6 empty] | BOONE | 6-412 | US 42 | 0.2 | 8.4 | 8.6 | RELIABILITY | MATCHED FED FUNDS(O) | INTERSECTION IMPROVEMENT PROJECT AT US 42 AND RICE PIKE/HICKS PIKE. US 42 MP 8.4 TO 8.6. TOLL CREDITS. (2012BOP)(AR/W) | R | SNK | SNK | 2017 | 750000 | 600000 | NO |  |  |  | 0
[6 empty] | BOONE | 6-412 | US 42 | 0.2 | 8.4 | 8.6 | RELIABILITY | MATCHED FED FUNDS(O) | INTERSECTION IMPROVEMENT PROJECT AT US 42 AND RICE PIKE/HICKS PIKE. US 42 MP 8.4 TO 8.6. TOLL CREDITS. (2012BOP)(AR/W) | U | SNK | SNK | 2017 | 600000 | 480000 | NO |  |  |  | 0
[6 empty] | BOONE | 6-412 | US 42 | 0.2 | 8.4 | 8.6 | RELIABILITY | MATCHED FED FUNDS(O) | INTERSECTION IMPROVEMENT PROJECT AT US 42 AND RICE PIKE/HICKS PIKE. US 42 MP 8.4 TO 8.6. TOLL CREDITS. (2012BOP)(AR/W) | C | SNK | SNK | 2017 | 2750000 | 2200000 | NO |  |  |  | 0
[6 empty] | BOONE | 6-415 | KY 237 | 0.45 | 10.9 | 11.35 | RELIABILITY | MATCHED FED FUNDS(O) | PROVIDE ADDITIONAL LEFT TURN LANE ONTO WORLDWIDE BLVD FROM KY 237. ADD ADDITIONAL THROUGH LANES ON KY 237 NORTH OF KY 2846 (TANNERS LN). PROVIDE LANE EXTENSION ON WORLDWIDE BLVD FROM KY 237. (2012BOP)(ADM. BY KYTC) | R | SNK | SNK | 2017 | 1000000 | 800000 | NO |  |  |  | 0
[6 empty] | BOONE | 6-415 | KY 237 | 0.45 | 10.9 | 11.35 | RELIABILITY | MATCHED FED FUNDS(O) | PROVIDE ADDITIONAL LEFT TURN LANE ONTO WORLDWIDE BLVD FROM KY 237. ADD ADDITIONAL THROUGH LANES ON KY 237 NORTH OF KY 2846 (TANNERS LN). PROVIDE LANE EXTENSION ON WORLDWIDE BLVD FROM KY 237. (2012BOP)(ADM. BY KYTC) | U | SNK | SNK | 2017 | 500000 | 400000 | NO |  |  |  | 0
[6 empty] | BOONE | 6-415 | KY 237 | 0.45 | 10.9 | 11.35 | RELIABILITY | MATCHED FED FUNDS(O) | PROVIDE ADDITIONAL LEFT TURN LANE ONTO WORLDWIDE BLVD FROM KY 237. ADD ADDITIONAL THROUGH LANES ON KY 237 NORTH OF KY 2846 (TANNERS LN). PROVIDE LANE EXTENSION ON WORLDWIDE BLVD FROM KY 237. (2012BOP)(ADM. BY KYTC) | C | SNK | SNK | 2017 | 3000000 | 2400000 | NO |  |  |  | 0
[6 empty] | BOONE | 6-417 | PV 1011 | 0.753 | 0.747 | 1.5 | RELIABILITY | NEW ROUTE(O) | EXTENSION OF WENDELL FORD BLVD TO AERO PKWY, 0.48 MILES. (2012BOP) | C | SNK | SNK | 2017 | 2366717 | 1893373.6 | NO |  |  |  | 0
|  |  | TIP FY 2016-19 ADM MOD #10. TIP MOD SHOWS 50,000 SNK AND 12,500 LOCAL. NO CHANGE TO STIP. |  |  | BOONE | 6-422 | CR 1002 | 0.558 | 2.1 | 2.658 | RELIABILITY | MATCHED FED FUNDS(O) | RECONSTRUCTION OF THE INTERSECTION OF CAMP ERNST ROAD AND LONGBRANCH ROAD. WIDENING OF 1,900 FEET OF LONGBRANCH ROAD. (2012BOP) | R | SNK | SNK | 2017 | 50000 | 40000 | NO |  |  |  | 0
|  |  | TIP FY 2016-19 ADM MOD #10. TIP MOD SHOWS 65,519 SNK AND 16,380 LOCAL. NO CHANGE TO STIP. |  |  | BOONE | 6-422 | CR 1002 | 0.558 | 2.1 | 2.658 | RELIABILITY | MATCHED FED FUNDS(O) | RECONSTRUCTION OF THE INTERSECTION OF CAMP ERNST ROAD AND LONGBRANCH ROAD. WIDENING OF 1,900 FEET OF LONGBRANCH ROAD. (2012BOP) | U | SNK | SNK | 2017 | 112000 | 89600 | NO |  |  |  | 0
|  |  | TIP FY 2016-19 ADM MOD #10 CHANGED FY ONLY IN TIP. NO CHANGE TO STIP. |  |  | BOONE | 6-422 | CR 1002 | 0.558 | 2.1 | 2.658 | RELIABILITY | MATCHED FED FUNDS(O) | RECONSTRUCTION OF THE INTERSECTION OF CAMP ERNST ROAD AND LONGBRANCH ROAD. WIDENING OF 1,900 FEET OF LONGBRANCH ROAD. (2012BOP) | C | SNK | SNK | 2017 | 524640 | 419712 | NO |  |  |  | 0
[6 empty] | BOONE | 6-423 | KY 3060 | 0.45 | 1.5 | 1.95 | RELIABILITY | MATCHED FED FUNDS(O) | CORRECT GEOMETRIC DEFICIENCIES AND ADD LEFT TURN LANES ON FROGTOWN ROAD AT TRIPLE CROWN BLVD AND CEDARWOOD.(2012BOP)(ADM. BY KYTC) | R | SNK | SNK | 2017 | 200000 | 160000 | NO |  |  |  | 0
[6 empty] | BOONE | 6-423 | KY 3060 | 0.45 | 1.5 | 1.95 | RELIABILITY | MATCHED FED FUNDS(O) | CORRECT GEOMETRIC DEFICIENCIES AND ADD LEFT TURN LANES ON FROGTOWN ROAD AT TRIPLE CROWN BLVD AND CEDARWOOD.(2012BOP)(ADM. BY KYTC) | U | SNK | SNK | 2017 | 120000 | 96000 | NO |  |  |  | 0
[6 empty] | BOONE | 6-423 | KY 3060 | 0.45 | 1.5 | 1.95 | RELIABILITY | MATCHED FED FUNDS(O) | CORRECT GEOMETRIC DEFICIENCIES AND ADD LEFT TURN LANES ON FROGTOWN ROAD AT TRIPLE CROWN BLVD AND CEDARWOOD.(2012BOP)(ADM. BY KYTC) | C | SNK | SNK | 2018 | 1200000 | 960000 | NO |  |  |  | 0
[6 empty] | BOONE | 6-431 |  |  |  |  | RELIABILITY | STRATGIC CORR STDY(O) | STUDY ALL MAJOR HIGHWAY CORRIDOR OPTIONS TO RELIEVE TRAFFIC IN THE BRENT SPENCE BRIDGE CORRIDOR, (INCLUDES IN-DEPTH LOOK AT EASTERN BYPASS OF GREATER CINCINNATI), AS WELL AS POSSIBLE TRAFFIC MANAGEMENT IMPROVEMENTS AT THE EXISTING BRENT SPENCE CROSSING. | P | NHPP | NH | 2017 | 2000000 | 2000000 | NO |  |  |  | 0
[6 empty] | BOONE | 6-700 | CR 1057L |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | TWO-LANE EXTENSION OF EXISTING VETERANS WAY BETWEEN KY 18 AND KY 237. LPA PROJECT (LET BY COUNTY)(2012BOP) | C | SNK | SNK | 2017 | 1640000 | 1312000 | NO |  |  |  | 0
[6 empty] | BOONE | 6-966.04 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | DEDICATED FEDERAL-AID STP FUNDS EARMARKED FOR NKY URBANIZED AREA AND SUBJECT TO MPO CONTROL FOR FY 2016. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C | SNK | SNK | 2017 | 14500000 | 11600000 | NO |  |  |  | 0
[6 empty] | BOONE | 6-966.05 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | DEDICATED FEDERAL-AID STP FUNDS EARMARKED FOR NKY URBANIZED AREA AND SUBJECT TO MPO CONTROL FOR FY 2017 (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C | SNK | SNK | 2017 | 8800000 | 7040000 | NO |  |  |  | 0
[6 empty] | BOONE | 6-966.06 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | DEDICATED FEDERAL-AID STP FUNDS EARMARKED FOR NKY URBANIZED AREA AND SUBJECT TO MPO CONTROL FOR FY 2018 (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C | SNK | SNK | 2018 | 8900000 | 7120000 | NO |  |  |  | 0
[6 empty] | BOONE | 6-966.07 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | DEDICATED FEDERAL-AID STP FUNDS EARMARKED FOR NKY URBANIZED AREA AND SUBJECT TO MPO CONTROL FOR FY 2019 (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C | SNK | SNK | 2019 | 9100000 | 7280000 | NO |  |  |  | 0
[6 empty] | BOONE | 6-966.08 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | DEDICATED FEDERAL-AID STP FUNDS EARMARKED FOR NKY URBANIZED AREA AND SUBJECT TO MPO CONTROL FOR FY 2020. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C | SNK | SNK | 2020 | 9100000 | 7280000 | NO |  |  |  | 0
[6 empty] | BOONE | 6-1087 | KY 842 | 0.074 | 0.094 | 0.141 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER NS (CNO&TP)RR ON RICHARDSON ROAD (KY 842) 0.14 MI E OF US 25 NEAR INDEPENDENCE (008B00092N)(SR=43) | D | STP | BRX | 2020 | 500000 | 500000 | NO |  |  |  | 0
|  |  | TIP FY 2016-19 ADM MOD #10. CHANGED FY AND AMOUNT IN TIP. NO CHANGE TO STIP. |  |  | BOONE | 6-8001.21 | KY 237 | 3.119 | 2.251 | 5.37 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT AND WIDEN KY 237 FROM VALLEY VIEW DRIVE TO ROGERS LANE. (14CCR) | C | STP | STP | 2018 | 13180000 | 13180000 | NO |  |  |  | 0
|  |  | TIP FY 2016-19 ADM MOD #10. ADDED PROJECT TO TIP. NO CHANGE TO STIP. |  |  | BOONE | 6-8001.22 | KY 237 |  | 2.251 | 5.37 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT AND WIDEN KY 237 FROM VALLEY VIEW DRIVE TO ROGERS LANE. | C | STP | STP | 2019 | 9000000 | 9000000 | NO |  |  |  | 0
|  |  | TIP FY 2016-19 ADM MOD #10. CHANGED FY IN TIP. NO CHANGE TO STIP. |  |  | BOONE | 6-8952 | KY 338 |  |  |  | RELIABILITY | SAFETY(P) | PHASE II - PEDESTRIAN SAFETY PROJECT TO RECONSTRUCT THE INTERSECTION OF IDLEWILD ROAD AND INSTALL SIDEWALKS ALONG IDLEWILD ROAD AND JEFFERSON STREET. (16CCN) | R | STP | STP | 2017 | 90000 | 90000 | NO |  |  |  | 0
|  |  | TIP FY 2016-19 ADM MOD #10. CHANGED FY IN TIP. NO CHANGE TO STIP. |  |  | BOONE | 6-8952 | KY 338 |  |  |  | RELIABILITY | SAFETY(P) | PHASE II - PEDESTRIAN SAFETY PROJECT TO RECONSTRUCT THE INTERSECTION OF IDLEWILD ROAD AND INSTALL SIDEWALKS ALONG IDLEWILD ROAD AND JEFFERSON STREET. (16CCN) | U | STP | STP | 2017 | 125000 | 125000 | NO |  |  |  | 0
|  |  | TIP FY 2016-19 ADM MOD #10. CHANGED FY IN TIP. NO CHANGE TO STIP. |  |  | BOONE | 6-8952 | KY 338 |  |  |  | RELIABILITY | SAFETY(P) | PHASE II - PEDESTRIAN SAFETY PROJECT TO RECONSTRUCT THE INTERSECTION OF IDLEWILD ROAD AND INSTALL SIDEWALKS ALONG IDLEWILD ROAD AND JEFFERSON STREET. (16CCN) | C | STP | STP | 2017 | 500000 | 500000 | NO |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2016.002 | 2016-10-04 | TIP FY 2016-19 ADM MOD #10 ADDING PROJECT PER TIP MOD. NEW |  |  | BOONE | 6-9010 | US 42 | 5.673 | 0 | 5.673 | SAFETY | SAFETY(P) | PERFORM LOW COST SAFETY IMPROVEMENTS ON US 42 FROM THE GALLATIN/BOONE COUNTY LINE TO KY 338. (2014BOP) | C | HSIP | SAF | 2017 | 1500000 | 1500000 | NO |  |  |  | 0
[6 empty] | BOURBON | 7-365.1 | KY 3364 | 0.1 | 5.389 | 5.489 | RELIABILITY | BRIDGE REHAB(P) | STRUCTURE OVER SCOTTS CREEK ON KY 3364, 0.7 MILE NORTH OF US 460 AT NORTH MIDDLETOWN (BRIDGE IMPROVEMENTS). (03KYDN)(2012BOP) (16CCN) | D | KYD | KYD | 2017 | 18723 | 18723 | NO |  |  |  | 0
[6 empty] | BOURBON | 7-1124 | CR 1308 | 0.1 | 3.538 | 3.638 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON CR-1308 (MP 3.588) OVER TOWNSEND CREEK; .9 MI E OF JCT KY 353; (STRUCTURALLY DEFICIENT, SR=33.2) 009C00043N | R | STP | BRZ | 2017 | 90000 | 90000 | NO |  |  |  | 0
[6 empty] | BOURBON | 7-1124 | CR 1308 | 0.1 | 3.538 | 3.638 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON CR-1308 (MP 3.588) OVER TOWNSEND CREEK; .9 MI E OF JCT KY 353; (STRUCTURALLY DEFICIENT, SR=33.2) 009C00043N | U | STP | BRZ | 2017 | 75000 | 75000 | NO |  |  |  | 0
[6 empty] | BOURBON | 7-1124 | CR 1308 | 0.1 | 3.538 | 3.638 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON CR-1308 (MP 3.588) OVER TOWNSEND CREEK; .9 MI E OF JCT KY 353; (STRUCTURALLY DEFICIENT, SR=33.2) 009C00043N | C | STP | BRZ | 2017 | 765000 | 765000 | NO |  |  |  | 0
[6 empty] | BOURBON | 7-8705 | US 460 | 6.302 | 1.394 | 7.696 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT US 460 FROM RUSSELL CAVE ROAD TO US 27 BYPASS IN PARIS; MP 1.394 TO MP 7.696.(12CCN)(14CCR)(16CCR) | R | STP | STP | 2017 | 3000000 | 3000000 | NO |  |  |  | 0
[6 empty] | BOURBON | 7-8705 | US 460 | 6.302 | 1.394 | 7.696 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT US 460 FROM RUSSELL CAVE ROAD TO US 27 BYPASS IN PARIS; MP 1.394 TO MP 7.696.(12CCN)(14CCR)(16CCR) | U | STP | STP | 2017 | 2500000 | 2500000 | NO |  |  |  | 0
[6 empty] | BOURBON | 7-8705 | US 460 | 6.302 | 1.394 | 7.696 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT US 460 FROM RUSSELL CAVE ROAD TO US 27 BYPASS IN PARIS; MP 1.394 TO MP 7.696.(12CCN)(14CCR)(16CCR) | C | STP | STP | 2017 | 20000000 | 20000000 | NO |  |  |  | 0
[6 empty] | BOURBON | 7-8705.01 | US 460 | 6.302 | 1.394 | 7.696 | RELIABILITY | PREFINANCD CONVRSN(O) | RECONSTRUCT US 460 FROM RUSSELL CAVE ROAD TO US 27 BYPASS IN PARIS; MP 1.394 TO MP 7.696. (ADDITIONAL FUNDING FOR C PHASE) (16CCR) | C | STP | STP | 2018 | 7700000 | 7700000 | NO |  |  |  | 0
[6 empty] | BOYD | 9-208.02 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | FEDERAL 'STP' FUNDS DEDICATED TO HUNTINGTON-ASHLAND MPO FOR FY 2016. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C | SAH | SAH | 2017 | 1150000 | 920000 | NO |  |  |  | 0
[6 empty] | BOYD | 9-208.03 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | FEDERAL 'STP' FUNDS DEDICATED TO HUNTINGTON-ASHLAND MPO FOR FY 2017. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C | SAH | SAH | 2017 | 1600000 | 1280000 | NO |  |  |  | 0
[6 empty] | BOYD | 9-208.04 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | FEDERAL 'STP' FUNDS DEDICATED TO HUNTINGTON-ASHLAND MPO FOR FY 2018. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C | SAH | SAH | 2018 | 1600000 | 1280000 | NO |  |  |  | 0
[6 empty] | BOYD | 9-208.05 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | FEDERAL 'STP' FUNDS DEDICATED TO HUNTINGTON-ASHLAND MPO FOR FY 2019. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C | SAH | SAH | 2019 | 1600000 | 1280000 | NO |  |  |  | 0
[6 empty] | BOYD | 9-208.06 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | FEDERAL 'STP' FUNDS DEDICATED TO HUNTINGTON-ASHLAND MPO FOR FY 2020. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C | SAH | SAH | 2020 | 1600000 | 1280000 | NO |  |  |  | 0
[6 empty] | BOYLE | 7-242.01 | US 68 |  | 6.4 | 6.418 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE U.S. 68 AND U.S. 150 BRIDGE OVER CHAPLIN RIVER, PERRYVILLE. 011B00042N (2005HPP-KY134)(EARMARK DOES NOT COVER TOTAL PROJECT COST OF $1,790,000). | C | HPP | HPP | 2017 | 364940 | 364940 | NO |  |  |  | 0
[6 empty] | BRACKEN | 6-1074 | KY 8 | 0.1 | 4.171 | 4.271 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-8 (MP 4.221) OVER SNAG CREEK; 1 MI W OF JCT KY 1109; (STRUCTURALLY DEFICIENT, SR=48.3) 012B00005N | R | NHPP | BRO | 2017 | 150000 | 150000 | NO |  |  |  | 0
[6 empty] | BRACKEN | 6-1074 | KY 8 | 0.1 | 4.171 | 4.271 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-8 (MP 4.221) OVER SNAG CREEK; 1 MI W OF JCT KY 1109; (STRUCTURALLY DEFICIENT, SR=48.3) 012B00005N | C | NHPP | BRO | 2017 | 2600000 | 2600000 | NO |  |  |  | 0
[6 empty] | BREATHITT | 10-1105 | CR 1165 | 0.048 | 0.092 | 0.14 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON MARIE ROBERTS ROAD (CR 1165) OVER TROUBLESOME CREEK 0.1 MILE SW OF KY 15(SR 27.1) 013C00011N | C | STP | BRZ | 2018 | 1610000 | 1610000 | NO |  |  |  | 0
[6 empty] | BREATHITT | 10-1110 | KY 378 | 0.028 | 0.672 | 0.7 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER FROZEN CREEK ON KY 378 0.7 MI N OF KY 1812. (013B00050N)(SR=41) | D | STP | BRX | 2019 | 250000 | 250000 | NO |  |  |  | 0
[6 empty] | BRECKINRIDGE | 4-1090 | CR 1021 | 0.02 | 1.42 | 1.44 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER SINKING CREEK ON DENTS BRIDGE ROAD (CR 1021) 1.4 MI W OF KY 333 (014C00003N)(SR=26) | D | STP | BRZ | 2017 | 130000 | 130000 | NO |  |  |  | 0
[6 empty] | BRECKINRIDGE | 4-1090 | CR 1021 | 0.02 | 1.42 | 1.44 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER SINKING CREEK ON DENTS BRIDGE ROAD (CR 1021) 1.4 MI W OF KY 333 (014C00003N)(SR=26) | R | STP | BRZ | 2019 | 30000 | 30000 | NO |  |  |  | 0
[6 empty] | BRECKINRIDGE | 4-1090 | CR 1021 | 0.02 | 1.42 | 1.44 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER SINKING CREEK ON DENTS BRIDGE ROAD (CR 1021) 1.4 MI W OF KY 333 (014C00003N)(SR=26) | U | STP | BRZ | 2019 | 50000 | 50000 | NO |  |  |  | 0
[6 empty] | BRECKINRIDGE | 4-1090 | CR 1021 | 0.02 | 1.42 | 1.44 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER SINKING CREEK ON DENTS BRIDGE ROAD (CR 1021) 1.4 MI W OF KY 333 (014C00003N)(SR=26) | C | STP | BRZ | 2020 | 500000 | 500000 | NO |  |  |  | 0
[6 empty] | BRECKINRIDGE | 4-8901 | KY 86 |  |  |  | RELIABILITY | SAFETY(P) | RECONSTRUCTION STUDY ON KY 86 FROM MP 15.957 TO MP 26.137. (16CCN) | P | STP | STP | 2018 | 500000 | 500000 | NO |  |  |  | 0
[6 empty] | BULLITT | 5-150.2 | KY 44 | 0.5 | 18.38 | 18.8 | SAFETY | SAFETY(P) | RECONSTRUCT KY-44 AT BOGARD/LLOYD LANE. (06CCN) (10CCR)(12CCR)(16CCR) | C | STP | STP | 2017 | 1280000 | 1280000 | NO |  |  |  | 0
[6 empty] | BULLITT | 5-391.2 | KY 480 | 0.83 | 2.01 | 2.84 | RELIABILITY | RECONSTRUCTION(O) | WIDEN CEDAR GROVE ROAD (KY 480) FROM CEDAR GROVE ELEMENTARY SCHOOL TO VALLEY VIEW DRIVE. (12CCR)(14CCR) (SEE 5-391.3 FOR INTERCHANGE IMPROVEMENTS) | C | STP | STP | 2017 | 4790000 | 4790000 | NO |  |  |  | 0
[6 empty] | BULLITT | 5-391.3 | KY 480 | 0.83 | 1.1 | 1.11 | RELIABILITY | RECONSTRUCTION(O) | IMPROVEMENTS TO THE I-65/KY 480 INTERCHANGE INCLUDING RAMP IMPROVEMENTS AND TURNING LANES. (12CCR)(14CCR)(2014BOP)(16CCR) | R | NHPP | NH | 2017 | 1800000 | 1800000 | NO |  |  |  | 0
[6 empty] | BULLITT | 5-391.3 | KY 480 | 0.83 | 1.1 | 1.11 | RELIABILITY | RECONSTRUCTION(O) | IMPROVEMENTS TO THE I-65/KY 480 INTERCHANGE INCLUDING RAMP IMPROVEMENTS AND TURNING LANES. (12CCR)(14CCR)(2014BOP)(16CCR) | U | NHPP | NH | 2017 | 500000 | 500000 | NO |  |  |  | 0
[6 empty] | BULLITT | 5-391.3 | KY 480 | 0.83 | 1.1 | 1.11 | RELIABILITY | RECONSTRUCTION(O) | IMPROVEMENTS TO THE I-65/KY 480 INTERCHANGE INCLUDING RAMP IMPROVEMENTS AND TURNING LANES. (12CCR)(14CCR)(2014BOP)(16CCR) | C | NHPP | NH | 2018 | 5200000 | 5200000 | NO |  |  |  | 0
[6 empty] | BULLITT | 5-538 | I 65 |  |  |  | RELIABILITY | NEW INTERCHANGE(O) | CONSTRUCT NEW I-65 INTERCHANGE BETWEEN KY 480 AND KY 245. | D | NHPP | NH | 2017 | 2500000 | 2500000 | NO |  |  |  | 0
[6 empty] | BULLITT | 5-538 | I 65 |  |  |  | RELIABILITY | NEW INTERCHANGE(O) | CONSTRUCT NEW I-65 INTERCHANGE BETWEEN KY 480 AND KY 245. | R | NHPP | NH | 2017 | 500000 | 500000 | NO |  |  |  | 0
[6 empty] | BULLITT | 5-538 | I 65 |  |  |  | RELIABILITY | NEW INTERCHANGE(O) | CONSTRUCT NEW I-65 INTERCHANGE BETWEEN KY 480 AND KY 245. | U | NHPP | NH | 2017 | 500000 | 500000 | NO |  |  |  | 0
[6 empty] | BULLITT | 5-538 | I 65 |  |  |  | RELIABILITY | NEW INTERCHANGE(O) | CONSTRUCT NEW I-65 INTERCHANGE BETWEEN KY 480 AND KY 245. | C | NHPP | NH | 2018 | 25000000 | 25000000 | NO |  |  |  | 0
[6 empty] | BULLITT | 5-1056 | KY 61 | 0.1 | 7.559 | 7.659 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-61 (MP 7.609) OVER BARLEY CREEK; .10 MI NORTH OF JCT KY 251; (STRUCTURALLY DEFICIENT, SR=36.5) 015B00013N | R | NHPP | BRO | 2017 | 20000 | 20000 | NO |  |  |  | 0
[6 empty] | BULLITT | 5-1056 | KY 61 | 0.1 | 7.559 | 7.659 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-61 (MP 7.609) OVER BARLEY CREEK; .10 MI NORTH OF JCT KY 251; (STRUCTURALLY DEFICIENT, SR=36.5) 015B00013N | C | NHPP | BRO | 2017 | 450000 | 450000 | NO |  |  |  | 0
[6 empty] | BULLITT | 5-8509 | KY 245 | 1.99 | 4.425 | 6.415 | RELIABILITY | MINOR WIDENING(O) | WIDEN KY-245 FROM BERNHEIM FOREST TO THE COMMUNITY COLLEGE. (08CCN)(10CCR)(14CCR)(16CCR) | C | STP | STP | 2017 | 10510000 | 10510000 | NO |  |  |  | 0
[6 empty] | BUTLER | 3-2042 | WN 9007 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | UPGRADE THE NATCHER PARKWAY TO INTERSTATE STANDARDS IN ORDER TO ESTABLISH "I-565"SPUR ROUTE BETWEEN BOWLING GREEN AND OWENSBORO. | C | NHPP | NH | 2017 | 10000000 | 10000000 | NO |  |  |  | 0
[6 empty] | BUTLER | 3-2042.01 | WN 9007 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | UPGRADE THE NATCHER PARKWAY TO INTERSTATE STANDARDS IN ORDER TO ESTABLISH "I-565"SPUR ROUTE BETWEEN BOWLING GREEN AND OWENSBORO. | C | NHPP | NH | 2019 | 10000000 | 10000000 | NO |  |  |  | 0
[6 empty] | CALDWELL | 2-1095 | KY 276 | 0.1 |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE KY 276 DRAINAGE STRUCTURE. (FLOOD REPAIR PROJECT) | R | STP | BRX | 2017 | 50000 | 50000 | NO |  |  |  | 0
[6 empty] | CALDWELL | 2-1095 | KY 276 | 0.1 |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE KY 276 DRAINAGE STRUCTURE. (FLOOD REPAIR PROJECT) | U | STP | BRX | 2017 | 25000 | 25000 | NO |  |  |  | 0
[6 empty] | CALDWELL | 2-1095 | KY 276 | 0.1 |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE KY 276 DRAINAGE STRUCTURE. (FLOOD REPAIR PROJECT) | C | STP | BRX | 2018 | 450000 | 450000 | NO |  |  |  | 0
[6 empty] | CALLOWAY | 1-1149 | CR 1411 | 0.04 | 1.027 | 1.067 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON CARLTON RD (CR 1411) OVER W FORK ROCKHOUSE CREEK 0.1 MILE W OF COLLINS RD (CR 1505)(SR 28.1)018C00110N (AR/W) | U | STP | BRZ | 2017 | 100000 | 100000 | NO |  |  |  | 0
[6 empty] | CALLOWAY | 1-1149 | CR 1411 | 0.04 | 1.027 | 1.067 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON CARLTON RD (CR 1411) OVER W FORK ROCKHOUSE CREEK 0.1 MILE W OF COLLINS RD (CR 1505)(SR 28.1)018C00110N (AR/W) | C | STP | BRZ | 2017 | 370000 | 370000 | NO |  |  |  | 0
[6 empty] | CALLOWAY | 1-8952 | CS 1047 |  |  |  | SAFETY | SAFETY(P) | IMPROVE N 16TH STREET FROM KY 1327 (5 POINTS) TO KY 121. (16CCN) | D | STP | STP | 2017 | 400000 | 400000 | NO |  |  |  | 0
[6 empty] | CALLOWAY | 1-8952 | CS 1047 |  |  |  | SAFETY | SAFETY(P) | IMPROVE N 16TH STREET FROM KY 1327 (5 POINTS) TO KY 121. (16CCN) | R | STP | STP | 2018 | 2000000 | 2000000 | NO |  |  |  | 0
[6 empty] | CALLOWAY | 1-8952 | CS 1047 |  |  |  | SAFETY | SAFETY(P) | IMPROVE N 16TH STREET FROM KY 1327 (5 POINTS) TO KY 121. (16CCN) | U | STP | STP | 2020 | 2000000 | 2000000 | NO |  |  |  | 0
[6 empty] | CAMPBELL | 6-183 | I 471 | 5.016 | 0 | 5.016 | RELIABILITY | RECONSTRUCTION(O) | STUDY AND REHABILITATE THE I-471 CORRIDOR, CAMPBELL COUNTY, KENTUCKY. (SEE ALSO 6-8104.00)(2005HPP-KY120) | C | HPP | HPP | 2017 | 1439840 | 1439840 | NO |  |  |  | 0
|  |  | TIP FY 2016-19 ADM MOD #10 CHANGED FY ONLY IN TIP. NO CHANGE TO STIP. |  |  | CAMPBELL | 6-407 | KY 9 | 0.15 | 21.82 | 21.97 | SAFETY | SAFETY(P) | KY 9 EXTENSION, CAMPBELL COUNTY. (2006KYD). (KYD FUNDING MOVED FROM 6-8101.02) | R | STP | STP | 2017 | 100000 | 100000 | NO |  |  |  | 0
|  |  | TIP FY 2016-19 ADM MOD #10 CHANGED FY ONLY IN TIP. NO CHANGE TO STIP. |  |  | CAMPBELL | 6-407 | KY 9 | 0.15 | 21.82 | 21.97 | SAFETY | SAFETY(P) | KY 9 EXTENSION, CAMPBELL COUNTY. (2006KYD). (KYD FUNDING MOVED FROM 6-8101.02) | C | STP | STP | 2017 | 2170000 | 2170000 | NO |  |  |  | 0
[6 empty] | CAMPBELL | 6-425 | KY 1120 | 0.292 | 1.375 | 1.667 | RELIABILITY | MATCHED FED FUNDS(O) | CONSTRUCT A SIDEWALK ON THE SOUTH SIDE OF KY 1120 (MEMORIAL PARKWAY) FROM PAVILION PARKWAY TO WILSON ROAD OVER I-471 IN NEWPORT. (2012BOP) | U | SNK | SNK | 2017 | 25000 | 20000 | NO |  |  |  | 0
[6 empty] | CAMPBELL | 6-427 | KY 1892 | 0.173 | 2.395 | 2.568 | RELIABILITY | MATCHED FED FUNDS(O) | ROADWAY REHABILITATION ON CAROTHERS ROAD FROM MONMOUTH STREET (US 27) TO RIGHT TURN LANE INTO NEWPORT SHOPPING CENTER. | C | SNK | SNK | 2017 | 1005052 | 804041.6 | NO |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2016.002 | 2016-10-04 | TIP FY 2016-19 ADM MOD #10 ADDING PROJECT TO TIP AND STIP. NEW |  |  | CAMPBELL | 6-434 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | NEWPORT RIVERFRONT COMMONS - CONSTRUCT TWO NEW PEDESTRIAN/BICYCLE BRIDGES TO CONNECT BOTH SIDES OF THE TAYLOR SOUTHGATE BRIDGE TO THE TRAILS ON TOP OF THE LEVEE (2016BOP) | D | SNK | SNK | 2016 | 10000 | 10000 | NO |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2016.002 | 2016-10-04 | TIP FY 2016-19 ADM MOD #10 ADDING PROJECT TO TIP AND STIP. NEW |  |  | CAMPBELL | 6-434 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | NEWPORT RIVERFRONT COMMONS - CONSTRUCT TWO NEW PEDESTRIAN/BICYCLE BRIDGES TO CONNECT BOTH SIDES OF THE TAYLOR SOUTHGATE BRIDGE TO THE TRAILS ON TOP OF THE LEVEE (2016BOP) | C | SNK | SNK | 2017 | 1097427 | 1097427 | NO |  |  |  | 0
[6 empty] | CAMPBELL | 6-1077 | KY 10 |  | 4.567 | 4.607 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 10 OVER TWELVE MILE CREEK SE OF KY 1997 (SR 6.4) 019B00006N | R | STP | BRX | 2017 | 150000 | 150000 | NO |  |  |  | 0
[6 empty] | CAMPBELL | 6-1077 | KY 10 |  | 4.567 | 4.607 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 10 OVER TWELVE MILE CREEK SE OF KY 1997 (SR 6.4) 019B00006N | U | STP | BRX | 2017 | 130000 | 130000 | NO |  |  |  | 0
[6 empty] | CAMPBELL | 6-1077 | KY 10 |  | 4.567 | 4.607 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 10 OVER TWELVE MILE CREEK SE OF KY 1997 (SR 6.4) 019B00006N | C | STP | BRX | 2018 | 1630000 | 1630000 | NO |  |  |  | 0
[6 empty] | CAMPBELL | 6-1085 | KY 8 | 0.054 | 18.017 | 18.071 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER TWELVEMILE CREEK ON KY 8 0.1 MI N OF NEISES ROAD (CR 1009). (019B00003N)(SR=46.1) | D | STP | BRX | 2017 | 280000 | 280000 | NO |  |  |  | 0
[6 empty] | CAMPBELL | 6-1085 | KY 8 | 0.054 | 18.017 | 18.071 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER TWELVEMILE CREEK ON KY 8 0.1 MI N OF NEISES ROAD (CR 1009). (019B00003N)(SR=46.1) | R | STP | BRX | 2019 | 200000 | 200000 | NO |  |  |  | 0
[6 empty] | CAMPBELL | 6-1085 | KY 8 | 0.054 | 18.017 | 18.071 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER TWELVEMILE CREEK ON KY 8 0.1 MI N OF NEISES ROAD (CR 1009). (019B00003N)(SR=46.1) | U | STP | BRX | 2019 | 190000 | 190000 | NO |  |  |  | 0
[6 empty] | CAMPBELL | 6-8105.01 | I 275 |  |  |  | RELIABILITY | NEW ROUTE(O) | TRANSPORTATION IMPROVEMENTS TO AA-I-275 CONNECTOR, CAMPBELL COUNTY. (2005HPP-KY155)(SEE 6-8105.00 FOR "KYD" COMPONENT)(06CCR)(10CCR) | C | HPP | HPP | 2017 | 940402 | 940402 | NO |  |  |  | 0
[6 empty] | CAMPBELL | 6-8105.02 | I 275 |  |  |  | RELIABILITY | NEW ROUTE(O) | TRANSPORTATION IMPROVEMENTS TO AA-I-275 CONNECTOR, CAMPBELL COUNTY. (2005HPP-KY166)(SEE 6-8105.00 FOR "KYD" COMPONENT) | C | HPP | HPP | 2017 | 7249112 | 7249112 | NO |  |  |  | 0
[6 empty] | CAMPBELL | 6-8105.03 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | CONSTRUCT NEW TECHNOLOGY TRIANGLE ACCESS ROAD, CAMPBELL COUNTY, KENTUCKY. (2005HPP-KY126)(2006BOPC).(10CCR) | C | HPP | HPP | 2017 | 1439839 | 1439839 | NO |  |  |  | 0
[6 empty] | CARROLL | 6-1084 | US 42 | 0.25 | 5.697 | 5.947 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER KENTUCKY RIVER ON US 42 IN PRESTONSVILLE/CARROLLTON 0.13 MI E OF KY 55. (021B00043N)(SR=27.8) | D | STP | BRX | 2020 | 2080000 | 2080000 | NO |  |  |  | 0
[6 empty] | CARTER | 9-1075 | US 60 | 0.1 | 4.061 | 4.161 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON US-60 (MP 4.111) OVER TYGARTS CREEK; .75 MI E OF JCT KY 1662; (STRUCTURALLY DEFICIENT, SR=47) 022B00037N | C | NHPP | BRO | 2017 | 990000 | 990000 | NO |  |  |  | 0
[6 empty] | CARTER | 9-1081 | KY 474 |  | 5.062 | 5.102 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 474 OVER SMITH CREEK IN CARTER AT INTERSECTION OF KY 474 AND NUNN ROAD(CR 1507)(SR 40.1) 022B00123N | C | STP | BRX | 2017 | 930000 | 930000 | NO |  |  |  | 0
[6 empty] | CHRISTIAN | 2-136 | KY 1682 | 4 |  |  | RELIABILITY | NEW ROUTE(O) | EXTEND KY-1682 FROM THE E.T. BREATHITT PARKWAY TO US-68/KY-80 EAST OF HOPKINSVILLE (HOPKINSVILLE NORTHEAST BYPASS). (16CCR) | D | STP | STP | 2017 | 2940000 | 2940000 | NO |  |  |  | 0
[6 empty] | CHRISTIAN | 2-136 | KY 1682 | 4 |  |  | RELIABILITY | NEW ROUTE(O) | EXTEND KY-1682 FROM THE E.T. BREATHITT PARKWAY TO US-68/KY-80 EAST OF HOPKINSVILLE (HOPKINSVILLE NORTHEAST BYPASS). (16CCR) | R | STP | STP | 2020 | 4700000 | 4700000 | NO |  |  |  | 0
[6 empty] | CHRISTIAN | 2-136 | KY 1682 | 4 |  |  | RELIABILITY | NEW ROUTE(O) | EXTEND KY-1682 FROM THE E.T. BREATHITT PARKWAY TO US-68/KY-80 EAST OF HOPKINSVILLE (HOPKINSVILLE NORTHEAST BYPASS). (16CCR) | U | STP | STP | 2020 | 2410000 | 2410000 | NO |  |  |  | 0
[6 empty] | CHRISTIAN | 2-180 | KY 911 | 1.8 | 0 | 1.835 | RELIABILITY | MAJOR WIDENING(O) | WIDEN KY-911 FROM US-41A TO OAK GROVE.(12CCR) | C | STP | STP | 2017 | 8800000 | 8800000 | NO |  |  |  | 0
[6 empty] | CHRISTIAN | 2-898 | EB 9004 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT THE BREATHITT PARKWAY INTERCHANGE AT KY 1682 NORTH OF HOPKINSVILLE. (BREATHITT PARKWAY/FUTURE INTERSTATE SPUR PROJECT) (16CCR) | D | NHPP | NH | 2019 | 1000000 | 1000000 | NO |  |  |  | 0
[6 empty] | CHRISTIAN | 2-898 | EB 9004 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT THE BREATHITT PARKWAY INTERCHANGE AT KY 1682 NORTH OF HOPKINSVILLE. (BREATHITT PARKWAY/FUTURE INTERSTATE SPUR PROJECT) (16CCR) | R | NHPP | NH | 2020 | 1000000 | 1000000 | NO |  |  |  | 0
[6 empty] | CHRISTIAN | 2-1085 | CR 1116 |  | 0.019 | 0.059 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON SUB STATION RD (CR 1116) OVER CSX RR 0.04 MILE E OF US 41 (SR 34.4) 024C00034N | C | STP | BRZ | 2017 | 500000 | 500000 | NO |  |  |  | 0
[6 empty] | CHRISTIAN | 2-1089 | US 41A | 0.032 | 15.386 | 15.418 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER CSX RR ON WALNUT STREET (US 41A) IN HOPKINSVILLE 475 FT NE OF EAST 21ST STREET (CS 1016) (024B00112N) (SR=30.3) | D | STP | BRX | 2019 | 550000 | 550000 | NO |  |  |  | 0
[6 empty] | CHRISTIAN | 2-1094 | CS 1262 | 0.038 | 0.372 | 0.41 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER N FORK LITTLE RIVER ON MILBROOKE DRIVE (CS 1262) 500 FT SW OF KAREN DRIVE (CS 1268) (SR 6) 024C00081N | D | STP | BRZ | 2017 | 350000 | 350000 | NO |  |  |  | 0
[6 empty] | CHRISTIAN | 2-1094 | CS 1262 | 0.038 | 0.372 | 0.41 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER N FORK LITTLE RIVER ON MILBROOKE DRIVE (CS 1262) 500 FT SW OF KAREN DRIVE (CS 1268) (SR 6) 024C00081N | R | STP | BRZ | 2018 | 150000 | 150000 | NO |  |  |  | 0
[6 empty] | CHRISTIAN | 2-1094 | CS 1262 | 0.038 | 0.372 | 0.41 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER N FORK LITTLE RIVER ON MILBROOKE DRIVE (CS 1262) 500 FT SW OF KAREN DRIVE (CS 1268) (SR 6) 024C00081N | U | STP | BRZ | 2018 | 350000 | 350000 | NO |  |  |  | 0
[6 empty] | CHRISTIAN | 2-1094 | CS 1262 | 0.038 | 0.372 | 0.41 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER N FORK LITTLE RIVER ON MILBROOKE DRIVE (CS 1262) 500 FT SW OF KAREN DRIVE (CS 1268) (SR 6) 024C00081N | C | STP | BRZ | 2019 | 800000 | 800000 | NO |  |  |  | 0
[6 empty] | CLARK | 7-1121 | KY 974 | 0.1 | 10.874 | 10.974 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-974 (MP 10.924) OVER DRY FORK; .05 MI E-CR 1124 @ALLNSVL; (STRUCTURALLY DEFICIENT, SR=23.1) 025B00090N | R | STP | BRX | 2017 | 100000 | 100000 | NO |  |  |  | 0
[6 empty] | CLARK | 7-1121 | KY 974 | 0.1 | 10.874 | 10.974 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-974 (MP 10.924) OVER DRY FORK; .05 MI E-CR 1124 @ALLNSVL; (STRUCTURALLY DEFICIENT, SR=23.1) 025B00090N | U | STP | BRX | 2017 | 90000 | 90000 | NO |  |  |  | 0
[6 empty] | CLARK | 7-1121 | KY 974 | 0.1 | 10.874 | 10.974 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-974 (MP 10.924) OVER DRY FORK; .05 MI E-CR 1124 @ALLNSVL; (STRUCTURALLY DEFICIENT, SR=23.1) 025B00090N | C | STP | BRX | 2017 | 380000 | 380000 | NO |  |  |  | 0
[6 empty] | CLARK | 7-8506.01 | I 64 | 2.575 | 95.1 | 97.675 | RELIABILITY | MAJOR WIDENING(O) | RECONSTRUCT I-64/MOUNTAIN PARKWAY INTERCHANGE TO ADD NEW RAMPS TO AND FROM THE EAST.(12CCR)(14CCR)(16CCR) | R | NHPP | NH | 2018 | 1700000 | 1700000 | NO |  |  |  | 0
[6 empty] | CLARK | 7-8506.01 | I 64 | 2.575 | 95.1 | 97.675 | RELIABILITY | MAJOR WIDENING(O) | RECONSTRUCT I-64/MOUNTAIN PARKWAY INTERCHANGE TO ADD NEW RAMPS TO AND FROM THE EAST.(12CCR)(14CCR)(16CCR) | U | NHPP | NH | 2018 | 900000 | 900000 | NO |  |  |  | 0
[6 empty] | CLARK | 7-8506.01 | I 64 | 2.575 | 95.1 | 97.675 | RELIABILITY | MAJOR WIDENING(O) | RECONSTRUCT I-64/MOUNTAIN PARKWAY INTERCHANGE TO ADD NEW RAMPS TO AND FROM THE EAST.(12CCR)(14CCR)(16CCR) | C | NHPP | NH | 2019 | 11620000 | 11620000 | NO |  |  |  | 0
[6 empty] | CLAY | 11-364 | KY 11 |  | 7.2 | 8.9 | RELIABILITY | RECONSTRUCTION(O) | CORRECT STANDARDIZED ROADWAY GEOMETRICS AND ADDRESS SAFETY ISSUES FROM SOUTH OF ENGINE BRANCH ROUTE TO US 421 (MP 7.2 TO MP 8.9). | D | STP | STP | 2019 | 500000 | 500000 | NO |  |  |  | 0
[6 empty] | CLAY | 11-1091 | CR 1004 |  | 0.144 | 0.184 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON BEECH CREEK RD (CR 1004) OVER GOOSE CREEK AT INTERSECTION WITH CHANDLER BRANCH RD (CR 1003)(SR 30.8) C00001N | C | STP | BRZ | 2018 | 2000000 | 2000000 | NO |  |  |  | 0
[6 empty] | CLAY | 11-1092 | CR 1154 |  | 0 | 0.035 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON MILL CREEK ROAD (CR 1154) OVER GOOSE CREEK AT JCT WITH KY 1524 (SR 47) 026C00025N | C | STP | BRZ | 2018 | 750000 | 750000 | NO |  |  |  | 0
[6 empty] | CLAY | 11-1099 | CR 1160 | 0.016 | 2.01 | 2.026 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER OTTER CREEK ON OTTER CREEK ROAD (CR 1160) AT JUNCTION WITH MAY FORK ROAD (CR 1158)(026C00031N)(SR=2) | D | STP | BRZ | 2019 | 150000 | 150000 | NO |  |  |  | 0
[6 empty] | CLAY | 11-1099 | CR 1160 | 0.016 | 2.01 | 2.026 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER OTTER CREEK ON OTTER CREEK ROAD (CR 1160) AT JUNCTION WITH MAY FORK ROAD (CR 1158)(026C00031N)(SR=2) | R | STP | BRZ | 2020 | 30000 | 30000 | NO |  |  |  | 0
[6 empty] | CLAY | 11-1099 | CR 1160 | 0.016 | 2.01 | 2.026 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER OTTER CREEK ON OTTER CREEK ROAD (CR 1160) AT JUNCTION WITH MAY FORK ROAD (CR 1158)(026C00031N)(SR=2) | U | STP | BRZ | 2020 | 50000 | 50000 | NO |  |  |  | 0
[6 empty] | CLINTON | 8-1062 | KY 738 | 0.01 | 6.478 | 6.488 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER CLEAR FORK CREEK ON KY 738 0.2 MI S OF US 127X. (027B00011N)(SR=31.5) | D | STP | BRX | 2019 | 250000 | 250000 | NO |  |  |  | 0
[6 empty] | CLINTON | 8-8601.26 | US 127 | 21.3 | 11.017 | 20.967 | RELIABILITY | RELOCATION(O) | RELOCATION OF US 127 FROM APPROX 1.14 MI N OF INTERSECTION OF KY 3063 & OLD US 127, EXTENDING N TO KY 1730, LOCATED APPROX 0.36 MI E OF THE INTER. OF KY 1730 & MANNTOWN RD.(SEE 8-108 & 8-115 FOR PE&ENV)(12CCR)(G&D)(SEE 8-8601.27 FOR SURFACING)(14CCR) | D | NHPP | NH | 2017 | 2300000 | 2300000 | NO |  |  |  | 0
[6 empty] | CLINTON | 8-8601.26 | US 127 | 21.3 | 11.017 | 20.967 | RELIABILITY | RELOCATION(O) | RELOCATION OF US 127 FROM APPROX 1.14 MI N OF INTERSECTION OF KY 3063 & OLD US 127, EXTENDING N TO KY 1730, LOCATED APPROX 0.36 MI E OF THE INTER. OF KY 1730 & MANNTOWN RD.(SEE 8-108 & 8-115 FOR PE&ENV)(12CCR)(G&D)(SEE 8-8601.27 FOR SURFACING)(14CCR) | U | NHPP | NH | 2019 | 550000 | 550000 | NO |  |  |  | 0
[6 empty] | CUMBERLAND | 8-1060 | KY 61 | 0.14 | 9.945 | 10.085 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER CUMBERLAND RIVER ON KY 61 0.1 MI N OF COLD SPRINGS ROAD (CR 1204).(029B00012N)(SR=32) | D | NHPP | BRO | 2017 | 500000 | 500000 | NO |  |  |  | 0
[6 empty] | CUMBERLAND | 8-1060 | KY 61 | 0.14 | 9.945 | 10.085 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER CUMBERLAND RIVER ON KY 61 0.1 MI N OF COLD SPRINGS ROAD (CR 1204).(029B00012N)(SR=32) | R | NHPP | BRO | 2017 | 50000 | 50000 | NO |  |  |  | 0
[6 empty] | CUMBERLAND | 8-1060 | KY 61 | 0.14 | 9.945 | 10.085 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER CUMBERLAND RIVER ON KY 61 0.1 MI N OF COLD SPRINGS ROAD (CR 1204).(029B00012N)(SR=32) | U | NHPP | BRO | 2017 | 50000 | 50000 | NO |  |  |  | 0
[6 empty] | CUMBERLAND | 8-1060 | KY 61 | 0.14 | 9.945 | 10.085 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER CUMBERLAND RIVER ON KY 61 0.1 MI N OF COLD SPRINGS ROAD (CR 1204).(029B00012N)(SR=32) | C | NHPP | BRO | 2019 | 4000000 | 4000000 | NO |  |  |  | 0
[6 empty] | CUMBERLAND | 8-1061 | KY 90 | 0.36 | 14.127 | 14.459 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER CUMBERLAND RIVER ON KY 90 0.27 MI SE OF KY 61 AT THE SCL OF BURKESVILLE. (029B00027N)(SR=35.4) | D | NHPP | BRO | 2017 | 500000 | 500000 | NO |  |  |  | 0
[6 empty] | CUMBERLAND | 8-1061 | KY 90 | 0.36 | 14.127 | 14.459 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER CUMBERLAND RIVER ON KY 90 0.27 MI SE OF KY 61 AT THE SCL OF BURKESVILLE. (029B00027N)(SR=35.4) | R | NHPP | BRO | 2017 | 50000 | 50000 | NO |  |  |  | 0
[6 empty] | CUMBERLAND | 8-1061 | KY 90 | 0.36 | 14.127 | 14.459 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER CUMBERLAND RIVER ON KY 90 0.27 MI SE OF KY 61 AT THE SCL OF BURKESVILLE. (029B00027N)(SR=35.4) | U | NHPP | BRO | 2017 | 50000 | 50000 | NO |  |  |  | 0
[6 empty] | CUMBERLAND | 8-1061 | KY 90 | 0.36 | 14.127 | 14.459 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER CUMBERLAND RIVER ON KY 90 0.27 MI SE OF KY 61 AT THE SCL OF BURKESVILLE. (029B00027N)(SR=35.4) | C | NHPP | BRO | 2018 | 5500000 | 5500000 | NO |  |  |  | 0
[6 empty] | DAVIESS | 2-237 | US 60 | 0.592 | 5.69 | 6.282 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT ON US 60 BETWEEN OAKFORD RD LOOP (CR 1370) TO ADDRESS FLOODING PROBLEM IN THE VICINITY OF THE KIMBERLY-CLARK PLANT (14CCR) | R | STP | STP | 2017 | 500000 | 500000 | NO |  |  |  | 0
[6 empty] | DAVIESS | 2-237 | US 60 | 0.592 | 5.69 | 6.282 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT ON US 60 BETWEEN OAKFORD RD LOOP (CR 1370) TO ADDRESS FLOODING PROBLEM IN THE VICINITY OF THE KIMBERLY-CLARK PLANT (14CCR) | U | STP | STP | 2017 | 500000 | 500000 | NO |  |  |  | 0
[6 empty] | DAVIESS | 2-237 | US 60 | 0.592 | 5.69 | 6.282 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT ON US 60 BETWEEN OAKFORD RD LOOP (CR 1370) TO ADDRESS FLOODING PROBLEM IN THE VICINITY OF THE KIMBERLY-CLARK PLANT (14CCR) | C | STP | STP | 2017 | 2000000 | 2000000 | NO |  |  |  | 0
[6 empty] | DAVIESS | 2-287.52 | US 60 | 2.2 |  |  | RELIABILITY | RELOCATION(O) | TRANSPORTATION IMPROVEMENTS TO US 60 OWENSBORO, DAVIESS COUNTY. (2005HPP-KY158)(2005HPP-KY167)(SEE 2-287.20 FOR "STP" COMPONENT) | C | HPP | HPP | 2017 | 2000000 | 2000000 | NO |  |  |  | 0
[6 empty] | DAVIESS | 2-1093 | CR 1014 | 0.014 | 1.326 | 1.34 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER BURNETT FORK ON FIELDS RD (CR 1014) 0.75 MI W OF KY 142 030C00001N SR 39 (14CCR) | R | STP | BRZ | 2017 | 75000 | 75000 | NO |  |  |  | 0
[6 empty] | DAVIESS | 2-1093 | CR 1014 | 0.014 | 1.326 | 1.34 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER BURNETT FORK ON FIELDS RD (CR 1014) 0.75 MI W OF KY 142 030C00001N SR 39 (14CCR) | U | STP | BRZ | 2017 | 75000 | 75000 | NO |  |  |  | 0
[6 empty] | DAVIESS | 2-1093 | CR 1014 | 0.014 | 1.326 | 1.34 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER BURNETT FORK ON FIELDS RD (CR 1014) 0.75 MI W OF KY 142 030C00001N SR 39 (14CCR) | C | STP | BRZ | 2017 | 350000 | 350000 | NO |  |  |  | 0
[6 empty] | DAVIESS | 2-2092 | WN 9007 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | UPGRADE THE NATCHER PARKWAY TO INTERSTATE STANDARDS IN ORDER TO ESTABLISH "I-565"SPUR ROUTE BETWEEN BOWLING GREEN AND OWENSBORO. | C | NHPP | NH | 2018 | 10000000 | 10000000 | NO |  |  |  | 0
[6 empty] | DAVIESS | 2-2092.01 | WN 9007 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | UPGRADE THE NATCHER PARKWAY TO INTERSTATE STANDARDS IN ORDER TO ESTABLISH "I-565"SPUR ROUTE BETWEEN BOWLING GREEN AND OWENSBORO. | C | NHPP | NH | 2020 | 11000000 | 11000000 | NO |  |  |  | 0
[6 empty] | ELLIOTT | 9-192.01 | KY 32 | 6.656 | 2 | 8.656 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT KY-32 FROM 0.408 MILES WEST OF STEGALL COLD SPRING ROAD TO KY-7 NEAR NEWFOUNDLAND. (PRIORITY SECTION I)(06CCR) (08CCR) (10CCR)(12CCR)(14CCR)(16CCR) | R | STP | STP | 2017 | 7720000 | 7720000 | NO |  |  |  | 0
[6 empty] | ELLIOTT | 9-192.01 | KY 32 | 6.656 | 2 | 8.656 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT KY-32 FROM 0.408 MILES WEST OF STEGALL COLD SPRING ROAD TO KY-7 NEAR NEWFOUNDLAND. (PRIORITY SECTION I)(06CCR) (08CCR) (10CCR)(12CCR)(14CCR)(16CCR) | U | STP | STP | 2018 | 10900000 | 10900000 | NO |  |  |  | 0
[6 empty] | ELLIOTT | 9-192.01 | KY 32 | 6.656 | 2 | 8.656 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT KY-32 FROM 0.408 MILES WEST OF STEGALL COLD SPRING ROAD TO KY-7 NEAR NEWFOUNDLAND. (PRIORITY SECTION I)(06CCR) (08CCR) (10CCR)(12CCR)(14CCR)(16CCR) | C | STP | STP | 2019 | 20000000 | 20000000 | YES |  |  |  | 0
[6 empty] | ELLIOTT | 9-192.02 | KY 32 | 6.656 | 2 | 8.656 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT KY-32 FROM 0.408 MILES WEST OF STEGALL COLD SPRING ROAD TO KY-7 NEAR NEWFOUNDLAND. (PRIORITY SECTION I)(16CCR) | C | STP | STP | 2020 | 20000000 | 20000000 | YES |  |  |  | 0
[6 empty] | ELLIOTT | 9-192.03 | KY 32 |  | 0 | 2 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT KY-32 FROM KY-504 NEAR ELLIOTTVILLE TO 0.408 MI WEST OF STEGALL COLD SPRING ROAD IN ELLIOTT COUNTY. (10CCR)(16CCN) | D | STP | STP | 2017 | 5000000 | 5000000 | NO |  |  |  | 0
[6 empty] | ELLIOTT | 9-228 | KY 7 | 6.956 | 0 | 6.956 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT KY 7 FROM SOUTH CITY LIMITS OF SANDY HOOK TOWARD WRIGLEY. (12CCR)(16CCR) | D | STP | STP | 2018 | 3380000 | 3380000 | NO |  |  |  | 0
[6 empty] | ELLIOTT | 9-8802 | KY 32 | 1 | 9.2 | 10.2 | RELIABILITY | MAJOR WIDENING(O) | KY-32 FROM 9.2 MILE MARKER TO 10.2 MILE MARKER WIDENING. (14CCN)(16CCR) | R | STP | STP | 2017 | 850000 | 850000 | NO |  |  |  | 0
[6 empty] | ELLIOTT | 9-8802 | KY 32 | 1 | 9.2 | 10.2 | RELIABILITY | MAJOR WIDENING(O) | KY-32 FROM 9.2 MILE MARKER TO 10.2 MILE MARKER WIDENING. (14CCN)(16CCR) | U | STP | STP | 2017 | 600000 | 600000 | NO |  |  |  | 0
[6 empty] | FAYETTE | 7-113.02 | KY 4 | 3.4 | 7.26 | 8.26 | RELIABILITY | MAJOR WIDENING(O) | NEW CIRCLE ROAD REHAB AND WIDENING FROM LEESTOWN ROAD TO NEAR GEORGETOWN ROAD. (12CCR)(14CCR) | C | NHPP | NH | 2019 | 18000000 | 18000000 | NO |  |  |  | 0
[6 empty] | FAYETTE | 7-220 | US 25 | 1 | 8.4 | 9.55 | SAFETY | BIKE/PED FACIL(O) | RICHMOND ROAD MULTIUSE PATH IN LEXINGTON BETWEEN EAGLE CREEK DRIVE AND JACOBSON PARK. (LOCAL MATCH) (ALL WORK BY LFUCG) (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | C | SLX | SLX | 2017 | 690000 | 552000 | NO |  |  |  | 0
[6 empty] | FAYETTE | 7-224.1 | CS 4174 | 1.9 | 0 | 2.01 | RELIABILITY | MINOR WIDENING(O) | CLAYS MILL ROAD; WIDEN FROM HARRODSBURG ROAD TO NEW CIRCLE ROAD (SECTION 1) (LFUCG T.I.P.) (LOCAL MATCH) (ALL WORK BY LFUCG) (CONSTRUCTION SEQU. 2) (SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | U | SLX | SLX | 2017 | 280000 | 224000 | NO |  |  |  | 0
[6 empty] | FAYETTE | 7-224.1 | CS 4174 | 1.9 | 0 | 2.01 | RELIABILITY | MINOR WIDENING(O) | CLAYS MILL ROAD; WIDEN FROM HARRODSBURG ROAD TO NEW CIRCLE ROAD (SECTION 1) (LFUCG T.I.P.) (LOCAL MATCH) (ALL WORK BY LFUCG) (CONSTRUCTION SEQU. 2) (SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | C | SLX | SLX | 2017 | 11735000 | 9388000 | NO |  |  |  | 0
[6 empty] | FAYETTE | 7-227.1 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | DEDICATED FEDERAL-AID STP FUNDS EARMARKED FOR LEXINGTON URBANIZED AREA AND SUBJECT TO MPO CONTROL FOR FY 2017. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C | SLX | SLX | 2017 | 3900000 | 3120000 | NO |  |  |  | 0
[6 empty] | FAYETTE | 7-227.11 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | DEDICATED FEDERAL-AID STP FUNDS EARMARKED FOR LEXINGTON URBANIZED AREA AND SUBJECT TO MPO CONTROL FOR FY 2018. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C | SLX | SLX | 2018 | 4600000 | 3680000 | NO |  |  |  | 0
[6 empty] | FAYETTE | 7-227.13 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | DEDICATED FEDERAL-AID STP FUNDS EARMARKED FOR LEXINGTON URBANIZED AREA AND SUBJECT TO MPO CONTROL FOR FY 2019. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C | SLX | SLX | 2019 | 8000000 | 6400000 | NO |  |  |  | 0
[6 empty] | FAYETTE | 7-227.14 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | DEDICATED FEDERAL-AID STP FUNDS EARMARKED FOR LEXINGTON URBANIZED AREA AND SUBJECT TO MPO CONTROL FOR FY 2020. (FUNDING SUBJECT TO FISCAL CONTRAINT PENDING MPO TIP) | C | SLX | SLX | 2020 | 8200000 | 6560000 | NO |  |  |  | 0
[6 empty] | FAYETTE | 7-229.2 |  | 0.3 |  |  | SAFETY | BIKE/PED FACIL(O) | SOUTH ELKHORN TRAIL IN LEXINGTON (PRIORITY SECTION 2); FROM JOSEPH BRYAN WAY THROUGH NS RAILROAD TUNNEL TO WAVELAND HISTORIC SITE (ALL WORK BY LFUCG). (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | C | SLX | SLX | 2017 | 400000 | 320000 | NO |  |  |  | 0
[6 empty] | FAYETTE | 7-229.3 |  | 0.3 |  |  | SAFETY | BIKE/PED FACIL(O) | SOUTH ELKHORN TRAIL(PRIORITY SECTION 3); FROM LOCHDALE TERRACE, EXTENDING NORTHERLY UNDER MAN O' WAR BOULEVARD TO SHILLITO PARK.(LOCAL MATCH)(DESIGN BY LFUCG)(ALL WORK BY LFUCG)(2004BOPC)(FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | C | SLX | SLX | 2017 | 625000 | 500000 | NO |  |  |  | 0
[6 empty] | FAYETTE | 7-252 | KY 922 | 1.837 | 1.47 | 3.22 | RELIABILITY | MAJOR WIDENING(O) | SIX-LANE NEWTOWN PIKE FROM KY-4 TO I-75. (16CCR) | R | STP | STP | 2017 | 3150000 | 3150000 | NO |  |  |  | 0
[6 empty] | FAYETTE | 7-252 | KY 922 | 1.837 | 1.47 | 3.22 | RELIABILITY | MAJOR WIDENING(O) | SIX-LANE NEWTOWN PIKE FROM KY-4 TO I-75. (16CCR) | U | STP | STP | 2019 | 5000000 | 5000000 | NO |  |  |  | 0
[6 empty] | FAYETTE | 7-252 | KY 922 | 1.837 | 1.47 | 3.22 | RELIABILITY | MAJOR WIDENING(O) | SIX-LANE NEWTOWN PIKE FROM KY-4 TO I-75. (16CCR) | C | STP | STP | 2019 | 20000000 | 20000000 | YES |  |  |  | 0
[6 empty] | FAYETTE | 7-366 | KY 4 | 1.3 | 8.731 | 10.015 | RELIABILITY | MAJOR WIDENING(O) | WIDEN NEW CIRCLE ROAD IN LEXINGTON FROM GEORGETOWN ROAD TO BOARDWALK AVENUE INCLUDING INTERCHANGE RECONSTRUCTION AT NEWTOWN PIKE.(2002BOPC)(2004BOPP)(10CCR)(12CCR)(14CCR) | C | NHPP | NH | 2017 | 12000000 | 12000000 | NO |  |  |  | 0
[6 empty] | FAYETTE | 7-366.02 | KY 4 | 1.3 | 8.731 | 10.015 | RELIABILITY | PREFINANCD CONVRSN(O) | WIDEN NEW CIRCLE ROAD IN LEXINGTON FROM GEORGETOWN ROAD TO BOARDWALK AVENUE INCLUDING INTERCHANGE RECONSTRUCTION AT NEWTOWN PIKE. (ADDITIONAL C-FUNDS FOR 7-366.00) | C | NHPP | NH | 2018 | 12000000 | 12000000 | NO |  |  |  | 0
[6 empty] | FAYETTE | 7-366.03 | KY 4 | 1.3 | 8.731 | 10.015 | RELIABILITY | PREFINANCD CONVRSN(O) | WIDEN NEW CIRCLE ROAD IN LEXINGTON FROM GEORGETOWN ROAD TO BOARDWALK AVENUE INCLUDING INTERCHANGE RECONSTRUCTION AT NEWTOWN PIKE. (ADDITIONAL C-FUNDS FOR 7-366.00) | C | NHPP | NH | 2019 | 10930000 | 10930000 | YES |  |  |  | 0
[6 empty] | FAYETTE | 7-413 | KY 922 | 0.33 | 2.72 | 3.05 | RELIABILITY | RECONSTRUCTION(O) | CONSTRUCT AN ADDITIONAL LANE ON KY 922 (NEWTOWN PIKE) FROM PINTAIL DR (MAIN ENTRANCE TO THE MARRIOTT GRIFFIN GATE) TO THE BEGINNING OF THE SOUTHBOUND I-75 ENTRANCE RAMP.(12CCR)(14CCR) | R | NHPP | NH | 2017 | 1500000 | 1500000 | NO |  |  |  | 0
[6 empty] | FAYETTE | 7-413 | KY 922 | 0.33 | 2.72 | 3.05 | RELIABILITY | RECONSTRUCTION(O) | CONSTRUCT AN ADDITIONAL LANE ON KY 922 (NEWTOWN PIKE) FROM PINTAIL DR (MAIN ENTRANCE TO THE MARRIOTT GRIFFIN GATE) TO THE BEGINNING OF THE SOUTHBOUND I-75 ENTRANCE RAMP.(12CCR)(14CCR) | U | NHPP | NH | 2017 | 500000 | 500000 | NO |  |  |  | 0
[6 empty] | FAYETTE | 7-413 | KY 922 | 0.33 | 2.72 | 3.05 | RELIABILITY | RECONSTRUCTION(O) | CONSTRUCT AN ADDITIONAL LANE ON KY 922 (NEWTOWN PIKE) FROM PINTAIL DR (MAIN ENTRANCE TO THE MARRIOTT GRIFFIN GATE) TO THE BEGINNING OF THE SOUTHBOUND I-75 ENTRANCE RAMP.(12CCR)(14CCR) | C | NHPP | NH | 2017 | 800000 | 800000 | NO |  |  |  | 0
[6 empty] | FAYETTE | 7-427 | CS 4524 | 0.1 | 11.773 | 11.873 | RELIABILITY | RECONSTRUCTION(O) | CONSTRUCT TURN LANES AT THE INTERSECTION OF MAN O' WAR BLVD (CS 4524) AND ALUMNI DRIVE (CS 3016). | R | SLX | SLX | 2017 | 18000 | 14400 | NO |  |  |  | 0
[6 empty] | FAYETTE | 7-427 | CS 4524 | 0.1 | 11.773 | 11.873 | RELIABILITY | RECONSTRUCTION(O) | CONSTRUCT TURN LANES AT THE INTERSECTION OF MAN O' WAR BLVD (CS 4524) AND ALUMNI DRIVE (CS 3016). | C | SLX | SLX | 2017 | 725000 | 580000 | NO |  |  |  | 0
[6 empty] | FAYETTE | 7-428 | CS 4524 | 0.1 | 12.736 | 12.836 | RELIABILITY | RECONSTRUCTION(O) | CONSTRUCT TURN LANES AT THE INTERSECTION OF MAN O' WAR BLVD (CS-4524) AND RICHMOND ROAD (US-25). | R | SLX | SLX | 2017 | 40000 | 32000 | NO |  |  |  | 0
[6 empty] | FAYETTE | 7-428 | CS 4524 | 0.1 | 12.736 | 12.836 | RELIABILITY | RECONSTRUCTION(O) | CONSTRUCT TURN LANES AT THE INTERSECTION OF MAN O' WAR BLVD (CS-4524) AND RICHMOND ROAD (US-25). | C | SLX | SLX | 2017 | 550000 | 440000 | NO |  |  |  | 0
[6 empty] | FAYETTE | 7-1129 | US 421 | 0.04 | 4.426 | 4.466 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON US 421 OVER FORK OF TOWN BRANCH AT INTERSECTION OF US 421 AND BRACKTOWN RD (CS 4008)(SR 27.8) 034B00018N | R | NHPP | BRO | 2017 | 125000 | 125000 | NO |  |  |  | 0
[6 empty] | FAYETTE | 7-1129 | US 421 | 0.04 | 4.426 | 4.466 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON US 421 OVER FORK OF TOWN BRANCH AT INTERSECTION OF US 421 AND BRACKTOWN RD (CS 4008)(SR 27.8) 034B00018N | U | NHPP | BRO | 2017 | 125000 | 125000 | NO |  |  |  | 0
[6 empty] | FAYETTE | 7-1129 | US 421 | 0.04 | 4.426 | 4.466 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON US 421 OVER FORK OF TOWN BRANCH AT INTERSECTION OF US 421 AND BRACKTOWN RD (CS 4008)(SR 27.8) 034B00018N | C | NHPP | BRO | 2017 | 800000 | 800000 | NO |  |  |  | 0
[6 empty] | FAYETTE | 7-1132 | CS 3605 |  | 1.656 | 1.696 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON MALABU DRIVE (CS 3605) OVER BRANCH HICKMAN CREEK AT JCT WITH TATES CREEK ROAD (KY 1974)(SR 40) 034C00038N | C | STP | BRZ | 2018 | 500000 | 500000 | NO |  |  |  | 0
[6 empty] | FAYETTE | 7-1141 | CR 1001 | 0.04 | 1.6 | 1.64 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER BRANCH OF NORTH ELKHORN CREEK ON HUME ROAD (CR 1001) 0.7 MI NW OF US 60 (034C00001N)(SR=44.5) | D | STP | BRZ | 2019 | 300000 | 300000 | NO |  |  |  | 0
[6 empty] | FAYETTE | 7-8507 | CS 2548 |  |  |  | RELIABILITY | NEW ROUTE(O) | COMPLETE CONSTRUCTION ON POLO CLUB BOULEVARD AT DEERHAVEN LANE AND TODDS ROAD. (08CCN)(FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C | SLX | SLX | 2017 | 1550000 | 1240000 | NO |  |  |  | 0
[6 empty] | FAYETTE | 7-8909 | I 75 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | WIDEN I-64/I-75 TO 8 LANES FROM BRYAN STATION OVERPASS (MP 112.012) TO NORTHERN SPLIT (MP 117.665) TO ALLEVIATE CONGESTION (SECTION 1). (16CCN) | D | NHPP | IM | 2017 | 500000 | 500000 | NO |  |  |  | 0
[6 empty] | FAYETTE | 7-8909 | I 75 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | WIDEN I-64/I-75 TO 8 LANES FROM BRYAN STATION OVERPASS (MP 112.012) TO NORTHERN SPLIT (MP 117.665) TO ALLEVIATE CONGESTION (SECTION 1). (16CCN) | R | NHPP | IM | 2017 | 1500000 | 1500000 | NO |  |  |  | 0
[6 empty] | FAYETTE | 7-8909 | I 75 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | WIDEN I-64/I-75 TO 8 LANES FROM BRYAN STATION OVERPASS (MP 112.012) TO NORTHERN SPLIT (MP 117.665) TO ALLEVIATE CONGESTION (SECTION 1). (16CCN) | U | NHPP | IM | 2018 | 1500000 | 1500000 | NO |  |  |  | 0
[6 empty] | FAYETTE | 7-8909 | I 75 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | WIDEN I-64/I-75 TO 8 LANES FROM BRYAN STATION OVERPASS (MP 112.012) TO NORTHERN SPLIT (MP 117.665) TO ALLEVIATE CONGESTION (SECTION 1). (16CCN) | C | NHPP | IM | 2019 | 40000000 | 40000000 | YES |  |  |  | 0
[6 empty] | FAYETTE | 7-8910 | I 75 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | WIDEN I-75 TO 8 LANES FROM C&O RAILROAD BRIDGE (MP 107.417) TO BRYAN STATION OVERPASS (MP 112.012) TO ALLEVIATE CONGESTION (SECTION 2). (16CCN). | D | NHPP | IM | 2017 | 1000000 | 1000000 | NO |  |  |  | 0
[6 empty] | FLEMING | 9-1084 | KY 32 | 0.04 | 7.76 | 7.8 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 32 OVER MUD LICK CREEK 0.2 MILES W OF CRAINTOWN RD (CR 1302)(SR 48.9) 035B00038N | R | NHPP | BRO | 2017 | 150000 | 150000 | NO |  |  |  | 0
[6 empty] | FLEMING | 9-1084 | KY 32 | 0.04 | 7.76 | 7.8 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 32 OVER MUD LICK CREEK 0.2 MILES W OF CRAINTOWN RD (CR 1302)(SR 48.9) 035B00038N | U | NHPP | BRO | 2017 | 250000 | 250000 | NO |  |  |  | 0
[6 empty] | FLEMING | 9-1084 | KY 32 | 0.04 | 7.76 | 7.8 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 32 OVER MUD LICK CREEK 0.2 MILES W OF CRAINTOWN RD (CR 1302)(SR 48.9) 035B00038N | C | NHPP | BRO | 2017 | 400000 | 400000 | NO |  |  |  | 0
[6 empty] | FLEMING | 9-1091 | KY 111 | 0.02 | 11.84 | 11.86 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER ALLISON CREEK ON KY 111 1.2 MI N OF KY 156. (035B00016N)(SR=32.1)(EBRP) | D | STP | BRX | 2020 | 500000 | 500000 | NO |  |  |  | 0
[6 empty] | FLEMING | 9-1092 | CR 1240 | 0.024 | 2.04 | 2.064 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER FLEMING CREEK ON MCINTIRE ROAD (CR 1240) AT THE JCT WITH PIKE BLUFF (CR 1305)(035C00065N)(SR=24) | D | STP | BRZ | 2017 | 350000 | 350000 | NO |  |  |  | 0
[6 empty] | FLEMING | 9-1092 | CR 1240 | 0.024 | 2.04 | 2.064 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER FLEMING CREEK ON MCINTIRE ROAD (CR 1240) AT THE JCT WITH PIKE BLUFF (CR 1305)(035C00065N)(SR=24) | R | STP | BRZ | 2019 | 75000 | 75000 | NO |  |  |  | 0
[6 empty] | FLEMING | 9-1092 | CR 1240 | 0.024 | 2.04 | 2.064 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER FLEMING CREEK ON MCINTIRE ROAD (CR 1240) AT THE JCT WITH PIKE BLUFF (CR 1305)(035C00065N)(SR=24) | U | STP | BRZ | 2019 | 50000 | 50000 | NO |  |  |  | 0
[6 empty] | FLEMING | 9-1092 | CR 1240 | 0.024 | 2.04 | 2.064 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER FLEMING CREEK ON MCINTIRE ROAD (CR 1240) AT THE JCT WITH PIKE BLUFF (CR 1305)(035C00065N)(SR=24) | C | STP | BRZ | 2020 | 600000 | 600000 | NO |  |  |  | 0
[6 empty] | FLEMING | 9-3021 | KY 158 |  |  |  | RELIABILITY | BRIDGE REHAB(P) | RESTORATION OF RINGO'S MILL COVERED BRIDGE LOCATED ON KY 158 AT RAWLINGS ROAD APPROX 7.274 MILES EAST OF HILLSBORO (FY2010 AND FY2011 NHCB PROJECT) (2010 BOPC). | D | KYD | KYD | 2017 | 5000 | 5000 | NO |  |  |  | 0
[6 empty] | FLEMING | 9-3021 | KY 158 |  |  |  | RELIABILITY | BRIDGE REHAB(P) | RESTORATION OF RINGO'S MILL COVERED BRIDGE LOCATED ON KY 158 AT RAWLINGS ROAD APPROX 7.274 MILES EAST OF HILLSBORO (FY2010 AND FY2011 NHCB PROJECT) (2010 BOPC). | C | KYD | KYD | 2017 | 503000 | 503000 | NO |  |  |  | 0
[6 empty] | FLEMING | 9-8804 | KY 111 |  |  |  | RELIABILITY | BRIDGE REHAB(P) | RESTORATION OF GRANGE CITY COVERED BRIDGE LOCATED ON KY-111 BETWEEN FLEMINGSBURG AND GRANGE CITY. (14CCN) (16CCR) | C | TE | TE | 2017 | 1200000 | 960000 | NO |  |  |  | 0
[6 empty] | FLOYD | 12-1.2 | KY 114 | 3.5 | 0 | 3.48 | RELIABILITY | MAJOR WIDENING(O) | MOUNTAIN PARKWAY CORRIDOR: EXTEND THE FOUR LANE MOUNTAIN PARKWAY FROM THE MAGOFFIN/FLOYD COUNTY LINE TO THE HEAD OF LEFT FORK OF ABBOTT CREEK. (SEE 12-1.01 FOR PE & ENV)(14CCR)(16CCR) | D | NHPP | NH | 2020 | 2900000 | 2900000 | NO |  |  |  | 0
[6 empty] | FLOYD | 12-1.3 | KY 114 | 3.9 | 3.48 | 7.354 | RELIABILITY | MAJOR WIDENING(O) | MOUNTAIN PARKWAY CORRIDOR: EXTEND THE FOUR LANE MOUNTAIN PARKWAY FROM THE HEAD OF LEFT FORK OF ABBOTT CREEK TO NEELEY BRANCH ROAD. (SEE 12-1.01 FOR PE & ENV)(14CCR)(16CCR) | D | NHPP | NH | 2019 | 3200000 | 3200000 | NO |  |  |  | 0
[6 empty] | FLOYD | 12-1.4 | KY 114 | 1.8 | 7.354 | 9.092 | RELIABILITY | MAJOR WIDENING(O) | MOUNTAIN PARKWAY CORRIDOR: EXTEND THE FOUR LANE MOUNTAIN PARKWAY FROM NEELEY BRANCH ROAD TO COUNTY ROAD 1386 AT PRESTONSBURG ELEMENTARY SCHOOL. (SEE 12-1.01 FOR PE & ENV)(14CCR)(16CCR) | D | NHPP | NH | 2018 | 1800000 | 1800000 | NO |  |  |  | 0
[6 empty] | FLOYD | 12-191 | US 23 | 1 | 12.775 | 13.775 | SAFETY | SAFETY(P) | MITIGATE SAFETY HAZARDS DUE TO SPEED, POOR ACCESS CONTROL BETWEEN KY 80 AND INTERSECTION WITH KY 3384.(12CCR) | R | NHPP | NH | 2017 | 400000 | 400000 | NO |  |  |  | 0
[6 empty] | FLOYD | 12-191 | US 23 | 1 | 12.775 | 13.775 | SAFETY | SAFETY(P) | MITIGATE SAFETY HAZARDS DUE TO SPEED, POOR ACCESS CONTROL BETWEEN KY 80 AND INTERSECTION WITH KY 3384.(12CCR) | U | NHPP | NH | 2017 | 500000 | 500000 | NO |  |  |  | 0
[6 empty] | FLOYD | 12-191 | US 23 | 1 | 12.775 | 13.775 | SAFETY | SAFETY(P) | MITIGATE SAFETY HAZARDS DUE TO SPEED, POOR ACCESS CONTROL BETWEEN KY 80 AND INTERSECTION WITH KY 3384.(12CCR) | C | NHPP | NH | 2018 | 1800000 | 1800000 | NO |  |  |  | 0
[6 empty] | FLOYD | 12-345 | US 23 |  | 21.5 | 21.8 | RELIABILITY | WEIGH STA REHAB(P) | UPGRADE EXISTING FLOYD COUNTY WEIGH STATION. | C | NHPP | NH | 2018 | 1000000 | 1000000 | NO |  |  |  | 0
[6 empty] | FLOYD | 12-1084 | KY 466 | 0.1 | 3.559 | 3.599 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-466 OVER LEFT FORK BEAVER CREEK (B30). (SR=37.5): (036B00030N) | C | STP | BRX | 2018 | 1090000 | 1090000 | NO |  |  |  | 0
[6 empty] | FLOYD | 12-1111 | KY 1100 |  | 5.231 | 5.271 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 1100 OVER LITTLE PAINT CREEK NEAR FLOYD/JOHNSON COUNTY LINE (SR 47.1) 036B00002N | R | STP | BRX | 2017 | 75000 | 75000 | NO |  |  |  | 0
[6 empty] | FLOYD | 12-1111 | KY 1100 |  | 5.231 | 5.271 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 1100 OVER LITTLE PAINT CREEK NEAR FLOYD/JOHNSON COUNTY LINE (SR 47.1) 036B00002N | U | STP | BRX | 2017 | 135000 | 135000 | NO |  |  |  | 0
[6 empty] | FLOYD | 12-1111 | KY 1100 |  | 5.231 | 5.271 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 1100 OVER LITTLE PAINT CREEK NEAR FLOYD/JOHNSON COUNTY LINE (SR 47.1) 036B00002N | C | STP | BRX | 2018 | 900000 | 900000 | NO |  |  |  | 0
[6 empty] | FLOYD | 12-1119 | KY 2557 | 0.146 | 0.152 | 0.298 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER LEVISA FORK ON KY 2557 AT JCT US 23 IN JUSTELL. (036B00040N)(SR=19.9) | D | STP | BRX | 2019 | 750000 | 750000 | NO |  |  |  | 0
[6 empty] | FLOYD | 12-1119 | KY 2557 | 0.146 | 0.152 | 0.298 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER LEVISA FORK ON KY 2557 AT JCT US 23 IN JUSTELL. (036B00040N)(SR=19.9) | R | STP | BRX | 2020 | 300000 | 300000 | NO |  |  |  | 0
[6 empty] | FLOYD | 12-1119 | KY 2557 | 0.146 | 0.152 | 0.298 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER LEVISA FORK ON KY 2557 AT JCT US 23 IN JUSTELL. (036B00040N)(SR=19.9) | U | STP | BRX | 2020 | 500000 | 500000 | NO |  |  |  | 0
[6 empty] | FLOYD | 12-1121 | KY 550 | 0.04 | 2.03 | 2.07 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER BRUSH CREEK ON KY 550 AT JCT WITH KY 850. (036B00015N)(SR=41.3)(EBRP) | D | STP | BRX | 2019 | 300000 | 300000 | NO |  |  |  | 0
[6 empty] | FLOYD | 12-1121 | KY 550 | 0.04 | 2.03 | 2.07 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER BRUSH CREEK ON KY 550 AT JCT WITH KY 850. (036B00015N)(SR=41.3)(EBRP) | R | STP | BRX | 2020 | 200000 | 200000 | NO |  |  |  | 0
[6 empty] | FLOYD | 12-1121 | KY 550 | 0.04 | 2.03 | 2.07 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER BRUSH CREEK ON KY 550 AT JCT WITH KY 850. (036B00015N)(SR=41.3)(EBRP) | U | STP | BRX | 2020 | 300000 | 300000 | NO |  |  |  | 0
[6 empty] | FLOYD | 12-8901 |  |  |  |  | RELIABILITY | SAFETY(P) | MOUNTAIN PARKWAY EXPANSION FROM PRESTONSBURG TO WEST VIRGINIA LINE. (16CCN) | P | NHPP | NH | 2017 | 3000000 | 3000000 | NO |  |  |  | 0
[6 empty] | FRANKLIN | 5-1065 | US 460 |  | 2.177 | 2.217 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON US 460 OVER SOUTH ELKHORN CREEK AT INTERSECTION OF US 460 AND N SCRUGGS LN(CR 1010)(SR 41.3) 037B00006N (PART-WIDTH CONSTRUCTION ON EXISTING LOCATION) | R | NHPP | BRO | 2017 | 100000 | 100000 | NO |  |  |  | 0
[6 empty] | FRANKLIN | 5-1065 | US 460 |  | 2.177 | 2.217 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON US 460 OVER SOUTH ELKHORN CREEK AT INTERSECTION OF US 460 AND N SCRUGGS LN(CR 1010)(SR 41.3) 037B00006N (PART-WIDTH CONSTRUCTION ON EXISTING LOCATION) | U | NHPP | BRO | 2017 | 200000 | 200000 | NO |  |  |  | 0
[6 empty] | FRANKLIN | 5-1065 | US 460 |  | 2.177 | 2.217 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON US 460 OVER SOUTH ELKHORN CREEK AT INTERSECTION OF US 460 AND N SCRUGGS LN(CR 1010)(SR 41.3) 037B00006N (PART-WIDTH CONSTRUCTION ON EXISTING LOCATION) | C | NHPP | BRO | 2018 | 700000 | 700000 | NO |  |  |  | 0
[6 empty] | FRANKLIN | 5-1078 | CR 1230 | 0.025 | 0.04 | 0.065 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER BENSON CREEK ON CRAB ORCHARD ROAD (CR 1230) 200 FT NW OF KY 151 NEAR I-64 EXIT 48 (037C00010N)(SR=23.9) (EBRP)(16CCR) | D | STP | BRZ | 2017 | 350000 | 350000 | NO |  |  |  | 0
[6 empty] | FRANKLIN | 5-1078 | CR 1230 | 0.025 | 0.04 | 0.065 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER BENSON CREEK ON CRAB ORCHARD ROAD (CR 1230) 200 FT NW OF KY 151 NEAR I-64 EXIT 48 (037C00010N)(SR=23.9) (EBRP)(16CCR) | R | STP | BRZ | 2017 | 10000 | 10000 | NO |  |  |  | 0
[6 empty] | FRANKLIN | 5-1078 | CR 1230 | 0.025 | 0.04 | 0.065 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER BENSON CREEK ON CRAB ORCHARD ROAD (CR 1230) 200 FT NW OF KY 151 NEAR I-64 EXIT 48 (037C00010N)(SR=23.9) (EBRP)(16CCR) | U | STP | BRZ | 2017 | 20000 | 20000 | NO |  |  |  | 0
[6 empty] | FRANKLIN | 5-1078 | CR 1230 | 0.025 | 0.04 | 0.065 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER BENSON CREEK ON CRAB ORCHARD ROAD (CR 1230) 200 FT NW OF KY 151 NEAR I-64 EXIT 48 (037C00010N)(SR=23.9) (EBRP)(16CCR) | C | STP | BRZ | 2018 | 875000 | 875000 | NO |  |  |  | 0
[6 empty] | FRANKLIN | 5-2035.7 | I 64 | 5.42 | 47.7 | 53.75 | RELIABILITY | PAVEMENT REHAB-INT(P) | PAVEMENT REHAB AND BRIDGE WIDENING ON I-64 FROM MP 47.70 TO MP 53.75. (2004BOPC)(DESIGN FUNDED UNDER 5-2035.40)(16CCN) | R | NHPP | IM | 2018 | 120000 | 120000 | NO |  |  |  | 0
[6 empty] | FRANKLIN | 5-2035.7 | I 64 | 5.42 | 47.7 | 53.75 | RELIABILITY | PAVEMENT REHAB-INT(P) | PAVEMENT REHAB AND BRIDGE WIDENING ON I-64 FROM MP 47.70 TO MP 53.75. (2004BOPC)(DESIGN FUNDED UNDER 5-2035.40)(16CCN) | U | NHPP | IM | 2019 | 110000 | 110000 | NO |  |  |  | 0
[6 empty] | FRANKLIN | 5-2035.7 | I 64 | 5.42 | 47.7 | 53.75 | RELIABILITY | PAVEMENT REHAB-INT(P) | PAVEMENT REHAB AND BRIDGE WIDENING ON I-64 FROM MP 47.70 TO MP 53.75. (2004BOPC)(DESIGN FUNDED UNDER 5-2035.40)(16CCN) | C | NHPP | IM | 2020 | 29250000 | 29250000 | YES |  |  |  | 0
[6 empty] | FRANKLIN | 5-8813 | US 60 | 0.098 | 8.019 | 8.117 | RELIABILITY | TRANSP ENHANCEMENT(P) | CONSTRUCTION AND SIDEWALK IMPROVEMENTS TO THE INTERSECTION OF SECOND STREET AND BRIDGE STREET INCLUDING THE SIDEWALK ALONG SECOND STREET TO EWING STREET. (14CCN)(16CCN) | C | TE | TE | 2017 | 610000 | 488000 | NO |  |  |  | 0
[6 empty] | FULTON | 1-25 | JC 9003 | 1.66 | 0 | 1.66 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT AND IMPROVE I-69 AT THE KENTUCKY/TENNESSEE STATE LINE TO US-51 INTERCHANGE AT FULTON. (I-69 CORRIDOR IMPROVEMENT)(2012BOP) | D | NHPP | NH | 2019 | 3000000 | 3000000 | NO |  |  |  | 0
[6 empty] | FULTON | 1-26 | JC 9003 | 19 | 1 | 3.434 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT ELEMENTS OF THE EXISTING PURCHASE PARKWAY BETWEEN MP 1 AND MP 20 INCLUDING THE RECONSTRUCTION OF THE KY339 INTERCHANGE IN WINGO, KY. (I-69 CORRIDOR IMPROVEMENT) (2012BOP) | R | NHPP | NH | 2019 | 750000 | 750000 | NO |  |  |  | 0
[6 empty] | FULTON | 1-1148 | CR 1011 |  | 0.247 | 0.287 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON HOLLAND LN (CR 1011) OVER BRANCH OF HARRIS FORK CREEK 0.26 MILE E OF KENTUCKY AVE (KY 307)(SR 31.9)038C00001N(12CCR)(AR/W) | U | STP | BRZ | 2017 | 100000 | 100000 | NO |  |  |  | 0
[6 empty] | GALLATIN | 6-8910 | I 71 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT I-71 FROM US 127 FROM MP 62.8 TO MP 64 TO IMPROVE GEOMETRICS. (16CCN). | D | NHPP | IM | 2019 | 2200000 | 2200000 | NO |  |  |  | 0
[6 empty] | GALLATIN | 6-8910 | I 71 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT I-71 FROM US 127 FROM MP 62.8 TO MP 64 TO IMPROVE GEOMETRICS. (16CCN). | R | NHPP | IM | 2020 | 1500000 | 1500000 | NO |  |  |  | 0
[6 empty] | GALLATIN | 6-8910 | I 71 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT I-71 FROM US 127 FROM MP 62.8 TO MP 64 TO IMPROVE GEOMETRICS. (16CCN). | U | NHPP | IM | 2020 | 500000 | 500000 | NO |  |  |  | 0
[6 empty] | GARRARD | 7-1120 | KY 1972 | 0.1 | 0.613 | 0.713 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-1972 (MP 0.663) OVER BR OF TURKEY CREEK; .50 MI EAST OF JCT KY 39; (STRUCTURALLY DEFICIENT, SR=11.5) 040B00023N | R | STP | BRX | 2017 | 75000 | 75000 | NO |  |  |  | 0
[6 empty] | GARRARD | 7-1120 | KY 1972 | 0.1 | 0.613 | 0.713 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-1972 (MP 0.663) OVER BR OF TURKEY CREEK; .50 MI EAST OF JCT KY 39; (STRUCTURALLY DEFICIENT, SR=11.5) 040B00023N | U | STP | BRX | 2017 | 60000 | 60000 | NO |  |  |  | 0
[6 empty] | GARRARD | 7-1120 | KY 1972 | 0.1 | 0.613 | 0.713 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-1972 (MP 0.663) OVER BR OF TURKEY CREEK; .50 MI EAST OF JCT KY 39; (STRUCTURALLY DEFICIENT, SR=11.5) 040B00023N | C | STP | BRX | 2017 | 350000 | 350000 | NO |  |  |  | 0
[6 empty] | GARRARD | 7-1122 | KY 563 | 0.1 | 3.84 | 3.915 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-563 (MP 3.89) OVER SUGAR CREEK; E-@ JCT KY 39; (STRUCTURALLY DEFICIENT, SR=21.7) 040B00034N | R | STP | BRX | 2017 | 80000 | 80000 | NO |  |  |  | 0
[6 empty] | GARRARD | 7-1122 | KY 563 | 0.1 | 3.84 | 3.915 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-563 (MP 3.89) OVER SUGAR CREEK; E-@ JCT KY 39; (STRUCTURALLY DEFICIENT, SR=21.7) 040B00034N | U | STP | BRX | 2017 | 70000 | 70000 | NO |  |  |  | 0
[6 empty] | GARRARD | 7-1122 | KY 563 | 0.1 | 3.84 | 3.915 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-563 (MP 3.89) OVER SUGAR CREEK; E-@ JCT KY 39; (STRUCTURALLY DEFICIENT, SR=21.7) 040B00034N | C | STP | BRX | 2017 | 430000 | 430000 | NO |  |  |  | 0
[6 empty] | GARRARD | 7-1138 | KY 1972 | 0.01 | 1.76 | 1.77 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER GILBERTS CREEK ON KY 1972 1.4 MI E OF CRAB ORCHARD ROAD (CR 1226) AT SECL OF LANCASTER. (040B00024N)(SR=35.5)(EBRP) | D | STP | BRX | 2020 | 300000 | 300000 | NO |  |  |  | 0
[6 empty] | GRANT | 6-411 | KY 36 | 2.9 | 13.7 | 14.761 | SAFETY | SAFETY(P) | ROADWAY IMPROVEMENTS TO KY-36 FROM US-25 AT WILLIAMSTOWN TO APPROXIMATELY 1 MILE EAST OF HEEKIN CLARKS ROAD.(12CCR)(14CCR) | R | STP | STP | 2017 | 400000 | 400000 | NO |  |  |  | 0
[6 empty] | GRANT | 6-411 | KY 36 | 2.9 | 13.7 | 14.761 | SAFETY | SAFETY(P) | ROADWAY IMPROVEMENTS TO KY-36 FROM US-25 AT WILLIAMSTOWN TO APPROXIMATELY 1 MILE EAST OF HEEKIN CLARKS ROAD.(12CCR)(14CCR) | U | STP | STP | 2017 | 1010000 | 1010000 | NO |  |  |  | 0
[6 empty] | GRANT | 6-411 | KY 36 | 2.9 | 13.7 | 14.761 | SAFETY | SAFETY(P) | ROADWAY IMPROVEMENTS TO KY-36 FROM US-25 AT WILLIAMSTOWN TO APPROXIMATELY 1 MILE EAST OF HEEKIN CLARKS ROAD.(12CCR)(14CCR) | C | STP | STP | 2017 | 9100000 | 9100000 | NO |  |  |  | 0
[6 empty] | GRANT | 6-8714 | CR 1138 | 0.05 | 0.28 | 0.33 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON SOUTH END OF BLANCHET ROAD 0.3 MILES NORTHEAST OF US 25. (SR=35.9) 041C00012N (12CCN) | R | STP | BRZ | 2017 | 270000 | 270000 | NO |  |  |  | 0
[6 empty] | GRANT | 6-8714 | CR 1138 | 0.05 | 0.28 | 0.33 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON SOUTH END OF BLANCHET ROAD 0.3 MILES NORTHEAST OF US 25. (SR=35.9) 041C00012N (12CCN) | U | STP | BRZ | 2017 | 480000 | 480000 | NO |  |  |  | 0
[6 empty] | GRANT | 6-8714 | CR 1138 | 0.05 | 0.28 | 0.33 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON SOUTH END OF BLANCHET ROAD 0.3 MILES NORTHEAST OF US 25. (SR=35.9) 041C00012N (12CCN) | C | STP | BRZ | 2019 | 1630000 | 1630000 | NO |  |  |  | 0
[6 empty] | GRANT | 6-8715 | CR 1138 | 0.07 | 1.95 | 2.02 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON NORTH END OF BLANCHET ROAD 0.2 MILES SOUTHEAST OF THE JUNCTION WITH US 25. (SR=28.1) 041C00014N (12CCN) | R | STP | BRZ | 2017 | 340000 | 340000 | NO |  |  |  | 0
[6 empty] | GRANT | 6-8715 | CR 1138 | 0.07 | 1.95 | 2.02 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON NORTH END OF BLANCHET ROAD 0.2 MILES SOUTHEAST OF THE JUNCTION WITH US 25. (SR=28.1) 041C00014N (12CCN) | U | STP | BRZ | 2017 | 100000 | 100000 | NO |  |  |  | 0
[6 empty] | GRANT | 6-8715 | CR 1138 | 0.07 | 1.95 | 2.02 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON NORTH END OF BLANCHET ROAD 0.2 MILES SOUTHEAST OF THE JUNCTION WITH US 25. (SR=28.1) 041C00014N (12CCN) | C | STP | BRZ | 2020 | 2250000 | 2250000 | NO |  |  |  | 0
[6 empty] | GRANT | 6-8716 | CR 1142 | 0.05 | 0.02 | 0.07 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON NORTH END OF DELANEY ROAD 0.1 MILE NORTH OF THE JUNCTION WITH US 25. (SR=21.5) 041C00016N (12CCN) | R | NHPP | BRO | 2017 | 180000 | 180000 | NO |  |  |  | 0
[6 empty] | GRANT | 6-8716 | CR 1142 | 0.05 | 0.02 | 0.07 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON NORTH END OF DELANEY ROAD 0.1 MILE NORTH OF THE JUNCTION WITH US 25. (SR=21.5) 041C00016N (12CCN) | U | NHPP | BRO | 2017 | 290000 | 290000 | NO |  |  |  | 0
[6 empty] | GRANT | 6-8716 | CR 1142 | 0.05 | 0.02 | 0.07 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON NORTH END OF DELANEY ROAD 0.1 MILE NORTH OF THE JUNCTION WITH US 25. (SR=21.5) 041C00016N (12CCN) | C | NHPP | BRO | 2017 | 2250000 | 2250000 | NO |  |  |  | 0
[6 empty] | GRAVES | 1-1147 | CR 1384 |  | 0.403 | 0.443 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON RULE SHACK ROAD OVER IC RAILROAD 0.4 MILE E OF KY 339(SR29.3)042C00146N | C | STP | BRZ | 2018 | 1250000 | 1250000 | NO |  |  |  | 0
[6 empty] | GRAVES | 1-1157 | CR 1088 | 0.1 | 0.3 | 0.4 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER PANTHER CREEK ON MCKENDREE CHURCH RD (CR 1088) 0.3 MI E OF KY 301 042C00010N SR 28.3 | D | STP | BRZ | 2019 | 280000 | 280000 | NO |  |  |  | 0
[6 empty] | GRAYSON | 4-8502 | US 62 |  | 23 | 25.5 | RELIABILITY | MINOR WIDENING(O) | WIDEN PORTIONS OF US-62 FROM LEITCHFIELD TO CLARKSON. (08CCN)(10CCR)(14CCN)(16CCR) | C | STP | STP | 2019 | 9120000 | 9120000 | NO |  |  |  | 0
[6 empty] | GREEN | 4-158.1 | KY 61 |  | 3.9 | 4.25 | RELIABILITY | RECONSTRUCTION(O) | COLUMBIA TO GREENSBURG PRIORITY SECTION 1B: KY-61 FROM KY-487 AT GRESHAM, NW TO 5000' SE OF US-68 IN GREENSBURG. TO CONSTRUCT INTERSECTION IMPROVEMENT AT KY61-KY487; (SEE ITEM #8-128.12)(2005HPP-KY125)(2005HPP-KY161). | R | HPP | HPP | 2017 | 200000 | 200000 | NO |  |  |  | 0
[6 empty] | GREEN | 4-158.1 | KY 61 |  | 3.9 | 4.25 | RELIABILITY | RECONSTRUCTION(O) | COLUMBIA TO GREENSBURG PRIORITY SECTION 1B: KY-61 FROM KY-487 AT GRESHAM, NW TO 5000' SE OF US-68 IN GREENSBURG. TO CONSTRUCT INTERSECTION IMPROVEMENT AT KY61-KY487; (SEE ITEM #8-128.12)(2005HPP-KY125)(2005HPP-KY161). | U | HPP | HPP | 2017 | 100000 | 100000 | NO |  |  |  | 0
[6 empty] | GREEN | 4-158.1 | KY 61 |  | 3.9 | 4.25 | RELIABILITY | RECONSTRUCTION(O) | COLUMBIA TO GREENSBURG PRIORITY SECTION 1B: KY-61 FROM KY-487 AT GRESHAM, NW TO 5000' SE OF US-68 IN GREENSBURG. TO CONSTRUCT INTERSECTION IMPROVEMENT AT KY61-KY487; (SEE ITEM #8-128.12)(2005HPP-KY125)(2005HPP-KY161). | C | HPP | HPP | 2017 | 1490000 | 1490000 | NO |  |  |  | 0
[6 empty] | GREENUP | 9-1073 | KY 244 | 0.1 | 0 | 0.207 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-244 (MP 0.103) OVER CSX RAILROAD; .05 MI N.E. OF JCT US 23; (STRUCTURALLY DEFICIENT, SR=47.9) 045B00039N (16CCR) | U | NHPP | BRO | 2017 | 1090000 | 1090000 | NO |  |  |  | 0
[6 empty] | GREENUP | 9-1073 | KY 244 | 0.1 | 0 | 0.207 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-244 (MP 0.103) OVER CSX RAILROAD; .05 MI N.E. OF JCT US 23; (STRUCTURALLY DEFICIENT, SR=47.9) 045B00039N (16CCR) | C | NHPP | BRO | 2018 | 5000000 | 5000000 | NO |  |  |  | 0
[6 empty] | GREENUP | 9-1073.01 | KY 244 |  | 0 | 0.207 | RELIABILITY | PREFINANCD CONVRSN(O) | REPLACE BRIDGE ON KY-244 (MP 0.103) OVER CSX RAILROAD; .05 MI N.E. OF JCT US 23; (STRUCTURALLY DEFICIENT, SR=47.9) 045B00039N (ADDITIONAL FUNDING FOR C PHASE)(16CCR) | C | NHPP | BRO | 2018 | 4740000 | 4740000 | NO |  |  |  | 0
[6 empty] | GREENUP | 9-1073.02 | KY 244 |  | 0 | 0.207 | RELIABILITY | PREFINANCD CONVRSN(O) | REPLACE BRIDGE ON KY-244 (MP 0.103) OVER CSX RAILROAD; .05 MI N.E. OF JCT US 23;(STRUCTURALLY DEFICIENT SR=47.9) 045B00039N (ADDITIONAL FUNDING FOR C PHASE)(16CCN) | C | NHPP | BRO | 2018 | 4370000 | 4370000 | NO |  |  |  | 0
[6 empty] | GREENUP | 9-1078 | CS 1023 | 0.1 | 0.071 | 0.171 | RELIABILITY | BRIDGE REPLACEMENT(P) | "DEMOLISH" BRIDGE ON CS-1023 (MP 0.121) OVER TOWN BRANCH; 100' S. JCT KY 2541; (STRUCTURALLY DEFICIENT, SR=16.5) 045C00051N | U | STP | BRZ | 2017 | 25000 | 25000 | NO |  |  |  | 0
[6 empty] | GREENUP | 9-1078 | CS 1023 | 0.1 | 0.071 | 0.171 | RELIABILITY | BRIDGE REPLACEMENT(P) | "DEMOLISH" BRIDGE ON CS-1023 (MP 0.121) OVER TOWN BRANCH; 100' S. JCT KY 2541; (STRUCTURALLY DEFICIENT, SR=16.5) 045C00051N | C | STP | BRZ | 2017 | 1000000 | 1000000 | NO |  |  |  | 0
[6 empty] | GREENUP | 9-1094 | CS 4041 | 0.016 | 0.05 | 0.066 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER POND RUN ON WILLIAMS AVE (CS 4041) IN RACELAND 250 FT NW OF POND RUN ROAD (CS 4001) (045C00119N) (SR=27.3) | D | STP | BRZ | 2019 | 350000 | 350000 | NO |  |  |  | 0
[6 empty] | GREENUP | 9-8509 | KY 207 |  |  |  | RELIABILITY | NEW ROUTE(O) | CONSTRUCT A NEW CONNECTOR ROAD CONNECTING FLATWOODS AT KY-207 AND KY-693 AND THE INDUSTRIAL PARKWAY CONNECTOR BETWEEN I-64 AND US-60. (08CCN)(16CCR) | R | STP | STP | 2017 | 8400000 | 8400000 | NO |  |  |  | 0
[6 empty] | GREENUP | 9-8509 | KY 207 |  |  |  | RELIABILITY | NEW ROUTE(O) | CONSTRUCT A NEW CONNECTOR ROAD CONNECTING FLATWOODS AT KY-207 AND KY-693 AND THE INDUSTRIAL PARKWAY CONNECTOR BETWEEN I-64 AND US-60. (08CCN)(16CCR) | U | STP | STP | 2019 | 6750000 | 6750000 | NO |  |  |  | 0
[6 empty] | GREENUP | 9-8509 | KY 207 |  |  |  | RELIABILITY | NEW ROUTE(O) | CONSTRUCT A NEW CONNECTOR ROAD CONNECTING FLATWOODS AT KY-207 AND KY-693 AND THE INDUSTRIAL PARKWAY CONNECTOR BETWEEN I-64 AND US-60. (08CCN)(16CCR) | C | STP | STP | 2020 | 26000000 | 26000000 | YES |  |  |  | 0
[6 empty] | HANCOCK | 2-316.1 | KY 69 |  |  |  | RELIABILITY | BRIDGE PAINTING(P) | BRIDGE PAINTING OF THE BOB CUMMINGS LINCOLN TRAIL BRIDGE OVER THE OHIO RIVER BETWEEN CANNELTON, INDIANA AND HAWESVILLE, KENTUCKY. INDOT IS THE LEAD STATE ON THE PROJECT. (2014BOP) | D | NHPP | BRO | 2017 | 25000 | 25000 | NO |  |  |  | 0
[6 empty] | HANCOCK | 2-316.11 | KY 69 |  |  |  | RELIABILITY | PREFINANCD CONVRSN(P) | BRIDGE PAINTING OF THE BOB CUMMINGS LINCOLN TRAIL BRIDGE OVER THE OHIO RIVER BETWEEN CANNELTON, INDIANA AND HAWESVILLE, KENTUCKY. INDOT IS THE LEAD STATE ON THE PROJECT. (ADDITIONAL FUNDING FOR C PHASE) | C | NHPP | BRO | 2019 | 2975000 | 2975000 | YES |  |  |  | 0
[6 empty] | HARDIN | 4-199 | US 31W | 0.4 | 36.4 | 36.8 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER P&L AND CSX RAILROADS (MP 36.4 TO 36.8 IN WEST POINT) (047B00007N).(16CCR) | C | STP | STP | 2019 | 9230000 | 9230000 | NO |  |  |  | 0
[6 empty] | HARDIN | 4-286.1 | I 65 | 0.1 | 81.95 | 82.05 | RELIABILITY | WEIGH STA REHAB(P) | I-65 SOUTHBOUND PORT OF ENTRY FOR A COMMERCIAL VEHICLE MONITORING STATION.(10CCR) | R | NHPP | IM | 2019 | 110000 | 110000 | NO |  |  |  | 0
[6 empty] | HARDIN | 4-286.1 | I 65 | 0.1 | 81.95 | 82.05 | RELIABILITY | WEIGH STA REHAB(P) | I-65 SOUTHBOUND PORT OF ENTRY FOR A COMMERCIAL VEHICLE MONITORING STATION.(10CCR) | U | NHPP | IM | 2019 | 1040000 | 1040000 | NO |  |  |  | 0
[6 empty] | HARDIN | 4-1077 | US 62 | 0.4 | 8.894 | 8.934 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON US 62 OVER UNNAMED STREAM 0.65 MILE SW OF KY 1375 (S LONG GROVE RD)(SR 48.5) 047B00052N | C | NHPP | BRO | 2017 | 490000 | 490000 | NO |  |  |  | 0
[6 empty] | HARDIN | 4-1093 | US 62 | 0.139 | 28.157 | 28.193 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON US 62 OVER ROLLING FORK AT THE HARDIN-NELSON CO LINE. (SR=49.3) 047B00023N | D | STP | BRX | 2019 | 800000 | 800000 | NO |  |  |  | 0
[6 empty] | HARLAN | 11-269.2 | US 421 |  |  |  | RELIABILITY | PREFINANCD CONVRSN(O) | HARLAN-VIRGINIA STATE LINE; RESCOPE US-421 FROM BARN BRANCH TO VIRGINIA STATE LINE. (ADDITIONAL FUNDS FOR C PHASE. SEE 11-269.10) (16CCN) | C | STP | STP | 2019 | 10000000 | 10000000 | YES |  |  |  | 0
[6 empty] | HARLAN | 11-269.3 | US 421 |  |  |  | RELIABILITY | PREFINANCD CONVRSN(O) | HARLAN-VIRGINIA STATE LINE; RESCOPE US-421 FROM BARN BRANCH TO VIRGINIA STATE LINE. (ADDITIONAL FUNDS FOR C PHASE. SEE 11-269.1 AND 11-269.2)(16CCN) | C | STP | STP | 2019 | 23800000 | 23800000 | YES |  |  |  | 0
[6 empty] | HARLAN | 11-1087 | KY 72 | 0.04 | 6.539 | 6.579 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 72 OVER CATRON CREEK AT INTERSECTION OF KY 72 AND SMITH LANE (CR 1226L)(SR 30) 048B00030N | C | STP | BRX | 2017 | 1300000 | 1300000 | NO |  |  |  | 0
[6 empty] | HARLAN | 11-1097 | KY 219 | 0.02 | 1.033 | 1.053 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER WALLINS CREEK ON KY 219 3.0 MILE SOUTH OF SCL OF WALLINS CREEK. (048B00047N)(SR=43.8) | D | STP | BRX | 2020 | 250000 | 250000 | NO |  |  |  | 0
[6 empty] | HARLAN | 11-1101 | US 119 | 0.118 | 34.787 | 34.905 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON US 119 OVER KY 160/MAIN ST IN HARLAN COUNTY, KY. (SR=32.3) 048B00126N | D | NHPP | BRO | 2019 | 800000 | 800000 | NO |  |  |  | 0
[6 empty] | HARLAN | 11-8703 | US 119 | 1 | 1.2 | 2.2 | RELIABILITY | MINOR WIDENING(O) | PROVIDE A PASSING BAY ON US 119 FROM MP 1.2 TO MP 2.2 IN HARLAN COUNTY.(12CCN)(14CCR)(16CCR) | R | NHPP | NH | 2017 | 500000 | 500000 | NO |  |  |  | 0
[6 empty] | HARLAN | 11-8703 | US 119 | 1 | 1.2 | 2.2 | RELIABILITY | MINOR WIDENING(O) | PROVIDE A PASSING BAY ON US 119 FROM MP 1.2 TO MP 2.2 IN HARLAN COUNTY.(12CCN)(14CCR)(16CCR) | U | NHPP | NH | 2017 | 500000 | 500000 | NO |  |  |  | 0
[6 empty] | HARLAN | 11-8703 | US 119 | 1 | 1.2 | 2.2 | RELIABILITY | MINOR WIDENING(O) | PROVIDE A PASSING BAY ON US 119 FROM MP 1.2 TO MP 2.2 IN HARLAN COUNTY.(12CCN)(14CCR)(16CCR) | C | NHPP | NH | 2019 | 3000000 | 3000000 | NO |  |  |  | 0
[6 empty] | HARLAN | 11-8807 | US 119 | 0.2 | 10 | 10.2 | SAFETY | SAFETY(P) | CONSTRUCT TURN LANES ONTO KY 840 FROM US 119. (14CCN) (16CCR) | D | NHPP | NH | 2017 | 100000 | 100000 | NO |  |  |  | 0
[6 empty] | HARLAN | 11-8807 | US 119 | 0.2 | 10 | 10.2 | SAFETY | SAFETY(P) | CONSTRUCT TURN LANES ONTO KY 840 FROM US 119. (14CCN) (16CCR) | R | NHPP | NH | 2017 | 25000 | 25000 | NO |  |  |  | 0
[6 empty] | HARLAN | 11-8807 | US 119 | 0.2 | 10 | 10.2 | SAFETY | SAFETY(P) | CONSTRUCT TURN LANES ONTO KY 840 FROM US 119. (14CCN) (16CCR) | U | NHPP | NH | 2018 | 75000 | 75000 | NO |  |  |  | 0
[6 empty] | HARLAN | 11-8807 | US 119 | 0.2 | 10 | 10.2 | SAFETY | SAFETY(P) | CONSTRUCT TURN LANES ONTO KY 840 FROM US 119. (14CCN) (16CCR) | C | NHPP | NH | 2018 | 1300000 | 1300000 | NO |  |  |  | 0
[6 empty] | HARLAN | 11-8808 | US 119 | 0.2 | 9.8 | 10 | SAFETY | SAFETY(P) | CONSTRUCT A LEFT TURN LANE FROM S US 119 ONTO KY 3152. (14CCN) (16CCR) | D | NHPP | NH | 2017 | 100000 | 100000 | NO |  |  |  | 0
[6 empty] | HARLAN | 11-8808 | US 119 | 0.2 | 9.8 | 10 | SAFETY | SAFETY(P) | CONSTRUCT A LEFT TURN LANE FROM S US 119 ONTO KY 3152. (14CCN) (16CCR) | R | NHPP | NH | 2017 | 25000 | 25000 | NO |  |  |  | 0
[6 empty] | HARLAN | 11-8808 | US 119 | 0.2 | 9.8 | 10 | SAFETY | SAFETY(P) | CONSTRUCT A LEFT TURN LANE FROM S US 119 ONTO KY 3152. (14CCN) (16CCR) | U | NHPP | NH | 2018 | 50000 | 50000 | NO |  |  |  | 0
[6 empty] | HARLAN | 11-8808 | US 119 | 0.2 | 9.8 | 10 | SAFETY | SAFETY(P) | CONSTRUCT A LEFT TURN LANE FROM S US 119 ONTO KY 3152. (14CCN) (16CCR) | C | NHPP | NH | 2018 | 1100000 | 1100000 | NO |  |  |  | 0
[6 empty] | HARLAN | 11-8906 | US 119 |  |  |  | RELIABILITY | SAFETY(P) | ADDRESS HORIZONTAL ALIGNMENT AND SAFETY ISSUES ON US 119 NEAR HARLAN/BELL COUNTY LINE. (16CCN) | C | NHPP | NH | 2019 | 17350000 | 17350000 | NO |  |  |  | 0
[6 empty] | HARRISON | 6-1093 | CR 1124 |  | 0.051 | 0.091 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON OLD LAIR RD (CR-1124) (0.071) OVER S. FORK LICKING RIVER. (SR=14.2) 049C00035N (16CCR) | D | STP | BRZ | 2017 | 500000 | 500000 | NO |  |  |  | 0
[6 empty] | HENDERSON | 2-79.3 | US 60 | 1 | 7.7 | 8.71 | RELIABILITY | MAJOR WIDENING(O) | WIDEN AND IMPROVE US 60 FROM WEST OF HENDERSON COMMUNITY COLLEGE (MP 7.7) EXTENDING EAST TO KY 425 (MP 8.7). (BOP2012) | C | STP | STP | 2017 | 5500000 | 5500000 | NO |  |  |  | 0
[6 empty] | HENDERSON | 2-700.13 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | FEDERAL 'STP' FUNDS DEDICATED TO HENDERSON FOR FY 2018. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C | SHN | SHN | 2018 | 600000 | 480000 | NO |  |  |  | 0
[6 empty] | HENDERSON | 2-700.14 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | FEDERAL 'STP' FUNDS DEDICATED TO HENDERSON FOR FY 2019. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | C | SHN | SHN | 2019 | 700000 | 560000 | NO |  |  |  | 0
[6 empty] | HENDERSON | 2-700.15 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | FEDERAL 'STP' FUNDS DEDICATED TO HENDERSON FOR FY 2020. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | C | SHN | SHN | 2020 | 700000 | 560000 | NO |  |  |  | 0
[6 empty] | HENDERSON | 2-711 | US 41 | 0.14 | 12.766 | 12.906 | SAFETY | SAFETY(P) | US 41/KY 812 INTERSECTION UPGRADE: ADD RIGHT TURN AND LEFT TURN LANES INCLUDING SIGNAL PHASING. KYTC PROJECT WITH KYTC PROVIDING 20% MATCH.(TOLL CREDITS)(FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | R | SHN | SHN | 2017 | 50000 | 40000 | NO |  |  |  | 0
[6 empty] | HENDERSON | 2-711 | US 41 | 0.14 | 12.766 | 12.906 | SAFETY | SAFETY(P) | US 41/KY 812 INTERSECTION UPGRADE: ADD RIGHT TURN AND LEFT TURN LANES INCLUDING SIGNAL PHASING. KYTC PROJECT WITH KYTC PROVIDING 20% MATCH.(TOLL CREDITS)(FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | U | SHN | SHN | 2017 | 100000 | 80000 | NO |  |  |  | 0
[6 empty] | HENDERSON | 2-711 | US 41 | 0.14 | 12.766 | 12.906 | SAFETY | SAFETY(P) | US 41/KY 812 INTERSECTION UPGRADE: ADD RIGHT TURN AND LEFT TURN LANES INCLUDING SIGNAL PHASING. KYTC PROJECT WITH KYTC PROVIDING 20% MATCH.(TOLL CREDITS)(FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C | SHN | SHN | 2017 | 550000 | 440000 | NO |  |  |  | 0
[6 empty] | HENDERSON | 2-713 | CS 1453 |  | 0.72 | 0.77 | RELIABILITY | BRIDGE REPLACEMENT(P) | WATHEN BRIDGE REPLACEMENT: REPLACE EXISTING BRIDGE WITH 6FT PRECAST CONCRETE BOX CULVERT, PAVEMENT AND GUARDRAIL. LPA PROJECT. CITY TO PROVIDE MATCH.(FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP)(051C00014) | R | SHN | SHN | 2017 | 10000 | 8000 | NO |  |  |  | 0
[6 empty] | HENDERSON | 2-713 | CS 1453 |  | 0.72 | 0.77 | RELIABILITY | BRIDGE REPLACEMENT(P) | WATHEN BRIDGE REPLACEMENT: REPLACE EXISTING BRIDGE WITH 6FT PRECAST CONCRETE BOX CULVERT, PAVEMENT AND GUARDRAIL. LPA PROJECT. CITY TO PROVIDE MATCH.(FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP)(051C00014) | U | SHN | SHN | 2017 | 15000 | 12000 | NO |  |  |  | 0
[6 empty] | HENDERSON | 2-713 | CS 1453 |  | 0.72 | 0.77 | RELIABILITY | BRIDGE REPLACEMENT(P) | WATHEN BRIDGE REPLACEMENT: REPLACE EXISTING BRIDGE WITH 6FT PRECAST CONCRETE BOX CULVERT, PAVEMENT AND GUARDRAIL. LPA PROJECT. CITY TO PROVIDE MATCH.(FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP)(051C00014) | C | SHN | SHN | 2017 | 200000 | 160000 | NO |  |  |  | 0
[6 empty] | HENDERSON | 2-714 | KY 2183 | 0.1 | 1.693 | 1.793 | RELIABILITY | MATCHED FED FUNDS(O) | KY 2183 / KY 1539 INTERSECTION AND UPGRADE: PROJECT WILL RECONSTRUCT THE INTERSECTION AND MAKE IMPROVEMENTS TO THE SOUTHBOUND APPROACH. (2012BOP) | R | SHN | SHN | 2017 | 400000 | 320000 | NO |  |  |  | 0
[6 empty] | HENDERSON | 2-714 | KY 2183 | 0.1 | 1.693 | 1.793 | RELIABILITY | MATCHED FED FUNDS(O) | KY 2183 / KY 1539 INTERSECTION AND UPGRADE: PROJECT WILL RECONSTRUCT THE INTERSECTION AND MAKE IMPROVEMENTS TO THE SOUTHBOUND APPROACH. (2012BOP) | U | SHN | SHN | 2017 | 400000 | 320000 | NO |  |  |  | 0
[6 empty] | HENDERSON | 2-714 | KY 2183 | 0.1 | 1.693 | 1.793 | RELIABILITY | MATCHED FED FUNDS(O) | KY 2183 / KY 1539 INTERSECTION AND UPGRADE: PROJECT WILL RECONSTRUCT THE INTERSECTION AND MAKE IMPROVEMENTS TO THE SOUTHBOUND APPROACH. (2012BOP) | C | SHN | SHN | 2017 | 600000 | 480000 | NO |  |  |  | 0
[6 empty] | HENDERSON | 2-715 | US 41 | 0.1 | 18.488 | 18.588 | RELIABILITY | MATCHED FED FUNDS(O) | US 41/ WOLF HILLS ROAD INTERSECTION UPGRADE: PROJECT WILL ADD DEDICATED RIGHT TURN AND LEFT TURN LANES INCLUDING SIGNAL PHASING TO BE MODIFIED OR ADDED TO EACH LEG OF THE INTERSECTION. (2012BOP) | R | SHN | SHN | 2017 | 50000 | 40000 | NO |  |  |  | 0
[6 empty] | HENDERSON | 2-715 | US 41 | 0.1 | 18.488 | 18.588 | RELIABILITY | MATCHED FED FUNDS(O) | US 41/ WOLF HILLS ROAD INTERSECTION UPGRADE: PROJECT WILL ADD DEDICATED RIGHT TURN AND LEFT TURN LANES INCLUDING SIGNAL PHASING TO BE MODIFIED OR ADDED TO EACH LEG OF THE INTERSECTION. (2012BOP) | U | SHN | SHN | 2017 | 100000 | 80000 | NO |  |  |  | 0
[6 empty] | HENDERSON | 2-715 | US 41 | 0.1 | 18.488 | 18.588 | RELIABILITY | MATCHED FED FUNDS(O) | US 41/ WOLF HILLS ROAD INTERSECTION UPGRADE: PROJECT WILL ADD DEDICATED RIGHT TURN AND LEFT TURN LANES INCLUDING SIGNAL PHASING TO BE MODIFIED OR ADDED TO EACH LEG OF THE INTERSECTION. (2012BOP) | C | SHN | SHN | 2017 | 500000 | 400000 | NO |  |  |  | 0
[6 empty] | HENDERSON | 2-1080 | US 60 | 0.208 | 19.236 | 19.444 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON US 60 OVER GREEN RIVER AT INTERSECTION WITH KY 1078 (SR 39)051B00015N.(12CCR) | U | NHPP | BRO | 2017 | 250000 | 250000 | NO |  |  |  | 0
[6 empty] | HENDERSON | 2-1080 | US 60 | 0.208 | 19.236 | 19.444 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON US 60 OVER GREEN RIVER AT INTERSECTION WITH KY 1078 (SR 39)051B00015N.(12CCR) | C | NHPP | BRO | 2017 | 14000000 | 14000000 | NO |  |  |  | 0
[6 empty] | HENDERSON | 2-1080.01 | US 60 | 0.208 | 19.236 | 19.444 | RELIABILITY | PREFINANCD CONVRSN(O) | REPLACE BRIDGE ON US 60 OVER GREEN RIVER AT INTERSECTION WITH KY 1078 (SR 39) 051B00015N (ADDITIONAL FUNDING FOR C PHASE) | C | NHPP | BRO | 2018 | 6000000 | 6000000 | NO |  |  |  | 0
[6 empty] | HENDERSON | 2-1080.02 | US 60 | 0.208 | 19.236 | 19.444 | RELIABILITY | PREFINANCD CONVRSN(O) | REPLACE BRIDGE ON US 60 OVER GREEN RIVER AT INTERSECTION WITH KY 1078 (SR 39) 051B00015N (ADDITIONAL FUNDING FOR C PHASE) | C | NHPP | BRO | 2019 | 5000000 | 5000000 | YES |  |  |  | 0
[6 empty] | HENDERSON | 2-1088.1 | I 69 |  |  |  | RELIABILITY | NEW ROUTE(O) | DEVELOP ALIGNMENT FOR INTERSTATE 69 HENDERSON/EVANSVILLE OHIO RIVER CROSSING (TO BE DEVELOPED IN CONCERT WITH 2-1088.00).(16CCR) | D | NHPP | NH | 2017 | 6000000 | 6000000 | NO |  |  |  | 0
[6 empty] | HENDERSON | 2-1088.1 | I 69 |  |  |  | RELIABILITY | NEW ROUTE(O) | DEVELOP ALIGNMENT FOR INTERSTATE 69 HENDERSON/EVANSVILLE OHIO RIVER CROSSING (TO BE DEVELOPED IN CONCERT WITH 2-1088.00).(16CCR) | R | NHPP | NH | 2018 | 20000000 | 20000000 | NO |  |  |  | 0
[6 empty] | HENDERSON | 2-1088.1 | I 69 |  |  |  | RELIABILITY | NEW ROUTE(O) | DEVELOP ALIGNMENT FOR INTERSTATE 69 HENDERSON/EVANSVILLE OHIO RIVER CROSSING (TO BE DEVELOPED IN CONCERT WITH 2-1088.00).(16CCR) | U | NHPP | NH | 2019 | 15000000 | 15000000 | NO |  |  |  | 0
[6 empty] | HICKMAN | 1-1062 | KY 1826 | 0.1 | 4.888 | 4.988 | SAFETY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-1826 OVER TOWN CREEK (B79) IN CLINTON. (SR=24.4): (053B00079N) | C | STP | BRX | 2018 | 2000000 | 2000000 | NO |  |  |  | 0
[6 empty] | HICKMAN | 1-1156 | CR 1011 | 0.055 | 0.25 | 0.305 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER IC RR ON BALTIMORE RD (CR 1011) 0.3 MI NW OF HICKMAN/GRAVES CO LINE 053C00003N SR 24.5 | D | STP | BRZ | 2019 | 380000 | 380000 | NO |  |  |  | 0
[6 empty] | HICKMAN | 1-1158 | KY 1301 | 0.057 | 1.039 | 1.096 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER HURRICANE BRANCH ON KY 1301, LOCATED 1.092 MI NW OF US 51 IN HICKMAN COUNTY, KY.(SR 21) (053B00083N) (2014BOP) | C | STP | BRX | 2017 | 300000 | 300000 | NO |  |  |  | 0
[6 empty] | HOPKINS | 2-137.02 | US 41A | 3.6 | 0 | 3.426 | RELIABILITY | MAJOR WIDENING(O) | US 41A PHASE II DESIGN AND RIGHT-OF-WAY. (2005HPP-KY135)(SEE 2-137.01 FOR "STP" COMPONENT) | C | HPP | HPP | 2018 | 2879680 | 2879680 | NO |  |  |  | 0
[6 empty] | HOPKINS | 2-1072 | KY 260 | 0.1 | 2.09 | 2.19 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-260 (MP 2.14) OVER OTTER CREEK; .20 MI EAST OF PENNYRILE PARKWAY; (FUNCTIONALLY OBSOLETE, SR=31.9) 054B00022N (14CCR) | R | STP | BRX | 2017 | 160000 | 160000 | NO |  |  |  | 0
[6 empty] | HOPKINS | 2-1072 | KY 260 | 0.1 | 2.09 | 2.19 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-260 (MP 2.14) OVER OTTER CREEK; .20 MI EAST OF PENNYRILE PARKWAY; (FUNCTIONALLY OBSOLETE, SR=31.9) 054B00022N (14CCR) | U | STP | BRX | 2017 | 300000 | 300000 | NO |  |  |  | 0
[6 empty] | HOPKINS | 2-1072 | KY 260 | 0.1 | 2.09 | 2.19 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-260 (MP 2.14) OVER OTTER CREEK; .20 MI EAST OF PENNYRILE PARKWAY; (FUNCTIONALLY OBSOLETE, SR=31.9) 054B00022N (14CCR) | C | STP | BRX | 2018 | 680000 | 680000 | NO |  |  |  | 0
[6 empty] | HOPKINS | 2-1081 | KY 293 |  | 0 | 0.044 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 293 AT THE CALDWELL/HOPKINS COUNTY LINE(SR 37.7)054B00115N | C | NHPP | BRO | 2017 | 1750000 | 1750000 | NO |  |  |  | 0
[6 empty] | HOPKINS | 2-1084 | KY 1069 | 0.04 | 2.355 | 2.395 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 1069 OVER OTTER CREEK AT INTERSECTION OF J D BUCHANAN RD (CR 1093)(SR 43.9)054B00157N | R | NHPP | BRO | 2017 | 150000 | 150000 | NO |  |  |  | 0
[6 empty] | HOPKINS | 2-1084 | KY 1069 | 0.04 | 2.355 | 2.395 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 1069 OVER OTTER CREEK AT INTERSECTION OF J D BUCHANAN RD (CR 1093)(SR 43.9)054B00157N | U | NHPP | BRO | 2017 | 170000 | 170000 | NO |  |  |  | 0
[6 empty] | HOPKINS | 2-1084 | KY 1069 | 0.04 | 2.355 | 2.395 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 1069 OVER OTTER CREEK AT INTERSECTION OF J D BUCHANAN RD (CR 1093)(SR 43.9)054B00157N | C | NHPP | BRO | 2017 | 450000 | 450000 | NO |  |  |  | 0
[6 empty] | JACKSON | 11-1090 | US 421 | 0.04 | 13.919 | 13.959 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON US 421 OVER PIGEON ROOST CREEK AT INTERSECTION WITH WATER STREET E(CS 1006)(SR 43.9)(AR/W) 055B00157N | C | NHPP | BRO | 2017 | 750000 | 750000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-21 | I 265 | 0.3 | 25.3 | 25.6 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | SNYDER FREEWAY; RECONSTRUCT 2 RAMPS AT I-265/I-64 INTERCHANGE EAST OF LOUISVILLE. (DESIGNED WITH 5-41.00)(2006BOPP)(12CCR) | R | NHPP | IM | 2017 | 4210000 | 4210000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-21 | I 265 | 0.3 | 25.3 | 25.6 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | SNYDER FREEWAY; RECONSTRUCT 2 RAMPS AT I-265/I-64 INTERCHANGE EAST OF LOUISVILLE. (DESIGNED WITH 5-41.00)(2006BOPP)(12CCR) | U | NHPP | IM | 2017 | 3380000 | 3380000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-21 | I 265 | 0.3 | 25.3 | 25.6 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | SNYDER FREEWAY; RECONSTRUCT 2 RAMPS AT I-265/I-64 INTERCHANGE EAST OF LOUISVILLE. (DESIGNED WITH 5-41.00)(2006BOPP)(12CCR) | C | NHPP | IM | 2019 | 24000000 | 24000000 | YES |  |  |  | 0
[6 empty] | JEFFERSON | 5-21.01 | I 265 | 0.3 | 25.3 | 25.6 | ECONOMIC DEVELOPMENT | PREFINANCD CONVRSN(O) | SNYDER FREEWAY; RECONSTRUCT 2 RAMPS AT I-265/I-64 INTERCHANGE EAST OF LOUISVILLE. (DESIGNED WITH 5-41.00)(ADDITIONAL FUNDS FOR C PHASE)(12CCR) | C | NHPP | IM | 2020 | 10000000 | 10000000 | YES |  |  |  | 0
[6 empty] | JEFFERSON | 5-63 | I 64 | 0.3 | 0 | 0.316 | SAFETY | BRIDGE INSPECTION(P) | I-64 BRIDGE (SHERMAN MINTON) OVER OHIO RIVER @ LOUISVILLE (B279); JOINT PROJECT WITH INDIANA TO PERFORM IN-DEPTH INSPECTION. (056B00279N) | C | NHPP | IM | 2017 | 160000 | 160000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-91.02 | CS 1001B | 1.5 | 1.6 | 2.925 | RELIABILITY | MAJOR WIDENING(O) | WIDEN FROM 2 TO 4 LANES FROM BEARGRASS CREEK TO ZORN AVENUE. (LOU T.I.P.) (KYTC MATCH) (SEE 5-91.07 FOR ADDITIONAL 'KYD' FUNDING FOR R PHASE.) (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | C | SLO | SLO | 2017 | 11500000 | 9200000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-159 | I 64 | 0.5 | 0.232 | 0.779 | RELIABILITY | RECONSTRUCTION(O) | WIDEN I-64 WESTBOUND RAMP TO I-264 WESTBOUND FROM ONE TO TWO LANES FOR ENTIRE LENGTH AND OTHER NEEDED IMPROVEMENTS TO ADDRESS WEAVE ISSUES AT MERGE ON I-264. (2006BOPP)(12CCR) | R | NHPP | NH | 2017 | 9430000 | 9430000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-159 | I 64 | 0.5 | 0.232 | 0.779 | RELIABILITY | RECONSTRUCTION(O) | WIDEN I-64 WESTBOUND RAMP TO I-264 WESTBOUND FROM ONE TO TWO LANES FOR ENTIRE LENGTH AND OTHER NEEDED IMPROVEMENTS TO ADDRESS WEAVE ISSUES AT MERGE ON I-264. (2006BOPP)(12CCR) | U | NHPP | NH | 2017 | 2350000 | 2350000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-159 | I 64 | 0.5 | 0.232 | 0.779 | RELIABILITY | RECONSTRUCTION(O) | WIDEN I-64 WESTBOUND RAMP TO I-264 WESTBOUND FROM ONE TO TWO LANES FOR ENTIRE LENGTH AND OTHER NEEDED IMPROVEMENTS TO ADDRESS WEAVE ISSUES AT MERGE ON I-264. (2006BOPP)(12CCR) | C | NHPP | NH | 2018 | 9680000 | 9680000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-205 | I 65 | 0.621 | 0 | 0.621 | SAFETY | SAFETY(P) | RECONSTRUCT SECOND CURVE ONLY ON I-65 SOUTHBOUND RAMP AT KY-1065 (OUTER LOOP).(SEE 5-205.01 FOR BREAKOUT IMPROVEMENTS) | C | NHPP | IM | 2017 | 1820000 | 1820000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-247.1 | KY 1450 | 1.6 | 1.873 | 3.542 | RELIABILITY | MAJOR WIDENING(O) | WIDEN BLUE LICK ROAD FROM SNYDER FREEWAY NORTH TO KY-61 (LOU T.I.P.) (SECTION 2) (RU-04DEOB)(08CCR)(12CCR)(16CCR) | C | STP | STP | 2017 | 10960000 | 10960000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-353 | CR 1006C | 0.85 | 0.457 | 1.232 | RELIABILITY | MINOR WIDENING(O) | ENGLISH STATION ROAD IN LOUISVILLE; WIDEN TO 3 LANES FROM AVOCA ROAD TO WEST AIKEN ROAD.(FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | C | SLO | SLO | 2017 | 4060000 | 3248000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-371.1 | KY 22 | 0.4 | 1.432 | 1.789 | SAFETY | SAFETY(P) | RECONSTRUCT KY-22 AT SPRINGCREST DRIVE. (06CCN) (2004BOPC)(14CCR)(EMERGENCY CULVERT REPLACEMENT AWARDED UNDER 5-371.12) | C | STP | STP | 2017 | 1000000 | 1000000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-371.13 | KY 22 | 0.4 | 2.537 | 2.937 | SAFETY | SAFETY(P) | RECONSTRUCT KY-22 AT GOOSE CREEK ROAD. (06CCN) (2004BOPC)(14CCR) | C | STP | STP | 2017 | 1320000 | 1320000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-378.1 | I 65 | 0.1 | 0 | 0.155 | RELIABILITY | RECONSTRUCTION(O) | EXTEND/RECONSTRUCT I-65 SB RAMP TO BROOK STREET (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C | SLO | SLO | 2017 | 2110000 | 1688000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-404.01 |  | 2.7 |  |  | RELIABILITY | NEW ROUTE(O) | EXTEND COOPER CHAPEL ROAD FROM BEULAH CHURCH ROAD TO BARDSTOWN ROAD (LOU T.I.P.) (ALL WORK BY LOUISVILLE METRO) (LOCALMATCH)(2004BOPC) (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | R | SLO | SLO | 2017 | 3750000 | 3000000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-413 | US 150 | 0.1 | 0.9 | 1.18 | SAFETY | SAFETY(P) | ALIGN INTERSECTION OF BROADWAY AND 18TH STREET BY MOVING THE SOUTH LEG OF 18TH STREET TO THE EAST (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | U | SLO | SLO | 2017 | 90000 | 72000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-413 | US 150 | 0.1 | 0.9 | 1.18 | SAFETY | SAFETY(P) | ALIGN INTERSECTION OF BROADWAY AND 18TH STREET BY MOVING THE SOUTH LEG OF 18TH STREET TO THE EAST (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C | SLO | SLO | 2017 | 760000 | 608000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-437.01 | KY 907 | 0.7 | 6.31 | 7.036 | RELIABILITY | MAJOR WIDENING(O) | WIDEN SOUTHSIDE DRIVE (KY-907) TO 5 LANES FROM NEW CUT ROAD TO NATIONAL TURNPIKE. (2004BOPC) (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | D | SLO | SLO | 2017 | 1000000 | 800000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-437.01 | KY 907 | 0.7 | 6.31 | 7.036 | RELIABILITY | MAJOR WIDENING(O) | WIDEN SOUTHSIDE DRIVE (KY-907) TO 5 LANES FROM NEW CUT ROAD TO NATIONAL TURNPIKE. (2004BOPC) (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | R | SLO | SLO | 2017 | 1000000 | 800000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-437.01 | KY 907 | 0.7 | 6.31 | 7.036 | RELIABILITY | MAJOR WIDENING(O) | WIDEN SOUTHSIDE DRIVE (KY-907) TO 5 LANES FROM NEW CUT ROAD TO NATIONAL TURNPIKE. (2004BOPC) (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | U | SLO | SLO | 2017 | 1000000 | 800000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-437.01 | KY 907 | 0.7 | 6.31 | 7.036 | RELIABILITY | MAJOR WIDENING(O) | WIDEN SOUTHSIDE DRIVE (KY-907) TO 5 LANES FROM NEW CUT ROAD TO NATIONAL TURNPIKE. (2004BOPC) (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | C | SLO | SLO | 2018 | 4000000 | 3200000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-439.03 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | REHABILITATION AND CONSTRUCTION OF VARIOUS SIDEWALK PROJECTS IN LOUISVILLE METRO. (2006BOPC) (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | C | SLO | SLO | 2017 | 100000 | 80000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-439.04 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | REHABILITATION AND CONSTRUCTION OF VARIOUS SIDEWALK PROJECTS IN LOUISVILLE METRO. (2006BOPC) (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | C | SLO | SLO | 2017 | 100000 | 80000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-439.05 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | REHABILITATION AND CONSTRUCTION OF VARIOUS SIDEWALK PROJECTS IN LOUISVILLE METRO. (2006BOPC) (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | C | SLO | SLO | 2018 | 100000 | 80000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-440.01 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | INSTALLATION OF SIDEWALKS TO FIX GAPS IN PEDESTRIAN NETWORK ON VARIOUS STATE MAINTAINED ROADS IN THE LOUISVILLE URBANIZED AREA. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | C | SLO | SLO | 2017 | 40000 | 32000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-440.02 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | INSTALLATION OF SIDEWALKS TO FIX GAPS IN PEDESTRIAN NETWORK ON VARIOUS STATE MAINTAINED ROADS IN THE LOUISVILLE URBANIZED AREA. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | C | SLO | SLO | 2017 | 40000 | 32000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-442 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | SENECA PARK LOOP EXTENSIONS (EAST AND WEST). (LOCAL MATCH)(ALL WORK BY LOUISVILLE METRO)(2004BOPC) (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | C | SLO | SLO | 2017 | 320000 | 256000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-442.02 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | SENECA PARK LOOP EXTENSIONS (EAST AND WEST). (LOCAL MATCH)(ALL WORK BY LOUISVILLE METRO)(2004BOPC) (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | C | SLO | SLO | 2017 | 650000 | 520000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-443.1 | KY 2053 | 0.3 | 0 | 0.343 | RELIABILITY | RECONSTRUCTION(O) | MT. WASHINGTON ROAD (KY-2053) SECTION 1; FROM PRESTON TO MAPLE WAY. (KYTC MATCH)(2004BOPC)(FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | D | SLO | SLO | 2017 | 320000 | 256000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-443.1 | KY 2053 | 0.3 | 0 | 0.343 | RELIABILITY | RECONSTRUCTION(O) | MT. WASHINGTON ROAD (KY-2053) SECTION 1; FROM PRESTON TO MAPLE WAY. (KYTC MATCH)(2004BOPC)(FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | R | SLO | SLO | 2017 | 490000 | 392000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-443.1 | KY 2053 | 0.3 | 0 | 0.343 | RELIABILITY | RECONSTRUCTION(O) | MT. WASHINGTON ROAD (KY-2053) SECTION 1; FROM PRESTON TO MAPLE WAY. (KYTC MATCH)(2004BOPC)(FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | U | SLO | SLO | 2017 | 120000 | 96000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-443.2 | KY 2053 | 2.46 | 0.343 | 2.804 | RELIABILITY | RECONSTRUCTION(O) | MT. WASHINGTON ROAD (KY-2053) SECTION 2; FROM MAPLE WAY TO CEDAR CREEK RD. (KYTC MATCH)(2004BOPC)(FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | D | SLO | SLO | 2017 | 290000 | 232000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-470.1 | CS 1049F |  | 0.047 | 0.58 | RELIABILITY | RECONSTRUCTION(O) | CONVERSION OF ONE-WAY STREETS IN DOWNTOWN LOUISVILLE TO TWO-WAY TRAFFIC (8TH, 7TH, SHELBY, CAMPBELL STREETS). PHASE 2 | C | SLO | SLO | 2017 | 748000 | 598400 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-474 | I 265 | 0.82 | 28.28 | 29.1 | SAFETY | SAFETY(P) | REDUCE CONGESTION AND IMPROVE SAFETY AT THE KY 3084 (OLD HENRY ROAD) INTERCHANGE. (12CCR) | C | NHPP | IM | 2017 | 5090000 | 5090000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-478.4 | US 31 |  | 9.749 | 11.69 | SAFETY | SAFETY(P) | IMPROVE SAFETY ON DIXIE HIGHWAY BY PLACING BARRIER WALLS FOR 2 MILES TO ELIMINATE CROSSOVER ACCIDENTS BETWEEN GREENWOOD ROAD (KY 1931) AND STONESTREET ROAD (CR 1003). (16CCN) | C | HSIP | SAF | 2017 | 500000 | 500000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-483 | I 71 | 3.6 | 9.1 | 11.315 | RELIABILITY | MAJOR WIDENING(O) | SIX LANE PRIORITY SECTION OF I-71 BETWEEN I-265 AND KY 329.(16CCR) | R | NHPP | NH | 2018 | 1000000 | 1000000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-483 | I 71 | 3.6 | 9.1 | 11.315 | RELIABILITY | MAJOR WIDENING(O) | SIX LANE PRIORITY SECTION OF I-71 BETWEEN I-265 AND KY 329.(16CCR) | U | NHPP | NH | 2019 | 500000 | 500000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-483 | I 71 | 3.6 | 9.1 | 11.315 | RELIABILITY | MAJOR WIDENING(O) | SIX LANE PRIORITY SECTION OF I-71 BETWEEN I-265 AND KY 329.(16CCR) | C | NHPP | NH | 2020 | 45000000 | 45000000 | YES |  |  |  | 0
[6 empty] | JEFFERSON | 5-484 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | CONSTRUCT A 2800' LONG, 10' WIDE MULTIUSE PATH THROUGH A.B. SAWYER PARK AND CONNECTING TO SURROUNDING NEIGHBORHOODS INCLUDES AN UNDERPASS, BRIDGE, AND SITE AMENITIES. | D | SLO | SLO | 2017 | 170000 | 136000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-484 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | CONSTRUCT A 2800' LONG, 10' WIDE MULTIUSE PATH THROUGH A.B. SAWYER PARK AND CONNECTING TO SURROUNDING NEIGHBORHOODS INCLUDES AN UNDERPASS, BRIDGE, AND SITE AMENITIES. | C | SLO | SLO | 2017 | 700000 | 560000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-485 | US 60A | 2.793 | 4.038 | 6.831 | RELIABILITY | PAVEMENT REHAB-PRI(P) | RE-CURB US 60A (EASTERN PARKWAY) FROM KY 1631 (CRITTENDEN DRIVE) TO US 31E (BARDSTOWN ROAD). | P | SLO | SLO | 2017 | 200000 | 160000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-485 | US 60A | 2.793 | 4.038 | 6.831 | RELIABILITY | PAVEMENT REHAB-PRI(P) | RE-CURB US 60A (EASTERN PARKWAY) FROM KY 1631 (CRITTENDEN DRIVE) TO US 31E (BARDSTOWN ROAD). | D | SLO | SLO | 2017 | 400000 | 320000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-485 | US 60A | 2.793 | 4.038 | 6.831 | RELIABILITY | PAVEMENT REHAB-PRI(P) | RE-CURB US 60A (EASTERN PARKWAY) FROM KY 1631 (CRITTENDEN DRIVE) TO US 31E (BARDSTOWN ROAD). | C | SLO | SLO | 2017 | 3800000 | 3040000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-486 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | GOOD SAMARITAN BICYCLE/PEDESTRIAN TRAIL CONNECTOR:CONSTRUCT A MULTI-USE BICYCLE & PEDESTRIAN TRAIL ALONG OLD TAYLORSVILLE ROAD & JEFFERSON ST IN DOWNTOWN JEFFERSONTOWN CONNECTING THE DOWNTOWN ST NETWORK TO THE GOOD SAMARITAN CENTER & BICYCLE/PED TRAIL. | C | SLO | SLO | 2017 | 162000 | 129600 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-487 |  |  |  |  | RELIABILITY | SCOPING STUDY(O) | PRELIMINARY DESIGN & SCOPING STUDY TO DETERMINE LOCATION OF A MULTI-USE BICYCLE & PEDESTRIAN TRAIL PROJECT ALONG TAYLORSVILLE ROAD FROM DOWNTOWN JEFFERSONTOWN TO 21ST CENTURY PARK. | P | SLO | SLO | 2017 | 189000 | 151200 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-489 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | DESIGN & CONSTRUCT SHARED USE PATH & LOUISVILLE LOOP TRAILHEAD FACILITIES THRU JEFFERSON MEMORIAL FOREST FROM NORTH END OF SAND QUARRY TUNNEL AT GENE SNYDER FWY TO WEST TERMINUS OF EXISTING MSD TRAIL APPROX. 2.7 MI WHICH WILL INCLUDE BRIDGE OVER POND CR. | D | SLO | SLO | 2017 | 333600 | 266880 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-490 |  | 2.5 |  |  | SAFETY | BIKE/PED FACIL(O) | DESIGN & CONSTRUCT SHARED USE PATH & LOUISVILLE LOOP TRAILHEAD FACILITIES THRU JEFFERSON MEMORIAL FOREST FROM BLEVINS GAP ROAD TO NORTH END OF SAND QUARRY TUNNEL AT GENE SNYDER FWY(THE TUNNEL WILL BE PART OF THIS SEGMENT) APPROX. 2.5 MILES. | D | SLO | SLO | 2017 | 210500 | 168400 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-491 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | DESIGN AND CONSTRUCT SHARED USE PATH AND LOUISVILLE LOOP TRAILHEAD FACILITIES THROUGH JEFFERSON MEMORIAL FOREST FROM PENDLETON RD AT MEDORA RD TO THE BEGINNING OF JEFFERSON MEMORIAL FOREST PROPERTY ON BLEVINS GAP RD APPROX. 1.3 MILES. | D | SLO | SLO | 2017 | 144240 | 115392 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-492 | CS 3596 |  | 0.494 | 1.005 | RELIABILITY | RECONSTRUCTION(O) | MIDDLETOWN STREETSCAPE PHASE VI. ROADWAY AND STREETSCAPE IMPROVEMENTS ON OLD SHELBYVILLE RD FROM EVERGREEN RD TO US 60 (SHELBYVILLE RD). | C | SLO | SLO | 2017 | 254000 | 203200 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-493 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | MISCELLANEOUS SIDEWALKS AND HANDICAP RAMPS: CONSTRUCT AND REPLACE VARIOUS SIDEWALKS AND HANDICAP RAMPS THROUGHOUT THE CITY ON A REOCCURRING ANNUAL BASIS. | C | SLO | SLO | 2017 | 37800 | 30240 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-495 | KY 1020 |  | 7.837 | 9.15 | SAFETY | BIKE/PED FACIL(O) | OLMSTED PARKWAYS MULTI-USE PATH SYSTEM-SOUTHERN PKWY: CONSTRUCTION OF A 2.5 MILE SHARED USE PATH SYSTEM ALONG SOUTHERN PARKWAY BETWEEN SOUTH 3RD AND NEW CUT ROAD. | C | SLO | SLO | 2017 | 1000000 | 800000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-496 | KY 2054 |  | 0.72 | 1.22 | SAFETY | BIKE/PED FACIL(O) | CONSTRUCTION OF A 0.5 MILE SHARED USE PATH SYSTEM ALONG ALGONQUIN PARKWAY BETWEEN WILSON AVENUE AND CYPRESS STREET. | C | SLO | SLO | 2017 | 1000000 | 800000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-497 | KY 2054 |  | 1.22 | 1.64 | SAFETY | BIKE/PED FACIL(O) | CONSTRUCTION OF A 0.45 MILE SHARED USE PATH SYSTEM ALONG ALGONQUIN PARKWAY BETWEEN CYPRESS STREET AND DIXIE HWY. | C | SLO | SLO | 2017 | 1000000 | 800000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-498 | KY 2054 |  | 1.64 | 2.717 | SAFETY | BIKE/PED FACIL(O) | CONSTRUCTION OF A 1.2 MILE SHARED USE PATH SYSTEM ALONG ALGONQUIN PARKWAY BETWEEN DIXIE HIGHWAY AND SHARP AVE. | C | SLO | SLO | 2017 | 1000000 | 800000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-499 | CR 1001B |  | 0 | 6.761 | SAFETY | BIKE/PED FACIL(O) | RIVER ROAD BICYCLE AND PEDESTRIAN IMPROVEMENTS FROM DOWNTOWN LOUISVILLE TO THE CITY OF PROSPECT (US 42), 8.5 MILES. (SEE 5-3036.00) | D | SLO | SLO | 2017 | 200000 | 160000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-499 | CR 1001B |  | 0 | 6.761 | SAFETY | BIKE/PED FACIL(O) | RIVER ROAD BICYCLE AND PEDESTRIAN IMPROVEMENTS FROM DOWNTOWN LOUISVILLE TO THE CITY OF PROSPECT (US 42), 8.5 MILES. (SEE 5-3036.00) | C | SLO | SLO | 2017 | 2043030 | 1634424 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-513 |  |  |  |  | SAFETY | MATCHED FED FUNDS(O) | CONSTRUCT SHARED USE PATH FROM NEIGHBORHOOD SIDEWALK TO REAR OF SCHOOL PROPERTY, AND PROVIDE OUTDOOR CLASSROOM AMENITIES ALONG SHARED USE PATH. PROJECT WILL INCLUDE WETLAND RESTORATION ON SCHOOL SITE.(FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | D | SLO | SLO | 2017 | 12500 | 10000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-513 |  |  |  |  | SAFETY | MATCHED FED FUNDS(O) | CONSTRUCT SHARED USE PATH FROM NEIGHBORHOOD SIDEWALK TO REAR OF SCHOOL PROPERTY, AND PROVIDE OUTDOOR CLASSROOM AMENITIES ALONG SHARED USE PATH. PROJECT WILL INCLUDE WETLAND RESTORATION ON SCHOOL SITE.(FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C | SLO | SLO | 2017 | 70000 | 56000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-516.02 |  |  |  |  | SAFETY | SAFETY(P) | VARIOUS SAFETY PROJECTS IN THE LOUISVILLE URBANIZED AREA. | C | SLO | SLO | 2017 | 1000000 | 800000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-516.03 |  |  |  |  | SAFETY | SAFETY(P) | VARIOUS SAFETY PROJECTS IN THE LOUISVILLE URBANIZED AREA. | C | SLO | SLO | 2017 | 1000000 | 800000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-518 | CR 1004H | 0.151 | 3.179 | 3.33 | RELIABILITY | MINOR WIDENING(O) | WIDEN WATTERSON TRAIL FROM 2 TO 3 LANES FROM RUCKRIEGEL PARKWAY (CS-2056H) TO MAPLE ROAD (CS-1132H) AND FROM OLD TAYLORSVILLE ROAD (CS-1119H) TO RUCKRIEGEL PARKWAY (KY 1819). PROJECT TO INCLUDE STREETSCAPE ENHANCEMENTS. | U | SLO | SLO | 2017 | 194169 | 155335.2 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-518 | CR 1004H | 0.151 | 3.179 | 3.33 | RELIABILITY | MINOR WIDENING(O) | WIDEN WATTERSON TRAIL FROM 2 TO 3 LANES FROM RUCKRIEGEL PARKWAY (CS-2056H) TO MAPLE ROAD (CS-1132H) AND FROM OLD TAYLORSVILLE ROAD (CS-1119H) TO RUCKRIEGEL PARKWAY (KY 1819). PROJECT TO INCLUDE STREETSCAPE ENHANCEMENTS. | C | SLO | SLO | 2017 | 509788 | 407830.4 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-519 | CR 1004H | 0.831 | 1.857 | 2.688 | SAFETY | BIKE/PED FACIL(O) | CONSTRUCT A MULTI-USE BICYCLE AND PEDESTRIAN TRAIL ALONG WATTERSON TRAIL FROM MULBERRY ROW WAY TO MANSFIELD ESTATES DRIVE. | C | SLO | SLO | 2017 | 656640 | 525312 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-521 | I 64 |  | 1.387 | 1.891 | RELIABILITY | BRIDGE REHAB(P) | REPAIR DRAINAGE SYSTEM ON THE I-64 BRIDGE OVER N.S. RAILROAD AND THE LEVEE AND REPAIR THE LEVEE.(056B00284N)(2014BOP) | C | NHPP | IM | 2017 | 400000 | 400000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-522 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | "SHARED USE PATH" LOUISVILLE LOOP TRAILHEAD FACILITIES THROUGH JEFFERSON MEMORIAL FOREST FROM NORTH END OF SAND QUARRY TUNNEL AT GENE SNYDER FWY TO WEST TERMINUS OF THE EXISTING MSD TRAIL APPROX 2.7 MI WHICH WILL INCLUDE A BRIDGE OVER POND CREEK. 2012BOP | D | SLO | SLO | 2017 | 333600 | 266880 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-531 | KY 1932 |  | 5.523 | 6.59 | RELIABILITY | MATCHED FED FUNDS(O) | IMPROVE THE SAFETY AND CONGESTION OF KY 1932 (CHENOWETH LANE) FROM US 60 (SHELBYVILLE ROAD) TO US 42 (BROWNSBORO ROAD) APPROXIMATELY 1.07 MILES (2014BOP). | D | SLO | SLO | 2017 | 1250000 | 1000000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-531 | KY 1932 |  | 5.523 | 6.59 | RELIABILITY | MATCHED FED FUNDS(O) | IMPROVE THE SAFETY AND CONGESTION OF KY 1932 (CHENOWETH LANE) FROM US 60 (SHELBYVILLE ROAD) TO US 42 (BROWNSBORO ROAD) APPROXIMATELY 1.07 MILES (2014BOP). | R | SLO | SLO | 2017 | 1766400 | 1413120 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-531 | KY 1932 |  | 5.523 | 6.59 | RELIABILITY | MATCHED FED FUNDS(O) | IMPROVE THE SAFETY AND CONGESTION OF KY 1932 (CHENOWETH LANE) FROM US 60 (SHELBYVILLE ROAD) TO US 42 (BROWNSBORO ROAD) APPROXIMATELY 1.07 MILES (2014BOP). | U | SLO | SLO | 2018 | 2000000 | 1600000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-536 | KY 1931 |  | 3.148 | 4.887 | RELIABILITY | MINOR WIDENING(O) | WIDEN KY 1931 FROM 2 TO 3 LANES FROM US 31W (DIXIE HWY) TO DOSS HIGH SCHOOL. (2014BOP) | R | SLO | SLO | 2018 | 3000000 | 2400000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-537 | I 265 | 3 | 23.409 | 34.727 | RELIABILITY | MAJOR WIDENING(O) | SIX LANE PRIORITY SECTION OF I-265 BETWEEN TAYLORSVILLE ROAD AND I-71. | D | NHPP | NH | 2017 | 2500000 | 2500000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-537 | I 265 | 3 | 23.409 | 34.727 | RELIABILITY | MAJOR WIDENING(O) | SIX LANE PRIORITY SECTION OF I-265 BETWEEN TAYLORSVILLE ROAD AND I-71. | R | NHPP | NH | 2018 | 2000000 | 2000000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-537 | I 265 | 3 | 23.409 | 34.727 | RELIABILITY | MAJOR WIDENING(O) | SIX LANE PRIORITY SECTION OF I-265 BETWEEN TAYLORSVILLE ROAD AND I-71. | U | NHPP | NH | 2020 | 2000000 | 2000000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-539 | I 71 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | PROVIDE COLLECTOR-DISTRIBUTOR LANE ON SOUTHBOUND I-71 TO FACILITATE RAMP MOVEMENTS TO AND FROM I-265. | C | NHPP | IM | 2017 | 5000000 | 5000000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-715.41 |  |  |  |  | RELIABILITY | I-CHANGE RECONST(O) | LOUISVILLE BRIDGES; KENTUCKY TRADITIONAL NH FUNDING FOR FY 2017 PLEDGED TO SUPPORT THE FINANCING OF THE LSIORB (CANNOT BE MOVED)(14CCR) | C | NHPP | NH | 2017 | 50000000 | 50000000 | YES |  |  |  | 0
[6 empty] | JEFFERSON | 5-804 | I 264 | 1.7 | 20.9 | 22.6 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT/WIDEN I-264 (WATTERSON EXPRESSWAY) FROM WESTPORT ROAD (KY 1447) TO I-71, INCLUDING THE US-42 INTERCHANGE AS A SPUI.(PROJECT INCLUDES 5-594) (12CCR)(14CCR) | D | NHPP | IM | 2017 | 3000000 | 3000000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-804 | I 264 | 1.7 | 20.9 | 22.6 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT/WIDEN I-264 (WATTERSON EXPRESSWAY) FROM WESTPORT ROAD (KY 1447) TO I-71, INCLUDING THE US-42 INTERCHANGE AS A SPUI.(PROJECT INCLUDES 5-594) (12CCR)(14CCR) | R | NHPP | NH | 2019 | 5020000 | 5020000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-804 | I 264 | 1.7 | 20.9 | 22.6 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT/WIDEN I-264 (WATTERSON EXPRESSWAY) FROM WESTPORT ROAD (KY 1447) TO I-71, INCLUDING THE US-42 INTERCHANGE AS A SPUI.(PROJECT INCLUDES 5-594) (12CCR)(14CCR) | U | NHPP | NH | 2019 | 710000 | 710000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-804 | I 264 | 1.7 | 20.9 | 22.6 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT/WIDEN I-264 (WATTERSON EXPRESSWAY) FROM WESTPORT ROAD (KY 1447) TO I-71, INCLUDING THE US-42 INTERCHANGE AS A SPUI.(PROJECT INCLUDES 5-594) (12CCR)(14CCR) | C | NHPP | NH | 2020 | 24170000 | 24170000 | YES |  |  |  | 0
[6 empty] | JEFFERSON | 5-965.14 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | DEDICATED FEDERAL AID STP FUNDS EARMARKED FOR LOUISVILLE URBANIZED AREA AND SUBJECT TO MPO CONTROL FOR FY 2016 (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | C | SLO | SLO | 2017 | 48700000 | 38960000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-965.15 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | DEDICATED FEDERAL AID STP FUNDS EARMARKED FOR LOUISVILLE URBANIZED AREA AND SUBJECT TO MPO CONTROL FOR FY 2017 (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C | SLO | SLO | 2017 | 5800000 | 4640000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-965.16 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | DEDICATED FEDERAL AID STP FUNDS EARMARKED FOR LOUISVILLE URBANIZED AREA AND SUBJECT TO MPO CONTROL FOR FY 2018 (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C | SLO | SLO | 2018 | 7700000 | 6160000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-965.17 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | DEDICATED FEDERAL AID STP FUNDS EARMARKED FOR LOUISVILLE URBANIZED AREA AND SUBJECT TO MPO CONTROL FOR FY 2019. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | C | SLO | SLO | 2019 | 23000000 | 18400000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-965.18 |  |  |  |  | RELIABILITY | MATCHED FED FUNDS(O) | DEDICATED FEDERAL AID STP FUNDS EARMARKED FOR LOUISVILLE URBANIZED AREA AND SUBJECT TO MPO CONTROL FOR FY 2020. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | C | SLO | SLO | 2020 | 23500000 | 18800000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-1061 | CR 1038L | 0.06 | 0 | 0.06 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON CR-1038L OVER BEE LICK CREEK; (STRUCTURALLY DEFICIENT, SR=4) 056C00104N | C | STP | BRZ | 2017 | 330000 | 330000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-1064 | US 60A |  | 5.698 | 5.738 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON EASTERN PARKWAY (US 60A) OVER SOUTH FORK BEARGRASS CREEK 0.2 MILE NE OF POPLAR LEVEL RD (KY 864)(SR 9.5) 056B00139N | R | NHPP | BRO | 2017 | 100000 | 100000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-1064 | US 60A |  | 5.698 | 5.738 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON EASTERN PARKWAY (US 60A) OVER SOUTH FORK BEARGRASS CREEK 0.2 MILE NE OF POPLAR LEVEL RD (KY 864)(SR 9.5) 056B00139N | C | NHPP | BRO | 2018 | 800000 | 800000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-1067 | US 150 | 0.04 | 3.6 | 3.64 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON E BROADWAY (US 150) OVER SOUTH FORK BEARGRASS CREEK AT INTERSECTION WITH BRENT STREET (CS 1312G)(SR 38) 056B00348N | R | NHPP | BRO | 2017 | 120000 | 120000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-1067 | US 150 | 0.04 | 3.6 | 3.64 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON E BROADWAY (US 150) OVER SOUTH FORK BEARGRASS CREEK AT INTERSECTION WITH BRENT STREET (CS 1312G)(SR 38) 056B00348N | U | NHPP | BRO | 2017 | 220000 | 220000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-1067 | US 150 | 0.04 | 3.6 | 3.64 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON E BROADWAY (US 150) OVER SOUTH FORK BEARGRASS CREEK AT INTERSECTION WITH BRENT STREET (CS 1312G)(SR 38) 056B00348N | C | NHPP | BRO | 2017 | 850000 | 850000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-1068 | CR 1004N |  | 0.737 | 0.777 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON FAIRMOUNT RD (CR 1004N) OVER CEDAR CREEK 0.2 MILE W OF FARMERS WAY (PR 1021N)(SR 41) 056C00054N | R | STP | BRZ | 2017 | 100000 | 100000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-1068 | CR 1004N |  | 0.737 | 0.777 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON FAIRMOUNT RD (CR 1004N) OVER CEDAR CREEK 0.2 MILE W OF FARMERS WAY (PR 1021N)(SR 41) 056C00054N | U | STP | BRZ | 2017 | 50000 | 50000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-1068 | CR 1004N |  | 0.737 | 0.777 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON FAIRMOUNT RD (CR 1004N) OVER CEDAR CREEK 0.2 MILE W OF FARMERS WAY (PR 1021N)(SR 41) 056C00054N | C | STP | BRZ | 2017 | 500000 | 500000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-1070 | CS 1017G | 0.04 | 1.293 | 1.333 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON E KENTUCKY ST (CS 1017G) OVER SOUTH FORK BEARGRASS CREEK 0.01 MILE E OF SCHILLER AVE (CS 1138G)(SR 48.8) 056C00083N | R | STP | BRZ | 2017 | 10000 | 10000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-1070 | CS 1017G | 0.04 | 1.293 | 1.333 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON E KENTUCKY ST (CS 1017G) OVER SOUTH FORK BEARGRASS CREEK 0.01 MILE E OF SCHILLER AVE (CS 1138G)(SR 48.8) 056C00083N | U | STP | BRZ | 2017 | 100000 | 100000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-1070 | CS 1017G | 0.04 | 1.293 | 1.333 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON E KENTUCKY ST (CS 1017G) OVER SOUTH FORK BEARGRASS CREEK 0.01 MILE E OF SCHILLER AVE (CS 1138G)(SR 48.8) 056C00083N | C | STP | BRZ | 2019 | 600000 | 600000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-1077 | CR 1001G | 0.02 | 2.48 | 2.5 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER NORTHERN DITCH ON GRADE LANE (CR 1001G) 0.34 MI S OF KY 1747 (FERN VALLEY ROAD) (056C00064N)(SR=25.4) | D | STP | BRZ | 2017 | 350000 | 350000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-1077 | CR 1001G | 0.02 | 2.48 | 2.5 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER NORTHERN DITCH ON GRADE LANE (CR 1001G) 0.34 MI S OF KY 1747 (FERN VALLEY ROAD) (056C00064N)(SR=25.4) | R | STP | BRZ | 2019 | 20000 | 20000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-1077 | CR 1001G | 0.02 | 2.48 | 2.5 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER NORTHERN DITCH ON GRADE LANE (CR 1001G) 0.34 MI S OF KY 1747 (FERN VALLEY ROAD) (056C00064N)(SR=25.4) | U | STP | BRZ | 2019 | 50000 | 50000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-1077 | CR 1001G | 0.02 | 2.48 | 2.5 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER NORTHERN DITCH ON GRADE LANE (CR 1001G) 0.34 MI S OF KY 1747 (FERN VALLEY ROAD) (056C00064N)(SR=25.4) | C | STP | BRZ | 2020 | 850000 | 850000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-1079 | CR 1001B | 0.07 | 3.8 | 3.87 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER GOOSE CREEK ON RIVER ROAD (CR 1001B) 0.2 MI N OF LIME KILN ROAD (CR 1002B) (056C00130N)(SR=26.5) | D | STP | BRZ | 2019 | 450000 | 450000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-8405 | I 264 | 0.1 | 8.08 | 8.18 | RELIABILITY | NEW INTERCHANGE(O) | INTERCHANGE AT MANSLICK ROAD (KY-1931) AND I-264. (08CCN)(10CCR)(12CCR)(14CCR)(16CCR) | R | NHPP | NH | 2019 | 4000000 | 4000000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-8405 | I 264 | 0.1 | 8.08 | 8.18 | RELIABILITY | NEW INTERCHANGE(O) | INTERCHANGE AT MANSLICK ROAD (KY-1931) AND I-264. (08CCN)(10CCR)(12CCR)(14CCR)(16CCR) | U | NHPP | NH | 2020 | 1800000 | 1800000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-8412 |  |  |  |  | SAFETY | SAFETY-RR PROTECTN(P) | RAILROAD SAFETY CROSSING. IMPROVE LIGHTING, ERECT SIGNALS UPGRADE AND ROADWAY CROSSINGS BETWEEN CARDINAL AND HILL STREETS. (08CCN)(12CCR) | C | HSIP | SAF | 2017 | 200000 | 200000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-8611 | KY 2053 | 1.501 | 0 | 1.501 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE AND WIDEN MT. WASHINGTON ROAD FROM PRESTON HIGHWAY TO PENN RUN CREEK BRIDGE. (10CCN)(12CCR)(SAME AS 5-8205.10) | D | STP | STP | 2019 | 630000 | 630000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-8810 | KY 1931 | 0.599 | 4.887 | 5.486 | RELIABILITY | MINOR WIDENING(O) | THREE LANE WIDENING ALONG KY-1931 FROM THE DOSS HIGH SCHOOL ENTRANCE TO PALATKA ROAD, INCLUDING INTERSECTION IMPROVEMENTS WITH PALATKA ROAD AND TURN LANES. (14CCN) | R | STP | STP | 2017 | 3130000 | 3130000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-8810 | KY 1931 | 0.599 | 4.887 | 5.486 | RELIABILITY | MINOR WIDENING(O) | THREE LANE WIDENING ALONG KY-1931 FROM THE DOSS HIGH SCHOOL ENTRANCE TO PALATKA ROAD, INCLUDING INTERSECTION IMPROVEMENTS WITH PALATKA ROAD AND TURN LANES. (14CCN) | U | STP | STP | 2017 | 1880000 | 1880000 | NO |  |  |  | 0
[6 empty] | JEFFERSON | 5-8810 | KY 1931 | 0.599 | 4.887 | 5.486 | RELIABILITY | MINOR WIDENING(O) | THREE LANE WIDENING ALONG KY-1931 FROM THE DOSS HIGH SCHOOL ENTRANCE TO PALATKA ROAD, INCLUDING INTERSECTION IMPROVEMENTS WITH PALATKA ROAD AND TURN LANES. (14CCN) | C | STP | STP | 2018 | 6080000 | 6080000 | NO |  |  |  | 0
[6 empty] | JESSAMINE | 7-87.5 |  | 2.66 |  |  | RELIABILITY | NEW ROUTE(O) | EAST NICHOLASVILLE BYPASS SECTION II; FROM KY-39, EXTENDING SOUTHWESTERLY TO US-27 SOUTH OF NICHOLASVILLE. (SEE 7-8305.00 FOR D PHASE.)(2000BOP)(12CCR)(16CCR) | C | STP | STP | 2018 | 12500000 | 12500000 | NO |  |  |  | 0
[6 empty] | JESSAMINE | 7-87.51 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | EAST NICHOLASVILLE BYPASS SECTION II; FROM KY-39, EXTENDING SOUTHWESTERLY TO US-27 SOUTH OF NICHOLASVILLE. (SEE 7-8305.00 FOR D PHASE.)(200BOP)(12CCR)(16CCN) | C | STP | STP | 2019 | 10000000 | 10000000 | NO |  |  |  | 0
[6 empty] | JESSAMINE | 7-414 | KY 1980 | 3.205 | 0 | 3.205 | SAFETY | SAFETY(P) | IMPROVE ROADWAY GEOMETRICS, TYPICAL SECTION, AND ROADWAY HAZARDS ON KY 1980 (BRANNON RD) FROM US 68 (HARRODSBURG RD) TO US 27 (NICHOLASVILLE RD)(12CCR) | R | STP | STP | 2019 | 7500000 | 7500000 | NO |  |  |  | 0
[6 empty] | JESSAMINE | 7-414 | KY 1980 | 3.205 | 0 | 3.205 | SAFETY | SAFETY(P) | IMPROVE ROADWAY GEOMETRICS, TYPICAL SECTION, AND ROADWAY HAZARDS ON KY 1980 (BRANNON RD) FROM US 68 (HARRODSBURG RD) TO US 27 (NICHOLASVILLE RD)(12CCR) | U | STP | STP | 2019 | 5000000 | 5000000 | NO |  |  |  | 0
[6 empty] | JESSAMINE | 7-915 | US 68 | 0.7 | 4.1 | 4.8 | SAFETY | SAFETY(P) | RECONSTRUCT INTERSECTION OF KY 29 NORTH OF WILMORE.(16CCR) | R | STP | STP | 2017 | 2630000 | 2630000 | NO |  |  |  | 0
[6 empty] | JESSAMINE | 7-915 | US 68 | 0.7 | 4.1 | 4.8 | SAFETY | SAFETY(P) | RECONSTRUCT INTERSECTION OF KY 29 NORTH OF WILMORE.(16CCR) | U | STP | STP | 2019 | 600000 | 600000 | NO |  |  |  | 0
[6 empty] | JESSAMINE | 7-1136 | KY 39 | 0.036 | 3.74 | 3.776 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER HICKMAN CREEK AT BLACK BRIDGE ON KY 39 1.3 MI N OF KY 1268. (057B00002N)(SR=49.5)(EBRP) | D | STP | BRX | 2019 | 350000 | 350000 | NO |  |  |  | 0
[6 empty] | JESSAMINE | 7-1136 | KY 39 | 0.036 | 3.74 | 3.776 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER HICKMAN CREEK AT BLACK BRIDGE ON KY 39 1.3 MI N OF KY 1268. (057B00002N)(SR=49.5)(EBRP) | R | STP | BRX | 2020 | 100000 | 100000 | NO |  |  |  | 0
[6 empty] | JESSAMINE | 7-1136 | KY 39 | 0.036 | 3.74 | 3.776 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER HICKMAN CREEK AT BLACK BRIDGE ON KY 39 1.3 MI N OF KY 1268. (057B00002N)(SR=49.5)(EBRP) | U | STP | BRX | 2020 | 200000 | 200000 | NO |  |  |  | 0
[6 empty] | JESSAMINE | 7-1144 | CR 1238 |  | 0.868 | 0.892 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON CR-1238 (0.88) OVER NS SYSTEM. (SR=26.3) 057R00605N | D | STP | BRZ | 2020 | 375000 | 375000 | NO |  |  |  | 0
[6 empty] | JESSAMINE | 7-8404 | US 27 |  |  |  | RELIABILITY | NEW ROUTE(O) | CONSTRUCT A NEW 4 LANE CONNECTOR BETWEEN US-27 AND I-75. (08CCN)(12CCR)(16CCR) | D | STP | STP | 2017 | 2000000 | 2000000 | NO |  |  |  | 0
[6 empty] | JESSAMINE | 7-8404 | US 27 |  |  |  | RELIABILITY | NEW ROUTE(O) | CONSTRUCT A NEW 4 LANE CONNECTOR BETWEEN US-27 AND I-75. (08CCN)(12CCR)(16CCR) | R | STP | STP | 2019 | 10000000 | 10000000 | NO |  |  |  | 0
[6 empty] | JESSAMINE | 7-8404 | US 27 |  |  |  | RELIABILITY | NEW ROUTE(O) | CONSTRUCT A NEW 4 LANE CONNECTOR BETWEEN US-27 AND I-75. (08CCN)(12CCR)(16CCR) | U | STP | STP | 2020 | 3000000 | 3000000 | NO |  |  |  | 0
[6 empty] | JESSAMINE | 7-8851 | KY 169 | 0.046 | 10.807 | 10.853 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE RAILROAD BRIDGE ON KY 169 (NORTH 3RD STREET) BETWEEN MEADOWLARK LANE & ILHARDT AVENUE.(SR=28.9)057R00603(14CCN)(16CCR) | D | NHPP | BRO | 2017 | 500000 | 500000 | NO |  |  |  | 0
[6 empty] | JESSAMINE | 7-8851 | KY 169 | 0.046 | 10.807 | 10.853 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE RAILROAD BRIDGE ON KY 169 (NORTH 3RD STREET) BETWEEN MEADOWLARK LANE & ILHARDT AVENUE.(SR=28.9)057R00603(14CCN)(16CCR) | C | NHPP | BRO | 2018 | 1500000 | 1500000 | NO |  |  |  | 0
[6 empty] | JOHNSON | 12-1114 | KY 40 |  | 0.372 | 0.412 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 40 OVER BRANCH OF LITTLE PAINT CREEK 0.38 MILE NE OF JOHNSON/MAGOFFIN COUNTY LINE (SR 12.5) 058B00012N | R | NHPP | BRO | 2017 | 400000 | 400000 | NO |  |  |  | 0
[6 empty] | JOHNSON | 12-1114 | KY 40 |  | 0.372 | 0.412 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 40 OVER BRANCH OF LITTLE PAINT CREEK 0.38 MILE NE OF JOHNSON/MAGOFFIN COUNTY LINE (SR 12.5) 058B00012N | U | NHPP | BRO | 2017 | 225000 | 225000 | NO |  |  |  | 0
[6 empty] | JOHNSON | 12-1114 | KY 40 |  | 0.372 | 0.412 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 40 OVER BRANCH OF LITTLE PAINT CREEK 0.38 MILE NE OF JOHNSON/MAGOFFIN COUNTY LINE (SR 12.5) 058B00012N | C | NHPP | BRO | 2017 | 950000 | 950000 | NO |  |  |  | 0
|  |  | TIP FY 2016-19 ADM MOD #10. CHANGED FY AND AMOUNT IN TIP ONLY. NO CHANGE TO STIP. |  |  | KENTON | 6-17.04 | I 75 |  | 191.277 | 191.777 | RELIABILITY | BRIDGE REHAB(P) | TRANSPORTATION IMPROVEMENTS TO BRENT SPENCE BRIDGE. (2005HPP-KY154): (059B00046N) (THESE FUNDS WILL BE USED BY KYTC FOR EXISTING BRIDGE MAINTENANCE,REPAIR AND PAINTING.) | C | HPP | HPP | 2017 | 16800000 | 16800000 | NO |  |  |  | 0
[6 empty] | KENTON | 6-17.05 | I 75 |  | 191.277 | 191.777 | RELIABILITY | BRIDGE REPLACEMENT(P) | KY 143 HPP EARMARK "REPLACE BRENT SPENCE BRIDGE, KENTON COUNTY, KENTUCKY". (2005HPP-KY143)(SEE 6-17.04 FOR ADDITIONAL 2005HPP FUNDING) | C | HPP | HPP | 2017 | 1600000 | 1600000 | NO |  |  |  | 0
[6 empty] | KENTON | 6-17.1 | I 75 |  |  |  | RELIABILITY | BRIDGE REHAB(P) | BRENT SPENCE BRIDGE PROJECT (ADDITIONAL PROJECT FUNDS FOR MAINTENANCE, REPAIR AND PAINTING). | C | NHPP | IM | 2018 | 13700000 | 13700000 | NO |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2016.002 | 2016-10-04 | TIP FY 2016-19 ADM MOD #10. ADDING PROJECT PER TIP MOD. NEW |  |  | KENTON | 6-162.01 | KY 536 | 4.476 | 0 | 4.476 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT KY-536 TO A 4 LANE URBAN SECTION FROM THE BOONE COUNTY LINE TO KY-17 (MP 0.0 TO MP 4.5). (00CCR)(04CCN)(06CCR)(2006BOPC)(PHASE I DESIGN SHOWN UNDER 6-162.00)(12CCR)(14CCR) | R | STP | STP | 2016 | 22050000 | 22050000 | NO |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2016.002 | 2016-10-04 | TIP FY 2016-19 ADM MOD #10. ADDING PROJECT PER TIP MOD. NEW |  |  | KENTON | 6-162.01 | KY 536 | 4.476 | 0 | 4.476 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT KY-536 TO A 4 LANE URBAN SECTION FROM THE BOONE COUNTY LINE TO KY-17 (MP 0.0 TO MP 4.5). (00CCR)(04CCN)(06CCR)(2006BOPC)(PHASE I DESIGN SHOWN UNDER 6-162.00)(12CCR)(14CCR) | U | STP | STP | 2017 | 4160000 | 4160000 | NO |  |  |  | 0
[6 empty] | KENTON | 6-162.1 | KY 1303 | 1.1 | 0 | 1.1 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT KY 1303 FROM KY 536 (MP 0.000) TO BEECHGROVE ELEMENTARY (MP 1.100) (PRIORITY SECTION 1). DESIGN PHASE UNDER PARENT NO. 6-162.01. (2012BOP)(16CCR) | R | STP | STP | 2019 | 3000000 | 3000000 | NO |  |  |  | 0
[6 empty] | KENTON | 6-162.1 | KY 1303 | 1.1 | 0 | 1.1 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT KY 1303 FROM KY 536 (MP 0.000) TO BEECHGROVE ELEMENTARY (MP 1.100) (PRIORITY SECTION 1). DESIGN PHASE UNDER PARENT NO. 6-162.01. (2012BOP)(16CCR) | U | STP | STP | 2020 | 1000000 | 1000000 | NO |  |  |  | 0
[6 empty] | KENTON | 6-162.2 | KY 536 | 1.061 | 0 | 1.061 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT KY 536 FROM THE EAST END OF THE NS RAILROAD BRIDGE (B91)(MP 14.363 IN BOONE) TO KY 1303 (MP 1.061). (16CCN) | R | STP | STP | 2017 | 3500000 | 3500000 | NO |  |  |  | 0
[6 empty] | KENTON | 6-162.2 | KY 536 | 1.061 | 0 | 1.061 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT KY 536 FROM THE EAST END OF THE NS RAILROAD BRIDGE (B91)(MP 14.363 IN BOONE) TO KY 1303 (MP 1.061). (16CCN) | U | STP | STP | 2019 | 1000000 | 1000000 | NO |  |  |  | 0
[6 empty] | KENTON | 6-162.2 | KY 536 | 1.061 | 0 | 1.061 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT KY 536 FROM THE EAST END OF THE NS RAILROAD BRIDGE (B91)(MP 14.363 IN BOONE) TO KY 1303 (MP 1.061). (16CCN) | C | STP | STP | 2020 | 8000000 | 8000000 | NO |  |  |  | 0
[6 empty] | KENTON | 6-418 | CS 2215 | 0.17 | 0 | 0.17 | RELIABILITY | MATCHED FED FUNDS(O) | PAVEMENT AND SIDEWALK RESTORATION ALONG 6TH STREET FROM SCOTT STREET TO RUSSELL STREET (1,400 FEET). ALSO SIDEWALK IMPROVEMENTS ON SCOTT STREET FROM 4TH STREET TO 6TH STREET (900 FEET). (2012BOP) | C | SNK | SNK | 2017 | 1280508 | 1024406.4 | NO |  |  |  | 0
|  |  | TIP FY 2016-19 ADM MOD #10. CHANGED FY IN TIP ONLY. NO CHANGE TO STIP. |  |  | KENTON | 6-419 | CR 1316 | 0.275 | 0 | 0.275 | RELIABILITY | MATCHED FED FUNDS(O) | PHASE I MULTI-USE PATH ALONG BROMLEY CRESCENT SPRINGS RD FROM ANDERSON ROAD TO AMSTERDAM ROAD. (2012BOP) | R | SNK | SNK | 2017 | 400000 | 320000 | NO |  |  |  | 0
|  |  | TIP FY 2016-19 ADM MOD #10. CHANGED FY IN TIP ONLY. NO CHANGE TO STIP. |  |  | KENTON | 6-419 | CR 1316 | 0.275 | 0 | 0.275 | RELIABILITY | MATCHED FED FUNDS(O) | PHASE I MULTI-USE PATH ALONG BROMLEY CRESCENT SPRINGS RD FROM ANDERSON ROAD TO AMSTERDAM ROAD. (2012BOP) | U | SNK | SNK | 2017 | 800000 | 640000 | NO |  |  |  | 0
[6 empty] | KENTON | 6-419 | CR 1316 | 0.275 | 0 | 0.275 | RELIABILITY | MATCHED FED FUNDS(O) | PHASE I MULTI-USE PATH ALONG BROMLEY CRESCENT SPRINGS RD FROM ANDERSON ROAD TO AMSTERDAM ROAD. (2012BOP) | C | SNK | SNK | 2017 | 3080000 | 2464000 | NO |  |  |  | 0
|  |  | TIP FY 2016-19 ADM MOD #10. CHANGED FY IN TIP ONLY. NO CHANGE TO STIP. |  |  | KENTON | 6-421 | KY 8 | 3.462 | 4.2 | 7.662 | RELIABILITY | MATCHED FED FUNDS(O) | PEDESTRIAN/BICYCLE TRAIL THROUGH THE CITIES OF LUDLOW, COVINGTON, NEWPORT & BELLEVUE ALONG THE OHIO RIVER. (2012BOP) | C | SNK | SNK | 2017 | 481600 | 385280 | NO |  |  |  | 0
[6 empty] | KENTON | 6-428.1 | CS 4128 |  | 2.19 | 3.11 | RELIABILITY | RESURFACING(P) | RESURFACE & STABILIZE DUDLEY ROAD FROM WINDING TRAILS TO THOMAS MORE PARKWAY (PHASE 1). (2014BOPC)(MOA WITH CITY OF EDGEWOOD). | C | SNK | SNK | 2017 | 1044000 | 835200 | NO |  |  |  | 0
[6 empty] | KENTON | 6-428.2 | CS 4128 |  | 1.46 | 2.19 | RELIABILITY | RESURFACING(P) | RESURFACE & STABILIZE DUDLEY ROAD FROM THOMAS MORE PARKWAY TO CATHERINE DRIVE (PHASE 2). (2014BOPC)(MOA WITH CITY OF EDGEWOOD). | C | SNK | SNK | 2017 | 924000 | 739200 | NO |  |  |  | 0
[6 empty] | KENTON | 6-429 | CS 2604 |  | 0.09 | 0.36 | RELIABILITY | RECONSTRUCTION(O) | LATONIA AVENUE ROADWAY RECONSTRUCTION FROM SOUTHERN AVENUE TO NEAR WEST 36TH STREET (2014BOP)(MOA WITH THE CITY OF COVINGTON). | C | SNK | SNK | 2017 | 588000 | 470400 | NO |  |  |  | 0
ADMINISTRATIVE MODIFICATION | 2016.002 | 2016-10-04 | TIP FY 2016-19 ADM MOD #10. ADDING PROJECT PER TIP MOD. NEW |  |  | KENTON | 6-430 | CS 2023 |  | 0 | 0.068 | RELIABILITY | RECONSTRUCTION(O) | WIDEN SIDEWALK FOR ADA COMPLIANCE AND ROADWAY RECONSTRUCTION ON JOHNSON ST & W RIVERCENTER BLVD FROM 3RD STREET TO THE EXISTING CONCRETE SECTION HEADING TOWARDS MADISON AVENUE IN COVINGTON. (2014BOP) | C | SNK | SNK | 2017 | 677800 | 677800 |  |  |  |  | 0
[6 empty] | KENTON | 6-1070 | CS 2097 | 0.079 | 0.144 | 0.223 | SAFETY | BRIDGE REPLACEMENT(P) | WEST 15TH STREET; REPLACE BRIDGE AND APPROACHES OVER CSX RR IN COVINGTON. (SR=19.1): (059C00029N)(12CCR) | R | STP | BRZ | 2017 | 830000 | 830000 | NO |  |  |  | 0
[6 empty] | KENTON | 6-1070 | CS 2097 | 0.079 | 0.144 | 0.223 | SAFETY | BRIDGE REPLACEMENT(P) | WEST 15TH STREET; REPLACE BRIDGE AND APPROACHES OVER CSX RR IN COVINGTON. (SR=19.1): (059C00029N)(12CCR) | U | STP | BRZ | 2017 | 550000 | 550000 | NO |  |  |  | 0
[6 empty] | KENTON | 6-1070 | CS 2097 | 0.079 | 0.144 | 0.223 | SAFETY | BRIDGE REPLACEMENT(P) | WEST 15TH STREET; REPLACE BRIDGE AND APPROACHES OVER CSX RR IN COVINGTON. (SR=19.1): (059C00029N)(12CCR) | C | STP | BRZ | 2018 | 2110000 | 2110000 | NO |  |  |  | 0
|  |  | TIP FY 2016-19 ADM MOD #10. CHANGED FY TO FY 2018 AND AMOUNT IN TIP. NO CHANGE TO STIP. |  |  | KENTON | 6-1075 | KY 1120 | 0.1 | 0.59 | 0.65 | RELIABILITY | BRIDGE REPLACEMENT(P) | EVALUATE BRIDGE ON KY-1120 (MP 0.621) OVER CSX RAILROAD; 11TH ST E OF RUSSELL ST; (STRUCTURALLY DEFICIENT, SR=19.5) 059B00083N | C | NHPP | BRO | 2017 | 750000 | 750000 | NO |  |  |  | 0
[6 empty] | KENTON | 6-8815 | US 25 | 0.415 | 11.675 | 12.09 | RELIABILITY | TRANSP ENHANCEMENT(P) | SIDEWALK AND CURB CONSTRUCTION ON DIXIE HIGHWAY FROM NORTH ARLINGTON NORTH TO COVINGTON SIDEWALK SYSTEM. (14CCN)(16CCR) | C | HSIP | SAF | 2017 | 1130000 | 1130000 | NO |  |  |  | 0
[6 empty] | KENTON | 6-8915 | I 275 |  |  |  | RELIABILITY | TRANSP ENHANCEMENT(P) | CONSTRUCT A SOUND BARRIER WALL ON I-275 FROM DIXIE HIGHWAY WESTBOUND. (16CCN) | D | STP | STP | 2017 | 100000 | 100000 | NO |  |  |  | 0
[6 empty] | KENTON | 6-8954 | CR 1021 | 0.022 | 0.027 | 0.65 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON ERNEST BRIDGE DR (CR 1021) OVER CSX RAILROAD. (16CCN) | C | STP | BRX | 2017 | 600000 | 600000 | NO |  |  |  | 0
[6 empty] | KNOTT | 12-283.4 | CS 1012 | 0.061 | 0 | 0.061 | SAFETY | SAFETY(P) | IMPROVEMENTS TO KY-550 IN HINDMAN; CONSTRUCT NEW BRIDGE OVER TROUBLESOME CREEK AT THE NEW ARTS AND CRAFTS COLLEGE @ KY 160. (16CCR) | R | NHPP | BRO | 2017 | 530000 | 530000 | NO |  |  |  | 0
[6 empty] | KNOTT | 12-283.4 | CS 1012 | 0.061 | 0 | 0.061 | SAFETY | SAFETY(P) | IMPROVEMENTS TO KY-550 IN HINDMAN; CONSTRUCT NEW BRIDGE OVER TROUBLESOME CREEK AT THE NEW ARTS AND CRAFTS COLLEGE @ KY 160. (16CCR) | C | NHPP | BRO | 2017 | 1630000 | 1630000 | NO |  |  |  | 0
[6 empty] | KNOTT | 12-1116 | CR 1008 |  | 0 | 0.04 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON ROCKLICK BRANCH (CR 1008) OVER RIGHT FORK BEAVER CREEK AT JCT WITH SOUTH HIGHWAY 7 (KY 7)(SR 43.9) 060C00006N | R | STP | BRZ | 2017 | 75000 | 75000 | NO |  |  |  | 0
[6 empty] | KNOTT | 12-1116 | CR 1008 |  | 0 | 0.04 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON ROCKLICK BRANCH (CR 1008) OVER RIGHT FORK BEAVER CREEK AT JCT WITH SOUTH HIGHWAY 7 (KY 7)(SR 43.9) 060C00006N | U | STP | BRZ | 2017 | 325000 | 325000 | NO |  |  |  | 0
[6 empty] | KNOTT | 12-1116 | CR 1008 |  | 0 | 0.04 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON ROCKLICK BRANCH (CR 1008) OVER RIGHT FORK BEAVER CREEK AT JCT WITH SOUTH HIGHWAY 7 (KY 7)(SR 43.9) 060C00006N | C | STP | BRZ | 2017 | 600000 | 600000 | NO |  |  |  | 0
[6 empty] | KNOTT | 12-1124 | CS 1016 | 0.012 | 0.018 | 0.03 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER RIGHT FORK TROUBLESOME CREEK ON FIELDWOOD DRIVE (CS1016) IN HINDMAN (060C00060N)(SR=21.9) | D | STP | BRZ | 2019 | 300000 | 300000 | NO |  |  |  | 0
[6 empty] | KNOTT | 12-8801 | KY 899 | 0.1 | 3.6 | 3.7 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT CURVE ON KY 899 IN KNOTT COUNTY BETWEEN MP 3.6 AND MP 3.7. (14CCN)(16CCN) | C | HSIP | SAF | 2018 | 125000 | 125000 | NO |  |  |  | 0
[6 empty] | KNOTT | 12-8904 | KY 3209 |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER BALLS FORK ON KY 3209. (16CCN) | C | STP | BRZ | 2017 | 1000000 | 1000000 | NO |  |  |  | 0
[6 empty] | KNOTT | 12-8908 |  |  |  |  | NEW ROUTES | NEW ROUTE(O) | CONSTRUCT AN ACCESS POINT OFF KY-7 AT APPROXIMATELY MP 13.2 TO CONNECT WITH JUSTIN EMERY LN (CR-1657), INCLUDING NEW BRIDGE FOR A SAFE CROSSING OVER RAILROAD TRACKS. (16CCN) | C | RRS | RRS | 2017 | 100000 | 100000 | NO |  |  |  | 0
[6 empty] | KNOX | 11-188 | US 25E | 1.976 | 24.221 | 26.197 | RELIABILITY | MAJOR WIDENING(O) | MAJOR WIDENING - ADDRESS SAFETY AND CAPACITY ON US 25E FROM CORBIN BYPASS TO KNOX/LAUREL COUNTY LINE. IMPROVE SAFETY ALONG CORRIDOR BY PROVIDING IMPROVED ACCESS MANAGEMENT.(12CCR) | C | NHPP | NH | 2018 | 7000000 | 7000000 | NO |  |  |  | 0
[6 empty] | KNOX | 11-1102 | CR 1325 | 0.004 | 0.191 | 0.195 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON OLD HWY 25 (CR 1325) JUST WEST OF US 25E. (SR=20.7) 061C00063N | D | STP | BRZ | 2019 | 250000 | 250000 | NO |  |  |  | 0
[6 empty] | KNOX | 11-8705 | KY 223 | 0.044 | 15.26 | 15.304 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE STINKING CREEK ROAD BROWNS BRANCH BRIDGE.(12CCN) | C | STP | BRX | 2017 | 900000 | 900000 | NO |  |  |  | 0
[6 empty] | LARUE | 4-1087 | KY 61 | 0.008 | 1.504 | 1.512 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER SOUTH FORK BRANCH ON KY 61 0.5 MILE NORTH OF KY 1906 (062B00010N) (SR=49.8) | D | STP | BRX | 2017 | 130000 | 130000 | NO |  |  |  | 0
[6 empty] | LARUE | 4-1087 | KY 61 | 0.008 | 1.504 | 1.512 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER SOUTH FORK BRANCH ON KY 61 0.5 MILE NORTH OF KY 1906 (062B00010N) (SR=49.8) | R | STP | BRX | 2019 | 50000 | 50000 | NO |  |  |  | 0
[6 empty] | LARUE | 4-1087 | KY 61 | 0.008 | 1.504 | 1.512 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER SOUTH FORK BRANCH ON KY 61 0.5 MILE NORTH OF KY 1906 (062B00010N) (SR=49.8) | U | STP | BRX | 2019 | 100000 | 100000 | NO |  |  |  | 0
[6 empty] | LARUE | 4-1087 | KY 61 | 0.008 | 1.504 | 1.512 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER SOUTH FORK BRANCH ON KY 61 0.5 MILE NORTH OF KY 1906 (062B00010N) (SR=49.8) | C | STP | BRX | 2020 | 400000 | 400000 | NO |  |  |  | 0
[6 empty] | LAUREL | 11-185 | US 25E | 2.024 | 0 | 2.024 | RELIABILITY | MAJOR WIDENING(O) | MAJOR WIDENING - ADDRESS SAFETY, CAPACITY, AND ACCESS MANAGEMENT ON US 25E FROM KNOX/LAUREL COUNTY LINE TO KY 770 (12CCR)(16CCR) | C | NHPP | NH | 2020 | 9250000 | 9250000 | NO |  |  |  | 0
[6 empty] | LAUREL | 11-1094 | CR 1341 |  | 1.071 | 1.111 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON DOG BRANCH SCHOOL RD (CR 1341) OVER SINKING CREEK 0.56 MILE NW OF SINKING CREEK RD (FD 781)(SR 13.8) 063C00025N | D | STP | BRZ | 2017 | 250000 | 250000 | NO |  |  |  | 0
[6 empty] | LAUREL | 11-1094 | CR 1341 |  | 1.071 | 1.111 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON DOG BRANCH SCHOOL RD (CR 1341) OVER SINKING CREEK 0.56 MILE NW OF SINKING CREEK RD (FD 781)(SR 13.8) 063C00025N | R | STP | BRZ | 2017 | 50000 | 50000 | NO |  |  |  | 0
[6 empty] | LAUREL | 11-1094 | CR 1341 |  | 1.071 | 1.111 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON DOG BRANCH SCHOOL RD (CR 1341) OVER SINKING CREEK 0.56 MILE NW OF SINKING CREEK RD (FD 781)(SR 13.8) 063C00025N | U | STP | BRZ | 2017 | 50000 | 50000 | NO |  |  |  | 0
[6 empty] | LAUREL | 11-1094 | CR 1341 |  | 1.071 | 1.111 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON DOG BRANCH SCHOOL RD (CR 1341) OVER SINKING CREEK 0.56 MILE NW OF SINKING CREEK RD (FD 781)(SR 13.8) 063C00025N | C | STP | BRZ | 2019 | 1000000 | 1000000 | NO |  |  |  | 0
[6 empty] | LAUREL | 11-1096 | KY 312 | 0.02 | 1.737 | 1.757 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER CRAIG CREEK ON KY 312 1.8 MILE SE OF KY 192. (063B00053N)(SR=49.4)(14CCR) | R | STP | BRX | 2017 | 100000 | 100000 | NO |  |  |  | 0
[6 empty] | LAUREL | 11-1096 | KY 312 | 0.02 | 1.737 | 1.757 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER CRAIG CREEK ON KY 312 1.8 MILE SE OF KY 192. (063B00053N)(SR=49.4)(14CCR) | U | STP | BRX | 2017 | 50000 | 50000 | NO |  |  |  | 0
[6 empty] | LAUREL | 11-1096 | KY 312 | 0.02 | 1.737 | 1.757 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER CRAIG CREEK ON KY 312 1.8 MILE SE OF KY 192. (063B00053N)(SR=49.4)(14CCR) | C | STP | BRX | 2018 | 1200000 | 1200000 | NO |  |  |  | 0
[6 empty] | LAUREL | 11-1105.01 | I 75 |  | 30.5 | 30.6 | RELIABILITY | BRIDGE REHAB(P) | REHAB BRIDGE ON I-75 AT MILEPOST 30.5 OVER LAUREL RIVER (SR 34.1) (B00043R AND B00043L) | C | NHPP | BRO | 2018 | 4000000 | 4000000 | NO |  |  |  | 0
[6 empty] | LAUREL | 11-8907 | KY 80 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | UPGRADE ROUTE FROM SOMERSET TO HAZARD TO INTERSTATE STANDARDS: EASTERN APPROACH TO THE ROCKCASTLE RIVER BRIDGE TO I-75 (SEGMENT 4) (16CCN) | D | NHPP | IM | 2017 | 1000000 | 1000000 | NO |  |  |  | 0
[6 empty] | LAUREL | 11-8908 | KY 80 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | UPGRADE ROUTE FROM SOMERSET TO HAZARD TO INTERSTATE STANDARDS: LONDON BYPASS, I-75 TO THE HAL ROGERS PARKWAY (SEGMENT 5). (16CCN) | D | NHPP | IM | 2017 | 1000000 | 1000000 | NO |  |  |  | 0
[6 empty] | LAUREL | 11-8909 | HR 9006 |  | 7.877 | 10.593 | RELIABILITY | RECONSTRUCTION(O) | UPGRADE ROUTE FROM SOMERSET TO HAZARD TO INTERSTATE STANDARDS: APPROXIMATELY 4 MILES EAST OF KY 192 TO CLAY/LAUREL LINE, MP 7.877 TO MP 10.593 (SEGMENT 6). (16CCN) | D | NHPP | IM | 2017 | 1000000 | 1000000 | NO |  |  |  | 0
[6 empty] | LAWRENCE | 12-1118 | CR 1202 |  | 0.844 | 0.884 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON MATTIE RD (CR 1202) OVER RIGHT FORK OF LITTLE BLAIN 0.38 MILE W OF ASH BRANCH RD (CR 1161)(SR 47) 064C00011N | R | STP | BRZ | 2017 | 75000 | 75000 | NO |  |  |  | 0
[6 empty] | LAWRENCE | 12-1118 | CR 1202 |  | 0.844 | 0.884 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON MATTIE RD (CR 1202) OVER RIGHT FORK OF LITTLE BLAIN 0.38 MILE W OF ASH BRANCH RD (CR 1161)(SR 47) 064C00011N | U | STP | BRZ | 2017 | 75000 | 75000 | NO |  |  |  | 0
[6 empty] | LAWRENCE | 12-1118 | CR 1202 |  | 0.844 | 0.884 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON MATTIE RD (CR 1202) OVER RIGHT FORK OF LITTLE BLAIN 0.38 MILE W OF ASH BRANCH RD (CR 1161)(SR 47) 064C00011N | C | STP | BRZ | 2018 | 350000 | 350000 | NO |  |  |  | 0
[6 empty] | LEE | 10-8852 | KY 52 | 0.678 | 11.78 | 12.26 | SAFETY | SAFETY(P) | CONSTRUCT SIDEWALKS, CURB AND GUTTER ON KY 52 FROM DOWNTOWN BEATTYVILLE TOWARD IRVINE. (14CCN)(AR/W)(16CCR) | C | STP | STP | 2017 | 3000000 | 3000000 | NO |  |  |  | 0
[6 empty] | LESLIE | 11-1078 | US 421 | 0.1 | 15.137 | 15.177 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON US-421 OVER STINNET CREEK (B08) 0.028 MILE SOUTH OF KY-406 NEAR STINNETT.(SR=26.0) (10CCR) | U | NHPP | BRO | 2017 | 180000 | 180000 | NO |  |  |  | 0
[6 empty] | LESLIE | 11-1078 | US 421 | 0.1 | 15.137 | 15.177 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON US-421 OVER STINNET CREEK (B08) 0.028 MILE SOUTH OF KY-406 NEAR STINNETT.(SR=26.0) (10CCR) | C | NHPP | BRO | 2019 | 3040000 | 3040000 | NO |  |  |  | 0
[6 empty] | LESLIE | 11-1089 | KY 80 |  | 5.142 | 5.182 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 80 OVER CUTSHIN CREEK AT INTERSECTION WITH BUSY HOLLOW DR (CR 1063)(SR 30) 066B00002N | C | NHPP | BRO | 2017 | 1681000 | 1681000 | NO |  |  |  | 0
[6 empty] | LESLIE | 11-1095 | US 421 | 0.014 | 18.423 | 18.437 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER MUNCY CREEK ON US 421 0.5 MILE SOUTH OF TAYLOR MORGAN ROAD (CR 1090).(066B00006N)(SR=31.5) | D | STP | BRX | 2017 | 350000 | 350000 | NO |  |  |  | 0
[6 empty] | LESLIE | 11-1095 | US 421 | 0.014 | 18.423 | 18.437 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER MUNCY CREEK ON US 421 0.5 MILE SOUTH OF TAYLOR MORGAN ROAD (CR 1090).(066B00006N)(SR=31.5) | R | STP | BRX | 2019 | 100000 | 100000 | NO |  |  |  | 0
[6 empty] | LESLIE | 11-1095 | US 421 | 0.014 | 18.423 | 18.437 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER MUNCY CREEK ON US 421 0.5 MILE SOUTH OF TAYLOR MORGAN ROAD (CR 1090).(066B00006N)(SR=31.5) | U | STP | BRX | 2019 | 75000 | 75000 | NO |  |  |  | 0
[6 empty] | LESLIE | 11-1095 | US 421 | 0.014 | 18.423 | 18.437 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER MUNCY CREEK ON US 421 0.5 MILE SOUTH OF TAYLOR MORGAN ROAD (CR 1090).(066B00006N)(SR=31.5) | C | STP | BRX | 2020 | 700000 | 700000 | NO |  |  |  | 0
[6 empty] | LESLIE | 11-1100 | CR 1528 | 0.012 | 0 | 0.012 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER WOLF CREEK ON COON CREEK ROAD (CR 1528) AT JCT WITH KY 3427 (066C00039N) (SR=30.1) (EBRP) | D | STP | BRZ | 2019 | 175000 | 175000 | NO |  |  |  | 0
[6 empty] | LESLIE | 11-1104 | CR 1219 | 0.012 | 0.016 | 0.028 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON MILE BRANCH RD (CR 1219) (MP 0.022) OVER BEECH FORK. (SR=4.0) 066C00048N | D | STP | BRZ | 2019 | 350000 | 350000 | NO |  |  |  | 0
[6 empty] | LESLIE | 11-1106 | CR 1207 |  | 0.022 | 0.034 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON WILLIAMS BRANCH RD (CR-1207) (0.028) OVER MIDDLE FORK KENTUCKY RIVER. (SR=2) 066C00020N | D | STP | BRZ | 2020 | 350000 | 350000 | NO |  |  |  | 0
[6 empty] | LESLIE | 11-8912 | HR 9006 |  | 35.929 | 44.188 | RELIABILITY | RECONSTRUCTION(O) | UPGRADE ROUTE FROM SOMERSET TO HAZARD TO INTERSTATE STANDARDS: 4 LANE FROM CLAY/LESLIE LINE TO HYDEN SPUR, MP 35.929 TO MP 44.188 (SEGMENT 9). (16CCN) | D | NHPP | NH | 2019 | 1000000 | 1000000 | NO |  |  |  | 0
[6 empty] | LESLIE | 11-8913 | HR 9006 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | UPGRADE ROUTE FROM SOMERSET TO HAZARD TO INTERSTATE STANDARDS: 4 LANE FROM HYDEN SPUR TO LESLIE/PERRY LINE (SEGMENT 10). (16CCN) | D | NHPP | NH | 2019 | 1000000 | 1000000 | NO |  |  |  | 0
[6 empty] | LETCHER | 12-199.1 | US 119 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT US-119 BY WIDENING TO 4-LANES, BEGINNING 0.15 MILES NORTH OF KY-15 AT END OF BRIDGE TO THE EXISTING 4-LANE AT BRASS DRIVE (SOUTH).(16CCN) | D | NHPP | NH | 2017 | 2000000 | 2000000 | NO |  |  |  | 0
[6 empty] | LETCHER | 12-199.1 | US 119 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT US-119 BY WIDENING TO 4-LANES, BEGINNING 0.15 MILES NORTH OF KY-15 AT END OF BRIDGE TO THE EXISTING 4-LANE AT BRASS DRIVE (SOUTH).(16CCN) | R | NHPP | NH | 2017 | 2400000 | 2400000 | NO |  |  |  | 0
[6 empty] | LETCHER | 12-199.1 | US 119 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT US-119 BY WIDENING TO 4-LANES, BEGINNING 0.15 MILES NORTH OF KY-15 AT END OF BRIDGE TO THE EXISTING 4-LANE AT BRASS DRIVE (SOUTH).(16CCN) | U | NHPP | NH | 2017 | 2400000 | 2400000 | NO |  |  |  | 0
[6 empty] | LETCHER | 12-199.11 | US 119 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT US-119 BY WIDENING TO 4-LANES, BEGINNING 0.15 MILES NORTH OF KY-15 AT END OF BRIDGE TO THE KY 2034/COUGAR DRIVE INTERSECTION.(16CCN) | C | NHPP | NH | 2018 | 10700000 | 10700000 | NO |  |  |  | 0
[6 empty] | LETCHER | 12-199.15 | US 119 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT US-119 BY WIDENING TO 4-LANES FROM KY 2034/COUGAR DRIVE TO THE EXISTING 4-LANE AT BRASS DRIVE (SOUTH).(16CCN) | C | NHPP | NH | 2018 | 17100000 | 17100000 | NO |  |  |  | 0
[6 empty] | LETCHER | 12-199.31 | US 119 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT US-119 BY WIDENING TO 4-LANES FROM EXISTING 4-LANE AT KY-1862 TO PAST JUST NORTH OF THE MAYKING MALL.(16CCN) | D | NHPP | NH | 2018 | 1350000 | 1350000 | NO |  |  |  | 0
[6 empty] | LETCHER | 12-199.31 | US 119 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT US-119 BY WIDENING TO 4-LANES FROM EXISTING 4-LANE AT KY-1862 TO PAST JUST NORTH OF THE MAYKING MALL.(16CCN) | R | NHPP | NH | 2019 | 1350000 | 1350000 | NO |  |  |  | 0
[6 empty] | LETCHER | 12-199.31 | US 119 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT US-119 BY WIDENING TO 4-LANES FROM EXISTING 4-LANE AT KY-1862 TO PAST JUST NORTH OF THE MAYKING MALL.(16CCN) | U | NHPP | NH | 2019 | 1350000 | 1350000 | NO |  |  |  | 0
[6 empty] | LETCHER | 12-199.32 | US 119 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT US-119 BY WIDENING TO 4-LANES FROM NORTH OF MAYKING MALL TO JUST SOUTH OF THE TRUCK PASSING LANES AND KY-3406.(16CCN) | D | NHPP | NH | 2020 | 600000 | 600000 | NO |  |  |  | 0
[6 empty] | LETCHER | 12-199.33 | US 119 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT US-119 BY WIDENING TO 4-LANES FROM KY-3406 AND THE BEGINNING OF THE NORTHBOUND TRUCK PASSING LANES TO JUST NORTH OF KY-805. (16CCN) | D | NHPP | NH | 2020 | 1300000 | 1300000 | NO |  |  |  | 0
[6 empty] | LETCHER | 12-199.34 | US 119 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT US-119 BY WIDENING TO 4-LANES FROM NORTH OF KY-805 TO THE EXISTING 4-LANE.(16CCN) | D | NHPP | NH | 2020 | 1000000 | 1000000 | NO |  |  |  | 0
[6 empty] | LETCHER | 12-199.5 | US 119 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT US-119 BY WIDENING TO 4-LANES ALONG A NEW ALIGNMENT (ORANGE) THROUGH THE GATEWAY INDUSTRIAL PARK TO US-23, INCLUDING US-23 FLYOVER RAMP.(16CCN) | D | NHPP | NH | 2017 | 3500000 | 3500000 | NO |  |  |  | 0
[6 empty] | LETCHER | 12-199.5 | US 119 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT US-119 BY WIDENING TO 4-LANES ALONG A NEW ALIGNMENT (ORANGE) THROUGH THE GATEWAY INDUSTRIAL PARK TO US-23, INCLUDING US-23 FLYOVER RAMP.(16CCN) | R | NHPP | NH | 2018 | 3600000 | 3600000 | NO |  |  |  | 0
[6 empty] | LETCHER | 12-199.5 | US 119 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT US-119 BY WIDENING TO 4-LANES ALONG A NEW ALIGNMENT (ORANGE) THROUGH THE GATEWAY INDUSTRIAL PARK TO US-23, INCLUDING US-23 FLYOVER RAMP.(16CCN) | U | NHPP | NH | 2018 | 2500000 | 2500000 | NO |  |  |  | 0
[6 empty] | LETCHER | 12-199.51 | US 119 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT US-119 BY WIDENING TO 4-LANES ALONG A NEW ALIGNMENT (ORANGE) THROUGH THE GATEWAY INDUSTRIAL PARK TO US-23.(16CCN) | C | NHPP | NH | 2020 | 18000000 | 18000000 | NO |  |  |  | 0
[6 empty] | LETCHER | 12-311.3 | US 119 | 3.48 |  |  | RELIABILITY | RELOCATION(O) | HARLAN-WHITESBURG; PINE MOUNTAIN; PARTRIDGE TO OVEN FORK; BEGINNING 1.3 MILES EAST OF THE HARLAN COUNTY LINE TO 1.71 MILES EAST OF KY-3404 NEAR JOE DAY BRANCH. (R/W FOR SECTIONS 1A & 1B) (F16) (2000BOPP) | R | NHPP | APD | 2017 | 3150000 | 3150000 | NO |  |  |  | 0
[6 empty] | LETCHER | 12-311.7 | US 119 | 2.86 |  |  | RELIABILITY | RELOCATION(O) | HARLAN-WHITESBURG; PINE MOUNTAIN; PARTRIDGE TO OVEN FORK; BEGINNING 1.71 MILES EAST OF KY-3404 NEAR JOE DAY BRANCH TO THE COMMUNITY OF OVEN FORK. (R/W FOR SECTIONS 3 & 4) (F16) (2000BOP)(16CCR) | R | NHPP | APD | 2017 | 3300000 | 3300000 | NO |  |  |  | 0
[6 empty] | LETCHER | 12-311.79 | US 119 | 1.55 |  |  | RELIABILITY | SURFACE(O) | HARLAN-WHITESBURG; PINE MOUNTAIN; PARTRIDGE TO OVEN FORK; SURFACING ON US-119 FROM 1000 FT WEST JCT. KY 3404 TO 0.15 MI WEST OF KY 806 AT OVEN FORK INCLUDING APPROACH TO EXISTING US 119. (SURFACING FOR CONSTRUCTION SECTIONS 2, 3A, 3B, AND 4). | C | NHPP | APD | 2018 | 5000000 | 5000000 | NO |  |  |  | 0
[6 empty] | LETCHER | 12-311.8 | US 119 | 1.6 | 8.6 | 10.2 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCTION OF US-119 FROM 0.15 MILE WEST OF KY-806 TO KY-932. 2012BOP | R | NHPP | APD | 2018 | 2500000 | 2500000 | NO |  |  |  | 0
[6 empty] | LETCHER | 12-311.8 | US 119 | 1.6 | 8.6 | 10.2 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCTION OF US-119 FROM 0.15 MILE WEST OF KY-806 TO KY-932. 2012BOP | U | NHPP | APD | 2019 | 300000 | 300000 | NO |  |  |  | 0
[6 empty] | LETCHER | 12-311.8 | US 119 | 1.6 | 8.6 | 10.2 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCTION OF US-119 FROM 0.15 MILE WEST OF KY-806 TO KY-932. 2012BOP | C | NHPP | APD | 2020 | 34000000 | 34000000 | NO |  |  |  | 0
[6 empty] | LETCHER | 12-1107 | CS 2026 | 0.1 | 0 | 0.1 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON CS-2026 OVER (MP 0.032) ELKHORN CREEK; AT EAST JENKINS; (STRUCTURALLY DEFICIENT, SR=13) 067C00058N | C | STP | BRZ | 2017 | 270000 | 270000 | NO |  |  |  | 0
[6 empty] | LETCHER | 12-1113 | KY 2034C | 0.04 | 0.006 | 0.046 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 2034C OVER N FORK KY RIVER 0.02 E OF US 119(SR 42.7) 067B00121N | R | STP | BRX | 2017 | 420000 | 420000 | NO |  |  |  | 0
[6 empty] | LETCHER | 12-1113 | KY 2034C | 0.04 | 0.006 | 0.046 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 2034C OVER N FORK KY RIVER 0.02 E OF US 119(SR 42.7) 067B00121N | U | STP | BRX | 2017 | 125000 | 125000 | NO |  |  |  | 0
[6 empty] | LETCHER | 12-1113 | KY 2034C | 0.04 | 0.006 | 0.046 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 2034C OVER N FORK KY RIVER 0.02 E OF US 119(SR 42.7) 067B00121N | C | STP | BRX | 2018 | 1350000 | 1350000 | NO |  |  |  | 0
[6 empty] | LETCHER | 12-1117 | CR 1359Q4 |  | 0.002 | 0.042 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON STEEL BRIDGE RD (CR 1359Q4) OVER NORTH FORK OF KENTUCKY RIVER AT JCT WITH HIGHWAY 7 (KY 7)(SR 24) C00080N | C | STP | BRZ | 2017 | 875000 | 875000 | NO |  |  |  | 0
[6 empty] | LETCHER | 12-1120 | KY 3404 | 0.012 | 0.782 | 0.794 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER POOR FORK OF CUMBERLAND RIVER ON KY 3404 100 FT SOUTH OF US 119. (067B00114N)(SR=11.7) | D | STP | BRX | 2017 | 275000 | 275000 | NO |  |  |  | 0
[6 empty] | LETCHER | 12-1120 | KY 3404 | 0.012 | 0.782 | 0.794 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER POOR FORK OF CUMBERLAND RIVER ON KY 3404 100 FT SOUTH OF US 119. (067B00114N)(SR=11.7) | R | STP | BRX | 2019 | 75000 | 75000 | NO |  |  |  | 0
[6 empty] | LETCHER | 12-1120 | KY 3404 | 0.012 | 0.782 | 0.794 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER POOR FORK OF CUMBERLAND RIVER ON KY 3404 100 FT SOUTH OF US 119. (067B00114N)(SR=11.7) | U | STP | BRX | 2019 | 75000 | 75000 | NO |  |  |  | 0
[6 empty] | LETCHER | 12-1125 | CR 1226 | 0.008 | 0.006 | 0.014 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON HAMPTON BRANCH (CR 1226) (MP 0.01) OVER COWAN CREEK. (SR=7.0) 067C00021N | D | STP | BRZ | 2017 | 200000 | 200000 | NO |  |  |  | 0
[6 empty] | LETCHER | 12-1125 | CR 1226 | 0.008 | 0.006 | 0.014 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON HAMPTON BRANCH (CR 1226) (MP 0.01) OVER COWAN CREEK. (SR=7.0) 067C00021N | R | STP | BRZ | 2019 | 150000 | 150000 | NO |  |  |  | 0
[6 empty] | LETCHER | 12-1125 | CR 1226 | 0.008 | 0.006 | 0.014 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON HAMPTON BRANCH (CR 1226) (MP 0.01) OVER COWAN CREEK. (SR=7.0) 067C00021N | U | STP | BRZ | 2019 | 100000 | 100000 | NO |  |  |  | 0
[6 empty] | LETCHER | 12-1126 | CR 1225 |  | 0.03 | 0.038 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON CR-1225 (0.034) OVER COWAN CREEK. (SR=3.0) 067C00020N | D | STP | BRZ | 2020 | 600000 | 600000 | NO |  |  |  | 0
[6 empty] | LEWIS | 9-1090 | KY 1068 | 0.02 | 1.74 | 1.76 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER LAUREL FORK ON KY 1068 30 FT S OF DEEP HOLE BRANCH ROAD (CR 1125).(068B00057N)(SR=60.1)(16CCR) | D | STP | BRX | 2017 | 500000 | 500000 | NO |  |  |  | 0
[6 empty] | LEWIS | 9-1090 | KY 1068 | 0.02 | 1.74 | 1.76 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER LAUREL FORK ON KY 1068 30 FT S OF DEEP HOLE BRANCH ROAD (CR 1125).(068B00057N)(SR=60.1)(16CCR) | R | STP | BRX | 2018 | 75000 | 75000 | NO |  |  |  | 0
[6 empty] | LEWIS | 9-1090 | KY 1068 | 0.02 | 1.74 | 1.76 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER LAUREL FORK ON KY 1068 30 FT S OF DEEP HOLE BRANCH ROAD (CR 1125).(068B00057N)(SR=60.1)(16CCR) | U | STP | BRX | 2018 | 75000 | 75000 | NO |  |  |  | 0
[6 empty] | LEWIS | 9-1090 | KY 1068 | 0.02 | 1.74 | 1.76 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER LAUREL FORK ON KY 1068 30 FT S OF DEEP HOLE BRANCH ROAD (CR 1125).(068B00057N)(SR=60.1)(16CCR) | C | STP | BRX | 2019 | 900000 | 900000 | NO |  |  |  | 0
[6 empty] | LEWIS | 9-8806 | KY 8 | 4.387 | 24.016 | 28.95 | NEW ROUTES | NEW ROUTE(O) | RECONSTRUCT KY-8 FROM KY-8C IN GARRISON TO SCAFFOLD LICK ROAD.(14CCN)(16CCR) | D | STP | STP | 2017 | 3000000 | 3000000 | NO |  |  |  | 0
[6 empty] | LEWIS | 9-8807 | KY 57 | 4.557 | 0 | 4.557 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT KY-57 FROM KY-9 TO FLEMING/LEWIS COUNTY LINE. (14CCN)(16CCR) | D | STP | STP | 2017 | 2100000 | 2100000 | NO |  |  |  | 0
[6 empty] | LEWIS | 9-8807 | KY 57 | 4.557 | 0 | 4.557 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT KY-57 FROM KY-9 TO FLEMING/LEWIS COUNTY LINE. (14CCN)(16CCR) | R | STP | STP | 2018 | 5200000 | 5200000 | NO |  |  |  | 0
[6 empty] | LEWIS | 9-8807 | KY 57 | 4.557 | 0 | 4.557 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT KY-57 FROM KY-9 TO FLEMING/LEWIS COUNTY LINE. (14CCN)(16CCR) | U | STP | STP | 2019 | 3400000 | 3400000 | NO |  |  |  | 0
[6 empty] | LEWIS | 9-8917 | KY 9 | 4.595 | 11.205 | 15.8 | RELIABILITY | PAVEMENT REHAB-PRI(P) | PAVEMENT REHABILITATION ON THE AA HIGHWAY (KY 9) FROM THE INTERSECTION OF KY 59 (MP 11.205) TO 0.481 MILES NORTH OF CR 1303 (MP 15.800) IN LEWIS COUNTY. A TOTAL OF 4.595 MILES. (16CCN) | C | NHPP | NH | 2019 | 1280000 | 1280000 | NO |  |  |  | 0
[6 empty] | LINCOLN | 8-196 | US 27 | 0.7 | 18.2 | 18.9 | RELIABILITY | MAJOR WIDENING(O) | WIDEN US-27 FROM KY-590 TO BELL STREET IN STANFORD (MP 18.2 TO MP 18.9). (INCLUDES NEW GOSHEN CUT-OFF ROAD)(2005HPP-KY115) | R | NHPP | NH | 2019 | 1400000 | 1400000 | NO |  |  |  | 0
[6 empty] | LINCOLN | 8-196 | US 27 | 0.7 | 18.2 | 18.9 | RELIABILITY | MAJOR WIDENING(O) | WIDEN US-27 FROM KY-590 TO BELL STREET IN STANFORD (MP 18.2 TO MP 18.9). (INCLUDES NEW GOSHEN CUT-OFF ROAD)(2005HPP-KY115) | U | NHPP | NH | 2019 | 1100000 | 1100000 | NO |  |  |  | 0
[6 empty] | LINCOLN | 8-1055 | KY 1247 | 0.04 | 17.67 | 17.71 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 1247 OVER ST. ASAPH CREEK 0.044 S OF KY 78(SR 45.4) 069B00055N | R | STP | BRX | 2017 | 120000 | 120000 | NO |  |  |  | 0
[6 empty] | LINCOLN | 8-1055 | KY 1247 | 0.04 | 17.67 | 17.71 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 1247 OVER ST. ASAPH CREEK 0.044 S OF KY 78(SR 45.4) 069B00055N | U | STP | BRX | 2017 | 350000 | 350000 | NO |  |  |  | 0
[6 empty] | LINCOLN | 8-1055 | KY 1247 | 0.04 | 17.67 | 17.71 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 1247 OVER ST. ASAPH CREEK 0.044 S OF KY 78(SR 45.4) 069B00055N | C | STP | BRX | 2018 | 810000 | 810000 | NO |  |  |  | 0
[6 empty] | LIVINGSTON | 1-1142 | US 60 | 0.344 | 12.524 | 12.868 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON US 60 OVER THE CUMBERLAND RIVER 0.27 MILE N OF KY 70 (SR 32.7) 070B00017N. | R | NHPP | BRO | 2017 | 500000 | 500000 | NO |  |  |  | 0
[6 empty] | LIVINGSTON | 1-1142 | US 60 | 0.344 | 12.524 | 12.868 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON US 60 OVER THE CUMBERLAND RIVER 0.27 MILE N OF KY 70 (SR 32.7) 070B00017N. | U | NHPP | BRO | 2017 | 370000 | 370000 | NO |  |  |  | 0
[6 empty] | LIVINGSTON | 1-1142 | US 60 | 0.344 | 12.524 | 12.868 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON US 60 OVER THE CUMBERLAND RIVER 0.27 MILE N OF KY 70 (SR 32.7) 070B00017N. | C | NHPP | BRO | 2018 | 15000000 | 15000000 | NO |  |  |  | 0
[6 empty] | LIVINGSTON | 1-1142.01 | US 60 | 0.344 | 12.524 | 12.868 | RELIABILITY | PREFINANCD CONVRSN(O) | REPLACE BRIDGE ON US 60 OVER THE CUMBERLAND RIVER 0.27 MILE N OF KY 70 (SR 32.7) 070B00017N (ADDITIONAL FUNDING FOR C PHASE) | C | NHPP | BRO | 2019 | 15000000 | 15000000 | YES |  |  |  | 0
[6 empty] | LIVINGSTON | 1-1142.02 | US 60 |  | 12.524 | 12.868 | RELIABILITY | PREFINANCD CONVRSN(O) | REPLACE BRIDGE ON US 60 OVER THE CUMBERLAND RIVER 0.27 MILE N OF KY 70 (SR 32.7) 070B00017N (ADDITIONAL FUNDING FOR C PHASE) | C | NHPP | BRO | 2020 | 15000000 | 15000000 | YES |  |  |  | 0
[6 empty] | LIVINGSTON | 1-1145 | KY 866 | 0.04 | 0.022 | 0.062 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 866 OVER FORK OF GUM CREEK 0.02 MILE N OF KY 1664(SR 44.5)070B00050N | C | STP | BRX | 2017 | 750000 | 750000 | NO |  |  |  | 0
[6 empty] | LYON | 1-8901 | KY 93 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT INTERSECTION AT JUNCTION OF KY-93 AND KY-3305. (16CCN) | C | STP | STP | 2017 | 1450000 | 1450000 | NO |  |  |  | 0
[6 empty] | MADISON | 7-236 | KY 595 |  | 2.565 | 2.665 | RELIABILITY | SCOPING STUDY(O) | COMPREHENSIVE TRAFFIC STUDY FOR INTERSECTION OF MAIN STREET AND BEREA COLLEGE CAMPUS, BEREA. (2005HPP-KY112)(MOA WITH BEREA). (16CCR) | C | HPP | HPP | 2017 | 500000 | 500000 | NO |  |  |  | 0
[6 empty] | MADISON | 7-251.01 | US 25 | 3.5 | 11.903 | 15.442 | RELIABILITY | MAJOR WIDENING(O) | WIDEN US-25 FROM US-421 NORTH TO KY-876. STATE TO PROVIDE DESIGN AND PLANS, AND FUNDS FOR THIS PROJECT ARE REQUESTED TO BE PAID TO THE MADISON COUNTY FISCAL COURT, WHICH SHALL COORDINATE THE PROJECT. (2005HPP-KY110)(06CCR) | C | HPP | HPP | 2017 | 719921 | 719921 | NO |  |  |  | 0
[6 empty] | MADISON | 7-251.4 | US 25 | 2.98 | 11.903 | 14.883 | RELIABILITY | MAJOR WIDENING(O) | PRIORITY SECTION II & III: WIDEN US-25 FROM US 421 TO PUMPKIN RUN.(SEE 7-251.10 FOR SEC III UTIL & CONST) (2006BOPC)(08CCR)(10CCR)(12CCR)(14CCR) | C | NHPP | NH | 2018 | 6910000 | 6910000 | NO |  |  |  | 0
[6 empty] | MADISON | 7-1126 | KY 3376 | 0.04 | 4.586 | 4.626 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 3376 OVER HAYS FORK 0.048 SOUTH OF US 421 (SR 23.1) 076B00086N. | C | STP | BRX | 2017 | 760000 | 760000 | NO |  |  |  | 0
[6 empty] | MADISON | 7-1130 | US 421 | 0.04 | 2.443 | 2.483 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON BATTLEFIELD MEMORIAL HWY (US 421) OVER COWBELL CREEK AT JCT WITH HIGHWAY 21 E (KY 21)(SR 45.5) 076B00021 | R | NHPP | BRO | 2017 | 90000 | 90000 | NO |  |  |  | 0
[6 empty] | MADISON | 7-1130 | US 421 | 0.04 | 2.443 | 2.483 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON BATTLEFIELD MEMORIAL HWY (US 421) OVER COWBELL CREEK AT JCT WITH HIGHWAY 21 E (KY 21)(SR 45.5) 076B00021 | U | NHPP | BRO | 2017 | 90000 | 90000 | NO |  |  |  | 0
[6 empty] | MADISON | 7-1130 | US 421 | 0.04 | 2.443 | 2.483 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON BATTLEFIELD MEMORIAL HWY (US 421) OVER COWBELL CREEK AT JCT WITH HIGHWAY 21 E (KY 21)(SR 45.5) 076B00021 | C | NHPP | BRO | 2017 | 625000 | 625000 | NO |  |  |  | 0
[6 empty] | MADISON | 7-1131 | CR 1158 |  | 0.252 | 0.292 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON OLD HAYS FORK LN (CR 1158) OVER BRANCH OF HAYS FORK 0.2 MILE SE OF BATTLEFIELD MEMORIAL HWY (US 421)(SR 16.9) 076C00023N | R | STP | BRZ | 2017 | 40000 | 40000 | NO |  |  |  | 0
[6 empty] | MADISON | 7-1131 | CR 1158 |  | 0.252 | 0.292 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON OLD HAYS FORK LN (CR 1158) OVER BRANCH OF HAYS FORK 0.2 MILE SE OF BATTLEFIELD MEMORIAL HWY (US 421)(SR 16.9) 076C00023N | U | STP | BRZ | 2017 | 40000 | 40000 | NO |  |  |  | 0
[6 empty] | MADISON | 7-1131 | CR 1158 |  | 0.252 | 0.292 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON OLD HAYS FORK LN (CR 1158) OVER BRANCH OF HAYS FORK 0.2 MILE SE OF BATTLEFIELD MEMORIAL HWY (US 421)(SR 16.9) 076C00023N | C | STP | BRZ | 2017 | 400000 | 400000 | NO |  |  |  | 0
[6 empty] | MADISON | 7-1137 | KY 3376 | 0.02 | 0.279 | 0.299 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER TERRILL BRANCH ROAD ON KY 3376 IN BEREA 200 FT N OF PEACHTREE DRIVE (CS 2072).(076B00085N)(SR=46.5) | D | STP | BRX | 2019 | 300000 | 300000 | NO |  |  |  | 0
[6 empty] | MADISON | 7-1142 | CR 1017 |  | 3.397 | 3.413 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON CR-1017 (3.405) OVER MUDDY CREEK. (SR=27.5) 076C00004N | D | STP | BRZ | 2020 | 275000 | 275000 | NO |  |  |  | 0
[6 empty] | MADISON | 7-1143 | CR 1044 |  | 0.003 | 0.011 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON CR-1044 (0.007) OVER BR OF MUDDY CREEK. (SR=29.5) 076C00066N | D | STP | BRZ | 2020 | 300000 | 300000 | NO |  |  |  | 0
[6 empty] | MADISON | 7-8403 | KY 627 | 0.1 | 0.073 | 0.193 | RELIABILITY | MAJOR WIDENING(O) | RECONSTRUCT AND WIDEN THE KY-627 BRIDGE OVER I-75 TO FIVE LANES TO IMPROVE TRAFFIC CONGESTION AND IMPROVE SAFETY. (INCLUDES 7-8400) (B40)(08CCN)(10CCR)(14CCR)(16CCR) | C | NHPP | NH | 2017 | 18720000 | 18720000 | NO |  |  |  | 0
[6 empty] | MADISON | 7-8820 | I 75 | 10.381 | 87.16 | 97.541 | RELIABILITY | PAVEMENT REHAB-INT(P) | REHABILITATION FROM CLAY'S FERRY BRIDGE TO BARNES MILL ROAD. (14CCN) | D | NHPP | IM | 2017 | 1500000 | 1500000 | NO |  |  |  | 0
[6 empty] | MAGOFFIN | 10-126.13 | KY 9009 | 2.4 | 71 | 73.4 | RELIABILITY | PREFINANCD CONVRSN(O) | MOUNTAIN PARKWAY CORRIDOR: WIDEN THE MOUNTAIN PARKWAY TO 4 LANES FROM APPROXIMATELY 0.4 MILES EAST OF KY 3050 OVERPASS (MP 71.0) TO 1.1 MI W OF BRIDGE OVER LICKING RIVER (MP 73.4). (2012BOP)(ADDITIONAL FUNDING FOR C PHASE)(16CCN) | C | NHPP | NH | 2017 | 12861470 | 12861470 | NO |  |  |  | 0
[6 empty] | MAGOFFIN | 10-126.4 | KY 9009 | 4.6 | 65 | 69.6 | RELIABILITY | MAJOR WIDENING(O) | MOUNTAIN PARKWAY CORRIDOR: WIDEN THE MOUNTAIN PARKWAY TO 4 LANES FROM 0.3MI W OF KY 3047 (65.0) TO 0.7 MI W OF MIDDLE FORK LICKING RIVER BRIDGE (69.6). (2012BOP)(14CCR)(16CCR) | U | NHPP | NH | 2017 | 850000 | 850000 | NO |  |  |  | 0
[6 empty] | MAGOFFIN | 10-126.4 | KY 9009 | 4.6 | 65 | 69.6 | RELIABILITY | MAJOR WIDENING(O) | MOUNTAIN PARKWAY CORRIDOR: WIDEN THE MOUNTAIN PARKWAY TO 4 LANES FROM 0.3MI W OF KY 3047 (65.0) TO 0.7 MI W OF MIDDLE FORK LICKING RIVER BRIDGE (69.6). (2012BOP)(14CCR)(16CCR) | C | NHPP | NH | 2020 | 40000000 | 40000000 | YES |  |  |  | 0
[6 empty] | MAGOFFIN | 10-126.5 | KY 9009 | 2.4 | 63.123 | 65 | RELIABILITY | MAJOR WIDENING(O) | MOUNTAIN PARKWAY CORRIDOR: WIDEN THE MOUNTAIN PARKWAY TO 4 LANES FROM 0.4 MI E OF THE KY-134 JOHNSON CREEK BR TO 0.3 MI W OF KY 3047 - SECTION 5. (14CCR)(16CCR) | U | NHPP | NH | 2017 | 630000 | 630000 | NO |  |  |  | 0
[6 empty] | MAGOFFIN | 10-126.5 | KY 9009 | 2.4 | 63.123 | 65 | RELIABILITY | MAJOR WIDENING(O) | MOUNTAIN PARKWAY CORRIDOR: WIDEN THE MOUNTAIN PARKWAY TO 4 LANES FROM 0.4 MI E OF THE KY-134 JOHNSON CREEK BR TO 0.3 MI W OF KY 3047 - SECTION 5. (14CCR)(16CCR) | C | NHPP | NH | 2017 | 15000000 | 15000000 | NO |  |  |  | 0
[6 empty] | MAGOFFIN | 10-126.51 | KY 9009 | 2.4 | 63.123 | 65 | RELIABILITY | PREFINANCD CONVRSN(O) | MOUNTAIN PARKWAY CORRIDOR: WIDEN THE MOUNTAIN PARKWAY TO 4 LANES FROM 0.4 MI E OF THE KY-134 JOHNSON CREEK BR TO 0.3 MI W OF KY 3047 - SECTION 5.(ADDITIONAL FUNDING FOR C PHASE)(16CCR) | C | NHPP | NH | 2018 | 15000000 | 15000000 | NO |  |  |  | 0
[6 empty] | MAGOFFIN | 10-126.52 | KY 9009 | 2.4 | 63.123 | 65 | RELIABILITY | PREFINANCD CONVRSN(O) | MOUNTAIN PARKWAY CORRIDOR: WIDEN THE MOUNTAIN PARKWAY TO 4 LANES FROM 0.4 MI E OF THE KY-134 JOHNSON CREEK BR TO 0.3 MI W OF KY 3047 - SECTION 5.(ADDITIONAL FUNDING FOR C PHASE)(16CCR) | C | NHPP | NH | 2019 | 7700000 | 7700000 | YES |  |  |  | 0
[6 empty] | MAGOFFIN | 10-140.1 | KY 9009 | 1.9 | 73.4 | 75.331 | RELIABILITY | PREFINANCD CONVRSN(O) | MOUNTAIN PARKWAY CORRIDOR: MOUNTAIN PARKWAY WIDENING AND SAFETY IMPROVEMENTS FROM MP 73.4, 1.1 MI W OF LICKING RIVER BRIDGE, TO MP 75.3 BURNING FORK BRIDGE. (08CCR)(10CCR)(12CCR)(14CCR)(ADDITIONAL FUNDING FOR 10-140.00)(16CCN) | C | NHPP | NH | 2017 | 10000000 | 10000000 | NO |  |  |  | 0
[6 empty] | MAGOFFIN | 10-166 | US 460 | 2.4 | 12.486 | 14.566 | RELIABILITY | MAJOR WIDENING(O) | MOUNTAIN PARKWAY CORRIDOR: WIDEN THE MOUNTAIN PARKWAY EXTENSION (KY 114/US 460) THROUGH THE CONGESTED AREA AT SALYERSVILLE FROM BURNING FORK BRIDGE TO KY 114. (14CCR)(R & U PHASES UNDER 10-166.01)(2014TIGER $24M) | C | KYD | KYD | 2017 | 24000000 | 24000000 | NO |  |  |  | 0
[6 empty] | MAGOFFIN | 10-169 | KY 114 | 5 | 0 | 5.026 | RELIABILITY | MAJOR WIDENING(O) | MOUNTAIN PARKWAY CORRIDOR: EXTEND THE FOUR LANE MOUNTAIN PARKWAY FROM US 460 TO THE MAGOFFIN/FLOYD COUNTY LINE. (SEE 12-1.01 FOR PE & ENV)(14CCR)(16CCR) | D | NHPP | NH | 2017 | 3000000 | 3000000 | NO |  |  |  | 0
[6 empty] | MAGOFFIN | 10-169 | KY 114 | 5 | 0 | 5.026 | RELIABILITY | MAJOR WIDENING(O) | MOUNTAIN PARKWAY CORRIDOR: EXTEND THE FOUR LANE MOUNTAIN PARKWAY FROM US 460 TO THE MAGOFFIN/FLOYD COUNTY LINE. (SEE 12-1.01 FOR PE & ENV)(14CCR)(16CCR) | R | NHPP | NH | 2018 | 8570000 | 8570000 | NO |  |  |  | 0
[6 empty] | MAGOFFIN | 10-169 | KY 114 | 5 | 0 | 5.026 | RELIABILITY | MAJOR WIDENING(O) | MOUNTAIN PARKWAY CORRIDOR: EXTEND THE FOUR LANE MOUNTAIN PARKWAY FROM US 460 TO THE MAGOFFIN/FLOYD COUNTY LINE. (SEE 12-1.01 FOR PE & ENV)(14CCR)(16CCR) | U | NHPP | NH | 2019 | 2500000 | 2500000 | NO |  |  |  | 0
[6 empty] | MAGOFFIN | 10-1099 | KY 2019 | 0.04 | 5.497 | 5.537 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 2019 OVER RACCOON CREEK 0.039 S OF KY 1081(SR 33.2)(AR/W)077B00063N | C | NHPP | BRO | 2017 | 680000 | 680000 | NO |  |  |  | 0
[6 empty] | MAGOFFIN | 10-8801 |  |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | BRIDGE NEAR NEW MAGOFFIN COUNTY HIGH SCHOOL NEAR OLD BURNING FORK ROAD. (14CCN)(16CCR) | C | NHPP | BRO | 2017 | 256370 | 256370 | NO |  |  |  | 0
[6 empty] | MAGOFFIN | 10-8901 | US 460 | 0.7 | 10 | 10.7 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT US 460 IN MAGOFFIN COUNTY AT IVY POINT HILL FROM MP 10.0 TO 10.7. (16CCN) | D | STP | STP | 2018 | 850000 | 850000 | NO |  |  |  | 0
[6 empty] | MAGOFFIN | 10-8901 | US 460 | 0.7 | 10 | 10.7 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT US 460 IN MAGOFFIN COUNTY AT IVY POINT HILL FROM MP 10.0 TO 10.7. (16CCN) | R | STP | STP | 2019 | 1500000 | 1500000 | NO |  |  |  | 0
[6 empty] | MAGOFFIN | 10-8901 | US 460 | 0.7 | 10 | 10.7 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT US 460 IN MAGOFFIN COUNTY AT IVY POINT HILL FROM MP 10.0 TO 10.7. (16CCN) | U | STP | STP | 2020 | 200000 | 200000 | NO |  |  |  | 0
[6 empty] | MARION | 4-8916 | KY 55 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | HEARTLAND PARKWAY: LEBANON BYPASS TO MARION/WASHINGTON LINE. (16CCN) | D | NHPP | NH | 2017 | 300000 | 300000 | NO |  |  |  | 0
[6 empty] | MARION | 4-8916 | KY 55 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | HEARTLAND PARKWAY: LEBANON BYPASS TO MARION/WASHINGTON LINE. (16CCN) | R | NHPP | NH | 2018 | 350000 | 350000 | NO |  |  |  | 0
[6 empty] | MARION | 4-8916 | KY 55 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | HEARTLAND PARKWAY: LEBANON BYPASS TO MARION/WASHINGTON LINE. (16CCN) | U | NHPP | NH | 2018 | 350000 | 350000 | NO |  |  |  | 0
[6 empty] | MARION | 4-8916 | KY 55 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | HEARTLAND PARKWAY: LEBANON BYPASS TO MARION/WASHINGTON LINE. (16CCN) | C | NHPP | NH | 2019 | 4500000 | 4500000 | NO |  |  |  | 0
[6 empty] | MARION | 4-8917 | US 68 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | HEARTLAND PARKWAY: MARION/TAYLOR LINE TO LEBANON BYPASS.(16CCN) | D | NHPP | NH | 2017 | 600000 | 600000 | NO |  |  |  | 0
[6 empty] | MARION | 4-8917 | US 68 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | HEARTLAND PARKWAY: MARION/TAYLOR LINE TO LEBANON BYPASS.(16CCN) | R | NHPP | NH | 2018 | 900000 | 900000 | NO |  |  |  | 0
[6 empty] | MARION | 4-8917 | US 68 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | HEARTLAND PARKWAY: MARION/TAYLOR LINE TO LEBANON BYPASS.(16CCN) | U | NHPP | NH | 2018 | 900000 | 900000 | NO |  |  |  | 0
[6 empty] | MARION | 4-8917 | US 68 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | HEARTLAND PARKWAY: MARION/TAYLOR LINE TO LEBANON BYPASS.(16CCN) | C | NHPP | NH | 2019 | 11000000 | 11000000 | NO |  |  |  | 0
[6 empty] | MARTIN | 12-154.16 | KY 40 | 1.6 |  |  | RELIABILITY | RELOCATION(O) | INEZ TO WARFIELD (SECTION 2-2): FROM BOOTH FORK TO KY-2031 [STA. 298+00 TO STA. 382+00 (ENGLISH)] (2002BOP)(16CCR) | C | STP | STP | 2020 | 48140000 | 48140000 | YES |  |  |  | 0
[6 empty] | MARTIN | 12-1092 | CR 1324 |  | 0 | 0.028 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON PR-1015 OVER ROCKCASTLE CREEK (C26) 275 FEET WEST JCT. KY-3 JUST SOUTH OF CROOKED RUN ROAD. (SR=2.0): (080C00026N) | C | STP | BRZ | 2017 | 60000 | 60000 | NO |  |  |  | 0
[6 empty] | MARTIN | 12-1112 | KY 40 | 0.07 | 19.63 | 19.7 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 40 OVER BUCK CREEK AT THE KY 2031 INTERSECTION (SR 49.8) 080B00002N.(AR/W) | C | NHPP | BRO | 2017 | 500000 | 500000 | NO |  |  |  | 0
[6 empty] | MASON | 9-1095 | US 68 | 0.4 | 16.8 | 17.2 | RELIABILITY | BRIDGE REHAB(P) | REPAIR BRIDGE ON US 68 OVER LAWRENCE CREEK 0.13 MI SW OF KY 3056. (081B00067N)(16CCR) | D | NHPP | BRO | 2017 | 550000 | 550000 | NO |  |  |  | 0
[6 empty] | MASON | 9-1095 | US 68 | 0.4 | 16.8 | 17.2 | RELIABILITY | BRIDGE REHAB(P) | REPAIR BRIDGE ON US 68 OVER LAWRENCE CREEK 0.13 MI SW OF KY 3056. (081B00067N)(16CCR) | C | NHPP | BRO | 2017 | 2000000 | 2000000 | NO |  |  |  | 0
[6 empty] | MASON | 9-8809 | US 68 | 0.15 | 11.75 | 11.9 | NEW ROUTES | NEW INTERCHANGE(O) | ADDITION OF AN INTERCHANGE ON HEATHER FRENCH HENRY SOUTHERN LOOP (US 62 AND US 68). (14CCN)(16CCR) | C | STP | STP | 2020 | 8000000 | 8000000 | NO |  |  |  | 0
[6 empty] | MASON | 9-8905 | US 62 |  |  |  | SAFETY | LIGHTING(P) | INSTALL DECORATIVE LIGHTING ON SIMON KENTON BRIDGE OVER OHIO RIVER IN MAYESVILLE.(16CCN) | C | STP | STP | 2018 | 300000 | 300000 | NO |  |  |  | 0
[6 empty] | MASON | 9-8906 | KY 3056 |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 3056 OVER SOUTH FORK LAWRENCE CREEK. (16CCN) | D | NHPP | BRO | 2017 | 400000 | 400000 | NO |  |  |  | 0
[6 empty] | MASON | 9-8906 | KY 3056 |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 3056 OVER SOUTH FORK LAWRENCE CREEK. (16CCN) | R | NHPP | BRO | 2018 | 175000 | 175000 | NO |  |  |  | 0
[6 empty] | MASON | 9-8906 | KY 3056 |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 3056 OVER SOUTH FORK LAWRENCE CREEK. (16CCN) | U | NHPP | BRO | 2019 | 175000 | 175000 | NO |  |  |  | 0
[6 empty] | MASON | 9-8906 | KY 3056 |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 3056 OVER SOUTH FORK LAWRENCE CREEK. (16CCN) | C | NHPP | BRO | 2020 | 1250000 | 1250000 | NO |  |  |  | 0
[6 empty] | MASON | 9-8910 | CR 1124 |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE THE BRIDGE ON DAVIS LANE. (16CCN) | D | STP | BRZ | 2017 | 500000 | 500000 | NO |  |  |  | 0
[6 empty] | MASON | 9-8910 | CR 1124 |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE THE BRIDGE ON DAVIS LANE. (16CCN) | R | STP | BRZ | 2018 | 100000 | 100000 | NO |  |  |  | 0
[6 empty] | MASON | 9-8910 | CR 1124 |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE THE BRIDGE ON DAVIS LANE. (16CCN) | U | STP | BRZ | 2019 | 150000 | 150000 | NO |  |  |  | 0
[6 empty] | MASON | 9-8910 | CR 1124 |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE THE BRIDGE ON DAVIS LANE. (16CCN) | C | STP | BRZ | 2020 | 1000000 | 1000000 | NO |  |  |  | 0
[6 empty] | MASON | 9-8911 | CR 1019 |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE THE BRIDGE ON KENNEDY CREEK ROAD. (16CCN) | D | STP | BRZ | 2017 | 300000 | 300000 | NO |  |  |  | 0
[6 empty] | MASON | 9-8911 | CR 1019 |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE THE BRIDGE ON KENNEDY CREEK ROAD. (16CCN) | R | STP | BRZ | 2018 | 150000 | 150000 | NO |  |  |  | 0
[6 empty] | MASON | 9-8911 | CR 1019 |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE THE BRIDGE ON KENNEDY CREEK ROAD. (16CCN) | U | STP | BRZ | 2019 | 100000 | 100000 | NO |  |  |  | 0
[6 empty] | MASON | 9-8911 | CR 1019 |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE THE BRIDGE ON KENNEDY CREEK ROAD. (16CCN) | C | STP | BRZ | 2020 | 550000 | 550000 | NO |  |  |  | 0
[6 empty] | MASON | 9-8916 | CR 1122 |  |  |  | RELIABILITY | BRIDGE REHAB(P) | REPAIR BRIDGE (081C00018N) ON DIXIE PIKE. (16CCN) | C | STP | BRZ | 2017 | 60000 | 60000 | NO |  |  |  | 0
[6 empty] | MCCRACKEN | 1-2 | I 24 | 1 | 0 | 1.067 | SAFETY | BRIDGE REHAB(P) | I-24 BRIDGE OVER THE OHIO RIVER @ PADUCAH (B100); JOINT PROJECT WITH ILLINOIS TO MITIGATE SCOUR (073B00100N) | C | NHPP | IM | 2017 | 260000 | 260000 | NO |  |  |  | 0
[6 empty] | MCCRACKEN | 1-154 | US 60 |  | 10.484 | 10.891 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | CONSTRUCT A DOUBLE-CROSSOVER DIAMOND INTERCHANGE ON US 60 AT THE I-24 INTERCHANGE NEAR KENTUCKY OAKS MALL. | R | NHPP | NH | 2017 | 210000 | 210000 | NO |  |  |  | 0
[6 empty] | MCCRACKEN | 1-154 | US 60 |  | 10.484 | 10.891 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | CONSTRUCT A DOUBLE-CROSSOVER DIAMOND INTERCHANGE ON US 60 AT THE I-24 INTERCHANGE NEAR KENTUCKY OAKS MALL. | U | NHPP | NH | 2017 | 320000 | 320000 | NO |  |  |  | 0
[6 empty] | MCCRACKEN | 1-154 | US 60 |  | 10.484 | 10.891 | ECONOMIC DEVELOPMENT | I-CHANGE RECONST(O) | CONSTRUCT A DOUBLE-CROSSOVER DIAMOND INTERCHANGE ON US 60 AT THE I-24 INTERCHANGE NEAR KENTUCKY OAKS MALL. | C | NHPP | NH | 2017 | 3790000 | 3790000 | NO |  |  |  | 0
[6 empty] | MCCRACKEN | 1-1115.1 | US 60 | 1 | 18.65 | 19.673 | RELIABILITY | RELOCATION(O) | RELOCATION AND MINOR WIDENING OF US-60 FROM CLARKS RIVER TO US-62 JCT.(10CCR)(14CCR)(LET W/ 1-1115.20)(16CCR) | R | NHPP | NH | 2017 | 3500000 | 3500000 | NO |  |  |  | 0
[6 empty] | MCCRACKEN | 1-1115.1 | US 60 | 1 | 18.65 | 19.673 | RELIABILITY | RELOCATION(O) | RELOCATION AND MINOR WIDENING OF US-60 FROM CLARKS RIVER TO US-62 JCT.(10CCR)(14CCR)(LET W/ 1-1115.20)(16CCR) | U | NHPP | NH | 2017 | 3120000 | 3120000 | NO |  |  |  | 0
[6 empty] | MCCRACKEN | 1-1115.1 | US 60 | 1 | 18.65 | 19.673 | RELIABILITY | RELOCATION(O) | RELOCATION AND MINOR WIDENING OF US-60 FROM CLARKS RIVER TO US-62 JCT.(10CCR)(14CCR)(LET W/ 1-1115.20)(16CCR) | C | STP | STP | 2019 | 10820000 | 10820000 | NO |  |  |  | 0
[6 empty] | MCCRACKEN | 1-1115.2 | US 62 | 1.5 | 12.881 | 14.358 | RELIABILITY | RELOCATION(O) | RELOCATION OF US-62 FROM US-60 DEPARTURE TO KY-1887 (PARK ROAD).(10CCR)(12CCR)(LET W/ 1-1115.10)(16CCR) | D | STP | STP | 2017 | 520000 | 520000 | NO |  |  |  | 0
[6 empty] | MCCRACKEN | 1-1115.2 | US 62 | 1.5 | 12.881 | 14.358 | RELIABILITY | RELOCATION(O) | RELOCATION OF US-62 FROM US-60 DEPARTURE TO KY-1887 (PARK ROAD).(10CCR)(12CCR)(LET W/ 1-1115.10)(16CCR) | R | STP | STP | 2018 | 4500000 | 4500000 | NO |  |  |  | 0
[6 empty] | MCCRACKEN | 1-1115.2 | US 62 | 1.5 | 12.881 | 14.358 | RELIABILITY | RELOCATION(O) | RELOCATION OF US-62 FROM US-60 DEPARTURE TO KY-1887 (PARK ROAD).(10CCR)(12CCR)(LET W/ 1-1115.10)(16CCR) | U | STP | STP | 2019 | 2710000 | 2710000 | NO |  |  |  | 0
[6 empty] | MCCRACKEN | 1-1115.2 | US 62 | 1.5 | 12.881 | 14.358 | RELIABILITY | RELOCATION(O) | RELOCATION OF US-62 FROM US-60 DEPARTURE TO KY-1887 (PARK ROAD).(10CCR)(12CCR)(LET W/ 1-1115.10)(16CCR) | C | STP | STP | 2020 | 8660000 | 8660000 | NO |  |  |  | 0
[6 empty] | MCCRACKEN | 1-1152 | KY 1954 | 0.022 | 0.768 | 0.79 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER BOTTOM DITCH ON KY 1954 0.7 MILE NORTH OF KY 348 (073B00096N) (SR=8.3). | D | STP | BRX | 2017 | 260000 | 260000 | NO |  |  |  | 0
[6 empty] | MCCRACKEN | 1-1152 | KY 1954 | 0.022 | 0.768 | 0.79 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER BOTTOM DITCH ON KY 1954 0.7 MILE NORTH OF KY 348 (073B00096N) (SR=8.3). | R | STP | BRX | 2019 | 140000 | 140000 | NO |  |  |  | 0
[6 empty] | MCCRACKEN | 1-1152 | KY 1954 | 0.022 | 0.768 | 0.79 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER BOTTOM DITCH ON KY 1954 0.7 MILE NORTH OF KY 348 (073B00096N) (SR=8.3). | U | STP | BRX | 2019 | 120000 | 120000 | NO |  |  |  | 0
[6 empty] | MCCRACKEN | 1-1152 | KY 1954 | 0.022 | 0.768 | 0.79 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER BOTTOM DITCH ON KY 1954 0.7 MILE NORTH OF KY 348 (073B00096N) (SR=8.3). | C | STP | BRX | 2020 | 560000 | 560000 | NO |  |  |  | 0
[6 empty] | MCCRACKEN | 1-1154 | KY 994 | 0.038 | 2.27 | 2.308 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER BRANCH OF BOTTOM DITCH ON KY 994 0.8 MI NW OF KY 348 (073B00015N)(SR=35.3)(EBRP) | D | STP | BRX | 2020 | 240000 | 240000 | NO |  |  |  | 0
[6 empty] | MCCREARY | 8-1065 | CR 1239 | 0.04 | 0.25 | 0.29 | RELIABILITY | BRIDGE REPLACEMENT(P) | BRIDGE OVER ROCK CREEK ON OLD FIDELITY-BELL FARM ROAD (CR 1239) 0.25 MI W OF ROCK CREEK ROAD (CR 1236) (074C00008N)(SR=22) | D | STP | BRZ | 2019 | 280000 | 280000 | NO |  |  |  | 0
[6 empty] | MCCREARY | 8-1065 | CR 1239 | 0.04 | 0.25 | 0.29 | RELIABILITY | BRIDGE REPLACEMENT(P) | BRIDGE OVER ROCK CREEK ON OLD FIDELITY-BELL FARM ROAD (CR 1239) 0.25 MI W OF ROCK CREEK ROAD (CR 1236) (074C00008N)(SR=22) | R | STP | BRZ | 2020 | 50000 | 50000 | NO |  |  |  | 0
[6 empty] | MCCREARY | 8-1065 | CR 1239 | 0.04 | 0.25 | 0.29 | RELIABILITY | BRIDGE REPLACEMENT(P) | BRIDGE OVER ROCK CREEK ON OLD FIDELITY-BELL FARM ROAD (CR 1239) 0.25 MI W OF ROCK CREEK ROAD (CR 1236) (074C00008N)(SR=22) | U | STP | BRZ | 2020 | 20000 | 20000 | NO |  |  |  | 0
[6 empty] | MCLEAN | 2-1078 | US 431 | 0.142 | 0 | 0.071 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE OVERFLOW STRUCTURE ON US-431 AT THE MUHLENBERG-MCLEAN CO LINE (SR 39) B00056N. | R | NHPP | BRO | 2017 | 200000 | 200000 | NO |  |  |  | 0
[6 empty] | MCLEAN | 2-1078 | US 431 | 0.142 | 0 | 0.071 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE OVERFLOW STRUCTURE ON US-431 AT THE MUHLENBERG-MCLEAN CO LINE (SR 39) B00056N. | U | NHPP | BRO | 2017 | 100000 | 100000 | NO |  |  |  | 0
[6 empty] | MCLEAN | 2-1078 | US 431 | 0.142 | 0 | 0.071 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE OVERFLOW STRUCTURE ON US-431 AT THE MUHLENBERG-MCLEAN CO LINE (SR 39) B00056N. | C | NHPP | BRO | 2017 | 2400000 | 2400000 | NO |  |  |  | 0
[6 empty] | MCLEAN | 2-1090 | KY 2385 | 0.08 | 3.5 | 3.58 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER BRANCH OF POND DRAIN CREEK ON KY 2385 0.9 MI SW OF KY 81 (075B00066N)(SR=43.6) | D | STP | BRX | 2019 | 440000 | 440000 | NO |  |  |  | 0
[6 empty] | MEADE | 4-1088 | KY 823 | 0.01 | 0.54 | 0.55 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER UNNAMED STREAM ON KY 823 0.5 MILE WEST OF KY 2734.(082B00008N) (SR=45.2) | D | STP | BRX | 2019 | 150000 | 150000 | NO |  |  |  | 0
[6 empty] | MERCER | 7-1116 | KY 152 | 0.1 | 18.818 | 18.894 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-152 OVER HERRINGTON LAKE AT THE MERCER/GARRARD COUNTY LINE (B05). (SR=3.0); (084B00005N) | C | NHPP | BRO | 2017 | 8000000 | 8000000 | NO |  |  |  | 0
[6 empty] | MERCER | 7-1116.01 | KY 152 |  | 18.818 | 18.894 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE AND APPROACHES ON KY-152 OVER HERRINGTON LAKE AT THE MERCER/GARRARD COUNTY LINE (B05). (SR=3.0)(084B00005N) | C | NHPP | BRO | 2017 | 7280000 | 7280000 | NO |  |  |  | 0
[6 empty] | MERCER | 7-1116.02 | KY 152 |  | 18.818 | 18.894 | RELIABILITY | PREFINANCD CONVRSN(P) | REPLACE BRIDGE AND APPROACHES ON KY-152 OVER HERRINGTON LAKE AT THE MERCER/GARRARD COUNTY LINE (B05). (SR=3.0)(084B00005N)(ADDITIONAL FUNDING FOR C PHASE) | C | NHPP | BRO | 2018 | 5000000 | 5000000 | NO |  |  |  | 0
[6 empty] | MERCER | 7-1128 | US 68 | 0.4 | 12.5 | 12.9 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON US 68 OVER SHAKER CREEK 0.019 W OF CHATHAM RD(CR-1113)(SR 36.2) 084B00001N | C | NHPP | BRO | 2017 | 710000 | 710000 | NO |  |  |  | 0
[6 empty] | METCALFE | 3-112.1 | KY 90 |  | 0 | 3.283 | RELIABILITY | SPOT IMPROVEMENTS(O) | SUMMER SHADE BYPASS. (06CCR)(2006BOPC)(08CCR)(12CCR)(14CCR) | R | STP | STP | 2017 | 2440000 | 2440000 | NO |  |  |  | 0
[6 empty] | METCALFE | 3-112.1 | KY 90 |  | 0 | 3.283 | RELIABILITY | SPOT IMPROVEMENTS(O) | SUMMER SHADE BYPASS. (06CCR)(2006BOPC)(08CCR)(12CCR)(14CCR) | U | STP | STP | 2018 | 1760000 | 1760000 | NO |  |  |  | 0
[6 empty] | METCALFE | 3-112.1 | KY 90 |  | 0 | 3.283 | RELIABILITY | SPOT IMPROVEMENTS(O) | SUMMER SHADE BYPASS. (06CCR)(2006BOPC)(08CCR)(12CCR)(14CCR) | C | STP | STP | 2020 | 15190000 | 15190000 | YES |  |  |  | 0
[6 empty] | METCALFE | 3-1087 | KY 496 | 0.02 | 11.201 | 11.221 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER OIL WELL BRANCH ON KY 496 0.5 MILE SE OF KY 533.(085B00025N) (SR=48.2)(EBRP) | D | STP | BRX | 2019 | 250000 | 250000 | NO |  |  |  | 0
[6 empty] | METCALFE | 3-1087 | KY 496 | 0.02 | 11.201 | 11.221 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER OIL WELL BRANCH ON KY 496 0.5 MILE SE OF KY 533.(085B00025N) (SR=48.2)(EBRP) | R | STP | BRX | 2020 | 75000 | 75000 | NO |  |  |  | 0
[6 empty] | METCALFE | 3-1087 | KY 496 | 0.02 | 11.201 | 11.221 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER OIL WELL BRANCH ON KY 496 0.5 MILE SE OF KY 533.(085B00025N) (SR=48.2)(EBRP) | U | STP | BRX | 2020 | 100000 | 100000 | NO |  |  |  | 0
[6 empty] | METCALFE | 3-8706 | US 68 | 2.191 | 17.835 | 20.026 | RELIABILITY | SPOT IMPROVEMENTS(O) | SPOT IMPROVEMENTS ON US-68 FROM THE CUMBERLAND PARKWAY TO THE GREEN/METCALFE COUNTY LINE.(12CCN)(16CCN) | R | STP | STP | 2018 | 1550000 | 1550000 | NO |  |  |  | 0
[6 empty] | METCALFE | 3-8706 | US 68 | 2.191 | 17.835 | 20.026 | RELIABILITY | SPOT IMPROVEMENTS(O) | SPOT IMPROVEMENTS ON US-68 FROM THE CUMBERLAND PARKWAY TO THE GREEN/METCALFE COUNTY LINE.(12CCN)(16CCN) | U | STP | STP | 2019 | 1200000 | 1200000 | NO |  |  |  | 0
[6 empty] | MONROE | 3-1084 | CR 1354 | 0.04 | 1.954 | 1.994 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON NEW SALEM RD (CR 1354) OVER PETER CREEK 0.2 MILE E OF BETHLEHAM CHURCH RD (CR 1335)(SR 20.4) 086C00015N | C | STP | BRZ | 2017 | 280000 | 280000 | NO |  |  |  | 0
[6 empty] | MONROE | 3-7020.01 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | CONSTRUCT NEW ROUTE FOR THE EAST TOMPKINSVILLE BYPASS "GRADE & DRAIN ONLY". (98CCN)(02CCR) (2002BOPC)(DESIGN "STP" FUNDING SHALL BE SUPPLEMENTAL TO THE AUTHORIZED AMOUNT ALREADY EXPENDED ON THIS PROJECT). (08CCR)(10CCR) | C | STP | STP | 2017 | 6930000 | 6930000 | NO |  |  |  | 0
[6 empty] | MONROE | 3-7020.17 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | CONSTRUCT NEW ROUTE FOR THE EAST TOMPKINSVILLE BYPASS "SURFACING ONLY". (98CCN)(02CCR) (2002BOPC)(DESIGN "STP" FUNDING SHALL BE SUPPLEMENTAL TO THE AUTHORIZED AMOUNT ALREADY EXPENDED ON THIS PROJECT). (08CCR)(10CCR) | C | STP | STP | 2018 | 7310000 | 7310000 | NO |  |  |  | 0
[6 empty] | MONTGOMERY | 7-6.01 | I 64 |  | 107.652 | 107.702 | RELIABILITY | REST AREA REHAB(P) | MONTGOMERY COUNTY I-64 WEST BOUND REST AREA IMPROVEMENTS. | C | NHPP | IM | 2017 | 250000 | 250000 | NO |  |  |  | 0
[6 empty] | MONTGOMERY | 7-240.01 | KY 1991 | 1.768 | 0 | 1.768 | RELIABILITY | MAJOR WIDENING(O) | WIDEN KY 1991 FROM MAYSVILLE ROAD TO MIDLAND TRAIL INDUSTRIAL PARK, MONTGOMERY COUNTY (SEE 7-8501.00 FOR "SPB" FUNDS)(2005HPP-KY129) | C | HPP | HPP | 2017 | 559899 | 559899 | NO |  |  |  | 0
[6 empty] | MONTGOMERY | 7-250.1 | US 460 | 1.48 | 18.125 | 19.6 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT US 460 AT LUCKY STOP HILL. (12CCR) | C | STP | STP | 2017 | 12980000 | 12980000 | NO |  |  |  | 0
[6 empty] | MONTGOMERY | 7-8819 | I 64 | 6.2 | 107.5 | 113.7 | RELIABILITY | MAJOR WIDENING(O) | WIDEN TO SIX LANES FROM MP 107.5 TO MP 113.7. (14CCN) | D | NHPP | IM | 2017 | 1500000 | 1500000 | NO |  |  |  | 0
[6 empty] | MORGAN | 10-126.6 | KY 9009 | 3.3 | 59.3 | 62.588 | RELIABILITY | MAJOR WIDENING(O) | MOUNTAIN PARKWAY CORRIDOR: WIDEN THE MOUNTAIN PARKWAY TO 4 LANES FROM CR 1226 PARKWAY ROAD TUNNEL (MP 59.3) TO 0.4 MI EAST OF THE KY-134 JOHNSON CREEK BRIDGE - SECTION 6.(12CCR)(14CCR)(16CCR) | U | NHPP | NH | 2017 | 900000 | 900000 | NO |  |  |  | 0
[6 empty] | MORGAN | 10-126.6 | KY 9009 | 3.3 | 59.3 | 62.588 | RELIABILITY | MAJOR WIDENING(O) | MOUNTAIN PARKWAY CORRIDOR: WIDEN THE MOUNTAIN PARKWAY TO 4 LANES FROM CR 1226 PARKWAY ROAD TUNNEL (MP 59.3) TO 0.4 MI EAST OF THE KY-134 JOHNSON CREEK BRIDGE - SECTION 6.(12CCR)(14CCR)(16CCR) | C | NHPP | NH | 2018 | 8000000 | 8000000 | NO |  |  |  | 0
[6 empty] | MORGAN | 10-126.61 | KY 9009 | 3.3 | 59.3 | 62.588 | RELIABILITY | PREFINANCD CONVRSN(O) | MOUNTAIN PARKWAY CORRIDOR: WIDEN THE MOUNTAIN PARKWAY TO 4 LANES FROM CR 1226 PARKWAY ROAD TUNNEL (MP 59.3) TO 0.4 MI EAST OF THE KY-134 JOHNSON CREEK BRIDGE - SECTION 6.(12CCR)(14CCR)(16CCR)(ADDITIONAL FUNDING FOR C PHASE) | C | NHPP | NH | 2019 | 12100000 | 12100000 | YES |  |  |  | 0
[6 empty] | MORGAN | 10-126.62 | KY 9009 | 3.3 | 59.3 | 62.588 | RELIABILITY | PREFINANCD CONVRSN(O) | MOUNTAIN PARKWAY CORRIDOR: WIDEN THE MOUNTAIN PARKWAY TO 4 LANES FROM CR 1226 PARKWAY ROAD TUNNEL (MP 59.3) TO 0.4 MI EAST OF THE KY-134 JOHNSON CREEK BRIDGE - SECTION 6.(12CCR)(14CCR)(16CCR)(ADDITIONAL FUNDING FOR C PHASE) | C | NHPP | NH | 2020 | 15000000 | 15000000 | YES |  |  |  | 0
[6 empty] | MORGAN | 10-1111 | US 460 | 0.05 | 25.74 | 25.79 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER WHITE OAK CREEK ON US 460 0.5 MILE NW OF KY 1000. (088B00021N)(SR=35) | D | STP | BRX | 2020 | 300000 | 300000 | NO |  |  |  | 0
[6 empty] | MORGAN | 10-8302 | US 460 | 0.5 | 1.6 | 2.1 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT AND STRAIGHTEN CURVE IN US-460 FROM MILEPOST 0.8 TO MILEPOST 2.1. (06CCN)(12CCR)(16CCR) | C | STP | STP | 2017 | 4370000 | 4370000 | NO |  |  |  | 0
[6 empty] | NELSON | 4-1078 | US 62 | 0.1 | 27.278 | 27.318 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGES ON US 62 (HINKLE CREEK) AND KY 48 IN BLOOMFIELD 090B00096N (SR 28.2) 090B00095N (SR 49.7)(12CCR) | R | NHPP | BRO | 2017 | 170000 | 170000 | NO |  |  |  | 0
[6 empty] | NELSON | 4-1078 | US 62 | 0.1 | 27.278 | 27.318 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGES ON US 62 (HINKLE CREEK) AND KY 48 IN BLOOMFIELD 090B00096N (SR 28.2) 090B00095N (SR 49.7)(12CCR) | U | NHPP | BRO | 2017 | 520000 | 520000 | NO |  |  |  | 0
[6 empty] | NELSON | 4-1078 | US 62 | 0.1 | 27.278 | 27.318 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGES ON US 62 (HINKLE CREEK) AND KY 48 IN BLOOMFIELD 090B00096N (SR 28.2) 090B00095N (SR 49.7)(12CCR) | C | NHPP | BRO | 2017 | 1400000 | 1400000 | NO |  |  |  | 0
[6 empty] | NELSON | 4-1089 | KY 509 | 0.018 | 3.61 | 3.628 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER FROMAN CREEK ON KY 509 0.9 MI W OF US 31E (090B00068N)(SR=38.7) | D | STP | BRX | 2020 | 150000 | 150000 | NO |  |  |  | 0
[6 empty] | NELSON | 4-1092 | CR 1215 | 0.02 | 0.12 | 0.14 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER DAVIS RUN ON HIGDON LOOP (CR 1215) 0.1 MI S OF US 31E NEAR SCL OF NEW HAVEN (090C00030N)(SR=27) (EBRP) | D | STP | BRZ | 2019 | 100000 | 100000 | NO |  |  |  | 0
[6 empty] | NICHOLAS | 7-310.3 | US 68 | 4.4 |  |  | RELIABILITY | MAJOR WIDENING(O) | PARIS-MAYSVILLE ROAD; RECONSTRUCT FROM MILLERSBURG TO KY-1455 AT CARLISLE (SECTION 3). (08CCR)(12CCR)(14CCR)(16CCR) | C | NHPP | NH | 2017 | 16870000 | 16870000 | NO |  |  |  | 0
[6 empty] | NICHOLAS | 9-205 | KY 36 | 0.183 | 3.1 | 3.283 | SAFETY | SAFETY(P) | RECONSTRUCT KY 36-KY 32 NEAR THE NICHOLAS COUNTY SCHOOLS PROPERTY. MP 3.10 TO MP 3.283. (12CCR)(16CCR) | R | STP | STP | 2017 | 1250000 | 1250000 | NO |  |  |  | 0
[6 empty] | NICHOLAS | 9-205 | KY 36 | 0.183 | 3.1 | 3.283 | SAFETY | SAFETY(P) | RECONSTRUCT KY 36-KY 32 NEAR THE NICHOLAS COUNTY SCHOOLS PROPERTY. MP 3.10 TO MP 3.283. (12CCR)(16CCR) | U | STP | STP | 2017 | 850000 | 850000 | NO |  |  |  | 0
[6 empty] | NICHOLAS | 9-205 | KY 36 | 0.183 | 3.1 | 3.283 | SAFETY | SAFETY(P) | RECONSTRUCT KY 36-KY 32 NEAR THE NICHOLAS COUNTY SCHOOLS PROPERTY. MP 3.10 TO MP 3.283. (12CCR)(16CCR) | C | STP | STP | 2017 | 4500000 | 4500000 | NO |  |  |  | 0
[6 empty] | NICHOLAS | 9-8951 | CR 1010 |  | 2.4 |  | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON ABNER'S MILL ROAD (CR 1010) 2.4 MILES NORTH OF KY 32. (16CCN) | C | STP | BRX | 2019 | 100000 | 100000 | NO |  |  |  | 0
[6 empty] | OHIO | 2-1077 | CR 1194 | 0.1 | 0.029 | 0.129 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON CR-1194 (MP 0.079) OVER THREELICK CREEK; .15 MI W JCT CR 5172; (STRUCTURALLY DEFICIENT, SR=2) 092C00128N (AR/W) | C | STP | BRZ | 2017 | 340000 | 340000 | NO |  |  |  | 0
[6 empty] | OHIO | 2-1083 | US 62 | 0.04 | 11.892 | 11.932 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON US 62 OVER BRANCH OF THREE LICK FORK 0.23 MILE E OF GREEN MEADOWS DR (CS 6068)(SR 47.2)092B00032 | R | NHPP | BRO | 2017 | 230000 | 230000 | NO |  |  |  | 0
[6 empty] | OHIO | 2-1083 | US 62 | 0.04 | 11.892 | 11.932 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON US 62 OVER BRANCH OF THREE LICK FORK 0.23 MILE E OF GREEN MEADOWS DR (CS 6068)(SR 47.2)092B00032 | U | NHPP | BRO | 2017 | 90000 | 90000 | NO |  |  |  | 0
[6 empty] | OHIO | 2-1083 | US 62 | 0.04 | 11.892 | 11.932 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON US 62 OVER BRANCH OF THREE LICK FORK 0.23 MILE E OF GREEN MEADOWS DR (CS 6068)(SR 47.2)092B00032 | C | NHPP | BRO | 2017 | 650000 | 650000 | NO |  |  |  | 0
[6 empty] | OHIO | 2-1091 | US 62 | 0.074 | 12 | 12.074 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER THREELICK FORK ON US 62 0.4 MILE E OF GREEN MEADOWS DRIVE (CS 6068) IN BEAVER DAM. (092B00033N)(SR=48) | D | STP | BRX | 2020 | 440000 | 440000 | NO |  |  |  | 0
[6 empty] | OHIO | 2-8810 | KY 69 | 5.761 | 7.556 | 13.317 | SAFETY | SAFETY-HAZARD ELIM(P) | WIDEN/RECONSTRUCT KY 69 FROM CENTERTOWN TO HARTFORD. (14CCN)(16CCR) | D | STP | STP | 2017 | 1690000 | 1690000 | NO |  |  |  | 0
[6 empty] | OHIO | 2-8810 | KY 69 | 5.761 | 7.556 | 13.317 | SAFETY | SAFETY-HAZARD ELIM(P) | WIDEN/RECONSTRUCT KY 69 FROM CENTERTOWN TO HARTFORD. (14CCN)(16CCR) | R | STP | STP | 2018 | 2500000 | 2500000 | NO |  |  |  | 0
[6 empty] | OHIO | 2-8810 | KY 69 | 5.761 | 7.556 | 13.317 | SAFETY | SAFETY-HAZARD ELIM(P) | WIDEN/RECONSTRUCT KY 69 FROM CENTERTOWN TO HARTFORD. (14CCN)(16CCR) | U | STP | STP | 2020 | 5000000 | 5000000 | NO |  |  |  | 0
[6 empty] | OLDHAM | 5-234 | KY 393 | 0.959 | 5.13 | 5.868 | RELIABILITY | MAJOR WIDENING(O) | KY-393 RECONSTRUCT FROM 140FEET SOUTH OF RAILROAD CROSSING (CSX) EXTENDING NORTHWEST TOWARDS KY 146 ENDING AT STATION 12+00 (DESIGN UNDER 5-230.00). (CONSTRUCTION SEQ.#2) | C | STP | STP | 2017 | 11520000 | 11520000 | NO |  |  |  | 0
[6 empty] | OLDHAM | 5-410.01 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | INTER-URBAN GREENWAY: CONSTRUCT A NON-MOTORIZED CORRIDOR FROM LAGRANGE TO JEFFERSON COUNTY LINE. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). (14CCR) | D | SLO | SLO | 2017 | 180000 | 144000 | NO |  |  |  | 0
[6 empty] | OLDHAM | 5-410.01 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | INTER-URBAN GREENWAY: CONSTRUCT A NON-MOTORIZED CORRIDOR FROM LAGRANGE TO JEFFERSON COUNTY LINE. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). (14CCR) | R | SLO | SLO | 2017 | 350000 | 280000 | NO |  |  |  | 0
[6 empty] | OLDHAM | 5-410.01 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | INTER-URBAN GREENWAY: CONSTRUCT A NON-MOTORIZED CORRIDOR FROM LAGRANGE TO JEFFERSON COUNTY LINE. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). (14CCR) | C | SLO | SLO | 2017 | 2080000 | 1664000 | NO |  |  |  | 0
[6 empty] | OLDHAM | 5-434 | CR 1002 | 0.75 | 0 | 0.747 | SAFETY | SAFETY(P) | CONSTRUCT AN UNINTERRUPTED RAIL UNDERPASS WEST OF LAGRANGE. (LOCAL MATCH)(ALL WORK BY OLDHAM COUNTY) (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). (14CCR) | U | SLO | SLO | 2017 | 1350000 | 1080000 | NO |  |  |  | 0
[6 empty] | OLDHAM | 5-434 | CR 1002 | 0.75 | 0 | 0.747 | SAFETY | SAFETY(P) | CONSTRUCT AN UNINTERRUPTED RAIL UNDERPASS WEST OF LAGRANGE. (LOCAL MATCH)(ALL WORK BY OLDHAM COUNTY) (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). (14CCR) | C | SLO | SLO | 2018 | 5600000 | 4480000 | NO |  |  |  | 0
[6 empty] | OLDHAM | 5-440.1 | KY 1793 | 0.286 | 1.542 | 1.828 | SAFETY | SAFETY(P) | CONSTRUCT SIDEWALKS ON KY 1793 FROM RIDGEVIEW DRIVE TO SETTLERS POINT TRAIL, AND A SIDEWALK CONNECTION FROM TIMOTHY WAY TO PEGGY BAKER PARK.(FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C | SLO | SLO | 2017 | 80000 | 64000 | NO |  |  |  | 0
[6 empty] | OLDHAM | 5-441.01 | US 42 | 0.9 | 0 | 0.942 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT US-42 FROM THE JEFFERSON/OLDHAM COUNTY LINE TO RIDGEMOOR DRIVE. (2004BOPC) (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | C | SLO | SLO | 2017 | 3510000 | 2808000 | NO |  |  |  | 0
[6 empty] | OLDHAM | 5-449 | KY 22 | 0.2 | 3.15 | 3.35 | RELIABILITY | RECONSTRUCTION(O) | INTERSECTION IMPROVEMENT AT KY 22 AND KY 329 IN CRESTWOOD. (ALL WORK BY KYTC)(2006BOPC)(FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | C | SLO | SLO | 2017 | 870000 | 696000 | NO |  |  |  | 0
[6 empty] | OLDHAM | 5-468.1 | CS 7000 | 0.041 | 0 | 0.041 | RELIABILITY | CONGESTION MITIGTN(O) | CONSTRUCTION OF A PARK AND RIDE FACILITY INCLUDING A PARKING LOT, SHELTER, PLAYGROUND, BIKE LOCKERS, WALKWAYS, AND A 1000' ACCESS ROAD LOCATED ON APPLE PATCH WAY OFF OF KY-329 NEAR I-71 EXIT 14 IN CRESTWOOD.(2010BOPC)(ADDITIONAL FUNDING)(14CCN) | C | SLO | SLO | 2017 | 308000 | 246400 | NO |  |  |  | 0
[6 empty] | OLDHAM | 5-483.1 | I 71 | 3.9 | 14.1 | 18 | RELIABILITY | MAJOR WIDENING(O) | WIDEN I-71 FROM FOUR TO SIX LANES FROM KY 329 (MP 14.1) TO KY 393 (MP 18.0). (16CCN) | D | NHPP | NH | 2019 | 3500000 | 3500000 | NO |  |  |  | 0
[6 empty] | OLDHAM | 5-483.1 | I 71 | 3.9 | 14.1 | 18 | RELIABILITY | MAJOR WIDENING(O) | WIDEN I-71 FROM FOUR TO SIX LANES FROM KY 329 (MP 14.1) TO KY 393 (MP 18.0). (16CCN) | R | NHPP | NH | 2020 | 1900000 | 1900000 | NO |  |  |  | 0
[6 empty] | OLDHAM | 5-483.2 | I 71 | 4.4 | 18 | 22.4 | RELIABILITY | MAJOR WIDENING(O) | WIDEN I-71 FROM FOUR TO SIX LANES FROM KY 393 (MP 18.0) TO KY 53 (MP 22.4), INCLUDING A NEW INTERCHANGE AT MP 20.6. (16CCN) | D | NHPP | NH | 2019 | 5500000 | 5500000 | NO |  |  |  | 0
[6 empty] | OLDHAM | 5-494 | CR 1209 |  | 1.43 | 1.44 | SAFETY | SAFETY-HAZARD ELIM(P) | OLD FLOYDSBURG ROAD SAFETY IMPROVEMENTS: REPLACE NARROW ONE-LANE CULVERT CROSSING; CLEAR TREES AND VEGETATION OUT OF RIGHT-OF-WAY; ADD SHOULDER TO THE ROAD, AND ADD SIGNAGE FOR SAFETY. | R | SLO | SLO | 2017 | 230000 | 184000 | NO |  |  |  | 0
[6 empty] | OLDHAM | 5-494 | CR 1209 |  | 1.43 | 1.44 | SAFETY | SAFETY-HAZARD ELIM(P) | OLD FLOYDSBURG ROAD SAFETY IMPROVEMENTS: REPLACE NARROW ONE-LANE CULVERT CROSSING; CLEAR TREES AND VEGETATION OUT OF RIGHT-OF-WAY; ADD SHOULDER TO THE ROAD, AND ADD SIGNAGE FOR SAFETY. | C | SLO | SLO | 2017 | 522000 | 417600 | NO |  |  |  | 0
[6 empty] | OLDHAM | 5-517.02 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | CONSTRUCT VARIOUS SIDEWALKS IN OLDHAM COUNTY. | C | SLO | SLO | 2017 | 100000 | 80000 | NO |  |  |  | 0
[6 empty] | OLDHAM | 5-517.03 |  |  |  |  | SAFETY | BIKE/PED FACIL(O) | CONSTRUCT VARIOUS SIDEWALKS IN OLDHAM COUNTY. | C | SLO | SLO | 2017 | 100000 | 80000 | NO |  |  |  | 0
[6 empty] | OLDHAM | 5-8852 | KY 53 | 2.617 | 3.068 | 5.685 | RELIABILITY | DESIGN ENGINEERING(O) | DESIGN FOR IMPROVING KY-53 FROM ZHALE SMITH ROAD TO KY-22 (TOTAL 3.2 MILES). (14CCN) | D | STP | STP | 2020 | 2000000 | 2000000 | NO |  |  |  | 0
[6 empty] | OWEN | 6-1088 | CR 1214 | 0.04 | 0.22 | 0.26 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER CEDAR CREEK ON SAWDRIDGE CREEK W ROAD (CR 1214) 0.2 MI N OF US 127 (094C00011N)(SR=20.3) | D | STP | BRZ | 2017 | 150000 | 150000 | NO |  |  |  | 0
[6 empty] | OWEN | 6-1088 | CR 1214 | 0.04 | 0.22 | 0.26 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER CEDAR CREEK ON SAWDRIDGE CREEK W ROAD (CR 1214) 0.2 MI N OF US 127 (094C00011N)(SR=20.3) | R | STP | BRZ | 2019 | 100000 | 100000 | NO |  |  |  | 0
[6 empty] | OWEN | 6-1088 | CR 1214 | 0.04 | 0.22 | 0.26 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER CEDAR CREEK ON SAWDRIDGE CREEK W ROAD (CR 1214) 0.2 MI N OF US 127 (094C00011N)(SR=20.3) | U | STP | BRZ | 2019 | 100000 | 100000 | NO |  |  |  | 0
[6 empty] | OWEN | 6-1088 | CR 1214 | 0.04 | 0.22 | 0.26 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER CEDAR CREEK ON SAWDRIDGE CREEK W ROAD (CR 1214) 0.2 MI N OF US 127 (094C00011N)(SR=20.3) | C | STP | BRZ | 2020 | 500000 | 500000 | NO |  |  |  | 0
[6 empty] | OWSLEY | 10-279.61 | KY 30 | 3.378 | 0 | 5.132 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT KY 30 FROM KY 847 TO THE JACKSON COUNTY LINE.(14CCR)(SEE 10-279.60 FOR PE & ENVIR) (AR/W)(16CCR) | D | STP | STP | 2017 | 2250000 | 2250000 | NO |  |  |  | 0
[6 empty] | OWSLEY | 10-279.61 | KY 30 | 3.378 | 0 | 5.132 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT KY 30 FROM KY 847 TO THE JACKSON COUNTY LINE.(14CCR)(SEE 10-279.60 FOR PE & ENVIR) (AR/W)(16CCR) | U | STP | STP | 2017 | 2500000 | 2500000 | NO |  |  |  | 0
[6 empty] | OWSLEY | 10-279.61 | KY 30 | 3.378 | 0 | 5.132 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT KY 30 FROM KY 847 TO THE JACKSON COUNTY LINE.(14CCR)(SEE 10-279.60 FOR PE & ENVIR) (AR/W)(16CCR) | C | STP | STP | 2018 | 16000000 | 16000000 | NO |  |  |  | 0
[6 empty] | OWSLEY | 10-279.62 | KY 30 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT KY 30 FROM KY 847 TO THE JACKSON COUNTY LINE.(14CCR)(SEE 10-279.60 FOR PE & ENVIR) (AR/W)(16CCR) | C | STP | STP | 2019 | 16510000 | 16510000 | NO |  |  |  | 0
[6 empty] | PENDLETON | 6-1073 | KY 159 | 0.1 | 3.589 | 3.689 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-159 (MP 3.639) OVER KINCAID CREEK; .2 MI. SOUTH OF JCT.KY 609; (STRUCTURALLY DEFICIENT, SR=42.4) 096B00004N | C | STP | BRX | 2018 | 2350000 | 2350000 | NO |  |  |  | 0
[6 empty] | PENDLETON | 6-1092 | CR 1020 | 0.006 | 0.395 | 0.401 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON HALE RD (CR 1020) 0.395MI N OF FLOUR CREEK RD. (SR=22.0) 096C00102N | D | STP | BRZ | 2017 | 30000 | 30000 | NO |  |  |  | 0
[6 empty] | PENDLETON | 6-1092 | CR 1020 | 0.006 | 0.395 | 0.401 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON HALE RD (CR 1020) 0.395MI N OF FLOUR CREEK RD. (SR=22.0) 096C00102N | R | STP | BRZ | 2018 | 50000 | 50000 | NO |  |  |  | 0
[6 empty] | PENDLETON | 6-1092 | CR 1020 | 0.006 | 0.395 | 0.401 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON HALE RD (CR 1020) 0.395MI N OF FLOUR CREEK RD. (SR=22.0) 096C00102N | U | STP | BRZ | 2018 | 10000 | 10000 | NO |  |  |  | 0
[6 empty] | PENDLETON | 6-1092 | CR 1020 | 0.006 | 0.395 | 0.401 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON HALE RD (CR 1020) 0.395MI N OF FLOUR CREEK RD. (SR=22.0) 096C00102N | C | STP | BRZ | 2019 | 200000 | 200000 | NO |  |  |  | 0
[6 empty] | PENDLETON | 6-1094 | CR 1207 |  | 1.612 | 1.624 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON EAST FAIRVIEW RD (CR-1207) (1.618) OVER S. FORK GRASSY CREEK. (SR=28) 096C00072N | D | STP | BRZ | 2020 | 250000 | 250000 | NO |  |  |  | 0
[6 empty] | PERRY | 10-158 | KY 15 | 1.243 | 13.269 | 14.512 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE SAFETY, UPGRADE GEOMETRICS, AND ADDRESS CAPACITY ISSUES FOR KY 15 IN PERRY COUNTY FROM MORTON BOULEVARD TO KY 15 BYPASS | C | NHPP | NH | 2017 | 25000000 | 25000000 | NO |  |  |  | 0
[6 empty] | PERRY | 10-158.01 | KY 15 | 1.243 | 13.269 | 14.512 | RELIABILITY | PREFINANCD CONVRSN(O) | IMPROVE SAFETY, UPGRADE GEOMETRICS, AND ADDRESS CAPACITY ISSUES FOR KY 15 IN PERRY COUNTY FROM MORTON BOULEVARD TO KY 15 BYPASS.(ADDITIONAL FUNDING FOR C PHASE) | C | NHPP | NH | 2018 | 15000000 | 15000000 | NO |  |  |  | 0
[6 empty] | PERRY | 10-158.02 | KY 15 | 1.243 | 13.269 | 14.512 | RELIABILITY | PREFINANCD CONVRSN(O) | IMPROVE SAFETY, UPGRADE GEOMETRICS, AND ADDRESS CAPACITY ISSUES FOR KY 15 IN PERRY COUNTY FROM MORTON BOULEVARD TO KY 15 BYPASS. (ADDITIONAL FUNDING FOR C PHASE) | C | NHPP | NH | 2019 | 12000000 | 12000000 | YES |  |  |  | 0
[6 empty] | PERRY | 10-1102 | KY 1146 | 0.033 | 2.679 | 2.712 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON BULAN HINER RD (KY 1146) OVER TRACE FORK AT JCT WITH KENTUCKY HIGHWAY 476 (KY 476)(SR 25.5) 097B00103N | C | STP | BRX | 2017 | 600000 | 600000 | NO |  |  |  | 0
[6 empty] | PERRY | 10-1112 | PR 1056 | 0.01 | 0.005 | 0.011 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER CLOVER FORK ON ROAD TO LEATHERWOOD SCHOOL 50 FT N OF KY 699 (097C00052N) (SR= 14.6) | D | STP | BRZ | 2017 | 250000 | 250000 | NO |  |  |  | 0
[6 empty] | PERRY | 10-1112 | PR 1056 | 0.01 | 0.005 | 0.011 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER CLOVER FORK ON ROAD TO LEATHERWOOD SCHOOL 50 FT N OF KY 699 (097C00052N) (SR= 14.6) | R | STP | BRZ | 2019 | 50000 | 50000 | NO |  |  |  | 0
[6 empty] | PERRY | 10-1112 | PR 1056 | 0.01 | 0.005 | 0.011 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER CLOVER FORK ON ROAD TO LEATHERWOOD SCHOOL 50 FT N OF KY 699 (097C00052N) (SR= 14.6) | U | STP | BRZ | 2019 | 50000 | 50000 | NO |  |  |  | 0
[6 empty] | PERRY | 10-1112 | PR 1056 | 0.01 | 0.005 | 0.011 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER CLOVER FORK ON ROAD TO LEATHERWOOD SCHOOL 50 FT N OF KY 699 (097C00052N) (SR= 14.6) | C | STP | BRZ | 2020 | 500000 | 500000 | NO |  |  |  | 0
[6 empty] | PERRY | 10-1113 | CR 1114 | 0.047 | 0.07 | 0.117 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER NORTH FORK KENTUCKY RIVER ON KENMONT ROAD (CR 1114) 380 FT SE OF KY 7 (097C00005N)(SR=48.6) | D | STP | BRZ | 2019 | 300000 | 300000 | NO |  |  |  | 0
[6 empty] | PERRY | 10-1114 | CR 1140 | 0.009 | 0 | 0.009 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER STRAIGHT FORK ON LITTLE LEATHERWOOD CREEK ROAD (CR 1140) AT JCT WITH KY 3348 (097C00013N)(SR=38) | D | STP | BRZ | 2019 | 250000 | 250000 | NO |  |  |  | 0
[6 empty] | PERRY | 10-1114 | CR 1140 | 0.009 | 0 | 0.009 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER STRAIGHT FORK ON LITTLE LEATHERWOOD CREEK ROAD (CR 1140) AT JCT WITH KY 3348 (097C00013N)(SR=38) | R | STP | BRZ | 2020 | 50000 | 50000 | NO |  |  |  | 0
[6 empty] | PERRY | 10-1114 | CR 1140 | 0.009 | 0 | 0.009 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER STRAIGHT FORK ON LITTLE LEATHERWOOD CREEK ROAD (CR 1140) AT JCT WITH KY 3348 (097C00013N)(SR=38) | U | STP | BRZ | 2020 | 75000 | 75000 | NO |  |  |  | 0
[6 empty] | PERRY | 10-8903 | HR 9006 |  | 57 |  | RELIABILITY | NEW INTERCHANGE(O) | NEW INTERCHANGE OFF OF A NEW EXIT 57 HAL ROGERS PARKWAY. (16CCN) | D | STP | STP | 2017 | 1340000 | 1340000 | NO |  |  |  | 0
[6 empty] | PERRY | 10-8903 | HR 9006 |  | 57 |  | RELIABILITY | NEW INTERCHANGE(O) | NEW INTERCHANGE OFF OF A NEW EXIT 57 HAL ROGERS PARKWAY. (16CCN) | R | STP | STP | 2018 | 530000 | 530000 | NO |  |  |  | 0
[6 empty] | PERRY | 10-8903 | HR 9006 |  | 57 |  | RELIABILITY | NEW INTERCHANGE(O) | NEW INTERCHANGE OFF OF A NEW EXIT 57 HAL ROGERS PARKWAY. (16CCN) | U | STP | STP | 2019 | 159000 | 159000 | NO |  |  |  | 0
[6 empty] | PERRY | 10-8903 | HR 9006 |  | 57 |  | RELIABILITY | NEW INTERCHANGE(O) | NEW INTERCHANGE OFF OF A NEW EXIT 57 HAL ROGERS PARKWAY. (16CCN) | C | STP | STP | 2020 | 13750000 | 13750000 | YES |  |  |  | 0
[6 empty] | PERRY | 10-8905 | KY 80 |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | REMOVE CONCRETE BARRIER ON KY-80 AND JUSTICE DRIVE IN HAZARD. (16CCN) | C | HSIP | SAF | 2017 | 500000 | 500000 | NO |  |  |  | 0
[6 empty] | PERRY | 10-8910 | KY 1166 | 0.04 | 0.624 | 0.664 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-1166 OVER RT. FK. MACES CREEK. SR=26.8 (16CCN) | D | NHPP | BRO | 2017 | 335000 | 335000 | NO |  |  |  | 0
[6 empty] | PERRY | 10-8910 | KY 1166 | 0.04 | 0.624 | 0.664 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-1166 OVER RT. FK. MACES CREEK. SR=26.8 (16CCN) | R | NHPP | BRO | 2018 | 155000 | 155000 | NO |  |  |  | 0
[6 empty] | PERRY | 10-8910 | KY 1166 | 0.04 | 0.624 | 0.664 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-1166 OVER RT. FK. MACES CREEK. SR=26.8 (16CCN) | U | NHPP | BRO | 2019 | 103000 | 103000 | NO |  |  |  | 0
[6 empty] | PERRY | 10-8910 | KY 1166 | 0.04 | 0.624 | 0.664 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-1166 OVER RT. FK. MACES CREEK. SR=26.8 (16CCN) | C | NHPP | BRO | 2020 | 1060000 | 1060000 | NO |  |  |  | 0
[6 empty] | PERRY | 10-8913 | KY 1168 |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 1168 OVER MACES CREEK. (16CCN) | D | NHPP | BRO | 2017 | 335000 | 335000 | NO |  |  |  | 0
[6 empty] | PERRY | 10-8913 | KY 1168 |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 1168 OVER MACES CREEK. (16CCN) | R | NHPP | BRO | 2018 | 155000 | 155000 | NO |  |  |  | 0
[6 empty] | PERRY | 10-8913 | KY 1168 |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 1168 OVER MACES CREEK. (16CCN) | U | NHPP | BRO | 2019 | 103000 | 103000 | NO |  |  |  | 0
[6 empty] | PERRY | 10-8913 | KY 1168 |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 1168 OVER MACES CREEK. (16CCN) | C | NHPP | BRO | 2020 | 1060000 | 1060000 | NO |  |  |  | 0
[6 empty] | PERRY | 10-8915 | CR 1150 | 0.05 | 0 | 0.05 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER LEATHERWOOD CREEK. SR=35 (16CCN) | D | NHPP | BRO | 2017 | 258000 | 258000 | NO |  |  |  | 0
[6 empty] | PERRY | 10-8915 | CR 1150 | 0.05 | 0 | 0.05 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER LEATHERWOOD CREEK. SR=35 (16CCN) | R | NHPP | BRO | 2018 | 103000 | 103000 | NO |  |  |  | 0
[6 empty] | PERRY | 10-8915 | CR 1150 | 0.05 | 0 | 0.05 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER LEATHERWOOD CREEK. SR=35 (16CCN) | U | NHPP | BRO | 2019 | 78000 | 78000 | NO |  |  |  | 0
[6 empty] | PERRY | 10-8915 | CR 1150 | 0.05 | 0 | 0.05 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER LEATHERWOOD CREEK. SR=35 (16CCN) | C | NHPP | BRO | 2020 | 583000 | 583000 | NO |  |  |  | 0
[6 empty] | PIKE | 12-263.55 | US 460 | 0.8 |  |  | RELIABILITY | RELOCATION(O) | PIKEVILLE TO VA STATE LINE; US 460/KY 80; MAINLINE BRIDGES OVER KY 195 @ MARROWBONE CREEK. (SECTION 5B) (2014BOP) | C | NHPP | APD | 2017 | 15000000 | 15000000 | NO |  |  |  | 0
[6 empty] | PIKE | 12-263.63 | US 460 | 1.7 |  |  | RELIABILITY | RELOCATION(O) | PIKEVILLE TO VA. STATE LINE; US460/KY80 FROM KY-195 TO EAST OF POND CREEK - SECTION 6A-2 BRIDGE AT POND CREEK.(14CCR) | C | NHPP | APD | 2017 | 20000000 | 20000000 | NO |  |  |  | 0
[6 empty] | PIKE | 12-263.67 | US 460 | 0.4 |  |  | RELIABILITY | RELOCATION(O) | PIKEVILLE TO VA. STATE LINE; US-460/KY-80 FROM DUNLEARY HOLLOW TO KY-80 AT BEAVER CREEK (SECTION 6C) BRIDGE ONLY.(14CCN)(16CCR) | C | NHPP | APD | 2017 | 43000000 | 43000000 | NO |  |  |  | 0
[6 empty] | PIKE | 12-263.68 | US 460 | 0.4 |  |  | RELIABILITY | PREFINANCD CONVRSN(O) | PIKEVILLE TO VA. STATE LINE; US-460/KY-80 FROM DUNLEARY HOLLOW TO KY-80 AT BEAVER CREEK (SECTION 6C) BRIDGE ONLY. (ADDITIONAL FUNDING FOR C PHASE 12-263.67)(14CCN)(16CCN) | C | NHPP | NH | 2019 | 17000000 | 17000000 | YES |  |  |  | 0
[6 empty] | PIKE | 12-263.69 | US 460 | 3.4 |  |  | RELIABILITY | SURFACE(O) | PIKEVILLE TO VA. STATE LINE; US-460/KY-80 FROM KY-195 TO DUNLEARY HOLLOW. (SURFACING FOR SECTIONS 6A & 6B) (2000BOP)(14CCN) | C | NHPP | APD | 2019 | 17550000 | 17550000 | NO |  |  |  | 0
[6 empty] | PIKE | 12-263.74 | US 460 | 0.6 |  |  | RELIABILITY | RELOCATION(O) | PIKEVILLE TO VA. STATE LINE; US 460/KY 80 AT BEAVER CREEK NEAR BEAVER BOTTOM (SECTION 7A-2), RAMP 2, GRADE, DRAIN AND SURFACING.(14CCR)(16CCR) | C | NHPP | APD | 2017 | 18500000 | 18500000 | NO |  |  |  | 0
[6 empty] | PIKE | 12-1104 | KY 610 | 0.1 | 8.096 | 8.196 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-610 (MP 8.146) OVER LONG FORK; .1 MI S OF JCT KY-1469; (STRUCTURALLY DEFICIENT, SR=32) (AR/W)098B00069N | C | NHPP | BRO | 2017 | 1100000 | 1100000 | NO |  |  |  | 0
[6 empty] | PIKE | 12-1105 | KY 1469 | 0.1 | 5.193 | 5.293 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-1469 (MP 5.243) OVER MARSHALL'S BRANCH; .72 MI E. JCT KY-3414; (STRUCTURALLY DEFICIENT, SR=7.5) 098B00242N | C | STP | BRX | 2017 | 500000 | 500000 | NO |  |  |  | 0
[6 empty] | PIKE | 12-1115 | KY 1441 | 0.04 | 10.279 | 10.319 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON FISHTRAP RD (KY 1441) OVER RACCOON CREEK AT INTERSECTION WITH COON CREEK (CR 1371)(SR 37.9) 098B00093N | U | STP | BRX | 2017 | 225000 | 225000 | NO |  |  |  | 0
[6 empty] | PIKE | 12-1115 | KY 1441 | 0.04 | 10.279 | 10.319 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON FISHTRAP RD (KY 1441) OVER RACCOON CREEK AT INTERSECTION WITH COON CREEK (CR 1371)(SR 37.9) 098B00093N | C | STP | BRX | 2018 | 950000 | 950000 | NO |  |  |  | 0
[6 empty] | PIKE | 12-1122 | CR 1181 | 0.038 | 0.04 | 0.078 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER LEVISA FORK ON SOUTH RIVER ROAD CONNECTOR (CR 1181-70) AT JCT WITH US 460 NEAR VIRGINIA STATE LN (098C00088N)(SR=49) | D | STP | BRZ | 2017 | 400000 | 400000 | NO |  |  |  | 0
[6 empty] | PIKE | 12-1122 | CR 1181 | 0.038 | 0.04 | 0.078 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER LEVISA FORK ON SOUTH RIVER ROAD CONNECTOR (CR 1181-70) AT JCT WITH US 460 NEAR VIRGINIA STATE LN (098C00088N)(SR=49) | R | STP | BRZ | 2019 | 100000 | 100000 | NO |  |  |  | 0
[6 empty] | PIKE | 12-1122 | CR 1181 | 0.038 | 0.04 | 0.078 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER LEVISA FORK ON SOUTH RIVER ROAD CONNECTOR (CR 1181-70) AT JCT WITH US 460 NEAR VIRGINIA STATE LN (098C00088N)(SR=49) | U | STP | BRZ | 2019 | 100000 | 100000 | NO |  |  |  | 0
[6 empty] | PIKE | 12-1123 | CR 1801 | 0.265 | 0.005 | 0.027 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER BLACKBERRY CREEK ON BIG BLUE SPRINGS ROAD (CR 1801) AT JCT WITH KY 1056 (098C00028N)(SR=15.2) | D | STP | BRZ | 2019 | 300000 | 300000 | NO |  |  |  | 0
[6 empty] | PULASKI | 8-59.11 | I 66 | 25 |  |  | RELIABILITY | PE & ENVIRONMENTAL(O) | SOMERSET TO LONDON. (2006KYD)(10CCR) | C | KYD | KYD | 2017 | 3219838 | 3219838 | NO |  |  |  | 0
[6 empty] | PULASKI | 8-59.21 | I 66 | 10 |  |  | RELIABILITY | NEW ROUTE(O) | HAL ROGERS PARKWAY NORTHEAST BYPASS AROUND SOMERSET. (2006KYD) | C | KYD | KYD | 2017 | 1470000 | 1470000 | NO |  |  |  | 0
[6 empty] | ROCKCASTLE | 8-6.02 | I 75 | 4.5 | 64.5 | 69 | RELIABILITY | MAJOR WIDENING(O) | I-75 IN ROCKCASTLE COUNTY, KENTUCKY (MILEPOINT 64.5 TO MILEPOINT 69.0), 4.5 MILES. (04KYD-KY070) | C | KYD | KYD | 2017 | 855000 | 855000 | NO |  |  |  | 0
[6 empty] | ROCKCASTLE | 8-8718 | I 75 | 4.5 | 64.5 | 69 | RELIABILITY | MAJOR WIDENING(O) | MAKE I-75 THREE LANES IN EACH DIRECTION FROM MP 64.5 TO MP 69.0. (12CCN)(DESIGN/BUILD)(16CCN) | C | NHPP | IM | 2017 | 35000000 | 35000000 | NO |  |  |  | 0
[6 empty] | ROCKCASTLE | 8-8718.02 | I 75 | 4.4 | 55.7 | 60.1 | RELIABILITY | MAJOR WIDENING(O) | MAKE I-75 THREE LANES IN EACH DIRECTION FROM MP 55.7 TO 60.1. (12CCN)(DESIGN/BUILD)(16CCN) | D | NHPP | IM | 2017 | 1500000 | 1500000 | NO |  |  |  | 0
[6 empty] | ROCKCASTLE | 8-8718.02 | I 75 | 4.4 | 55.7 | 60.1 | RELIABILITY | MAJOR WIDENING(O) | MAKE I-75 THREE LANES IN EACH DIRECTION FROM MP 55.7 TO 60.1. (12CCN)(DESIGN/BUILD)(16CCN) | R | NHPP | IM | 2017 | 750000 | 750000 | NO |  |  |  | 0
[6 empty] | ROCKCASTLE | 8-8718.02 | I 75 | 4.4 | 55.7 | 60.1 | RELIABILITY | MAJOR WIDENING(O) | MAKE I-75 THREE LANES IN EACH DIRECTION FROM MP 55.7 TO 60.1. (12CCN)(DESIGN/BUILD)(16CCN) | U | NHPP | IM | 2017 | 250000 | 250000 | NO |  |  |  | 0
[6 empty] | ROCKCASTLE | 8-8718.02 | I 75 | 4.4 | 55.7 | 60.1 | RELIABILITY | MAJOR WIDENING(O) | MAKE I-75 THREE LANES IN EACH DIRECTION FROM MP 55.7 TO 60.1. (12CCN)(DESIGN/BUILD)(16CCN) | C | NHPP | IM | 2018 | 45000000 | 45000000 | NO |  |  |  | 0
[6 empty] | ROCKCASTLE | 8-8718.1 | I 75 | 4.4 | 60.1 | 64.5 | RELIABILITY | MAJOR WIDENING(O) | MAKE I-75 THREE LANES IN EACH DIRECTION FROM MP 60.1 TO MP 64.5.(12CCN)(DESIGN/BUILD)(16CCN) | U | NHPP | IM | 2017 | 1790000 | 1790000 | NO |  |  |  | 0
[6 empty] | ROCKCASTLE | 8-8718.1 | I 75 | 4.4 | 60.1 | 64.5 | RELIABILITY | MAJOR WIDENING(O) | MAKE I-75 THREE LANES IN EACH DIRECTION FROM MP 60.1 TO MP 64.5.(12CCN)(DESIGN/BUILD)(16CCN) | C | NHPP | IM | 2018 | 15000000 | 15000000 | NO |  |  |  | 0
[6 empty] | ROCKCASTLE | 8-8718.11 | I 75 | 4.4 | 60.1 | 64.5 | RELIABILITY | PREFINANCD CONVRSN(O) | MAKE I-75 THREE LANES IN EACH DIRECTION FROM MP 60.1 TO MP 64.5.(ADDITIONAL FUNDS FOR C PHASE. SEE 8-8718.10 AND 8-8718.12)(12CCN)(DESIGN/BUILD)(16CCN) | C | NHPP | IM | 2019 | 15000000 | 15000000 | YES |  |  |  | 0
[6 empty] | ROCKCASTLE | 8-8718.12 | I 75 |  | 60.1 | 64.5 | RELIABILITY | PREFINANCD CONVRSN(O) | MAKE I-75 THREE LANES IN EACH DIRECTION FROM MP 60.1 TO MP 64.5.(ADDITIONAL FUNDS FOR C PHASE. SEE 8-8718.10 AND 8-8718.11)(12CCN)(DESIGN/BUILD)(16CCN) | C | NHPP | IM | 2020 | 12500000 | 12500000 | YES |  |  |  | 0
[6 empty] | ROWAN | 9-61 | I 64 |  | 147.5 | 148 | ECONOMIC DEVELOPMENT | WEIGH STA REHAB(P) | UPGRADE EXISTING ROWAN COUNTY WEIGH STATION. | C | NHPP | IM | 2017 | 1000000 | 1000000 | NO |  |  |  | 0
[6 empty] | ROWAN | 9-1093 | CR 1140 | 0.01 | 0.01 | 0.02 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER BULL FORK ON HORSEMAN CEMETERY ROAD (CR 1140) AT JCT WITH BULLFORK ROAD (CR 1222) (103C00108N)(SR=32.5)(EBRP) | D | STP | BRZ | 2019 | 350000 | 350000 | NO |  |  |  | 0
[6 empty] | ROWAN | 9-1093 | CR 1140 | 0.01 | 0.01 | 0.02 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER BULL FORK ON HORSEMAN CEMETERY ROAD (CR 1140) AT JCT WITH BULLFORK ROAD (CR 1222) (103C00108N)(SR=32.5)(EBRP) | R | STP | BRZ | 2020 | 50000 | 50000 | NO |  |  |  | 0
[6 empty] | ROWAN | 9-1093 | CR 1140 | 0.01 | 0.01 | 0.02 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER BULL FORK ON HORSEMAN CEMETERY ROAD (CR 1140) AT JCT WITH BULLFORK ROAD (CR 1222) (103C00108N)(SR=32.5)(EBRP) | U | STP | BRZ | 2020 | 50000 | 50000 | NO |  |  |  | 0
[6 empty] | ROWAN | 9-8406 | KY 377 | 8.2 | 0 | 8.2 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT KY 377 FROM KY 32 (MP 0.0) TO JUST NORTH OF KY 799 (MP 8.2+-) TO IMPROVE SAFETY, CAPACITY, EFFICIENCY AND HIGHWAY SYSTEMS CONNECTIVITY. (08CCN)(10CCR)(16CCR) | C | STP | STP | 2019 | 41600000 | 41600000 | YES |  |  |  | 0
[6 empty] | ROWAN | 9-8912 | US 60 |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE THE WEST BRIDGE ON US 60 AT SUNNYBROOK.(16CCN) | D | NHPP | BRO | 2017 | 600000 | 600000 | NO |  |  |  | 0
[6 empty] | ROWAN | 9-8912 | US 60 |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE THE WEST BRIDGE ON US 60 AT SUNNYBROOK.(16CCN) | R | NHPP | BRO | 2017 | 50000 | 50000 | NO |  |  |  | 0
[6 empty] | ROWAN | 9-8912 | US 60 |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE THE WEST BRIDGE ON US 60 AT SUNNYBROOK.(16CCN) | U | NHPP | BRO | 2017 | 75000 | 75000 | NO |  |  |  | 0
[6 empty] | ROWAN | 9-8912 | US 60 |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE THE WEST BRIDGE ON US 60 AT SUNNYBROOK.(16CCN) | C | NHPP | BRO | 2018 | 750000 | 750000 | NO |  |  |  | 0
[6 empty] | ROWAN | 9-8914 | CR 1025 |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON LITTLE PERRY ROAD OVER TRIPLETT CREEK.(16CCN) | D | STP | BRZ | 2017 | 400000 | 400000 | NO |  |  |  | 0
[6 empty] | ROWAN | 9-8914 | CR 1025 |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON LITTLE PERRY ROAD OVER TRIPLETT CREEK.(16CCN) | R | STP | BRZ | 2018 | 175000 | 175000 | NO |  |  |  | 0
[6 empty] | ROWAN | 9-8914 | CR 1025 |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON LITTLE PERRY ROAD OVER TRIPLETT CREEK.(16CCN) | U | STP | BRZ | 2019 | 100000 | 100000 | NO |  |  |  | 0
[6 empty] | ROWAN | 9-8914 | CR 1025 |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON LITTLE PERRY ROAD OVER TRIPLETT CREEK.(16CCN) | C | STP | BRZ | 2020 | 900000 | 900000 | NO |  |  |  | 0
[6 empty] | ROWAN | 9-8915 | KY 801 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | WIDEN KY 801 FROM NEAR MMRC REGIONAL PARK TO KY 158 IN FLEMING CO. (16CCN) | P | STP | STP | 2017 | 75000 | 75000 | NO |  |  |  | 0
[6 empty] | ROWAN | 9-8915 | KY 801 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | WIDEN KY 801 FROM NEAR MMRC REGIONAL PARK TO KY 158 IN FLEMING CO. (16CCN) | D | STP | STP | 2017 | 1500000 | 1500000 | NO |  |  |  | 0
[6 empty] | ROWAN | 9-8915 | KY 801 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | WIDEN KY 801 FROM NEAR MMRC REGIONAL PARK TO KY 158 IN FLEMING CO. (16CCN) | R | STP | STP | 2018 | 2000000 | 2000000 | NO |  |  |  | 0
[6 empty] | ROWAN | 9-8915 | KY 801 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | WIDEN KY 801 FROM NEAR MMRC REGIONAL PARK TO KY 158 IN FLEMING CO. (16CCN) | U | STP | STP | 2019 | 1000000 | 1000000 | NO |  |  |  | 0
[6 empty] | ROWAN | 9-8915 | KY 801 |  |  |  | RELIABILITY | MAJOR WIDENING(O) | WIDEN KY 801 FROM NEAR MMRC REGIONAL PARK TO KY 158 IN FLEMING CO. (16CCN) | C | STP | STP | 2020 | 12500000 | 12500000 | YES |  |  |  | 0
[6 empty] | RUSSELL | 8-108 | US 127 | 3.444 |  |  | RELIABILITY | RECONSTRUCTION(O) | US-127 FROM NORTH BANK OF THE CUMBERLAND RIVER TO THE JAMESTOWN BYPASS. (00CCR) (08CCR)(10CCR)(12CCR)(G&D)(14CCR) | C | NHPP | NH | 2016 | 43200000 | 43200000 | YES |  |  |  | 0
[6 empty] | RUSSELL | 8-8601.21 | US 127 | 2.52 |  |  | RELIABILITY | RELOCATION(O) | RELOCATE US 127 FR APPROX .36 MI E OF INTERSECTION KY 1730 & MANNTOWN RD EXTEND N TO N BANK OF CUMBERLAND RIVER INCLUDING NEW BRIDGE OVER LAKE CUMBERLAND FR CLINTON CO TO RUSSELL CO(SEE 8-108&8-115 FOR PE&ENV)(12CCR)(SEE 8-8601.22-SURFACING)(14CCR) | D | NHPP | NH | 2017 | 1900000 | 1900000 | NO |  |  |  | 0
[6 empty] | RUSSELL | 8-8601.21 | US 127 | 2.52 |  |  | RELIABILITY | RELOCATION(O) | RELOCATE US 127 FR APPROX .36 MI E OF INTERSECTION KY 1730 & MANNTOWN RD EXTEND N TO N BANK OF CUMBERLAND RIVER INCLUDING NEW BRIDGE OVER LAKE CUMBERLAND FR CLINTON CO TO RUSSELL CO(SEE 8-108&8-115 FOR PE&ENV)(12CCR)(SEE 8-8601.22-SURFACING)(14CCR) | R | NHPP | NH | 2017 | 2100000 | 2100000 | NO |  |  |  | 0
[6 empty] | RUSSELL | 8-8601.21 | US 127 | 2.52 |  |  | RELIABILITY | RELOCATION(O) | RELOCATE US 127 FR APPROX .36 MI E OF INTERSECTION KY 1730 & MANNTOWN RD EXTEND N TO N BANK OF CUMBERLAND RIVER INCLUDING NEW BRIDGE OVER LAKE CUMBERLAND FR CLINTON CO TO RUSSELL CO(SEE 8-108&8-115 FOR PE&ENV)(12CCR)(SEE 8-8601.22-SURFACING)(14CCR) | U | NHPP | NH | 2017 | 810000 | 810000 | NO |  |  |  | 0
[6 empty] | RUSSELL | 8-8601.21 | US 127 | 2.52 |  |  | RELIABILITY | RELOCATION(O) | RELOCATE US 127 FR APPROX .36 MI E OF INTERSECTION KY 1730 & MANNTOWN RD EXTEND N TO N BANK OF CUMBERLAND RIVER INCLUDING NEW BRIDGE OVER LAKE CUMBERLAND FR CLINTON CO TO RUSSELL CO(SEE 8-108&8-115 FOR PE&ENV)(12CCR)(SEE 8-8601.22-SURFACING)(14CCR) | C | NHPP | NH | 2018 | 10880000 | 10880000 | NO |  |  |  | 0
[6 empty] | RUSSELL | 8-8601.22 | US 127 | 2.52 |  |  | RELIABILITY | PREFINANCD CONVRSN(O) | RECONSTRUCT US 127 FR APPROX .36 MI E OF INTERSECTION KY 1730 & MANNTOWN RD EXTEND N TO N BANK OF CUMBERLAND RIVER INCLUDE NEW BRIDGE OVER LAKE CUMBERLAND FR CLINTON CO TO RUSSELL CO(SEE 8-108&8-115 FOR PE&ENV) (ADDITIONAL C-FUNDS FOR 8-8601.21)(16CCR) | C | NHPP | NH | 2019 | 15000000 | 15000000 | YES |  |  |  | 0
[6 empty] | SCOTT | 7-102.5 |  | 4.7 |  |  | RELIABILITY | BYPASS(O) | GEORGETOWN NORTHWEST BYPASS; FROM KY-32, EAST TO I-75. (04CCR)(2004BOPC)(SEE 7-102.01 FOR "HPP" COMPONENT)(10CCR)(12CCR)(16CCR) | U | STP | STP | 2017 | 3540000 | 3540000 | NO |  |  |  | 0
[6 empty] | SCOTT | 7-102.5 |  | 4.7 |  |  | RELIABILITY | BYPASS(O) | GEORGETOWN NORTHWEST BYPASS; FROM KY-32, EAST TO I-75. (04CCR)(2004BOPC)(SEE 7-102.01 FOR "HPP" COMPONENT)(10CCR)(12CCR)(16CCR) | C | STP | STP | 2018 | 14710000 | 14710000 | NO |  |  |  | 0
[6 empty] | SCOTT | 7-1127 | KY 1689 | 0.04 | 1.801 | 1.841 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 1689 OVER LECOMPTES RUN 0.46 MILE W OF KY 227(SR 9.4) 105B00038N | R | STP | BRX | 2017 | 60000 | 60000 | NO |  |  |  | 0
[6 empty] | SCOTT | 7-1127 | KY 1689 | 0.04 | 1.801 | 1.841 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 1689 OVER LECOMPTES RUN 0.46 MILE W OF KY 227(SR 9.4) 105B00038N | U | STP | BRX | 2017 | 60000 | 60000 | NO |  |  |  | 0
[6 empty] | SCOTT | 7-1127 | KY 1689 | 0.04 | 1.801 | 1.841 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 1689 OVER LECOMPTES RUN 0.46 MILE W OF KY 227(SR 9.4) 105B00038N | C | STP | BRX | 2018 | 600000 | 600000 | NO |  |  |  | 0
[6 empty] | SCOTT | 7-1139 | CR 1022 | 0.02 | 1.19 | 1.21 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER NS (CNO&TP)RR ON FIELDS ROAD (CR 1022) AT SCOTT/HARRISON CO LINE (105R00607N)(SR=28.8) (EBRP) | D | STP | BRZ | 2018 | 300000 | 300000 | NO |  |  |  | 0
[6 empty] | SCOTT | 7-1139 | CR 1022 | 0.02 | 1.19 | 1.21 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER NS (CNO&TP)RR ON FIELDS ROAD (CR 1022) AT SCOTT/HARRISON CO LINE (105R00607N)(SR=28.8) (EBRP) | R | STP | BRZ | 2019 | 100000 | 100000 | NO |  |  |  | 0
[6 empty] | SCOTT | 7-1139 | CR 1022 | 0.02 | 1.19 | 1.21 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER NS (CNO&TP)RR ON FIELDS ROAD (CR 1022) AT SCOTT/HARRISON CO LINE (105R00607N)(SR=28.8) (EBRP) | U | STP | BRZ | 2019 | 250000 | 250000 | NO |  |  |  | 0
[6 empty] | SCOTT | 7-1139 | CR 1022 | 0.02 | 1.19 | 1.21 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER NS (CNO&TP)RR ON FIELDS ROAD (CR 1022) AT SCOTT/HARRISON CO LINE (105R00607N)(SR=28.8) (EBRP) | C | STP | BRZ | 2020 | 1250000 | 1250000 | NO |  |  |  | 0
[6 empty] | SCOTT | 7-8907 | KY 227 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT KY-227 FROM MP 2.98 TO MP 3.34 TO IMPROVE HORIZONTAL CURVE. (16CCN) | D | STP | STP | 2017 | 225000 | 225000 | NO |  |  |  | 0
[6 empty] | SCOTT | 7-8907 | KY 227 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT KY-227 FROM MP 2.98 TO MP 3.34 TO IMPROVE HORIZONTAL CURVE. (16CCN) | R | STP | STP | 2018 | 225000 | 225000 | NO |  |  |  | 0
[6 empty] | SCOTT | 7-8907 | KY 227 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT KY-227 FROM MP 2.98 TO MP 3.34 TO IMPROVE HORIZONTAL CURVE. (16CCN) | U | STP | STP | 2018 | 325000 | 325000 | NO |  |  |  | 0
[6 empty] | SCOTT | 7-8907 | KY 227 |  |  |  | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT KY-227 FROM MP 2.98 TO MP 3.34 TO IMPROVE HORIZONTAL CURVE. (16CCN) | C | STP | STP | 2019 | 1250000 | 1250000 | NO |  |  |  | 0
[6 empty] | SHELBY | 5-1069 | CR 1036 |  | 0.462 | 0.502 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON SCRABBLE RD (CR 1036) OVER BACKBONE CREEK 0.47 MILE E OF CEDARMORE RD (KY 1922)(SR 44.2) 106C00055N | C | STP | BRZ | 2018 | 450000 | 450000 | NO |  |  |  | 0
[6 empty] | SHELBY | 5-8511 | KY 53 | 1.9 | 6.064 | 8.006 | RELIABILITY | RECONSTRUCTION(O) | WIDEN KY-53 TO FOUR LANES FROM I-64 TO US-60. (08CCN)(10CCN)(12CCR)(14CCR)(16CCR) | C | STP | STP | 2019 | 11290000 | 11290000 | NO |  |  |  | 0
[6 empty] | SPENCER | 5-1076 | KY 1169 |  | 8.53 | 8.552 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER BUCK CREEK ON KY 1169 75 FT EAST OF YODER TIPTON ROAD (CR 1142). (108B00022N)(SR=45.6)(EBRP) | D | STP | BRX | 2020 | 350000 | 350000 | NO |  |  |  | 0
[6 empty] | SPENCER | 5-1080 | KY 2885 |  | 2.629 | 2.635 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER SIMPSON CREEK ON KY 2885 (WEST RIVER ROAD) AT JCT WITH NETHERTON LANE (CR 1082) 3-TON WEIGHT LIMIT (SR=2)(108B00041N) | R | STP | BRX | 2017 | 100000 | 100000 | NO |  |  |  | 0
[6 empty] | SPENCER | 5-1080 | KY 2885 |  | 2.629 | 2.635 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER SIMPSON CREEK ON KY 2885 (WEST RIVER ROAD) AT JCT WITH NETHERTON LANE (CR 1082) 3-TON WEIGHT LIMIT (SR=2)(108B00041N) | U | STP | BRX | 2017 | 50000 | 50000 | NO |  |  |  | 0
[6 empty] | SPENCER | 5-1080 | KY 2885 |  | 2.629 | 2.635 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER SIMPSON CREEK ON KY 2885 (WEST RIVER ROAD) AT JCT WITH NETHERTON LANE (CR 1082) 3-TON WEIGHT LIMIT (SR=2)(108B00041N) | C | STP | BRX | 2017 | 500000 | 500000 | NO |  |  |  | 0
[6 empty] | TAYLOR | 4-142.2 | KY 555 |  |  |  | RELIABILITY | NEW ROUTE(O) | HEARTLAND PARKWAY; CAMPBELLSVILLE BYPASS FROM KY-55 SOUTH TO KY-70. (2010BOP)(14CCR)(16CCR) | U | NHPP | NH | 2017 | 1000000 | 1000000 | NO |  |  |  | 0
[6 empty] | TAYLOR | 4-142.2 | KY 555 |  |  |  | RELIABILITY | NEW ROUTE(O) | HEARTLAND PARKWAY; CAMPBELLSVILLE BYPASS FROM KY-55 SOUTH TO KY-70. (2010BOP)(14CCR)(16CCR) | C | NHPP | NH | 2019 | 15190000 | 15190000 | NO |  |  |  | 0
[6 empty] | TAYLOR | 4-142.3 | KY 555 |  |  |  | RELIABILITY | NEW ROUTE(O) | HEARTLAND PARKWAY; CAMPBELLSVILLE BYPASS FROM KY-70 TO US-68 EAST OF CAMPBELLSVILLE. (2010BOP)(16CCR) | R | STP | STP | 2019 | 4920000 | 4920000 | NO |  |  |  | 0
[6 empty] | TAYLOR | 4-142.3 | KY 555 |  |  |  | RELIABILITY | NEW ROUTE(O) | HEARTLAND PARKWAY; CAMPBELLSVILLE BYPASS FROM KY-70 TO US-68 EAST OF CAMPBELLSVILLE. (2010BOP)(16CCR) | U | STP | STP | 2019 | 500000 | 500000 | NO |  |  |  | 0
[6 empty] | TAYLOR | 4-142.3 | KY 555 |  |  |  | RELIABILITY | NEW ROUTE(O) | HEARTLAND PARKWAY; CAMPBELLSVILLE BYPASS FROM KY-70 TO US-68 EAST OF CAMPBELLSVILLE. (2010BOP)(16CCR) | C | STP | STP | 2020 | 10770000 | 10770000 | YES |  |  |  | 0
[6 empty] | TAYLOR | 4-8920 | KY 55 |  | 0 | 8.003 | RELIABILITY | RECONSTRUCTION(O) | CONSTRUCT 2 LANES WITH PASSING LANE TO CONTINUE ROUTE FROM ADAIR/TAYLOR COUNTY LINE TO CAMPBELLSVILLE BYPASS. MP 0.00 TO MP 8.003. (16CCN) | D | NHPP | NH | 2018 | 500000 | 500000 | NO |  |  |  | 0
[6 empty] | TAYLOR | 4-8920 | KY 55 |  | 0 | 8.003 | RELIABILITY | RECONSTRUCTION(O) | CONSTRUCT 2 LANES WITH PASSING LANE TO CONTINUE ROUTE FROM ADAIR/TAYLOR COUNTY LINE TO CAMPBELLSVILLE BYPASS. MP 0.00 TO MP 8.003. (16CCN) | R | NHPP | NH | 2019 | 1000000 | 1000000 | NO |  |  |  | 0
[6 empty] | TAYLOR | 4-8920 | KY 55 |  | 0 | 8.003 | RELIABILITY | RECONSTRUCTION(O) | CONSTRUCT 2 LANES WITH PASSING LANE TO CONTINUE ROUTE FROM ADAIR/TAYLOR COUNTY LINE TO CAMPBELLSVILLE BYPASS. MP 0.00 TO MP 8.003. (16CCN) | U | NHPP | NH | 2020 | 1000000 | 1000000 | NO |  |  |  | 0
[6 empty] | TRIMBLE | 5-135.81 | US 421 | 0.6 | 18.776 | 19.198 | RELIABILITY | BRIDGE REPLACEMENT(P) | NEW MILTON-MADISON BRIDGE APPROACHES TO REALIGN US 421 AT BOTTOM OF HILL AT NEW BRIDGE LOCATION. | C | NHPP | BRO | 2017 | 870000 | 870000 | NO |  |  |  | 0
[6 empty] | TRIMBLE | 5-905 | US 421 | 0.04 | 11.278 | 11.678 | SAFETY | SAFETY(P) | ADDRESS SAFETY ISSUES AND ACCESS AT THE INTERSECTION OF US-421/KY-1226 AT MP 11.5. (12CCR) | R | STP | STP | 2017 | 320000 | 320000 | NO |  |  |  | 0
[6 empty] | TRIMBLE | 5-905 | US 421 | 0.04 | 11.278 | 11.678 | SAFETY | SAFETY(P) | ADDRESS SAFETY ISSUES AND ACCESS AT THE INTERSECTION OF US-421/KY-1226 AT MP 11.5. (12CCR) | U | STP | STP | 2017 | 260000 | 260000 | NO |  |  |  | 0
[6 empty] | TRIMBLE | 5-905 | US 421 | 0.04 | 11.278 | 11.678 | SAFETY | SAFETY(P) | ADDRESS SAFETY ISSUES AND ACCESS AT THE INTERSECTION OF US-421/KY-1226 AT MP 11.5. (12CCR) | C | STP | STP | 2017 | 830000 | 830000 | NO |  |  |  | 0
[6 empty] | TRIMBLE | 5-1075 | KY 2871 | 0.04 | 0.228 | 0.268 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER LITTLE KENTUCKY RIVER ON KY 2871 150 FT NW OF KY 1335. (112B00029N) (SR=46.2)(14CCR)(16CCR) | R | STP | BRX | 2017 | 10000 | 10000 | NO |  |  |  | 0
[6 empty] | TRIMBLE | 5-1075 | KY 2871 | 0.04 | 0.228 | 0.268 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER LITTLE KENTUCKY RIVER ON KY 2871 150 FT NW OF KY 1335. (112B00029N) (SR=46.2)(14CCR)(16CCR) | U | STP | BRX | 2017 | 24000 | 24000 | NO |  |  |  | 0
[6 empty] | TRIMBLE | 5-1075 | KY 2871 | 0.04 | 0.228 | 0.268 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER LITTLE KENTUCKY RIVER ON KY 2871 150 FT NW OF KY 1335. (112B00029N) (SR=46.2)(14CCR)(16CCR) | C | STP | BRX | 2018 | 1300000 | 1300000 | NO |  |  |  | 0
[6 empty] | UNION | 2-1073 | KY 359 | 0.1 | 0.921 | 1.021 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-359 (MP 0.971) OVER LOST CREEK; .95 MI N.E. OF JCT US-60; (FUNCTIONALLY OBSOLETE, SR=34.5) 113B00006N (LET W/ 2-1074) | C | NHPP | BRO | 2017 | 570000 | 570000 | NO |  |  |  | 0
[6 empty] | UNION | 2-1074 | KY 359 | 0.1 | 1.143 | 1.243 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-359 (MP 1.193) OVER SINKING CREEK; 1.1 MI N.E. OF JCT US-60; (FUNCTIONALLY OBSOLETE, SR=12.6) 113B00007N (LET W/ 2-1073) | C | NHPP | BRO | 2017 | 570000 | 570000 | NO |  |  |  | 0
[6 empty] | WARREN | 3-16.05 | I 65 |  |  |  | RELIABILITY | PREFINANCD CONVRSN(O) | CONSTRUCTION OF NEW I-65 INTERCHANGE IN WARREN COUNTY. (SURFACING ONLY, SEE 16.03 FOR G&D) (SEE 3-16.00 FOR STP COMPONENT) (ADDITIONAL C-FUNDS FOR 3-16.04) | C | NHPP | IM | 2017 | 6000000 | 6000000 | NO |  |  |  | 0
[6 empty] | WARREN | 3-202 | WN 9007 | 0.2 | 9.4 | 9.6 | SAFETY | SAFETY(P) | RECONSTRUCT THE EXISTING NATCHER PARKWAY/US 231 INTERCHANGE ON WEST SIDE OF BOWLING GREEN. (12CCR) | D | NHPP | NH | 2017 | 1250000 | 1250000 | NO |  |  |  | 0
[6 empty] | WARREN | 3-202 | WN 9007 | 0.2 | 9.4 | 9.6 | SAFETY | SAFETY(P) | RECONSTRUCT THE EXISTING NATCHER PARKWAY/US 231 INTERCHANGE ON WEST SIDE OF BOWLING GREEN. (12CCR) | R | NHPP | NH | 2019 | 1740000 | 1740000 | NO |  |  |  | 0
[6 empty] | WARREN | 3-202 | WN 9007 | 0.2 | 9.4 | 9.6 | SAFETY | SAFETY(P) | RECONSTRUCT THE EXISTING NATCHER PARKWAY/US 231 INTERCHANGE ON WEST SIDE OF BOWLING GREEN. (12CCR) | U | NHPP | NH | 2019 | 1690000 | 1690000 | NO |  |  |  | 0
[6 empty] | WARREN | 3-1077 | KY 234 | 0.06 | 9.746 | 9.806 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY-234 OVER DRAKES CREEK 0.097 E OF SHAKER MILL RD (CR-1131) (SR 42.8) 114B00012N. | C | NHPP | BRO | 2018 | 5850000 | 5850000 | NO |  |  |  | 0
[6 empty] | WARREN | 3-8707 | WN 9007 | 0.6 | 3.4 | 4 | RELIABILITY | NEW INTERCHANGE(O) | CONSTRUCT A NEW INTERCHANGE ON THE NATCHER PARKWAY AT ELROD ROAD IN BOWLING GREEN (MP 3.4 TO MP 4.0).(12CCN) | D | NHPP | NH | 2019 | 800000 | 800000 | NO |  |  |  | 0
[6 empty] | WASHINGTON | 4-1094 | KY 528 |  | 1.433 | 1.441 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON KY 528 (MP 1.437) OVER ROAD RUN BRANCH. (SD,SR=46.6)(115B00043N) | D | STP | BRX | 2020 | 150000 | 150000 | NO |  |  |  | 0
[6 empty] | WASHINGTON | 4-8956 | CR 1140 |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON TEXAS-MACKVILLE ROAD (CR 1140) OVER PRATHER CREEK. (16CCN) | C | STP | BRX | 2018 | 175000 | 175000 | NO |  |  |  | 0
[6 empty] | WASHINGTON | 4-8957 | CR 1140 |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON TEXAS-MACKVILLE ROAD (CR 1140) AT MP 0.349 OVER LONG LICK CREEK. (16CCN) | C | STP | BRX | 2017 | 175000 | 175000 | NO |  |  |  | 0
[6 empty] | WAYNE | 8-1050 | CR 1136 | 0.1 | 0.175 | 0.275 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON CR-1136 (MP 0.225) OVER LITTLE SOUTH FORK RIVER; 0.25 MI SE OF JCT CR-5137; (STRUCTURALLY DEFICIENT, SR=16.6) 116C00007N | U | STP | BRZ | 2017 | 80000 | 80000 | NO |  |  |  | 0
[6 empty] | WAYNE | 8-1050 | CR 1136 | 0.1 | 0.175 | 0.275 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE ON CR-1136 (MP 0.225) OVER LITTLE SOUTH FORK RIVER; 0.25 MI SE OF JCT CR-5137; (STRUCTURALLY DEFICIENT, SR=16.6) 116C00007N | C | STP | BRZ | 2017 | 570000 | 570000 | NO |  |  |  | 0
[6 empty] | WHITLEY | 11-1105 | I 75 |  | 27.85 | 27.95 | RELIABILITY | BRIDGE REHAB(P) | REHAB BRIDGE ON I-75 AT MILEPOINT 27.9 OVER LYNN CAMP CREEK (SR 34.1) (B00063R AND B00063L) | C | NHPP | BRO | 2017 | 4000000 | 4000000 | NO |  |  |  | 0
[6 empty] | WOLFE | 10-126.7 | KY 9009 | 2.5 | 56.8 | 57.72 | RELIABILITY | MAJOR WIDENING(O) | MOUNTAIN PARKWAY CORRIDOR: WIDEN THE MOUNTAIN PARKWAY TO 4 LANES FROM 0.45 MI W OF KY 205 (MP 56.8) TO CR 1226 PARKWAY ROAD TUNNEL (MP 59.30). (2012BOP)(14CCR)(16CCR) | U | NHPP | NH | 2017 | 2400000 | 2400000 | NO |  |  |  | 0
[6 empty] | WOLFE | 10-126.7 | KY 9009 | 2.5 | 56.8 | 57.72 | RELIABILITY | MAJOR WIDENING(O) | MOUNTAIN PARKWAY CORRIDOR: WIDEN THE MOUNTAIN PARKWAY TO 4 LANES FROM 0.45 MI W OF KY 205 (MP 56.8) TO CR 1226 PARKWAY ROAD TUNNEL (MP 59.30). (2012BOP)(14CCR)(16CCR) | C | NHPP | NH | 2018 | 18670000 | 18670000 | NO |  |  |  | 0
[6 empty] | WOLFE | 10-126.71 | KY 9009 | 2.5 | 56.8 | 57.72 | RELIABILITY | PREFINANCD CONVRSN(O) | MOUNTAIN PARKWAY CORRIDOR: WIDEN THE MOUNTAIN PARKWAY TO 4 LANES FROM 0.45 MI W OF KY 205 (MP 56.8) TO CR 1226 PARKWAY ROAD TUNNEL (MP 59.30). (ADDITIONAL C-FUNDS FOR 10-126.70)(16CCR) | C | NHPP | NH | 2018 | 8000000 | 8000000 | NO |  |  |  | 0
[6 empty] | WOLFE | 10-126.72 | KY 9009 |  | 56.8 | 59.3 | RELIABILITY | PREFINANCD CONVRSN(O) | MOUNTAIN PARKWAY CORRIDOR: WIDEN THE MOUNTAIN PARKWAY TO 4 LANES FROM 0.45 MI W OF KY 205 (MP 56.8) TO CR 1226 PARKWAY ROAD TUNNEL (MP 59.30). (ADDITIONAL C-FUNDS FOR 10-126.70)(16CCN) | C | NHPP | NH | 2018 | 8000000 | 8000000 | NO |  |  |  | 0
[6 empty] | WOLFE | 10-168.1 | KY 9009 | 11 | 45.8 | 56.8 | RELIABILITY | MAJOR WIDENING(O) | MOUNTAIN PARKWAY CORRIDOR: WIDEN THE MTN PKY TO 4 LANES FROM 0.6 MI W OF KY 191 OVERPASS TO 0.45 MI W OF KY 205 INTERCHANGE. (SEE 10-126.03 FOR PE & ENVIR FUNDS)(2012BOP)(14CCN)(ADDITIONAL FUNDS FOR 10-168.00)(16CCR) | D | NHPP | NH | 2017 | 5200000 | 5200000 | NO |  |  |  | 0
[6 empty] | WOLFE | 10-168.1 | KY 9009 | 11 | 45.8 | 56.8 | RELIABILITY | MAJOR WIDENING(O) | MOUNTAIN PARKWAY CORRIDOR: WIDEN THE MTN PKY TO 4 LANES FROM 0.6 MI W OF KY 191 OVERPASS TO 0.45 MI W OF KY 205 INTERCHANGE. (SEE 10-126.03 FOR PE & ENVIR FUNDS)(2012BOP)(14CCN)(ADDITIONAL FUNDS FOR 10-168.00)(16CCR) | R | NHPP | NH | 2018 | 5000000 | 5000000 | NO |  |  |  | 0
[6 empty] | WOODFORD | 7-1140 | CR 1217 | 0.03 | 1.15 | 1.18 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER GRIER CREEK ON GRIER CREEK ROAD (CR 1217) 0.8 MI W OF SCOTTS FERRY ROAD (CR 1215) (120C00017N)(SR=31.5) | D | STP | BRZ | 2019 | 325000 | 325000 | NO |  |  |  | 0
[6 empty] | WOODFORD | 7-1140 | CR 1217 | 0.03 | 1.15 | 1.18 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER GRIER CREEK ON GRIER CREEK ROAD (CR 1217) 0.8 MI W OF SCOTTS FERRY ROAD (CR 1215) (120C00017N)(SR=31.5) | R | STP | BRZ | 2020 | 50000 | 50000 | NO |  |  |  | 0
[6 empty] | WOODFORD | 7-1140 | CR 1217 | 0.03 | 1.15 | 1.18 | RELIABILITY | BRIDGE REPLACEMENT(P) | REPLACE BRIDGE OVER GRIER CREEK ON GRIER CREEK ROAD (CR 1217) 0.8 MI W OF SCOTTS FERRY ROAD (CR 1215) (120C00017N)(SR=31.5) | U | STP | BRZ | 2020 | 100000 | 100000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-65.13 |  |  |  |  | RELIABILITY | BRIDGE REHAB(P) | BRIDGE REPAIRS ON VARIOUS BRIDGES ON THE NHS FOR FY 2016. (2009BOPP) | C | NHPP | IM | 2017 | 3500000 | 3500000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-65.14 |  |  |  |  | RELIABILITY | BRIDGE REHAB(P) | BRIDGE REPAIRS ON VARIOUS BRIDGES ON THE NHS FOR FY 2017. (2009BOPP) | C | NHPP | IM | 2017 | 3700000 | 3700000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-65.15 |  |  |  |  | RELIABILITY | BRIDGE REHAB(P) | BRIDGE REPAIRS ON VARIOUS BRIDGES ON THE NHS FOR FY 2018. (2009BOPP) | C | NHPP | IM | 2018 | 3800000 | 3800000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-65.16 |  |  |  |  | RELIABILITY | BRIDGE REHAB(P) | BRIDGE REPAIRS ON VARIOUS BRIDGES ON THE NHS FOR FY 2019. | C | NHPP | IM | 2019 | 3800000 | 3800000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-65.17 |  |  |  |  | RELIABILITY | BRIDGE REHAB(P) | BRIDGE REPAIRS ON VARIOUS BRIDGES ON THE NHS FOR FY 2020. | C | NHPP | IM | 2020 | 3800000 | 3800000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-66.11 |  |  |  |  | RELIABILITY | ITS(P) | 'ITS' ACTIVITIES ON VARIOUS NHS ROUTES IN KENTUCKY FOR FY 2016. | C | NHPP | NH | 2017 | 2000000 | 2000000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-66.12 |  |  |  |  | RELIABILITY | ITS(P) | 'ITS' ACTIVITIES ON VARIOUS NHS ROUTES IN KENTUCKY FOR FY 2017. | C | NHPP | NH | 2017 | 2000000 | 2000000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-66.13 |  |  |  |  | RELIABILITY | ITS(P) | 'ITS' ACTIVITIES ON VARIOUS NHS ROUTES IN KENTUCKY FOR FY 2018. | C | NHPP | NH | 2018 | 2000000 | 2000000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-66.14 |  |  |  |  | RELIABILITY | ITS(P) | 'ITS' ACTIVITIES ON VARIOUS NHS ROUTES IN KENTUCKY FOR FY 2019. | C | NHPP | NH | 2019 | 2000000 | 2000000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-66.15 |  |  |  |  | RELIABILITY | ITS(P) | 'ITS' ACTIVITIES ON VARIOUS NHS ROUTES IN KENTUCKY FOR FY 2020. | C | NHPP | NH | 2020 | 2000000 | 2000000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-195.12 |  |  |  |  | RELIABILITY | TRANSP ENHANCEMENT(P) | STATEWIDE TRANSPORTATION ENHANCEMENT (98CCR) | C | TE | TE | 2017 | 14500000 | 11600000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-195.13 |  |  |  |  | RELIABILITY | TRANSP ENHANCEMENT(P) | STATEWIDE TRANSPORTATION ENHANCEMENT (98CCR) | C | TE | TE | 2017 | 16700000 | 13360000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-195.14 |  |  |  |  | RELIABILITY | TRANSP ENHANCEMENT(P) | STATEWIDE TRANSPORTATION ENHANCEMENT FOR FY 2012. (98CCR) | C | TE | TE | 2018 | 17000000 | 13600000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-195.15 |  |  |  |  | RELIABILITY | TRANSP ENHANCEMENT(P) | STATEWIDE TRANSPORTATION ENHANCEMENT FOR FY 2013. (98CCR) | C | TE | TE | 2019 | 17400000 | 13920000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-195.16 |  |  |  |  | RELIABILITY | TRANSP ENHANCEMENT(P) | STATEWIDE TRANSPORTATION ENHANCEMENT FOR FY 2014 (98CCR) | C | TE | TE | 2020 | 11600000 | 9280000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-219.14 |  |  |  |  | RELIABILITY | CONGESTION MITIGTN(O) | NON-ATTAINMENT AREAS STATEWIDE CMAQ FUNDED PROJECTS FOR FY 2016. | C | CM | CM | 2017 | 15000000 | 12000000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-219.15 |  |  |  |  | RELIABILITY | CONGESTION MITIGTN(O) | NON-ATTAINMENT AREAS STATEWIDE CMAQ FUNDED PROJECTS FOR FY 2017. | C | CM | CM | 2017 | 16700000 | 13360000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-219.16 |  |  |  |  | RELIABILITY | CONGESTION MITIGTN(O) | NON-ATTAINMENT AREAS STATEWIDE CMAQ FUNDED PROJECTS FOR FY 2018. | C | CM | CM | 2018 | 17000000 | 13600000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-219.17 |  |  |  |  | RELIABILITY | CONGESTION MITIGTN(O) | NON-ATTAINMENT AREAS STATEWIDE CMAQ FUNDED PROJECTS FOR FY 2019. | C | CM | CM | 2019 | 17400000 | 13920000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-219.18 |  |  |  |  | RELIABILITY | CONGESTION MITIGTN(O) | NON-ATTAINMENT AREAS STATEWIDE CMAQ FUNDED PROJECTS FOR FY 2020. | C | CM | CM | 2020 | 14300000 | 11440000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-224.12 |  |  |  |  | RELIABILITY | PAVEMENT REHAB-PRI(P) | PAVEMENT REHAB ON STATE (NON RS) SYSTEM ROUTES IN KENTUCKY FOR FY 2016.(16CCR) | C | STP | STP | 2017 | 5000000 | 5000000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-224.13 |  |  |  |  | RELIABILITY | PAVEMENT REHAB-PRI(P) | PAVEMENT REHAB ON STATE (NON RS) SYSTEM ROUTES IN KENTUCKY FOR FY 2019. | C | STP | STP | 2019 | 10000000 | 10000000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-327.13 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | STATEWIDE BRIDGE INSPECTION FOR FY 2017 | C | NHPP | BRO | 2017 | 2500000 | 2500000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-327.14 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | STATEWIDE BRIDGE INSPECTION FOR FY 2018. | C | NHPP | BRO | 2018 | 2600000 | 2600000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-327.15 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | STATEWIDE BRIDGE INSPECTION FOR FY 2019. | C | NHPP | BRO | 2019 | 2600000 | 2600000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-327.16 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | STATEWIDE BRIDGE INSPECTION FOR FY 2020. | C | NHPP | BRO | 2020 | 2600000 | 2600000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-333.12 |  |  |  |  | RELIABILITY | FOREST HIGHWAY(P) | STATEWIDE FEDERAL LANDS ACCESS PROGRAM FEDERAL HIGHWAY FUNDS FOR FY 2016. | C | FH | FH | 2017 | 1641000 | 1641000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-333.13 |  |  |  |  | RELIABILITY | FOREST HIGHWAY(P) | STATEWIDE FEDERAL LANDS ACCESS PROGRAM FEDERAL HIGHWAY FUNDS FOR FY 2017. | C | FH | FH | 2017 | 1641000 | 1641000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-333.14 |  |  |  |  | RELIABILITY | FOREST HIGHWAY(P) | STATEWIDE FEDERAL LANDS ACCESS PROGRAM FEDERAL HIGHWAY FUNDS FOR FY 2018. | C | FH | FH | 2018 | 1641000 | 1641000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-333.15 |  |  |  |  | RELIABILITY | FOREST HIGHWAY(P) | STATEWIDE FEDERAL LANDS ACCESS PROGRAM FEDERAL HIGHWAY FUNDS FOR FY 2019. | C | FH | FH | 2019 | 1641000 | 1641000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-333.16 |  |  |  |  | RELIABILITY | FOREST HIGHWAY(P) | STATEWIDE FEDERAL LANDS ACCESS PROGRAM FEDERAL HIGHWAY FUNDS FOR FY 2020. | C | FH | FH | 2020 | 1641000 | 1641000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-337.11 |  |  |  |  | RELIABILITY | PAVEMENT REHAB-INT(P) | STATEWIDE I-STATE ROUTES FOR FY 2016. (12CCR)(16CCR) | C | NHPP | IM | 2017 | 5000000 | 5000000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-337.12 |  |  |  |  | RELIABILITY | PAVEMENT REHAB-INT(P) | STATEWIDE I-STATE ROUTES FOR FY 2017. (12CCR)(16CCR) | C | NHPP | IM | 2017 | 5000000 | 5000000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-337.13 |  |  |  |  | RELIABILITY | PAVEMENT REHAB-INT(P) | STATEWIDE I-STATE ROUTES FOR FY 2018. (12CCR)(16CCR) | C | NHPP | IM | 2018 | 5000000 | 5000000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-337.14 |  |  |  |  | RELIABILITY | PAVEMENT REHAB-INT(P) | STATEWIDE I-STATE ROUTES FOR FY 2019.(14CCR) | C | NHPP | IM | 2019 | 40000000 | 40000000 | YES |  |  |  | 0
[6 empty] | ZVARIOUS | 99-337.15 |  |  |  |  | RELIABILITY | PAVEMENT REHAB-INT(P) | STATEWIDE I-STATE ROUTES FOR FY 2020.(14CCR) | C | NHPP | IM | 2020 | 12000000 | 12000000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-346.12 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | STATEWIDE OFF-SYSTEM BRIDGE INSPECTION FOR FY 2016 | C | STP | BRZ | 2017 | 900000 | 900000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-346.13 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | STATEWIDE OFF-SYSTEM BRIDGE INSPECTION FOR FY 2017 | C | STP | BRZ | 2017 | 1000000 | 1000000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-346.14 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | STATEWIDE OFF-SYSTEM BRIDGE INSPECTION FOR FY 2018 | C | STP | BRZ | 2018 | 1100000 | 1100000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-346.15 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | STATEWIDE OFF-SYSTEM BRIDGE INSPECTION FOR FY 2019. | C | STP | BRZ | 2019 | 1100000 | 1100000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-346.16 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | STATEWIDE OFF-SYSTEM BRIDGE INSPECTION FOR FY 2020. | C | STP | BRZ | 2020 | 1100000 | 1100000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-352.12 |  |  |  |  | SAFETY | SAFETY-RR SEPARATN(P) | RAIL PROTECTION ON VARIOUS ROUTES FOR FY 2016. | C | RRP | RRP | 2017 | 3800000 | 3800000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-352.13 |  |  |  |  | SAFETY | SAFETY-RR SEPARATN(P) | RAIL PROTECTION ON VARIOUS ROUTES FOR FY 2017. | C | RRP | RRP | 2017 | 3800000 | 3800000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-352.14 |  |  |  |  | SAFETY | SAFETY-RR PROTECTN(P) | RAIL PROTECTION ON VARIOUS ROUTES FOR FY 2018. | C | RRP | RRP | 2018 | 3800000 | 3800000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-352.15 |  |  |  |  | SAFETY | SAFETY-RR PROTECTN(P) | RAIL PROTECTION ON VARIOUS ROUTES FOR FY 2019. | C | RRP | RRP | 2019 | 4000000 | 4000000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-352.16 |  |  |  |  | SAFETY | SAFETY-RR PROTECTN(P) | RAIL PROTECTION ON VARIOUS ROUTES FOR FY 2020. | C | RRP | RRP | 2020 | 4200000 | 4200000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-369.06 |  |  |  |  | RELIABILITY | PAVEMENT REHAB-PRI(P) | PAVEMENT REHABILITATION FOR VARIOUS NHS ROUTES IN KENTUCKY FOR FY 2016.(14CCR)(16CCR) | C | NHPP | NH | 2017 | 5000000 | 5000000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-369.07 |  |  |  |  | RELIABILITY | PAVEMENT REHAB-PRI(P) | PAVEMENT REHABILITATION FOR VARIOUS NHS ROUTES IN KENTUCKY FOR FY 2017. (16CCR) | C | NHPP | NH | 2017 | 5000000 | 5000000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-369.08 |  |  |  |  | RELIABILITY | PAVEMENT REHAB-PRI(P) | PAVEMENT REHABILITATION FOR VARIOUS NHS ROUTES IN KENTUCKY FOR FY 2018. (16CCR) | C | NHPP | NH | 2018 | 5000000 | 5000000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-369.09 |  |  |  |  | RELIABILITY | PAVEMENT REHAB-PRI(P) | PAVEMENT REHABILITATION FOR VARIOUS NHS ROUTES IN KENTUCKY FOR FY 2019. | C | NHPP | NH | 2019 | 20000000 | 20000000 | YES |  |  |  | 0
[6 empty] | ZVARIOUS | 99-369.1 |  |  |  |  | RELIABILITY | PAVEMENT REHAB-PRI(P) | PAVEMENT REHABILITATION FOR VARIOUS NHS ROUTES IN KENTUCKY FOR FY 2020. | C | NHPP | NH | 2020 | 25000000 | 25000000 | YES |  |  |  | 0
[6 empty] | ZVARIOUS | 99-388.06 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | OHIO RIVER BRIDGES FRACTURE CRITICAL FOR FY 2016. | C | NHPP | BRO | 2017 | 1200000 | 1200000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-388.07 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | OHIO RIVER BRIDGES FRACTURE CRITICAL FOR FY 2017. | C | NHPP | BRO | 2017 | 1500000 | 1500000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-388.08 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | OHIO RIVER BRIDGES FRACTURE CRITICAL FOR FY 2018. (12CCR) | C | NHPP | BRO | 2018 | 1600000 | 1600000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-388.09 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | OHIO RIVER BRIDGES FRACTURE CRITICAL FOR FY 2019. | C | NHPP | BRO | 2019 | 1600000 | 1600000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-388.1 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | OHIO RIVER BRIDGES FRACTURE CRITICAL FOR FY 2020. | C | NHPP | BRO | 2020 | 1600000 | 1600000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-911.05 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | STATEWIDE SAFETY PROGRAM FOR FY 2016.(HSIP) | C | HSIP | SAF | 2017 | 37000000 | 37000000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-911.06 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | STATEWIDE SAFETY PROGRAM FOR FY 2017. (HSIP)(14CCR) | C | HSIP | SAF | 2017 | 40800000 | 40800000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-911.07 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | STATEWIDE SAFETY PROGRAM FOR FY 2018.(HSIP) | C | HSIP | SAF | 2018 | 41600000 | 41600000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-911.08 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | STATEWIDE SAFETY PROGRAM FOR FY 2019.(HSIP) | C | HSIP | SAF | 2019 | 42300000 | 42300000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-911.09 |  |  |  |  | SAFETY | SAFETY-HAZARD ELIM(P) | STATEWIDE SAFETY PROGRAM FOR FY 2020. (HSIP) | C | HSIP | SAF | 2020 | 45400000 | 45400000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-1063.13 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | STATEWIDE UNDERWATER BRIDGE INSPECTION FOR FY 2017 | C | STP | BRX | 2017 | 500000 | 500000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-1063.14 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | STATEWIDE UNDERWATER BRIDGE INSPECTION FOR FY 2018 | C | STP | BRX | 2018 | 500000 | 500000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-1063.15 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | STATEWIDE UNDERWATER BRIDGE INSPECTION FOR FY 2019. | C | STP | BRX | 2019 | 500000 | 500000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-1063.16 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | STATEWIDE UNDERWATER BRIDGE INSPECTION FOR FY 2020. | C | STP | BRX | 2020 | 500000 | 500000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-1071.04 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | STATEWIDE PROGRAM TO FUND BRIDGE SCOUR COUNTER-MEASURES FOR STATE-MAINTAINED BRIDGES | C | NHPP | BRO | 2017 | 1500000 | 1500000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-1071.05 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | STATEWIDE PROGRAM TO FUND BRIDGE SCOUR COUNTER-MEASURES FOR STATE-MAINTAINED BRIDGES | C | NHPP | BRO | 2017 | 1500000 | 1500000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-1071.07 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | STATEWIDE PROGRAM TO FUND BRIDGE SCOUR COUNTER-MEASURES FOR STATE-MAINTAINED BRIDGES. | C | NHPP | BRO | 2019 | 1500000 | 1500000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-1071.08 |  |  |  |  | SAFETY | BRIDGE INSPECTION(P) | STATEWIDE PROGRAM TO FUND BRIDGE SCOUR COUNTER-MEASURES FOR STATE-MAINTAINED BRIDGES. | C | NHPP | BRO | 2020 | 1500000 | 1500000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-1073.05 |  |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | STATEWIDE "BRO" FUNDS. | C | NHPP | BRO | 2018 | 1000000 | 1000000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-1074.06 |  |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | STATEWIDE OFF SYSTEM BRIDGE REPLACEMENT PROJECTS FOR 2018. | C | STP | BRZ | 2018 | 1000000 | 1000000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-1075.08 |  |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | STATEWIDE "BRX" FUNDS FOR FY 2018. | C | STP | BRX | 2018 | 500000 | 500000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-1083 |  |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | BRO PROJECT ACTIVITY IN 2020. | C | NHPP | BRO | 2020 | 15000000 | 15000000 | YES |  |  |  | 0
[6 empty] | ZVARIOUS | 99-9050.04 |  |  |  |  | RELIABILITY | MAJOR WIDENING(O) | GARVEE BOND DEBT SERVICE FOR I-65; I-75; AND I-64 FOR FY 2016. (JM03-FD53 "IM" COMPONENT) | C | NHPP | IM | 2017 | 17500000 | 17500000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-9050.05 |  |  |  |  | RELIABILITY | MAJOR WIDENING(O) | GARVEE BOND DEBT SERVICE FOR I-65; I-75; AND I-64 FOR FY 2016. (JM03-FD53 "NH" COMPONENT) | C | NHPP | NH | 2017 | 26300000 | 26300000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-9050.06 |  |  |  |  | RELIABILITY | MAJOR WIDENING(O) | GARVEE BOND DEBT SERVICE FOR I-65; I-75; AND I-64 FOR FY 2017. (JM03-FD53 "IM" COMPONENT) | C | NHPP | IM | 2017 | 17500000 | 17500000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-9050.07 |  |  |  |  | RELIABILITY | MAJOR WIDENING(O) | GARVEE BOND DEBT SERVICE FOR I-65; I-75; AND I-64 FOR FY 2017. (JM03-FD53 "NH" COMPONENT) | C | NHPP | NH | 2017 | 26300000 | 26300000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-9050.08 |  |  |  |  | RELIABILITY | MAJOR WIDENING(O) | GARVEE BOND DEBT SERVICE FOR I-65; I-75; AND I-64 FOR FY 2018. (JM03-FD53 "IM" COMPONENT) | C | NHPP | IM | 2018 | 17800000 | 17800000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-9050.09 |  |  |  |  | RELIABILITY | MAJOR WIDENING(O) | GARVEE BOND DEBT SERVICE FOR I-65; I-75; AND I-64 FOR FY 2018. (JM03-FD53 "NH" COMPONENT) | C | NHPP | NH | 2018 | 26700000 | 26700000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-9050.1 |  |  |  |  | RELIABILITY | MAJOR WIDENING(O) | GARVEE BOND DEBT SERVICE FOR I-65; I-75; AND I-64 FOR FY 2019. (JM03-FD53 "IM" COMPONENT) | C | NHPP | IM | 2019 | 17800000 | 17800000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-9050.11 |  |  |  |  | RELIABILITY | MAJOR WIDENING(O) | GARVEE BOND DEBT SERVICE FOR I-65; I-75; AND I-64 FOR FY 2019. (JM03-FD53 "NH" COMPONENT) | C | NHPP | NH | 2019 | 26700000 | 26700000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-9068.01 | US 60 | 0.001 |  |  | SAFETY | BRIDGE REPLACEMENT(P) | US 68/KY 80 LAKE BARKLEY AND KENTUCKY LAKE GARVEE BOND DEBT SERVICE (BRO) FOR FY 2016.(079B00023N, 111B00020N) | C | NHPP | BRO | 2017 | 9100000 | 9100000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-9068.02 | US 68 | 0.001 |  |  | SAFETY | BRIDGE REPLACEMENT(P) | US 68/KY 80 LAKE BARKLEY AND KENTUCKY LAKE GARVEE BOND DEBT SERVICE (BRO) FOR FY 2017. (079B00023N, 111B00020N) | C | NHPP | BRO | 2017 | 9100000 | 9100000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-9068.03 | US 68 | 0.001 |  |  | SAFETY | BRIDGE REPLACEMENT(P) | US 68/KY 80 LAKE BARKLEY AND KENTUCKY LAKE GARVEE BOND DEBT SERVICE (BRO) FOR FY 2018. (079B00023N, 111B00020N) | C | NHPP | BRO | 2018 | 9100000 | 9100000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-9068.05 | US 68 |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | US 68/KY 80 LAKE BARKLEY AND KENTUCKY LAKE GARVEE BOND DEBT SERVICE (BRO) FOR FY 2019. (079B00023N, 111B00020N) | C | NHPP | BRO | 2019 | 9100000 | 9100000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-9068.61 | US 68 |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | US 68/KY 80 LAKE BARKLEY AND KENTUCKY LAKE GARVEE BOND DEBT SERVICE FOR FY 2020. (12CCR) | C | NHPP | BRO | 2020 | 9100000 | 9100000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-9068.62 | US 68 |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | US 68/KY 80 LAKE BARKLEY AND KENTUCKY LAKE GARVEE BOND DEBT SERVICE FOR FY 2016. | C | STP | STP | 2017 | 8900000 | 8900000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-9068.63 | US 68 |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | US 68/KY 80 LAKE BARKLEY AND KENTUCKY LAKE GARVEE BOND DEBT SERVICE FOR FY 2017. | C | STP | STP | 2017 | 9100000 | 9100000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-9068.64 | US 68 |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | US 68/KY 80 LAKE BARKLEY AND KENTUCKY LAKE GARVEE BOND DEBT SERVICE FOR FY 2018. | C | STP | STP | 2018 | 9100000 | 9100000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-9068.65 | US 68 |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | US 68/KY 80 LAKE BARKLEY AND KENTUCKY LAKE GARVEE BOND DEBT SERVICE FOR FY 2019. | C | STP | STP | 2019 | 9100000 | 9100000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-9068.66 | US 68 |  |  |  | RELIABILITY | BRIDGE REPLACEMENT(P) | US 68/KY 80 LAKE BARKLEY AND KENTUCKY LAKE GARVEE BOND DEBT SERVICE FOR FY 2020. | C | STP | STP | 2020 | 9100000 | 9100000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-9659.12 |  |  |  |  | RELIABILITY | RECONSTRUCTION(O) | GARVEE BOND DEBT SERVICE FOR LOUISVILLE BRIDGES PROJECT FOR FY 2016. (JZ1-FD53 "IM" COMPONENT) | C | NHPP | IM | 2017 | 5900000 | 5900000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-9659.13 |  |  |  |  | RELIABILITY | RECONSTRUCTION(O) | GARVEE BOND DEBT SERVICE FOR LOUISVILLE BRIDGES PROJECT FOR FY 2016. (JZ1-FD53 "NH" COMPONENT) | C | NHPP | NH | 2017 | 8800000 | 8800000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-9659.15 |  |  |  |  | RELIABILITY | RECONSTRUCTION(O) | GARVEE BOND DEBT SERVICE FOR LOUISVILLE BRIDGES PROJECT FOR FY 2017. (JZ1-FD53 "IM" COMPONENT) | C | NHPP | IM | 2017 | 13700000 | 13700000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-9659.16 |  |  |  |  | RELIABILITY | RECONSTRUCTION(O) | GARVEE BOND DEBT SERVICE FOR LOUISVILLE BRIDGES PROJECT FOR FY 2017. (JZ1-FD53 "NH" COMPONENT) | C | NHPP | NH | 2017 | 20600000 | 20600000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-9659.18 |  |  |  |  | RELIABILITY | RECONSTRUCTION(O) | GARVEE BOND DEBT SERVICE FOR LOUISVILLE BRIDGES PROJECT FOR FY 2018. (JZ1-FD53 "IM" COMPONENT) | C | NHPP | IM | 2018 | 13700000 | 13700000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-9659.19 |  |  |  |  | RELIABILITY | RECONSTRUCTION(O) | GARVEE BOND DEBT SERVICE FOR LOUISVILLE BRIDGES PROJECT FOR FY 2018. (JZ1-FD53 "NH" COMPONENT) | C | NHPP | NH | 2018 | 20600000 | 20600000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-9659.21 |  |  |  |  | RELIABILITY | RECONSTRUCTION(O) | GARVEE BOND DEBT SERVICE FOR LOUISVILLE BRIDGES PROJECT FOR FY 2019. (JZ1-FD53 "IM" COMPONENT) | C | NHPP | IM | 2019 | 13700000 | 13700000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-9659.22 |  |  |  |  | RELIABILITY | RECONSTRUCTION(O) | GARVEE BOND DEBT SERVICE FOR LOUISVILLE BRIDGES PROJECT FOR FY 2019. (JZ1-FD53 "NH" COMPONENT) | C | NHPP | NH | 2019 | 20600000 | 20600000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-9659.23 |  |  |  |  | RELIABILITY | RECONSTRUCTION(O) | GARVEE BOND DEBT SERVICE FOR LOUISVILLE BRIDGES PROJECT FOR FY 2020. (JZ1-FD53 "IM" COMPONENT) | C | NHPP | IM | 2020 | 25100000 | 25100000 | NO |  |  |  | 0
[6 empty] | ZVARIOUS | 99-9659.24 |  |  |  |  | RELIABILITY | RECONSTRUCTION(O) | GARVEE BOND DEBT SERVICE FOR LOUISVILLE BRIDGES PROJECT FOR FY 2020. (JZ1-FD53 "NH" COMPONENT) | C | NHPP | NH | 2020 | 37700000 | 37700000 | NO |  |  |  | 0

## STATE-FUNDED REG SIGNIFICANT
MODIFICATION OR AMENDMENT | STIP ADMINISTRATIVE MODIFICATION OR AMENDMENT NUMBER | APPROVAL DATE | COMMENTS | COUNTY | ID NUMBER | ROUTE NO. | LENGTH | BMP1 | EMP1 | PRIORITY | TYPEWORK | 2016 HWY PLAN DESCRIPTION | PHASE | TYPE OF FUND | FISCAL YEAR | TOTAL PHASE COST | FEDERAL PORTION | ILLUSTRATIVE PROJECT
|  |  |  | BOONE | 6-351.1 | US 25 | 0.636 | 4.859 | 5.085 | RELIABILITY | MAJOR WIDENING(O) | DRY RIDGE-FLORENCE ROAD; 5-LANE US-25 FROM RICHWOOD ROAD TO WINNING COLORS DRIVE WITH GRADE SEPARATION OF KY-338 AT US-25 & RR OVERPASS FOR KY-338. (2004BOPC)(2006BOPC)(12CCR)(NO BUILD)(14CCN) | D | SP | 2017 | 2010000 | 0 | YES
|  |  |  | BOONE | 6-351.1 | US 25 | 0.636 | 4.859 | 5.085 | RELIABILITY | MAJOR WIDENING(O) | DRY RIDGE-FLORENCE ROAD; 5-LANE US-25 FROM RICHWOOD ROAD TO WINNING COLORS DRIVE WITH GRADE SEPARATION OF KY-338 AT US-25 & RR OVERPASS FOR KY-338. (2004BOPC)(2006BOPC)(12CCR)(NO BUILD)(14CCN) | R | SP | 2017 | 3640000 | 0 | YES
|  |  |  | BOONE | 6-351.1 | US 25 | 0.636 | 4.859 | 5.085 | RELIABILITY | MAJOR WIDENING(O) | DRY RIDGE-FLORENCE ROAD; 5-LANE US-25 FROM RICHWOOD ROAD TO WINNING COLORS DRIVE WITH GRADE SEPARATION OF KY-338 AT US-25 & RR OVERPASS FOR KY-338. (2004BOPC)(2006BOPC)(12CCR)(NO BUILD)(14CCN) | U | SP | 2017 | 2510000 | 0 | YES
|  |  |  | BOONE | 6-351.1 | US 25 | 0.636 | 4.859 | 5.085 | RELIABILITY | MAJOR WIDENING(O) | DRY RIDGE-FLORENCE ROAD; 5-LANE US-25 FROM RICHWOOD ROAD TO WINNING COLORS DRIVE WITH GRADE SEPARATION OF KY-338 AT US-25 & RR OVERPASS FOR KY-338. (2004BOPC)(2006BOPC)(12CCR)(NO BUILD)(14CCN) | C | SP | 2019 | 4370000 | 0 | YES
|  |  |  | BOONE | 6-351.2 | US 25 | 2.346 | 5.085 | 7.431 | RELIABILITY | MAJOR WIDENING(O) | DRY RIDGE-FLORENCE ROAD; 5-LANE US-25 FROM WINNING COLORS DRIVE TO BEESOM DRIVE. (2006BOPC) (10CCR)(NO BUILD)(14CCN) | D | SP | 2017 | 1710000 | 0 | YES
|  |  |  | BOONE | 6-351.3 | US 25 | 0.379 | 7.431 | 7.81 | RELIABILITY | MAJOR WIDENING(O) | DRY RIDGE-FLORENCE ROAD; 5-LANE US-25 FROM BEESOM DRIVE TO ARISTOCRAT DRIVE WITH GRADE SEPARATION OF KY 536 AT US 25. (2006BOPC) (10CCR)(NO BUILD)(14CCN) | D | SP | 2017 | 1770000 | 0 | YES
|  |  |  | BOONE | 6-351.4 | US 25 | 1.37 | 7.81 | 9.18 | RELIABILITY | MAJOR WIDENING(O) | DRY RIDGE-FLORENCE ROAD; 5-LANE US-25 FROM ARISTOCRAT DRIVE TO RR SPUR CROSSING. (2004BOPC)(2006BOPC) (10CCR)(NO BUILD)(14CCN) | D | SP | 2017 | 950000 | 0 | YES
|  |  |  | BOONE | 6-8630 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | CONSTRUCT A NEW LOOP ROAD AROUND THE CAMPUS OF GATEWAY COLLEGE LOCATED OFF MOUNT ZION ROAD. (10CCN) | C | SB2 | 2017 | 500000 | 0 | YES
|  |  |  | BOONE | 6-8953 | I 275 |  |  |  | RELIABILITY | SAFETY(P) | INTERCHANGE JUSTIFICATION STUDY AT I-275 AND GRAVES ROAD. BOONE COUNTY FISCAL COURT WILL PROVIDE A 50% MATCH ($375,000). (16CCN) | D | SPP | 2017 | 375000 | 0 | YES
|  |  |  | BOYD | 9-8400 | US 60 | 2.02 | 0.2 | 4.02 | RELIABILITY | CONGESTION MITIGTN(O) | US 60 FROM I-64 AT INTERCHANGE 181 (MP 0.2) EXTENDING NORTHERLY TO THE KY 180 (MP 4.02) INTERSECTION AT CANNONSBURG, INCLUDING SUPERELEVATION CORRECTION ALONG KY 180 AT THE US 60 INTERSECTION. (08CCN) (10CCR)(12CCR) | C | SB2 | 2017 | 30290000 | 0 | YES
|  |  |  | BULLITT | 5-347.5 | KY 44 | 2.3 | 23.14 | 25.44 | RELIABILITY | RECONSTRUCTION(O) | MT. WASHINGTON-TAYLORSVILLE RD; RECONSTRUCT KY 44 FROM MT. WASHINGTON BYPASS EAST 2.0 MILES (04CCN)(16CCR) | R | SP | 2017 | 890000 | 0 | YES
|  |  |  | BULLITT | 5-347.5 | KY 44 | 2.3 | 23.14 | 25.44 | RELIABILITY | RECONSTRUCTION(O) | MT. WASHINGTON-TAYLORSVILLE RD; RECONSTRUCT KY 44 FROM MT. WASHINGTON BYPASS EAST 2.0 MILES (04CCN)(16CCR) | U | SP | 2017 | 1090000 | 0 | YES
|  |  |  | BULLITT | 5-347.5 | KY 44 | 2.3 | 23.14 | 25.44 | RELIABILITY | RECONSTRUCTION(O) | MT. WASHINGTON-TAYLORSVILLE RD; RECONSTRUCT KY 44 FROM MT. WASHINGTON BYPASS EAST 2.0 MILES (04CCN)(16CCR) | C | SP | 2020 | 4680000 | 0 | YES
|  |  |  | BULLITT | 5-8857 | KY 44 | 9.793 | 13.072 | 22.865 | RELIABILITY | MAJOR WIDENING(O) | WIDEN TO 5 LANES BETWEEN MOUNT WASHINGTON AND SHEPHERDSVILLE. (14CCN) | D | SP | 2017 | 3000000 | 0 | YES
|  |  |  | CAMPBELL | 6-8101.25 | KY 9 |  |  |  | RELIABILITY | NEW ROUTE(O) | RECONSTRUCT KY 9 ALONG A NEW ROUTE FROM NORTH OF 10TH STREET TO 5TH STREET. (2014BOP) | C | SPP | 2017 | 4000000 | 0 | YES
|  |  |  | CAMPBELL | 6-8104 | I 471 | 0.1 | 4.722 | 4.822 | RELIABILITY | NEW ROUTE(O) | CONSTRUCT NEW I-471 SOUTHBOUND OFF-RAMP AT KY-8 (SEE ALSO 6-183.00). (02CCN)(06CCN) | R | SP | 2017 | 2700000 | 0 | YES
|  |  |  | GREENUP | 9-132 | KY 2 | 4 | 13.2 | 17.2 | RELIABILITY | PE & ENVIRONMENTAL(O) | RECONSTRUCT KY-2 FROM MP 13.2 TO US-23 (MP 17.2)(08CCN)(14CCR)(16CCR) | R | SPP | 2018 | 6070000 | 0 | YES
|  |  |  | GREENUP | 9-132 | KY 2 | 4 | 13.2 | 17.2 | RELIABILITY | PE & ENVIRONMENTAL(O) | RECONSTRUCT KY-2 FROM MP 13.2 TO US-23 (MP 17.2)(08CCN)(14CCR)(16CCR) | U | SPP | 2019 | 3380000 | 0 | YES
|  |  |  | GREENUP | 9-132 | KY 2 | 4 | 13.2 | 17.2 | RELIABILITY | PE & ENVIRONMENTAL(O) | RECONSTRUCT KY-2 FROM MP 13.2 TO US-23 (MP 17.2)(08CCN)(14CCR)(16CCR) | C | SPP | 2020 | 36000000 | 0 | YES
|  |  |  | JEFFERSON | 5-122 | KY 1065 | 0.2 | 9.944 | 10.009 | SAFETY | SAFETY(P) | MAJOR REVISION OF THE INTERSECTION LOCATED AT THE OUTER LOOP, FEGENBUSH LANE, AND BEULAH CHURCH ROAD. TURN LANE TO BE COMPLETED BY TRANSPORTATION CABINET PER AGREEMENT. (04CCN)(08CCR)(10CCR)(12CCR) | C | SPP | 2017 | 5570000 | 0 | YES
|  |  |  | JEFFERSON | 5-344.01 | KY 1747 | 1.6 | 12.289 | 13.632 | RELIABILITY | RECONSTRUCTION(O) | WIDEN SOUTHBOUND HURSTBOURNE LANE TO 3 LANES FROM LINN STATION RD (CS-1004H) TO EDEN AVE (CS-1660H). (06CCR)(03KYD)(2006BOPP)(SEE 5-344.02 FOR KYD C PHASE)(14CCR) | R | SPP | 2017 | 2960000 | 0 | YES
|  |  |  | JEFFERSON | 5-344.01 | KY 1747 | 1.6 | 12.289 | 13.632 | RELIABILITY | RECONSTRUCTION(O) | WIDEN SOUTHBOUND HURSTBOURNE LANE TO 3 LANES FROM LINN STATION RD (CS-1004H) TO EDEN AVE (CS-1660H). (06CCR)(03KYD)(2006BOPP)(SEE 5-344.02 FOR KYD C PHASE)(14CCR) | U | SPP | 2017 | 3140000 | 0 | YES
|  |  |  | JEFFERSON | 5-344.01 | KY 1747 | 1.6 | 12.289 | 13.632 | RELIABILITY | RECONSTRUCTION(O) | WIDEN SOUTHBOUND HURSTBOURNE LANE TO 3 LANES FROM LINN STATION RD (CS-1004H) TO EDEN AVE (CS-1660H). (06CCR)(03KYD)(2006BOPP)(SEE 5-344.02 FOR KYD C PHASE)(14CCR) | C | SPP | 2018 | 6850000 | 0 | YES
|  |  |  | JEFFERSON | 5-8205.1 | KY 2053 | 1.501 | 0 | 1.501 | RELIABILITY | MINOR WIDENING(O) | IMPROVE AND WIDEN MT WASHINGTON ROAD FROM PRESTON HIGHWAY TO PENN RUN CREEK BRIDGE. (10CCN)(SAME AS 5-8611.00) | R | SP | 2017 | 3260000 | 0 | YES
|  |  |  | JEFFERSON | 5-8205.1 | KY 2053 | 1.501 | 0 | 1.501 | RELIABILITY | MINOR WIDENING(O) | IMPROVE AND WIDEN MT WASHINGTON ROAD FROM PRESTON HIGHWAY TO PENN RUN CREEK BRIDGE. (10CCN)(SAME AS 5-8611.00) | U | SP | 2017 | 6390000 | 0 | YES
|  |  |  | JEFFERSON | 5-8205.2 | KY 2053 | 1.187 | 1.501 | 2.688 | RELIABILITY | MINOR WIDENING(O) | IMPROVE AND WIDEN MT. WASHINGTON ROAD FROM PENN RUN CREEK BRIDGE TO CEDAR CREEK ROAD. (10CCN)(SAME AS 5-8612.00) | D | SP | 2017 | 1000000 | 0 | YES
|  |  |  | JEFFERSON | 5-8205.2 | KY 2053 | 1.187 | 1.501 | 2.688 | RELIABILITY | MINOR WIDENING(O) | IMPROVE AND WIDEN MT. WASHINGTON ROAD FROM PENN RUN CREEK BRIDGE TO CEDAR CREEK ROAD. (10CCN)(SAME AS 5-8612.00) | R | SP | 2018 | 1500000 | 0 | YES
|  |  |  | JEFFERSON | 5-8205.2 | KY 2053 | 1.187 | 1.501 | 2.688 | RELIABILITY | MINOR WIDENING(O) | IMPROVE AND WIDEN MT. WASHINGTON ROAD FROM PENN RUN CREEK BRIDGE TO CEDAR CREEK ROAD. (10CCN)(SAME AS 5-8612.00) | U | SP | 2018 | 1300000 | 0 | YES
|  |  |  | JEFFERSON | 5-8502 | KY 1020 | 2.054 | 0.615 | 2.669 | RELIABILITY | MAJOR WIDENING(O) | WIDEN KY-1020, NATIONAL TURNPIKE, FROM FAIRDALE ROAD TO SOUTH PARK ROAD. MP .615 TO MP 2.669. (08CCN) | D | SP | 2017 | 1350000 | 0 | YES
|  |  |  | JEFFERSON | 5-8503 | KY 2055 | 1.36 | 0 | 1.36 | RELIABILITY | MAJOR WIDENING(O) | WIDEN KY-2055 (MT. HOLLY ROAD) FROM NATIONAL TURNPIKE TO FAIRDALE ROAD. (08CCN)(16CCR) | D | SP | 2017 | 1050000 | 0 | YES
|  |  |  | JEFFERSON | 5-8503 | KY 2055 | 1.36 | 0 | 1.36 | RELIABILITY | MAJOR WIDENING(O) | WIDEN KY-2055 (MT. HOLLY ROAD) FROM NATIONAL TURNPIKE TO FAIRDALE ROAD. (08CCN)(16CCR) | R | SP | 2018 | 1050000 | 0 | YES
|  |  |  | JEFFERSON | 5-8503 | KY 2055 | 1.36 | 0 | 1.36 | RELIABILITY | MAJOR WIDENING(O) | WIDEN KY-2055 (MT. HOLLY ROAD) FROM NATIONAL TURNPIKE TO FAIRDALE ROAD. (08CCN)(16CCR) | U | SP | 2019 | 5220000 | 0 | YES
|  |  |  | JEFFERSON | 5-8503 | KY 2055 | 1.36 | 0 | 1.36 | RELIABILITY | MAJOR WIDENING(O) | WIDEN KY-2055 (MT. HOLLY ROAD) FROM NATIONAL TURNPIKE TO FAIRDALE ROAD. (08CCN)(16CCR) | C | SP | 2020 | 9750000 | 0 | YES
|  |  |  | JEFFERSON | 5-8611 | KY 2053 | 1.501 | 0 | 1.501 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE AND WIDEN MT. WASHINGTON ROAD FROM PRESTON HIGHWAY TO PENN RUN CREEK BRIDGE. (10CCN)(12CCR)(SAME AS 5-8205.10) | R | SP | 2020 | 3500000 | 0 | YES
|  |  |  | JEFFERSON | 5-8611 | KY 2053 | 1.501 | 0 | 1.501 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE AND WIDEN MT. WASHINGTON ROAD FROM PRESTON HIGHWAY TO PENN RUN CREEK BRIDGE. (10CCN)(12CCR)(SAME AS 5-8205.10) | U | SP | 2020 | 7200000 | 0 | YES
|  |  |  | JEFFERSON | 5-8612 | KY 2053 | 1.187 | 1.501 | 2.688 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE AND WIDEN MT. WASHINGTON ROAD FROM PENN RUN CREEK BRIDGE TO CEDAR CREEK ROAD. (10CCN)(12CCR)(SAME AS 5-8205.20) | D | SP | 2017 | 800000 | 0 | YES
|  |  |  | JEFFERSON | 5-8612 | KY 2053 | 1.187 | 1.501 | 2.688 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE AND WIDEN MT. WASHINGTON ROAD FROM PENN RUN CREEK BRIDGE TO CEDAR CREEK ROAD. (10CCN)(12CCR)(SAME AS 5-8205.20) | R | SP | 2017 | 2020000 | 0 | YES
|  |  |  | JEFFERSON | 5-8612 | KY 2053 | 1.187 | 1.501 | 2.688 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE AND WIDEN MT. WASHINGTON ROAD FROM PENN RUN CREEK BRIDGE TO CEDAR CREEK ROAD. (10CCN)(12CCR)(SAME AS 5-8205.20) | U | SP | 2017 | 1650000 | 0 | YES
|  |  |  | JEFFERSON | 5-8612 | KY 2053 | 1.187 | 1.501 | 2.688 | RELIABILITY | RECONSTRUCTION(O) | IMPROVE AND WIDEN MT. WASHINGTON ROAD FROM PENN RUN CREEK BRIDGE TO CEDAR CREEK ROAD. (10CCN)(12CCR)(SAME AS 5-8205.20) | C | SP | 2019 | 7910000 | 0 | YES
|  |  |  | JEFFERSON | 5-8801 | CR 1015G | 1.229 | 0 | 1.229 | RELIABILITY | MINOR WIDENING(O) | WIDEN RANGELAND ROAD TO 3 LANES FOR 1.23 MILES. (14CCN) | R | SPP | 2017 | 860000 | 0 | YES
|  |  |  | JEFFERSON | 5-8801 | CR 1015G | 1.229 | 0 | 1.229 | RELIABILITY | MINOR WIDENING(O) | WIDEN RANGELAND ROAD TO 3 LANES FOR 1.23 MILES. (14CCN) | U | SPP | 2017 | 990000 | 0 | YES
|  |  |  | JEFFERSON | 5-8801 | CR 1015G | 1.229 | 0 | 1.229 | RELIABILITY | MINOR WIDENING(O) | WIDEN RANGELAND ROAD TO 3 LANES FOR 1.23 MILES. (14CCN) | C | SPP | 2017 | 3080000 | 0 | YES
|  |  |  | JEFFERSON | 5-8904 |  |  |  |  | NEW ROUTES | TRANSP ENHANCEMENT(P) | HILLTOP PATHWAY FROM TYLER PARK TO A STREET CROSSWALK AT EDGELAND AVENUE. (16CCN) | P | SP | 2018 | 77000 | 0 | YES
|  |  |  | JEFFERSON | 5-8907 | KY 1450 |  | 0 | 1.88 | RELIABILITY | MAJOR WIDENING(O) | 4-LANE BLUE LICK RD FROM GENE SNYDER TO BULLITT COUNTY LINE. (16CCN) | D | SPP | 2017 | 2500000 | 0 | YES
|  |  |  | JEFFERSON | 5-8907 | KY 1450 |  | 0 | 1.88 | RELIABILITY | MAJOR WIDENING(O) | 4-LANE BLUE LICK RD FROM GENE SNYDER TO BULLITT COUNTY LINE. (16CCN) | R | SP | 2018 | 12000000 | 0 | YES
|  |  |  | JEFFERSON | 5-8907 | KY 1450 |  | 0 | 1.88 | RELIABILITY | MAJOR WIDENING(O) | 4-LANE BLUE LICK RD FROM GENE SNYDER TO BULLITT COUNTY LINE. (16CCN) | U | SP | 2019 | 10000000 | 0 | YES
|  |  |  | JEFFERSON | 5-8907 | KY 1450 |  | 0 | 1.88 | RELIABILITY | MAJOR WIDENING(O) | 4-LANE BLUE LICK RD FROM GENE SNYDER TO BULLITT COUNTY LINE. (16CCN) | C | SP | 2020 | 37500000 | 0 | YES
|  |  |  | KENTON | 6-8307.1 | KY 1501 | 1.032 | 0 | 1.032 | RELIABILITY | RECONSTRUCTION(O) | RECONSTRUCT HANDS PIKE (KY 1501) FROM KY 17 TO CRYSTAL LAKE DRIVE.(12CCR)(14CCR)(16CCR) | C | SPP | 2017 | 5800000 | 0 | YES
|  |  |  | KENTON | 6-8914 | KY 1501 |  |  |  | RELIABILITY | NEW ROUTE(O) | EXTEND HANDS PIKE (KY 1501) TO KY 177. (16CCN) | D | SP | 2018 | 500000 | 0 | YES
|  |  |  | KENTON | 6-8916 |  |  |  |  | RELIABILITY | NEW ROUTE(O) | EXTEND HOUSTON ROAD TO CINEMA PROPERTY. (16CCN) | D | SPP | 2018 | 250000 | 0 | YES
|  |  |  | OLDHAM | 5-304.1 | KY 22 | 2.1 | 3.25 | 5.32 | RELIABILITY | MAJOR WIDENING(O) | RECONSTRUCT KY-22 FROM KY-329 TO ABBOTT LANE. (2004BOPC)(08CCR)(10CCR)(12CCR) | R | SP | 2017 | 2560000 | 0 | YES
|  |  |  | OLDHAM | 5-304.1 | KY 22 | 2.1 | 3.25 | 5.32 | RELIABILITY | MAJOR WIDENING(O) | RECONSTRUCT KY-22 FROM KY-329 TO ABBOTT LANE. (2004BOPC)(08CCR)(10CCR)(12CCR) | U | SP | 2017 | 2540000 | 0 | YES
|  |  |  | OLDHAM | 5-304.1 | KY 22 | 2.1 | 3.25 | 5.32 | RELIABILITY | MAJOR WIDENING(O) | RECONSTRUCT KY-22 FROM KY-329 TO ABBOTT LANE. (2004BOPC)(08CCR)(10CCR)(12CCR) | C | SP | 2019 | 12340000 | 0 | YES
|  |  |  | OLDHAM | 5-304.2 | KY 22 | 2.2 | 5.32 | 7.5 | RELIABILITY | MAJOR WIDENING(O) | RECONSTRUCT KY-22 TO 5-LANES FROM ABBOTT LANE TO PROPOSED KY-393 INTERSECTION AND CONTINUING WITH 3-LANES TO EXISTING KY-393. (2004BOPC) | D | SP | 2017 | 910000 | 0 | YES
|  |  |  | OLDHAM | 5-304.2 | KY 22 | 2.2 | 5.32 | 7.5 | RELIABILITY | MAJOR WIDENING(O) | RECONSTRUCT KY-22 TO 5-LANES FROM ABBOTT LANE TO PROPOSED KY-393 INTERSECTION AND CONTINUING WITH 3-LANES TO EXISTING KY-393. (2004BOPC) | R | SP | 2017 | 3840000 | 0 | YES
|  |  |  | OLDHAM | 5-304.2 | KY 22 | 2.2 | 5.32 | 7.5 | RELIABILITY | MAJOR WIDENING(O) | RECONSTRUCT KY-22 TO 5-LANES FROM ABBOTT LANE TO PROPOSED KY-393 INTERSECTION AND CONTINUING WITH 3-LANES TO EXISTING KY-393. (2004BOPC) | U | SP | 2017 | 2540000 | 0 | YES
|  |  |  | OLDHAM | 5-304.2 | KY 22 | 2.2 | 5.32 | 7.5 | RELIABILITY | MAJOR WIDENING(O) | RECONSTRUCT KY-22 TO 5-LANES FROM ABBOTT LANE TO PROPOSED KY-393 INTERSECTION AND CONTINUING WITH 3-LANES TO EXISTING KY-393. (2004BOPC) | C | SP | 2019 | 10950000 | 0 | YES
|  |  |  | OLDHAM | 5-367 |  | 5 |  |  | RELIABILITY | NEW ROUTE(O) | CONSTRUCT NEW ROUTE FROM OLD HENRY INTERCHANGE AT I-265 TO CRESTWOOD BYPASS. (98CCR)(2004BOPP)(10CCN)(14CCR) | R | SP | 2017 | 500000 | 0 | YES
|  |  |  | OLDHAM | 5-367 |  | 5 |  |  | RELIABILITY | NEW ROUTE(O) | CONSTRUCT NEW ROUTE FROM OLD HENRY INTERCHANGE AT I-265 TO CRESTWOOD BYPASS. (98CCR)(2004BOPP)(10CCN)(14CCR) | U | SP | 2017 | 500000 | 0 | YES
|  |  |  | OLDHAM | 5-367 |  | 5 |  |  | RELIABILITY | NEW ROUTE(O) | CONSTRUCT NEW ROUTE FROM OLD HENRY INTERCHANGE AT I-265 TO CRESTWOOD BYPASS. (98CCR)(2004BOPP)(10CCN)(14CCR) | C | SP | 2017 | 15000000 | 0 | YES
|  |  |  | OLDHAM | 5-367.2 |  | 2.2 |  |  | RELIABILITY | NEW ROUTE(O) | EXTENSION OF OLD HENRY ROAD EAST TO ASH AVENUE (KY362). (12CCR) | C | SB2 | 2017 | 15000000 | 0 | YES