**SPECIAL NOTE FOR CONTRACT COMPLETION DATE AND**

**PENALTIES ON BRIDGE REPAIR CONTRACTS**

**1. COMPLETION DATE.** The Contractor has the option of selecting the starting date for this Contract. Once selected, notify the Department in writing of the date selected at least two weeks prior to beginning work. All work is to be completed by the date listed below. An allotted number of Calendar days are assigned to the/each structure in this contract as shown below.

 STRUCTURE NO. OF CALENDAR DAYS COMPLETION DATE

 XXXBXXXXN 00 XXXXX XX, 20XX

Contrary to Section 108.07.03, the Engineer will begin charging calendar days for a structure on the day the Contractor starts work or sets up traffic control on that particular structure. A **penalty of $500.00 per day** will be assessed when the allotted number of calendar days is exceeded for each structure.

All construction must be completed in accordance with the weather limitations specified in Section 606 and/or Section 601 as applicable. No extension of Contract time will be granted due to inclement weather or temperature limitations that occur due to starting work on the Contract or a structure late in the construction season.