## Slide 1
Expedited Project Development
Making the Most out of Right of Way Showings

## Slide 2: A Tale of Two Projects
11-185.00 US 25E Laurel County 11-188.00 US 25E Knox County
ADT – 26,148 ADT – 23,380
Access Management, Access Management, Signal Relocation &
Signal Relocation, Pavement Rehab Elimination, Pavement Rehab

## Slide 3: 41 Parcels 21 Appraisals, 20 MAR 16 Commercial, 4 Residential & 1 Farm 3 Relocations – All Business

## Slide 4: ROW Work Structure
Project Report
  Onsite Field Review with ROW Staff, Review Appraiser and Design Project Manager after final plans were received
Sales Book
  All Appraisal Staff compiled sales information together along with review appraiser
Minor Acquisition Review
  Data used from Sales Book coupled with individual parcel inspection (i.e. fences, asphalt, etc.)

## Slide 5: ROW Work Structure
Property Owner Contacts
  Notification of upcoming meeting only
Right of Way Plan Showing (Property Owners Only)
  Scheduled Offer to Purchase Meetings Early
  Scheduled Remaining Property Owners in Afternoon
Appraisals Completed
  Continued working closely with the reviewer
  Scheduled relocation parcels first
Results???

## Slide 6: Results
11 Offers to Property Owners and 2 were signed
ROW Clear within 1 year
Letting Date was never moved
Only 6 Condemnations
Lots and Lots of Experience

## Slide 7: Lessons Learned
What we felt worked well:
Joint ROW and Design Field Review – Immediate evaluation of impacts, Plan Omissions, Parcel Elimination
Offer to Purchases at Public Meeting – Meeting went well, but we thought results could be improved
What we thought could be improved:
More and Earlier Property Owner Contact
Plan review earlier in the process
Eliminating Duplicate Work – Same sales data for appraisals had to be entered multiple times due to being used by multiple appraisers

## Slide 8: Project Challenges

## Slide 9: Censorship!!!

## Slide 10: They Moved…But to Where??

## Slide 11: 53 Parcels 23 Appraisals, 30 MARS 23 Commercial 0 Relocations

## Slide 12: Kept Same ROW Work Structure With Exceptions
Draft ROW Plans used for Project Report
  Sped up meeting time and eliminated a required revision.
  Ultimately led to better plans as a result of collaboration and better communication
Better Plans Faster to Sign or Sue Faster to Letting
Joint Design/ROW Field Review
  Examples

## Slide 13: Eliminated Parcels

## Slide 14: Eliminated Parcels

## Slide 15: Misidentified Plan Information

## Slide 16: Post???

## Slide 17: Plans Corrected to Show Public ROW

## Slide 18: Plans Corrected to Show Public ROW

## Slide 19: Plans Corrected to Show Public ROW

## Slide 20: KY Supreme Court Decision Affecting ROW
ELLINGTON v. BECRAFT - Decided December 14, 2017 - Refines case law to better define how roads are established.
  County Roads are “public roads” which have been formally accepted by the fiscal court as a part of the county road system (requires a formal action by the county)
  Public Roads are informal dedications (no action by any governmental agency) that can be completed in two ways.
    Estoppel - based upon promises (either express or implied) and reliance thereon by the public.
    Prescription – Ruled to be the same as adverse possession. Must meet all requirements (i.e. a prescriptive easement can be acquired by actual, hostile, open and notorious, exclusive, and continuous possession of the property for the statutory period of fifteen years)

## Slide 21: Result of Public Road Recognition
Fee Simple Acquisition was reduced by 73,752 SF
Greater than $300k savings to KYTC
Property owner reaction is mixed

## Slide 22: Sales Data Pilot Program Same sales data had to be entered multiple times.

## Slide 23: Eliminating Duplicate Work

## Slide 24: Implemented Mandatory Property Owner Involvement in MAR Process
Created a consistent approach
  MARS follow similar process as Appraisals from a property owner perspective
Allowed for Property Owner Concerns to be addressed
  Plan Omissions, Entrance Changes (Not Enhancements), Etc.
Opportunity to see plans and discuss
  Allowed for reflection on work being done and questions to be asked prior to the meeting while ROW Plans were being finalized

## Slide 25: Offer to Purchase ROW Showing
Scheduled specific meeting times with MAR parcels
All other property owners were given a conventional meeting time
Participants:
  ROW Staff – Including agents, supervisor, review appraiser and CO staff (with administrative settlement authority)
  Design Staff – Project Manager, Design Consultant and Utility Representative
Personal relationships established during MAR process paid off

## Slide 26: Results
Made 14 Offers to Purchase (All were MARs)
Signed 9 on meeting day and one additional a couple days later
Kick-off for Appraisals
  Made appropriate contacts for affected businesses and discussed their concerns

## Slide 27: Lessons Learned
Project Applicability
    Must have high percentage of MARs
    MAR property owners shouldn’t also have appraisals
    MAR parcels must have local signatory authority (availability to be present)
Cross-Discipline communication and teamwork is crucial
Early Property Owner involvement in the MAR process shows significant results