## Slide 1
Planning & Scoping Cost Estimates
(and also some Highway Design updates)
Steve De Witte & Patrick Perry
September 6, 2023

## Slide 2
​THE KYTC MISSION
To provide a safe, efficient, environmentally sound and fiscally responsible transportation system that delivers economic opportunity and enhances the quality of life in Kentucky

## Slide 3: What is a cost estimate?

## Slide 4: TYPES OF COST ESTIMATES

## Slide 5
RESEARCH
ABSTRACT
DESIGN

## Slide 6
RESEARCH
ABSTRACT
DESIGN

## Slide 7
RESEARCH
ABSTRACT
DESIGN

## Slide 8
RESEARCH
ABSTRACT
DESIGN

## Slide 9
RESEARCH
ABSTRACT
DESIGN

## Slide 11: WHY ARE COST ESTIMATES IMPORTANT?

## Slide 12
​THE KYTC MISSION
To provide a safe, efficient, environmentally sound and fiscally responsible transportation system that delivers economic opportunity and enhances the quality of life in Kentucky

## Slide 13
RESEARCH
ABSTRACT
DESIGN
“The journey is the safest when the roadmap is the clearest.”

## Slide 14
RESEARCH
ABSTRACT
DESIGN
Notes: What happens now, low-ball estimates, plan gets overloaded, ask for more money multiple times

## Slide 15: Planning and scoping estimates

## Slide 16
RESEARCH
ABSTRACT
DESIGN

## Slide 19: PROJECT IDENTIFICATION ESTIMATES

## Slide 20
RESEARCH
ABSTRACT
DESIGN
Project Maturity | Estimating Methodology | Estimate Range | Level of Effort
0 to 5% | Parametric | -50% to +200% | Low
Examples:
SWCP/SWIPP
“YUM Center”
Initial CHAF Estimate
Sources of Risk:
Lack of Project Definition
Contingency
Gigantic

## Slide 21
RESEARCH
ABSTRACT
DESIGN

## Slide 22: CONCEPTUAL PROJECT ESTIMATES

## Slide 23
RESEARCH
ABSTRACT
DESIGN
Project Maturity | Estimating Methodology | Estimate Range | Level of Effort
3% to 15% | Historical Bid-Based with some Parametric | -40% to +100% | Medium
Bid-Based
Excavation/Embankment
Asphalt Base/Surface
DGA
Concrete
Curb & Cutter
Sidewalk
Parametric
Structures
Mob/Demob
MOT
Contingency
Depends on Complexity

## Slide 24
RESEARCH
ABSTRACT
DESIGN

## Slide 25
RESEARCH
ABSTRACT
DESIGN
Project Maturity | Estimating Methodology | Estimate Range | Level of Effort
3% to 15% | Historical Bid-Based with some Parametric | -40% to +100% | Medium
Examples:
Most Planning Studies
Sources of Risk:
Known Unknowns
Environmental
ROW/Utilities
Geotech
Structures
Drainage
Unknown Unknowns
Inflation of bid items
Availability of Materials
Labor Cost

## Slide 26
RESEARCH
ABSTRACT
Ok to assume absolutely nothing is going to go right!
“We can reuse pavement in this section.”
“We should have good rock.”
“ROW will be donated.”
Don’t take THE “ROSY” PATH

## Slide 27
Bid Items
Pavement
Excavation
Parametric
Other Phases
Drainage/MOT/Mobilization
Contingencies
Remember all those risks? Account for them
Curb/Gutter/Sidewalk
Miscellaneous

## Slide 28: PRELIMINARY LINE AND GRADE ESTIMATE

## Slide 29
RESEARCH
ABSTRACT
Turn This:
Into This:

## Slide 30
RESEARCH
ABSTRACT
DESIGN
Project Maturity | Estimating Methodology | Estimate Range | Level of Effort
10% to 30% | Historical Bid-Based or Cost-Based | -30% to +50% | High
Examples:
Fully scoped projects (“Design” projects)
Sources of Risk:
ROW/Utilities
Lighting

## Slide 31: Improvements to the process

## Slide 32
COST ESCALATION

## Slide 33
RESEARCH
ABSTRACT
DESIGN
Need to account for TIME contingency
If we started a Planning study today, we’re already into the next biennium for Design.
+10%

## Slide 34
RESEARCH
ABSTRACT
DESIGN
Need to account for TIME contingency
+20%
Design and Environmental will take 2 years.
TOTAL: +30%

## Slide 35
RESEARCH
ABSTRACT
DESIGN
Need to account for TIME contingency
+20%
Utilities and Right-of-Way will take 2 years.
TOTAL: +50%

## Slide 36
Bid Items
Pavement
Excavation
Parametric
Other Phases
Drainage/MOT/Mobilization
Contingencies
See all those risks? Account for them
Curb/Gutter/Sidewalk
Miscellaneous
Escalation
Time Risk

## Slide 37
DOCUMENT ALL OF THIS

## Slide 38
STRENGTHENING THE handoff

## Slide 39
STRENGTHENING THE handoff
Planning
Design
Scoping
0%
5%
30%
15%
PL&G
2+ Years?

## Slide 40
RESEARCH
ABSTRACT
DESIGN
WHO: For Planning Study-related projects, Planning (District and Central Office) to stay involved until “Scoping” is complete at PL&G
WHY: Understand Planning’s thought process to meet Purpose & Need
Various points where “handoff” occurs
Better estimates = better for everybody

## Slide 41
Location “smell tests”

## Slide 42
RESEARCH
ABSTRACT
DESIGN
PLANNING ESTIMATES

## Slide 43
Revisit OFTEN

## Slide 44
RESEARCH
ABSTRACT
DESIGN
REVISIT ESTIMATE

## Slide 45
THE FUTURE
Coming Soon!
Still working out bugs with construction procurement

## Slide 46
RESEARCH
ABSTRACT
DESIGN

## Slide 47
Special Thanks: Chris Van Dyke, Bryan Gibson, Jeff Jasper, and Bob Lewis

## Slide 48
KEY TAKEAWAYS
Planning & Scoping Estimates are Difficult but Critical to KYTC success
Planning to stay involved on certain projects until PL&G
Location will “smell test” Planning estimates
Keep Goal of Estimate range in mind (e.g. -40% to +100%)
Better Estimates = Better for Everyone

## Slide 49: Highway design updates

## Slide 50
Highway Design Manual
Updates coming in late 2023
Mostly minor changes
Two major changes
Shoulder Superelevation
Intersection Control Evaluation (ICE)
Next update will occur when the new edition of the Green Book is released

## Slide 51
Shoulder Superelevation (Current)
Note 5 ) FOR A PAVED SHOULDER WIDTH LESS THAN OR EQUAL TO 4 FEET, NO BREAK IN SLOPE IS REQUIRED. FOR A PAVED SHOULDER WIDTH GREATER THAN 4 FEET, THE BREAK IN SLOPE ON THE HIGH SIDE IS TO OCCUR AT THE MIDPOINT, OR AS APPROPRIATE, WITH A MAXIMUM ROLL-OVER OF 12 PERCENT.

## Slide 52
Shoulder Superelevation

## Slide 53
Intersection Control Evaluation
ICE
Currently In development
Goal is to implement in this round of HDM updates
Assist the project team in determining most appropriate Intersection type.
Will hear more about this on Day 3
Notes: SPICE and CapX tools to analyze

## Slide 54
Consultant Performance Evaluations
Work in Progress
More robust
Besides the PM and Location Engineer other Divisions/Branches will provide input on the evaluation.
Eventually this will be part of the Professional Services Consultant Portal
The goal is to make this system useful and meaningful.

## Slide 55
I have a plan
You know I have a plan for that road.
Jeez! As long as it’s just a plan
M. Pelfrey
T. Layson

## Slide 56
I have a plan
If it was easy, it’d already be in Design.
De Witte
Perry

## Slide 57
QUESTIONS/DISCUSSION
Patrick Perry, P.E., P.L.S.
TE Branch Manager – Roadway Design
Patrick.Perry@ky.gov
502-782-4925
Steve De Witte, P.E.
TE Branch Manager – Strategic Planning
Stephen.DeWitte@ky.gov
502-782-5056