## Slide 1: Consultant Property Management and Demolition – Lessons Learned
Amy Ishmael, KYTC
Mark Askin, Strand Associates, Inc.®

## Slide 2: BSB Update
72 Parcels total, 53 active
41 Parcels purchased, 12 submitted for condemnation
14 parcels require demolition, 8 active

## Slide 3: Property management report
Memo
Project summary of improvements
Improvements to be removed photographs

## Slide 4: Property management report

## Slide 5: Property management report

## Slide 6: ACM testing
Property is acquired or right of entry is obtained
Request Asbestos Containing Material testing (ACM)

## Slide 7: ACM Testing

## Slide 8: ACM testing

## Slide 9: ACM Testing Complete
If test results are positive, have asbestos abated from property!

## Slide 10: Utilities
Agent, PM, and Supervisor verify utilities have been disconnected by the owners
  This doesn’t clear the site!
Contact the utility to have services removed or plugged
LESSON LEARNED No. 1 – Demolition was delayed on project because utilities were disconnected but not removed

## Slide 11: Cost Estimate for Demolition
Send Memo to KYTC for approval

## Slide 12: Demolition solicitation
Demolition Checklist
Solicitation for removal of improvements
Create a “Before” photo log
Aerial location maps
Project plans
Cost estimate

## Slide 13: Demolition solicitation

## Slide 14: Demolition solicitation

## Slide 15: Demolition solicitation

## Slide 16: Demolition solicitation

## Slide 17: Demolition solicitation

## Slide 18: Demolition solicitation
Address questions by bidders with Addendum to solicitation

## Slide 19: Project is awarded
Consultants cannot approve any bids or compensation – Lesson Learned No. 2
Work order issued to contractor
Must have letter accompanying work order with project dates, etc.
Lesson Learned No. 3 failed to include letter.

## Slide 20: Pre-improvement removal meeting
Meeting with contractor

## Slide 21: Pre-improvement removal meeting
What are the contractor’s specifications:

## Slide 22: Pre-improvement removal meeting

## Slide 23: Pre-improvement removal meeting

## Slide 24: Pre-improvement removal meeting

## Slide 25: Division of Air Quality submittal
Complete submittal on:
  Asbestos Notifications - Kentucky Energy and Environment Cabinet
What is needed?
  Contractor’s name and address
  Owner’s name
  Project location
  Contract dates
  Waste transporter
  Disposal site

## Slide 26: Demolition work begins
Demolition inspection log and photographs

## Slide 27: Demolition complete
Work acceptance
Inspection logs
Contractor’s invoice on his letterhead
Updated project summary of improvements
Vendor evaluation

## Slide 28: Demolition complete

## Slide 29: Demolition complete

## Slide 30: Demolition complete

## Slide 31: Other Issues
City of Covington required Zoning Permit

## Slide 32: Questions?