## 1.Title
Kentucky Transportation Cabinet
RBOC RFP Price Proposal - Tolling Component 1
Price Proposal By:
Appendix B - Tolling Component One
Price Proposal Worksheet Tabs
| Number | Name | No. Printed Pages / Tab
| Tab1 | Title | 1
| Tab2 | Instructions | 2
| Tab3 | Tabulation-Roadside | 3
| Tab4 | Price-Roadside | 4
| Tab5 | Tabulation-BOS | 5
| Tab6 | Price-BOS | 6
| Tab7 | Summary | 7
| Tab8 | Progress Payments | 9

## 2.Instructions
KYTC TOLL COLLECTION SYSTEM PRICE PROPOSAL INSTRUCTIONS
This page provides notes and instructions for completing the Price Proposal forms.
Shaded blocks are remarks, estimated quantities or equations and should not be changed by the proposer, except for labor categories. Existing labor categories shall be left in, however the proposer may add other categories as desired.
Project Sections: Note that proposers shall use this spreadsheet form for proposing on individual sections, and simply leave other pages blank for sections for which no proposal is offered. On any given page for either the Roadside, BOS, or operations, however, all items must be addressed. Even if the proposer intends to not ask for compensation according to any item, a "0" must be added to ensure the block was not simply missed.
Quantities: If the entered quantities must be changed for you to provide a complete, compliant proposal, please make that change but also highlight it for review.
Prices: All cells requiring a price entry are numbered by subsection (I, II, or III) and then a grouped sequence number such as "I.104" (for Toll Facility Host Application Software). Enter prices in the highlighted blocks shown thus:
General:
The Proposing Contractors are provided the Pricing Excel spreadsheet as a courtesy, however all Proposing Contractors using this spreadsheet accept all risk and responsibility for the workbook and results. Each Proposing Contractor is implicitly making a proposal compliant with the full Scope of Work and all the Functional Requirements of this RFP. In the event that a pay item or some type of compensation is not identified in the Price Proposal which is ultimately accepted by KYTC, the successful Proposing Contractor may not ask for additional compensation.
Tab1. Title
This tab contains the mandatory block for the Contractor's name, and presents the outline.
Tab2. Instructions
This tab provides user assistance. Note the Contractor remains responsible for preparation of a complete offer and proper price proposal.
Tab3a. Tabulation-Roadside
This tab shows the tabulation of quantities between the various toll zones, plazas and the host system locations.
Tab3b. Tabulation-ITS
This tab shows the tabulation of ITS quantities to be maintained by the Roadside contractor, and also presents the ITS system design concept information for prospective Roadside contractors.
Tab4. Price-Roadside
The first two sheets are for purchase quotes
The third sheet allows for alternate lease-purchase pricing of the Roadside.
Note that prices are required for both purchase and lease-purchase options.
The last sheet provides labor rates for supplemental work during the term of the contract.
Note the rows for ITS Maintenance (11/26/08) pricing and the remarks.
Roadside PURCHASE:
I.1 through I.27 represent the measurement and payment for the system hardware to be provided under this contract. Some items are measured by "each", "lane", "toll zone" or "plaza," others are "lump sum (LS)." All will be subject to milestone partial payments. The tabulations columns identify the locations in the field for deployment. All hardware required to completely meet the specifications and requirements of this contract shall be addressed in these pay items. If additional pay items are desired by the Contractor, extra blank spaces are provided for use. In referring to the units of access control readers, this estimate includes buildings, gantries, lane cabinets, etc.
I.101 through I.107 represent the measurement and payment for the system software development and licenses, to include the commercial software as well as application software. All will be subject to milestone partial payments. All software required to completely meet the specifications and requirements of this contract shall be addressed in these pay items. If additional pay items are desired by the Contractor, extra blank spaces are provided for use.
Roadside PURCHASE:
I.201 through I.205 represent the measurement and payment for all work required to install the Roadside system, in the field and in the Operations Center. The Traffic Control line item is estimated for 60 days of lane closure. If the Contractor is able to use X lane-days of traffic control to complete installation and Site Acceptance Testing, where X<60 lane-days, KYTC will pay the Contractor for X + (60-X)/2 days, to share in the benefit of reducing installation time. KYTC will not pay above 60 lane-days unless circumstances beyond the Contractors' reasonable control cause delays.
I.301 through I.308 represent measurement and payment for project development, documentation, the testing program and training.
I.401 and I.402 are for warranty and maintenance services. They are calculated and paid on a per-lane basis after the lane passes Site Acceptance and is in actual revenue collection operations. Partial months will be pro-rated. Note that warranty and maintenance of ALL of the Roadside system is incidental to the measurement and payment for the lanes, so the cost to provide warranty and maintenance of the Toll Zones, Plazas and Toll Facility Host should be included.
ITS.401 through ITS.404 are the monthly costs to maintain the hardware and software provided by the ITS vendor under a separate contract. Detailed maintenance description is provided in Appendix J and the tabulation of ITS quantities is presented on Tab 3b.
Roadside LEASE-PURCHASE OPTION:
I.L101 is the alternate monthly lease-to-own price, for the 60 months beginning January 2011 through December 2015, for use of the Roadside system.
I.L201 through I.L402 and ITS.L401 through ITS.L404represent measurement and payment for work and services required to provide the system under the leasing scenario.
Roadside LABOR RATES:
I.601 to I.611 are unit labor rates measured hourly (including benefits, etc.). These represent the rates to be paid for work over and above the normal scope of maintenance services, for example for extra work orders to modify an accepted design or integrate new technology not in the original scope of work.
Tab5. Tabulation-BOS
This tab shows the tabulation of quantities between the CSC storefront, the CSC Ops Center and the KYTC Administration Building.
Tab6. Price-BOS
The first sheet is for purchase quotes
The second sheet allows for alternate lease pricing of the BOS.
Note that prices are required for both purchase and lease-purchase options.
The last sheet provides labor rates for supplemental work during the term of the contract, and also unit prices at various activity levels for mailing costs. Mail costs are not "bids" but the source of the prices is needed for evaluation of the methodology and base lines for future actual costs.
BOS PURCHASE:
II.1 through II.14 represent measurement and payment for the system hardware to be provided under this contract. Items are listed "lump sum" except for the number of workstations, which may vary from the estimated number. All will be subject to milestone partial payments. All hardware required to completely meet the specifications and requirements of this contract shall be addressed in these pay items. If additional pay items are desired by the Contractor, extra blank spaces are provided for use.
II.101 through II.106 represent the measurement and payment for the system software development and licenses, to include the commercial software as well as application software. All will be subject to milestone partial payments. All software required to completely meet the specifications and requirements of this contract shall be addressed in these pay items.
II.201 represents the measurement and payment to install the BOS system in all required locations.
II.301 through II.308 represent measurement and payment for project development, documentation, the testing program and training.
II.401 and II.402 are for warranty and maintenance services. They are calculated and paid on a monthly basis beginning on January 1, 2011 through December 31, 2015. Note that warranty and maintenance of ALL of the BOS system is incidental to the monthly payments.
BOS LEASE-PURCHASE OPTION:
II.L101 is the alternate monthly lease-to-own price, for the 60 months beginning January 2011 through December 2015, for use of the BOS system.
II.L201 through II.L308 represent measurement and payment for work and services required to provide the system under the leasing scenario.
BOS LABOR RATES:
II.601 to II.608 are unit labor rates measured hourly (including benefits, etc.). These represent the rates to be paid for work over and above the normal scope of maintenance services, for example for extra work orders to modify an accepted design or integrate new technology not in the original scope of work.
Tab7. Ops
Cost Pass-Through Items: Items that will be a pass through with no mark-ups or overhead shall be:
CSC lease and build out costs
Postage for customer mailings
Any leased communication lines
Phone lines and all related 800 number costs
* These costs should not be included in the submitted pricing.
III.1 represents the fixed monthly fee to cover overhead, profit and all other non-direct-labor costs not designated as pass-through. Monthly payments to begin upon CSC opening to the public.
III.2 to III.3 represent project development items to be paid on the basis of milestone completions. The Contractor's overhead, profit, and non-direct-labor costs from NTP to CSC public opening shall be covered by this monthly fee.
III.101 to III.116 represent staffing required in various positions. Total prices (to include benefits, compensation for overtime and benefit hours for leave, sick leave, internal company training) on an hourly basis are to be provided. This allows the most flexibility in staffing levels. No other costs, profit or other benefits, etc., shall be added to these for compensation. Note that rates for 2010 (the ramp-up period) as well as 2011 and 2015 are to be provided.
Quantities: Note that quantities are the current estimate based on projected traffic. The quantities shown will be used for the price evaluations. Refer to Appendix J for details on ITS Maintenance Requirements.
Tab8. Summary
This sheet requires no input by the Contractor but rolls up costs from various portions of the Price Proposal.
Tab9. Progress Payments
This sheet requires no input by the Contractor. It is the spreadsheet for progress payments which appears in the RFP Section IV.
KYTC - May 2013

## 3. Tabulation-Roadside
Kentucky Transportation Cabinet
Roadside Toll Collection System |  |  |  |  | Tabulation of Quantities in 2013
(rev 4/3/2013) |  |  |  |  | CSC / Ops | Downtown Bridge |  |  |  | Kennedy Bridge |  |  |  | East Bridge
[5 empty] | Center | Mainline & Ramps |  |  |  | Mainline & Ramps |  |  |  | Mainlines
No. |  | Pay Item Description | Total Count | Unit of Measure | Toll Fac Host | Plaza Bldg | DB-1 |  | R-1 | Plaza Bldg | KB-1 |  | R-2 | Plaza Bldg | ECC-1 | ECC-2
[5 empty] | DB-1 |  | Single Direction | Reversible | Single Direction |  | Single Direction | Reversible | Single Direction |  | Single Direction | Single Direction
I. | 1 | Lane Controller Set | 8 | Toll Zone |  |  | 1 | 1 | 1 |  | 1 | 1 | 1 |  | 1 | 1
I. | 2 | VTS Rear Cameras | 31 | Lane |  |  | 4 | 4 | 4 |  | 4 | 4 | 3 |  | 4 | 4
I. | 3 | VTS Front Cameras | 31 | Lane |  |  | 4 | 4 | 4 |  | 4 | 4 | 3 |  | 4 | 4
I. | 4 | VTS Toll Zone Components | 8 | Toll Zone |  |  | 1 | 1 | 1 |  | 1 | 1 | 1 |  | 1 | 1
I. | 5 | Plaza VTS System | 3 | Plaza |  | 1 |  |  |  | 1 |  |  |  | 1
I. | 6 | ETC Lane Equipment | 31 | Lane |  |  | 4 | 4 | 4 |  | 4 | 4 | 3 |  | 4 | 4
I. | 7 | AVC Profilers | 31 | Lane |  |  | 4 | 4 | 4 |  | 4 | 4 | 3 |  | 4 | 4
I. | 8 | AVC Presence Loops | 31 | Lane |  |  | 4 | 4 | 4 |  | 4 | 4 | 3 |  | 4 | 4
I. | 9 | AVC Smart Loops | 31 | Lane |  |  | 4 | 4 | 4 |  | 4 | 4 | 3 |  | 4 | 4
I. | 10 | CCTV Overview Cameras | 8 | Toll Zone |  |  | 1 | 1 | 1 |  | 1 | 1 | 1 |  | 1 | 1
I. | 11 | CCTV Surveillance Cameras | 8 | Toll Zone |  |  | 1 | 1 | 1 |  | 1 | 1 | 1 |  | 1 | 1
I. | 12 | Plaza CCTV Control and Storage | 3 | Plaza |  | 1 |  |  |  | 1 |  |  |  | 1
I. | 13 | CCTV Host Control | 1 | LS | 1
I. | 14 | Access Control Readers | 19 | Each |  | 1 | 2 | 2 | 2 | 1 | 2 | 2 | 2 | 1 | 2 | 2
I. | 15 | Access Control System | 3 | Plaza |  | 1 |  |  |  | 1 |  |  |  | 1
I. | 16 | Access Control Host Control | 1 | LS | 1
I. | 17 | Roadside Spare Parts Inventory | 1 | LS | 1
I. | 18 | Plaza Server System | 3 | Plaza |  | 1 |  |  |  | 1 |  |  |  | 1
I. | 19 | Plaza Rack-Mount Maintenance Workstation | 3 | Plaza |  | 1 |  |  |  | 1 |  |  |  | 1
I. | 20 | Plaza and Toll Zone UPS | 3 | Plaza |  | 1 |  |  |  | 1 |  |  |  | 1
I. | 21 | Plaza LAN & Network Control | 3 | Plaza |  | 1 |  |  |  | 1 |  |  |  | 1
I. | 22 | Toll Facility WAN & Network Control | 1 | LS
I. | 23 | Toll Facility Host Server | 1 | Each | 1
I. | 24 | Hot-Swap Backup Toll Facility Host Server | 1 | Each |  | 1
I. | 25 | Ops Center Workstations | 2 | Each | 2
I. | 26 | Admin Building Workstations | 0 | Each
I. | 27 | Monitor - 42 Inch LCD Monitor | 0 | Each
I. | 28 | 16-channel CCTV Control and Monitor | 0 | Each
I. | 101 | Lane Controller Application SW | 8 | Toll Zone |  |  | 1 | 1 | 1 |  | 1 | 1 | 1 |  | 1 | 1
I. | 102 | Plaza VTS SW | 3 | Plaza |  | 1 |  |  |  | 1 |  |  |  | 1
I. | 103 | Plaza Server Application SW | 3 | Plaza |  | 1 |  |  |  | 1 |  |  |  | 1
I. | 104 | Toll Facility Host Application SW | 1 | LS | 1
I. | 105 | Lane Controller COTS SW | 8 | Toll Zone |  |  | 1 | 1 | 1 |  | 1 | 1 | 1 |  | 1 | 1
I. | 106 | Plaza Server COTS SW | 3 | Plaza |  | 1 |  |  |  | 1 |  |  |  | 1
I. | 107 | Toll Facility Host COTS SW | 1 | LS | 1
I. | 201 | Lane Installation | 31 | Lane |  |  | 4 | 4 | 4 |  | 4 | 4 | 3 |  | 4 | 4
I. | 202 | Lane Installation Traffic Control | 62 | Lane Days |  |  | 8 | 8 | 8 |  | 8 | 8 | 6 |  | 8 | 8
I. | 203 | Toll Zone Installation | 8 | Toll Zone |  |  | 1 | 1 | 1 |  | 1 | 1 | 1 |  | 1 | 1
I. | 204 | Plaza Installation | 3 | Plaza |  | 1 |  |  |  | 1 |  |  |  | 1
I. | 205 | Toll Facility Host Installation | 1 | LS | 1
I. | 301 | Roadside Contractor Program Administration | 0 | Months
I. | 302 | Roadside Design and Documentation | 1 | LS | 1
I. | 303 | Roadside As-Built Records | 1 | LS | 1
I. | 304 | Factory Acceptance Tests | 1 | LS | 1
I. | 305 | Site Acceptance Testing | 3 | Plaza |  | 1 |  |  |  | 1 |  |  |  | 1
I. | 306 | Final Acceptance Testing | 3 | Plaza |  | 1 |  |  |  | 1 |  |  |  | 1
I. | 307 | Final Acceptance Reporting and Approval | 1 | LS | 1
I. | 308 | Roadside Training | 1 | LS | 1
I. | 401 | Roadside Warranty Period Svcs | 372 | Lane-Month |  |  | 48 | 48 | 48 |  | 48 | 48 | 36 |  | 48 | 48
I. | 402 | Roadside Maintenance Svcs | 1488 | Lane-Month |  |  | 192 | 192 | 192 |  | 192 | 192 | 144 |  | 192 | 192
KYTC - May 2013

## 4.Price-Roadside
Kentucky Transportation Cabinet
Roadside Toll Collection System |  |  |  |  | Unit and Total Purchase Prices
| by: | 0
No. |  | Pay Item Description | Total Count | Unit of Measure | Contractor Unit Price | Total Price | Remarks
I. | 1 | Lane Controller Set | 8 | Toll Zone |  | 0
I. | 2 | VTS Rear Cameras | 31 | Lane |  | 0
I. | 3 | VTS Front Cameras | 31 | Lane |  | 0
I. | 4 | VTS Toll Zone Components | 8 | Toll Zone |  | 0
I. | 5 | Plaza VTS System | 3 | Plaza |  | 0
|  | ETC Lane Equipment | 31 | Lane |  | 0 | KYTC to select technology separately from RBOC Procurement
I. | 6 | AVC Profilers | 31 | Lane |  | 0
I. | 7 | AVC Presence Loops | 31 | Lane |  | 0
I. | 8 | AVC Smart Loops | 31 | Lane |  | 0
I. | 9 | CCTV Overview Cameras | 8 | Toll Zone |  | 0
I. | 10 | CCTV Surveillance Cameras | 8 | Toll Zone |  | 0
I. | 11 | Plaza CCTV Control and Storage | 3 | Plaza |  | 0
I. | 12 | CCTV Host Control | 1 | LS |  | 0
I. | 13 | Access Control Readers | 19 | Each |  | 0
I. | 14 | Access Control System | 3 | Plaza |  | 0
I. | 15 | Access Control Host Control (with 200 cards) | 1 | LS |  | 0
I. | 16 | Roadside Spare Parts Inventory | 1 | LS |  | 0
I. | 17 | Plaza Server System | 3 | Plaza |  | 0
I. | 18 | Plaza Rack-Mount Maintenance Workstation | 3 | Plaza |  | 0
I. | 19 | Plaza and Toll Zone UPS | 3 | Plaza |  | 0
I. | 20 | Plaza LAN & Network Control | 3 | Plaza |  | 0
I. | 21 | Toll Facility WAN & Network Control | 1 | LS |  | 0
I. | 22 | Toll Facility Host Server | 1 | LS |  | 0
I. | 23 | Hot-Swap Backup Toll Facility Host Server | 1 | LS |  | 0
I. | 24 | Ops Center Workstations | 2 | Each |  | 0
I. | 25 | Admin Building Workstations | 0 | Each |  | 0
I. | 26 | Monitor - 42 Inch LCD Monitor | 0 | Each |  | 0
I. | 27 | 16-channel CCTV Control and Monitor | 0 | Each |  | 0
I. | [5 empty] | 0 | Rows 35-41 are available for additional items.
I. | [5 empty] | 0
I. | [5 empty] | 0
I. | [5 empty] | 0
I. | [5 empty] | 0
I. | [5 empty] | 0
I. | [5 empty] | 0
[6 empty] | 0 | Roadside HARDWARE PURCHASE
Roadside Toll Collection System |  |  |  |  | Unit and Total Purchase Prices
| by: | 0
No. |  | Pay Item Description | Total Count | Unit of Measure | Unit Price | Total Price | Remarks
I. | 101 | Lane Controller Application SW | 8 | Toll Zone |  | 0
I. | 102 | Plaza VTS SW | 3 | Plaza |  | 0
I. | 103 | Plaza Server Application SW | 3 | Plaza |  | 0
I. | 104 | Toll Facility Host Application SW | 1 | LS |  | 0
I. | 105 | Lane Controller COTS SW | 8 | Toll Zone |  | 0
I. | 106 | Plaza Server COTS SW | 3 | Plaza |  | 0
I. | 107 | Toll Facility Host COTS SW | 1 | LS |  | 0
[6 empty] | 0 | Roadside SOFTWARE PURCHASE
I. | 201 | Lane Installation | 31 | Lane |  | 0
I. | 202 | Lane Installation Traffic Control | 62 | Lane Days |  | 0
I. | 203 | Toll Zone Installation | 8 | Toll Zone |  | 0
I. | 204 | Plaza Installation | 3 | Plaza |  | 0
I. | 205 | Toll Facility Host Installation | 1 | LS |  | 0
[6 empty] | 0 | Roadside INSTALLATION SUBTOTAL
I. | 301 | Roadside Contractor Program Administration | 0 | Months |  | 0
I. | 302 | Roadside Design and Documentation | 1 | LS |  | 0
I. | 303 | Roadside As-Built Records | 1 | LS |  | 0
I. | 304 | Factory Acceptance Tests | 1 | LS |  | 0 | F.A.Tests to be conducted off-site.
I. | 305 | Site Acceptance Testing | 3 | Plaza |  | 0
I. | 306 | Final Acceptance Testing | 3 | Plaza |  | 0
I. | 307 | Final Acceptance Reporting and Approval | 1 | LS |  | 0
I. | 308 | Roadside Training | 1 | LS |  | 0
[6 empty] | 0 | Roadside PROJECT DEVELOPMENT
I. | 401 | Roadside Warranty Period Svcs | 372 | Lane-Month |  | 0 | Note that Roadside Warranty and Maintenance services for toll zones, plazas and host are incidental and included.
I. | 402 | Roadside Maintenance Svcs | 1488 | Lane-Month |  | 0
[6 empty] | 0 | Roadside WARRANTY AND MAINTENANCE
Roadside Toll Collection System |  |  |  |  | Table of Labor Rates for Supplemental Work
| by: | 0
|  | Roadside EXTENDED SERVICES LABOR |  |  | Activity Period
[5 empty] | 2014 | 2015 | 2016 | 2017 | 2018
I. | 601 | Project Manager |  | Total Hourly Rate (with benefits)
I. | 602 | Maintenance Supervisor
I. | 603 | Maintenance Technician
I. | 604 | Installation Technician
I. | 605 | Installation Supervisor
I. | 606 | Tester
I. | 607 | Systems Engineer
I. | 608 | Systems Analyst
I. | 609 | Tech Writer
I. | 610 | Programmer
I. | 611 | Other (Provide Detail Listing)
Roadside Toll Collection System |  |  |  |  | Pass Through Bond Costs
| by: | Toll Facility Host Installation
|  | Roadside EXTENDED SERVICES LABOR |  |  | Activity Period
[5 empty] | 2014 | 2015 | 2016 | 2017 | 2018
I. | 701 | Warranty Bond
I. | 702 | Maintenance Performance and Payment Bonds
KYTC - May 2013

## 5.Tabulation-BOS
Kentucky Transportation Cabinet |  |  |  |  | Tabulation of Quantities
Back Office System |  |  |  |  | CSC / Ops | KY/IN
[5 empty] | Center | Storefronts
No. |  | Pay Item Description | Total Count | Unit of Measure | BOS System | location tbd
[5 empty] | 0-0 | 0-1
II. | 1 | Host Hardware | 1 | LS | 1
II. | 2 | Backup Host Server | 1 | LS | 1
II. | 3 | VTS BOS Server | 1 | LS | 1
II. | 4 | BOS Reports Server | 1 | LS | 1
II. | 5 | BOS Archive Server | 1 | LS | 1
II. | 6 | CSC Web Server | 1 | LS | 1
II. | 7 | Office Workstations | 18 | Each | 10 | 8
II. | 9 | CSC / VTC Workstations | 67 | Each | 55 | 12
II. | 10 | IVR System | 1 | LS | 1
II. | 11 | Operations Center & Storefront Phone System w/ phones | 1 | LS | 1
II. | 12 | Telecommunications and LAN / WAN | 1 | LS | 1
II. | 13 | Operations Center / Walk-Ins Electrical / UPS | 1 | LS | 1
II. | 14 | BOS Spare Parts Inventory | 1 | LS | 1
II. | 15 | BOS/Walk-Ins Printers/Scanners | 4 | Each | 2 | 2
II. | 101 | Host Application SW | 1 | LS | 1
II. | 102 | Database Design and SW | 1 | LS | 1
II. | 103 | COTS SW | 1 | LS | 1
II. | 104 | CSC Workstation Application SW | 1 | LS | 1
II. | 105 | VTS OCR and System Application SW | 1 | LS | 1
II. | 106 | Web Site SW | 1 | LS | 1
II. | 201 | BOS Installation | 1 | LS | 1
II. | 301 | BOS Contractor Program Administration | 24 | Months | 24
II. | 302 | BOS Design and Documentation | 1 | LS | 1
II. | 303 | BOS As-Built Records | 1 | LS | 1
II. | 304 | BOS Factory Acceptance Tests | 1 | LS | 1
II. | 305 | BOS Site Acceptance Testing | 1 | LS | 1
II. | 306 | BOS Final Acceptance Testing | 1 | LS | 1
II. | 307 | Final Acceptance Reporting and Approval | 1 | LS | 1
II. | 308 | BOS Training | 1 | LS | 1
II. | 401 | BOS Warranty Period Svcs | 12 | Month | 12
II. | 402 | BOS Maintenance Svcs | 48 | Month | 48
KYTC - May 2013

## 6.Price-BOS
Kentucky Transportation Cabinet
Back Office System |  |  |  |  | Unit and Total Purchase Prices
| by: | 0
No. |  | Pay Item Description | Total Count | Unit of Measure | Unit Price | Total Price | Remarks
BOS includes Customer Service Center and the Walk-in Centers. In addition BOS includes any required connections to Joint Board, KYTC and INDOT.
II. | 1 | Host Hardware | 1 | LS |  | 0
II. | 2 | Backup Host Server | 1 | LS |  | 0
II. | 3 | VTS BOS Server | 1 | LS |  | 0
II. | 4 | BOS Reports Server | 1 | LS |  | 0
II. | 5 | BOS Archive Server | 1 | LS |  | 0
II. | 6 | CSC Web Server | 1 | LS |  | 0
II. | 7 | Office Workstations | 18 | Each |  | 0
II. | 9 | CSC / VTC Workstations | 67 | Each |  | 0
II. | 10 | IVR System | 1 | LS |  | 0 | Covers 3 locations
II. | 11 | Operations Center & Storefront Phone System w/ phones | 1 | LS |  | 0 | CSC, Admin, Conference Rooms and two (2) Walk-In Centers
II. | 12 | Telecommunications and LAN / WAN | 1 | LS |  | 0
II. | 13 | Operations Center / Walk-Ins Electrical / UPS | 1 | LS |  | 0
II. | 14 | BOS Spare Parts Inventory | 1 | LS |  | 0
II. | 15 | BOS/Walk-Ins Printers/Scanners | 4 | Each |  | 0
II. | [5 empty] | 0 | Rows 21-27 are available for additional items.
II. | [5 empty] | 0
II. | [5 empty] | 0
II. | [5 empty] | 0
II. | [5 empty] | 0
II. | [5 empty] | 0
II. | [5 empty] | 0
[6 empty] | 0 | BOS HARDWARE
II. | 101 | Host Application SW | 1 | LS |  | 0
II. | 102 | Database Design and SW | 1 | LS |  | 0
II. | 103 | COTS SW | 1 | LS |  | 0
II. | 104 | CSC Workstation Application SW | 1 | LS |  | 0
II. | 105 | VTS OCR and System Application SW | 1 | LS |  | 0
II. | 106 | Web Site SW | 1 | LS |  | 0
[6 empty] | 0 | BOS SOFTWARE
II. | 201 | BOS Installation | 1 | LS |  | 0
II. | 301 | BOS Contractor Program Administration | 24 | Months |  | 0
II. | 302 | BOS Design and Documentation | 1 | LS |  | 0
II. | 303 | BOS As-Built Records | 1 | LS |  | 0
II. | 304 | BOS Factory Acceptance Tests | 1 | LS |  | 0 | To be conducted at test locations mutually agreed to between the Roadside Contractor and KYTC.
II. | 305 | BOS Site Acceptance Testing | 1 | LS |  | 0
II. | 306 | BOS Final Acceptance Testing | 1 | LS |  | 0
II. | 307 | Final Acceptance Reporting and Approval | 1 | LS |  | 0
II. | 308 | BOS Training | 1 | LS |  | 0
[6 empty] | 0 | BOS INSTALLATION / PROJECT DEVELOPMENT
II. | 401 | BOS Warranty Period Svcs | 12 | Month |  | 0 | Note that warranty and maintenance services for the Operations Center, CSC and Walk-in Centers are incidental and included.
II. | 402 | BOS Maintenance Svcs | 48 | Month |  | 0
[6 empty] | 0 | BOS WARRANTY AND MAINTENANCE SERVICES
Back Office System |  |  |  |  | Table of Labor Rates for Supplemental Work (Purchase or Lease-Purchase Option)
| by: | 0
|  | BOS EXTENDED SERVICES LABOR |  |  | Activity Period
[5 empty] | 2014 | 2015 | 2016 | 2017 | 2018
II. | 601 | Project Manager |  | Total Hourly Rate (With Benefits)
II. | 602 | Sr Software Developer
II. | 603 | Database Administrator
II. | 604 | Database Analyst
II. | 605 | Software Developer
II. | 606 | Programmer
II. | 607 | Technician
II. | 608 | Other (Provide Detail Listing)
II. | 609 | Misc. Bond Pass-through
II. | 610 | Performance Bond Pass-through
Back Office System |  |  |  |  | Pass Through Bond Costs
| by: | 0
|  | Roadside EXTENDED SERVICES LABOR |  |  | Activity Period
[5 empty] | 2014 | 2015 | 2016 | 2017 | 2018
II. | 701 | Warranty Bond
II. | 702 | Maintenance Performance and Payment Bonds
KYTC - May 2013

## 7.Infrastructure
Kentucky Transportation Cabinet
Roadside Toll Infrastructure |  |  |  |  | Unit and Total Purchase Prices
| by: | 0
No. |  | Pay Item Description | Total Count | Unit of Measure | Contractor Unit Price | Total Price | Remarks
I. | 1 | Mainline Toll Zone Buildings | 4 | F&I Each |  | 0
I. | 2 | Mainline Generators | 4 | F&I Each |  | 0
I. | 3 | Mainline Propane Tanks | 4 | F&I LS Each |  | 0
I. | 4 | Lightning Protection System Building | 4 | Each |  | 0
I. | 5 | Ramp Generators | 2 | F&I Each |  | 0
I. | 6 | Ramp Propane Tanks | 2 | F&I LS Each |  | 0
I. | [5 empty] | 0
I. | [5 empty] | 0
I. | [5 empty] | 0
I. | [5 empty] | 0
I. | [5 empty] | 0
I. | [5 empty] | 0
I. | [5 empty] | 0
[6 empty] | 0 | Roadside Toll Infrastructure
Roadside Toll Infrastructure |  |  |  |  | Unit and Total Purchase Prices
| by: | 0
No. |  | Pay Item Description | Total Count | Unit of Measure | Unit Price | Total Price | Remarks
I. | 101 | Site to Site Communications |  | LF |  | 0 | Conduit fiber Furnish and Install (F&I)
I. | 102 | Intrasite Communications |  | LF |  | 0
I. | 103 | Site to CSC Communications |  | LF |  | 0
I. | 104 | Communications Auxiliary Equipment |  | LS |  | 0
I. | 105 |  |  |  |  | 0
I. | 106 |  |  |  |  | 0
I. | 107 |  |  |  |  | 0
[6 empty] | 0 | Roadside Communications Infrastructure
KYTC - May 2013

## 8.Summary
Kentucky Transportation Cabinet
TOLL COLLECTION SYSTEM ESTIMATED COSTS SUMMARY
0
Roadside HARDWARE | 0
Roadside SOFTWARE | 0
Roadside INSTALLATION AND PROJECT DEVELOPMENT | 0 |  | Total Roadside Cap Cost: | 0 | 0 | / lane
BOS HARDWARE | 0
BOS SOFTWARE | 0
BOS INSTALLATION AND PROJECT DEVELOPMENT | 0 |  | Total BOS Cap Cost: | 0 | 0 | / lane
ESTIMATED TOLL SYSTEM CAPITAL COSTS |  |  |  | 0 | 0 | / lane
Year of Operation
| Prior to 2014 | 2015 | 2016 | 2017 | 2018 | 2019
Lanes in revenue collection service under warranty: | 0 | 26 | 38 | 0 | 0 | 0
Lanes in revenue collection service under maintenance: | 0 | 0 | 26 | 64 | 64 | 64
Roadside WARRANTY | 0 | 0 | 0 | 0 | 0 | 0
Roadside MAINTENANCE | 0 | 0 | 0 | 0 | 0 | 0
BOS WARRANTY | 0 | 0 | 0 | 0 | 0 | 0
BOS MAINTENANCE | 0 | 0 | 0 | 0 | 0 | 0
TOTAL TOLLS OPERATIONS COSTS | 0 | 0 | 0 | 0 | 0 | 0
KYTC - May 2013

## 9.Progress Payments
Kentucky Transportation Cabinet
0
Progress Payments - System Purchases
| Project Phase | Phase I | Phase I | Phase II | Phase II | Phase III
| Project Progress Milestone | NTP | DDD Acceptance | FAT Acceptance | Site Acceptance | Final Acceptance
Roadside PURCHASE | Roadside HARDWARE | 5% | 20% | 25% | 40% | 10%
| Roadside SOFTWARE | 5% | 20% | 25% | 40% | 10%
| Roadside INSTALLATION | 5% |  |  | 85% | 10%
| Roadside Contractor Program Administration | Begin monthly payments to length of contract
| Roadside Design and Documentation | 5% | 85% |  |  | 10%
| Roadside As-Built Records |  |  |  |  | 100%
| Factory Acceptance Tests |  |  | 90% |  | 10%
| Site Acceptance Testing |  |  |  | 90% | 10%
| Final Acceptance Testing |  |  |  |  | 100%
| Final Acceptance Reporting and Approval |  |  |  |  | 100%
| Roadside Training |  |  |  | 50% | 50%
| Roadside WARRANTY AND MAINTENANCE | Begin monthly payments to length of contract
BOS PURCHASE | BOS HARDWARE | 5% | 20% | 25% | 40% | 10%
| BOS SOFTWARE | 5% | 20% | 25% | 40% | 10%
| BOS INSTALLATION | 5% |  |  | 85% | 10%
| BOS Contractor Program Administration | Begin monthly payments to length of contract
| BOS Design and Documentation | 5% | 85% |  |  | 10%
| BOS As-Built Records |  |  |  |  | 100%
| BOS Factory Acceptance Tests |  |  | 90% |  | 10%
| BOS Site Acceptance Testing |  |  |  | 90% | 10%
| BOS Final Acceptance Testing |  |  |  |  | 100%
| Final Acceptance Reporting and Approval |  |  |  |  | 100%
| BOS Training |  |  |  | 50% | 50%
| BOS WARRANTY AND MAINTENANCE | Begin monthly payments to length of contract